## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction"
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Edge Lifter 3T
tickbox | ID Plate
tickbox | Reinforcement
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
tickbox | Concrete N40 Pan2 Mix
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
section | Installation
checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
tickbox | Set out
tickbox | Core Holes
tickbox | Install dowels
checkpoint | Installation of precast panels including backpropping. Correct location, connections, finish confirmed against shop drawings.
checkpoint | Grouting and sealing
checkpoint | Remove backpropping when instructed by consulting Engineers.
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Installers Checklist
section | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Nexus 3T Edge Lifter
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Panel Thickness confirmed
dropdown | Panel Thickness: | 125mm
checkpoint | Check Concrete cover around reo 45mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD Steel Trowel Finish
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Pan2 Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
holdpoint | Request Signoff