## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-012
[11 empty] | Revision : 1 | 2024-07-19
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Hyland Hwy Ch 32.5km Landslip Remediation |  | Ground Anchor Installation & Testing |  | Name: | Justin Barnes | Name: | Cameron Beattie |  | Name: | Cameron Beattie
Contract No: |  | 7AG50026 |  | Specifications: VicRoads Standard Specification Section 705
|  |  |  | Structure / Component: Retaining Wall |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : | 2024-07-19 | Date : | 2024-07-19 |  | Date : | 2024-07-19
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Design and Submissions
1.1 | Hot Dip Galvanised certification of DYWIDAG threadbar |  | Prior to commencement | Galvanising achieved as per drawings | Drawings | Current revision of Drawings | Certificate | Verify | Site Engineer
1.2 | Approved grout product |  | Prior to commencement | Proposed grout product approved prior to commencement of works | Drawings | Approval | This ITP Signed | AP | Geotechnical Engineer Site Engineer
1.3 | Acceptable individual bar length |  | Prior to commencement | Bar Lengths conform with minimal length of 3000mm as per drawings | Drawings | Verify | This ITP Signed |  | Site Engineer
1.4 | Acceptable internal duct diameter |  | Prior to commencement | Internal duct diameter to allow 5mm grout annulus around bar circumference | Drawings | Verify | This ITP Signed |  | Site Engineer
1.5 | Supplier of materials to supply product certification |  | Prior to commencement | Certification of threadbar and al other ground anchor material to be certified | Drawings | Verify | Manufacturers Certificate | HP* | Site Engineer
2 | Ground Anchors - Installation
2.1 | Records of ground anchor drilling and grouting taken for each hole |  | Each Anchor | Logs to be taken during drilling | Borelogs | Verify | Checklist / Form | IP | Site Engineer
2.2 | Appropriate placement of spacers along anchor |  | Each Anchor | Spacers placed at a maximum of 1000mm | Drawings | Verify | This ITP Signed | WP | Site Engineer
2.3 | Inspection of Ground Anchor Drilling |  | First 4 Anchors | First 4 x Ground Anchors to be witnessed by, and borelogs taken by Geotechnical Engineer, | Borelogs | Verify | Checklist / Form | IP | Geotechnical Engineer
2.4 | External grout tubes to reach distal end of anchor hole and not withdrawn until completion of grouting |  | Each Anchor | Grout inserted at the end of the anchor hole to ensure desired grouting location | Drawings | Verify | This ITP Signed | WP | Site Engineer
2.5 | Anchor location |  | Each Anchor | All anchors drilled at the location and to the minimum diameter specified | Drawings Survey setout | Survey | Survey Report | HP | Site Engineer Superintendent
2.6 | Acceptable hole |  | Each Anchor | Acceptance that the hole is clean with minimal smearing | Drawings | Verify | This ITP Signed | HP | Site Engineer Superintendent
2.7 | Anchor assembly supports |  | Each Anchor | Ensure adequate supports are in place to minimise likelihood of damage / bending to anchor assembly | Drawings | Verify | This ITP Signed | WP | Site Engineer
2.8 | Corrosion Inhibiting Compound |  | Each Anchor | CIC has filled the entire trumpet and protective cap | Drawings | Verify | This ITP Signed | WP | Site Engineer
2.9 | Protective Caps |  | Each Anchor | Protective Caps are watertight, allow for inspection and refilling of CIC | Drawings | Verify | This ITP Signed | WP | Site Engineer
2.1 | Fluidity Testing |  | Each Anchor | Fluidity of emerging grout to be within 20% of inserted grout to ensure all low quality ground is displaced | Drawings | Verify | Test | TP | Site Engineer
2.11 | Threadbar - post stress |  | Each Anchor | Following stressing, all bars to be cut to allow for a minimum of 150mm to stick out from the bearing plate | Drawings | Verify | This ITP Signed | WP | Site Engineer
3 | Ground Anchors - Testing
3.1 | 7 Day Grout Strength |  | 3 x 75mm cubes per anchor or batch (lesser) tested | 32MPa achieved | TfNSW | Test | Strength result | TP | Site Engineer
3.2 | 28 Day Grout Strength |  | 3 x 75mm cubes per anchor or batch (lesser) tested | 40MPa achieved | TfNSW | Test | Strength result | TP | Site Engineer
3.3 | Bleed Test |  | One Test / Once per 4 hours | Final bleeding < 0.5% | ASTM C940 | Test | Bleed test result | TP | Site Engineer
3.4 | Fluidity Test - <20s after mixing |  | Once per batch | Grout to pass through cone test in <20s | ASTM C939 | Test | Fluidity Test Result | TP | Site Engineer
3.5 | Fluidity Test - 45m after mixing |  | Once per batch | Grount to pass through cone test within 3s of first test | ASTM C939 | Test | Fluidity Test Result | TP | Site Engineer
3.6 | Proof Testing |  | 3 x Anchors Prior to Production Anchors | Proof Testing undertaken in accordance with drawings to determine characteristics of ultimate resistance | Drawings | Verify | This ITP Signed | HP | Geotechnical Engineer Site Engineer Superintendent
3.7 | Suitability Testing |  | 3 x Anchors Prior to Production Anchors | Suitability Testing undertaken in accordance with drawings to confirm anchor design, drilling method and installation will be adequate in existing ground conditions | Drawings | Verify | This ITP Signed | HP | Geotechnical Engineer Site Engineer Superintendent
3.8 | Acceptance Testing |  | Each Anchor | Acceptance testing undertaken in accordance with drawings to confirm adequate bond strength and conform with acceptance criteria | Drawings | Verify | This ITP Signed | HP | Geotechnical Engineer Site Engineer Superintendent
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent