## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-012 - Ground Anchors | itp |  |  |  |  | ITP-012 - Ground Anchors
section | 1.0 - Design and Submissions
checkpoint | 1.1 - Hot Dip Galvanised certification of DYWIDAG threadbar
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Galvanising achieved as per drawings
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Current revision of Drawings
label | RECORD OF CONFORMITY: Certificate
label | Verify
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.2 - Approved grout product
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Proposed grout product approved prior to commencement of works
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Approval
label | RECORD OF CONFORMITY: This ITP Signed
label | AP
label | RESPONSIBILITY: Geotechnical Engineer, Site Engineer
date | Date Completed:
checkpoint | 1.3 - Acceptable individual bar length
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Bar Lengths conform with minimal length of 3000mm as per drawings
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Acceptable internal duct diameter
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Internal duct diameter to allow 5mm grout annulus around bar circumference
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Supplier of materials to supply product certification
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Certification of threadbar and al other ground anchor material to be certified
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Manufacturers Certificate
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2.0 - Ground Anchors - Installation
checkpoint | 2.1 - Records of ground anchor drilling and grouting taken for each hole
label | FREQUENCY: Each Anchor
label | ACCEPTANCE CRITERIA: Logs to be taken during drilling
label | REFERENCE DOCUMENTS: Borelogs
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Checklist / Form
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Appropriate placement of spacers along anchor
label | FREQUENCY: Each Anchor
label | ACCEPTANCE CRITERIA: Spacers placed at a maximum of 1000mm
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Inspection of Ground Anchor Drilling
label | FREQUENCY: First 4 Anchors
label | ACCEPTANCE CRITERIA: First 4 x Ground Anchors to be witnessed by, and borelogs taken by Geotechnical Engineer,
label | REFERENCE DOCUMENTS: Borelogs
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Checklist / Form
label | IP
label | RESPONSIBILITY: Geotechnical Engineer
date | Date Completed:
checkpoint | 2.4 - External grout tubes to reach distal end of anchor hole and not withdrawn until completion of grouting
label | FREQUENCY: Each Anchor
label | ACCEPTANCE CRITERIA: Grout inserted at the end of the anchor hole to ensure desired grouting location
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.5 - Anchor location
label | FREQUENCY: Each Anchor
label | ACCEPTANCE CRITERIA: All anchors drilled at the location and to the minimum diameter specified
label | REFERENCE DOCUMENTS: Drawings, Survey setout
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: Survey Report
label | HP
label | RESPONSIBILITY: Site Engineer, Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Acceptable hole
label | FREQUENCY: Each Anchor
label | ACCEPTANCE CRITERIA: Acceptance that the hole is clean with minimal smearing
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer, Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Anchor assembly supports
label | FREQUENCY: Each Anchor
label | ACCEPTANCE CRITERIA: Ensure adequate supports are in place to minimise likelihood of damage / bending to anchor assembly
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.8 - Corrosion Inhibiting Compound
label | FREQUENCY: Each Anchor
label | ACCEPTANCE CRITERIA: CIC has filled the entire trumpet and protective cap
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.9 - Protective Caps
label | FREQUENCY: Each Anchor
label | ACCEPTANCE CRITERIA: Protective Caps are watertight, allow for inspection and refilling of CIC
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.10 - Fluidity Testing
label | FREQUENCY: Each Anchor
label | ACCEPTANCE CRITERIA: Fluidity of emerging grout to be within 20% of inserted grout to ensure all low quality ground is displaced
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.11 - Threadbar - post stress
label | FREQUENCY: Each Anchor
label | ACCEPTANCE CRITERIA: Following stressing, all bars to be cut to allow for a minimum of 150mm to stick out from the bearing plate
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3.0 - Ground Anchors - Testing
checkpoint | 3.1 - 7 Day Grout Strength
label | FREQUENCY: 3 x 75mm cubes per anchor or batch (lesser) tested
label | ACCEPTANCE CRITERIA: 32MPa achieved
label | REFERENCE DOCUMENTS: TfNSW
label | INSPECTION/TEST METHOD: Test
label | RECORD OF CONFORMITY: Strength result
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - 28 Day Grout Strength
label | FREQUENCY: 3 x 75mm cubes per anchor or batch (lesser) tested
label | ACCEPTANCE CRITERIA: 40MPa achieved
label | REFERENCE DOCUMENTS: TfNSW
label | INSPECTION/TEST METHOD: Test
label | RECORD OF CONFORMITY: Strength result
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Bleed Test
label | FREQUENCY: One Test / Once per 4 hours
label | ACCEPTANCE CRITERIA: Final bleeding < 0.5%
label | REFERENCE DOCUMENTS: ASTM C940
label | INSPECTION/TEST METHOD: Test
label | RECORD OF CONFORMITY: Bleed test result
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.4 - Fluidity Test - <20s after mixing
label | FREQUENCY: Once per batch
label | ACCEPTANCE CRITERIA: Grout to pass through cone test in <20s
label | REFERENCE DOCUMENTS: ASTM C939
label | INSPECTION/TEST METHOD: Test
label | RECORD OF CONFORMITY: Fluidity Test Result
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - Fluidity Test - 45m after mixing
label | FREQUENCY: Once per batch
label | ACCEPTANCE CRITERIA: Grount to pass through cone test within 3s of first test
label | REFERENCE DOCUMENTS: ASTM C939
label | INSPECTION/TEST METHOD: Test
label | RECORD OF CONFORMITY: Fluidity Test Result
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.6 - Proof Testing
label | FREQUENCY: 3 x Anchors, Prior to Production Anchors
label | ACCEPTANCE CRITERIA: Proof Testing undertaken in accordance with drawings to determine characteristics of ultimate resistance
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | HP
label | RESPONSIBILITY: Geotechnical Engineer, Site Engineer, Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Suitability Testing
label | FREQUENCY: 3 x Anchors, Prior to Production Anchors
label | ACCEPTANCE CRITERIA: Suitability Testing undertaken in accordance with drawings to confirm anchor design, drilling method and installation will be adequate in existing ground conditions
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | HP
label | RESPONSIBILITY: Geotechnical Engineer, Site Engineer, Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Acceptance Testing
label | FREQUENCY: Each Anchor
label | ACCEPTANCE CRITERIA: Acceptance testing undertaken in accordance with drawings to confirm adequate bond strength and conform with acceptance criteria
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | HP
label | RESPONSIBILITY: Geotechnical Engineer, Site Engineer, Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: