## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Internal Painting - Door / Door Frame |  | Internal Painting - Door / Door Frame | ddd0a92e-4031-497e-86df-2caa1a5fc75e
| checkpoint | Confirm correct colours as per currect colour schedule (photo of title block of colour schedule)
| checkpoint | Surface is clean and free from contaminants - Ready for paint
| checkpoint | Sealer Coat applied to all surfaces including top and bottom of door (Product details)
| checkpoint | Check door/frame for damage / contaminants/ dry - Acceptable for paint finish
| checkpoint | First Coat (Photo of product used)
| checkpoint | Check doors / frame for damage / contaminants/ dry - Acceptable for paint finish
| checkpoint | Second Coat
| checkpoint | Final Inspection: Paint coverage acceptable / no visibale bleed through / No overpaint / no damage
| checklist | Internal Painting - Room / Corridor / Lift Lobby |  | Internal Painting - Room / Corridor / Lift Lobby | ce676b71-2058-47c4-a860-7aa959b5a246
| checkpoint | Confirm correct colours as per currect colour schedule (photo of title block of colour schedule)
| checkpoint | Surface is clean and free from contaminants - Ready for paint
| checkpoint | Plastic Protecton installed
| checkpoint | Sealer Coat applied (Product details)
| checkpoint | Check walls/ceilings for damage / contaminants/ dry - Acceptable for paint finish
| checkpoint | First Coat walls General area - (Photo of product used)
| checkpoint | First Coat ceilings general area- (Photo of product used)
| checkpoint | First Coat walls Wet area - (Photo of product used)
| checkpoint | First Coat ceilings Wet area- (Photo of product used)
| checkpoint | Check walls/ceilings for damage / contaminants/ dry - Acceptable for paint finish
| checkpoint | Second Coat walls General area
| checkpoint | Second Coat ceilings general area
| checkpoint | Second Coat walls Wet area
| checkpoint | Second Coat ceilings Wet area
| checkpoint | Final Inspection: Paint coverage acceptable / no visibale bleed through / No overpaint / no damage