## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-185-CIV-Camms - Furniture Installation-Wamarra
ITP Description: |  | Camms - Furniture Installation-Wamarra
Discipline (e.g. CIV/STR/RAIL: |  | 185-CIV
Revision Number: |  | 0
Revision Date: |  | 2024-07-17
ITP created by: |  | Chloe Mitchell
ITP approved for use by: |  | VM
Special Notes to ConQA Team : |  | ITP for Camms Road
Inspection & Test Plan - Furniture Installation
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-07-17
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | AS1428.2 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | AS2890.1 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | AS/NZS1428.4.1 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | AS4422 - 1996 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.5 | Non Dependent | AS4685.1:2014 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Preliminary Activities Completed |  | All ‘pre-construction’ authorisations and checks completed and approved. Ensure that the following items have been actioned: • SWMS reviewed and approved • Plant Pre-start Inspection • Service locations identified • Permits issued • Traffic Management Plans All staff inducted | Verify | Prior to works start | IP |  | This ITP Signed-off
2.2 | Work Lot Map | Work Lot Map | Work lot map attached to work lot. | Verify | Prior to works start | IP |  | This ITP Signed-off
2.3 | Survey Set out | IFC Drawings | Location and heights of drainage components to be setout prior to commencing works as per the alignment and position as dictated by the approved drawings. | Verify | Prior to works start | IP |  | This ITP Signed-off
3 | Material Compliance
3.1 | EPDM Softfall Rubber |  | Rubber to be 3-part mix for EPDM containing: • E011 Light Brown • E090 Brown • E080 Orange | Verify | Prior to commencing any activity | HP* | Surveyor SE/PE Nominated Authority | Material Approval This signed off ITP
3.2 | FU1A Platform Seat | CSA Drawing #CS9576 AS1428.2 | Platform Benches manufactured as per approved shop drawings and in accordance with AS1428.2. | Verify | Prior to commencing any activity | HP* | Surveyor SE/PE Nominated Authority | Material Approval This signed off ITP
3.3 | FU1B – Seat | CSA Drawing #CS9654 AS1428.2 | Platform Benches manufactured as per approved shop drawings and in accordance with AS1428.2. | Verify | Prior to commencing any activity | HP* | Surveyor SE/PE Nominated Authority | Material Approval This signed off ITP
3.4 | FU3A – Boulder Small | MRP-052-C-SME-DRG-82-CBE-AUD-1003 | Boulder to be bronze to yellow colour granite ranging from 0.5 – 0.8m. | Verify | Prior to commencing any activity | HP* | Surveyor SE/PE Nominated Authority | Material Approval This signed off ITP
3.5 | FU3B – Boulder Medium | MRP-052-C-SME-DRG-82-CBE-AUD-1003 | Boulder to be bronze to yellow colour granite ranging from 0.8 – 1.2m. | Verify | Prior to commencing any activity | HP* | Surveyor SE/PE Nominated Authority | Material Approval This signed off ITP
3.6 | FU3C – Boulder Larger | MRP-052-C-SME-DRG-82-CBE-AUD-1003 | Boulder to be bronze to yellow colour granite ranging from 1.2 – 1.8m. | Verify | Prior to commencing any activity | HP* | Surveyor SE/PE Nominated Authority | Material Approval This signed off ITP
3.7 | Cyclist Fencing | Moddex Drawing # 17380 Sheet 1 Moddex Drawing # 17380 Sheet 3 MRP-052-C-SME-DRG-80-CBE-CRG-2102 | Cyclist fencing to be manufactured as per the approved shop drawings. | Verify | Prior to commencing any activity | HP* | Surveyor SE/PE Nominated Authority | Material Approval This signed off ITP
3.8 | Bollards | Safety Xpress BOLSM140 | Bollards to be manufactured as per the approved shop drawings. | Verify | Prior to commencing any activity | HP* | Surveyor SE/PE Nominated Authority | Material Approval This signed off ITP
3.9 | Speed Humps | AS2890.1 | Speed Humps to be manufactured as per the approved shop drawings. | Verify | Prior to commencing any activity | HP* | Surveyor SE/PE Nominated Authority | Material Approval This signed off ITP
4 | Wheel Stops | MRP-052-C-SME-DRG-80-CBE-CRG-1401 | Wheel Stops to be manufactured as per the approved shop drawings. | Verify | Prior to commencing any activity | HP* | Surveyor SE/PE Nominated Authority | Material Approval This signed off ITP
4 | Pre-construction Activities
4.1 | Setting Out - Position of Posts and Signs | Section 714.06 IFC Drawings | Set out work in accordance with IFC Drawings. The required positions of all posts and signs shall be checked and confirmed by the Supervisor before the erection of posts | Verify | Prior to start | HP* | Surveyor SE/PE Nominated Authority | This ITP Signed-off
5 | Construction Activities
5.1 | EPDM Rubber Granules | MRP-052-C-SME-DRG-80-CBE-CRG-5201 Impact attenuation and fall zone dimensions as per AS4685.1:2014 and AS4422 - 1996 | Top wearing course shall typically comprise EPDM rubber granules with pigmentation of granules continuous for their entire cross section. Minimum 40mm depth shall be maintained or as specified by Playground manufacturer for impact attenuation. All wet pour to have rolled edges. Material to consist of two-layer profile (wet pour application) Apply primer or polyurethane coat to the concrete to ensure adequate bonding of the rubber material Do not install rubber in temperature greater than 30degrees Softfall rubber shall be installed in a single pour to prevent joins and edges Finished surface shall have an even appearance, be free from localised depressions, be flush with adjacent edges and true to line & level Thicknesses of single density and double density rubber surfacing shall be as per the below table depending on fall heights. 600mm fall height 15mm single density rubber 1100mm fall height 15mm granule + 20mm base under surfacing 1600mm fall height 15mm granule + 35mm base under surfacing 1800mm fall height 15mm granule + 45mm base under surfacing 2200mm fall height 15mm granule + 65mm base under surfacing 2600mm fall height 15mm granule + 75mm base under surfacing 3000mm fall height 15mm granule + 85mm base under surfacing Beached Edging 420mm | Verify | Per Lot | HP* | SE/PE Nominated Authority | Rubber Surfacing TDS/Manufacturer’s Manual Delivery Dockets Rubber Attenuation Certification Supplier Warranty Slip Resistance Test (if applicable) Manufacturer’s Warranty
5.2 | Installation of Furniture - FU1A-Platform Bench | CSA Drawing #CS9576 AS1428.2 | Fixing method to be bolt down as per manufacturer’s recommended installation requirements. Footing details to comply with the below: • 300x300x300mm deep for isolated pad footings • 125mm deep for slab footings • 25MPa concrete • Bolt down to footings with 4 x M12 x 75mm Dynabolts or similar | Visual Inspection | Per Lot | IP | SE/PE | This ITP Signed-off
5.3 | Installation of Furniture - FU1B - Seat | MRP-052-C-SME-DRG-82-CBE-AUD-1003 | Fixing method to be bolt down as per manufacturer’s recommended installation requirements. Footing details to comply with the below: • 300x300x300mm deep for isolated pad footings • 125mm deep for slab footings • 25MPa concrete • Bolt down to footings with 4 x M12 x 75mm Dynabolts or similar | Visual Inspection | Per Lot | IP | SE/PE | This ITP Signed-off
5.4 | FU1C – Station Seating | CSA Drawing #CS6506 AS1428.2 | Fixing method to be bolt down as per manufacturer’s recommended installation requirements. Footing details to comply with the below: • 300x300x300mm deep for isolated pad footings • 125mm deep for slab footings • 25MPa concrete • Bolt down to footings with 4 x M12 x 75mm Dynabolts or similar | Visual Inspection | Per Lot | IP | SE/PE | This ITP Signed-off
5.5 | FU3A, FU3B & FU3C - Boulders | MRP-052-C-SME-DRG-82-CBE-AUD-1003 | Boulders on Slope: • To be installed in various sizes with minimum diameter of 500mm in any direction. • Minimum 50% of boulder surface to be compacted into subgrade. Boulders on Flat Planting Bed/Adjacent to Tree Planting: • To be installed in various sizes with minimum diameter of 500mm in any direction. • Stabilised embedment to concrete base of boulder to finish 50mm below adjoining finished surface. | Visual Inspection | Per Lot | IP | SE/PE | This ITP Signed-off
5.6 | Cyclist Fencing | Moddex Drawing # 17380 Sheet 1 Moddex Drawing # 17380 Sheet 3 | Cyclist fencing to be installed as per the approved shop drawings and as per the manufacturers specifications | Visual Inspection | Per Lot | IP | SE/PE | This ITP Signed-off
5.7 | Bollards | Safety Xpress BOLSM140 | Bollards to be installed as per the approved shop drawings and as per the manufacturers specifications. Fixing method to be bolt down as per manufacturer’s recommended installation requirements. | Visual Inspection | Per Lot | IP | SE/PE | This ITP Signed-off
5.8 | Speed Humps | MRP-052-C-SME-DRG-80-CBE-CRG-2102 AS2890.1 | Speed humps to be installed as per the approved shop drawings and as per the manufacturers specifications. Fixing method to be bolt down as per manufacturer’s recommended installation requirements. | Visual Inspection | Per Lot | IP | SE/PE | This ITP Signed-off
5.9 | Wheel Stops | MRP-052-C-SME-DRG-80-CBE-CRG-7101 MRP-052-C-SME-DRG-80-CBE-CRG-7102 AS2890.1 | Wheel stops to be installed as per the approved shop drawings and as per the manufacturers specifications. Fixing method to be bolt down as per manufacturer’s recommended installation requirements. | Visual Inspection | Per Lot | IP | SE/PE | This ITP Signed-off
6 | Conformance
5.1 | Redline Markup Drawings |  | Redline drawing to be produced and maintained by engineers to include all changes during construction Redline to use attest IFC version of the design drawings to identify any variations | Document Review | Per Lot | IP | SE/PE | This ITP Signed-off
5.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed-off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /