## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 1 | itp | CHK-001-CIV-Stormwater Drainage Pipes Installation |  | f23e8c72-1285-4052-838f-3463eb36ef27
| section | 1 - Referenced Documentation
| checkpoint | Referenced Documentation
6a8f1633-4b09-5c94-b40b-9ca5edd687b8 | note | Document Title: CHK-CIV-CAMMS-Stormwater Drainage Pipes Installation
0b3a7186-b641-51db-bca8-64217c383364 | note | ITP Description: CAMMS-Stormwater Drainage Pipes Installation
1d4561fa-0836-5b7d-ad02-50cfe06fa99b | note | Discipline (e.g. CIV/STR/RAIL): CIV
164ae465-489c-5d7c-a7bd-3422fd501cbe | note | Revision Number: A
fbaaf70f-6716-5f75-968c-580cd5081831 | note | Revision Date: [Date of Approval]
10fec5c8-9542-5a1f-9767-19751cb7911f | note | ITP created by: Victor Mira
4e0b007b-7894-5499-9242-ab879aee2211 | note | ITP approved for use by: [Approval Authority]
f246eecc-feb9-5032-adca-04fa9534acd0 | note | 1.1 - Non Dependent
fa445180-8b36-5e55-8e2f-7edc0aeb6222 | note | REFERENCE: VR 701
a48c6c84-0cb7-5894-9224-e7ac2cd48ed8 | note | 1.2 - Main ITP
8bc32ed1-500b-519c-a0b3-cd8fe0d3df3e | note | REFERENCE: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
9d3f5831-b66a-5a2d-a7be-2e5a779f2d6c | note | ACCEPTANCE CRITERIA: This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0
8dc89c47-748b-5b59-a46a-4a42794f9c41 | textbox | Enter: Main ITP Lot Number
| section | 2 - Preliminaries - Materials
| checkpoint | 2.1 - Bedding
112d26e8-0175-5314-a1e7-db8cfa045dc7 | note | REFERENCE: VR 701
75aacb90-6e8f-5309-b446-6a38d42bd36e | note | – – – – – – – – – – – – – – – – –
25b97db7-59b5-5924-9528-8df0e2daf019 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
492d4227-f88e-504b-ab9b-5fff3b98cc2e | note | ATTACH: Bedding Material Delivery Docket
2ac92082-816d-5838-84ee-ed1335283457 | note | – – – – – – – – – – – – – – – – –
02b9aa51-e443-5aa5-82c4-b0ece6d20240 | note | METHOD: Document Review
5269e997-a8aa-59bc-af57-78ffbab9cf6c | note | – – – – – – – – – – – – – – – – –
e730dab4-bc3d-5f6d-a9b4-b017b2a892aa | note | FREQUENCY: Each Lot
fefd9f14-7787-5092-aade-ad86a34963b6 | note | – – – – – – – – – – – – – – – – –
83a5f27f-80ff-5e34-9070-821eb28f196f | note | CATEGORY: HP*
7e26365d-5e79-561f-9e2d-167ee3cb559f | note | – – – – – – – – – – – – – – – – –
50ff810f-395c-5b68-b5cc-01eea969e170 | note | RESPONSIBILITY: SE
79784687-eade-5ebf-b8e3-d6837dddce4c | note | – – – – – – – – – – – – – – – – –
0f8510b3-ded5-5a2c-9aac-b3535b7caa48 | note | VERIFYING DOCUMENTS: Material Delivery Docket
3ec7fe8d-7961-568a-8331-29c39a8d950c | note | – – – – – – – – – – – – – – – – –
1d66d0b3-509c-5d7f-b0cf-b61eec5a353f | date | Date Completed:
| checkpoint | 2.2 - Backfill Material
56d7ec6b-61ee-59a2-9be2-9429bf66a37c | note | REFERENCE: VR 701
df5cf847-a4d3-5fb7-8423-e82133d0af55 | note | – – – – – – – – – – – – – – – – –
ff0c8b82-0fdd-59f3-9a18-aae7f01714b2 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
9f5a9b27-4256-5980-b382-1fcb6108741a | note | ATTACH: Backfill Material Delivery Docket
35fc5e36-fe1f-51de-8f78-08a1bebdb780 | note | – – – – – – – – – – – – – – – – –
b9a7d378-4f4c-5d6b-be0f-478a941d5e67 | note | METHOD: Document Review
a788699a-d55a-592c-b6ad-75a16ddcba6c | note | – – – – – – – – – – – – – – – – –
d6d01014-16d2-5d4e-825e-f9261b71108f | note | FREQUENCY: Each Lot
84c2ba7d-3463-5dc9-966a-25760aaf8220 | note | – – – – – – – – – – – – – – – – –
d9100fa7-f178-52a5-84a8-8f8d7660f01f | note | CATEGORY: HP*
14907310-5068-5fca-8d69-b15390472813 | note | – – – – – – – – – – – – – – – – –
a662a49f-dafb-5701-9750-aa783c18308e | note | RESPONSIBILITY: SE
05ab2f3d-5825-5afe-88fa-bb84045cb7a6 | note | – – – – – – – – – – – – – – – – –
f5b37a86-9f51-5fb3-bb94-cc23c74c398f | note | VERIFYING DOCUMENTS: Material Delivery Docket
b71debd0-3f04-50b3-9e81-760f7ec7a8ae | note | – – – – – – – – – – – – – – – – –
40b15b94-2f7f-556e-9d39-40c7fdf1587a | date | Date Completed:
| checkpoint | 2.3 - Stabilized Sand
983e9905-6157-5ef7-bbde-4a7d41254935 | note | REFERENCE: VR 701
a85555ee-aa0f-590c-8f2c-53ab0fb68873 | note | – – – – – – – – – – – – – – – – –
9224dc97-25ff-5f49-a9b4-34ea8bebe0bd | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe
076fe3d7-dfe9-5cac-a474-d1ff3f80e2d2 | note | ATTACH: Selected Backfill Material Delivery Docket
8899fb2f-664d-5657-a485-083e93111301 | note | – – – – – – – – – – – – – – – – –
b2d73a35-f083-50c3-817d-633be81866a9 | note | METHOD: Document Review
57d0e470-0f1d-5ae1-ad23-76c4b34171e5 | note | – – – – – – – – – – – – – – – – –
e957e8e6-b179-5c79-bdf7-bf668fe51817 | note | FREQUENCY: Each Lot
c2071fa6-368d-5beb-8b9e-e07696a45d75 | note | – – – – – – – – – – – – – – – – –
1735e300-65ae-5406-b839-07e1c622ce4b | note | CATEGORY: HP*
94b7d5a1-d72a-5526-915f-9a61345a6dcc | note | – – – – – – – – – – – – – – – – –
b9efd279-7fa6-5e38-a215-94727713b997 | note | RESPONSIBILITY: SE
b322ab5a-a8ea-5481-8ac7-a3838aceaf1a | note | – – – – – – – – – – – – – – – – –
28162e12-6028-53e3-9a1c-5852e4e2ee74 | note | VERIFYING DOCUMENTS: Material Delivery Docket
e023cc1a-a789-570c-92e6-378731e571da | note | – – – – – – – – – – – – – – – – –
6b6f0f46-73bb-5a6f-b5af-b48181348ac9 | date | Date Completed:
| section | 3 - Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Subcontractor QA Submissions and ITP
6282a1e9-8d72-5e96-a3a7-37fb6666f74d | note | REFERENCE: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
61ab24f6-109f-5167-8054-10ae90af74fa | note | – – – – – – – – – – – – – – – – –
c148ebd6-21ce-5c08-bec9-cf7e5b756d38 | note | ACCEPTANCE CRITERIA: Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
24faa741-a0c9-57c0-ab9f-7b3a27fca0f4 | note | ATTACH: Subcontractor Signed ITP
98a1c72a-4e21-5d95-baa1-7966a8e79a37 | note | – – – – – – – – – – – – – – – – –
b9807d33-109b-52bb-8adf-736312ca57c3 | note | METHOD: Document Review
7a11df47-e2b0-5209-a3de-617750f6c6bd | note | – – – – – – – – – – – – – – – – –
464802ba-391b-50a0-bcd9-65ba55fd83f7 | note | FREQUENCY: Each Lot (in case undertaken by subcontractor)
966f7ff4-618f-57af-ad5e-3c9904f43d87 | note | – – – – – – – – – – – – – – – – –
505ef43a-ce43-5a66-994e-30e9d528919d | note | CATEGORY: HP*
ff98f790-7b18-5c9a-be14-1d29070c3dbe | note | – – – – – – – – – – – – – – – – –
01082698-ddab-5173-8d49-26eb0897107c | note | RESPONSIBILITY: SE
6fc64aba-f133-50b5-8760-36f07d4984b9 | note | – – – – – – – – – – – – – – – – –
0625b969-138c-552d-bcc5-e5dcfd302769 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
9b471f4b-012d-5d60-9716-002e7dd4a567 | note | – – – – – – – – – – – – – – – – –
f35a4d9d-6d48-54c8-a89f-90b3b8278926 | date | Date Completed:
| section | 4 - Pre-construction Activities
| checkpoint | 4.1 - Survey Set-Out-
9e1eab0d-90c2-5a47-aed3-fe3f2d3b4c35 | note | REFERENCE: 710.10
0781fa78-5eee-5ff9-9ac2-8e6ee61915b0 | note | – – – – – – – – – – – – – – – – –
92e8a024-0e45-51b7-97d9-5e964a48be22 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
fe48275c-f106-5ba9-ad70-c0bfde5f216d | note | • The culverts constructed shall be constructed true to line and level.
fed43d41-3ae0-525f-b73e-f23220828fbd | note | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
bda96671-4eb1-5594-81ca-e33f232d968b | note | – – – – – – – – – – – – – – – – –
c1a2097f-6ca8-5e22-8d54-ae43aa9da9db | note | METHOD: Survey, Measure
47f753c5-0020-5f74-8a2f-9deadd1a68c1 | note | – – – – – – – – – – – – – – – – –
4f4d1a07-9894-56d0-a07a-15f29d44daed | note | FREQUENCY: Each Lot
194fffbd-00f9-58f2-8882-1953bbf33f69 | note | – – – – – – – – – – – – – – – – –
b461c80f-b758-5a44-a4d1-d99991604efb | note | CATEGORY: HP*
26c7bfde-8541-52b6-b07a-437f453e8cb2 | note | – – – – – – – – – – – – – – – – –
d74cf8b9-494f-52f8-baeb-b46847d24d30 | note | RESPONSIBILITY: SE
d0fc71cc-330b-5b4b-a9e9-cbfdc8e90594 | note | – – – – – – – – – – – – – – – – –
5c92ad1c-d406-5d54-b9d3-6e2d1c6116f7 | note | VERIFYING DOCUMENTS: This ITP, Main Lot Map
f060859b-2f7c-513b-8ef8-1d6112c96234 | note | – – – – – – – – – – – – – – – – –
b9e0eb7b-92de-57d7-b245-cedabcd644e8 | date | Date Completed:
| section | 5 - Construction Activities
| checkpoint | 5.1 - Trench Excavation
a8a4c0ed-238d-578c-814f-27a33ad3b596 | note | REFERENCE: VR 701.15
5b8a71bd-974a-5ccb-894a-0f8c4ec2ecbc | note | – – – – – – – – – – – – – – – – –
5ff02dc8-e03f-5c07-b3a6-2457f98e9d2f | note | ACCEPTANCE CRITERIA: For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
0a20bac1-7659-5d41-b250-21bd2163499f | note | ○ Horizontal Clearance to wall of trench
2a375815-ea78-544f-8cd4-c248d4ad0ab0 | note | ○ Pipe Culverts:
9861827d-d988-5741-9f51-78bf5afe0c39 | note | • 300mm<Horizontal clearance for corrugated metal culverts<1000mm
7cc6b6b1-29dd-57aa-bcdb-17928599cea2 | note | • 300mm<Horizontal clearance for other Pipe culverts<600mm
b694e911-d623-5e09-b8c8-8fbdd18a3b98 | note | ○ Box Culverts:
b149a6d9-05b9-5ce2-bbac-067141047ef3 | note | • 0.5 times the height of the culvert<Horizontal clearance<overall height of the culvert
00cacc65-5275-5b2b-985f-2204fb4ba98e | note | – – – – – – – – – – – – – – – – –
eca53355-8244-5ad9-9b8e-474494d34b30 | note | METHOD: Measure
8163e263-f0b9-5e7f-80bb-6b7459021d00 | note | – – – – – – – – – – – – – – – – –
2d1cb8c9-c516-5d90-8695-dabd7d16ad30 | note | FREQUENCY: Each Lot
58cc7f7d-cd49-5736-a297-6b2b937562dc | note | – – – – – – – – – – – – – – – – –
5f8c790d-2fc3-5710-93ef-fc19db9974ed | note | CATEGORY: IP
a496f792-576d-5106-bd13-30ff63734ea3 | note | – – – – – – – – – – – – – – – – –
fe1cb052-44ee-50d0-aea7-46229e87b6f4 | note | RESPONSIBILITY: SE
c7049752-5a73-5c55-9285-ae044fde16c5 | note | – – – – – – – – – – – – – – – – –
7c0e286e-f99c-577c-aa85-ee052ecfc6c4 | note | VERIFYING DOCUMENTS: This ITP
efe3f6e0-99d3-5eff-ba08-5c755270b673 | note | – – – – – – – – – – – – – – – – –
e82f9cf7-befd-5914-ad63-a4458832fec7 | date | Date Completed:
| checkpoint | 5.2 - Trench Base
a919ace4-072e-5ef0-833f-cfae52e5f773 | note | REFERENCE: VR 701.15
b54a2b70-fc77-5b96-a4d0-622045d6a701 | note | – – – – – – – – – – – – – – – – –
90f15287-cd41-539f-afa4-95e8d33a1083 | note | ACCEPTANCE CRITERIA: The base of the trench shall be compacted to refusal using mechanical plant
61ee2723-be41-5f70-b725-6468ed869c35 | note | – – – – – – – – – – – – – – – – –
b0c34977-7992-56d2-823d-2be2844c1896 | note | METHOD: Visual
b9791a45-407e-5a45-9119-728fd55cb099 | note | – – – – – – – – – – – – – – – – –
f3f2e14d-c7e7-5472-af2a-2b3b93f65cb1 | note | FREQUENCY: Each Lot
e192e1f3-2f06-50c6-ae51-379ebb92fd7b | note | – – – – – – – – – – – – – – – – –
4589c7c7-d448-55ec-bf29-9f2348f7dce5 | note | CATEGORY: SP
773a6cb5-13f5-562b-bb3f-f067ac298101 | note | – – – – – – – – – – – – – – – – –
48ebb2d8-70d5-5a56-915a-b26aa4fc889b | note | RESPONSIBILITY: SE
91a03416-60b2-5a5c-ac5c-e25658d66068 | note | – – – – – – – – – – – – – – – – –
3c30d0fe-00bb-5c0c-ba7d-9faa3842df84 | note | VERIFYING DOCUMENTS: This ITP
328a6db3-7d2e-5184-9344-44cf8c5f14af | note | – – – – – – – – – – – – – – – – –
5309ba00-2f1a-5cd7-b736-e741557af9ce | date | Date Completed:
| checkpoint | 5.3 - Bedding-Placement and compaction
8d99643d-d532-5918-89b4-52430361fd3e | note | REFERENCE: VR 701.16, VR 701.20 (a)
f16029e7-78b2-54c3-9bb6-83fab71a8df5 | note | – – – – – – – – – – – – – – – – –
436dc547-17cf-5428-bd87-78fd20d17c26 | note | ACCEPTANCE CRITERIA: Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
919938bd-a576-5db3-96aa-092f24d43652 | note | • 100 mm where D < 1500 mm
1768a0bd-f69a-54fb-8d97-8c18d708d69a | note | • 200 mm where D ≥ 1500 mm
8f275c2a-5891-5dac-83f9-1aa88a37407a | note | – Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
5a24a4ad-22dc-566a-ad8d-6f9b978b6524 | note | – Bedding shall be compacted to refusal using hand held mechanical equipment.
1ef81008-18e1-5b65-8326-09a2d19b3ff7 | note | – Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer
6de7d30a-075a-53c6-8a0e-5d5113541bde | note | – – – – – – – – – – – – – – – – –
3bcc94b7-2e21-5f14-b9dc-7a5aacc8d57b | note | METHOD: Visual, Measure
1a1e3dc2-de04-5838-9be5-c565b0237f52 | note | – – – – – – – – – – – – – – – – –
cc18b923-7981-5012-b423-606f4ec36272 | note | FREQUENCY: Each Lot
47d6d7b3-2bf2-5526-9171-1b086c658523 | note | – – – – – – – – – – – – – – – – –
d362886f-1cd7-56a6-8d77-33c6dc5a7d11 | note | CATEGORY: SP
31adce63-eead-55d1-a027-aabcb78b1768 | note | – – – – – – – – – – – – – – – – –
0884af87-9664-5db6-875c-e79b984348ff | note | RESPONSIBILITY: SE
cec9e406-f21b-5794-8c83-dd31364b9a60 | note | – – – – – – – – – – – – – – – – –
81948628-d0de-5cf5-9cdf-6e9ed677ded6 | note | VERIFYING DOCUMENTS: This ITP
afcb40e4-874d-5dbe-886d-aa259dfda4e2 | note | – – – – – – – – – – – – – – – – –
a335b4c6-12ba-51d0-b2e4-fb1b65f3197e | date | Date Completed:
| checkpoint | 5.4 - Laying pipes-Bedding conformity
4b55453e-54cc-5b81-b236-694c90f2e939 | note | REFERENCE: VR 701.17
5fa976e9-cdb6-5f2b-be03-6d5a195498eb | note | – – – – – – – – – – – – – – – – –
f015c67d-a538-5759-8995-3071f808e479 | note | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
6875e759-ba42-5773-8886-a4d29e6eb897 | note | – – – – – – – – – – – – – – – – –
92792248-6425-5e1a-b924-50abe1090317 | note | METHOD: Visual
9ff55620-dda5-5364-b771-6c3bc5a65f45 | note | – – – – – – – – – – – – – – – – –
15f79af3-8eab-504a-be49-a3353fd77382 | note | FREQUENCY: Each Lot
b97c0bd2-04b8-5f94-bfe6-e44673b3e27a | note | – – – – – – – – – – – – – – – – –
193dbdf2-eb36-5b42-bb07-e6bc66967e86 | note | CATEGORY: HP*
6f322c0d-f8d7-5225-929d-1d424d1bbddb | note | – – – – – – – – – – – – – – – – –
cf6d003b-2cd9-5835-9b96-4f975e51be5b | note | RESPONSIBILITY: SE
c1ab84af-64b2-5dd1-a32d-c2cd44a5a0bf | note | – – – – – – – – – – – – – – – – –
0176d83e-c1fb-5c4d-b51d-988f73be76d1 | note | VERIFYING DOCUMENTS: This ITP
82fc6d8f-1dd9-530d-8d0f-c60ca0d92739 | note | – – – – – – – – – – – – – – – – –
d7f89450-ccb7-5815-b0b7-47677e49190a | date | Date Completed:
| checkpoint | 5.5 - Pipe Laying
2e3567de-b9ee-5474-bdea-ca0553841e2f | note | REFERENCE: VR 701.16, VR 701.17
01534b4c-6ae1-5bea-bc5c-5620cfc9146d | note | – – – – – – – – – – – – – – – – –
7f46ca30-52b5-5868-aac9-0e56c0a8f6d1 | note | ACCEPTANCE CRITERIA: Laying of pipes or box culverts shall commence from the downstream end.
dc45c946-4e1d-5ffe-900d-bbfe75f217bc | note | – Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
2292ba0b-29d1-5b0e-a75b-447825e14ed1 | note | – The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
f117a149-2056-5835-9534-21ebefb058df | note | – The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
0fcc6c34-1522-56fa-9111-b036947eaf36 | note | – When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
7104eda8-7b3d-5993-a4cd-baa128790e59 | note | – – – – – – – – – – – – – – – – –
292e43d8-ddce-5d8e-91a0-25b8de3f9da4 | note | METHOD: Visual
a60f8010-2e14-5277-a25b-ff2cb7d91843 | note | – – – – – – – – – – – – – – – – –
e778ad26-8d05-518c-8d23-9e6055da1ab6 | note | FREQUENCY: Each Pipe
982971d9-f01c-5481-b117-5aec20d99d23 | note | – – – – – – – – – – – – – – – – –
2f2438e3-38dc-5632-9c8b-dd7a90b2774c | note | CATEGORY: SP
43314ecb-814c-5a8b-bcea-45639c5e0eb0 | note | – – – – – – – – – – – – – – – – –
5501d278-3f9a-5126-b6c8-c277555bab8c | note | RESPONSIBILITY: SE
fc5d1676-aa80-5739-b247-ca9e5407aaf6 | note | – – – – – – – – – – – – – – – – –
a75dd251-bdbe-5206-8181-475d1d4b18b2 | note | VERIFYING DOCUMENTS: This ITP
093e87b6-b6b3-5e53-b407-e957f04767cf | note | – – – – – – – – – – – – – – – – –
cce2bc9f-2c4c-5454-84e7-b36ef9ec793e | date | Date Completed:
| checkpoint | 5.6 - Pipe Joints and rotation
060bd2ab-2885-5b7f-9bf5-322311dce3a7 | note | REFERENCE: VR 70.18
5bbb5370-e76c-5af6-b9ae-82e4ef2e2600 | note | – – – – – – – – – – – – – – – – –
b72ad68f-e69f-521d-94f0-09bfa00120d6 | note | ACCEPTANCE CRITERIA: All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
c4fbdb16-d695-5dd1-a671-ba255a233a0f | note | – Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
6b61051b-d4f6-5fc8-8a2f-c8b7fe6f66ec | note | – – – – – – – – – – – – – – – – –
49003247-f5b5-57d5-94b6-e292a88b7dac | note | METHOD: Visual
f21e2aa1-1e07-5303-9eb7-f55aee514da0 | note | – – – – – – – – – – – – – – – – –
e05d0a00-52c4-542b-ba67-e70f865bc495 | note | FREQUENCY: Each Pipe
8cc34092-bd94-5e95-a5df-e8071372fe12 | note | – – – – – – – – – – – – – – – – –
6243fed9-9799-549e-a8a7-53e3633ebfe6 | note | CATEGORY: SP
ea87ce1e-1230-5bb3-bb1d-9759077e9022 | note | – – – – – – – – – – – – – – – – –
10871007-a23d-525d-aa14-3efc7adf1727 | note | RESPONSIBILITY: SE
206e9b87-8b8a-5527-939e-12290bda7909 | note | – – – – – – – – – – – – – – – – –
8b53d03a-2d9f-5c70-b054-506e2654083e | note | VERIFYING DOCUMENTS: This ITP
024b711b-3a7a-57d3-a945-3016c853c1c4 | note | – – – – – – – – – – – – – – – – –
2b2f8633-dc6f-53fc-b07d-94c4d63b18e9 | date | Date Completed:
| checkpoint | 5.7 - Conformity with drawings
8b716f3d-88d4-5b91-b74a-a9ae7ca87891 | note | REFERENCE: VR 701.10
1419699f-4779-5d88-9dc8-cdf453ab6a57 | note | – – – – – – – – – – – – – – – – –
47e510b4-2712-5429-8cc8-12d6eb2f5737 | note | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
cbcc04ab-2424-5ad4-a3ff-fe51ee1c14a0 | note | • Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
4442fe07-59d6-5fb9-8b93-6ed9f7f2b367 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
ba1f8a7d-fda1-579c-ac5e-4e57fdc3f423 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
6f7058d9-ca7a-558c-9eab-afbcf9a3fe26 | note | (c) invert level of pipes at pits ±50 mm
2e33953a-6e6c-57db-8627-9810b8f1fd8f | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
c4ee982f-e3dc-50cf-8148-78f299a316db | note | ATTACH: Survey Report
01498990-95f0-5726-a96d-f6515d3c4743 | note | – – – – – – – – – – – – – – – – –
ce261310-80f4-51e8-b2d5-97297b071a19 | note | METHOD: Measure
611cdcbd-f067-562f-9d80-82d9bce709f0 | note | – – – – – – – – – – – – – – – – –
3f5e785d-c4ea-5418-b2e5-4f60953f9f7c | note | FREQUENCY: Each Lot
311191b9-2f7b-5561-8d5f-d86c48ce5d26 | note | – – – – – – – – – – – – – – – – –
98e81741-685a-5ba0-8c82-c413da099f42 | note | CATEGORY: HP*
af71a0ab-1f1f-5aba-9ab4-926ef4c1f53d | note | – – – – – – – – – – – – – – – – –
41117d9f-2024-5101-97b5-9a7ec50efd16 | note | RESPONSIBILITY: SE
130c50dd-92b9-509c-9fa3-dd6d63a3834b | note | – – – – – – – – – – – – – – – – –
1982cb35-c5ea-5ea2-ba71-dffd30f32f54 | note | VERIFYING DOCUMENTS: Survey Report
d52b837c-5d57-56d3-93cc-8969d4d33d21 | note | – – – – – – – – – – – – – – – – –
2129b440-25f7-51b4-ae91-5cd75088a64a | date | Date Completed:
| checkpoint | 5.8 - Backfill-Under area to be paved
887a6c93-afe9-535c-bf3f-9f315156d88c | note | REFERENCE: VR 701.19 (a) i
280a9ec0-b8e0-56e5-83aa-b130d8ad45cc | note | – – – – – – – – – – – – – – – – –
4fa58f1d-416a-5735-8bb9-8deca3060c32 | note | ACCEPTANCE CRITERIA: Culvert under area to be paved
9ba6cfb8-ace7-5d68-8751-ffd6e62c007f | note | – Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
3409691a-177a-5044-8995-a8ba5ee163bf | note | – Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
d86fca46-f491-50fa-bbe5-cf7980316864 | note | – – – – – – – – – – – – – – – – –
417190e4-1c2e-5794-a268-0ff91a2a8bfe | note | METHOD: Visual
1b6dc6a0-94b5-509b-b3aa-2f8ff134fd87 | note | – – – – – – – – – – – – – – – – –
71735c95-8785-5f25-a675-8cb4ca75a79e | note | FREQUENCY: Each Lot
fd5a4c94-0d60-510d-ad20-94a27a840112 | note | – – – – – – – – – – – – – – – – –
76ab1f82-4472-57a5-9700-12f337bd7a1d | note | CATEGORY: SP
c4d18859-e11b-5c70-9f0e-5ba17b6a0306 | note | – – – – – – – – – – – – – – – – –
43a95796-dac7-58d1-8299-24107bd1cc9c | note | RESPONSIBILITY: SE
d6d267d8-36ff-5df8-a2c5-54d026e9e8bb | note | – – – – – – – – – – – – – – – – –
be6070ca-ed7f-5a0d-b05e-cf90fc3f6405 | note | VERIFYING DOCUMENTS: This ITP
24c925f3-d8df-5b9a-884d-d88438d7afb9 | note | – – – – – – – – – – – – – – – – –
e32e60b3-02d2-504d-b616-1723749b2085 | date | Date Completed:
| checkpoint | 5.9 - Backfill-Under area not to be paved
73824c56-773b-5a67-9107-35b226b63f02 | note | REFERENCE: VR 701.19 (a) ii
00edb995-d3f4-50f0-9ede-1655720acb1b | note | – – – – – – – – – – – – – – – – –
5062e60e-46aa-500f-b235-d471ded408c7 | note | ACCEPTANCE CRITERIA: The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level
8efc5420-89f7-5f5d-8b03-138daaca0e68 | note | – – – – – – – – – – – – – – – – –
5c9885f1-e78e-565f-8e9a-c9b16c32c358 | note | METHOD: Visual
42e78396-47ed-5a7e-a05f-161bad54fff9 | note | – – – – – – – – – – – – – – – – –
6159cb10-8895-5c91-8a04-f10cd4882fda | note | FREQUENCY: Each Lot
49a33bb5-a5fe-514c-b77c-aef7696afc8b | note | – – – – – – – – – – – – – – – – –
5d60988a-72b8-574b-9d61-9f7472f66f12 | note | CATEGORY: SP
d8857176-2e31-5bf6-a9ba-314d010deb19 | note | – – – – – – – – – – – – – – – – –
a284344b-d8a6-58ec-8c18-2e51bb7ee3cc | note | RESPONSIBILITY: SE
d8b74215-068b-5bd9-99ac-52928db24a2a | note | – – – – – – – – – – – – – – – – –
02249dac-c30e-59ef-8ad8-c8ad0dbde4df | note | VERIFYING DOCUMENTS: This ITP
c197c6c4-3a45-5f82-a533-5960b42c405c | note | – – – – – – – – – – – – – – – – –
fdb61a0e-70fd-5eda-b1af-e51d0a1729db | date | Date Completed:
| checkpoint | 5.10 - Backfilling with cement stabilised sand
9008cb95-a264-5db3-af73-0539eaab7286 | note | REFERENCE: VR 701.19 (c)
786bead9-4906-5c48-86de-0b3864a25184 | note | – – – – – – – – – – – – – – – – –
e7f084ea-c7bd-5d0d-b4dc-d86ad0719b9a | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height
9606e787-c9bf-5f7e-8fc4-dbae4ae4efe8 | note | – – – – – – – – – – – – – – – – –
0c85a82e-a1c1-572e-9f7b-e2f264d64f2f | note | METHOD: Visual
fb519463-908e-5f49-b82e-67ece094b189 | note | – – – – – – – – – – – – – – – – –
91aa3881-b108-52d8-b15c-b25ba8cc446a | note | FREQUENCY: Each Lot
04584fdf-29cb-5cb3-ae76-7abc41055722 | note | – – – – – – – – – – – – – – – – –
e767dca2-0284-55cf-af60-b00f6e558e07 | note | CATEGORY: SP
62924015-fd38-529b-ac99-e7a9910f7856 | note | – – – – – – – – – – – – – – – – –
b621d760-d70d-5447-90bc-01d9469f78f9 | note | RESPONSIBILITY: SE
5804fa22-430f-5397-a018-c86e8b4050c1 | note | – – – – – – – – – – – – – – – – –
47a28f49-c46b-5937-b0b6-a90e0c60ad88 | note | VERIFYING DOCUMENTS: This ITP
e304782c-7b86-5cb0-a494-82b01e49c1bc | note | – – – – – – – – – – – – – – – – –
3bcba2e9-16bf-5fbe-810b-9d227abcbd73 | date | Date Completed:
| checkpoint | 5.11 - Backfill Placement
a16745af-6aad-5fcf-a6d9-8a54b15eb2d8 | note | REFERENCE: VR 701.20
8f5804c0-06f2-51c5-9958-0f8518795d11 | note | – – – – – – – – – – – – – – – – –
034c1494-4936-5921-977f-af924ff4e381 | note | ACCEPTANCE CRITERIA: Backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
9a3be1bd-058c-5a94-b9a3-3c0ac2dcca4d | note | – – – – – – – – – – – – – – – – –
f375c072-9e5b-53e0-9d64-581323249479 | note | METHOD: Visual
20895346-6083-508f-8a4d-4fc2f3ed88ea | note | – – – – – – – – – – – – – – – – –
82665dcc-96de-5e94-80f4-fd4723f6cbaf | note | FREQUENCY: Each Lot
65d2a652-39c3-5ec5-86c9-d2748c087c70 | note | – – – – – – – – – – – – – – – – –
92d94ec5-3861-5f5a-86d1-d7d59df22225 | note | CATEGORY: SP
39159a19-3923-5262-963b-354b22625637 | note | – – – – – – – – – – – – – – – – –
02670583-2a34-5a49-a5da-4e69761db2c5 | note | RESPONSIBILITY: SE
583c9c8a-c62e-5177-b781-9ef9763d9a1b | note | – – – – – – – – – – – – – – – – –
76811fb0-d488-5c24-8f62-ae5300a66b0f | note | VERIFYING DOCUMENTS: This ITP
dc469d97-af7a-5aef-8647-9f3fbd93e97a | note | – – – – – – – – – – – – – – – – –
4cfb7c3c-4aca-51f8-9e8a-d28ef83c8ace | date | Date Completed:
| checkpoint | 5.12 - Backfill Compaction
b71b933e-e49c-5fca-bef8-011168f558b8 | note | REFERENCE: VR 701 (b)
bd2a6219-ec30-5546-9d23-1ac784899ee8 | note | – – – – – – – – – – – – – – – – –
f2f84038-14a8-5c91-a8e6-34bfaa2df979 | note | ACCEPTANCE CRITERIA: 20% of all bedding/Backfill layers for each culvert shall be tested.
49a61fb0-af56-551d-8c2e-49d387c0983f | note | – Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
943374f7-ec4b-5106-95d8-a0746464e4c5 | note | – Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
ee2f5221-a7df-560a-9165-05f8c219cbfd | note | – – – – – – – – – – – – – – – – –
7976bbef-5d6a-5e11-a43b-02635d1e2d1b | note | METHOD: Test
0dc28c23-ce6b-50a9-98f4-936ba9ab765d | note | – – – – – – – – – – – – – – – – –
0b75dba7-a850-5a83-acae-7efb71b70730 | note | FREQUENCY: Each Lot
fded4bcd-6a48-5d3b-b959-ac1c46c2098e | note | – – – – – – – – – – – – – – – – –
21b11351-62e6-5328-a358-4c1b95152b59 | note | CATEGORY: HP*
9c1ef8ae-34a8-507a-8bac-2ded96ea53aa | note | – – – – – – – – – – – – – – – – –
d5d5bb35-ed96-5131-a3f1-09da4d4de04d | note | RESPONSIBILITY: PE
c87e57c7-ec77-5147-b4e8-27ee39ed7c88 | note | – – – – – – – – – – – – – – – – –
7f4db9f4-ff20-59c9-8baa-3467ee01478f | note | VERIFYING DOCUMENTS: This ITP
4bd438fc-bfdc-5578-9b4a-621e5a695a52 | note | – – – – – – – – – – – – – – – – –
c0b09011-b20f-5991-980d-07d4c3bf3585 | date | Date Completed:
| section | 6 - Post-construction Activities
| checkpoint | 6.1 - Compaction and Moisture content tests
c0024530-12e9-5f22-9423-7a419fe125f5 | note | REFERENCE: VR 701.20
6af2e3a0-e2a7-57e6-a6a9-931afa349b6d | note | – – – – – – – – – – – – – – – – –
7552da4b-4c09-556b-af2e-2582d04dcf91 | note | ACCEPTANCE CRITERIA: Bedding and backfill shall be assessed for compaction and or moisture in lots.
230e78d4-0328-5235-9759-18b0ab1eeeb0 | note | • The number of tests per lot shall be three.
ceb3e844-02df-5710-9832-bfd4a6a0d041 | note | • A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls.
d82e25c4-873c-5882-9f44-f1af8c914c4b | note | • Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
52bb3852-8e6d-557a-b353-8f178003c24a | note | ATTACH: Compaction and Moisture content test results:
0db151a5-1c2a-566c-990f-13d97efc521d | note | – – – – – – – – – – – – – – – – –
c43599ba-6376-5b4b-bc7e-771ff96cc1e2 | note | METHOD: Document Review
9686cb47-fbe0-595c-a3f5-c01f8e21fa7b | note | – – – – – – – – – – – – – – – – –
6916e9b2-8680-5025-9c8a-da5f75ef13a5 | note | FREQUENCY: Each Lot
1c5eae59-2261-5d2c-a0f2-a9cdf189b5a3 | note | – – – – – – – – – – – – – – – – –
b39a2ebb-1e40-57d8-a30c-f34cd8f87e91 | note | CATEGORY: IP
270c8cd4-03e4-5162-aa51-29d546848f0f | note | – – – – – – – – – – – – – – – – –
5de6d807-23de-59cb-b8cd-b1f7a92adbb6 | note | RESPONSIBILITY: SE/PE
21b30764-944c-561f-9bfe-22a2b6ae2a09 | note | – – – – – – – – – – – – – – – – –
7458dbdf-6f90-583f-98ee-1bcad095aa33 | note | VERIFYING DOCUMENTS: Test Results
ec9e0fd7-d7cb-5ba5-9817-ae408cb7364f | note | – – – – – – – – – – – – – – – – –
00e6ceab-778c-5df3-b4f3-c52267bf7afd | date | Date Completed:
| checkpoint | Final Inspection
8f262dab-c0b7-5f71-8960-831b1316ed11 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
17e5af41-0df2-510f-a3c1-8c72014dbc7b | textbox | Name:
6300f5e0-9901-5e49-8be5-1588f1b0c1fe | textbox | Position:
21a469a4-1741-584d-90e4-934d3687735d | date | Date Completed:
| signoff | Sign ITP
| checklist | CHK-002-CIV-CAMMS-Stormwater Drainage Pit Installation Rev 1 | itp | CHK-002-CIV-CAMMS-Stormwater Drainage Pit Installation Rev 1 |  | 1cd84ae7-48dd-4ca8-b587-550af6137787
| section | Referenced Documentation
| checkpoint | Referenced Documentation
7df574cf-f5d9-5be9-9086-add4f035aafa | note | Document Title: CHK-CIV-CAMMS-Stormwater Drainage Pipes Installation
64430489-1fb5-5847-83c7-f5aeb3eb074b | note | ITP Description: CAMMS-Stormwater Drainage Pipes Installation
cbaf7b1a-a4f5-5edf-9fc5-0c2a178959cd | note | Discipline (e.g. CIV/STR/RAIL): CIV
a39dfbb6-9011-565b-8658-6e9aa67d1773 | note | Revision Number: 1
e7c4a04f-a3b2-588d-814d-9adc11f75ce8 | note | Revision Date: 7/08/2023
7b15d4d7-0f10-50c5-9c28-73dd50e9e8ee | note | ITP created by: Victor Mira
528c2901-ee1b-5207-9f9d-c856a7c56bf5 | note | ITP approved for use by: Aldrin Guinchoma
fc98df63-72a1-5b07-a503-f18661b74e28 | note | 1.1 Non Dependent
9611d24b-2a49-5dae-839f-9892db4717e1 | note | Reference: VR 701
2db50318-866c-5495-a161-d6d22525755c | note | 1.2 Main ITP
0432f6b4-f44f-5d44-b624-45795dfa4497 | note | Reference: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
66c33e35-20b9-514d-aaf3-1eb190da18af | note | Acceptance Criteria: This ITP Should be used in Conjunction with ITP-CIV-CAMMS-Stormwater Drainage Rev 0
c686938c-e90d-5a31-ae0c-8cc236e8d95d | textbox | Enter: Main ITP Lot Number
| section | Preliminaries - Materials
| checkpoint | 2.1 Bedding
a51ee963-3dc9-5a80-84cb-12f0d2aef99e | note | REFERENCE: VR 701
34b3b73f-1e79-5e96-b264-06cc7f568741 | note | – – – – – – – – – – – – – – – – –
558f00bc-b854-5c3b-8f9a-5bc30a54e566 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and Shall conform with the Material Approval in the Main ITP.
6e5c52c9-2698-5d18-8c7f-df2671bc9738 | note | – – – – – – – – – – – – – – – – –
2ad9bcdf-180d-583b-9136-635906f5f440 | note | METHOD: Document Review
1f6a5243-3aee-5bae-aaba-e8cae29335e9 | note | – – – – – – – – – – – – – – – – –
d9a90433-6969-53e1-b3f4-3de439d16783 | note | FREQUENCY: Each Lot
b5612d37-ef8b-5db0-be9d-6d546427cee3 | note | – – – – – – – – – – – – – – – – –
b2273257-0b04-5697-a0af-b40760aae948 | note | CATEGORY: HP*
9a012584-f898-52c1-88f2-daef0ee68892 | note | – – – – – – – – – – – – – – – – –
6513c97c-d50e-54a2-9462-a80875c6485c | note | RESPONSIBILITY: SE
36259753-4fd5-5e0a-9c4b-b83858d1554d | note | – – – – – – – – – – – – – – – – –
824db693-a2ac-5bf4-ba75-020050ec79e6 | note | VERIFYING DOCUMENTS: Material Delivery Docket
f9f87500-99ad-511b-bedc-16dd234ee427 | date | Date Completed:
| checkpoint | 2.2 Backfill Material
6cf92675-c519-57a5-bdf8-cd5261dd11d3 | note | REFERENCE: VR 701
d382f010-3a47-54fe-bc16-c514c807e34d | note | – – – – – – – – – – – – – – – – –
b244612e-f262-5a4b-886e-affbecf56b63 | note | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the Material Approval in the Main ITP.
70499952-03df-5927-b9e1-12272ec25b94 | note | – – – – – – – – – – – – – – – – –
5771e6c7-9598-5ace-ad7f-ada15099c20e | note | METHOD: Document Review
fc17d08c-7e34-51aa-97b8-0ce2653a4c03 | note | – – – – – – – – – – – – – – – – –
0279a336-ac3b-53c1-8404-6c1c88518074 | note | FREQUENCY: Each Lot
bdeaf4bc-53eb-53f9-9d0b-4ec12d0521d8 | note | – – – – – – – – – – – – – – – – –
415583e4-3339-5ac9-8bae-961eec62c48f | note | CATEGORY: HP*
747c4f59-7bcb-5868-9e16-0343e060e5a7 | note | – – – – – – – – – – – – – – – – –
c09b2723-788e-55f9-82bb-036f53c45191 | note | RESPONSIBILITY: SE
2f3039f0-f976-525a-ad40-cbe4538c65c5 | note | – – – – – – – – – – – – – – – – –
c96ae0c1-eb8c-5f44-b89e-7a456b57552b | note | VERIFYING DOCUMENTS: Material Delivery Docket
de37c1da-7fe4-5c70-abb5-6f010858d483 | date | Date Completed:
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Subcontractor QA Submissions and ITP
d6ff992b-f8b4-521c-b8a9-6907b6d65a76 | note | REFERENCE: ITP-CIV-CAMMS-Stormwater Drainage Rev 0
0af65cdc-33fa-5439-bb7f-af062d988e52 | note | – – – – – – – – – – – – – – – – –
5dcd3d41-e6d1-539e-9660-e78a51e6b8ef | note | ACCEPTANCE CRITERIA: Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
5cd83f85-6c76-5cd3-9f86-e9fde2cb0740 | note | ATTACH: Subcontractor Signed ITP
b0be07e3-8ab7-5601-bbea-851af57a6791 | note | – – – – – – – – – – – – – – – – –
7a5ef945-f9b4-585e-9b51-2d69b3d1b055 | note | METHOD: Document Review
306a8f5c-ead9-55a4-9d3a-20c3ba4f9f09 | note | – – – – – – – – – – – – – – – – –
24616d3c-df66-58f3-8e5c-dc6080772a18 | note | FREQUENCY: Each Lot (in case undertaken by subcontractor)
257f74b8-79c8-5820-b99d-b3f55544e6a1 | note | – – – – – – – – – – – – – – – – –
ed1bf283-9198-5eab-ad20-7b9075094c42 | note | CATEGORY: HP*
d566b669-d508-5591-b00b-88ec98cd7bdf | note | – – – – – – – – – – – – – – – – –
7982339e-6f8c-54f7-ae3e-055160d059e3 | note | RESPONSIBILITY: SE
22f9d0a1-80c5-56f1-a090-96eed053163a | note | – – – – – – – – – – – – – – – – –
f4619519-28ab-5357-8ec2-bba37762a0ce | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
0453ab66-f447-5572-98db-593e1adb10ce | date | Date Completed:
| section | Construction Activities
| checkpoint | 3.1 Survey Set Out
73a8be24-e304-56a1-a1ec-0cc96e65eb30 | note | REFERENCE: VR 701.10
f5b76864-4d3f-5257-b4a2-edd09e2b3613 | note | – – – – – – – – – – – – – – – – –
25589803-ad68-5b64-a013-49483e0420ee | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
27ed5c38-9238-50f3-8056-c91700aa8094 | note | – – – – – – – – – – – – – – – – –
e9183397-dbd7-5cf2-b5de-d5bf152d8285 | note | METHOD: Visual inspection
9dadb0dd-95a1-5a46-9d95-15e2588fc75d | note | – – – – – – – – – – – – – – – – –
65c51c20-9874-52b7-80d2-f2ac984b8fce | note | FREQUENCY: Each Lot
cbb4e4a6-e69e-5244-a6a6-4fdb96988159 | note | – – – – – – – – – – – – – – – – –
30db872f-ec5f-595b-b9e5-47f485f26544 | note | CATEGORY: HP*
317f77fc-9c98-5c56-9ff6-1348f0bc4db1 | note | – – – – – – – – – – – – – – – – –
3aff0fa1-25dd-56de-addf-27dc5eb3b32b | note | RESPONSIBILITY: SE
f84c2288-90a9-5cf3-b6fe-b992210a2bdb | note | – – – – – – – – – – – – – – – – –
b37dddfa-be5a-5071-a151-d0a030d7e21b | note | VERIFYING DOCUMENTS: This ITP
db95a59d-2826-5578-9e33-3b627b17e552 | date | Date Completed:
| checkpoint | 3.2 Pit Excavation
8e3c76fe-66d2-569f-9fef-8e71b08f8c35 | note | REFERENCE: VR 705.05
bf49f073-19d2-5f3a-a6ad-87f747dca7a5 | note | – – – – – – – – – – – – – – – – –
d45ab735-209a-5409-ab67-08aacd2280e6 | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
54f4d963-371f-5a67-81fb-095edfcbe1b3 | note | – – – – – – – – – – – – – – – – –
4346b75c-43ba-54f0-beec-ebcaaa89b93e | note | METHOD: Visual inspection
a24a592a-beca-58ba-99c2-2b219fd390d5 | note | – – – – – – – – – – – – – – – – –
6376ec87-21ac-5c20-b340-92b64c172529 | note | FREQUENCY: Each Lot
d9cbfaf2-1f10-5966-bd0b-59fa4749e402 | note | – – – – – – – – – – – – – – – – –
4bb9de10-9a94-5a7a-a1b2-8c0be1a498c5 | note | CATEGORY: IP
6213537b-c203-5d57-8a64-d153d0db5af5 | note | – – – – – – – – – – – – – – – – –
90fc654f-d172-5f1b-b0aa-acbd61a8cc5c | note | RESPONSIBILITY: SE
9cc6b751-0652-5ac0-8421-5159c89b1841 | note | – – – – – – – – – – – – – – – – –
8cc21f61-6246-5df8-9d46-798c7cac16a8 | note | VERIFYING DOCUMENTS: This ITP
d5809ed8-bf11-59d5-982e-8096075067f9 | date | Date Completed:
| checkpoint | 3.3 Excavation Foundation
d00c549e-5739-57fc-ba0b-53268e77009c | note | REFERENCE: VR 705.05
c6810ea7-23c9-547a-aa51-785eac67ba89 | note | – – – – – – – – – – – – – – – – –
70cfebd1-c787-5a0a-8e31-5e1a258e9fdc | note | ACCEPTANCE CRITERIA: Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
8ec698b6-9e30-559f-aa4a-9b641e0b7b24 | note | > 80mm for clay foundations
85c28796-c1f8-5d60-855d-30cabb0793d8 | note | > 150mm for rock foundations
4dcab8d4-6da6-5f8c-92a9-e6081708a256 | note | – – – – – – – – – – – – – – – – –
31141a1d-e9fe-515c-97b0-e16fbfdd5738 | note | METHOD: Visual inspection
a23faee8-44be-5a01-9b71-d5fd0d697252 | note | – – – – – – – – – – – – – – – – –
24529031-94ff-586c-a77f-de8a32ccbcc3 | note | FREQUENCY: Each Lot
c0470cb6-65a1-5e64-9827-a8bfc19e8e8c | note | – – – – – – – – – – – – – – – – –
d6b4a690-c31f-5487-99fe-4b4b5307dff4 | note | CATEGORY: IP
d0339678-4269-5753-90aa-4e8c24a6b641 | note | – – – – – – – – – – – – – – – – –
5ffbfa42-3d98-5e02-b5f8-34993b6b3cd5 | note | RESPONSIBILITY: SE
f159cf8d-7e56-56b2-b745-6bf9cf5a354a | note | – – – – – – – – – – – – – – – – –
b965c078-f7dd-57d4-bc53-e07cd6407cd8 | note | VERIFYING DOCUMENTS: This ITP
ccc994f7-4e6e-5eaf-9851-bc2968a9d199 | date | Date Completed:
| checkpoint | 5.7 Placement of Pit-Conformity with drawings
1197db57-e12d-5e19-a7fd-444413f33ab5 | note | REFERENCE: VR 701.10
b47a9489-2e11-56e4-a8db-4b5bfab522a3 | note | – – – – – – – – – – – – – – – – –
90d5b3ae-4052-56d0-bf77-e3eb3785530b | note | ACCEPTANCE CRITERIA: The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
60b3d2ac-545b-5104-a0a8-a3f6bf2d876c | note | Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
eec40ff5-2023-5fb6-8e3e-2aa60929756d | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
fb062500-5f73-5b7f-98a5-60e43f2aa087 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
7af37a0e-1f5e-57ed-b5dc-63b75e47310e | note | (c) invert level of pipes at pits ±50 mm
675724d7-aa12-58eb-9ae0-5ea4fd96f9ac | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
e68c2296-901d-57fc-95c5-719a2498c4b5 | note | ATTACH: Survey Report
9e94baf2-28a4-5811-b8c3-2ac9fc82c8de | note | – – – – – – – – – – – – – – – – –
02e69115-43fc-5167-b4bc-efb1d3c322bc | note | METHOD: Measure
b744d03c-046a-56a6-97cf-5e7c8c8207a5 | note | – – – – – – – – – – – – – – – – –
5201e616-f5ea-5c62-aede-f9930b923a08 | note | FREQUENCY: Each Lot
1d40a946-c135-50fd-a61a-9080dab81a75 | note | – – – – – – – – – – – – – – – – –
4f10842e-9cc2-57be-a3f7-1e3f48d10953 | note | CATEGORY: HP*
e1dcf850-3055-53fb-afd8-c9b2c656fd98 | note | – – – – – – – – – – – – – – – – –
b17740d5-f311-5496-b30d-132fb6207c32 | note | RESPONSIBILITY: SE
6930c120-4235-58ef-bb92-edd22c82d228 | note | – – – – – – – – – – – – – – – – –
dc46b88a-6035-5ff3-9b64-c88fc7b24de9 | note | VERIFYING DOCUMENTS: Survey Report
53af2b8b-3462-566f-887b-d3e905e572b1 | date | Date Completed:
| checkpoint | 3.4 Jointing
c1aeb1d8-4b03-5282-9640-3912db8b24c9 | note | REFERENCE: VR 705.11
6aeb4d15-f457-5111-b5cf-098e9907160b | note | – – – – – – – – – – – – – – – – –
b214aec2-3f46-5e1c-bca0-e63d89d38f70 | note | ACCEPTANCE CRITERIA: All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
191e4a7d-f077-5156-9944-3f57475ad9db | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
a7bc5dcf-34f0-5d12-8041-51229c1d064e | note | – – – – – – – – – – – – – – – – –
b4912e8d-362b-5d80-9eff-14a11173c2a4 | note | METHOD: Visual inspection
6adc9f93-5c59-516a-bc96-fdfe7ab5dc08 | note | – – – – – – – – – – – – – – – – –
f4890521-0dea-56a2-8d2e-7dddd4455608 | note | FREQUENCY: Each Lot
7dd600ab-fa3a-5432-8c7a-65e3b938adc6 | note | – – – – – – – – – – – – – – – – –
347b66ac-6f6a-572d-9c06-76e2b28cc99e | note | CATEGORY: IP
31e73d5a-b7e6-543a-8202-9a1e5e836fb2 | note | – – – – – – – – – – – – – – – – –
2125187f-bfa8-553e-a09c-ac4c14cac571 | note | RESPONSIBILITY: SE
a1e72024-6da4-5eb3-96e5-44630836e99c | note | – – – – – – – – – – – – – – – – –
b0b7488a-f4dd-5830-832e-eac37d83d6bb | note | VERIFYING DOCUMENTS: This ITP
1ada8404-2e49-51fd-aae6-c2fb4e3c3d37 | date | Date Completed:
| checkpoint | 3.5 Shaping of Floor
83c68943-a770-50f1-8bbe-50f7a558f2f8 | note | REFERENCE: VR 705.13
121b67d9-b16e-552c-a812-2ff320b9703b | note | – – – – – – – – – – – – – – – – –
ab27325d-a328-5c42-aa14-91e87c252d11 | note | ACCEPTANCE CRITERIA: Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
2d28cc72-f797-5cd8-b1a5-b6c202688c1a | note | – – – – – – – – – – – – – – – – –
ead84078-e393-5aa7-8814-7eb8006ad09f | note | METHOD: Visual inspection
a1985ac3-bfcb-5ad4-a098-0f73ab1bd819 | note | – – – – – – – – – – – – – – – – –
3139d89b-4284-57c0-af4f-b967f7bcb8db | note | FREQUENCY: Each Lot
94a251ba-f974-57e5-9314-cac1e3c413ec | note | – – – – – – – – – – – – – – – – –
65e41cac-0a6f-5470-bfc7-e9d0f3c594dd | note | CATEGORY: IP
de7c61d8-a06d-5c8e-ad90-ba6d24dc358c | note | – – – – – – – – – – – – – – – – –
6f4c2ce2-46ed-5f55-ab33-52a34346d654 | note | RESPONSIBILITY: SE
14edf8a5-7ef8-50af-bd84-a327786e7602 | note | – – – – – – – – – – – – – – – – –
c744f5ed-f5df-5173-94a1-f4a02867b7b0 | note | VERIFYING DOCUMENTS: This ITP
6edbad1b-c249-5db6-81b8-0baea5a1a68a | date | Date Completed:
| checkpoint | 3.6 Step Irons
c61fe9d0-67f1-5374-bbe3-01256c113b16 | note | REFERENCE: VR 705.12
a86ae905-9833-5d78-b791-936614f9644b | note | – – – – – – – – – – – – – – – – –
7076dde8-11d7-52ec-a751-948aaff616ca | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
ae581563-3a85-581e-92fc-db77825ef46a | note | – – – – – – – – – – – – – – – – –
754ca9ec-43d2-5d4b-b63d-363005b622cc | note | METHOD: Visual inspection
8bab9961-cfcf-5d76-a76b-480966e6639c | note | – – – – – – – – – – – – – – – – –
be474652-ae50-56d9-bdbe-f302138c15a9 | note | FREQUENCY: Each Lot
4d3daa42-21e9-5036-bc98-fca930cc182a | note | – – – – – – – – – – – – – – – – –
1c1536a0-6002-52d7-b55d-b7f6bbd1fd34 | note | CATEGORY: IP
dd5464d8-0ee7-58c1-971a-7a9909ff6190 | note | – – – – – – – – – – – – – – – – –
c0226dc6-84c9-544f-b166-fdfcd92c0797 | note | RESPONSIBILITY: SE
c0e820b6-7d18-51e6-a6ed-aeefd25f98d1 | note | – – – – – – – – – – – – – – – – –
014146ba-f8cc-5025-86be-23e48f1af23d | note | VERIFYING DOCUMENTS: This ITP
371f9f5e-77f3-5abc-94ad-659047c0ab2c | date | Date Completed:
| checkpoint | 3.7 Fitting of Covers
ed15ad3e-3f68-50d0-a1f0-6ec1f6ef1808 | note | REFERENCE: VR 705.17
3b36ea0d-7b96-58a0-b981-0ef1456bffba | note | – – – – – – – – – – – – – – – – –
6dc455fa-e465-5bf2-8316-ca4e431c6cf7 | note | ACCEPTANCE CRITERIA: Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
db238a2f-f7d5-590f-9023-df1fc2106f73 | note | ○ Height shall be within 10mm of the design level
867db234-8d12-5f11-aae8-07c183ff8e82 | note | – – – – – – – – – – – – – – – – –
ba2082fb-9940-51db-83f5-8bcd77679b5e | note | METHOD: Visual inspection
b65dc473-e48c-5a9a-8b48-ce1c319190b3 | note | – – – – – – – – – – – – – – – – –
50fbe3fa-a0f7-53f7-b161-f95283274a33 | note | FREQUENCY: Each Lot
5b5ffd0a-4242-5057-951b-35936828104f | note | – – – – – – – – – – – – – – – – –
43437974-eb1f-5146-ad63-4cb505fc668a | note | CATEGORY: IP
2a360a8b-dabf-5e4d-996b-7b173c3e0f85 | note | – – – – – – – – – – – – – – – – –
3402fd93-9d83-596a-bb0c-ccfd86d7d352 | note | RESPONSIBILITY: SE
63a46bc4-5604-5055-9e87-8024842abcf9 | note | – – – – – – – – – – – – – – – – –
7c08583b-a59c-5de0-a759-aa7995090e34 | note | VERIFYING DOCUMENTS: This ITP
25551026-69ff-5cf4-8431-f141e4e46fa3 | date | Date Completed:
| checkpoint | 3.9 Backfilling Around Drainage Pits
2a2c81e1-b06d-552b-923a-b357218cbd96 | note | REFERENCE: VR 705.18
0211df3e-5e38-59be-8c3d-2007fe8ab761 | note | – – – – – – – – – – – – – – – – –
2d6a4481-dd16-5f3c-bc83-2f1cf52d4000 | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
6228ed74-c55b-5752-8329-28e3bffc8916 | note | – – – – – – – – – – – – – – – – –
5bcea257-78f3-5644-8b0f-89ea202b666f | note | METHOD: Visual inspection
2a7e3ca3-b0fc-5657-bb6d-5c2c42caf3ee | note | – – – – – – – – – – – – – – – – –
bfc1c3ec-b36a-5c23-b953-7c76b76d4ffa | note | FREQUENCY: Each Lot
1a7d99c8-4407-50b0-9a73-b46242efd5e7 | note | – – – – – – – – – – – – – – – – –
789b3d55-fe90-5433-a885-4d49dd55e2db | note | CATEGORY: IP
abd78ff8-e541-5890-83cc-4b2ae9c5a53c | note | – – – – – – – – – – – – – – – – –
7729992b-acfe-50c9-b04f-e055b95c0bee | note | RESPONSIBILITY: SE
8c58fa92-838e-5437-9aa3-be5c8347ccd5 | note | – – – – – – – – – – – – – – – – –
f1eee706-c8d5-501f-b134-8b3341bcf0f9 | note | VERIFYING DOCUMENTS: This ITP
aa0cc01b-85ff-5d88-85a6-cc371b7c6e37 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Compaction and Moisture content tests
0249829a-3845-555c-92d4-d8d10572bd2d | note | REFERENCE: VR 701.20
38befb03-24f3-5202-bff4-d3355c3efccf | note | – – – – – – – – – – – – – – – – –
3aa2813a-d52f-5da5-87c9-ea5b05e67663 | note | ACCEPTANCE CRITERIA: Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
c2295d14-4dc2-5ff0-9d72-40eb4550dd47 | note | ATTACH: Compaction and Moisture content test results:
cf0b6e9b-2b02-52ec-938d-996ff33bb333 | note | – – – – – – – – – – – – – – – – –
718196ee-30c5-5cb3-b275-e8eb0942252b | note | METHOD: Document Review
51e0dc48-3ec2-5ef7-9933-14541246a624 | note | – – – – – – – – – – – – – – – – –
afaa8fd3-b7e4-5c0c-a835-bf6371f8035e | note | FREQUENCY: Each Lot
2bc2ef11-8de0-590a-8258-ae437ee95fb9 | note | – – – – – – – – – – – – – – – – –
44aac192-4f60-5d2e-82fb-884be39445ae | note | CATEGORY: IP
d6ae4eb6-2a03-53c5-9b0c-3f0a70cdbd29 | note | – – – – – – – – – – – – – – – – –
6509d2f1-05ff-587e-a4b2-be748aef3d92 | note | RESPONSIBILITY: SE/PE
204a42da-a6d9-5d88-95e9-6627c13ed239 | note | – – – – – – – – – – – – – – – – –
d0f840f4-6d21-562b-a59b-30eea623f72d | note | VERIFYING DOCUMENTS: Test Results
af9ff277-14d4-525d-8b20-9dab81f4fcbe | date | Date Completed:
| checkpoint | 6.2 CCTV Inspection
f52aaa2e-e099-59d8-b9c8-443d4000c0c3 | note | REFERENCE: VR 701.30
4becab17-fa1d-5f35-94e7-eabce37541b2 | note | – – – – – – – – – – – – – – – – –
9ee6f303-63c2-5b72-9e31-02868a5a1b1c | note | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
8ad489b3-a3ee-52d3-9626-ccfdff579a53 | note | ATTACH: CCTV Report (PDF):
dd4b8e20-d1dd-59a2-b75e-e85fb1dd156a | note | – – – – – – – – – – – – – – – – –
bc5bd3e2-40cd-50cc-90fd-51c1ce1da06b | note | METHOD: Document Review
fcbe654d-84cf-51ed-a8fd-f318bbd6cc5c | note | – – – – – – – – – – – – – – – – –
00a5e66b-01ce-56a5-9cd7-abd64adf1ca7 | note | FREQUENCY: Each Lot
5db14538-e50a-5631-98f5-518370b9f5cf | note | – – – – – – – – – – – – – – – – –
3d8d1de8-5c04-519a-b02e-659e47e1499d | note | CATEGORY: HP
e6cd3f7d-487c-5966-9c37-555a94d61353 | note | – – – – – – – – – – – – – – – – –
d3d9d94c-f673-544f-a261-3b798460fd92 | note | RESPONSIBILITY: Nominated Authority
2a2f41ca-2ed0-5bbb-8d4f-9b715f183563 | note | – – – – – – – – – – – – – – – – –
16d55ea8-5240-5042-a75e-db43bc17896d | note | VERIFYING DOCUMENTS: CCTV Reports
9c8838ae-3792-5be0-86a4-60b098a8adde | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
fdad069f-7ec1-52c8-ae44-94ae15930a04 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
1d878e06-1ad1-5d8f-90d2-9c6b4d835de6 | textbox | Name:
517711e7-2302-54e4-9be7-f460e9d5ff7c | textbox | Position:
2fdbcd54-6ffa-5cc3-9a38-408da8145a46 | date | Date Completed:
| signoff | Sign ITP
| checklist | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | itp | CHK-003-CIV-Reinforced Concrete Pipe RCP-Material Inspection |  | 68ba0c44-4839-4ace-8129-64d49bbb9e6a
| checkpoint | CHK-003-CIV-Reinforced Concrete Pipe RCP-Material Inspection
019b2fcb-282f-5c03-8510-431764122020 | note | Document Title: CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
2e985c30-43bc-5d1f-af5a-ef4b3c6d7b66 | note | Check list Description: Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
14dbd2be-5e2d-533b-9141-c209548ddeee | note | Discipline (e.g. CIV/STR/RAIL): CIV
0408e18b-9ec2-530d-99a4-3f8dc49ded20 | note | Revision Number: 0
d57dfd10-cc6c-5046-8c38-83665359dcf2 | note | Revision Date: [Date of Approval]
ed9d2be5-138c-5841-84b7-05f0043e9d88 | note | ITP created by: Jon De Castro
b2cb522f-3dde-546a-b1ee-abc3ff3e45ae | note | ITP approved for use by: Aldrin Guinchoma
| checkpoint | 1 - Materials - Fabrication
a31d80e0-9e92-56ca-bba7-ff75790fa978 | note | REFERENCE:
037a6c07-3cb9-5657-b97f-181c52d18494 | note | • IFC Drawings
1fe6dbb8-e520-586d-bb55-62d99625d0b3 | note | • Section 620
35d3ed0e-43bf-5b2b-ba5e-27e31b2ec9b4 | note | • Section 701
d71c2ef3-7063-581b-9742-4776ddfaa98c | note | • Section 705
14d20d00-a26d-535f-8f49-fdb852033cb8 | note | ---------------------------------
44be64df-c925-5801-8cb5-5561d61b9000 | note | ACCEPTANCE CRITERIA:
96778c0b-9592-58f7-932f-665ec11547e4 | note | (1) Precast items manufactured in accordnace with IFC Drawings
53b71c7b-85d6-595c-9feb-7e7f231bf898 | textbox | - Drawing Ref No.
5f66c1fc-9bb4-5fc4-9dfa-e1aa5eda178c | note | ---------------------------------
d9d585b2-96b1-5120-b997-d81bec3533fa | note | METHOD: Visual Inspection
a8615e53-b4b9-5079-ba5c-a2789afb27db | note | ---------------------------------
0ae9e1e1-876b-5ffe-a598-2ac5ea35bd2d | note | FREQUENCY: Each Lot
f2e5db36-0a4f-518e-b1d8-dd07387f53aa | note | ---------------------------------
48a2a278-3c84-5831-88ab-eb30a62cc44e | note | CATEGORY: IP
16c2965d-c577-5190-8e0f-565e9e4259ab | note | ---------------------------------
980af84b-e4da-542b-a3cd-8f34e8e87de0 | note | RESPONSIBILITY: SE
3a17464d-f6cc-5453-a034-f1a0e8c1a264 | note | ---------------------------------
6a8760dc-a643-5df4-ba94-997d0593c3ff | note | VERIFYING DOCUMENTS: Material Delivery Docket
0372291c-020f-581d-a98e-7d2db3a921c5 | note | ---------------------------------
101e42e4-3f6f-5b0e-8e35-9484ffdfe762 | date | Date Completed:
| checkpoint | 2 - Materials - Delivery
df8ecff6-40cd-5898-968f-f3d5615a8f4e | note | REFERENCE:
1c89a5bd-8e5b-5145-8db3-bb6817e267ec | note | • IFC Drawings
00dcc04c-df1d-5694-98c9-50bf90199517 | note | • Section 620
e36ae1bc-2cee-5516-b266-2c3b07c39ea4 | note | • Section 701
46867914-f07f-5e53-bd41-ea570f0bcc41 | note | • Section 705
8ca3d48d-c6bd-5cf0-b47e-3ed8458e9f5c | note | ---------------------------------
f9b0e62e-4560-5b96-8fb5-dcaa56ffa01d | note | ACCEPTANCE CRITERIA:
58da26b8-caf0-574c-8c47-a3a67145807d | note | (1) Purchase Order and Material Description and Qtys matches
8a3784fe-cf53-538f-a363-9cfd9c137025 | note | (2) Ensure precast concrete elements are as per IFC Drawings upon delivery and no damage evident.
8a28b79a-c7af-555f-8b6d-b8440dfedd0f | note | (3) Lifting and Manufacture compliance certification provided
8e0ed233-d02a-5c32-b320-e1483b893281 | textbox | - Purchase Order No.
c3872f8d-536b-5c19-a82d-8a35e4744197 | note | ---------------------------------
46df0f86-5f7c-508c-b062-b794526e0990 | note | METHOD: Visual Inspection
b722609d-8305-571b-b3d3-06b6e045193b | note | ---------------------------------
daebe469-96b1-50e0-a603-239db95b7f45 | note | FREQUENCY: Each Lot
e30a5e47-bf68-5d59-ae52-6aae23cca778 | note | ---------------------------------
503fc436-3ce7-57fc-a5d4-1c2e13c36622 | note | CATEGORY: IP
d67fdcf2-6170-5fdb-8872-affd95041ca3 | note | ---------------------------------
7c27e44b-c16e-5563-92d5-66f0222aa4b1 | note | RESPONSIBILITY: SE
ef0aa3f1-61cb-503d-ae67-03e866d59025 | note | ---------------------------------
8cf4a1be-1988-5874-8193-661c552774cc | note | VERIFYING DOCUMENTS:
74fd841c-dd64-54ba-b810-24188d33b8c7 | note | • Material Delivery Docket
c323c157-8d44-52ed-9928-d4cd15766eb6 | note | • Purchase Order
5163ea7e-abfd-500e-955d-aff06cee0d4d | note | ---------------------------------
4e8776ab-e1cf-5116-87a6-346f4e2e6e36 | date | Date Completed:
| checkpoint | 3 - Materials - Manufacture's Certificate of Compliance
8be78c5e-1f83-512c-b66c-3e80b63419fc | note | REFERENCE:
142180f1-b30e-5a59-a162-6a1a88cab887 | note | • IFC Drawings
c12f060c-e2fd-5649-afcc-b0b79f950497 | note | • Section 620
cb8ad936-1a02-50ff-a1d1-bcd7db2d5188 | note | • Section 701
1d684104-4992-5794-b8c1-3459fab12d4e | note | • Section 705
27358ced-61e7-5e93-8c42-0f2f07a4a990 | note | ---------------------------------
409c2c7c-a228-5b05-a42a-39e7cbfd9c50 | note | ACCEPTANCE CRITERIA:
5b8f8a8b-48ad-5cff-93dc-ae0628bb2c0c | note | (1) Ensure Manufacturer’s certificates of compliance are received for precast RCP during delivery on site and min required strength is achieved prior to transporting.
e3a7be83-fc13-5eba-9344-a5903a61cc84 | note | ---------------------------------
2b9ef523-10b8-5958-9841-0ef79d407c9c | note | METHOD: Visual Inspection
92bfcef3-ce66-59f2-b945-08917f3f1b26 | note | ---------------------------------
4ec5241a-87ca-58ba-8353-1493262c5e85 | note | FREQUENCY: Each Lot
dd536b47-d716-5f0c-a6de-87cdcf079a41 | note | ---------------------------------
c1afbc9d-668a-5d31-a055-791c969dc70a | note | CATEGORY: IP
6b2f63a1-41d5-5e5c-af92-7893daaaa1a1 | note | ---------------------------------
d01c84e1-6e63-5748-ba62-b573715d2054 | note | RESPONSIBILITY: SE
46d181a5-fba8-5abd-822f-bec41d47ed52 | note | ---------------------------------
dbc6a4e0-2688-51d8-9591-351cf9fd8366 | note | VERIFYING DOCUMENTS:
b4a335c0-7256-5ab6-afbd-dea24cf63dd2 | note | • Material Delivery Docket
92808e45-ad04-5857-b09d-4e0736045f4c | note | • Compliance Certificate
016dd470-72e9-5c87-b17e-298a7d55716a | note | ---------------------------------
d8d11084-342e-58a0-a041-66781c1842c1 | date | Date Completed:
| checkpoint | 4 - Materials - Delivery to site & Storage
c273c18d-9d18-5a08-ae99-2bb21dc955de | note | REFERENCE:
5f8aee41-7970-55fd-a421-9b1db3336337 | note | • IFC Drawings
9ece20c0-c8f8-55ee-8263-648d3da2e947 | note | • Section 620
279812cb-d761-585f-ace9-5703d8a81e26 | note | • Section 701
f62075c6-da2e-5421-b9c5-9dc1c4ccd367 | note | • Section 705
3e176a84-b1c4-52f5-a4b2-fbf8e649d340 | note | ---------------------------------
47e6d5a1-cc7c-5b82-b84c-e4952d840d9c | note | ACCEPTANCE CRITERIA:
c2e51c54-506b-557c-898e-8f1e13cd3375 | note | (1) Identification of product is legible (Stamp, Label, Etc) and should be marked on every precast element.
f6a5263f-4ff9-5149-a107-eda9b040687e | note | (2) Precast elements are unloaded and stored properly on site as per manufacturer's instructions.
c3ec9166-6bd4-5fc6-9049-38e20bf4b00d | note | ---------------------------------
2b8cf4a5-5dfc-5d69-85d6-fadf78b7e987 | note | METHOD: Visual Inspection
c4da6700-7522-5aa5-930d-2ef07287d37d | note | ---------------------------------
a4ffb242-686a-56d3-8463-65ba0e2b8e42 | note | FREQUENCY: Each Lot
fc8ebf0b-29c2-535b-a58c-36c07ab499dc | note | ---------------------------------
a2f3ddc4-af3d-5ce6-a61d-86ecd3152613 | note | CATEGORY: IP
4f73a631-a0dd-5159-b12e-059426b152c8 | note | ---------------------------------
65188cce-f55c-5483-ac42-2577350a7015 | note | RESPONSIBILITY: SE
e32c9e73-fdf9-5e1b-a394-5d51cc585406 | note | ---------------------------------
6757f880-f5b6-51b0-b688-0940bad0ba65 | note | VERIFYING DOCUMENTS: Material Delivery Docket
00750c6f-bed8-56bd-a67d-fb5864bcbb3b | note | ---------------------------------
ec97f1a7-cfa4-5dff-8c9e-fd14476f086b | date | Date Completed:
| checkpoint | 5 - Materials - Others
a5a52d65-933f-58a9-a0a2-5594403bf23d | note | REFERENCE:
2da5bd4d-dc1f-5546-86c2-ae827027ec0c | note | • IFC Drawings
231ec838-2e6a-5127-a238-be357e3034b6 | note | • Section 620
e1eda32d-9ef7-53fe-b645-0bca6fda293c | note | • Section 701
729aee64-fbfb-51ca-9614-4ba01e4f7217 | note | • Section 705
a8f7a54f-0f32-5f90-9d32-d14c66a1d713 | note | ---------------------------------
1fec4b7c-9e67-5197-8166-cdabea260a0d | note | ACCEPTANCE CRITERIA:
60fe8f50-335a-5ab3-a4bc-3efb0c5d9753 | textbox | (For Additional Comments)
d19c29b2-2d3c-50fa-9133-9518edbccebe | note | ---------------------------------
4ffd4269-e5dd-577d-8a52-8f922be7dbc5 | note | METHOD: Visual Inspection
981c522a-e5b5-5cee-af7e-c5b906ab684a | note | ---------------------------------
50ce190d-cf5f-5145-8b4f-e85c35653a5c | note | FREQUENCY: Each Lot
6737c280-9192-5a0d-9ce4-867420b5503e | note | ---------------------------------
3d0ae120-cb81-5ca1-b131-7ddde0554d4e | note | CATEGORY: IP
7527edea-95c9-5e4b-869a-b4cc2fc033e0 | note | ---------------------------------
a335d91a-7ea0-5af1-8287-b1e7bbfdeca9 | note | RESPONSIBILITY: SE
aa0635d2-b4ce-5565-9e18-8b2dc5eb80df | note | ---------------------------------
a49f0d90-7151-5d75-9c4c-99ac18e20957 | note | VERIFYING DOCUMENTS: Material Delivery Docket
1151319a-4aa3-5c59-888c-131653459a07 | note | ---------------------------------
779385c1-ffce-5ad0-bd63-f7e231414293 | date | Date Completed:
| checklist | CHK-004-STR-CAMMS-RSS Walls-Fill Placement Rev 2 | itp | CHK-004-STR-CAMMS-RSS Walls-Fill Placement Rev 2 |  | af562932-84b5-4288-adf4-16194af816d1
| checkpoint | CHK-004-STR-CAMMS-RSS Walls-Fill Placement
f09d8581-968b-5ebb-91a5-ec4733760071 | note | Document Title: CHK-004-STR-CAMMS-RSS Walls-Fill Placement
ff2f1dfc-c707-56af-8940-a33a95804df9 | note | Check list Description: RSS Walls-Fill Placement
f93827aa-5f2a-5183-b039-5ff4f7c0c0fe | note | Discipline (e.g. CIV/STR/RAIL): STR
e9fe9be7-ee90-5e63-93ec-7d7d0b14c2ea | note | Revision Number: 1
eb6091fa-366d-571d-98d8-eb588320a5a9 | note | Revision Date: 1/05/2023
8c769145-28ea-5413-a24e-5e4af301970e | note | ITP created by: Victor Mira
b913fbf1-480f-56c6-b52d-d3f484877bcd | note | ITP approved for use by: Victor Mira
| checkpoint | 1 - Soil reinforcement - Straps
7145b6e2-1edf-55a1-8672-f46c45ba76ef | note | REFERENCE: 682.08
6921ae79-8b53-552e-b12f-2c88b8ede1ee | note | – – – – – – – – – – – – – – – – –
674ef257-686e-57d9-8607-2e0f99a50e12 | note | ACCEPTANCE CRITERIA: Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
60db4c1c-67c3-5c79-9ac1-4e45fc2a1845 | note | • Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
27952fff-5844-5c88-9968-2dcc197f5c49 | note | – – – – – – – – – – – – – – – – –
3613b641-7548-593e-81dd-e0a97b203682 | note | METHOD: Visual
8d6ed4e6-c105-5776-bb12-4b002969891e | note | – – – – – – – – – – – – – – – – –
8d23641d-bb9e-5c98-9871-1d7461737912 | note | FREQUENCY: Each strap
8098612b-c6db-54a6-86a7-1b4cf514bac4 | note | – – – – – – – – – – – – – – – – –
3f2f10bf-6e90-5997-b83f-4d45ac61fcea | note | CATEGORY: IP
dd0d09c7-a305-58c0-8048-0800ccd2b7c3 | note | – – – – – – – – – – – – – – – – –
3feaa987-1a8f-5f1e-ab11-9bab45bde0b9 | note | RESPONSIBILITY: SE/PE
d6380a00-25f1-5857-a043-1bb9e3b0abd5 | note | – – – – – – – – – – – – – – – – –
b37964c4-a57d-5326-9a8b-47d6d9f145a0 | note | VERIFYING DOCUMENTS: This Checklist
f655dc6b-ff88-5913-b284-1caa2f3f9950 | note | – – – – – – – – – – – – – – – – –
455a7e86-06e4-5583-896d-b74a61502540 | date | Date Completed:
| checkpoint | 2 - Soil reinforcements - Connections
175aa34a-8782-534b-bdbb-e2221c298aa7 | note | REFERENCE: Installation manual
6482701c-0cf2-5e42-acf3-6edf63cd13b2 | note | – – – – – – – – – – – – – – – – –
29fee35a-709c-5c4e-acdf-67b3ce2b8ac6 | note | ACCEPTANCE CRITERIA: Correct number of reinforcing element shall be attached to each panel
5bec1816-c907-5641-b60c-b4a1118f3ad4 | note | – – – – – – – – – – – – – – – – –
7ac5921f-d588-5683-9358-9fa94d19c185 | note | METHOD: Visual
f7245198-c4cc-535a-bc51-5aae0637a4af | note | – – – – – – – – – – – – – – – – –
d8ea75b4-01ea-56a9-b01b-e48169e212ac | note | FREQUENCY: Each panel
6b206ee2-7c1e-5ec0-af5f-2fa86a20eb18 | note | – – – – – – – – – – – – – – – – –
1e44d1a8-b178-5937-bdba-19df53664476 | note | CATEGORY: IP
11f76b4e-46da-55bf-a445-f4558699164d | note | – – – – – – – – – – – – – – – – –
83a95c6a-f3dd-5087-88f8-c4f7c70d0ce8 | note | RESPONSIBILITY: SE/PE
0461e92b-9aa1-56b2-b96a-7611935714ca | note | – – – – – – – – – – – – – – – – –
cb1b2e0c-2509-561d-aa25-32530d80928d | note | VERIFYING DOCUMENTS: This Checklist
7376e96e-a45d-5de5-b774-81e0afc78215 | note | – – – – – – – – – – – – – – – – –
e75643dc-1e29-5598-b3c0-f7bdcfd40737 | date | Date Completed:
| checkpoint | 3 - Soil reinforcements - Connections
28995cbb-4e08-5d56-b8f2-6c275a2fc82c | note | REFERENCE: IFC Drawings
94bd2838-b311-53ac-8991-a83cb3721bac | note | • Schedule of lengths: MRP-052-C-RFL-DRG-33-CBE-CSW-1302,1403,1503,1602
d158a99f-dde8-5485-9010-120bf62123c9 | note | • Connections arrangement: MRP-052-C-RFL-DRG-33-CBE-CSW-1901
616c46a6-bda1-54f1-9d58-387116c411ab | note | – – – – – – – – – – – – – – – – –
c2812fad-ab10-58f7-bd21-007931a32328 | note | ACCEPTANCE CRITERIA: Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
f9fe02c9-0f4d-53b2-92e9-5a31a3629ea2 | note | – Bolts are to be snug tight.
a289d7c8-8420-56c6-ad8f-e07e91400823 | note | – – – – – – – – – – – – – – – – –
17378304-f599-5759-b8d5-9b1da00bc5e8 | note | METHOD: Visual
93aab342-02db-575e-bf81-7a921026ae57 | note | – – – – – – – – – – – – – – – – –
cdb56cca-c94a-5c79-9766-cdb6d52b75ce | note | FREQUENCY: Each fill layer
7142199e-c6b7-5c7c-ad29-32d9b7474088 | note | – – – – – – – – – – – – – – – – –
28ffe264-bd0b-5195-a551-9373dace9771 | note | CATEGORY: IP
50391a3a-ef31-51f7-85e8-8aa3f9a05164 | note | – – – – – – – – – – – – – – – – –
078f3f30-88e6-5cde-9aa3-22a0538f0cb4 | note | RESPONSIBILITY: SE/PE
10053f46-fead-5204-928b-b1ff0ac04e6d | note | – – – – – – – – – – – – – – – – –
04e59617-aa8d-5346-8406-508164173134 | note | VERIFYING DOCUMENTS: This Checklist
137f3b78-f408-5b4b-968f-104e5b597b72 | note | – – – – – – – – – – – – – – – – –
9dfa4ba0-3aed-5d1d-a871-e9a523f4a562 | date | Date Completed:
| checkpoint | 4 - Soil reinforcements - Plan arrangement
46653a12-e04e-5407-92fd-3272fdaa0501 | note | REFERENCE: IFC Drawings
6646ba90-5421-5dfe-972f-73d7c72c4f73 | note | • Arrangements: MRP-052-C-RFL-DRG-33-CBE-CSW-1102 to 1104 VR682.06
c774b250-7a59-5c31-b6c3-8f381fc79d6e | note | – – – – – – – – – – – – – – – – –
102c12b5-6700-554a-b221-c928e69e24c3 | note | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
6fbe2224-508d-544b-b0c1-12499447439c | note | – Grid Strips shall not overlapped
d4f78391-03e8-582d-a03b-cfc2848fb629 | note | – – – – – – – – – – – – – – – – –
ed345ddb-13ea-5487-a20f-047aa3f876d1 | note | METHOD: Visual
039bd368-4d89-52c6-a323-8a39748dfdb1 | note | – – – – – – – – – – – – – – – – –
f79a10ce-5062-56c6-8885-cbf43ef9a606 | note | FREQUENCY: Each fill Layer
3d14fe45-9e69-5fb0-9d18-2f65bed391af | note | – – – – – – – – – – – – – – – – –
bfca1f20-7796-55ac-9075-b4a2537c5d55 | note | CATEGORY: IP
aa0c9e63-df8d-5132-8de1-857890293d45 | note | – – – – – – – – – – – – – – – – –
39a50441-7a97-5c4a-a0b1-c6ba65c04955 | note | RESPONSIBILITY: Surveyor/SE
3998075a-97c3-5aa8-8414-ca74f371ce30 | note | – – – – – – – – – – – – – – – – –
a0b09398-b041-598a-936e-da3c111c52d7 | note | VERIFYING DOCUMENTS: This Checklist
5d3942eb-4d33-5b07-9435-d23c095fa75a | note | – – – – – – – – – – – – – – – – –
5acd1804-f7d5-5b1e-8bf5-20f2b54c9b01 | date | Date Completed:
| checkpoint | 5 - Soil reinforcements - Plan arrangement
7ff34b47-f741-514d-99fc-88f4e0370acd | note | REFERENCE: IFC Drawings
1bcd5609-50b3-54e2-a21a-af9d7ff2c633 | note | • Arrangements: MRP-052-C-RFL-DRG-33-CBE-CSW-1102 to 1104 VR682.06
7f5a5a2a-df1e-5e9a-992c-2f510daed94f | note | – – – – – – – – – – – – – – – – –
4a55fdfb-034f-52aa-b5af-f100534bbffa | note | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
7742eca1-54a3-52bb-b06d-65e7f6ce0444 | note | – Grid Strips are not to pass over pile cap. RSS used in conjunction with a bridge abutment shall be independent of the bridge structure.
7372f4cd-b2de-55f2-a467-ce27a7e15714 | note | – – – – – – – – – – – – – – – – –
34a187d7-8b01-5f4a-884d-67b83676e4ab | note | METHOD: Visual
fa8b2bb3-cb4e-5b55-8c48-0ea3b57f2ae6 | note | – – – – – – – – – – – – – – – – –
ea6e4c63-2ef1-52a7-af37-efee2b74f01f | note | FREQUENCY: Where applicable
06445b96-05ea-5eca-90fc-185a6701ce8f | note | – – – – – – – – – – – – – – – – –
7d947383-b0ff-563d-95b1-b936e29d7ba0 | note | CATEGORY: IP
7a359fad-57d8-525e-89c6-78510a178b71 | note | – – – – – – – – – – – – – – – – –
00b27943-828e-5e8e-99f1-47ed7c2b7479 | note | RESPONSIBILITY: PE/SE
7de4ae58-ff68-5b67-ad83-24ff67da92ad | note | – – – – – – – – – – – – – – – – –
dbd3fc26-be60-53f6-ab77-ff456e0f92f0 | note | VERIFYING DOCUMENTS: This Checklist
af8a67b1-2c57-5e6e-a03e-5f029e4e55f7 | note | – – – – – – – – – – – – – – – – –
828a7438-85de-57a6-ba76-790676c09709 | date | Date Completed:
| checkpoint | 6 - Soil reinforcements - vertical deviation
738bb264-0697-5808-a42e-9595efd05e20 | note | REFERENCE: IFC Drawings
f35225db-8285-5359-90f2-c35d1589f465 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1702
947fe590-a02e-5a80-9415-7853f4cf2111 | note | – – – – – – – – – – – – – – – – –
35399e68-7cc4-5002-aa68-88d4fc55e9a1 | note | ACCEPTANCE CRITERIA: The vertical deviation of the soil reinforcement shall be within +1% upwards and -0.3% downwards of the soil reinforcement length, relative to the connection height.
e7391f73-f90c-5d7e-b8d5-92fda2ce9690 | note | • Avoid clash with drainage as directed in IFC Drawings.
b41badc4-4b91-5baa-8e71-73f866b9e403 | note | – – – – – – – – – – – – – – – – –
bb5952cc-51c7-5a49-958f-e39dc3770699 | note | METHOD: Measure, Survey
87939e79-50fa-5e40-a5ef-3beec099c4e6 | note | – – – – – – – – – – – – – – – – –
da7cd5ff-2193-501b-b4e1-2e42ceba3149 | note | FREQUENCY: Each Fill Layer
07a0b286-d5dc-5ae0-8f5f-763f96cddc72 | note | – – – – – – – – – – – – – – – – –
6254f418-85d2-5b68-a012-abf9bb7fe98c | note | CATEGORY: IP
d307c9ee-00eb-55c8-ba37-04ea7d7b3750 | note | – – – – – – – – – – – – – – – – –
b76b8973-ac5f-5772-858c-9bd38ebcfdc9 | note | RESPONSIBILITY: Surveyor/SE
c5a29645-b72e-5729-8cb0-f5029f3b5121 | note | – – – – – – – – – – – – – – – – –
1c7f7396-d7f4-5a59-883f-127f96444861 | note | VERIFYING DOCUMENTS: This Checklist
5510e6ac-eca1-542a-8850-fbb8b105bc21 | note | – – – – – – – – – – – – – – – – –
8672f831-352e-58cb-a771-4bb4ba885883 | date | Date Completed:
| checkpoint | 7 - Fill - Pacement
a887c2ea-c7d1-5c0d-a1e2-3ae4b148b16f | note | REFERENCE: 204.10
61a0b1d6-ea29-572f-a0df-cd7e3c30d3b8 | note | – – – – – – – – – – – – – – – – –
849c7c91-9dd8-5a27-95de-d4ec3d6a0a70 | note | ACCEPTANCE CRITERIA: Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm
ae9347ce-2f63-54e1-a781-869765186b5b | note | • All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps
6cf33a3c-0b97-5542-a26a-6f27353e023d | note | – – – – – – – – – – – – – – – – –
18bae2a4-541a-50b0-883b-29dc77134982 | note | METHOD: Measure, Visual
27140bc5-1016-5273-b339-14e66e593737 | note | – – – – – – – – – – – – – – – – –
eb9ca134-5af8-5732-878f-97f019f5e66a | note | FREQUENCY: Each Fill Layer
fc087ffe-87a2-58c8-8219-e62e841c8577 | note | – – – – – – – – – – – – – – – – –
1440a0a4-3476-59a2-b0e5-1ee970c30c3e | note | CATEGORY: IP
132436f3-1484-5b2c-bbbc-b36f23d9885d | note | – – – – – – – – – – – – – – – – –
2bc97323-895c-5459-a5c2-f6595cafa5f3 | note | RESPONSIBILITY: PE/SE
ce3812bb-b9b0-5950-96ec-8e7bb90b89cd | note | – – – – – – – – – – – – – – – – –
26b70fa8-92fe-5018-9521-159fcd3c6e4c | note | VERIFYING DOCUMENTS: This Checklist
0350b649-2290-5ab4-a443-a8ae92ada642 | note | – – – – – – – – – – – – – – – – –
330011a7-7384-58ec-b8e7-322976b257aa | date | Date Completed:
| checkpoint | 8 - Select backfill - moisture content
ede30106-cae1-542d-813d-3bdab8518974 | note | REFERENCE: IFC Drawings
9b4a8a79-7f32-50b2-90be-c65577ab7f95 | note | – – – – – – – – – – – – – – – – –
af06be78-e907-580a-8a9c-22b5fe0fadb7 | note | ACCEPTANCE CRITERIA: Moisture content of the backfill shall be maintained evenly at all times.
ff3588a3-01c3-5475-886e-9c32282e4785 | note | • Moisture content shall be within 0% to -2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content, must be allowed to dry
a3daf6af-ff31-551e-821e-707d26ee3750 | note | – – – – – – – – – – – – – – – – –
f8932425-58cb-5188-b6de-8c79c61c45ce | note | METHOD: Measure
5b3d40f1-bc21-5707-b298-c71e649a8f41 | note | – – – – – – – – – – – – – – – – –
20d46102-9dbf-5ad5-bfc2-a03ed164021d | note | FREQUENCY: Each Fill Layer
3bcd07a3-2556-5080-bd66-a4ce941ac36d | note | – – – – – – – – – – – – – – – – –
58976da2-6e3c-5ae9-b117-f98f50467a3a | note | CATEGORY: IP
13be8b0b-8451-58e3-9aff-6d5ce0a05b22 | note | – – – – – – – – – – – – – – – – –
059c2a88-6403-591e-9e33-4b96eefa3d08 | note | RESPONSIBILITY: PE/SE
7c7d1f5a-66d5-58a4-a4ca-afcdf3d9e0ed | note | – – – – – – – – – – – – – – – – –
59a2d17b-4811-5c3e-a963-55f82f32ca93 | note | VERIFYING DOCUMENTS: Attached Test Results
68122c44-6a62-5762-a4cc-0d9a203937e8 | note | – – – – – – – – – – – – – – – – –
11eac5c8-f279-510f-943c-350352a477af | date | Date Completed:
| checkpoint | 9 - Select backfill - placement
e2198e41-b84a-5c98-a8ee-587d920cd7f5 | note | REFERENCE: IFC Drawings
b03893f6-b0a4-5b8a-86d8-0e6d1f3d0ddb | note | – – – – – – – – – – – – – – – – –
e356bdb1-9e78-58ea-accf-969d8e4e4bfb | note | ACCEPTANCE CRITERIA: Select backfill shall be placed in accordance with Vicroads section 204 and compacted to 98% of standard proctor density.
044eb40a-d686-5f56-9155-51cb3a1bd88f | note | • Compaction within 1 meter of the wall face shall be achieved by a light weight (Hand Operated) mechanical tamper roller or vibratory system.
10f2fe50-57af-5669-91b5-f36860339fd2 | note | • No large compaction equipment shall be allowed in this zone.
9c63149f-d594-5e3a-b073-5c575d8e907f | note | • Compaction beyond 1 meter of the wall face shall be in accordance with the table VR 204.111
fbfa8ce1-c169-5546-86ce-dff583d8783d | note | – – – – – – – – – – – – – – – – –
168128bb-5ef6-5e87-8812-de991581970c | note | METHOD: Measure
894e5d23-baa8-5147-a87e-aead2286d289 | note | – – – – – – – – – – – – – – – – –
5aefcd75-246e-5224-a265-fde28b1cc65f | note | FREQUENCY: Each Fill Layer
74958cc1-7c03-58ea-a413-d5f4126acdff | note | – – – – – – – – – – – – – – – – –
e6bb156d-49fb-5f91-b4bf-a9871072f424 | note | CATEGORY: HP*
addc152b-e22d-5de6-b006-56fdc6d78cc5 | note | – – – – – – – – – – – – – – – – –
8984b784-004d-5fd4-9728-70fa90416144 | note | RESPONSIBILITY: PE/SE
9822ebfa-88f6-51e1-b0aa-08d614a18b2d | note | – – – – – – – – – – – – – – – – –
8f358c40-7704-5444-ad2e-52d88474c284 | note | VERIFYING DOCUMENTS: This Checklist
e1727d11-2b92-5083-92cb-30480b43c08f | note | – – – – – – – – – – – – – – – – –
3d28c19a-b510-58b5-ac2a-0f69138812e6 | date | Date Completed:
| checkpoint | 10 - Select back fill - reduced frequency
f25fd5c4-9bbf-555c-b7f8-d08222bf4214 | note | ACCEPTANCE CRITERIA: After three consecutive lots of like material have achieved the specified requirement, the contractor may seek the superintendent's agreement to reduce the frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
5948d8f3-2b8d-5f58-badc-7ea2dc1ee324 | textbox | Three Consecutive Lots tested to satisfy this requirement.
2cd364eb-2bc9-5aa8-b550-5b1fe9358ec2 | note | – – – – – – – – – – – – – – – – –
dd7a4e45-366e-558f-ae81-241cfa5e6eb8 | note | METHOD: Document review
ce1b6a2e-2bee-5910-bb24-28976170b074 | note | – – – – – – – – – – – – – – – – –
e52f9a69-51b2-5a4c-ac2f-2a795fa30b9d | note | FREQUENCY: Each Fill Layer
23b61b1c-c22f-528f-8dd2-dbb2fb3b42b7 | note | – – – – – – – – – – – – – – – – –
7dea4c32-7146-5a43-a3af-fb22ec861117 | note | CATEGORY: IP
22044160-494c-5cba-9b52-a0c84d0df6b4 | note | – – – – – – – – – – – – – – – – –
4a28a8ee-4cd2-5736-b5ec-8df179c5e908 | note | RESPONSIBILITY: Nominated Authority/PE
c84962f1-2926-5fda-b3fb-fea5cda2f5c2 | note | – – – – – – – – – – – – – – – – –
55b5a02f-4bed-5ba5-aeef-be91065bb52b | note | VERIFYING DOCUMENTS: Referenced Lots in This Checklist
b18cdc07-fe70-57eb-818d-c7c17ca886b0 | note | – – – – – – – – – – – – – – – – –
3e911f0b-23d5-53bb-97dd-eaa439b44ac1 | date | Date Completed:
| checkpoint | 11 - Select Backfill - Testing frequency - acceptance
57dbaf15-de85-5140-aa1e-da92b1d33339 | note | REFERENCE: IFC Drawings
8dc757c0-7ad8-595b-8b4f-6b3d793befbd | note | • VR 204.14
c8e2be7c-72f6-5030-be52-301c49ef7ef8 | note | • VR 682.16
b31963e7-b85b-5563-9239-38612839bb7f | note | – – – – – – – – – – – – – – – – –
6ced8d17-3f81-54f9-95c7-f9894bc1ede3 | note | ACCEPTANCE CRITERIA: Testing frequency shall be in accordance with Vicroad Specification section 204.14
cf1b8b52-0a2c-5a5f-b958-d84191f6174a | note | • The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance.
f5ff93ac-701a-52bb-9284-248c3c914ae1 | note | • No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted.
1efcc395-b96b-52a9-a973-538a08858648 | note | • If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed
f39bfa44-b11b-5e9d-b70e-c9f76d8224a3 | note | Attach: Compaction test results
3c373fcd-a86a-53bc-92b4-4dc2b6bf63f2 | note | – – – – – – – – – – – – – – – – –
00d473b1-be36-5923-9a8d-b25f11113f7b | note | METHOD: Measure
ff14c97b-389d-5c00-a66b-4316648f26a7 | note | – – – – – – – – – – – – – – – – –
ddeb4e93-fca7-550e-bdfa-8d01c81203d0 | note | FREQUENCY: Each Fill Layer or every second layer as agreed
6cb3f4f3-e083-5df0-b220-7310fd6def99 | note | – – – – – – – – – – – – – – – – –
49338b8a-b957-5999-94c7-4f3c7b921b03 | note | CATEGORY: HP
d26d0c70-fe29-58d7-bd20-884d5d47e5ec | note | – – – – – – – – – – – – – – – – –
dbd7f3c2-4c3d-56a4-bf7c-a5785821f522 | note | RESPONSIBILITY: Nominated Authority
39860132-9cb1-58b8-bee1-250d4a436e7d | note | – – – – – – – – – – – – – – – – –
15d218fc-7eb3-5eac-801f-e5e0259d9f45 | note | VERIFYING DOCUMENTS: Attached Test Results
1f199daa-e988-57fd-af32-e73a92e77d43 | note | – – – – – – – – – – – – – – – – –
7d89d082-8989-5099-8a51-36bbb88148f7 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 12 - Select backfill - acceptance
a50b0bf2-6e68-56d7-9f7f-d27f107d79fb | note | REFERENCE: VR 204.12
19cc1df1-5a66-5ca5-ab33-de2083919a8c | note | – – – – – – – – – – – – – – – – –
4c171616-140f-5923-a452-8c015a005c99 | note | ACCEPTANCE CRITERIA: All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
a70d745b-98fb-501e-be50-7a847b50832d | note | – – – – – – – – – – – – – – – – –
69b8225d-dee3-5c7e-88c1-e95a60bc5754 | note | METHOD: Visual
9e15648d-952f-5013-90bd-456ca4dd74fb | note | – – – – – – – – – – – – – – – – –
56933712-8e7c-569a-ad4e-e31fc8395c9b | note | FREQUENCY: Every Fill Layer
1014b2f7-89d4-5486-8229-e450fab3807a | note | – – – – – – – – – – – – – – – – –
ac281ddd-7dcf-5018-b20c-7796e096ae50 | note | CATEGORY: HP
9489232f-8c9d-5144-9d17-ce01f0a8cc50 | note | – – – – – – – – – – – – – – – – –
fbc3663e-d909-5d97-9896-8ad6b0bd4e0b | note | RESPONSIBILITY: Nominated Authority
89471f88-0f26-5b6c-8c93-6eb080c31db0 | note | – – – – – – – – – – – – – – – – –
723109f4-3db9-526f-ae72-cd483f86216f | note | VERIFYING DOCUMENTS: This Checklist
c6d3def0-8f19-5a1d-aee1-99d58372850e | note | – – – – – – – – – – – – – – – – –
a006d01a-2b5e-56f4-85bf-7e56f7c0122c | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
7276f07f-cf0a-52a7-a222-4bf26062a688 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
bb339f41-e53c-579c-bf82-8caf2e5df9ba | textbox | Name:
aa9702ab-4795-5221-9cf4-d1d06923b4f7 | textbox | Position:
e39a4561-bc61-57d4-80f7-e93be278f832 | date | Completion Date:
| signoff | Signature
| checklist | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation Rev 2 | itp | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation Rev 2 |  | c62ef726-2c3b-40cb-90d2-0cf77d810730
| checkpoint | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation
c5a16d14-8fd7-5673-bcb3-40b769e5a9fa | note | Document Title: CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation
c75fad33-c825-5fc3-b1a5-85a4c10ea66b | note | Check list Description: RSS Walls - Panel installation
b3c32878-4e5f-59a4-ad27-88b6feb26cc9 | note | Discipline (e.g. CIV/STR/RAIL): STR
e7a9bc07-bcb4-5d32-9bea-b42261067476 | note | Revision Number: 1
c2c7b40d-ed5f-52eb-8402-abbdd9652bf2 | note | Revision Date: 1/05/2023
1b0525ee-efc0-59ab-bdd6-c9b9f80f2da2 | note | ITP created by: Victor Mira
1d513f23-5118-5fba-bee2-65d3ed1b530e | note | ITP approved for use by: Victor Mira
| checkpoint | 1 - Panels - survey set out - Tolerance
23a66d11-c81b-5d90-8e2b-b135187d2f60 | note | REFERENCE: IFC Drawings
8ca8be64-881e-5af3-8b23-f28b4653ee4b | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
b4e7572c-c98d-583e-a095-f1ce60c84a9e | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
038f8606-35b9-530d-982f-6b45e1c9867e | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
fe60598e-c3bc-5543-96c7-c143300dbb67 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
0dfdb242-2f10-5432-8aad-a055d29038ed | note | • VR 682.20
f4e0c35b-6fea-592e-b448-acfbf39b7989 | note | – – – – – – – – – – – – – – – – –
e03fc02b-1069-523c-ac53-64060ecc39b2 | note | ACCEPTANCE CRITERIA: Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
26f9d85c-38d3-5362-8932-318223282810 | note | – – – – – – – – – – – – – – – – –
832fb03c-9168-5749-bb32-70252f5a244e | note | METHOD: Measure
e1439810-e913-505c-ae91-edb6e762be58 | note | – – – – – – – – – – – – – – – – –
71cef091-ed70-5fbf-abd5-e70c270a09d7 | note | FREQUENCY: Base course panels
f7502225-9b4b-5f83-a84e-540d1f32ae99 | note | – – – – – – – – – – – – – – – – –
ee31311e-f205-567c-b8c8-6f6deedce921 | note | CATEGORY: IP
791942bf-a635-5e77-88f6-7060067b5998 | note | – – – – – – – – – – – – – – – – –
9fee023b-d43e-5aa0-b994-f9a12671b491 | note | RESPONSIBILITY: Surveyor/PE
4fd7f7b8-3241-577d-86f3-afd6889a9e61 | note | – – – – – – – – – – – – – – – – –
b91051c5-4bde-50dd-b600-030774884652 | note | VERIFYING DOCUMENTS: This Checklist
cbebf9bb-ce4f-5d17-bd1f-900d572369d0 | note | – – – – – – – – – – – – – – – – –
f867021f-bd1f-5a7d-ac79-6312478e3492 | date | Date Completed:
| checkpoint | 2 - Mark - up panel for construction team
a54d2561-18b6-5022-a718-d6bb791389ce | note | REFERENCE: Construction Manual
7ec78dc3-4d0d-583a-9266-dfc4aab028d9 | note | – – – – – – – – – – – – – – – – –
22d6852d-7f91-58ae-b765-473405f0442d | note | ACCEPTANCE CRITERIA: Mark number of strips per row on the back of each panel.
282449de-19ee-5f4d-b45b-5de8214b18ea | note | – Mark design locatoin (Wall number, row and column) as per elevation drawings on the back of each panel
27579e98-933b-53a6-9fb0-d2b7f30e8776 | note | – – – – – – – – – – – – – – – – –
c4eb7d05-e586-5302-9c0e-eae30c7cf0b7 | note | METHOD: Visual
242fb79a-02da-5db4-a65b-2ee08ff8e15c | note | – – – – – – – – – – – – – – – – –
d03ee3f5-d262-5d30-9186-3881bc24450e | note | FREQUENCY: Each panel
45530eb1-08c9-5fa3-97a4-5ee25a4f7ffe | note | – – – – – – – – – – – – – – – – –
8c6685e2-bb21-5a48-a85f-97c38567385d | note | CATEGORY: IP
68df1298-b827-57c1-ae4a-e2dccedf6bcb | note | – – – – – – – – – – – – – – – – –
00f9fe8a-066f-5da0-a875-4c476b75d62c | note | RESPONSIBILITY: SE
b1e0247f-d109-5e17-8d32-717788774de4 | note | – – – – – – – – – – – – – – – – –
17879788-7f09-50d8-b4c8-c02bd278a32a | note | VERIFYING DOCUMENTS: This Checklist
559ad51c-656f-5dc0-b9e9-91380e8d71df | note | – – – – – – – – – – – – – – – – –
39d430eb-aa71-5ae1-a8a4-4ea4ee83fcf0 | date | Date Completed:
| checkpoint | 3 - Panel installation
3bb41032-8098-57a8-9358-95587937464a | note | REFERENCE: IFC Drawing:
70042d7f-219d-5ea2-9d9b-c20cd6177eea | note | Schedules:
1a36cd5a-7bdd-5cfc-8b07-2dc802e09f9a | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1302
dfa2be3a-44e7-5f7d-af19-fe42b8e0e147 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1403
73568bb3-4275-59ba-aeb0-69b9fd1c42ca | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1503
c17619f3-e33f-5883-ad05-39d6332890ec | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1602
c2683d72-2447-5110-b19c-9489fa4dcae2 | note | Instructions:
23582b7b-6ce2-59cb-9ce3-a205fd753569 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1803
5f2cd94c-fad7-55f3-99de-cab4ce4061c6 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1804
a3a56a56-696b-5840-9a30-873283f6ee90 | note | – – – – – – – – – – – – – – – – –
1aa0c1a1-e396-5b99-adb1-e03490c1011c | note | ACCEPTANCE CRITERIA: RSS Panels are to be installed as per IFC Drawings and specified schedule.
5a26c661-5401-53fd-9715-bff9dc8adc82 | note | – Check for correct architectural pattern
f6785c57-ba34-5309-8f68-6e2d59d9aa67 | note | – Check for Weephole Locations
dd703921-8cb5-5cf1-a235-587bdf628e8d | note | – Check the 19mm nominal gap to be maintained
8be10dc3-03a5-5b1a-843e-24060261fd35 | note | – Check the 1 in 40 slope is to be maintained
d6ce6772-94ba-5fbb-aef0-76257a03688c | note | – – – – – – – – – – – – – – – – –
26593c92-68cd-5827-be75-42e69ec0bbab | note | METHOD: Visual, Measure
5ff37e92-53c4-5780-9c94-a85d26af8920 | note | – – – – – – – – – – – – – – – – –
99bf4faf-956f-5254-9b37-7247e89578f2 | note | FREQUENCY: Each panel
f0058788-3752-5c57-883a-6283c26e490f | note | – – – – – – – – – – – – – – – – –
4bf0c283-d54a-5ed9-8ca6-ad4d11db1b6f | note | CATEGORY: WP
e0b962bf-3cc6-5bf3-b987-d2e425d33dbb | note | – – – – – – – – – – – – – – – – –
2a7ba18e-7ffd-5d77-b239-f5f0c07186c0 | note | RESPONSIBILITY: SE
bec01d8d-8ba6-5543-b859-617be33d3068 | note | – – – – – – – – – – – – – – – – –
e71af293-7ba3-582b-b38a-d877034fe306 | note | VERIFYING DOCUMENTS: This Checklist
53081d18-7b90-5479-994a-4bc944d31504 | note | – – – – – – – – – – – – – – – – –
bceee11e-ed48-57e8-be45-7b61245b5543 | date | Date Completed:
| checkpoint | 4 - Panel installation - Abutment interfaces
2c00f9b7-a277-5a5a-9979-906dd2f60fbf | note | REFERENCE: IFC Drawings
113edc7b-ba49-565f-9ce3-86129a1015ff | note | • MRP-052-C-SME-DRG-32-MPK-CSW-2052
4243c3ea-5376-5c7b-b8ca-42289e40de8e | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1105
2df9a8c9-87c6-5069-ae4c-3cb63348ed01 | note | – – – – – – – – – – – – – – – – –
46a0b2af-cb0e-53ad-ba03-2073f7e52f39 | note | ACCEPTANCE CRITERIA: 20mm nominal gap between panels and Abutment wall is to be mainatined
a049662c-6ed1-5d74-8853-85ecb9822682 | note | – 300mm wide x 6mm thk Galvanized plates fixed to abutment wall and Adjacent panel as per IFC drawings.
645b9f2e-a6d1-5e87-a43b-891536103985 | note | – 600mm wide BITAC tape installed
1a06227d-f000-5d97-8cb5-05ccca847277 | note | – – – – – – – – – – – – – – – – –
3f5728c2-4931-5a04-9b64-8c4631b5a11e | note | METHOD: Measure
854221ed-1c1d-59fd-8929-45014b576f5e | note | – – – – – – – – – – – – – – – – –
00bc96da-19c1-5a03-be89-3bebdec8f539 | note | FREQUENCY: Where applicable
f7f6cb3c-5b1e-5e46-b248-e5b95252b556 | note | – – – – – – – – – – – – – – – – –
112e3be3-57ba-5ae6-a766-7f5e2f26112f | note | CATEGORY: IP
b8b8f520-8cfd-57da-bf35-71244ea36ac4 | note | – – – – – – – – – – – – – – – – –
b3d29da7-2407-5666-9586-d72a51b0a39c | note | RESPONSIBILITY: SE/PE
adebb367-c6a9-512c-b0b4-797a9281291c | note | – – – – – – – – – – – – – – – – –
f995fa8a-ec76-5429-8895-d4c4aeac0f23 | note | VERIFYING DOCUMENTS: This Checklist
07c25085-be13-5a73-b96b-b4b702d4a9e1 | note | – – – – – – – – – – – – – – – – –
bbcba258-d29d-5aeb-bed9-79727ad13d67 | date | Date Completed:
| checkpoint | 5 - Filter fabric - Installation
281be809-1b15-5f9a-bc4c-ec54fd160ee8 | note | REFERENCE: IFC Drawings
d363558f-439b-56a4-a45d-95619b20e490 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1803
ef4b2a75-ed23-52a5-ad07-99cb43b0c6a2 | note | – – – – – – – – – – – – – – – – –
1b80d513-f2b5-5491-93aa-daef5aca2cd2 | note | ACCEPTANCE CRITERIA: Install Filter Fabric against all vertical and horizontal joints
7dfc11c0-65fe-567c-8153-ba44ad8b764f | note | – – – – – – – – – – – – – – – – –
c4ab92b0-f224-5ac4-826c-ea008d13bf6a | note | METHOD: Visual
94fbf997-5af3-511e-a2ff-dbad3d294a07 | note | – – – – – – – – – – – – – – – – –
3639bd1c-1e2b-5470-89ff-17765d7f79a2 | note | FREQUENCY: Each course of panel installation
d61f508f-a64f-50d0-8de6-cd9ddf7270e2 | note | – – – – – – – – – – – – – – – – –
713a07ee-45ae-55c6-8d24-33aaa945fe9b | note | CATEGORY: IP
45bb1b74-a748-50e0-bc12-5bfd2a2ac905 | note | – – – – – – – – – – – – – – – – –
aaad321a-36e0-5865-b287-18fa5b93e550 | note | RESPONSIBILITY: SE
c122cb0e-b52d-524b-bb15-0e771aac1719 | note | – – – – – – – – – – – – – – – – –
1cb0367e-75ac-531a-a225-06f0145a0612 | note | VERIFYING DOCUMENTS: This Checklist
da3def15-225f-573d-a30a-951dff2f1327 | note | – – – – – – – – – – – – – – – – –
995c35a2-83d2-508c-a200-6405354f61b2 | date | Date Completed:
| checkpoint | 6 - Drainage - Strip Drain
fcf0237d-865a-535d-bef0-835964fe099e | note | REFERENCE: IFC Drawings
f760aa20-4a10-532e-ab80-6e3a4d1bbe7a | note | • MRP-052-C-SME-DRG-32-MPK-CSW-2053
b60a1d07-d40c-5e85-b16e-52d2e35c4093 | note | – – – – – – – – – – – – – – – – –
313e0339-b68c-50ce-a767-0809db8f23f2 | note | ACCEPTANCE CRITERIA: Install 150mm wide vertical strip drain "PRODRAIN PD20"-at every vertical joint between panels in RSS wall.
24701114-612b-52fb-8bf8-742e241251e9 | note | • Ensure no gap is formed between strip drain and RSS panels
cd929267-b18f-50e1-85c8-6deb08780e2d | note | – – – – – – – – – – – – – – – – –
e11fe419-c661-51f3-aa0a-2cfbb23ee8fe | note | METHOD: Visual
a5e6c454-ee7a-5734-9261-f678ce57ebad | note | – – – – – – – – – – – – – – – – –
8b788e96-b93f-5fbf-a41d-1f4f667fecc9 | note | FREQUENCY: Each course of panel installation
7d6b27ca-c00d-5858-b4ed-88437f568e2a | note | – – – – – – – – – – – – – – – – –
9c0a3cf5-859f-5559-b03a-fe6e5fe952fb | note | CATEGORY: IP
d2d2d06d-a816-589a-8036-b12314f36ba9 | note | – – – – – – – – – – – – – – – – –
2e50e39d-ef35-5c28-8477-ec3eeb9dc472 | note | RESPONSIBILITY: SE
3d4f2ee8-41f7-5d30-9445-28421c960c15 | note | – – – – – – – – – – – – – – – – –
a1ebe31d-74ba-572a-b1b4-69323b723678 | note | VERIFYING DOCUMENTS: This Checklist
b47cbb4c-4478-50c1-8254-829fc7acf869 | note | – – – – – – – – – – – – – – – – –
fb72623a-fee8-543c-a9fb-b0754cee2519 | date | Date Completed:
| checkpoint | 7 - Panel installation - Survey reference points
48d1a665-1dba-5775-8b3a-6b28f1e67168 | note | REFERENCE: VR 682.21
159d2442-aa54-5d5c-9809-4b489ed7c04a | note | – – – – – – – – – – – – – – – – –
8b6802dc-2272-5a1a-ae70-27231607bfe3 | note | ACCEPTANCE CRITERIA: To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
daf5e89d-dc58-508f-8da0-503c108ca91c | note | – – – – – – – – – – – – – – – – –
c99ca691-ce5d-5108-b838-8ea48d438c19 | note | METHOD: Visual
f79900df-f42c-5035-8a84-bc041a78cba2 | note | – – – – – – – – – – – – – – – – –
eb2bf11f-1213-526c-8a3e-33e69033076f | note | FREQUENCY: Each course of panel installation
281daa7c-906f-5110-b6dc-773ae41d4247 | note | – – – – – – – – – – – – – – – – –
e65ecf24-a9c4-57a9-921b-6109dc114bd9 | note | CATEGORY: IP
cb2244eb-1d84-5f23-a3e6-45e21c8c36a2 | note | – – – – – – – – – – – – – – – – –
6f41e742-6059-580f-9857-730660639c15 | note | RESPONSIBILITY: Surveyor/SE
62328cc8-f116-5c9e-b8c8-446ba5905296 | note | – – – – – – – – – – – – – – – – –
466a9442-cfaa-5995-a4eb-b23e1a37b9ab | note | VERIFYING DOCUMENTS: This Checklist
2a576ff9-381b-52b5-9ecf-ba9f53132f67 | note | – – – – – – – – – – – – – – – – –
551cfb7f-4c7f-5c3c-a866-e15eaaf13e5d | date | Date Completed:
| checkpoint | 8 - Traceability of precast units and records
bd727285-11da-53b5-88dd-2b764151b902 | note | REFERENCE: VR 620.09
98be84e8-6df8-51f9-82a3-88bf7b6b9e3d | note | – – – – – – – – – – – – – – – – –
64bbadfc-874b-5477-8f99-70b519bf7d45 | note | ACCEPTANCE CRITERIA: Unique ID of precast panel is recorded.
fd6a1188-53df-5d83-bb74-4e703b833d7e | note | ATTACH: marked-up elevation drawings or installation record with reference to panel ID
a995fa8b-9aea-5cbe-92bf-e6ecb887c660 | note | – – – – – – – – – – – – – – – – –
f5cc8514-439a-50bf-910d-c6f33bcc4c3c | note | METHOD: Visual
59506b47-d793-57e2-9c84-4073f30ec51e | note | – – – – – – – – – – – – – – – – –
4b9440c5-212a-5aed-a944-461a6fbe407a | note | FREQUENCY: Each panel
3d2df8de-46a0-540f-8361-f9b53a555afa | note | – – – – – – – – – – – – – – – – –
9fd8b91a-16db-5451-8f4f-f7c964819960 | note | CATEGORY: IP
694ff59b-540c-5560-80b5-8780db689b93 | note | – – – – – – – – – – – – – – – – –
4155fdff-9f4b-56de-9add-2f8357f06060 | note | RESPONSIBILITY: SE/PE
45999bd0-ed74-5ad7-9f60-733c317e8721 | note | – – – – – – – – – – – – – – – – –
e19a2e14-9aec-561b-bca0-bee8f1c8a88e | note | VERIFYING DOCUMENTS: Attached marked-up drawing or installation record
c10942d9-3dd2-599b-9d98-c955ce5f667d | note | – – – – – – – – – – – – – – – – –
fc5753dc-1827-59ac-8f5b-a3defb45b30b | date | Date Completed:
| checkpoint | 9 - Panels installation - Conformance Survey
34695902-daef-565f-8a0d-11d76cd6a904 | note | REFERENCE: IFC Drawings
a76089db-bf8f-5a6a-ae28-f22870447ac0 | note | • VR 682.06
146879ee-cbd0-5a79-a56b-68163137e8ad | note | • VR 682.17
db762e8d-4dc8-550b-af25-9402b87ed03b | note | • VR 682.20
915275e6-93ba-5e14-8b24-cf4e47ad226d | note | – – – – – – – – – – – – – – – – –
2bb74069-5a67-5793-9faa-359b5f2b1a82 | note | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
0b37c4bd-4413-5d31-8c3d-2d52aece63ec | note | The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
66103a84-1cb4-5c84-bbca-a9d9fb554471 | note | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
c47addd8-9c5c-5b4c-b7d7-6f61d054bafc | note | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
9d25e40b-6223-5544-843e-ca967a9438a7 | note | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap
9669028d-5d99-5761-bf4b-0417137ab185 | note | – The wall level shall not deviate from the specified level by more than ±20mm
87926d59-23bc-58f5-833a-f01d8e090317 | note | – The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
1391a4fc-9ff2-5542-b8ac-a640ee0792a6 | note | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
0c36ec03-8e7c-5cfd-ae5d-65b453ac0dcf | note | Attach: Survey Report
f48aaade-39c8-5bd4-9ecc-fa557f64db0b | note | – – – – – – – – – – – – – – – – –
73d267c6-6390-5ad9-9975-0ed0cae2bc96 | note | METHOD: Survey, Measure
a2fc2eb5-0fad-561a-ac4d-378643cce10d | note | – – – – – – – – – – – – – – – – –
071ee6e6-7590-5fb9-9d92-05c8b3700572 | note | FREQUENCY: Each course of panel installation
084205dc-4bb1-5870-9ba3-a07fa1ef83f1 | note | – – – – – – – – – – – – – – – – –
5687f847-696c-5521-a64f-6856122dd8f5 | note | CATEGORY: HP*
0a376d96-b85b-58e0-9117-202852facf02 | note | – – – – – – – – – – – – – – – – –
98c678c4-c945-5fa5-b461-fe8e6d6890c6 | note | RESPONSIBILITY: Surveyor/PE
a419bbda-b98d-5f53-9571-e42871ac7ea7 | note | – – – – – – – – – – – – – – – – –
9900df89-8f4c-511b-801c-9068d001d398 | note | VERIFYING DOCUMENTS: Survey Report
7223d2e3-0094-5359-8325-c5ab91fe6757 | note | – – – – – – – – – – – – – – – – –
2cbfe2bc-8754-55ac-83f6-c0d5ff05b907 | date | Date Completed:
| checkpoint | Final Inspection
db45e4b2-f016-513e-bbe7-7e6d09735799 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
704cba7f-2aa6-532f-867c-e92bc9cd18fb | textbox | Name:
d1d6d11c-db25-58e4-bf48-5a2acdd76150 | textbox | Position:
1b0e467b-937c-5048-85da-8dc77932e3c6 | date | Completion Date:
| signoff | Signature
| checklist | CHK-006-STR-RSS Walls-Material Inspection-Precast Panel | itp | CHK-006-STR-RSS Walls-Material Inspection-Precast Panel |  | 313e7df7-988c-4daa-84ae-9d7ae79f17ed
| checkpoint | CHK-006-STR-RSS Walls-Material Inspection-Precast Panel
ac5edd73-6e20-52e4-a760-be910f5f5a0d | note | Document Title: CHK-006-STR-RSS Walls-Material Inspection-Precast Panel
540ebf6c-f1b4-5ffa-bd28-5c706dfe9943 | note | Check list Description: RSS Walls-Material Inspection-Precat Panels
183c6d9b-0c29-55ac-a633-bd56dbf76f80 | note | Discipline (e.g. CIV/STR/RAIL): STR
409b8ea2-a030-5be0-832c-6688aca814a6 | note | Revision Number: 0
4d1240fa-1edd-5b8c-b89e-ce6a74229fa6 | note | Revision Date: 10/01/2023
8af45c10-8d78-5af0-bb78-197d0a445b8c | note | ITP created by: Victor Mira
46bb26c6-1933-5609-9d26-940e889d2e6f | note | ITP approved for use by: Victor Mira
| checkpoint | 1 - Delivery Details
60273477-7ef2-5a33-a52a-6cea6585f58f | note | ACCEPTANCE CRITERIA:
baa7506c-3dcb-562e-afba-a3da00889db8 | textbox | Enter: Delivery Docket Number:
3ca3bd2c-42c9-50c1-bdc8-d595a5201638 | date | Enter:Delivery Date:
06e4a677-de18-51a6-a156-0eabb2acf21f | textbox | Enter:Element ID (s):
8db3a2eb-c85b-5102-bd80-f417b34deeaf | note | Attach: Delivery Docket and packaging Slip
a4332fad-104b-54e5-996b-530be58304bd | note | – – – – – – – – – – – – – – – – –
3bc4ddc6-e0db-558b-950b-e88d6184e6ca | note | METHOD: Document Review, Visual
8b55c965-eaac-506b-a16c-0ec092d28821 | note | – – – – – – – – – – – – – – – – –
4d1caa2f-51c9-5601-a3cd-d4322dc836e4 | note | FREQUENCY: Each Delivery
ec4b310f-f153-5a86-94f5-3c8bf6193598 | note | – – – – – – – – – – – – – – – – –
6b9b74a3-a4e7-5515-b52b-6cf618f27bfe | note | CATEGORY: IP
0064734b-03d3-5e3e-8779-0f43e392cd22 | note | – – – – – – – – – – – – – – – – –
f9c07177-761a-544e-8a1e-d1f130292c91 | note | RESPONSIBILITY: PE/SE
6bb02a3a-5877-5afb-a869-d37d7de6fbb5 | note | – – – – – – – – – – – – – – – – –
b84c28ec-5879-5751-a16b-ea95dd744b7d | note | VERIFYING DOCUMENTS: This Checklist
c0844c2e-65d2-5205-876f-a15c003b3f82 | note | – – – – – – – – – – – – – – – – –
cf9384ff-0988-5c1a-98cb-6f3a1947ee66 | date | Date Completed:
| checkpoint | 2 - Packaging Inspection-Quantity
2c939a38-81ea-54b4-ae98-7fb28c55ff70 | note | ACCEPTANCE CRITERIA: Does the number of packages in the delivery match that listed on the freight list/packaging slip?
8cc12b92-6a55-5e82-ab81-f44b63fb31c8 | note | – – – – – – – – – – – – – – – – –
141aff59-f6b3-5128-b26b-6d4785953063 | note | METHOD: Visual
afa3fca9-73a8-5345-bb0b-2e506e060073 | note | – – – – – – – – – – – – – – – – –
a64cd12c-51d5-571f-837a-a3ea0fbfef7e | note | FREQUENCY: Each Delivery
6d64a809-08f6-5d20-ab7d-af538613b6f4 | note | – – – – – – – – – – – – – – – – –
a587e540-ba9f-59f2-9c47-27ab1a6851be | note | CATEGORY: IP
9eafcef3-cc79-52b9-8161-6b5172602033 | note | – – – – – – – – – – – – – – – – –
7a789e1d-6cbb-5492-a211-bf553756bb2c | note | RESPONSIBILITY: PE/SE
6c549f55-3dfd-5750-8e09-03c7c3d58739 | note | – – – – – – – – – – – – – – – – –
2a77fc91-5c63-5d84-a935-76e99d7c4251 | note | VERIFYING DOCUMENTS: This Checklist
b1abcaa1-5043-50e3-8e03-290b58c9ac94 | note | – – – – – – – – – – – – – – – – –
bfb8e544-731d-53e7-a914-6c6a3d6ce2d1 | date | Date Completed:
| checkpoint | 3 - Packaging Inspection-Delivery Contents
44637807-0117-593e-ba57-40b39017b72a | note | ACCEPTANCE CRITERIA: Do the contents of the delivery match the freight list/packaging slip?
067a42c7-5c30-56aa-b7d7-39dddfc4aa03 | note | – – – – – – – – – – – – – – – – –
a5d19921-5e2d-5e50-939b-f6e042e199ec | note | METHOD: Document Review, Visual
ce7bd541-91b4-5c90-af51-6f93d33e2154 | note | – – – – – – – – – – – – – – – – –
9931d534-5cbd-506c-9dcb-2c465b2f6bdf | note | FREQUENCY: Each Delivery
6de1d315-65df-5db7-a2ed-7fa067d7fa72 | note | – – – – – – – – – – – – – – – – –
0cb8d113-dc0f-562d-969e-2935a0854b9d | note | CATEGORY: IP
f561b983-f950-5112-a612-7b162a30de06 | note | – – – – – – – – – – – – – – – – –
c86d5575-8da3-5504-beb0-37e3533f6547 | note | RESPONSIBILITY: PE/SE
b14d5a16-7534-58d3-9e70-f6ee9db5754d | note | – – – – – – – – – – – – – – – – –
cc211635-99da-5a06-b01e-90521ae4bfb0 | note | VERIFYING DOCUMENTS: This Checklist
47ef8d8a-53dd-55cc-9517-daea42bc373b | note | – – – – – – – – – – – – – – – – –
e733808a-0dbc-596e-aebf-f8aab43194cd | date | Date Completed:
| checkpoint | 4 - Packaging Inspection-Birth Certificate
2a7681ca-5cfe-55af-b0d4-ec1b11020bff | note | ACCEPTANCE CRITERIA:
d4481b27-a6a6-5560-823c-2ef9cda2ac8a | note | • Is the delivery accompanied by Precast items Birth Certificates?
8002dc21-1eb4-566d-accb-7276922a7e5b | note | • Precast components are to be marked on the birth certificate.
aae48f17-e47d-548e-a983-619de2b00734 | note | • Cast date and lot are to be marked on the birth certificate.
d074f40f-10ac-546c-a47f-4adf571e9edc | note | – – – – – – – – – – – – – – – – –
2a2b9e50-7e45-5d2b-a697-e5beca6b95fb | note | METHOD: Document Review
a8c0ea8a-23e2-54b9-9cea-3d905ee9ad02 | note | – – – – – – – – – – – – – – – – –
3d08238d-47d4-545b-b372-bb673060895d | note | FREQUENCY: Each Precast item
94450fb1-4c26-53a6-ba09-55771f8e0ed0 | note | – – – – – – – – – – – – – – – – –
96ff9385-c26e-5c92-957e-6d8eb8eb70df | note | CATEGORY: IP
d6a9e2ec-da0b-5643-ab2a-26a7ed71d4db | note | – – – – – – – – – – – – – – – – –
e1deaa13-56ea-5955-b219-8ad681673d91 | note | RESPONSIBILITY: PE/SE
c62e72d8-61ba-5575-b7c7-2ee06411258a | note | – – – – – – – – – – – – – – – – –
408bf047-21bf-5139-9c5d-0e1f19264394 | note | VERIFYING DOCUMENTS: This Checklist
0ffaf530-3fff-5b03-b707-b9a3819ebfa2 | note | – – – – – – – – – – – – – – – – –
a90ed40d-6af4-5d67-bb71-5138a8fcbaad | date | Date Completed:
| checkpoint | 5 - Packaging Inspection-Transport
56ecfda4-718a-5681-b017-b631157b84c7 | note | ACCEPTANCE CRITERIA:
6b59c57c-23a9-5d9c-9798-f191b7ae612d | note | • Is the condition of packaging acceptable.
8ee2cecb-6f4c-54cd-9155-bed05c5f53d3 | note | • Precast items are protected from damage during the transport
322e8bdf-b70d-5273-a8d8-2763506e3764 | note | – – – – – – – – – – – – – – – – –
ff67cd7f-e168-5370-adc4-588c98d5a1bf | note | METHOD: Visual
1acf9516-e1f8-5012-8802-dee4e265109b | note | – – – – – – – – – – – – – – – – –
83c7b5f1-47d9-540e-8c4e-1d0fc1a34c9b | note | FREQUENCY: Each Precast item
b4283930-0b52-5a64-9756-34548f987351 | note | – – – – – – – – – – – – – – – – –
5268a7c4-9515-5204-8d46-73a007105002 | note | CATEGORY: IP
d6882759-d191-56e1-ade0-14a05483af07 | note | – – – – – – – – – – – – – – – – –
4591baa1-e954-5650-8c34-eddc93e2564d | note | RESPONSIBILITY: PE/SE
8116e11c-008f-5688-afc9-3cb491e8c5b9 | note | – – – – – – – – – – – – – – – – –
a0740bbb-e6dd-5b57-acb9-bff3729489a0 | note | VERIFYING DOCUMENTS: This Checklist
2dccbe44-7cb3-5dc7-9ac3-a20ebe8d74e3 | note | – – – – – – – – – – – – – – – – –
9f52efd2-21ba-5818-b4fd-75674ccacc36 | date | Date Completed:
| checkpoint | 6 - Fault IDs:
cef238d6-5c6f-550c-88a7-58e004654303 | note | ACCEPTANCE CRITERIA:
4f48e937-57df-57b7-9c1e-fc165e780826 | note | For each precast type delivered, check for the following:
a59cc754-7e6a-51a6-8f4e-77d313007bfc | note | 1 - Identification markings match the panel type
d522f9c2-362a-580a-b0c7-faf17fd6bfe8 | note | 2 - Panels fabricated as per drawings
74ec8e7e-319f-56d5-a6a0-cbe7db10eb71 | note | 3 - Cracks
55b6f328-5801-593b-9463-06399c5906dc | note | 4 - Spalling/Damage to concrete surface
812157e1-ca2c-5a54-99d8-1d647fd37775 | note | 5 - Exposed Reinforcement
5ae7f3a3-4d52-5c54-a05d-8390778b92db | note | 6 - Damage to Anti-Graffiti coating
a526de2b-9271-5cd5-91b3-89203110cbe9 | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
2965dd20-3081-5efd-85ea-3f43d9233e8a | note | – – – – – – – – – – – – – – – – –
6d46abf9-9d1e-53cf-8b0e-51eb86ef55a1 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 1
a8a4a087-c64e-5618-9144-dd4cddb1e805 | note | REFERENCE: Item 6 on this Checklist
c3fa6549-a783-546c-a10a-cf3df1e21627 | note | – – – – – – – – – – – – – – – – –
9275fc6a-f433-5c5d-83f5-130113b212a3 | note | ACCEPTANCE CRITERIA:
813e2a2f-99f7-58c9-adbd-0622532f8c73 | note | For Each Precast type delivered:
9df27243-4a23-50c6-afe9-d34dada6ccd1 | textbox | Enter: Panel Identification:
16e93610-a04c-521c-8b4d-303bfd082d86 | textbox | Enter: Quantity:
c66c2cc0-87d7-569a-be49-eaf51ad9553f | textbox | Enter: Fault ID if any:
1108a98d-a019-5750-a215-5532512f1799 | note | – – – – – – – – – – – – – – – – –
0f148067-53ec-5a73-88d0-a490f9a4accf | note | METHOD: Visual, Measure
425734c6-f35a-5d49-b16f-b7df4e6a7934 | note | – – – – – – – – – – – – – – – – –
d474eefa-34ed-5822-ac17-b49994d3b3b0 | note | FREQUENCY: Each precast type delivered
d2349433-dbd4-5d83-9680-eff2c74bc8a6 | note | – – – – – – – – – – – – – – – – –
ad01b4e5-9788-54eb-b04a-0691bf1a9298 | note | CATEGORY: IP
932b5eee-d44d-51fa-92dd-7d5048174bab | note | – – – – – – – – – – – – – – – – –
b7b394c0-7e37-5b03-b6d3-b25920d0010f | note | RESPONSIBILITY: PE/SE
6f53b868-9796-593a-a2fb-773ec9ea673e | note | – – – – – – – – – – – – – – – – –
5feaa888-10d4-5854-91a7-d97b60fa2a78 | note | VERIFYING DOCUMENTS: This Checklist
4f62c0da-4de9-58ea-b629-b7f42523dcaf | note | – – – – – – – – – – – – – – – – –
4006c81d-15dc-5548-bfcb-54679a79b22f | date | Date Completed:
| checkpoint | 7 - Check for Faults - 2
f07aeae9-7223-55f2-ae87-4a40daea0545 | note | REFERENCE: Item 6 on this Checklist
6a055545-62cb-5c4a-b6de-95767e0932cf | note | – – – – – – – – – – – – – – – – –
1978fc90-3763-5606-87aa-fcd2b8708603 | note | ACCEPTANCE CRITERIA:
ef62d64f-d158-5a9c-992b-8e1f0729d9b7 | note | For Each Precast type delivered:
0ea5f888-a04d-5d0b-90ce-2348047d3300 | textbox | Enter: Panel Identification:
5204f43c-feec-5cb8-b41b-2258340d0165 | textbox | Enter: Quantity:
952bf077-dbc6-54dc-b294-42dd17fbec2f | textbox | Enter: Fault ID if any:
71fbb545-7c18-53fc-8a6f-92b5b29049b2 | note | – – – – – – – – – – – – – – – – –
b6519440-e62d-5beb-8da5-d9310f3cac56 | note | METHOD: Visual, Measure
d62ac89c-231c-57cb-bbda-4815fd2c64c0 | note | – – – – – – – – – – – – – – – – –
11c7e122-b43b-58ec-b540-ea2925066e7d | note | FREQUENCY: Each precast type delivered
4ae7d4f0-9c6d-5286-96f6-b117d71879a7 | note | – – – – – – – – – – – – – – – – –
7fa11b9e-ca58-59d9-b1d0-4f1804805569 | note | CATEGORY: IP
1ca45c9f-10f4-501b-aedd-1bcd8772a241 | note | – – – – – – – – – – – – – – – – –
d9fa76c6-3ba1-5653-b91e-7562dd0c75c0 | note | RESPONSIBILITY: PE/SE
5e1ddcca-44cd-5d63-aef6-e0b87ecc8f52 | note | – – – – – – – – – – – – – – – – –
b3be098b-970b-5636-b912-ff7a666146a3 | note | VERIFYING DOCUMENTS: This Checklist
9eeaf66e-3bb0-5f7d-8813-b1984d15a14b | note | – – – – – – – – – – – – – – – – –
0f4dd411-229d-5716-9ba0-4d0b55d9e68b | date | Date Completed:
| checkpoint | 7 - Check for Faults - 3
2d87ef1c-8f60-5c7f-864b-17728689403b | note | REFERENCE: Item 6 on this Checklist
790ca294-6b64-56a6-a12f-c0656767da4e | note | – – – – – – – – – – – – – – – – –
6b5345a7-ff31-5419-ac33-24d8f80a847a | note | ACCEPTANCE CRITERIA:
8e0d1eb6-d670-5fb7-836d-df17d6fa9cac | note | For Each Precast type delivered:
a913e891-6641-5028-b4ef-b66f9f2aa94d | textbox | Enter: Panel Identification:
41d2ff53-0760-586e-bb74-8417af85be48 | textbox | Enter: Quantity:
9e7ff219-81c8-575d-a2fb-53b2adfe6cc9 | textbox | Enter: Fault ID if any:
7627461e-6f66-519e-a773-ee4478b89ef1 | note | – – – – – – – – – – – – – – – – –
3e096089-5811-52f4-bdaf-58b2cd047136 | note | METHOD: Visual, Measure
3cbea1cc-4f27-5a04-9549-93a1986c20fd | note | – – – – – – – – – – – – – – – – –
1387ba6c-268f-5ead-ae8d-a85578a32c38 | note | FREQUENCY: Each precast type delivered
815cbfb0-50d0-59fc-b772-090087d3b088 | note | – – – – – – – – – – – – – – – – –
e2c1c86b-0e35-529f-bc4f-9703a924dfcc | note | CATEGORY: IP
c0abfb4f-9956-5eea-8e57-c4353d798ea9 | note | – – – – – – – – – – – – – – – – –
10a66208-b658-5abe-9b58-1c8f185d2c20 | note | RESPONSIBILITY: PE/SE
2b2282bf-106a-53f7-928d-2172be60b736 | note | – – – – – – – – – – – – – – – – –
bbda3e97-eaca-59fc-956c-e1bdf549f50f | note | VERIFYING DOCUMENTS: This Checklist
f8f0f1de-c021-554a-8317-49ff73c83163 | note | – – – – – – – – – – – – – – – – –
6bbfa326-4c76-56d4-852a-3dc49a787749 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 4
354db6dc-6974-5527-8fe9-1761b182816c | note | REFERENCE: Item 6 on this Checklist
49482c2f-45f4-58e8-bbc4-e9262dc95407 | note | – – – – – – – – – – – – – – – – –
997abe63-2d43-5f18-be6f-0a94fc5eea9b | note | ACCEPTANCE CRITERIA:
312a903e-a072-5ea7-9697-c960e018cfa5 | note | For Each Precast type delivered:
da2c7c98-7ade-5a67-9dfc-6db2206cc420 | textbox | Enter: Panel Identification:
10cf4eb6-3405-5676-b0b2-60762439a730 | textbox | Enter: Quantity:
f90fc5d1-e2e3-5d95-a6b7-3e69a5a7ce48 | textbox | Enter: Fault ID if any:
5f48a64b-7e1e-59d6-8d0a-d4e9e878021d | note | – – – – – – – – – – – – – – – – –
cd46ec4e-c38e-5876-91c3-8114ebf0f307 | note | METHOD: Visual, Measure
32cdd89c-7559-55ad-b6c4-d109068b566d | note | – – – – – – – – – – – – – – – – –
8219af12-3336-5a70-a271-0f83a2741fe8 | note | FREQUENCY: Each precast type delivered
9857d3f0-1159-52cd-9ad7-19c4f4cab54e | note | – – – – – – – – – – – – – – – – –
56b96a14-5b78-5714-9dfd-0e8a381eded8 | note | CATEGORY: IP
5549fc18-a277-560f-b0c4-509d13afdbba | note | – – – – – – – – – – – – – – – – –
427a5cee-4d45-5074-a58a-d1f52abb5c07 | note | RESPONSIBILITY: PE/SE
72148379-34cb-53c4-8d34-8a90d5e0cc7d | note | – – – – – – – – – – – – – – – – –
3d881835-44b8-589e-8466-8a7469492952 | note | VERIFYING DOCUMENTS: This Checklist
8e880aa1-e27a-58aa-ad11-68b34950efa1 | note | – – – – – – – – – – – – – – – – –
ed9caf5a-6463-5e3d-aa01-f50aa535ecca | date | Date Completed:
| checkpoint | 7 - Check for Faults - 5
47888e0d-d607-5104-9b75-47c945ee2270 | note | REFERENCE: Item 6 on this Checklist
b36823e1-2f11-5d72-83f0-82c81623552b | note | – – – – – – – – – – – – – – – – –
04d0e2ca-3844-5cc8-9fa5-cfa4e1c5b83e | note | ACCEPTANCE CRITERIA:
43b40a23-44f8-550d-a1f8-8730597c762d | note | For Each Precast type delivered:
0abf1b8e-05e5-5830-8835-b7e2375a64d3 | textbox | Enter: Panel Identification:
cc9f462a-6d43-5004-a154-079841b578d8 | textbox | Enter: Quantity:
ae4d8888-70e7-5cd3-a39d-b071160a0469 | textbox | Enter: Fault ID if any:
341c7ab1-e6bc-5432-b05a-b89e39c9ba6a | note | – – – – – – – – – – – – – – – – –
249776ee-0a73-577d-958c-f3cb013335b5 | note | METHOD: Visual, Measure
bda34787-ad9e-5329-8c6f-c323e800d32c | note | – – – – – – – – – – – – – – – – –
90d403d9-19ca-5c51-94ab-f83737f775f0 | note | FREQUENCY: Each precast type delivered
cf35e0de-2d92-5a93-9060-b6a0270a4f20 | note | – – – – – – – – – – – – – – – – –
c4e24de9-b78d-5b73-b2ea-d9058b4f8897 | note | CATEGORY: IP
7db5d3c8-13ef-54fb-bdf9-47c54d1bcc36 | note | – – – – – – – – – – – – – – – – –
527055f2-ee0d-5507-80cb-4206d0058f24 | note | RESPONSIBILITY: PE/SE
460ecc90-04ed-5102-a7eb-1b1ea1237cc7 | note | – – – – – – – – – – – – – – – – –
229ac313-57e6-5d4a-a083-d244e16fd660 | note | VERIFYING DOCUMENTS: This Checklist
baea465d-b7f0-5602-a5fb-a21847896353 | note | – – – – – – – – – – – – – – – – –
055cd4cb-c1ad-5841-a4b6-f769b4750f49 | date | Date Completed:
| checkpoint | Final Inspection
3f78dd43-87cc-5048-8b2a-748801709492 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
fc6eb294-38c6-5f28-b8df-227c405d5b55 | textbox | Name:
b95ff21b-3cda-5b53-b6ee-9d0d60d2db9c | textbox | Position:
d77b3e99-6ffc-5997-8edd-b221a471e9ae | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-008-CIV-Stormwater Drainage Supply & Installation Rev 0 | itp | ITP-008-CIV-Stormwater Drainage Supply & Installation |  | f0057fe0-c8e4-484c-80e0-9ef7aa4b232d
| section | 1.0 - Referenced Documentation
| checkpoint | Referenced Documentation
e2751394-2957-525f-b752-cd15f3e93bee | note | Document Title: ITP-008-CIV-Stormwater Drainage Supply & Installation
5019af8e-450e-5050-9bb2-cd6c42de5ef5 | note | ITP Description: Stormwater Drainage Supply & Installation
172f3998-4372-53a2-a02b-2e90fa989d1a | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
046a2a61-0ee1-5330-b5bc-65f69d82c49a | note | Discipline (e.g. CIV/STR/RAIL): CIV
4ad1f441-8313-5241-86b4-5bb4474713fe | note | Revision Number: 0
384b60d7-b146-5da2-a856-88c9d9ef3c3a | note | Revision Date: [Date of approval]
73c335ba-638e-5b45-9ac4-d99100aa5118 | note | ITP created by: Jon De Castro
296996d7-91fd-5df7-a787-2d4629431844 | note | ITP approved for use by: Aldrin Guinchoma
91595832-721e-5119-ae8a-d28c10ba08e0 | note | 1.1 - Non Dependent
b146aa0c-1173-5045-83e4-36d2901ee8da | note | Reference Documents: VicRoads Section 701 (May 2020)
94bac89d-2576-5a14-96b6-f196f0de95c9 | note | Acceptance Criteria: N/A
e4ed74af-684a-51cf-908b-0deb33078edd | note | Method: N/A
9a027dd9-91ba-5d2b-b96d-009adf96567e | note | Frequency: N/A
340d6721-def1-50a3-abb4-c51cc399fb1d | note | Category: N/A
449581df-0a10-5d08-953c-7e3c70046e44 | note | Verifying Documents: N/A
4bc2b308-8c13-533a-bc48-602f09c8f6a9 | note | 1.2 - Non Dependent
64360c7e-b6cb-58f2-83cc-41a1562d95aa | note | Reference Documents: VicRoads Section 705 (June 2021)
257f28e8-437f-5aea-a9bb-ed5a7b97e8a1 | note | 1.3 - Non Dependent
51272973-df6c-5283-8e84-e03d6fe6e451 | note | Reference Documents: IFC Drawings
861f54ae-12f4-5da0-bdfb-516cef8f6498 | note | 1.4 - Non Dependent
b9d149de-1927-5fdd-8c27-d40776fdabaa | note | Reference Documents: CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
1396c4ce-335b-5b9b-ae1c-e665b2e91b77 | note | 1.5 - Non Dependent
b2fff9aa-850f-53bd-add0-e0d44437e8e9 | note | Reference Documents: CHK-002-CIV-Stormwater Drainage Pits Installation Rev 0
| section | 2.0 - Preliminaries-Materials
| checkpoint | 2.1 Drainage Reinforced Concrete Pipes (RCP)
72dd290f-837f-55cc-bf3b-c55c6792532b | note | REFERENCE:
b40fed04-6b40-5613-8d60-834bac321bb1 | note | • Section 701.04
98e98bdd-a9a6-5be8-8ccd-274a17ff2996 | note | • Section 701.05
344ff1da-7654-5c00-bb93-6d2216a891d6 | note | • Section 701.09
11c9af9a-5e28-578e-905c-56b2abc3e07a | note | ---------------------------------
2b0c7c20-764a-562a-940b-fc7ace7496fe | note | ACCEPTANCE CRITERIA:
a40b56c2-df35-5041-83a3-13a3c183ac80 | note | • Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and Sections 701.05 & 701.09
6aee0c3f-7898-5bf8-ad4b-cdb07916bbd0 | note | • Precast reinforced concrete box culverts shall comply with the requirements of Section 701.04
cda608e8-9a71-5970-a53f-084af8a5ad31 | note | • Rubber ring joints shall comply with the requirements of AS 1646
dc6fb512-378b-56a9-9222-8257568a81a1 | textbox | Enter: Teambinder Material Approval number
8e9ca2b8-be43-5b28-a718-d10196777443 | note | ---------------------------------
1fae7860-71c3-55bb-ad05-26274ff95d79 | note | METHOD: Document Review
36d6ee04-2dc6-56d7-a667-2a1384d214cd | note | ---------------------------------
e9ef7a52-186d-513b-b0dc-bd2ec1e5163c | note | FREQUENCY: Each lot
247263c0-6668-5b0d-9172-54f76c6c6edd | note | ---------------------------------
a1c990ac-0d23-5d4d-abe3-3da3063fb6c1 | note | CATEGORY: HP
f8f2e736-2e91-5c4c-96dc-8e96e1f32801 | note | ---------------------------------
39700d8d-a5cd-5848-b825-1dacb76a395c | note | RESPONSIBILITY: Nominated Authority
9f51a136-3f27-5f83-8258-406f04c4b7d0 | note | ---------------------------------
68c7eee8-569d-5236-ba91-6a0e43aa5fa8 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
50bdf263-5863-55fc-a4bd-957d81ba3c17 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Drainage Flexible Pipes
74632b10-4d0d-55b2-b026-a145b877657a | note | REFERENCE: Section 701.08
a7fc5cf8-dbe3-58a4-b6e4-471090697a38 | note | ---------------------------------
adf9f13d-323a-5212-94a1-aafd73f6fceb | note | ACCEPTANCE CRITERIA:
543e0cfa-287b-5ea7-9b32-27c73e0753a5 | note | • Flexible pipes shall be supplied in accordance with 701.08
17bc7a1c-0736-5058-a6bf-1f1f0742943f | textbox | Enter: Teambinder Material Approval number
817618f7-1658-52b0-bfe1-c9aa134839ac | note | ---------------------------------
837d8eaf-5751-5a78-817a-7c21618a16dc | note | METHOD: Document Review
b6e796b2-9a7a-57b1-9138-5d1bbb4ca446 | note | ---------------------------------
e77996f8-d4b1-5cc1-802d-0292c343e87d | note | FREQUENCY: Each lot
35c33040-a2f6-56c1-b2e0-4cea343d982f | note | ---------------------------------
639c70b9-886f-58dd-ade9-e449c110d2d6 | note | CATEGORY: HP
98c15e25-c9c9-54c4-b803-a1172126e4e8 | note | ---------------------------------
de577255-0edd-506a-8684-9075564b54ca | note | RESPONSIBILITY: Nominated Authority
49b7d6aa-8bca-5302-aea3-aed2dd02e2fd | note | ---------------------------------
ff81cd81-14d0-5ba0-b3aa-b499ee63244f | note | VERIFYING DOCUMENTS: Teambinder Material Approval
5b40e90c-cbde-5e08-8cef-d1bf8e7198c7 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Precast Drainage Pit
3fa0aa0f-3654-53b1-95e7-e835c3b9d8a9 | note | REFERENCE:
25440711-896e-5641-8139-236b4990e065 | note | • Section 705.07
7fa67d8f-a1b0-57fc-9c0b-ab13bcb7cc46 | note | • Section 705.04
fbb2fd70-a471-57a9-8309-49288930bfcd | note | • Section 705.09
7913efe1-067a-5eb8-b434-c2cce846b0c6 | note | ---------------------------------
d0c7518e-795a-5b6b-97e6-83068391d03d | note | ACCEPTANCE CRITERIA:
cbedd37f-4f0b-5baf-b0a1-421932cb0e03 | note | • Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
5aac7492-a3be-5911-bf7b-c6a1905831b4 | note | • All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
ec7b98e7-ccd9-5762-980b-4fa79177fb8f | textbox | Enter: Teambinder Material Approval number
ee4e8ff5-348a-5019-863b-8b683ef540a8 | note | ---------------------------------
aa19b129-af88-56dc-96e9-fa75c13f0330 | note | METHOD: Document Review
7b82fcba-f576-541b-bd63-9f0cba858232 | note | ---------------------------------
b6375994-d9e1-5f5e-9836-4dbec8764120 | note | FREQUENCY: Each lot
fc1a170a-c961-540e-884a-315bc1a380dc | note | ---------------------------------
ae5a3819-e6e8-526c-884c-39bba251a6ac | note | CATEGORY: HP
60189a5a-7b63-5d01-83a9-6122b149ece5 | note | ---------------------------------
2d028e7d-af87-5a9f-82cd-f51f2dd5ced0 | note | RESPONSIBILITY: Nominated Authority
ec465bf5-5e4b-557c-830e-c7d3570135c9 | note | ---------------------------------
90b1a268-19bd-5742-a620-60ba29befa23 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
5696ace7-acea-5890-a748-f8bb814833ac | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Cast in Place Drainage Pit
90301796-48c9-5307-93dd-0b2c24e1e5a6 | note | REFERENCE:
d32dde1f-0bef-5c14-9594-bdefb5005b12 | note | • Section 705.06
9f6b36d2-b3a8-58cf-b6d1-caa407526fa1 | note | • IFC Drawings
29239391-3d09-53e3-94d6-2342bd1b2e8c | note | ---------------------------------
179ca199-6f23-528d-87ee-4b169f58d298 | note | ACCEPTANCE CRITERIA:
3a261e5a-ee13-5c83-94a7-216b436379ee | note | • Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
eb05070e-f6e1-5fdf-b6aa-692852f8efe6 | note | ---------------------------------
a3eeb1b6-98f4-5601-b509-8c7e7804a9cd | note | METHOD: Document Review
2447fd27-2168-5814-9cd8-ec071f9ef28f | note | ---------------------------------
55cfbef8-31f1-5cdd-b047-86e60e3c9a24 | note | FREQUENCY: Each lot
3d84a244-333f-53c0-85b9-78cbce98aef1 | note | ---------------------------------
578ae35d-16a7-5397-96a2-a5a2851f0a96 | note | CATEGORY: HP
1c40ba4d-db0f-57e4-8b31-be58ea1caa65 | note | ---------------------------------
6c24d75a-3e53-55ff-84ea-3dbac70469bf | note | RESPONSIBILITY: Nominated Authority
cb6b5aac-5409-5417-a934-811072fc1add | note | ---------------------------------
8b68dbf4-5ebc-56d1-928a-c2162e0beb01 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
633abd7e-78ec-5cc8-b0d4-16eaf6397ed0 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.5 Drainage Pit - Step Irons
686f6058-be99-52db-8238-1e8179e6a39f | note | REFERENCE:
4d856409-8bd6-5b83-ad2f-7d6c4e727559 | note | • Section 705.04
e8af6840-5858-58ee-92c1-8f064a9e1d93 | note | • Section 705.12
93584fc6-7d99-58e4-bddb-dc2433650371 | note | ---------------------------------
91d990cb-12f1-57e6-b300-69633f42166c | note | ACCEPTANCE CRITERIA:
aaedf0ec-4477-51a1-a3c3-27089038ec6c | note | • Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
0ee6b4b8-6c20-59fb-ae6b-b016d11f4f08 | note | • Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
00a03e3f-a75e-5ea8-958e-43d53d005200 | textbox | Enter: Teambinder Material Approval number
75db50e3-a3df-50f6-8910-2bf5f23c241a | note | ---------------------------------
3d91385f-1a44-5b19-b521-46b45340fa9f | note | METHOD: Document Review
557bbb07-c9e8-572c-8e3b-7afaf630d9ee | note | ---------------------------------
f85923aa-ce1b-5b4f-9407-4402b4faa1fc | note | FREQUENCY: Each lot
f491e346-ba19-5481-87d2-9eb2c0bb1485 | note | ---------------------------------
f7422b37-791a-53d0-94eb-d935e5df7c50 | note | CATEGORY: HP
5cc66eb4-216f-5b93-a323-fce1d4b8963f | note | ---------------------------------
2209f915-d607-54b3-88be-8278724c2ff3 | note | RESPONSIBILITY: Nominated Authority
9cc290ca-c270-5b8c-8663-bec5347d0d15 | note | ---------------------------------
c49db9df-28ba-5e0d-82de-a9f22ea0c5ab | note | VERIFYING DOCUMENTS: Teambinder Material Approval
817b6f0a-ce4c-5671-bc7a-a6e5bbdd8726 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.6 Drainage Bedding Material
3b556434-e477-54d2-b1d1-7a88179818ea | note | REFERENCE: Section 701.09
b27a2c85-1d4e-5562-b15a-9d3389539b62 | note | ---------------------------------
d0f8924f-168d-5319-97ca-deb72c0c9de3 | note | ACCEPTANCE CRITERIA:
17e61d0e-3e91-5c9f-a7b9-3e474eee8e06 | note | • Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
0e5360ca-5dee-5a18-983f-1fc8d0ccff95 | textbox | Enter: Teambinder Material Approval number
042933ba-2af5-57ae-8a55-b79ac51e0957 | note | ---------------------------------
e167d2b7-c37d-54cb-abe2-fd8bb7e96d45 | note | METHOD: Document Review
a1fad11f-1f34-5c4c-9a00-3492e0c597b4 | note | ---------------------------------
abb01105-0742-5c45-95c2-ac3cd7f43faa | note | FREQUENCY: Each lot
655ab0e2-88d1-5b32-b272-dabf46a9a8f2 | note | ---------------------------------
b35d3f3d-56c2-5d8c-9451-f86a8d519371 | note | CATEGORY: HP
080f1303-d61c-5d59-a97a-94882ef424a0 | note | ---------------------------------
c7f1f432-852b-5f95-9918-9ab8f8fd6a36 | note | RESPONSIBILITY: Nominated Authority
88775c85-8a25-58ea-a97c-5d630e270aa2 | note | ---------------------------------
663edf75-9bff-5b25-8bde-436300070a1f | note | VERIFYING DOCUMENTS: Teambinder Material Approval
92178d96-9d01-58a9-9b1e-9d78e761c0c6 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.7 Drainage Backfill Material
2a3108e2-1b4d-5820-b7eb-c2996d1cca43 | note | REFERENCE:
fc3c85be-c6e3-5c84-ad09-7b980b7d4183 | note | • Section 701.09
24e1d0f2-425f-5830-9ac7-e6547d64381c | note | • Section 701.19
27265410-0ba9-5cda-9875-7095aa411b4c | note | ---------------------------------
f60e378b-03d0-5f53-b414-f86cab31f286 | note | ACCEPTANCE CRITERIA:
2d8de61c-ae75-5f07-9171-aa922e19bdf0 | note | • Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
455b3605-80b4-59e2-a444-1690737d651f | note | • Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
c5861fd6-e5eb-5d4d-854d-22e695fb7ed7 | textbox | Enter: Teambinder Material Approval number
4a392498-198c-5889-9123-66992ad5b393 | note | ---------------------------------
e8919ef5-e9f6-533d-80b6-689169bdb7fc | note | METHOD: Document Review
cd265166-e4f9-538e-af3c-a22790cd8765 | note | ---------------------------------
8c75de63-a7db-59ee-b6af-90b7cb014034 | note | FREQUENCY: Each lot
81c79b49-dacd-5c81-a2e5-2c359424fa50 | note | ---------------------------------
84872e85-7a9d-5586-b9aa-9033abd780e7 | note | CATEGORY: HP
2acbaa76-7c19-5093-b234-e1cd3fa72639 | note | ---------------------------------
ca8bf2e0-3536-5fb8-abd1-22545ce216a2 | note | RESPONSIBILITY: Nominated Authority
b35beef5-a3ac-58b2-ad7e-d1f4e55ea944 | note | ---------------------------------
4cc41ffc-2bee-572b-a742-6aeebb04e585 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
67e17d2f-a210-5871-bffe-13a1a9e1884e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | 3.0 - Preliminaries-Documents
| checkpoint | 3.1 Subcontractor ITP (where required)
4911583c-93fb-50b5-90bc-8fb7134adfc7 | note | REFERENCE: Subcontractor ITP
b27a6cf9-e4d0-5eca-89eb-62cfd02ca5b7 | note | ---------------------------------
947402dd-909a-544b-9006-f19d712ccba8 | note | ACCEPTANCE CRITERIA: Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
7fd5184f-d403-54a1-bf39-62ef944cbdb5 | note | ---------------------------------
61c2ace9-9865-527b-a9a1-48ab3ec95fc1 | note | METHOD: Document Review
d5d7fcd2-4259-5d1a-830d-2347f5cc2f6a | note | ---------------------------------
529b37b6-c0d5-5e32-911b-a21eaf550ff8 | note | FREQUENCY: Each Lot
ce562711-8d44-58c8-87b8-b9bdc481ff36 | note | ---------------------------------
e2d703cc-9d58-5284-a17c-77dd05dd377f | note | CATEGORY: HP*
a5fb7c65-4553-5b66-8ae5-ec498bd0b5cd | note | ---------------------------------
c3af47a3-5832-5b02-96d9-65a66d8279be | note | RESPONSIBILITY: PE
b422fd10-14f2-58ed-a579-d90c0f8fbad4 | note | ---------------------------------
d4df0739-d035-5cba-b797-034b9f5cbd24 | note | VERIFYING DOCUMENTS: Subcontractor ITP
9c14985f-bb42-5b07-a893-5772e3b29b43 | date | Date Completed:
| section | 4.0 - Pre-Construction Activities
| checkpoint | 4.1 Survey Set Out - Pits & Pipes
f5ba4c92-cc56-54f1-93cd-82da408a1099 | note | REFERENCE:
d012c4a9-46ad-567c-9376-62731d8a86b7 | note | • IFC Drawings
7196cbdd-aeee-5b1f-8d4b-2ab9f7c49ec3 | note | • Section 701.10
fa558275-abca-52fd-80b4-b8cd7e1bbbf8 | note | ---------------------------------
1ca25bbe-f672-5b46-a588-020f6cf83c95 | note | ACCEPTANCE CRITERIA:
d11320fd-309c-5134-a390-3aa3c0350691 | note | • Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
ad8abb4f-53cf-534e-8cf3-ef8ef160b6cb | note | • Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
e9a8a5a9-8020-5be6-9a37-211601238514 | note | ---------------------------------
1b31f3d2-7587-5b30-aa7d-b2f0b8dced6d | note | METHOD: Survey
cc658ed6-675a-5790-aabd-003421d47e5d | note | ---------------------------------
1178068a-96f7-53a8-a9ae-93b90d4c80f7 | note | FREQUENCY: Each Lot
880ed773-b9a8-5779-a571-f084df55c4c5 | note | ---------------------------------
11d65277-f8e5-5097-b39d-98d3c5708271 | note | CATEGORY: HP*
6d620ee5-0d15-5a80-8aa3-a8affd9bfeee | note | ---------------------------------
8293ff39-44e1-58e6-a454-5028fc97ccf5 | note | RESPONSIBILITY: PE
a6d5aeec-bc8b-5323-ae46-3279c5532d30 | note | ---------------------------------
fbccf4c4-0d12-56b5-91b3-cd0a75e016d9 | note | VERIFYING DOCUMENTS:
7b9bec99-d0d0-5727-8d10-c7b39e7f7dd0 | note | • CHK-001-CIV-Stormwater Drainage Pipes Installation
999708a8-e016-55f2-890b-75999ded1f21 | note | • CHK-002-CIV-Stormwater Drainage Pits Installation
666545f8-f8ba-5137-880c-aff036702ebb | date | Date Completed:
| section | 5.0 - Construction / Installation Activities
| checkpoint | 5.1 Pits - Excavation
d9090fdd-20ad-574e-8465-0fc76d6f5392 | note | REFERENCE:
b2fb1d38-ad86-57c2-a4fe-4e249c3ba8b0 | note | • IFC Drawings
ff6aab59-1004-507d-b41c-c92389eca0c8 | note | • Section 705.05
07357c1a-ad93-57a1-bcff-53b39d7449af | note | ---------------------------------
6a9ad102-9a8b-5ef0-85fc-72194a727375 | note | ACCEPTANCE CRITERIA:
9723be50-9eb1-5960-89c7-e4d9303ce6e8 | note | • Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
3fd052ce-8ab8-5acd-935d-61bb562d313c | note | ---------------------------------
6bcb8219-be37-5ec4-8596-22d502197a5f | note | METHOD:
ed5836a0-3b4d-57ea-9928-65fda8bd97e7 | note | • Visual inspection
f778cf7b-43c3-55cc-8c6d-5050fa41ea0b | note | • Measure
54c3e994-a8c3-5121-8ad4-0bae986d1312 | note | ---------------------------------
6117072c-8781-5de9-a09c-90055cae3de7 | note | FREQUENCY: Each Lot
6ab9f6c1-74cc-5859-a285-90784ccdc5e4 | note | ---------------------------------
9df2089c-fe42-5439-911a-96de66dcaadd | note | CATEGORY: IP
99ebbc6d-5b9a-5bdb-aad6-64b137d629c5 | note | ---------------------------------
c47408f1-aa41-5ed9-b9e4-fc8a772b29c4 | note | RESPONSIBILITY: SE
17840d3f-8e91-5c48-8a40-caf49203d41c | note | ---------------------------------
9d6156fa-5482-54d7-a75c-08faa1c3b2ea | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
21ce4176-f476-5cb7-b3b4-8786edc6890a | date | Date Completed:
| checkpoint | 5.2 Pits - Placement of Bedding Material
31c53472-11b3-5ea8-90d0-9b6295344c08 | note | REFERENCE:
d1f4ed0a-390a-5d64-8fff-f32bdd169efc | note | • IFC Drawings
8251bb28-f753-5518-a071-24aa07b84189 | note | • Section 705.05
4088c04b-2a32-5f61-8494-4940f767c0b4 | note | ---------------------------------
0c93b7d2-5155-5e6d-bb96-a7b406cbe4a2 | note | ACCEPTANCE CRITERIA:
cfbbc8ec-f843-5872-b19e-ee905ebb832a | note | • Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
7a029243-e41e-5bc5-b5ee-2ac20b5c2aa3 | note | > 80mm for clay foundations
64946dcb-f321-501b-8940-fe690480fb3b | note | > 150mm for rock foundations
1347c019-6ded-56b7-bdda-346edd321bb9 | note | ---------------------------------
acf5346a-8895-5d77-9a26-e9b8a53decb2 | note | METHOD:
783c6881-47e2-546f-99b4-d634d11512fa | note | • Visual inspection
45dc97f8-fc22-54cf-a93e-fb63f5968537 | note | • Measure
c0e3c5ba-247f-5c41-8eef-06312b5a8056 | note | ---------------------------------
e244410e-73e7-554a-8e3d-304bc94691fe | note | FREQUENCY: Each Lot
bbefca17-2c8c-56ca-a1c6-d5ec0f120bca | note | ---------------------------------
afdcaee1-a6b2-5b3b-83c7-9892b89538c8 | note | CATEGORY: IP
9105a25f-7422-549c-9f3c-6e7899512131 | note | ---------------------------------
0a7356e2-7656-5b31-8d08-0582297fe0cd | note | RESPONSIBILITY: SE
c9bf96c4-eccc-58fc-9402-f1d721830cdc | note | ---------------------------------
8eac134a-b2f9-5f68-942e-bf6edc4db7ea | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
0cb20ae2-0cbd-5c45-8651-aab785e419ab | date | Date Completed:
| checkpoint | 5.3 Pits - Bedding Testting
58015304-b47a-5dcb-8e63-1b5366b71454 | note | REFERENCE:
fbb39d7b-166a-5429-9ba6-e3794056d6fa | note | • IFC Drawings
98e08fab-5ef6-5e13-8efc-405449648e42 | note | • Section 701.20
c869aed3-abb5-534e-b11b-a37b84e91434 | note | ---------------------------------
ecc32a69-4377-5963-908e-c1d2d66609ee | note | ACCEPTANCE CRITERIA:
d71a11cf-2663-55c1-9466-4f3436604f19 | note | • Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
04f1304b-0429-5c02-a464-9b94114bac8c | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
3d011ec3-b5c5-5d60-960b-f353bc090509 | note | ---------------------------------
67472862-948d-59d6-9ae3-893190402d83 | note | METHOD: Compaction Test
df4b8302-29aa-5d8f-9fc7-4d668b975e4b | note | ---------------------------------
6b90db13-b6a2-5f68-b7a5-4f74326cb37f | note | FREQUENCY: Each Lot
cdaf2f4a-01fd-50cd-ac8d-e4f025a8bd54 | note | ---------------------------------
48f92296-0c1a-5f58-8c74-25d7b3ebff21 | note | CATEGORY: IP
01636edf-4548-5d1c-a7c9-479b3b299495 | note | ---------------------------------
36c42651-5d48-5a30-87b7-f43235165080 | note | RESPONSIBILITY: SE
62ab82be-7424-5077-b7ce-3cdb53682e9c | note | ---------------------------------
bc13b31b-3670-57f4-b551-d406f28e5f2a | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
4334dded-8720-5ca5-99d1-fcab46763d81 | date | Date Completed:
| checkpoint | 5.4 Pits - Placement of Precast Drainage Pit
fc8fc2d2-523a-50d6-bd8d-24cc8985752e | note | REFERENCE:
6a4bcd2e-35f6-5e24-b510-32a48b630a8c | note | • IFC Drawings
a2bc7f20-2bbe-5d13-b0c5-09248044e7a0 | note | • Section 701.10
4fd3f9ae-f79a-50b6-a149-c8be2d0c2ac8 | note | ---------------------------------
abe61a0e-57fd-5d0f-9c44-4bc2bb6b958f | note | ACCEPTANCE CRITERIA:
1ee6d1a9-d3cb-5cff-bb83-695222db36cf | note | Survey pick-up to verify:
93c14a19-a150-5749-9a13-357eb6769bb0 | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
f25cae3b-fb64-5643-9fd6-da22e4fafb31 | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
c4ce9071-fd21-58e2-bc5d-498600b96446 | note | ---------------------------------
08ec9d15-d893-5ef2-a073-52191af6d8c5 | note | METHOD:
f5f9d7b6-d086-5965-bf5d-29862501fc7f | note | • Visual inspection
f57bbef0-a546-58a5-a633-fedd60ebf00a | note | • Measure
e1f7ec90-d422-5a20-8c36-6868f8356c46 | note | ---------------------------------
55be9116-7b3a-53f1-868b-523c03354ccd | note | FREQUENCY: Each Lot
8192d9f8-1159-5b8d-a6eb-6e3e3c4ecf0f | note | ---------------------------------
2c1cec38-fd99-5bc9-980a-1a49b6cf11f9 | note | CATEGORY: IP
12ae1edf-90b2-5558-b420-7199426444d0 | note | ---------------------------------
7367cf72-0c0e-5bde-9cc9-0efd8cb1360e | note | RESPONSIBILITY: SE
b54cac99-1c84-51ba-a74a-f0cd1e3883f3 | note | ---------------------------------
b25a37a9-ea3e-5f78-97dc-a4aa964fc6f1 | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
88643f05-573b-5120-b5cf-b6717c9425e8 | date | Date Completed:
| checkpoint | 5.5 Pits - Cast in Place Drainage Pit
6a41d046-af65-5037-8980-e1d220046d61 | note | REFERENCE:
480f1597-f5e5-572e-9506-938acafddbf8 | note | • IFC Drawings
78b5d320-b9b7-5d27-924f-8e8251040c13 | note | • Section 705.06
443d4c39-096b-512b-9a77-57ebddcd702d | note | • Section 610
74b91421-f758-532c-970c-d2cc10ef2d53 | note | • Section 611
1cbbf914-680c-5824-af60-ced3bd7c8b93 | note | ---------------------------------
50b697c0-d19a-5729-b33f-4c9bb71c879a | note | ACCEPTANCE CRITERIA:
6d2e4778-e3b9-50dc-bba3-a62361723dac | note | • Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
138b769d-13e1-5533-90f7-b1f61a97b9a6 | note | • Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
850e07cf-4722-5568-86d1-27f2b67b5229 | note | ---------------------------------
ac2da850-40c9-5f26-af2e-35e300fb11d9 | note | METHOD:
aa2b47f2-88f5-532c-94f2-0714686a63fd | note | • Survey
2a7cfc41-3d6e-59ec-a527-bead44b3f325 | note | • Measure
19f81144-3789-576c-8d65-c05e51268bba | note | ---------------------------------
f6786af2-8cd2-59ae-aa68-f6c2e11d5011 | note | FREQUENCY: Each Lot
5f9d7abd-2cec-5cd1-8e34-1d8877bdfb52 | note | ---------------------------------
241381ae-c821-5989-8644-3a5e65096baa | note | CATEGORY: IP
8e8aa289-4a2a-5f07-8504-139d01468310 | note | ---------------------------------
8d879b05-c46f-5380-bf4e-a9db394761e9 | note | RESPONSIBILITY: SE
913053a1-49f8-52b0-9926-b2bd8294e017 | note | ---------------------------------
73233301-a44d-56a8-b1f8-bd99be4f1d7d | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
f7a6aad5-4a6b-50ae-8575-698f9ec04125 | date | Date Completed:
| checkpoint | 5.6 Pits - Jointing & Drainage Connections
37a20f1c-dd86-5a5f-8dbc-955d58b44456 | note | REFERENCE: Section 705.11
8ac5cde8-8fad-586f-9a13-c872aa78c138 | note | ---------------------------------
27a806fa-e7ea-5301-a3c9-c77d2a03669d | note | ACCEPTANCE CRITERIA:
737b3cde-62f9-5761-bf7f-80814adeca7c | note | • All connections to drainage pits shall be neatly made in accordance with Section 705.11.
182a0ade-2c04-59d3-86c1-392008fd953e | note | • Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
1bc08f59-49ed-5ff9-871d-f2b2e6ee8f5b | note | • Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
a83a08ed-a1a5-5974-884a-b2c728ab428e | note | • Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
ff05fe47-c5e9-5fc8-9854-8725f04a3d9d | note | ---------------------------------
519bd56b-5f17-560a-b7da-f508f6cf04fd | note | METHOD:
509664a4-ae43-55b1-a57a-261e9a97afdc | note | • Visual inspection
81113ca8-2859-5e49-b107-b0deab2f891a | note | • Measure
367c97fe-3c21-5e9f-ba4c-cec7674d17b0 | note | ---------------------------------
a120acf8-587b-5396-9d04-9b7a0f42ea24 | note | FREQUENCY: Each Lot
be2d93c1-ce9c-56c4-8b28-cca8e101eb95 | note | ---------------------------------
0c664acb-adb7-5b7e-85f2-e62921d77b7c | note | CATEGORY: IP
c5658ad7-1cb9-52f7-9243-df29ac789a36 | note | ---------------------------------
5429ee84-215f-58b9-8284-96ca994e66b3 | note | RESPONSIBILITY: SE
390611d0-7862-5d03-ada4-f8f608a03421 | note | ---------------------------------
1ef9014c-87d4-5e9c-90f0-e180fef5e6be | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
fb493ab1-a11f-5bcc-be4a-6c59d5888421 | date | Date Completed:
| checkpoint | 5.7 Pits - Shaping of Floor
2d260c04-8767-53a7-b1ef-f8e02cbe78e1 | note | REFERENCE: Section 705.13
492b4301-d3b1-590c-922a-76f713b00d25 | note | ---------------------------------
f50f0028-0120-5203-8910-0c4b2395c670 | note | ACCEPTANCE CRITERIA:
3d73c0b9-4cef-5771-84f4-bc2a09f49fb2 | note | • Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
6e0a229f-bf35-5be8-bd8d-ec02c7b7967a | note | ---------------------------------
8493535f-9e12-5a70-b2b8-8043aaa9f7b7 | note | METHOD:
117a3e63-4fc1-5b23-b312-d36205c27915 | note | • Visual inspection
3c591d15-90a7-5e30-b143-e60edcc45a1e | note | • Measure
2e2520e5-16bc-5f50-a8a3-e51c426b9c71 | note | ---------------------------------
d410eecc-49a1-5c40-8472-649ed2b02173 | note | FREQUENCY: Each Lot
0381907f-b328-59a3-b289-4b8ae428475a | note | ---------------------------------
b14e852e-4df1-5b86-85bd-4217b6bda365 | note | CATEGORY: IP
dafebe31-2ed9-543d-bc38-7743bf581d17 | note | ---------------------------------
c8553e28-168f-5cb8-b365-98ecd2591065 | note | RESPONSIBILITY: SE
122ec5c8-4882-5ce8-b51f-584187a6f567 | note | ---------------------------------
7eb7c4ec-f1ed-58e3-bc7d-16c18841dc65 | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
1c778f64-a650-51af-bebd-0142fbab4275 | date | Date Completed:
| checkpoint | 5.8 Pits - Step Irons
6eccb508-780e-5415-9e3d-cc70915ef4d9 | note | REFERENCE:
68980c60-1036-518e-9dd6-795ee4e782c5 | note | • IFC Drawings
a1659860-abd7-5238-a38c-4902ef8b6bf1 | note | • Section 705.12
eed30823-6e84-55b2-9ea5-b9010ed1c62b | note | ---------------------------------
0241ae25-cd02-5144-8134-9921b1172310 | note | ACCEPTANCE CRITERIA:
2a2014d0-bec8-5300-94b4-e48ea40d247b | note | • Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
b65f2e42-5a58-5aa4-87fc-865936f7d0eb | note | • Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
b558c6fc-fe9c-5a7a-b07c-986617df6e65 | note | ---------------------------------
0110630d-54b2-5394-a126-9878236fd338 | note | METHOD:
f052a075-0598-53d2-b2b3-5481f636c2c0 | note | • Visual inspection
695f4266-2cd4-5204-82b0-ee1438525598 | note | • Measure
6deba9e0-af83-58db-86c8-cd93af2e944d | note | ---------------------------------
362b5101-5022-5604-9b84-2288858c376a | note | FREQUENCY: Each Lot
7945e76e-8122-5224-9ad0-a8b5d16cd2f3 | note | ---------------------------------
84a5ed44-3046-5cd7-b6aa-bbc8575354db | note | CATEGORY: IP
22532fd9-60f2-5602-9b4b-9b25e291542e | note | ---------------------------------
fdd309df-22a4-5e2a-98ae-64bc7f9f55e3 | note | RESPONSIBILITY: SE
ab8398d0-9064-57c9-9b04-63a2e9597abe | note | ---------------------------------
c123437c-027d-5cde-ad91-6b1cdbd2055f | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
f5d5a723-4b4e-51cb-bbae-8b8d60de49e0 | date | Date Completed:
| checkpoint | 5.9 Pits - Fitting of Covers
be80c5b3-d487-56e9-896a-3c933721141b | note | REFERENCE:
4fbea3a6-ab89-54a0-9601-d8ca75f18992 | note | • IFC Drawings
4c11ada6-8eff-548e-a557-36fd9f4f09c0 | note | • Section 705.17
91b9d085-2092-5d2f-9a1d-32bd54b21d3c | note | ---------------------------------
613caead-f73d-5c43-9b50-c09753dfdd31 | note | ACCEPTANCE CRITERIA:
08a3f876-d840-58fb-8c99-6ec4ecb97de4 | note | • Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
1b19124d-3855-5eae-b733-afcc5434dce8 | note | • Height shall be within 10mm of the design level.
319dac53-38ba-5592-90f1-67fd8167bb48 | note | ---------------------------------
b68971a4-fc65-5986-a69a-77a1ea51ecb4 | note | METHOD:
71770c54-5b1f-5739-a4a0-10416de0cd0f | note | • Visual inspection
1340edc4-88bd-550b-86cc-cb64ded3807c | note | • Measure
592bd8fa-db20-5acf-a5b2-f6ea7473330d | note | ---------------------------------
4a53ff84-6fa1-5bc9-bd70-dc3d607a2f0f | note | FREQUENCY: Each Lot
14cc3f04-7a89-5143-920a-768d140beb68 | note | ---------------------------------
7add3bc7-b614-5a27-ac14-01b8b38db6d8 | note | CATEGORY: IP
b5f71305-7962-5361-8803-338561dbb1ca | note | ---------------------------------
b680088d-0d87-57ae-8ba9-cf2b889f9504 | note | RESPONSIBILITY: SE
aa2a6998-cc74-5996-9dad-c49e5f867e7c | note | ---------------------------------
a18fb9aa-56ac-592c-8d8f-c75099d7f8b0 | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
ab95933e-5bd4-5d15-8913-baac5207662a | date | Date Completed:
| checkpoint | 5.10 Pits - Pit Lids
4dd1d453-ec93-5971-877a-44c6af8e5a78 | note | REFERENCE: IFC Drawings
87a5342d-db56-51d8-a441-19f5e97cc454 | note | ---------------------------------
654cb06e-1493-54db-b8ec-1e9f2e5b7989 | note | ACCEPTANCE CRITERIA:
0a879cab-526d-5b90-aaa3-1bacf9e0b0f1 | note | • All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
5a21187c-98c4-500f-9615-5384b3ad6037 | note | ---------------------------------
1dd6817d-a12d-508a-8ef3-229af0f7520e | note | METHOD: Visual inspection
fd14c551-cefc-5cbc-bcc2-d51e8ee58010 | note | ---------------------------------
a5cc1c9d-9b86-5050-9e54-fa673f8903a4 | note | FREQUENCY: Each Lot
755bf258-ce9e-58ab-9e62-b9ca4aa31a8e | note | ---------------------------------
fd0f5f9c-17da-518e-8f75-e95a134e593b | note | CATEGORY: IP
42fb48f4-f66d-5395-844a-695be8f9c3a2 | note | ---------------------------------
969bf20c-0ab3-53e9-926e-203fbc5a5225 | note | RESPONSIBILITY: SE
d06b5b78-0645-5bea-9e36-70aad86cd62f | note | ---------------------------------
4617416c-9e4c-5700-b6aa-eaae7c7aa193 | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
bb75bcc6-f642-5501-b0dd-82c0e2475289 | date | Date Completed:
| checkpoint | 5.11 Pits - Backfilling Around Drainage Pits
986238ec-3c01-56bd-a658-83d9783949d9 | note | REFERENCE: Section 705.18
04a3a570-b95d-54ea-84b2-0622a5053c12 | note | ---------------------------------
bea3de94-671a-55e1-afec-4861fafc04b2 | note | ACCEPTANCE CRITERIA:
be70134b-3223-5cac-84d2-b32b615e63e2 | note | • Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
5c37d3a9-30b3-509e-9b58-1eecc138e4ef | note | ---------------------------------
8afcc5c0-7338-5a01-bd9b-34b2cd500513 | note | METHOD:
3560df30-5b49-51e6-9e70-eb93e36545cd | note | • Visual inspection
069c82e4-15f1-5aef-a1ae-165edc02fe7e | note | • Measure
6522f5b5-d725-5dd0-a3e5-47c7dd1fa637 | note | ---------------------------------
28a96f30-e268-5bb4-b89f-cad5f02f0639 | note | FREQUENCY: Each Lot
d6382286-6468-5749-a961-a9d368406880 | note | ---------------------------------
54319fb6-fdfb-5ae9-8d5c-ad2957857760 | note | CATEGORY: IP
f2ac6cab-2280-5ad6-b8d6-44f9edb95bd9 | note | ---------------------------------
83fc22a4-8103-52af-a95d-3812650e5cd8 | note | RESPONSIBILITY: SE
f08696c9-c1d0-55bb-8d53-f9d514d19430 | note | ---------------------------------
f6ec18a8-4a1c-5774-9908-2075269dbedc | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
c4458eb9-7501-55dc-a2aa-7bb34b6a98de | date | Date Completed:
| checkpoint | 5.12 Pipes - Trench Excavation
825fa705-9050-5597-90f3-00bff881b062 | note | REFERENCE:
d4bd3fdc-9c96-5e41-952c-8a4308b6022a | note | • IFC Drawings
ee0781f5-ae46-5154-8436-547d71761da2 | note | • Section 701.15
3a9f162b-651a-599b-91b8-579ff1e4d2b3 | note | ---------------------------------
957645c1-33c5-55f9-bb5e-e54646c2e816 | note | ACCEPTANCE CRITERIA:
ad9ed1c8-00bf-55b7-9285-a37b2d45d6e2 | note | • Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
bff779d2-7e46-5201-98b5-3c0e856b7493 | note | > 300mm, < 600mm for RCP
ee3b641b-51a4-52fd-9a3a-957981544cb0 | note | > 150mm for Flexible Pipe
cbf9b86a-e15b-539c-9d91-19f43511cfc9 | note | • The base of the trench shall be compacted to refusal using mechanical plant.
5aaac2b6-0838-5c9a-b39a-d7bc67b4fa59 | note | ---------------------------------
793e46bd-339f-515d-813d-e40e3973c6db | note | METHOD:
1904dd1e-dd79-540b-b04a-5f2e18cbaeae | note | • Visual inspection
564f4027-936c-5d11-b082-7da0e56b2710 | note | • Measure
59c30003-b4e9-5713-ab4d-2ca8c5a18d1e | note | ---------------------------------
81b37202-ef81-5903-932d-050692d4b07c | note | FREQUENCY: Each Lot
c5955e7e-6d4e-51ac-907b-311690f285f7 | note | ---------------------------------
51ec9f0e-d9f7-5b1c-96c8-a23bd3d9353f | note | CATEGORY: IP
98840b93-f8ac-5dbb-aa05-42c52980d17b | note | ---------------------------------
fee2bc0b-b5f0-55f8-9433-ef788f4a2905 | note | RESPONSIBILITY: SE
e775e3c8-8267-57fb-89e3-44e0e267ffdd | note | ---------------------------------
e99cdd42-60c9-54ce-8379-f73c5e77fb52 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
d2e65ada-36a5-5218-9138-144a7841eda1 | date | Date Completed:
| checkpoint | 5.13 Pipes - Bedding Placement
0e0be699-77d5-51cd-b098-b4006e835eea | note | REFERENCE:
72c6c51f-edea-5fe2-8ea9-2b4ca856cf96 | note | • IFC Drawings
ca0e2abf-3808-5fd1-ab7a-fe69ea7f3241 | note | • Section 701.16
a146065c-4e9f-55e7-a57b-1086b66294db | note | ---------------------------------
69d8c09e-f4d6-5ec1-8423-28e32b7870e0 | note | ACCEPTANCE CRITERIA:
5ff1818c-d783-5de6-90c3-54d9f7625d93 | note | • Bedding material shall be provided and placed in the full width of the trench to the below minimum:
3c9dbd09-5166-52a3-96d1-a89830d5dd9c | note | > 100mm where D<1500mm
3a9c3b3f-cc53-5910-a616-24ca18a5e0ec | note | > 200mmwhwere D≥1500mm
7c45ac09-17f1-5956-a14c-098093c254e1 | note | • Bedding material shall be placed and compacted in layers <150mm loose thickness
d16b5bcc-527e-573f-8521-3db97e74d166 | note | ---------------------------------
5295f10d-38d5-572c-bad4-c6df53d3f0ce | note | METHOD:
4a94a0a7-c2e7-533d-aaa2-d5da8c48983e | note | • Visual inspection
cca4141c-b4ec-5113-9d9e-c4b99012d50f | note | • Measure
711a8490-4e76-57ee-b643-93ab2b893013 | note | ---------------------------------
b36c776d-29d2-5769-9b7a-7d2c5a88459e | note | FREQUENCY: Each Lot
32166b85-6859-5ebf-b1f2-9aa61f9e4394 | note | ---------------------------------
24807a68-53df-5c55-8306-78ba40a324c0 | note | CATEGORY: IP
871f6f7e-43da-554a-b2da-17291b8747c6 | note | ---------------------------------
43832779-2508-5636-97de-a7e598d09cde | note | RESPONSIBILITY: SE
ffc57698-048b-5416-a0d3-6e96858125e5 | note | ---------------------------------
72f9ff23-3b72-5fdf-9dd3-174f16386f5c | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
a4166f13-4e68-5005-864d-72497c2fc716 | date | Date Completed:
| checkpoint | 5.14 Pipes - Bedding Testting
10928101-2b30-58eb-85da-765c8bbc8739 | note | REFERENCE:
2f443549-74df-5c9c-bba6-02a07c6b914d | note | • IFC Drawings
f573bc6d-c43c-5410-b91f-8b4747d223dd | note | • Section 701.20
3202c20d-dac3-5665-93c6-5dcf687938f6 | note | ---------------------------------
086b3155-879b-585a-b32a-4d3956fb669c | note | ACCEPTANCE CRITERIA:
da3eef78-54ff-55c1-ae10-e4ee962efa5f | note | • Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
9f8e1bdc-218b-51bc-b85e-c120eda2ba28 | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
9c38abd8-cdfc-5d35-9f50-ad09bfc5dcc9 | note | ---------------------------------
bfa2395a-2287-5b47-820a-a038b7993855 | note | METHOD: Compaction Test
d7c418e7-cad5-57ab-ba35-366e78876c07 | note | ---------------------------------
69083f0e-bd45-56ab-836b-506223a45fc1 | note | FREQUENCY: Each Lot
48d2bae0-2573-5a68-8caf-c811ffa365bb | note | ---------------------------------
61cf5c86-0d4e-5108-b5e4-82cacae831c4 | note | CATEGORY: IP
7eca22e3-6fa2-5fce-9933-d788ad68d868 | note | ---------------------------------
32c91886-0bc4-5dc1-9116-60b3ead6ac43 | note | RESPONSIBILITY: SE
9c08ceb1-9e48-535c-9673-384f8a85451f | note | ---------------------------------
5d714ec2-7bb1-5976-b1d7-b9ddb1c0f466 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
53ee4a78-b292-54a0-8153-0d7bfa3997b6 | date | Date Completed:
| checkpoint | 5.15 Pipes - Placement of Pipe - RCP
19709c44-cdfb-5188-a888-1dfbd79a68b2 | note | REFERENCE:
b3b553f8-050c-5470-9e6d-d6b080cc9e6a | note | • IFC Drawings
22f1ec40-5e9c-512b-80bb-f26d7d7c70fe | note | • Section 701.17
f8f253b0-ca33-56c2-89bf-6305a02d25fd | note | • Section 701.20
bd43a944-9f03-520b-9f3f-e1818aaf4420 | note | ---------------------------------
886035bd-c738-5f10-a9d0-bf844a297e1b | note | ACCEPTANCE CRITERIA:
9af674da-62e0-5ce0-ae5f-5de161b4fa97 | note | • Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
4d803245-12b4-5014-bcd0-0ec29bad596c | note | • Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
f0bacef0-3561-58a5-af6f-56c1e9788281 | note | • Gaps between spigot and socket are in accordance with the manufacturers specifications
09cb1ffd-bfae-5e31-8520-4969fd6bae43 | note | • The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
97d08a9e-28f9-5ba2-9ea4-4639e51417f8 | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
9ad18ded-9158-5e8d-b812-bb48537bea21 | note | • The spacing for multiple row culverts shall be as shown in Table 701.171
381caf37-ea10-5bc2-bd97-3c03e4d59d52 | note | ---------------------------------
861dd98c-b807-5951-995c-a2c8c9f2f845 | note | METHOD:
1ecbb728-4e3f-5664-b030-12aaafb9e5c5 | note | • Visual inspection
6612264c-f04b-5d62-a109-dcc7b77fe1ff | note | • Measure
a959c07a-113d-545d-b099-b6d0eb8469b4 | note | ---------------------------------
41d418d5-0fb0-51c8-9afe-5ac647e22fe4 | note | FREQUENCY: Each Lot
840f1982-aef1-5dd2-883f-23bf1ec20f37 | note | ---------------------------------
29a0049b-34b3-5dce-bdb8-e393cdba97da | note | CATEGORY: IP
860c7906-fafd-5390-bd2e-b7eba2b91b4a | note | ---------------------------------
d522d516-1de6-5635-97e7-eadf637ad1ec | note | RESPONSIBILITY: SE
c2ecdb98-c201-55dc-a5b5-467a38e83019 | note | ---------------------------------
7c27adff-2795-5210-8a39-01c3aa397326 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
cf0982bd-7481-5281-a6f9-69caad78c82b | date | Date Completed:
| checkpoint | 5.16 Pipes-Placement of Pipe - Flexible Pipe
77939416-4402-53a3-becd-ba4ecc8e93b7 | note | REFERENCE:
04103d7b-a54d-5592-960b-d1c5decae299 | note | • IFC Drawings
7fb3f3f1-25f2-59fe-9fd7-7c08eab0d898 | note | • Section 701.17
597ed688-69da-5264-9587-97df2ef58c59 | note | • Section 701.22
06b84d03-90b0-5010-87f6-cc0ac5fddd33 | note | ---------------------------------
8eabb116-80c9-5e5e-8f80-4aed960691e9 | note | ACCEPTANCE CRITERIA:
3c404933-5c7c-5493-aec4-32da6371936b | note | • All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
9e484397-69e6-5d18-91a7-732d782f5d3b | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
1d046eda-fc8a-5182-bbbf-4afe2aa71cc9 | note | ---------------------------------
ec14303d-a5b9-59c5-8f48-72fe2d5a19af | note | METHOD: Visual inspection
3f2059e2-f365-5645-bc1b-103338ec7c1e | note | ---------------------------------
3d4176d2-0c4e-5b4e-a6b8-fa0fc0243ad8 | note | FREQUENCY: Each Lot
8f8b967d-61ef-5b5a-9292-cf24fd2e46dc | note | ---------------------------------
9a1cd252-a89b-52f6-a7dd-1fb3e0b8a6b4 | note | CATEGORY: IP
1d14b302-1c79-5ec7-b2de-8cfcb0637987 | note | ---------------------------------
b0b376ab-71bf-5c75-9f4b-b51c6c4669ee | note | RESPONSIBILITY: SE
b07c028c-3e61-5b9b-8055-392f29180170 | note | ---------------------------------
f4a44e7d-7519-5955-a9e3-0239a622b5e6 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
03454355-e625-5b36-b33e-8816a794df53 | date | Date Completed:
| checkpoint | 5.17 Pipes - Lifting Holes
611d0660-de20-50d2-ae78-b822da73ce00 | note | REFERENCE: Section 701.18
969fff30-944b-50c7-bcc5-051634db6b25 | note | ---------------------------------
8f263795-2065-55e8-95e5-f3ca37cf44d2 | note | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
0c312676-f16d-5c77-b861-f262ba0ea108 | note | ---------------------------------
98ae1f3a-a2a9-58c2-be5d-784b04dc6956 | note | METHOD: Visual inspection
7ba8658b-39e5-59fb-a3d4-09c779e4c59a | note | ---------------------------------
ac2cd612-bc36-50d0-9522-2d23e77a34bb | note | FREQUENCY: Each Lot
6a129a82-09ec-5b67-b592-9f19c9aecd81 | note | ---------------------------------
7f86853d-6d30-56ab-a2a3-97bb7026ae8a | note | CATEGORY: IP
60ea5dd9-6a50-5b49-abea-d48927eaf3be | note | ---------------------------------
15b0c0d5-8ae8-5fd7-9106-fc8a3f688c71 | note | RESPONSIBILITY: SE
8565fd07-818c-5b50-a98e-23fdde7e8861 | note | ---------------------------------
382cc0b0-faef-5976-90ee-b27fdc400f25 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
9dde3ebb-fad0-5b87-9efb-c1831e352566 | date | Date Completed:
| checkpoint | 5.18 Pipes - As-built survey pick-up
4d21a00b-d197-57e6-83af-30a90739bf99 | note | REFERENCE:
2d859a68-4f2f-5bf6-8992-dce7db89637e | note | • IFC Drawings
06aa52e4-7963-51e1-9e2f-826ea249569f | note | • Section 710.10
114b541a-957e-5bde-b253-2b7ba4f20c30 | note | ---------------------------------
d827eff9-19bc-56fd-b988-dae7e0b456cd | note | ACCEPTANCE CRITERIA:
3c047fbd-2d7d-551c-a3e9-75cff5946c81 | note | Each run of underground drainage shall be Survey verified prior to backfilling.
eb5d4b84-d1a5-516f-b017-751d40159317 | note | – Offset pits to kerb +/- 20mm
b6d46f49-d242-5618-ab5f-a96026b3e07a | note | – Plan location pits not adjacent to kerb +/- 100mm
18082fc2-f894-5222-beb0-1afb8adbfc23 | note | – Invert level of pipes at pits +/- 50mm
820b3135-c5a2-5357-b5a6-536093bf4496 | note | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
c3d5dd27-8dee-5ed8-b1ea-dee55224f815 | note | ---------------------------------
902fb734-612f-5a16-b193-9e7f739931b5 | note | METHOD: Survey
12aa7995-8f31-53f0-b163-ed5120ccbf46 | note | ---------------------------------
3c01f23f-7286-52a6-92c6-c7686eda215b | note | FREQUENCY: Each Lot
24018108-1211-56de-9907-75f252a86fb4 | note | ---------------------------------
9ed231c4-c6e1-54f4-bc3d-bdaf51a45884 | note | CATEGORY: IP
94d2e69f-cd2d-5e08-bb5a-5c175b8f256e | note | ---------------------------------
4c4f73b1-b56f-5696-9bc0-ff44a26bfd76 | note | RESPONSIBILITY: SE
ab4e5d2d-96dd-57a0-82c5-d532dbc0e596 | note | ---------------------------------
316e3e3e-1001-5dab-893d-bbc35dd9d140 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
b73df8bf-eac6-5560-ad0e-64e8512699a5 | date | Date Completed:
| checkpoint | 5.19 Pipes - Backfill Placement
7a2cc00b-b1cc-527f-8d22-03f4125ae6bb | note | REFERENCE:
5d657d4f-23ea-5397-8786-155ed1be4ca3 | note | • IFC Drawings
015b0c3e-9397-5093-b8ec-412fba0058df | note | • Section 701.16
fdb9f601-c31d-502d-9be1-731a68557708 | note | ---------------------------------
80a4900f-5f17-569a-beee-fe943ba08d83 | note | ACCEPTANCE CRITERIA:
5c9a683e-9e14-517a-86d7-3ee0399cc06d | note | • Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
4183f836-400b-5d9c-b08c-dfa4fb1e4b33 | note | • Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
3a4dd02a-1c26-5a1f-a92b-4ba8070d37db | note | ---------------------------------
4ebc29ec-2c70-557c-9edb-1f78fb6d160f | note | METHOD:
5f554034-a70b-5ad2-8ae7-54bdb95a7d56 | note | • Visual inspection
11aea135-448d-5db9-a24e-c39640f8671e | note | • Measure
5702d10e-bfec-5800-8171-45db2f39e28a | note | ---------------------------------
15d7540a-1c98-594a-b1c7-74bfdf7213dd | note | FREQUENCY: Each Lot
a842ae5c-b054-5a31-bfd6-7773570de5fe | note | ---------------------------------
f1b9b065-0790-56a6-884e-5e2ad8ef0c46 | note | CATEGORY: IP
8740f231-fbbc-572c-9e31-54e10cbcc747 | note | ---------------------------------
1068f614-ec91-5189-bf31-959ef937b6c4 | note | RESPONSIBILITY: SE
6a16cf15-54c5-5d8e-8deb-6c6bfb3e90fb | note | ---------------------------------
9009af6a-5d29-55ba-b9b1-18b6fc1ba44e | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
424a8e3e-d74c-5fe0-b02e-a2f2fa5dfa7c | date | Date Completed:
| checkpoint | 5.20 Pipes - Backfill Testing
c0f57d05-a90a-5f42-a4fd-2035b0359677 | note | REFERENCE:
240d1e6f-201e-588a-acfc-277091fc902b | note | • IFC Drawings
b10f906d-b651-5575-9448-14128cf0174d | note | • Section 701.20
5d09bbfe-add9-5d6e-a9ec-ea56fc676d59 | note | • Section 701.29
0184bf96-4aba-5da0-a7d3-4c5e35090006 | note | ---------------------------------
aec7f6aa-0c24-5ddf-9bb4-3d975182baa8 | note | ACCEPTANCE CRITERIA:
13d82307-84f9-5a53-b699-aae4cbf04399 | note | • Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
ae0bd65a-ec8d-53e4-ba2b-13477e8a55f5 | note | • Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
c03a32fb-3d27-54aa-8d93-af3ce64e2690 | note | ---------------------------------
0b1b66a2-4864-524c-aad6-f57088886010 | note | METHOD: Visual inspection
b11c62e5-c555-5efb-a73a-0f926777c508 | note | ---------------------------------
9370d6e8-dd47-55ad-8c07-6903160e46f8 | note | FREQUENCY: Each Lot
56843ccb-f3a8-5fba-9d8c-786b9a54a59b | note | ---------------------------------
1ee078f2-134f-5422-8773-3ba878e7d9f5 | note | CATEGORY: HP*
2974e8f9-54fe-5ef7-af35-6649f8b7832d | note | ---------------------------------
5691bf3e-3123-5615-99d4-5bbc2d344ed1 | note | RESPONSIBILITY: PE
287fe581-0dfc-5691-8fa2-667d7253348e | note | ---------------------------------
46711938-2ef5-5edb-aca9-50f2ccf6e0f8 | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
4dfc0104-bc2d-555e-b62b-d9cc5036b219 | date | Date Completed:
| section | 6.0 - Post-construction / Post-installation Activities
| checkpoint | 6.1 Flushing & CCTV
159bcd39-4510-5d40-b35a-a73ea651ce01 | note | REFERENCE:
85eb4301-7474-514f-9f38-62cdc9084881 | note | • Section 701.28
199a2224-acbd-54fa-8eea-d04e18edc644 | note | • Section 701.30
2f6f6ab6-c932-5214-a874-85efec932a96 | note | ---------------------------------
2f08cb28-1de9-504a-9364-5f86797c454b | note | ACCEPTANCE CRITERIA:
07d34c6d-4fce-5ae3-a415-ea0f5c5079ee | note | • All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
249e3201-6888-5be5-b685-f746065fcde5 | note | • All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
237b88b9-b9da-5b2a-9a80-0df04d10ac7e | note | ---------------------------------
ff9fa6ff-9e71-5852-bbb2-13739ac55962 | note | METHOD: Record Review
f389914d-4d0b-5dbe-b9b7-28e2e820ded2 | note | ---------------------------------
f8f37fab-04e8-5c74-8d53-d2495c69ba8c | note | FREQUENCY: Each lot
8acb0aa0-3068-5a46-961d-62312e2623b2 | note | ---------------------------------
96d0f832-eedf-5084-9ea5-59ecaccf4a98 | note | CATEGORY: HP
62622c57-ec3a-50ab-9166-8eb0f9a5dda0 | note | ---------------------------------
1c5b6976-8baf-53a9-9319-9c0144060b8c | note | RESPONSIBILITY: Nominated Authority
471c5513-2d4d-523d-a58a-60449d0dc30a | note | ---------------------------------
cb4fcdf8-61ab-55d4-b90b-e7821dceee52 | note | VERIFYING DOCUMENTS:
ee8c0b8e-5930-5fed-b111-e7b8f1c60b1d | note | • This ITP
fb7f222d-f561-50da-985c-d590d3dadcb1 | note | • CCTV Reports
89c14410-158b-57c5-96b3-aeb87f767805 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 6.2 As Built Survey
a1cbc581-66c4-5e05-a23f-fadbf1e2fbe4 | note | REFERENCE: Section 701.10
efc6cec3-d607-55c0-8239-0782991995d5 | note | ---------------------------------
55262a37-0d2e-5ca6-b05a-6ff06ca4db1b | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
02c4346b-8e00-5208-8c5c-aa1de16dcf94 | note | ---------------------------------
f52c8f8c-9c05-5b6f-8037-79b28e1395fa | note | METHOD: Document Review
de761392-0047-587c-a3f2-2fd0932bd6e8 | note | ---------------------------------
ea43d0ee-a987-511e-b271-2ea8e9fda5e8 | note | FREQUENCY: Each lot
7fb86dcd-3dc6-559a-85a7-8631eccae803 | note | ---------------------------------
110b14aa-3038-5595-b2f6-cd63226ff707 | note | CATEGORY: IP
fb040add-5fb9-5536-a003-c11fcc6f1eff | note | ---------------------------------
2db84356-8873-5015-8045-cada1b970b65 | note | RESPONSIBILITY: SE
530ddf72-8ccb-53cc-9a5c-2d8349a3229d | note | ---------------------------------
8ae65123-89ac-5501-8dba-e2e0216c33db | note | VERIFYING DOCUMENTS:
55a676b8-b806-5935-ab7a-a51dd5aecae2 | note | • This ITP
96f24d11-a0b5-5d69-949f-8227c170c978 | note | • As Built Survey Report
beb9e650-b340-5765-87e5-b09d457ecc08 | date | Date Completed:
| checkpoint | 6.3 Repairs to Damaged Pipes
038a7a6e-a304-5ebb-b7e1-0a51274a1504 | note | REFERENCE: Section 701.31
e9432abc-0c4f-5dc7-888e-168e15b6ff6a | note | ---------------------------------
0173f728-70ee-5417-adae-6a0aea3f32c3 | note | ACCEPTANCE CRITERIA:
6bcc2ce3-ed44-50b2-9b6a-44701160d2fe | note | Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
f618e6b1-34a1-531b-b50c-aa7fba22db8f | note | • cracks wider than 0.5 mm
9f8b5068-1ab9-531d-9bbd-f5f7c9aae961 | note | • spalling of concrete
9edcb5ef-f6ce-538f-9b48-9d2ebfd9a07d | note | • exposed reinforcement
8ed994c7-cbb1-547b-9090-b5d6e80a5090 | note | • joints that are not fully engaged.
59e1e2f2-97ae-5229-966c-3ac9ae0591dd | note | Any pipes with defects greater than the following limits shall be removed and replaced:
0870eccd-4e03-5eae-9068-938d23586755 | note | • longitudinal cracks greater than 2 mm
83393a75-a530-5d41-8ad4-e23d14474209 | note | • circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
6692fa63-5d8f-5831-8ef6-929b56682247 | note | • circumferential cracks around part of the circumference with width greater than 4 mm
6bc4a133-19e7-5411-8afe-02503f4ee0d1 | note | • penetrations with area greater than 400 mm2
4501d997-9869-54f5-9cb1-67f46ab400b1 | note | • pipe joints that are separated.
0e7286d5-1869-5a58-963f-856f4e6a05e2 | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
a8700aec-529d-5566-b849-80f68eb57c4e | note | • hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
45dee190-fa62-5295-936b-71ee9ab223ef | note | • fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
bc65d82f-c362-5102-8618-e6777e9b4b4e | note | • spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
45da4401-85f5-50d9-b09c-7f529b639a67 | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
3f40ad12-8e66-5f63-abec-60de09e76ff2 | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
f9000906-fcae-5aae-94a5-e783cc100ada | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
f1a172b5-0aa5-55c2-b18a-1d544ce7a3c8 | note | ---------------------------------
8f9b90c1-10e6-515f-8c66-e5943ce759f0 | note | METHOD:
228b213a-b69d-5ed9-b7e3-eab859726860 | note | • Document Review for Repair Procedure
848a4b12-318f-5617-8fac-01dbfce80e11 | note | • CCTV Report Review
d4fa9bc6-d851-5231-801f-0425ca0325d5 | note | • Visual Inspection
0e38733b-6976-5add-a297-022942d7130b | note | ---------------------------------
b3616051-16a7-5568-9967-7c79d6c51df6 | note | FREQUENCY: Each lot
6fc051fe-5677-5366-bf9a-703c0e74672a | note | ---------------------------------
19756bf2-ae3c-526e-8add-54c0ab597a45 | note | CATEGORY: HP
ffa2c7e9-7463-52b3-914c-7ac855ad642e | note | ---------------------------------
6a195576-b829-52de-b4ee-f20cdecdd1f9 | note | RESPONSIBILITY: Nominated Authority
6c8fec64-4055-5e2a-8abf-b4ff42accdca | note | ---------------------------------
acf23e40-f118-5f6e-9986-6167a9b0a02a | note | VERIFYING DOCUMENTS:
a1d3f3d9-d2d4-53e1-9186-d58e9d462b4a | note | • This ITP
56482cbe-d340-5bac-8407-8e3116d7c06b | note | • Approved Repair Procedure
fe8797fd-8317-5e34-a714-0204cda238c5 | note | • Post Repair CCTV Report
5b8a6c6b-8844-55f3-a248-cce7f23916a5 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
cfafe55a-2b51-58d8-9710-cb8dbd02c4d9 | note | REFERENCE: MRPA Quality Management Plan
fabcd401-4f32-5273-8889-f467a7a18aca | note | ---------------------------------
9f316faa-ee12-5b8c-bbf1-0c5515759ea8 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
4bff4195-fcec-5526-82b5-77dcadb7a1f9 | note | ---------------------------------
0a880d20-403a-5491-80bb-26fc301dd006 | note | METHOD: Document Review
1a195a48-0ded-5bfa-b366-89bd3b5354f1 | note | ---------------------------------
96e014b3-dfa6-58ca-801b-59683ecf740e | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
c28bc619-9ba4-5c04-b8a3-015bf7b6358e | note | ---------------------------------
f4f54f2a-be70-5d95-ba01-d82945aabebf | note | CATEGORY: HP*
f0ece616-3252-5d28-a099-ee55ada31ce6 | note | ---------------------------------
452185ca-1ed3-5ad7-9191-61c727168d13 | note | RESPONSIBILITY: PE
e64fc34e-d7e5-576c-b893-8d9e4276f649 | note | ---------------------------------
40e013b2-3180-5dc4-b90d-a48292079636 | note | VERIFYING DOCUMENTS: This ITP
cb9564e8-9395-5d94-b48a-c0db0d2fc8e1 | date | Date Completed:
| checkpoint | Metropolitan Roads Program Alliance Final Inspection
fa8d856f-ad43-55f1-969a-6d1badd09428 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
5fcc9e4b-42d2-58eb-ba33-f3ceea67d3f0 | textbox | Name:
e6feccf9-68b6-520b-a7cd-3e7668aede9e | textbox | Position:
fe36629f-e735-5b19-8bed-95332a57a4b6 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-009-STR-Bored Piling Rev 0 | itp | ITP-009-STR-Bored Piling |  | 4b9003f8-8151-4362-b039-66f19e04c449
| section | Referenced Documentation
| checkpoint | Referenced Documentation
52fa5381-7f92-5400-8bb4-c481246ece1b | note | Document Title: ITP-009-STR-Bored Piling
2c2d6ba4-28ff-5076-a45a-fc0c47d69bd2 | note | ITP Description: Bored Piling
77c717b2-e162-59c0-bf4d-a77a8dd9890c | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
212aef7c-d24e-5d6b-9a39-d5f01812b080 | note | Discipline (e.g. CIV/STR/RAIL): 009-STR
ad7bfeee-8a64-5903-b907-0feec7fec2e1 | note | Revision Number: 0
edc909c4-fc3c-553b-8537-14f3aba04e62 | note | Revision Date: 11/10/2022
8a5b7355-f54e-543d-a7e4-226209c7c883 | note | ITP created by:
23af4e33-d6aa-54a6-9d2b-1711eefd90f6 | note | ITP approved for use by:
718adae9-f64d-536f-92ba-1652c207c1ae | note | 1.1 - Non Dependent
0631f35f-66c7-597d-8183-07b7471efa09 | note | Reference Documents:
575cff68-dc4e-5649-a878-f9e5f0ecf925 | note | • VicRoads Section 606 July 2017
67083365-e0a9-5f1e-b3a8-874277c2df0a | note | 1.2 - Non Dependent
c8bf7e37-ab26-5aa6-ae0a-42f9985b02b3 | note | Reference Documents:
d639850f-b897-5bde-9f50-7c295372c345 | note | • VicRoads Section 610 Feb 2020
9cc3e9c1-75cf-51bb-a7bf-ce607728c2f8 | note | 1.3 - Non Dependent
518986af-874e-552f-a608-00d1f86d359e | note | Reference Documents:
919e322e-ef2f-5ce2-a4e9-93bb2f88fb9d | note | • VicRoads Section 611 November 2018
c0451440-8b56-5621-82f4-43e48354165f | note | 1.4 - Non Dependent
cab47aea-ad32-5f28-a5cf-a62be25952ea | note | Reference Documents:
8f7ef28f-6a38-583f-8a36-171b9231c81f | note | • AS2159-2009
b07381a8-e3fa-5378-a29d-d34fe583c33d | note | 1.5 - Non Dependent
4350757c-864a-57a9-8d5a-f089b4625da6 | note | Reference Documents:
5407deb2-665b-5435-a4b3-f0520ed3e10c | note | • AS3810.1 2018
c7480114-60c6-585a-9bc7-cfa268204117 | note | 1.6 - Non Dependent
7989f8de-ed7e-50c7-8bae-fb46ecc70ba6 | note | Reference Documents:
33fd1675-48d2-5a36-bf5d-0a1b7082c2cc | note | • AS5100.3-2017
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
f9ec52d7-6720-55bb-84fe-3df33308254e | note | REFERENCE:
bc1d6b24-9ed7-5e78-885f-5c6906aeec78 | note | 610.07
d5f9ba87-c25d-5a0d-9d3a-0bf2a9e56902 | note | Table 610.071
5cc1974a-89ac-50de-a22c-9e997d95f708 | note | – – – – – – – – – – – – – – – – –
4b367dd5-7fd4-579d-be68-7cf5f43be6bd | note | ACCEPTANCE CRITERIA:
d2966f00-9e6c-5176-8791-0162a375ccac | note | • Concrete Mix is Registered with VicRoads.
f3dccb5b-632e-59da-90c8-6046af1fe44b | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
3ec1d9a1-482e-5f18-a417-4772bb8a96b7 | textbox | Enter: Teambinder Material Approval number
f9a27263-c218-5491-90c4-414147c419c3 | note | – – – – – – – – – – – – – – – – –
94b11045-40ce-512a-a7e2-3ae694fc84d5 | note | METHOD: Document Review
2e927562-6c57-554b-aec9-e3f97f8feb09 | note | – – – – – – – – – – – – – – – – –
ef74f23c-255d-5a34-8508-733bf9614ad4 | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
097f1e5f-7c08-52e6-9e98-e5f40280abc0 | note | – – – – – – – – – – – – – – – – –
726d6a41-cd0c-5581-8b45-ad8c45db4106 | note | CATEGORY: HP
8567a3c6-ff1d-530c-893c-b185657990d5 | note | – – – – – – – – – – – – – – – – –
c3685c7e-02c6-5789-a7de-f3b87a5bde25 | note | RESPONSIBILITY: Nominated Authority
1df1af45-6b20-5bb8-a996-bdc8c24b506b | note | – – – – – – – – – – – – – – – – –
eda71dd0-47f9-52cc-8905-0264cb5ff5f0 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
d5f28fdb-0736-55ce-af0d-cd5e94e71eea | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
b7b645b3-b7e7-5152-9940-259c96e79482 | note | REFERENCE: 611.05 (a)
ff285166-ba8f-5825-b52f-b6360968bf45 | note | – – – – – – – – – – – – – – – – –
0d385491-a8e7-536b-a73d-b029e6425a66 | note | ACCEPTANCE CRITERIA:
ae7df377-9991-53d8-8a25-ced6a531d247 | note | • Current ACRS certification for materials and for bar processing.
46010d56-c566-59a1-9858-089bd6178f46 | note | • Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
dfffbb20-5088-5def-ba55-934af8647721 | textbox | Enter: Teambinder Material Approval number
442ea5fc-60da-5758-93b6-af84dc2f115c | note | – – – – – – – – – – – – – – – – –
7ae33f1f-c621-5ee6-8d60-f61621b0a78d | note | METHOD: Document Review
b8095f3a-228f-5fc9-9ff4-dfb1450c45f8 | note | – – – – – – – – – – – – – – – – –
48c4a90a-eb2a-5e72-8f33-f0fdd24b6fa7 | note | FREQUENCY: Once for each supplier, 14 days of award of contract
cfde858b-1517-5d88-afc1-5d649dbadf4e | note | – – – – – – – – – – – – – – – – –
283bfbc9-07df-5a76-affc-c89f27e70428 | note | CATEGORY: HP
88d87da6-b010-55e4-bb4d-593715776e9d | note | – – – – – – – – – – – – – – – – –
32052a74-8e98-548a-aa1c-8a913f377fcc | note | RESPONSIBILITY: Nominated Authority
b8bee204-2f5d-52d8-b4c8-416f859e5b88 | note | – – – – – – – – – – – – – – – – –
f59a0a9a-ca38-533e-88a8-e55f8d7ecc3a | note | VERIFYING DOCUMENTS: This ITP
0c7b12a2-1600-578a-9322-1f0e95e3191e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
32bbadad-28f5-50d2-a490-3dcd320ac940 | note | REFERENCE: 610.26 (a)
7060c616-badc-5c47-98d2-703ef853a4e4 | note | – – – – – – – – – – – – – – – – –
14e47d4f-c4d9-5d6e-a1c3-dacb68ae5d98 | note | ACCEPTANCE CRITERIA:
1a9fc080-304c-55ff-a894-17423053f614 | note | • Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
ec19b6d3-11cb-5e52-8ae7-95de4bcae11f | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
113caa8c-c6d2-5dea-b154-47eb162b7fb6 | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
534a4b5c-4f95-5a44-9d89-2b6497937196 | textbox | Enter: Teambinder Material Approval number
94afac09-2b06-5244-92cd-289d1a6b4d5f | note | – – – – – – – – – – – – – – – – –
af2fa23d-5fb8-524e-bc71-de17e9e6a3c7 | note | METHOD: Document Review
0937d39c-0c3e-5f37-88f0-d7c46b26a16a | note | – – – – – – – – – – – – – – – – –
1f5d6159-5a96-52b7-ae5a-1bb080f0273f | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
54a88e2c-5f7e-5bb3-bcaa-12f26321c2d7 | note | – – – – – – – – – – – – – – – – –
d2850ffb-79e8-55ce-b986-1e2a64b4ea64 | note | CATEGORY: HP
66a4e47c-d3dd-5665-a9c7-6ff3320041da | note | – – – – – – – – – – – – – – – – –
e9122874-018a-52b0-aeba-bc3d7e58ac97 | note | RESPONSIBILITY: Nominated Authority
94283f24-ba4d-5d86-a8f2-55f4785487a0 | note | – – – – – – – – – – – – – – – – –
6f7bc0e9-6f25-573d-9da7-5d97e74bea91 | note | VERIFYING DOCUMENTS: This ITP
f0f2c9ea-9da7-5c02-bd77-f2b2639e3703 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Working Platform certification
c9e4fb5c-4829-5061-a064-0a52b86c89aa | note | REFERENCE: -
51b1090b-0474-59c2-aaf7-131e1bbc1fce | note | – – – – – – – – – – – – – – – – –
60f8af1f-d74e-5c56-8ddd-73469eedfa30 | note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement
fecc628b-fddf-5eeb-a058-2c9a67fa8374 | note | – – – – – – – – – – – – – – – – –
96fc436b-6d09-54d9-95ec-2dfae3171c60 | note | METHOD: Document Review
c66cd20b-5523-526a-aaf0-5b85b3c1fbe3 | note | – – – – – – – – – – – – – – – – –
0f00208e-d935-5441-bbfc-514206980546 | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
c8735659-aac2-5253-8d38-e94de6acc01d | note | – – – – – – – – – – – – – – – – –
a8f3fade-3d78-5549-98fc-4ee905da09be | note | CATEGORY: HP
bf0b0c4d-6034-5447-92d4-e1bceffb901b | note | – – – – – – – – – – – – – – – – –
452d6077-ec8f-5fd5-9057-a0a04ed247a0 | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
eb1bc9ac-1ab7-5ee4-8302-d69fde181891 | note | – – – – – – – – – – – – – – – – –
0a968724-9d11-5cdb-beba-d5914832af2e | note | VERIFYING DOCUMENTS: This ITP
a19a7013-27b6-593e-8057-7fa4b759e953 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Piling Operations Work Procedure
7e0a8aec-8c0d-5e82-a802-6c51c52758b6 | note | REFERENCE: 606.03 (a)
b654e747-4464-5618-8d4e-97f46135f2fd | note | – – – – – – – – – – – – – – – – –
237272d8-7bac-5850-9bb4-0a559bb24df2 | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
dba8e25f-02da-5316-a336-edce6a4cc564 | textbox | Enter: Teambinder Approval number
b43d955d-8809-5d56-876a-15520799e107 | note | – – – – – – – – – – – – – – – – –
992ee446-b5f2-5adf-8b9b-62659a7cffc8 | note | METHOD: Document Review
16f05ef8-045a-5684-a382-94b23f48f4e8 | note | – – – – – – – – – – – – – – – – –
8ff5aed5-e4b7-5710-b054-d47b46c6785d | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
2ffc20a8-fc6d-5ec9-95b2-3f6301b8cd90 | note | – – – – – – – – – – – – – – – – –
d016d519-254b-5051-969b-e6c840c7a8cb | note | CATEGORY: HP
a703042d-3146-5a80-9dfd-13565613045b | note | – – – – – – – – – – – – – – – – –
2a800fe2-935c-563c-beed-5b51b71a2ac7 | note | RESPONSIBILITY: Nominated Authority
a8fd2277-c0a2-5dc1-9695-853a14ca90f7 | note | – – – – – – – – – – – – – – – – –
cd1e4829-73d9-5521-8942-c523e937f55d | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
7122e299-8fbc-536a-811d-e84fa6a22b98 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Temporary Steel Casings
e456b16a-c8d7-5389-a6cf-babf89ce0824 | note | REFERENCE: 606.03 (b)
15f7d266-1a3c-5a82-b4ab-7de09688bd26 | note | – – – – – – – – – – – – – – – – –
a3810d3e-de68-5ee8-be9b-4e03b846d72b | note | ACCEPTANCE CRITERIA:
ea95881e-68bd-51dd-800e-9676018bb233 | note | • Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
6816b67f-c68f-58c9-a6f4-f9c122148828 | note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
98c193b3-cc16-5646-abe5-f506d745acd1 | note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
a3e0d1f4-e5e5-520a-91bf-262386541ce0 | textbox | Enter: Teambinder Approval number
840f39f5-2ccb-5b6d-b116-c6cecabe12c3 | note | – – – – – – – – – – – – – – – – –
8da83028-0f4c-5b66-97a8-424124829e68 | note | METHOD: Document Review
fd670178-9c0b-5d44-ba69-a92ba4a230f6 | note | – – – – – – – – – – – – – – – – –
a4d4bf0d-6890-5ad2-b75d-72b7f1badb39 | note | FREQUENCY: Where applicable, once, prior to use
ae147cdd-8a5f-578d-98fa-dfac104a3ebe | note | – – – – – – – – – – – – – – – – –
50db6fdc-db64-5ea1-b605-fc7b6d2d7d98 | note | CATEGORY: HP
910a22f3-f2d5-56a5-ac5f-01799149a16b | note | – – – – – – – – – – – – – – – – –
fb1bffe3-e28e-5275-a001-e6443bc8c0eb | note | RESPONSIBILITY: Nominated Authority
f113513b-2ee4-5f6b-8230-4c9344fa080f | note | – – – – – – – – – – – – – – – – –
4225087c-1077-599d-9446-8f51535a0e72 | note | VERIFYING DOCUMENTS: This ITP
81a88703-350a-52b7-aee3-8206ee4fddfa | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.4 Casting Under Water Procedure
3904a830-e946-5547-ac51-4f3f42350611 | note | REFERENCE: 606.06 (a)
1feb4396-f8ec-5887-8ebc-10aad9a808a5 | note | – – – – – – – – – – – – – – – – –
ddd424a8-bf09-5690-a6f4-fa40184de56d | note | ACCEPTANCE CRITERIA:
c4c19078-6ee8-5f5f-9a44-1a6790cdd662 | note | • Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
d64fa74a-75ea-5e0d-859a-469bc5cc1a09 | textbox | Enter: Teambinder Approval number
b57fde01-cfd8-53e1-bd8b-300635f51798 | note | • Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
d8bfe649-68f9-55e6-8de3-ef97007e4f82 | note | – – – – – – – – – – – – – – – – –
72ad5a3a-213c-57cd-bc2c-6b437e11d4f9 | note | METHOD: Document Review
f505e575-d09e-5f2f-95a6-f2aed13d72ff | note | – – – – – – – – – – – – – – – – –
f03ced72-3ddc-592f-9882-f81dfee1e333 | note | FREQUENCY: Where applicable, once, prior to placement of concrete
54d6169d-96ad-5c02-a41f-11729127d64b | note | – – – – – – – – – – – – – – – – –
b69d86b2-4034-586e-a7f2-58141432e7d4 | note | CATEGORY: HP
f030e221-75de-59f2-9fb5-59f5d926efbb | note | – – – – – – – – – – – – – – – – –
eaf51dec-df6e-54b4-b3b1-0cc51f498499 | note | RESPONSIBILITY: Nominated Authority
283fa6bc-6a03-595f-8e85-ea52a0bab996 | note | – – – – – – – – – – – – – – – – –
35dbb304-b0e8-5f41-96b9-39123e49f810 | note | VERIFYING DOCUMENTS: This ITP
4c33449e-1b0c-532c-97f5-a8e4efafa85c | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.5 Boring With Bentonite or Polymer Fluids
001dc125-dcd6-500c-b420-146886b3499d | note | REFERENCE: 606.03 (c)
cad15905-5e4c-5ac9-a64e-ce4ad1bf0ed3 | note | – – – – – – – – – – – – – – – – –
3af5c556-d1f7-5e00-92b9-024c1e91c924 | note | ACCEPTANCE CRITERIA:
cb30b0de-6d9e-5046-80b5-1e8cb88fa2b9 | note | • Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
47b75531-5066-5a4a-a26c-40dca3632c5c | textbox | Enter: Teambinder Approval number
3a493e96-db69-5009-af28-a35957d3ef3b | note | • Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
f643b916-514f-51e7-b97f-c24360263e2d | note | – – – – – – – – – – – – – – – – –
f4ff55eb-ba61-5634-b993-5dce25069366 | note | METHOD: Document Review
5f2147e1-f783-5eb0-96c6-d117ac625072 | note | – – – – – – – – – – – – – – – – –
28c8f4e8-f3ff-5124-a6a2-693f2a05e4cb | note | FREQUENCY: Where applicable, once, prior to commencement of boring
fd389d57-d3b3-53dd-aadf-41006fa174fb | note | – – – – – – – – – – – – – – – – –
b74a2502-8205-5a38-8f97-538c1ce29ef3 | note | CATEGORY: HP
221f2711-fc8e-5269-a37a-625b1c929fca | note | – – – – – – – – – – – – – – – – –
4e9ebe07-00b8-5e0d-82a6-84ef2b4cab31 | note | RESPONSIBILITY: Nominated Authority
1967d4e7-4006-5266-8c12-b6d372fd00cb | note | – – – – – – – – – – – – – – – – –
3a7be694-a908-507e-bcdb-43603b85c5cb | note | VERIFYING DOCUMENTS: This ITP
0aba3beb-476d-506e-a983-e974ec4bfd94 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.6 Dynamic Pile Testing Procedure
5c07b1d6-dfab-55af-884a-b2ab6c762879 | note | REFERENCE: 606.07 (c)
311bb4cc-d826-5393-9a1a-f113d584a08a | note | – – – – – – – – – – – – – – – – –
e52526ea-2d66-50d1-944a-a4f5f8df5910 | note | ACCEPTANCE CRITERIA:
509d0494-64ae-580a-8da7-fd3d3182fb73 | note | • Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
b27127e5-91fb-5ecd-ae5f-ce5e6b4acb6f | textbox | Enter: Teambinder Approval number
ea01df4d-f709-5346-98a5-9ff262eae81b | note | – – – – – – – – – – – – – – – – –
1e281150-2ed2-5815-b3c0-4fa6ddb382a4 | note | METHOD: Document Review
d511e08c-8e2b-53e7-9900-7ffbbd9265f7 | note | – – – – – – – – – – – – – – – – –
1f6a6b1f-e44c-549a-8d1e-20988b13f84d | note | FREQUENCY: Once, prior to testing
dca58c95-8f65-5839-a3e1-c300cbace64c | note | – – – – – – – – – – – – – – – – –
4ab1edfd-ba09-592c-b8d8-2b6f28654398 | note | CATEGORY: HP
3a49772c-9aaf-5eb9-bb29-e80d4b9fac20 | note | – – – – – – – – – – – – – – – – –
a4811b54-06b9-5d26-917c-0552e93865a3 | note | RESPONSIBILITY: Nominated Authority
6f4dfdbb-d5cb-5874-a4f8-b22a736f2017 | note | – – – – – – – – – – – – – – – – –
12ee48f1-8ff3-5fa8-9f68-ac9cb5c79f6b | note | VERIFYING DOCUMENTS: This ITP
36f2f781-e3f2-5f62-9061-df0e41067a62 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.7 Pre-qualified Pile Testing Consultant
949c090a-5f08-5478-9eb9-6b2fb2145728 | note | REFERENCE: 606.07
09c15931-e4bb-58dd-836b-8b0b863c2717 | note | – – – – – – – – – – – – – – – – –
3c834cca-0f6f-595c-b3de-63a23b889d32 | note | ACCEPTANCE CRITERIA:
b4fef640-36d5-5b6e-b6b6-9b672c17bf15 | note | • All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
f28bab00-9f1b-57f8-9958-581c59292a44 | note | • Details of the consultant to be submitted for review to the Nominated Authority.
3c43dcb3-7d79-54f9-9ecb-03341fd36f83 | textbox | Enter: Teambinder Approval number
e0719f0f-37a7-547a-beb3-0ab744ba6858 | note | – – – – – – – – – – – – – – – – –
84c6e1f6-b75f-5960-8675-c755ced3f94b | note | METHOD: Document Review
f8dcb74b-0736-5426-b6be-72a377d687b4 | note | – – – – – – – – – – – – – – – – –
19e8dd95-773c-5617-95f5-b454f79d18f1 | note | FREQUENCY: Once, two weeks prior to testing
6eb426a9-07a8-5571-b4b0-6512dacfaae8 | note | – – – – – – – – – – – – – – – – –
b47cbffb-8af6-5ebd-83da-13bb8b8f5687 | note | CATEGORY: HP
80ea157a-988b-5387-b602-03c8da33540e | note | – – – – – – – – – – – – – – – – –
59de6927-5da8-59a6-b9b9-a19d305d753c | note | RESPONSIBILITY: Nominated Authority
6dc45cdb-bd59-54ee-ab9c-a05020fd66d9 | note | – – – – – – – – – – – – – – – – –
3cd28b57-5c72-54d7-9e0e-d414e4b26e79 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
9cdf8e14-9488-5b38-8040-390d6ea14540 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.8 Reinforcement Welding Specifications & Qualifications
8cb2dcf2-d2e2-536e-8ec0-d6d35742729c | note | REFERENCE:
b1b97f39-2c31-5948-a5b4-ca0da3e2a3b9 | note | 611.13 (a)
331e3d42-96b1-53f1-9875-c5a9aa890b7d | note | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
e2be3a92-7881-584e-bd7f-0d57324f1113 | note | 611.14 (b)
0f60840c-ca66-585e-a265-e0df8930d415 | note | – – – – – – – – – – – – – – – – –
8abf435e-7794-569b-a13e-fc285151a1ac | note | ACCEPTANCE CRITERIA:
2a818cbe-8250-5e8c-89b8-2430bf6c9a07 | note | • Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
586166c3-49ec-54bd-b857-cf46a11f2986 | textbox | Enter: Teambinder Approval number
2e94e801-47c7-5274-bd39-b3b02a470390 | note | – – – – – – – – – – – – – – – – –
17c3899e-091e-5d74-8d0d-4a92be387f37 | note | METHOD: Document Review
271f5e56-1024-5b77-a684-6f28a9b9cdff | note | – – – – – – – – – – – – – – – – –
0a7ada04-4fef-592c-949c-055aeb489e27 | note | FREQUENCY: Where applicable, once, prior to welding
a4446d8f-7149-5d79-8a9d-cb8e2e8d7778 | note | – – – – – – – – – – – – – – – – –
713edab5-8dbe-5af2-99e6-c4858e002de9 | note | CATEGORY: HP
c5d29d56-b783-5749-8390-dc308aeb2eff | note | – – – – – – – – – – – – – – – – –
a04f2a76-5638-5d24-a37a-f52ea38a45e7 | note | RESPONSIBILITY: Nominated Authority
d8c3d317-3413-5bd8-a09c-1fb5868066eb | note | – – – – – – – – – – – – – – – – –
64b8b438-ce43-5734-a700-b629b8637bf1 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
4d25c1c1-cab2-5c6f-b794-8a7657e7fffa | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
184b4294-9264-5d23-9241-a14978164234 | note | REFERENCE: MRPA Quality Management Plan
e34b3ec0-4605-580a-a874-a7333aefa49c | note | – – – – – – – – – – – – – – – – –
e708b842-f867-5ed4-987f-15f35eefddc0 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
eb7b3bf9-5f26-5bf0-a66d-200d2c199c98 | note | – – – – – – – – – – – – – – – – –
9e098647-e160-51c4-a177-1ac024c58e85 | note | METHOD: Document Review
e55d27e2-ec5c-54c3-999f-60b054cf55a3 | note | – – – – – – – – – – – – – – – – –
573758ee-451a-57e6-b043-5e7ed4a35c0f | note | FREQUENCY: Prior to starting Works and at regular intervals
56994085-35d4-5b8c-acd9-7ba3150e9cca | note | – – – – – – – – – – – – – – – – –
baf905ab-df5d-58e4-b646-6523719ed01b | note | CATEGORY: HP*
638c8d54-14fe-5022-849e-1a073f04efb8 | note | – – – – – – – – – – – – – – – – –
05c42d70-6fd4-5c9d-bc4d-ba732ad6827a | note | RESPONSIBILITY: All
d2da4d9a-c9ec-5b36-936d-f211763c1e2f | note | – – – – – – – – – – – – – – – – –
139bb36e-43d3-543d-9790-752c4c651087 | note | VERIFYING DOCUMENTS: This ITP
71cdfdfe-aaca-5fa1-b02d-7047ed2cb65d | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
f3055229-ef38-52a4-b376-6c66da9578ca | note | REFERENCE:
875064e2-333f-547b-bb63-cb4b507ce67b | note | IFC Drawings
d2ede88d-da9c-5a22-b693-614edca97541 | note | 606.08 (a - c)
140794b2-b54a-5de4-9202-60f37206c7de | note | – – – – – – – – – – – – – – – – –
a799edfb-4eb8-5c88-945e-fa8d5878da16 | note | ACCEPTANCE CRITERIA:
5ab8ccbe-6c44-53e0-ba6d-2a21b51ecb02 | note | • Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
82b057a4-0456-5261-a05d-e0a7886deacd | note | • Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
b4d5d1cc-5ffb-5f15-8079-50466a497e7c | note | – – – – – – – – – – – – – – – – –
9ef45056-24a6-50fc-bf87-37e19594a74e | note | METHOD:
56229457-b904-56fa-ab8b-f6bdd85cc5eb | note | • Measure
945f6558-c0b2-50eb-ae6c-8e5eb5a0dce3 | note | • Visual
bc17366f-0a5d-54bb-85c0-00b1b5071f11 | note | – – – – – – – – – – – – – – – – –
41a877a3-3719-5e42-9909-5531286b1a43 | note | FREQUENCY: Each pile
cd381719-59c7-5f86-b2bf-43c2fde0b344 | note | – – – – – – – – – – – – – – – – –
202c6e27-3bdb-50ca-bc14-3f29091c8e8b | note | CATEGORY: IP
4664b29c-57e1-5240-8f2a-3c1e692fe09d | note | – – – – – – – – – – – – – – – – –
d860bf65-5f60-59a5-a820-7ef21770edcb | note | RESPONSIBILITY:
6ce8eade-cb1e-54df-9db5-919817011b5a | note | • Surveyor
0a94276e-331f-514c-b770-0332d60bf15b | note | • SE
dc614ca9-eaa0-5f4b-8068-c83f7bc01a2d | note | – – – – – – – – – – – – – – – – –
f3c3d0be-9661-5e9e-9b51-084573630029 | note | VERIFYING DOCUMENTS: This ITP
a94efc2c-a997-50f9-8473-05e6d9530fde | date | Date Completed:
| checkpoint | 4.3 Protection of Adjacent Piles
5e338647-ed2d-57cd-8efb-e55936763916 | note | REFERENCE: 606.04
46d1ace9-4e9a-5a2f-8375-6c7694d6c94b | note | – – – – – – – – – – – – – – – – –
8415349c-8677-56ed-b1db-78971afeba43 | note | ACCEPTANCE CRITERIA:
d26b7935-1345-5298-a7a2-4b2f9299ad20 | note | • Pile construction shall not:
6c1a4094-15a0-5b4e-a469-bffcd696d9f5 | note | i. result in damage to adjacent newly cast piles due to ground vibration.
9b2b3aad-edb8-53b6-9a16-e79b4b73551a | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
256723e0-9f86-50e6-b97f-ba588e25efaf | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
805b535a-ed9b-5dea-a9a4-7b3d0e3c1225 | note | – – – – – – – – – – – – – – – – –
981f3aab-68bd-5a49-951b-3c5148b18cf5 | note | METHOD:
dc17e302-2089-5633-85ca-c46ecbe2cb17 | note | • Measure
9919623d-8707-5d8d-9483-a38fe79a16d5 | note | • Visual
4c01efbb-bd0c-52ff-bfd5-4d319894697e | note | – – – – – – – – – – – – – – – – –
5bb3c1e5-fc40-5e55-9b45-3348da745c30 | note | FREQUENCY: Each pile
8f0650ad-4594-5447-9144-881d88ca72a7 | note | – – – – – – – – – – – – – – – – –
d9a81f05-ecf8-5479-8cd0-4ad55c62c049 | note | CATEGORY: HP*
1123222d-0b36-5b39-a79b-7e328f0fe89b | note | – – – – – – – – – – – – – – – – –
ef2c4f50-59ab-54e5-98b9-86cd5787f04e | note | RESPONSIBILITY: SPE/PE
a862cc19-4139-59ea-af80-6df0d0cc65a1 | note | – – – – – – – – – – – – – – – – –
985b2886-668e-5af2-a2ef-39931d3a9a89 | note | VERIFYING DOCUMENTS: This ITP
4b241ed0-be67-5111-9d39-649aa1f480be | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Boring Operations
5b8af99e-6c5d-59a3-9a34-31a3c89f19c2 | note | REFERENCE:
6cb2092f-3bee-57f1-bfaa-ea142eada30b | note | IFC Drawings
9e1d41b5-515e-5faf-80af-7ca645aae55d | note | 606.03 (a)
0ebfafec-d047-55b8-8b9f-fb20a3d7b14c | note | – – – – – – – – – – – – – – – – –
2c0095f2-2862-5410-8304-30fa06960bb1 | note | ACCEPTANCE CRITERIA:
8f47e637-4c94-5d3f-8a53-d9444e603c9d | note | • Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
45d3792e-2573-595f-98aa-4ded19451085 | note | • Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
9a6812e1-fefd-57aa-93ee-489b4126985b | note | • Excavation clean and de-watered (where applicable) for inspection.
2594c267-2586-5cc9-99bb-0dc569a2e9c3 | note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
2bdb2e0d-c713-592e-9607-df67e49431a1 | note | • Excavated material to be disposed of as appropriate to maintain a clean site.
6c6206c5-872e-5527-bc8d-f4612a28aa8b | note | – – – – – – – – – – – – – – – – –
b30ccc7b-c7ea-5cd1-989c-60f3bab8602e | note | METHOD:
ff2424e6-d1a3-593c-9ceb-f8eba0c46367 | note | • Measure
c7afa41d-1be8-5cc2-b24f-f687ba6d9f01 | note | • Visual
1b71b34d-9333-5ea6-9daa-44018cd4d030 | note | – – – – – – – – – – – – – – – – –
267c3edc-82f0-5db2-b49a-f79abfc15457 | note | FREQUENCY: Each pile
cad0a253-f81a-5778-a573-a340303072a3 | note | – – – – – – – – – – – – – – – – –
53757d1c-896a-5a95-930f-8ba012c46f85 | note | CATEGORY: IP
de9826b9-4550-53bd-b625-90c97b4a8360 | note | – – – – – – – – – – – – – – – – –
e2693023-ac06-53ce-9719-35dcea95b488 | note | RESPONSIBILITY:
86d7c5d0-7977-5460-bfa9-155136dc450f | note | • Surveyor
28ed8a7b-8426-5b58-ad05-260bc888747f | note | • SE/PE/SPE
f6056cfe-6072-530d-91c2-9c1903b24262 | note | – – – – – – – – – – – – – – – – –
37247ee1-c7e7-5830-9005-f9318539760e | note | VERIFYING DOCUMENTS: This ITP
0e630cdb-cc92-57ea-a7bf-7fb3249d973f | date | Date Completed:
| checkpoint | 5.2 Formwork Extension
b6797db5-8f1a-5193-960d-6162774d4f57 | note | REFERENCE: IFC Drawings
3a642acc-e973-5d2d-aa46-dd87c899619a | note | – – – – – – – – – – – – – – – – –
c64c778e-233b-5376-8d93-58cb46d78714 | note | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
537b60d5-be34-589b-80c6-8e505b721fb3 | note | – – – – – – – – – – – – – – – – –
f9d6c7d1-f73b-57a8-b17c-b1170d72b340 | note | METHOD:
f62c4634-93b5-5502-a923-081f923fa7e7 | note | • Measure
ef2e9789-c3e2-5ce9-b88b-193c4e2fa5bc | note | • Visual
923f0a66-f885-54c3-8756-8ca88e3c4c04 | note | – – – – – – – – – – – – – – – – –
2dd2653e-7e45-5caa-8540-fb632987de53 | note | FREQUENCY: Where applicable, each pile
f66a9886-1989-597a-8d65-4071e9baf443 | note | – – – – – – – – – – – – – – – – –
1965134d-646e-5749-a673-1b742a458048 | note | CATEGORY: IP
64a24485-efd7-560e-93bf-de8310b5e2c2 | note | – – – – – – – – – – – – – – – – –
0f0c593e-22e2-5351-a7e5-b3981c0e8ed0 | note | RESPONSIBILITY:
14f0ab65-6e6e-5ea9-a9f2-4904c8dfb1f5 | note | • Surveyor
02c1340f-0d7a-54ae-96d7-fd6b22c44ab4 | note | • SE/PE/SPE
1d028e00-25b3-5ae6-b554-cc6154120bd6 | note | – – – – – – – – – – – – – – – – –
93cdbda8-4d09-504c-a9e8-cb72349e854e | note | VERIFYING DOCUMENTS: This ITP
a008f0c7-beb7-54d4-9e90-344c0e389b4c | date | Date Completed:
| checkpoint | 5.3 Inspection of Pile Excavation
908cf23f-a48f-5715-9380-6f6741f5c945 | note | REFERENCE: 606.05
43730929-0469-5104-97d1-539ba8ddcfa4 | note | – – – – – – – – – – – – – – – – –
22636935-6f74-555c-accb-83e50300849a | note | ACCEPTANCE CRITERIA:
41772c49-c836-596d-beb4-93d795f80af2 | note | • Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
c4178880-fc19-50d1-8b1d-0d6d9e8c45c2 | note | • Attach: Geotechnical Field Sheet or Report
d77bd15a-2d42-5ba6-9692-9f5b46ef2821 | note | – – – – – – – – – – – – – – – – –
4723d3fb-304b-594b-bfb0-38be12df114c | note | METHOD:
e5e7e527-9976-58be-99e5-40f80b5d7062 | note | • Measure
27174d12-2b72-562b-ba02-e7d57e432b9c | note | • Visual
9a1ebe36-dd48-5550-a665-28757e5893ec | note | – – – – – – – – – – – – – – – – –
e522095b-7525-594e-9fe0-59f394ebe085 | note | FREQUENCY: Each pile
8a5c9aa4-19b2-59f6-9917-d0fb942dccc9 | note | – – – – – – – – – – – – – – – – –
b0d24629-e0bc-54ff-831f-c1a0770848d8 | note | CATEGORY: HP
44fe9f1a-8592-538a-a376-a0e9b073f85b | note | – – – – – – – – – – – – – – – – –
e8f481f0-f047-5c74-b6e2-6062226d91d6 | note | RESPONSIBILITY: Geotechnical Engineer
f7ace0eb-22c6-5e2d-aa8e-24b52ae0251e | note | – – – – – – – – – – – – – – – – –
dc33544c-3543-547d-afae-15a5226c47d1 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
e7a266df-097b-5cb4-9207-b97035b57229 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.4 Reinforcement - Placement
fb41695d-4601-5774-8c57-71aebac387d8 | note | REFERENCE:
5fc19c93-04b7-570b-887f-8eff9e08a652 | note | IFC Drawings
b9fdaf84-1330-5f0f-a850-b0b8367ccac2 | note | 611.06
55106d6f-c2c8-527c-937f-a245e8a0f34f | note | 611.09
8757a8ad-d9e6-59f3-9af0-8486e1160e0c | note | 611.10
70741d57-6763-523f-9ce2-c2f7f8063189 | note | 611.11
86d984d2-fa34-544c-bed1-7ea5c8f433ae | note | 611.12
4c82e585-c868-5105-90bd-96812e916b48 | note | 606.06 (a)
293bf9ab-dac9-542c-b580-d648291a88bf | note | – – – – – – – – – – – – – – – – –
f3c08f0f-9589-5fb6-bdb2-4d8a211963ac | note | ACCEPTANCE CRITERIA:
0f567ff5-3e64-5b63-b122-32a19e365626 | note | • The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
1ef96832-5a55-551a-8ceb-38c496149828 | note | • Projecting reinforcement is the correct length and location.
933c190b-94b3-52a5-a3cd-621be900be85 | note | • Splice lengths achieve the minimum length and are in contact for this length.
28f3d39a-6ccb-58e8-98a4-3722bde1216f | note | • The reinforcement surface condition is free from dirt, debris and damage.
c9bb9db2-51c2-59bc-ab3b-4465f37f24c9 | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
276cf8db-c4d6-5f63-8aa4-812b031c619f | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
40728aff-b0dc-5831-8e20-31693cc312c5 | note | – – – – – – – – – – – – – – – – –
7b68cae8-22fc-58a6-a69f-47637d29e8ad | note | METHOD:
9c04c931-5e42-5e8b-af6d-27ad8ae3e1d6 | note | • Measure
fe4fa412-8332-552c-ba52-490cb7a8d57a | note | • Visual
884ff9db-867f-5993-b8b2-330fe176e154 | note | – – – – – – – – – – – – – – – – –
3bf54891-f033-51bf-853d-f113f73ffdf4 | note | FREQUENCY: Each pile
0702d125-2bf3-5898-b54b-5178a030d226 | note | – – – – – – – – – – – – – – – – –
6f92b7db-1bfe-51ee-a86f-fcb05d65cd30 | note | CATEGORY: IP
113626d2-601d-5a41-8b35-fada598facba | note | – – – – – – – – – – – – – – – – –
95bfc037-64d4-54af-be32-250046e6b1d6 | note | RESPONSIBILITY:
4f38a872-d9c6-5602-a9cc-4bd5a9862d8d | note | • Foreman
3c001345-f79d-52ce-b27e-1ffbfc5a8d41 | note | • SE/PE/SPE
ed0c5e4d-1b95-51b4-8f0b-b167ff730859 | note | – – – – – – – – – – – – – – – – –
662074ae-ffc4-57bb-abeb-f06a9eadc7b1 | note | VERIFYING DOCUMENTS: This ITP
2254d36e-4dd1-5b4b-8192-1cec69b60d7f | date | Date Completed:
| checkpoint | 5.5 Reinforcement - Electrical Continuity
6c2ffd54-2acf-5267-9f86-5164124cf2e5 | note | REFERENCE:
f4e76d9c-5430-5e17-881e-8dc644f4fe6a | note | IFC Drawings
747e0529-ad44-597e-9684-d7f6c48e2fa4 | note | 610.29 (d)
c718903d-0cb8-55cb-9fc8-a469b2e8e2d2 | note | 610.43
b115b553-24b5-50f7-90ab-17aae259db3e | note | – – – – – – – – – – – – – – – – –
979818ba-544d-540d-8bc4-d47010142c4c | note | ACCEPTANCE CRITERIA:
78e47b44-8d11-5134-b149-710d33ff2d44 | note | • Pile reinforcement cage to be made electrically continuous by:
e7dd9145-1004-580b-be2f-b167866c6ce4 | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
e16569dc-fcc6-5f73-a617-cadec8df7798 | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
16c0a444-c56a-57b2-ba60-695cccb5254c | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
47f22b2d-bd2d-54a4-9404-984ffdedaca8 | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
1a69d8df-d934-50ec-8225-2c4c33b0f9e8 | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
c4cb3727-fa70-573a-90ef-f1e56bc8e7eb | note | – – – – – – – – – – – – – – – – –
50f3482d-792e-540b-bcce-475b3b72ace5 | note | METHOD:
15a1905b-0ef8-5981-bf03-18dccba90531 | note | • Measure
78d99041-3651-552e-a44d-13825c6226b3 | note | • Visual
c32ee306-a0c6-5276-9482-5e620c25f987 | note | – – – – – – – – – – – – – – – – –
20f753cb-730b-5964-a754-baaee7889514 | note | FREQUENCY: Where applicable, each pile
8981778c-3d94-5e45-95d1-35c111cda609 | note | – – – – – – – – – – – – – – – – –
9a3bb6cd-5dd3-515d-8fc6-992495f38c71 | note | CATEGORY: IP
6efb60c4-7dd4-582c-b5a7-73c8a77c852a | note | – – – – – – – – – – – – – – – – –
30fc4f1e-3e2c-574e-9706-7169f65fbcc3 | note | RESPONSIBILITY:
94d6596b-3067-5047-8928-feec3addb5d6 | note | • Earthing Engineer
776b0787-d915-5d7c-a5d0-e435ab62b959 | note | • SE/PE/SPE
0906dde0-2855-5f04-a52e-f5c041ba9f9d | note | – – – – – – – – – – – – – – – – –
8731249b-b035-597a-a7ab-48e0c6b92d5e | note | VERIFYING DOCUMENTS: This ITP
c13d8d7a-518a-566c-8612-7513718b8798 | date | Date Completed:
| checkpoint | 5.6 Cast-in Items
f0a91598-6448-57bc-b8af-f38b277da2e3 | note | REFERENCE:
bc3857fb-626c-5787-a7a7-8dae8a1d7662 | note | IFC Drawings
3700168f-c94a-5bbb-bc1e-501cbf60bae7 | note | 610.46 (a), Table 610.462
f1b455e0-5de8-5a2d-9901-2c92d942eb11 | note | 610.47 (a), Table 610.472
585df82c-bc6d-5a4d-bd19-0d3ee9f4853a | note | AS3810.1 Table 3.3.6.2
1a07fe37-4f67-5626-a373-85006a15b895 | note | – – – – – – – – – – – – – – – – –
3221b025-b921-5202-94a8-270b087f1070 | note | ACCEPTANCE CRITERIA:
a4d9b194-d415-598c-9848-0bfaabb3cbe8 | note | • All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
c44d62cc-b033-51bc-aae0-4112ac8426e1 | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
5456c545-8965-50fb-b79e-4f7c42629d45 | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
c5b6b0ff-9bc5-556d-8821-122d431eb926 | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
6458a195-221c-5ee8-ac7b-68e3caeac690 | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
b75b63b6-12fb-558e-b0e6-931064d31e30 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
1fd5e36b-a5ee-5923-885d-d4efb50e25ee | note | ii. Running dimensions of a group of the above = ±6mm
9c6ba492-b335-5918-a3d3-5aacabbbb3b5 | note | iii. Ducts and conduit location = ±12mm
d941cae4-0d08-5d92-837f-64b6f65ba284 | note | iv. Diameter of ducts and conduits = ±3mm
da8101df-b5c9-571c-9b80-e24e791e5547 | note | – – – – – – – – – – – – – – – – –
4c678050-0bb9-5753-8227-4762d3b70fe2 | note | METHOD:
5cbb054c-9bfe-5fc3-b45b-49fb4d73bea3 | note | • Measure
36e075bc-4c5a-55f9-982f-23ccc72baa72 | note | • Visual
8c534a50-b451-5ee6-83a4-0b21e571e45d | note | – – – – – – – – – – – – – – – – –
c24a57ef-338d-57b3-91da-d67e322098a9 | note | FREQUENCY: Where applicable, each pile
bc04cb35-4eaa-5514-ab3c-7c1106067e18 | note | – – – – – – – – – – – – – – – – –
7b90119f-9bdd-5db5-900c-858d5fb5df06 | note | CATEGORY: IP
a1aec0ae-3db3-51cf-80af-e622c01e660d | note | – – – – – – – – – – – – – – – – –
b4d93bb1-6dc3-5085-8293-26f0bf2f5f5f | note | RESPONSIBILITY:
d37adf33-1060-5967-9655-8318ca04949b | note | • Foreman
e035e217-0090-540f-be1d-a9d97b8884bb | note | • SE/PE/SPE
100b2ddc-6c43-5a86-8355-0eecdd95943d | note | – – – – – – – – – – – – – – – – –
e6290714-cee7-5643-865e-03ea3479b016 | note | VERIFYING DOCUMENTS: This ITP
7fc1ead9-e925-51a7-b6a6-fce481acbdd8 | date | Date Completed:
| checkpoint | 5.7 Pre-pour Inspection
ccb1aea9-6ca7-53ea-b218-af9499528574 | note | REFERENCE:
a9891590-b6c8-55ff-b539-f439bddec7a0 | note | IFC Drawings
683d2725-6d12-5768-802f-ee1f467d677c | note | 610.18 (a) (ii) & (iii)
6ef80670-3582-5f72-be8b-5d527fcf7ad4 | note | – – – – – – – – – – – – – – – – –
e9b1522e-ac3a-5c3e-9c5b-9e907f9054a9 | note | ACCEPTANCE CRITERIA:
aaae04ef-c689-58c7-8f25-b5f5a6bcbe75 | note | • Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
de845f86-3434-50d1-9344-6a7005ed30c7 | note | • All foreign material has been completely removed from the excavation.
d56c7d52-e2c5-5907-b8ae-3c35c7f67c17 | note | – – – – – – – – – – – – – – – – –
8a6aa75e-5d48-553d-b102-5e9ef49fbe8d | note | METHOD:
f0c3167d-6bd7-5381-8fe3-43d7b4e3421e | note | • Measure
57e01dd4-ce13-5445-8f2b-de1e37be6e3f | note | • Visual
6a0aea67-d1fa-5741-9e52-4e3d497105f2 | note | – – – – – – – – – – – – – – – – –
34f8de60-219e-5434-9e08-fa22065fad92 | note | FREQUENCY: Each pile
384dc97d-5246-5180-9fb8-db077d00cc5a | note | – – – – – – – – – – – – – – – – –
20e89be9-7499-5664-aa4c-1aa6951ff23b | note | CATEGORY: HP
3211e7f8-57ac-5a84-83f4-de7231dc18f5 | note | – – – – – – – – – – – – – – – – –
db64ed9b-83c2-5eac-992c-3375022d095d | note | RESPONSIBILITY: Nominated Authority
43caab17-7a72-5fdc-b4b8-f9618f690fb9 | note | – – – – – – – – – – – – – – – – –
8fd5b646-bab6-5104-9b39-44210d140ce2 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
2b0094f7-efa9-53b7-bee3-fe70277c95fa | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.8 Weather Conditions & Evaporation Limits
4ae13755-0459-5a88-862b-b2ec265b2ad8 | note | REFERENCE:
da60b163-8e44-5513-b514-041d7e9b62b0 | note | Hot and/or Cold Weather Concreting Procedure
837243e0-2032-5278-8fb0-18512655f7f8 | note | 610.17
495dcee6-6065-53b4-ad86-a1f1d80c5a8e | note | 610.17 (a) & (e)
75141da4-fffc-576e-bb8a-01e101f6b2cb | note | Table 610.171
9326bd23-5b67-501e-97a9-1a0ec8271e7a | note | – – – – – – – – – – – – – – – – –
98598ef7-ea29-5a29-8c7e-817e6935ad69 | note | ACCEPTANCE CRITERIA:
799a343f-1b38-520f-8134-012a086119d7 | note | • All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
64ae8e62-55c5-531c-aa46-4e5f71532de5 | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
5da17b89-0d0a-52e3-b0eb-b801f7d7e379 | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
d7ac17e7-4e97-508e-92c1-41f7111e4535 | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
bb4f1306-aa0b-5670-8bfa-7d031abdf776 | note | • Record: Required information on the Concrete Pour Record.
0138f79c-efa8-585c-ba68-e0f6b976b926 | note | – – – – – – – – – – – – – – – – –
d5d7887b-04d7-5c7c-afb9-274f49cace75 | note | METHOD:
efe53f2c-74c1-5899-a49b-aff7568f3d0e | note | • Measure
231c83f2-f1ad-5fb4-822b-101796f8338f | note | • Visual
e6785d06-da06-5be5-8b13-6bf2cfabebce | note | – – – – – – – – – – – – – – – – –
c074d7ed-b147-52f8-b849-9e371c8153bd | note | FREQUENCY: Each pile
047b7264-e22b-54bb-830a-ea13e5a8b523 | note | – – – – – – – – – – – – – – – – –
a85730ce-ef27-534f-a464-29cbd462dbdd | note | CATEGORY: IP
2b776525-4e6a-5dcd-8047-ccad2afa9bef | note | – – – – – – – – – – – – – – – – –
9360dad6-667a-57fb-8e03-754531855cea | note | RESPONSIBILITY:
5c07b353-4e98-57f7-9b89-bef30c66c002 | note | • Foreman
d743607e-3c9e-5708-baed-7068ffc1e981 | note | • SE/PE/SPE
6379ad95-c7c8-55cd-ba97-952e5fe11a8d | note | – – – – – – – – – – – – – – – – –
70a3e1f6-79b8-5651-b3d7-d0cd19ebfab9 | note | VERIFYING DOCUMENTS: This ITP
07515d90-b409-51b8-8ea3-8837206546ec | date | Date Completed:
| checkpoint | 5.9 Concrete Testing - Sampling Frequency
1382ce67-6442-5c1b-aa61-e326e19ff602 | note | REFERENCE:
74328e2d-331e-5997-8f59-d5f4444882d4 | note | Site Sampling & Testing Procedure
75e52dc4-202a-54e7-96e5-815be23ee4b6 | note | 610.16 (b), Table 610.161
bc6492e5-c756-5ead-b454-83a7111cd4e8 | note | – – – – – – – – – – – – – – – – –
92a280e0-b343-54c8-91e3-9fb087904179 | note | ACCEPTANCE CRITERIA:
1a785b38-c52c-59d5-8af6-a64fd799bd23 | note | • Concrete cast in one continuous operation to be tested at a frequency as shown below:
5199c201-07bc-5da1-ad6c-88c62a209bd1 | note | 0m3 to 10m3 = 1 sample
a689f10f-4bda-582c-9ebb-f7c6c1482eba | note | 10m3 to 25m3 = 2 samples
92602b1d-849b-58e9-a91b-013dbed21be8 | note | 25m3 to 50m3 = 3 samples
cefcecbd-49b9-53dd-a4c4-abc29209cade | note | 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
b9a12f12-b1cb-5d49-a7fa-ddb24c17f29b | note | • For each additional 50m3 and additional sample shall be taken.
7dede268-4ff3-5730-b6b5-0ef669c80fac | note | • Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
db88e327-3a66-582f-a5d5-a459573de9d9 | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
6a0cfb67-553c-5fcc-a96c-082b9f5e0d37 | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
65517170-454d-51a7-8f81-2eef058f0aaa | note | • Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
4ce33dbc-6d13-5020-b3fb-1e5e0101db82 | note | • Record: Required information on the Concrete Pour Record.
bdf0bd54-13af-50a9-a5af-4007b5bf58ef | note | – – – – – – – – – – – – – – – – –
87be18f7-a81b-557d-b277-4780894811c1 | note | METHOD: Test
3b2f5893-e05f-582d-8c0b-7b5e76629253 | note | – – – – – – – – – – – – – – – – –
852eca50-5c93-555b-ab86-258795766bed | note | FREQUENCY: Each pile
ea8f2c30-c385-5d66-b8f2-9edb55226947 | note | – – – – – – – – – – – – – – – – –
54bfc334-b141-5188-81d2-565f61d5c802 | note | CATEGORY: IP
b5fcb9e3-0d7d-5cde-a2bf-2ff2be3fc568 | note | – – – – – – – – – – – – – – – – –
710cdc76-9746-5928-9675-c5180ca05cb4 | note | RESPONSIBILITY:
26214e97-442a-57fc-9baf-ba2a926a479e | note | • Concrete Tester
67d349a6-8821-5e46-a034-05c84a206983 | note | • Foreman
1d8c52c9-e16c-599a-a750-8ebaf021dc8a | note | • SE/PE/SPE
6d7f106c-999d-5491-ae16-d0a98809ccf8 | note | – – – – – – – – – – – – – – – – –
f7732eda-68e9-5186-bbb9-90f1c44c1244 | note | VERIFYING DOCUMENTS: This ITP
c82d4c33-ea30-5911-8c68-d1709c6646dc | date | Date Completed:
| checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
303c18a3-aafc-555c-aedf-dcdb9165d8c4 | note | REFERENCE: 610.13 (b)
0f5311cd-fc2d-5270-8aaf-fcd70e91fc97 | note | – – – – – – – – – – – – – – – – –
e6692335-b494-5984-8e42-3a1b7b6ece48 | note | ACCEPTANCE CRITERIA:
eed3bb58-905c-5e0d-a1c9-6a52bc81abb6 | note | • Spread range = 550mm to 750mm
000e0527-af76-584b-86b1-9aab605d80cf | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
5e9bde99-95f2-5f34-94b2-622908681825 | note | • Passability = ≤10mm (aggregate height differential)
d796fb8a-3094-541b-a455-03dc12782410 | note | • Record: Required information on the Concrete Pour Record.
1bc37562-78b2-5cde-9d30-c02ac544979e | note | – – – – – – – – – – – – – – – – –
1261a5c6-4c8b-56d8-b20d-e0af62150bc2 | note | METHOD: Test
aaa9aca6-cfcc-5ee1-a6ee-82e4af00af55 | note | – – – – – – – – – – – – – – – – –
7d37e873-ecb8-5432-9dd1-8ecbf51e63b9 | note | FREQUENCY: Each sample of Self-compacting Concrete
b0d0dda2-d781-5ce1-8bcd-53504ca3b69e | note | – – – – – – – – – – – – – – – – –
cd78d7fe-d772-5aa3-a192-42b7cbf83d8a | note | CATEGORY: IP
22e1bc46-81d8-575b-9ef3-ffb8ee076f2d | note | – – – – – – – – – – – – – – – – –
3163e72a-fb4a-5c06-aa8d-6dd92d9e8314 | note | RESPONSIBILITY: Concrete Tester
55964e68-9a0c-5e51-8ef4-3ddf844f409a | note | – – – – – – – – – – – – – – – – –
ef799eb4-9997-5cbf-99d6-c2fa1cc04a09 | note | VERIFYING DOCUMENTS: This ITP
c6719e76-32f8-5c24-a0c9-ed771379883c | date | Date Completed:
| checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
e22309a8-efd7-5d10-aedc-4165fdbaa8b9 | note | REFERENCE: Site Sampling & Testing Procedure 610.16
da1614cc-ff53-5d9a-82ff-11182e2a5948 | note | – – – – – – – – – – – – – – – – –
3bdd4925-ad2d-556d-8427-df34ed6cd274 | note | ACCEPTANCE CRITERIA:
cae0acd7-cd78-57dd-a033-b2940e16e295 | note | • Correct quantity of cylinders manufactured per sample.
6773aefc-1b63-5003-87b3-36acf215458e | note | • Record: Required information on the Concrete Pour Record.
57942b8a-3d0f-5678-a346-19c5be20c6c6 | note | – – – – – – – – – – – – – – – – –
b8672514-f96e-507d-89fd-a5dd611aa725 | note | METHOD: Test
b7f6e96e-63a7-507f-91f5-cf308d9de5c6 | note | – – – – – – – – – – – – – – – – –
20b7fbfe-7a6f-5c34-b3a1-371f5365e9ec | note | FREQUENCY: Each sample
131c288a-3c39-5202-9266-69faf2868d85 | note | – – – – – – – – – – – – – – – – –
4ca6b648-9d3a-54f8-b604-cc68911b68ca | note | CATEGORY: IP
1f661a58-c6d8-5b27-a06e-338ded7b56a1 | note | – – – – – – – – – – – – – – – – –
082603b4-a64b-5353-8469-684876be589a | note | RESPONSIBILITY: Concrete Tester
90cc3038-3c79-5108-97b9-ccdf32aac757 | note | – – – – – – – – – – – – – – – – –
a30a2b2e-373f-538a-86bd-3fcb4dc6e6b0 | note | VERIFYING DOCUMENTS: This ITP
6d71efc3-3367-5ed7-8143-c3dea5fed8a4 | date | Date Completed:
| checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
b9bde0a9-e2c0-56bb-a5c9-2f44083d3c51 | note | REFERENCE:
e920d1f1-481e-559c-9879-17320836f83f | note | Piling Quality Procedure
a10fdfb0-8200-5717-8b38-16d01aec4caa | note | 610.18 (a) & (b)
80dc3c58-7689-56ab-bbce-7295add6fd7a | note | 610.18 (d) (i)
9c399a3f-4ff3-5506-a2fa-618e96496364 | note | 606.06 (a & b)
1baf149c-76c4-5d03-9720-4da2f518124c | note | – – – – – – – – – – – – – – – – –
cd5dca6d-abf6-5dbb-875f-c5231b3b35aa | note | ACCEPTANCE CRITERIA:
b8ed5be6-917f-55ed-8fd1-b2e0dbe69d83 | note | • Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
c1a383a0-40c3-5b1e-9b75-146387fd68ee | note | • All concrete batches are traceable.
2a18c480-6373-51b0-972d-4f2573bb0310 | note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
f9a1b51f-aa43-55c8-84bc-7427d2e4da2e | note | • The initial discharge is pumped to waste until a consistent workable mix is discharged.
dab8a50c-6537-54a6-8a51-c4201edeed08 | note | • The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
1eba0a67-f756-51a8-97f6-73138a96ebc7 | note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
9d39f2c6-377e-58ab-ad7c-65b3fb4e036e | note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
6f866d9c-837c-5ced-b28d-461e43a6f045 | note | • Record: Required information on the Concrete Pour Record.
4942db2c-94a3-5c5b-8f03-73d7d8423123 | note | • Attach: Concrete Pour Record
0ed615ae-5db2-557c-8143-b152be104781 | note | • Attach: Concrete Dockets
489b190e-963b-57fa-92b7-fdd3d627512a | note | – – – – – – – – – – – – – – – – –
32b4b13e-3501-5f7c-86c8-5db8b0fac90a | note | METHOD: Visual
75b35f67-d095-58a5-a983-ecf8f6a97074 | note | – – – – – – – – – – – – – – – – –
5224947d-5a5d-5706-a32a-d30689777d16 | note | FREQUENCY: Each load
2da807b5-69ef-5129-b0c4-ef29dac04bce | note | – – – – – – – – – – – – – – – – –
5f33d5e9-a7c4-5016-a9c4-75ab44fcf37e | note | CATEGORY: SP
dc36632e-6146-51d7-9a8a-c93e70fb9c98 | note | – – – – – – – – – – – – – – – – –
1aece2e7-4ee5-5058-af7a-7c3fc32a8bd9 | note | RESPONSIBILITY:
9cc3dbd6-6995-5b02-9fe3-6d62f54d39ce | note | • Foreman
ea66409b-3b62-52da-9a48-e9162ebe1ce8 | note | • SE/PE/SPE
95a280e8-1e05-5d86-999a-01f56e5d1d5a | note | – – – – – – – – – – – – – – – – –
f584ae30-c695-5e36-9405-42dc8fdfb163 | note | VERIFYING DOCUMENTS: -
037ce166-0947-5186-b04f-ab15fa2cf586 | date | Date Completed:
| checkpoint | 5.13 Surface Finishes
54b23332-f6d2-58c8-bdb8-2cfcd6d95ce9 | note | REFERENCE:
28755c5a-1ab9-5660-a909-6ee2ece84536 | note | IFC Drawings
2c6ab414-5ac8-521e-a7fa-9d648a772315 | note | 610.31
61b45c5f-b92e-5289-ad93-00007c9f43eb | note | 610.20
6024488d-5a47-52f7-924e-e50e5d6932b3 | note | – – – – – – – – – – – – – – – – –
a290f02e-9011-54c9-9e13-3687b5e78242 | note | ACCEPTANCE CRITERIA:
c4f963cc-0787-5bc2-84a7-53534be4b2d9 | note | • Surface finish as per IFC drawings.
cd9eb635-5653-5508-97c9-29ab62c51889 | note | • Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
9e557e50-6e31-5351-90b3-a39aeb7319ab | note | • Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
c1be53e4-f452-5051-823d-c98efdfcde57 | note | – – – – – – – – – – – – – – – – –
4d56bedb-05c3-598d-88b0-d2f790f7a463 | note | METHOD: Visual
dcd67dd7-5c6f-52e2-aa14-6262c9d22380 | note | – – – – – – – – – – – – – – – – –
5b42095c-06d5-5970-a086-c553e74a1c79 | note | FREQUENCY: Each pile
58216b22-1f28-5631-8176-833e4537e0d3 | note | – – – – – – – – – – – – – – – – –
64f6bf28-96df-56c2-bd8a-5c653cda82d5 | note | CATEGORY: IP
b29802c0-88a4-500f-80cb-6dc0068865ef | note | – – – – – – – – – – – – – – – – –
5b7a1df3-5357-51e3-9629-095e3014d68a | note | RESPONSIBILITY:
416d0cdc-a0fe-52f7-94d3-bcda9fc58b6b | note | • Foreman
78ce9bba-778e-56dd-9af8-678555530bf7 | note | • SE/PE/SPE
be0914e2-d937-5f0d-8091-e7b52a85b66b | note | – – – – – – – – – – – – – – – – –
fe398dd9-dcca-5197-b23e-a27b7827af03 | note | VERIFYING DOCUMENTS: This ITP
d70f9596-c0f5-5d99-aa33-031038e5e544 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Pile Trimming
57ac4ef7-3180-5f93-a597-68aaf4004dd1 | note | REFERENCE:
77cb3b31-38f0-511d-abe5-3886d87ac2e9 | note | IFC Drawings
6328244c-0eb1-5887-9925-2e1a2e30562a | note | AS2159 Clause 7.2.2 - 3
83400853-922c-580f-906d-09bc355cd34b | note | 606.06 (a & b)
f185fb5f-52cf-572f-97fc-da463f57c461 | note | – – – – – – – – – – – – – – – – –
0967324a-56da-5304-bfa8-00fcfe3f4d42 | note | ACCEPTANCE CRITERIA:
eac07fbf-ad08-5c3b-aa7a-c7c5fb225336 | note | • Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
ce62f0c3-820b-50f4-8157-a18511f8ad2b | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage
a6aad965-612a-5db0-b51d-360cb78121f9 | note | • Any weak or damaged concrete shall be removed back to sound concrete.
151dce38-db41-55ae-9b07-eeb5f414e78d | note | – – – – – – – – – – – – – – – – –
d72d7461-58e5-5480-822a-23bf5b7f172b | note | METHOD:
66f35c34-0d3a-568c-a1f9-a8bc96dd55b5 | note | • Measure
43017313-852a-5c9f-bfb2-b0e19d9dba5b | note | • Visual
621871e5-c198-5791-b7a6-c2a4fa792f51 | note | – – – – – – – – – – – – – – – – –
19280a38-6c64-5a91-bb5b-42860b9bdb9a | note | FREQUENCY: Where applicable, each pile
7a857f0e-001a-5013-ad5b-6fef219c49db | note | – – – – – – – – – – – – – – – – –
eb00e354-43c7-5564-b1e7-ef4c7061fd71 | note | CATEGORY: IP
8e307f85-9399-57b1-99e4-f1a3cf1f901e | note | – – – – – – – – – – – – – – – – –
12cce601-0234-5f90-94f1-5f5b110f2207 | note | RESPONSIBILITY: SE/PE/SPE
dbf961a5-1034-50a6-9e28-33eb80fee433 | note | – – – – – – – – – – – – – – – – –
9f509c76-b16a-5cd3-a442-c444f76fbcbf | note | VERIFYING DOCUMENTS: This ITP
a6a5ec34-0f1c-5311-8404-f6a0870a2dd6 | date | Date Completed:
| checkpoint | 6.2 Compressive Strength Test Results
018b039f-a339-5a07-a183-a13207ec9921 | note | REFERENCE:
3d2f4a8a-f69c-5639-8981-e093765e1b2b | note | IFC Drawings
a55c7d51-a36b-5d5c-ae45-1e49a14cdded | note | Table 610.05.051
20283e48-23f9-567c-8bd7-0f0db228e924 | note | 610.16 (g)
19507a1e-2f45-57a6-aa9a-3bbc068ecf43 | note | – – – – – – – – – – – – – – – – –
37e28c28-67b4-5e35-9ec2-e8e7d8199060 | note | ACCEPTANCE CRITERIA:
9c9bc6bf-4609-5c13-8a10-9e82e8de1128 | note | • 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
d404a19d-6b3b-5ec1-bd77-3a5f5e0acad5 | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
a2c58583-8ee6-5c47-9229-7452c82dd4ab | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
cab6a59d-97ec-5d00-a5fa-6a94b18cdce1 | note | • Attach: Compressive Strength Test Results
e8685b9d-b648-50b9-b42e-fdc9355d53a3 | note | – – – – – – – – – – – – – – – – –
01e3c3c3-f425-5e44-a519-ad5c1be5ac29 | note | METHOD: Document Review
ee056bc5-698c-508f-b8f8-bb143bb50893 | note | – – – – – – – – – – – – – – – – –
76a92605-10e7-523e-8544-32491ba28c3b | note | FREQUENCY: Each cylinder
99e391c5-39f3-5821-8619-e30c9a210363 | note | – – – – – – – – – – – – – – – – –
667fe7b3-1bb7-5a41-b5f0-7c45ca3d2ea1 | note | CATEGORY: IP
47e69056-4475-58b5-826f-a024c7be5973 | note | – – – – – – – – – – – – – – – – –
7b0c03d5-e352-579b-972b-12677865986c | note | RESPONSIBILITY: SE/PE/SPE
aa0536f2-da3f-5268-919b-deba77fb7345 | note | – – – – – – – – – – – – – – – – –
a212881b-6a5d-5d29-95bf-dc31525feb4e | note | VERIFYING DOCUMENTS: This ITP
79778218-cdc8-514f-bdf9-8ec579ff9b34 | date | Date Completed:
| checkpoint | 6.3 Pile Integrity Testing
826b09e2-5acf-5937-a427-c24c62581328 | note | REFERENCE:
178fe60f-99d5-56a9-b9d5-f83fd0fa29c9 | note | 606.07 (a, d & e)
0c80ff81-7c06-5070-9f44-426a57f98e41 | note | AS2159 Clause 8.8
a67840f8-85cb-5fa5-9c4f-48ecbbf35da3 | note | – – – – – – – – – – – – – – – – –
2115b309-6921-533e-8e50-119400ae4b79 | note | ACCEPTANCE CRITERIA:
363adf33-a47f-5e3b-a030-11f9370a51df | note | • Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
b9c9f5b4-f236-57da-a7ad-2314cf5b9832 | note | • Cross-sectional area = ≥95%
ddd2fff0-5d55-55c6-b96d-9000b6c4341f | note | • If any test fails, all piles shall be tested.
87cdf53a-6968-5dd8-ba4a-4d8a7663e5da | note | • Attach: Pile Integrity Test Report
8675b9ca-caf4-5895-a256-0b760b0a4439 | note | – – – – – – – – – – – – – – – – –
64b3f293-c8fe-5bd5-a181-9edfc2e05a97 | note | METHOD: Document Review
31de156a-3c3b-5a8b-b97a-4d3000ca4ac3 | note | – – – – – – – – – – – – – – – – –
db5037ec-e767-5eac-85b6-34a9be1741c8 | note | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
73e42e9a-f2d7-5a88-91e1-14a9a0a000d7 | note | – – – – – – – – – – – – – – – – –
19353df2-86b2-5bed-b2ac-8053c33a33e3 | note | CATEGORY: IP
cdb4b066-07b3-5569-9554-29997dd48a90 | note | – – – – – – – – – – – – – – – – –
ec0086b0-eaf0-5608-bbe9-91f7f455c94e | note | RESPONSIBILITY:
5feb6007-5c92-5779-ab27-ebfc1e5b1b4f | note | • Testing Consultant
13aaad43-ab15-525d-b123-32132ce3b5de | note | • SE/PE/SPE
b201d981-87af-55cf-815e-97ac3b1b35c6 | note | – – – – – – – – – – – – – – – – –
6d442335-0a49-5934-b136-8b5168f9c7a1 | note | VERIFYING DOCUMENTS: This ITP
555c01ab-f524-5c8b-bf0b-91a8a97f5338 | date | Date Completed:
| checkpoint | 6.4 Static Load Testing
50c78768-997f-5a34-ac91-dad527fa6f7a | note | REFERENCE:
f1f80288-9bfe-5312-978e-b251b1957cf5 | note | IFC Drawings
e5eb585e-983c-5c68-8052-3a36d4c639ae | note | 606.07 (b, d & e)
917e537a-d454-5cc9-90ce-e9ca60034e51 | note | AS2159 Clause 8.4
9ae5e0e0-ea3d-53ea-9e2f-bffaab8d4207 | note | – – – – – – – – – – – – – – – – –
bdd66bdc-3792-580b-a277-1a53b8381fb6 | note | ACCEPTANCE CRITERIA:
823fe2c8-5b4c-5baf-90c0-bedfd7e38c0d | note | • Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
314c269f-dabf-5cf5-9b63-e2dd09d9ea61 | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
c4b9c380-5026-5aec-b94f-5d98d27a89e4 | note | ii. Creep rate = <2mm / log cycle of time at the test load
3bc6b4a0-3194-5acb-abe1-df13493c0087 | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
67b30180-469a-5906-b41f-72d0f1bd165c | note | • Attach: Static Load Test Report
bc37be61-31ba-5a2f-b31b-aa5718ae65a3 | note | – – – – – – – – – – – – – – – – –
65789b53-aad5-5164-9b45-d54ef6d1e2c0 | note | METHOD: Document Review
a9b6920c-80c2-5a6a-b47b-77b857a83bb1 | note | – – – – – – – – – – – – – – – – –
7e156a4b-7472-5860-8917-bf6eb08ac747 | note | FREQUENCY: Where applicable, as shown on the IFC Drawings
4e2ed3f8-e41a-5271-84a7-2422fc5c123e | note | – – – – – – – – – – – – – – – – –
cc194558-c95d-56de-b720-fe593387e962 | note | CATEGORY: IP
ddba2631-47e9-5658-b192-21f95203141c | note | – – – – – – – – – – – – – – – – –
fb3931d0-472e-55e2-8048-3f98ebbecb71 | note | RESPONSIBILITY:
031dbfbd-1a66-563b-b2c7-272075a743b1 | note | • Testing Consultant
be480f71-62d4-5fb8-b72c-86f87041d877 | note | • SE/PE/SPE
8d0439c2-1728-5571-9f4b-730a69361077 | note | – – – – – – – – – – – – – – – – –
b77062a7-d772-5b49-9338-aa876453f6af | note | VERIFYING DOCUMENTS: This ITP
e2d5a759-2266-5135-9a5e-fbf28a44bd56 | date | Date Completed:
| checkpoint | 6.5 Dynamic Pile Testing
6783e93d-db0e-5111-936d-89b29a4d5829 | note | REFERENCE:
905a8cbc-70f9-5811-9e9e-7ed5be7eaa9a | note | 606.07 (c, d & e)
4148c449-24e6-5f17-a91f-b0eb878cf391 | note | AS2159 Clause 8.7
0b7523a3-9c64-57da-832d-544bbc8c08bf | note | – – – – – – – – – – – – – – – – –
394320c4-7c38-5d87-8f40-ef68fbcbb160 | note | ACCEPTANCE CRITERIA:
9eda13c5-cf5c-5df6-a846-73c3d13bccca | note | • Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
b77086dc-caf0-5267-9b9b-d4ae7270a282 | note | • Measured Ultimate capacity = ≥ values on IFC drawings
57c1eab3-52bc-5978-b49f-8dcf05a90a01 | note | • Attach: Dynamic Pile Test Report
a85b13aa-9071-5e29-b755-b246f17f43d3 | note | – – – – – – – – – – – – – – – – –
f04bab84-378b-5a98-8e27-bd22a600df67 | note | METHOD: Document Review
a4f3cee2-08b8-56cd-a28b-6a3fe2502061 | note | – – – – – – – – – – – – – – – – –
62a19c15-e109-5b71-a1aa-ec5bf030ef88 | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
aa49f960-b032-55b4-9aa9-1b331b2e4908 | note | – – – – – – – – – – – – – – – – –
ad6add9a-f414-5a2f-9260-3ab51cc518c4 | note | CATEGORY: IP
84f10c7a-a1e3-5614-bd8d-c31687d956d4 | note | – – – – – – – – – – – – – – – – –
38fd1f3f-c3c2-5b65-86cb-9982681e33e2 | note | RESPONSIBILITY:
dd87504c-d29b-5ae8-958f-90adcfab9ebc | note | • Testing Consultant
1de3a340-ac6b-5754-88b7-63568f37beed | note | • SE/PE/SPE
7023f29d-8eff-5bff-b28d-b16cb2f1ccc5 | note | – – – – – – – – – – – – – – – – –
ac175a20-c97d-5d33-a317-d9165b551d22 | note | VERIFYING DOCUMENTS: This ITP
642ad420-07a5-522f-99af-041b1cf7fc2f | date | Date Completed:
| checkpoint | 6.6 As-built Survey
4cdd0235-2ab6-53b4-b53d-619a25c432a4 | note | REFERENCE:
004e708f-0dca-50ae-9204-6d57ec2fe97a | note | IFC Drawings
0f4fbd8c-dfe2-5b38-911c-1da8a2113963 | note | 606.08 (a - c)
0e1fe053-7f9c-52c6-93b2-dc4f0736c41a | note | AS2159 Clause 7.2.2
4b8c1096-cc44-528e-bd6d-bfbc72fe463b | note | – – – – – – – – – – – – – – – – –
8e9bf5c1-77d7-57a3-9578-81e60ddc3f1e | note | ACCEPTANCE CRITERIA:
53e733e2-ca49-51c4-8994-e11c8a570709 | note | • The following tolerances apply to piles:
3c90fde0-514c-5893-98c4-f20bfbc80bae | note | i. Pile head plan location = ±75mm
a50801ab-9431-5776-9a33-e09d2ad1b631 | note | ii. Variance from vertical or rake = 1:100
eed0d59e-fb38-53ae-854e-12c3eeab07e3 | note | iii. Irregularities in straightness = 1:100
c096ed3d-29c5-5737-b9af-98a634078ccc | note | iv. RL = ±25mm
d86e1be4-38a6-5ad0-a8ac-1f7566d930da | note | • Attach: Survey As-builts / Survey Report
49801844-e8d1-5daa-b70f-26434b192901 | note | – – – – – – – – – – – – – – – – –
7485bfdf-aeb8-5a92-8814-26c7fc371eaf | note | METHOD: Document Review
aa3b6c8e-4337-5778-9fb9-e0c752f9c3f0 | note | – – – – – – – – – – – – – – – – –
83339143-0ed4-5ed2-b638-39feffd3cc13 | note | FREQUENCY: Each pile
573e4047-7f15-588a-9ad8-8febb2ef9a6d | note | – – – – – – – – – – – – – – – – –
e11eff2c-70ee-5516-8cd9-21f16ab2e446 | note | CATEGORY: IP
4db3adef-c0fb-5084-9ef9-6d1c8f868dce | note | – – – – – – – – – – – – – – – – –
5df88f8a-aa8d-59b7-af48-74c9f5f5d606 | note | RESPONSIBILITY:
02344539-6ddb-565d-8de2-0a04ea56130f | note | • Surveyor
1e8695b6-e59d-509b-983b-2f53608e8330 | note | • SE/PE/SPE
26d2248d-17a8-53dd-b8d9-fcbaaa58928b | note | – – – – – – – – – – – – – – – – –
73b814fd-49c2-52f6-8c00-78dab99430b8 | note | VERIFYING DOCUMENTS: This ITP
38988427-198f-59aa-a768-7fcf0b9be95e | date | Date Completed:
| checkpoint | 6.7 Non-conformance Report (NCR) Closure
172fefa4-2020-53c9-8a46-50f0eb5b4e2c | note | REFERENCE: MRPA Quality Management Plan
5be0cf20-429d-52c2-b9a1-f4541d32a22e | note | – – – – – – – – – – – – – – – – –
bd862dc9-136c-5aeb-9240-c21a8fc96cc2 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
9a714d65-ded6-50c6-853d-825813251398 | note | – – – – – – – – – – – – – – – – –
d8900b95-7084-5c47-9b22-1986774213d6 | note | METHOD: Document Review
f3f15852-56f3-5611-ac87-ac264dc08296 | note | – – – – – – – – – – – – – – – – –
466ba696-9e22-51b5-b8af-458a049ceb5d | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
b7c7420e-bc68-5ec6-bf80-966d3a395c88 | note | – – – – – – – – – – – – – – – – –
56ac734d-7949-54c8-9d09-e8f6787b8047 | note | CATEGORY: HP*
4adf119d-67f3-53a7-ac4d-d7b5ff5f396d | note | – – – – – – – – – – – – – – – – –
34936249-80e7-5026-aaa8-30a4773fae3e | note | RESPONSIBILITY: SE/PE/SPE
7a240b43-c51a-5c13-ba4f-fee782441a98 | note | – – – – – – – – – – – – – – – – –
53b7aafe-c15b-51f4-b76b-3148a40fb715 | note | VERIFYING DOCUMENTS: This ITP
fb3248d7-dc7b-5bb9-ad86-f3d608eb7e36 | date | Date Completed:
| checkpoint | Metropolitan Roads Program Alliance Final Inspection
3c51eba2-4d52-5331-8f96-d11d9fd4b388 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
7cae7b1d-daad-5634-bab5-092af6643f14 | textbox | Name:
6278deb0-64b7-5254-9809-24d46396795b | textbox | Position:
9f617c41-f000-5ffc-a960-c0b823d39d37 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-010-STR-CFA Piling Rev 0 | itp | ITP-010-STR-CFA Piling |  | d8587987-3159-4ec7-9010-ae91619766bf
| section | Referenced Documentation
| checkpoint | Referenced Documentation
7549e2a7-1046-5128-a10e-91343c2ab068 | note | Document Title: ITP-010-STR-CFA Piling
829cd9ce-68b2-539f-bd23-7273ed749c30 | note | ITP Description: CFA Piling
a3e3891f-72ab-5dfc-b908-3fedcbcc4552 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
8e8590a4-c64b-5d15-bf0f-a420007c3b73 | note | Discipline (e.g. CIV/STR/RAIL): 010-STR
c5911cd5-c847-5547-958a-7e4825ce43a6 | note | Revision Number: 0
78db8539-cc84-5649-873d-b352bad32f0e | note | Revision Date: 11/10/2022
abb17e33-687e-593d-b213-c4041b71f4bc | note | ITP created by: Victor Mira
c242f2c1-1528-5b71-a194-0bb14f860a5b | note | ITP approved for use by: Victor Mira
77484c8e-bf5b-5b2c-b2bf-0c5b5ba8d1b8 | note | 1.1 - Non Dependent
59903b61-657c-5520-86ad-4b5d8e5af298 | note | Reference Documents:
ca51b91d-f563-54b3-a14f-b6cee83fa8c4 | note | • VicRoads Section 607 March 2015
efcbe3d1-50ef-565b-b0b4-348dc112157e | note | 1.2 - Non Dependent
f4f5672e-d3fe-5b82-874c-ab470595ee4e | note | Reference Documents:
e3de9717-deca-5fe9-afd6-02f2ac36dbb2 | note | • VicRoads Section 610 June 2019
09f1c815-3e13-5fbb-821d-1eada10827d0 | note | 1.3 - Non Dependent
fbff4bf4-31be-5584-b573-34de19f19bb5 | note | Reference Documents:
31361a17-c6c3-55c9-8b0d-452eeb8f4114 | note | • VicRoads Section 611 November 2018
773d1ca9-1320-5171-a5ba-71c18a413b25 | note | 1.4 - Non Dependent
d0e3994c-93c5-5748-ac34-2551e78da040 | note | Reference Documents:
0df5e3fc-2b03-5075-beed-b6af53357e8c | note | • AS2159-2009
951518e2-4968-5861-b015-7025143d9606 | note | 1.5 - Non Dependent
b56863f1-0ffd-51fd-9b92-94d63cd35dbb | note | Reference Documents:
159afbb0-dea8-5732-8b69-92184f00a514 | note | • AS3810.1-2015
be4ee8f6-d48f-5d9b-b5c9-26cb5c187e4d | note | 1.6 - Non Dependent
5b912002-b8dd-5e32-9cc2-27ae2f27caff | note | Reference Documents:
3f031999-60a0-5bdb-a900-b6dba9a8ac1f | note | • AS5100.3-2017
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
e6b6fce8-8da4-5f27-9dac-7d581aebe422 | note | REFERENCE:
02941778-7648-57a5-bad2-4cbd16e9b864 | note | 610.07
42c5aa25-d29d-5f23-a7ed-da4bc9625e28 | note | Table 610.071
64a869c8-35b2-58b9-bd99-0ff242dc7642 | note | – – – – – – – – – – – – – – – – –
546cccf6-cdc6-5877-b01d-8314042ecf6a | note | ACCEPTANCE CRITERIA:
e2f9dcc9-f355-563f-b89a-d7db6a8fcfdd | note | • Concrete Mix is Registered with VicRoads.
aa449da5-e992-5a3c-b05c-0824be9fa509 | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
40674fce-2247-529a-9d9b-d8ae2978d410 | textbox | Enter: Teambinder Material Approval number
c917990f-dcc3-5504-85d1-904b7f40480b | note | – – – – – – – – – – – – – – – – –
34d4fda3-c9fc-51ad-b45e-ba78a947de10 | note | METHOD: Document Review
f4ca3ea2-1add-58b7-a6e1-10964205b9e1 | note | – – – – – – – – – – – – – – – – –
1ab6d61e-9f1e-5719-8806-73d71c5d042b | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
af7e8ea7-ab53-5f7d-bc9b-2ace8f41c185 | note | – – – – – – – – – – – – – – – – –
b8b10749-405d-5dbe-abf8-14c8f3557e03 | note | CATEGORY: HP
7e7ff1a0-777d-5406-bb6d-0e7de37abe4b | note | – – – – – – – – – – – – – – – – –
84431e09-2bde-555a-a438-a3015a221fba | note | RESPONSIBILITY: Nominated Authority
c93fcd6f-d5c3-5a6a-ad8a-1ddc7d21c29a | note | – – – – – – – – – – – – – – – – –
ee09559e-e1eb-5692-a710-921644c91d82 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
1497753e-057f-5c45-8e00-1932fab86c0d | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
e00671e0-1948-5f86-9fcc-1f5ff19f0367 | note | REFERENCE: 611.05 (a)
e6173f55-4793-5248-a24f-81a30a57b07d | note | – – – – – – – – – – – – – – – – –
5c2674fc-8ef2-5115-847f-65b682c56f16 | note | ACCEPTANCE CRITERIA:
0af97f76-e186-58c3-8c66-78ecef6e71f2 | note | • Current ACRS certification for materials and for bar processing.
0fb03936-aa0b-5e00-b8e3-c9ed45d7e5a0 | note | • Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
ef8d0620-11a0-5fc5-8489-df2e86b07120 | textbox | Enter: Teambinder Material Approval number
414f97df-6ec3-539c-86b1-72c1571d7b18 | note | – – – – – – – – – – – – – – – – –
06558eee-7b16-5813-894e-39e2c70a0598 | note | METHOD: Document Review
9c5eb10c-8f34-5480-adb0-e11f2d19e0c1 | note | – – – – – – – – – – – – – – – – –
6ea7afa9-8409-5ed6-849b-8eda0f7a1325 | note | FREQUENCY: Once for each supplier, 14 days of award of contract
04faf56f-8c61-5ed4-a741-6c76f78a4866 | note | – – – – – – – – – – – – – – – – –
48683286-273e-597b-9115-159b85f1de26 | note | CATEGORY: HP
57dc0cb8-dc62-56bf-b862-93123f6e84a2 | note | – – – – – – – – – – – – – – – – –
8d5ccd10-21c1-5512-9c77-c04ecc209be2 | note | RESPONSIBILITY: Nominated Authority
a10933ed-0e5b-55a9-9b82-c521805a1238 | note | – – – – – – – – – – – – – – – – –
2ae4b7dd-05d2-56cd-81a3-b4959357545c | note | VERIFYING DOCUMENTS: This ITP
7173f7db-60a6-53ca-86d6-1e6bf23f2c46 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros Certification
12f1996f-cb7a-589a-85e2-6c11ba309f94 | note | REFERENCE: 610.26 (a)
fdf85ddb-bfd8-5559-8ccb-94c1659fab56 | note | – – – – – – – – – – – – – – – – –
5fbf9ae7-b5a1-5a89-9d0b-9c8b8a507392 | note | ACCEPTANCE CRITERIA: Wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
d2b74115-73f5-5714-9e28-f69e32b28f92 | textbox | Enter: Teambinder Material Approval number
0ead1d8b-fb44-5b4e-87fa-71f1d2c48685 | note | – – – – – – – – – – – – – – – – –
14f684e5-883b-5588-9e3e-d7b358bfabf9 | note | METHOD: Document Review
1d233384-d965-52a8-962f-47aea34b081e | note | – – – – – – – – – – – – – – – – –
59a50cae-9b3c-542d-b223-a16f7f22e9ae | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
dedbac89-6650-5063-8daf-fdb2d546d721 | note | – – – – – – – – – – – – – – – – –
f16e7fd2-3ea4-5e06-b980-564138849cf8 | note | CATEGORY: HP
abee02ab-0f3a-5c21-ba1e-defa015e9e7f | note | – – – – – – – – – – – – – – – – –
bed15107-a396-51f6-829d-5c4b222f6b2b | note | RESPONSIBILITY: Nominated Authority
c612f2e9-85df-5798-811a-9b6dcc8f6148 | note | – – – – – – – – – – – – – – – – –
d19337af-80fd-58d3-b3cf-14c26487cba1 | note | VERIFYING DOCUMENTS: This ITP
3edca008-bacf-5ee6-9060-52819c5b42e1 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Working Platform certification
e0b63556-ee4f-5dd1-909a-7fd4bd7b35bb | note | REFERENCE: Piling platform design
5a106df2-c6f1-5174-88c8-32124664bc0d | note | – – – – – – – – – – – – – – – – –
214ffec4-6820-5070-bc8e-e8267d1f572c | note | ACCEPTANCE CRITERIA:
44fdf388-06b9-5e03-960b-4ec2dc59db2b | note | • Satisfies minimum plant bearing pressures requirement.
792d43a4-53df-5de3-b108-4ec5cff74a39 | note | • ATTACH: Piling Platform Certificate
6128419d-85ba-5d7e-87d5-aecae35a0797 | note | – – – – – – – – – – – – – – – – –
961f24a5-0351-5da3-b38a-7f5a7c841b3f | note | METHOD: Document Review
2bc93b80-e817-5206-b8ba-af4a731dc38d | note | – – – – – – – – – – – – – – – – –
02e59985-2f1b-5776-a993-3fde57ee35f2 | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
7e764fb0-a55a-57cd-9907-5875431a9916 | note | – – – – – – – – – – – – – – – – –
e2f3d338-13da-5ce8-bd6a-6159cf530f26 | note | CATEGORY: HP
1ad651c9-1d37-5668-acbc-5acb6784ddfe | note | – – – – – – – – – – – – – – – – –
a41a5ade-8cf5-5b25-80d2-ddfdfe82316b | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
e5f9177b-58ee-5685-abe4-ab7963f606d9 | note | – – – – – – – – – – – – – – – – –
a3ce368e-59a0-5e28-ac94-d82a53627289 | note | VERIFYING DOCUMENTS:
37ea9857-b872-5922-bc6e-de9ef7d376b5 | note | • This ITP
cc0ce12c-e583-5eb7-866b-f8905449b72e | note | • Platform Certification
2fc8c7ef-5774-5379-9fe9-5e9e6b1f0711 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Concrete CFA Pile Design
53a75d3d-f1c6-5dee-abc7-388e5d7bfdd2 | note | REFERENCE:
00f1d1fe-3661-5068-9bd7-290d01f937d2 | note | 607.01
bb9f2e02-c05a-5a0d-9e7c-8009bd251bee | note | IFC Drawings
fc651d42-9301-57be-9427-3eaf45a39240 | note | – – – – – – – – – – – – – – – – –
ad95baa6-a171-58bc-93c8-1999e2fec21b | note | ACCEPTANCE CRITERIA: Concrete CFA piles shall not be used in foundations for bridges and other structures on or over roads without the approval of the Superintendent.
ddf46129-1132-5f78-a3f4-86b1812d5c46 | textbox | Enter: Teambinder Approval number
28aefae1-8796-5f80-94c4-9228e921094a | note | – – – – – – – – – – – – – – – – –
44a96bea-390d-5db1-a08d-45462ee47421 | note | METHOD: Document Review
1876c45b-02ea-5f58-a12c-e8cab2baed4a | note | – – – – – – – – – – – – – – – – –
8c14a288-abf9-5db1-9977-35fae1c122fa | note | FREQUENCY: Where applicable, once, 4 weeks prior to the commencement of piling
12ae9c6d-a1f6-5277-9c87-540380c09663 | note | – – – – – – – – – – – – – – – – –
41e1dfb2-1c62-515e-93fa-6c7feae7b993 | note | CATEGORY: HP
6ca52adc-0c29-5097-ab25-005d7b5353ab | note | – – – – – – – – – – – – – – – – –
8306cf6a-121d-523d-9eb7-f5e6338f9743 | note | RESPONSIBILITY: Nominated Authority
8c9ed939-9394-5a54-8dd2-073b4c57ad4c | note | – – – – – – – – – – – – – – – – –
8001036e-30b9-5f83-8487-9c09751669f4 | note | VERIFYING DOCUMENTS: This ITP
1dcaeaa8-5cdd-5d26-a411-3deb430bf052 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Piling Operations Work Procedure
8dd3e6f7-8991-5693-9b27-9c5f60863dde | note | REFERENCE: 606.03 (a)
c16a0ca2-612a-5133-b870-13cffb87b9ba | note | – – – – – – – – – – – – – – – – –
4be58bac-163f-5738-aab5-9c94eb51b47c | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
5709bc97-c884-5e50-b3e9-7e084d6ee105 | textbox | Enter: Teambinder Approval number
1fc6d3c0-f428-54a2-948e-a80423d7f794 | note | – – – – – – – – – – – – – – – – –
fe88073e-d76a-5107-b03d-a74ee544f63f | note | METHOD: Document Review
c770750d-a667-596a-9007-274f2670a892 | note | – – – – – – – – – – – – – – – – –
0bb7a3fb-b6fd-58c7-adf9-bbac79d099ba | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
6ef99a5f-23ad-5f4b-9644-f094ff3b551b | note | – – – – – – – – – – – – – – – – –
3a3b6efc-b3c6-523c-96a6-2b763c4f21bc | note | CATEGORY: HP
e26958c6-d2c8-59c1-9d88-9fb9bacc4dbe | note | – – – – – – – – – – – – – – – – –
b6cbead7-f9c4-5b58-a3bc-9099571995e4 | note | RESPONSIBILITY: Nominated Authority
dc823df7-22ec-52aa-907f-1cb488d8a5f9 | note | – – – – – – – – – – – – – – – – –
0bffaff7-8973-593e-b0e1-146d84be7c72 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
0585a0ad-e8c9-52f4-981e-4e9fe0c70729 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.4 Casting Under Water Procedure
adaf1930-341c-5ca4-aa2a-6581b9aa7d42 | note | REFERENCE: 607.04
9a1c2593-ebbb-5334-bf20-c452ff1806a1 | note | – – – – – – – – – – – – – – – – –
cbdadcf4-eb9c-5551-ab74-975a8c5405d3 | note | ACCEPTANCE CRITERIA:
f29f9d68-5cba-5430-a784-abe61fdfbe33 | note | • Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority.
3c12781b-39c1-5b38-ada5-b08d6ff04aa4 | textbox | Enter: Teambinder Approval number
5dee6dcf-9002-5513-80de-8c2c2add1375 | note | • Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
450fd102-b4ce-52f4-b67f-b4f135ca325f | note | – – – – – – – – – – – – – – – – –
0c81f093-6e12-5053-9bf4-4ee5b6385bb1 | note | METHOD: Document Review
ef53942d-a378-5beb-a227-a864254c0de1 | note | – – – – – – – – – – – – – – – – –
a1f18d49-71c4-51bc-aad4-5abbcf398daf | note | FREQUENCY: Where applicable, once, prior to placement of concrete
4b38b0ac-45a7-5fa1-b0a0-2744f18a225b | note | – – – – – – – – – – – – – – – – –
41647c13-2d4a-5b1f-9615-f939d2f9a73b | note | CATEGORY: HP
3479660c-dbe8-5c79-83d2-2c93bd051e93 | note | – – – – – – – – – – – – – – – – –
01acfe2e-152e-5878-a759-e3f95c7b014e | note | RESPONSIBILITY: Nominated Authority
a8e1112a-4101-5a9f-943a-4a604cc54f71 | note | – – – – – – – – – – – – – – – – –
87275e00-5a93-5f2a-aa3f-a5a7ef3e324f | note | VERIFYING DOCUMENTS: This ITP
32edc87a-f08a-5bbd-be24-918f3226e1a7 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.5 Dynamic Pile Testing Procedure
fa11e898-2ae0-56cc-898a-46e23bac7d2e | note | REFERENCE: 607.07
2236c0cb-63ea-5f63-8e20-39dd269e474b | note | – – – – – – – – – – – – – – – – –
10b00ece-f10e-5d05-8500-dc8f8d6a3c53 | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
e50c1d6b-7844-5e7d-8b7b-0b7d8ce03d80 | textbox | Enter: Teambinder Approval number
e5e8ed85-cb67-5e0b-9e00-dc079188247a | note | – – – – – – – – – – – – – – – – –
e53c48e9-5dda-5eee-a48f-7cfd31d41e26 | note | METHOD: Document Review
ab393b26-b5b4-52d5-adf0-e2c299fcc187 | note | – – – – – – – – – – – – – – – – –
a07d0533-3df3-5940-bc33-b1857116021d | note | FREQUENCY: Once, prior to testing
5fc58fa0-0d79-5cc8-8909-903a5d73759a | note | – – – – – – – – – – – – – – – – –
14024248-73a9-5b55-b1cc-b5a667484b3e | note | CATEGORY: HP
956394d3-c147-58ba-bc49-157d15d17515 | note | – – – – – – – – – – – – – – – – –
29f4143e-b62b-57c6-89f3-710b4e65ef32 | note | RESPONSIBILITY: Nominated Authority
189d1a13-889c-5173-9e94-7808cd796671 | note | – – – – – – – – – – – – – – – – –
1ddedc7c-9105-5a8d-9c60-fb26ae9aedee | note | VERIFYING DOCUMENTS: This ITP
07522865-dbb1-5abf-aa9b-568ec56ec1a4 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.6 Pre-qualified Pile Testing Consultant
788ada95-27c5-50fa-80b8-be6b7e910288 | note | REFERENCE: 607.07
b611765d-7bc3-5e72-ae1b-938cea159663 | note | – – – – – – – – – – – – – – – – –
aadc1e89-c5d8-5cbe-b030-da7da2fa1db9 | note | ACCEPTANCE CRITERIA:
b994803f-5670-5693-85ef-f4201023b125 | note | • All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
9c6e8a25-6619-5f8f-b2f3-d9b1a19d530a | note | • Details of the consultant to be submitted for review to the Nominated Authority.
c3f4bf77-9642-559d-8740-77dc39203aca | textbox | Enter: Teambinder Approval number
ec7c5367-0e11-5164-b8d7-215a69cc0561 | note | – – – – – – – – – – – – – – – – –
6170bf87-b6b0-521e-8ccf-da8d3a5affe1 | note | METHOD: Document Review
251bbea5-bd4e-577f-904e-a5c36f270897 | note | – – – – – – – – – – – – – – – – –
c00e152c-344c-55fd-91bc-59fa67316b4a | note | FREQUENCY: Once, 2 weeks prior to testing
9c915265-5db8-57e4-8624-c93b1780917c | note | – – – – – – – – – – – – – – – – –
4c3db164-5867-5277-896f-aae60d1ceab6 | note | CATEGORY: HP
89877b47-2eb7-5b85-903d-d2f185984bc5 | note | – – – – – – – – – – – – – – – – –
242621d7-0878-5ae4-a2b4-73570b82f38b | note | RESPONSIBILITY: Nominated Authority
8f40897b-59cd-53a2-b7da-c5e8022fbc1a | note | – – – – – – – – – – – – – – – – –
afac3d60-ceaa-5b63-b3cc-8a1ef53b6eff | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
38d8f895-c53f-5f3a-aa81-4b9217ab7be3 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.7 Reinforcement Welding Specifications & Qualifications
c2a6103e-1117-54c3-bd3f-b8fe70b3435d | note | REFERENCE:
06e7d05c-b184-5ead-8c0f-accc386321ad | note | 611.13 (a)
2e171c67-7a17-5a87-b666-81a320090ee8 | note | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
59a3a6f4-4409-5862-a5e3-99dadabe1cb1 | note | 611.14 (b)
65848c5f-4b3a-5aaa-a9d9-c0c49122c2e6 | note | – – – – – – – – – – – – – – – – –
0b58663d-6fef-51eb-a786-6471378d3894 | note | ACCEPTANCE CRITERIA: Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
ccced383-60ec-5b49-adc4-f7d22c788287 | textbox | Enter: Teambinder Approval number
873c70f6-c2dc-5a45-94a7-4137745aba81 | note | – – – – – – – – – – – – – – – – –
d2d3f91b-11db-5d4d-8658-7e2bdde03b51 | note | METHOD: Document Review
835d64a5-8630-54a5-a85e-5855838d8f4d | note | – – – – – – – – – – – – – – – – –
294fdc0e-1f51-59b2-a30d-1c25244e5e4a | note | FREQUENCY: Where applicable, once, prior to welding
5a1e1f0b-94b0-5150-bee5-664e1d16b662 | note | – – – – – – – – – – – – – – – – –
9b30ba64-c36a-5aab-b38d-54fe892a62c5 | note | CATEGORY: HP
d3b5a346-f8a8-50b7-a42c-3cb8db26281d | note | – – – – – – – – – – – – – – – – –
36cc2f55-76c2-5cdc-b635-5fba2488c564 | note | RESPONSIBILITY: Nominated Authority
4090a053-f7dc-5d42-be19-4df2dd34d1fc | note | – – – – – – – – – – – – – – – – –
f913e472-edbb-57fd-83d7-5b4b071516c4 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
879c350f-bd62-5d59-b298-8421f286ca8c | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
8302eeab-9c92-5ed5-aeb4-ad268bc74c40 | note | REFERENCE: MRPA Quality Management Plan
599df973-8d56-5efb-8b4e-93ed11d1805e | note | – – – – – – – – – – – – – – – – –
068d7f47-7473-59f2-b6de-8f3752d6e8d3 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
15120bad-5da1-5e76-92ad-a7d1f16a8f3d | note | – – – – – – – – – – – – – – – – –
3261dd6c-dfa0-5f52-9ae0-d7c20841c2c1 | note | METHOD: Document Review
82f5eb63-6921-5d57-9e33-bb28552db41b | note | – – – – – – – – – – – – – – – – –
f6a7ebd8-2678-5bff-9e02-0f77d8003b96 | note | FREQUENCY: Prior to starting Works and at regular intervals
046db6e5-928c-5627-84a5-933a82e81cf9 | note | – – – – – – – – – – – – – – – – –
f447ce0e-70f9-5e08-ae38-611530345a27 | note | CATEGORY: HP*
669ad4e8-2bad-5c43-a00b-de0bed470544 | note | – – – – – – – – – – – – – – – – –
58173127-3081-5a2e-bd67-e18abaec5173 | note | RESPONSIBILITY: All
4cbd6afd-9620-5694-9999-65b06c0c08b9 | note | – – – – – – – – – – – – – – – – –
780bb735-8028-5925-8d1a-150e92689f5b | note | VERIFYING DOCUMENTS: This ITP
5bb6c783-3c40-5756-aeff-daeb30fc283c | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
b45bbb32-07c0-5931-bd7a-23f0a6bc9cc8 | note | REFERENCE:
306f490f-d869-5a1a-aa5b-be8c803a2af3 | note | IFC Drawings
6b1a2e93-114e-59b2-af65-affbf445eff4 | note | 607.06 (a )
e0d1a6dc-605a-560c-bf01-a2a5c851e5c1 | note | – – – – – – – – – – – – – – – – –
3779384e-9434-5ed1-a5d6-a04890ff7c94 | note | ACCEPTANCE CRITERIA:
576b9328-dc02-5d89-aa90-9cd579096680 | note | • Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
0624a16b-e9a8-573f-a295-3df8f000d1ad | note | • Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
76cd3dde-d7d6-5cb2-8960-cef5e53d086a | note | – – – – – – – – – – – – – – – – –
f10a042e-df12-5d84-9eab-5a16fee74acb | note | METHOD:
8292fd6f-1447-51a6-b7d6-ad5c4f65dc1e | note | • Measure
96419738-7015-5f15-9c04-124beb25dc0c | note | • Visual
bd720192-a0ee-5a03-992b-2e9ccada0a51 | note | – – – – – – – – – – – – – – – – –
5ed23c66-a65f-5365-9515-198c571bd089 | note | FREQUENCY: Each pile
e3d52180-e50e-55c6-bbf2-80a4198abf20 | note | – – – – – – – – – – – – – – – – –
2c6ae7a2-1650-5df1-ba02-dede6b1839f7 | note | CATEGORY: IP
4d5bf8c0-bcc6-5657-b4d7-da4c1b230ab7 | note | – – – – – – – – – – – – – – – – –
b16c38a4-292a-59fe-99c0-2d87190d771e | note | RESPONSIBILITY:
3ed2cd5f-dc8a-51c5-84e6-bac46553656b | note | • Surveyor
1ced7f52-19a7-5f2c-b0ce-283c39697543 | note | • SE/PE/SPE
231182e8-6dd0-5ed5-8820-7b3ad7abb97a | note | – – – – – – – – – – – – – – – – –
d2581f63-3ecc-57b2-bb05-58b70c304167 | note | VERIFYING DOCUMENTS: This ITP
01c03029-12ba-5faa-ae92-b7abf547f174 | date | Date Completed:
| checkpoint | 4.3 Protection of Adjacent Piles
1d64cdb3-027e-58b8-9ce9-9e226690c2ee | note | REFERENCE: 607.05
8c6ccfc8-8e6e-5505-9a10-3476eaa84cb3 | note | – – – – – – – – – – – – – – – – –
6b6c829e-eac7-5762-b7c4-7f9c1a1da551 | note | ACCEPTANCE CRITERIA:
d2bd5f92-2320-54e4-98d2-aaff52067904 | note | • Pile construction shall not result in damage to adjacent newly cast piles due to ground vibration.
677f2e83-3b76-53cd-9099-33464305d338 | note | • Pile excavation shall not commence within 2 metres or three pile diameters (whichever is the greater) of a newly cast pile until the concrete in the newly cast pile has attained a strength of 15 Mpa
064456fb-daf5-52fd-833c-a040b008b4a1 | note | – – – – – – – – – – – – – – – – –
c45d1635-3ace-5877-9b23-229fbc11c967 | note | METHOD:
960a68d3-c459-5044-871d-1f96e7a4ec79 | note | • Measure
43cef934-a07d-5754-b6bd-a42cc10fe0ca | note | • Visual
3ae0e3a7-4b22-5e8f-8f30-971ceca5f721 | note | – – – – – – – – – – – – – – – – –
393ca6d8-87bf-5655-a8c2-b8da1ae9cf2e | note | FREQUENCY: Each pile
44d5ac73-4fbd-5c64-a805-d7a44cf9b98d | note | – – – – – – – – – – – – – – – – –
af307444-7c0c-5039-8e7c-09f632fd1bd1 | note | CATEGORY: HP*
7bc8e781-1b23-557b-9516-e7eb2c67357d | note | – – – – – – – – – – – – – – – – –
52a498e0-b698-5458-9036-ad20ce22944f | note | RESPONSIBILITY: SPE/PE
96a733bf-171d-532a-b4bb-ce1abb3391b0 | note | – – – – – – – – – – – – – – – – –
a9639976-9f8b-53cf-a4b2-3bb7df2d0c6e | note | VERIFYING DOCUMENTS: This ITP
8b44bc78-4df6-52b8-b782-398c7a243648 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Reinforcement - Inspection
a317cc07-4c31-5101-8a6a-a5bf585088a4 | note | REFERENCE:
704ee794-d7ff-5e36-9047-aa68723ccd0f | note | IFC Drawings
58d841e4-4b6f-5f48-9257-79151c34ecd3 | note | 611.06
c4679b0b-9d4a-5849-b149-3d9bbd61dc1b | note | 611.09
7afb3a5f-68d7-52e8-b770-09dbc2127557 | note | 611.10
75a4e45c-2be6-538f-9918-4788142c1743 | note | 611.11
7969bbc6-e371-5872-b839-fa26491ca880 | note | 611.12
434c010f-434f-5148-9805-51442ba596ff | note | – – – – – – – – – – – – – – – – –
6cd9e403-507c-5074-b814-e99f2f197d60 | note | ACCEPTANCE CRITERIA:
d79f2ba9-c416-5fb8-b024-846142230387 | note | • The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
b9e4b6c3-9cc5-5cf6-acd2-5f399feb3446 | note | • Projecting reinforcement is the correct length and location.
4f0c5ec8-4a96-5a82-a970-17eee18de989 | note | • Splice lengths achieve the minimum length and are in contact for this length.
e4d48e21-acf3-5a3b-8cd7-d22e3e6184d5 | note | • The reinforcement surface condition is free from dirt, debris and damage.
e56cc545-3984-5dd1-bcc6-05bf2c76a436 | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
85e20c21-4d32-59c6-be4c-a900970b705c | note | • The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
71c484d9-91c6-59a7-913d-e2492505d438 | note | – – – – – – – – – – – – – – – – –
8ad2d9d0-9182-5e30-9dca-7617a26c82c7 | note | METHOD:
d8a382c7-449a-54c3-b8e2-6b0ba800754b | note | • Measure
39976510-4255-5558-b19b-c465a462ab99 | note | • Visual
6435c942-cd71-526b-bef7-536ec966e38b | note | – – – – – – – – – – – – – – – – –
4c9ad975-cdfb-5d54-92cf-e9c1272483a2 | note | FREQUENCY: Each pile
0388204d-35cc-57ef-a3bd-cd408d589426 | note | – – – – – – – – – – – – – – – – –
15b82808-81d1-5dca-bb33-f661da694f3b | note | CATEGORY: IP
f355eb71-a635-50e0-9886-f2b44fa0e411 | note | – – – – – – – – – – – – – – – – –
6259d671-7169-53d9-bc36-e3b3f4d14a76 | note | RESPONSIBILITY:
c8128fde-d471-5210-b1d6-e1be535beeb0 | note | • Foreman
ef2bec1b-521c-5a95-9e78-65802320f696 | note | • SE/PE/SPE
63f5b36b-2022-591f-8b1d-48b692f03997 | note | – – – – – – – – – – – – – – – – –
6e83879b-9c0c-520e-a16c-67c18f9dec3b | note | VERIFYING DOCUMENTS: This ITP
68a3f965-218e-5569-98d1-8d302f04b79d | date | Date Completed:
| checkpoint | 5.2 Reinforcement - Electrical Continuity
4691d0bc-5b63-5918-af84-88b4ed8da2bd | note | REFERENCE:
48bf9f5e-bb57-5865-910c-d744546060ff | note | IFC Drawings
3a9b409f-899d-5f98-b589-3b6dd566fa11 | note | 610.29 (d)
376d8ef0-ba56-5ce8-a22a-16608553e4f4 | note | 610.43
f34a45c0-afa9-5595-99bf-46a8991d7456 | note | – – – – – – – – – – – – – – – – –
d79e96bf-da9e-5e68-8d4e-e0373f384fc0 | note | ACCEPTANCE CRITERIA:
5556b74b-3f04-5894-8679-d068339da059 | note | • Pile reinforcement cage to be made electrically continuous by:
5e525698-dc16-5e9c-8dfa-ee118dc60d55 | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
3333ecbf-d145-5721-a4ca-ed5de17a6f6e | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
c2762147-3a6a-5ce0-b476-04991b2763b2 | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
bbcc0550-5479-52ad-92b7-1e8b6c9aa05e | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
e25fa60c-b638-5ceb-82af-b03ff06aafaa | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
23a77bff-413d-5b97-b49d-d40713df65b3 | note | – – – – – – – – – – – – – – – – –
00c94f15-caf3-5996-8bb0-3960297a154f | note | METHOD:
45c3bde8-cf59-5cee-b0f2-c34ff6a756e7 | note | • Measure
993feaa7-7e0b-5897-86ea-d697c78de124 | note | • Visual
866f4884-915d-50b8-83d6-ee331c6de02e | note | – – – – – – – – – – – – – – – – –
901807b6-6971-5dfb-855f-236595a6cc2a | note | FREQUENCY: Where applicable, each pile
263f00de-a20b-564c-9e6a-2b94f0f412f3 | note | – – – – – – – – – – – – – – – – –
d7ef6155-f64f-5c7c-9221-b8a91801b9b3 | note | CATEGORY: IP
8fb3cbd3-6182-5e9c-bf1d-9259426dd22b | note | – – – – – – – – – – – – – – – – –
fbbb9d26-a6d1-5a45-a4fa-68c1e8467161 | note | RESPONSIBILITY:
4e1235fa-bf8e-5dc7-9117-19db9b262676 | note | • Earthing Engineer
7adb1e9c-23f0-53e4-ad9c-e1e001767198 | note | • SE/PE/SPE
f7809c77-b2b2-513b-a5b9-587ae7a08cbb | note | – – – – – – – – – – – – – – – – –
5ab7dbbf-22cb-51f4-8512-c86672c88137 | note | VERIFYING DOCUMENTS: This ITP
471af065-cc9f-5c03-8aed-2eeae4f6a89b | date | Date Completed:
| checkpoint | 5.3 Augering Operations
a921fdb3-e9e5-5e9b-8398-c01208c3524c | note | REFERENCE:
ca7cb904-6bdd-5c31-bc20-cdea9c869343 | note | IFC Drawings
d7d5d020-c066-5f71-9e5b-905205b0aa8a | note | 607.04
3ba9bdd2-0f8e-5d7d-944e-16cf846aa29b | note | – – – – – – – – – – – – – – – – –
3d9f7769-4cd7-5513-8a3c-f450fada6116 | note | ACCEPTANCE CRITERIA:
220d0c7e-4b01-50f1-acd5-3aa16e278270 | note | • Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
56e19195-e209-53d7-a8b9-ac86e0f18c63 | note | • The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process.
622069a3-6c0c-5d1a-85df-0517e8e464aa | note | • Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
f34c9a33-0137-5a77-bb87-3ffdaacbf6c9 | note | – – – – – – – – – – – – – – – – –
027f3f2f-861e-5a69-a282-bba3f7459a62 | note | METHOD:
aedfa89c-77ea-5dcd-80c0-464606d812c4 | note | • Measure
7e15b893-83dc-51e4-bb02-961a2a6af3e9 | note | • Visual
cc8e3298-63c2-5175-a250-2b1920713499 | note | – – – – – – – – – – – – – – – – –
b59de282-e015-574a-af72-8964e7789b43 | note | FREQUENCY: Each pile
85c956ef-d04a-5636-a6cd-02095e6c9487 | note | – – – – – – – – – – – – – – – – –
ef471b89-63f8-50a2-8489-0c6c11543e3d | note | CATEGORY: IP
2ad93007-4bee-5794-b13f-9f9a20d54e25 | note | – – – – – – – – – – – – – – – – –
ee20b9a7-762c-54db-a4a7-4890b62538a7 | note | RESPONSIBILITY:
f93ed0fb-1f9b-55b7-a48e-3e641a519a3e | note | • Surveyor
594bafd6-b6b9-54db-8af2-21bd1c532211 | note | • SE/PE/SPE
4e23f366-151c-5d4f-a24b-b79f0964a8e1 | note | – – – – – – – – – – – – – – – – –
cfb57e13-c643-5bde-a158-4fb6e48335e3 | note | VERIFYING DOCUMENTS: This ITP
984ffcac-1de4-51db-88fc-c22bec98d789 | date | Date Completed:
| checkpoint | 5.4 Inspection of Excavated Material
5a83c3f2-49ed-56b8-9044-e2cff5ce3fdc | note | REFERENCE: 607.04
9dac00db-3dbc-5882-8ec3-91e2dcece376 | note | – – – – – – – – – – – – – – – – –
66351ea9-0f28-5615-9ac6-3f97cdeb1e8d | note | ACCEPTANCE CRITERIA:
2611c619-80c5-5a16-8c0d-13fc4327db44 | note | • Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
2ebd6efd-8e9c-57d7-a2fa-83b3016df793 | note | • Attach: Geotechnical Field Sheet or Report
27eed6a3-96cd-5299-8acc-e12ccc20bd76 | note | – – – – – – – – – – – – – – – – –
458ace61-0fa4-52ad-9552-fcc92387bd34 | note | METHOD:
198dd56e-b7ac-52d7-98ab-6677eb617627 | note | • Measure
4144e958-a656-5202-8589-b6b62f0aa1ce | note | • Visual
09c5a053-74d1-58c1-8b65-06858d0f5795 | note | – – – – – – – – – – – – – – – – –
d6e09971-9e10-50b1-aec3-ecdef1a8b876 | note | FREQUENCY: Each pile
fdf1a5f4-f2cc-5ec2-8480-e214fc993887 | note | – – – – – – – – – – – – – – – – –
8b7aff69-9e5c-5b73-9640-13f76b650c5b | note | CATEGORY: HP
db2c8fa2-650b-52b9-9670-e61b5d149377 | note | – – – – – – – – – – – – – – – – –
e65617e9-14e0-5bf5-bea2-8fc44fb49219 | note | RESPONSIBILITY: Geotechnical Engineer
402e9f50-f852-58cd-ac4c-42de7230be31 | note | – – – – – – – – – – – – – – – – –
df67e5d8-1536-5322-bf03-021aebf78b8a | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
4c17856c-adb2-5176-bf86-00f6d91fac47 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.5 Increase in Depth Beyond Design
a855b737-51fc-5b03-9fa9-342834f74eee | note | REFERENCE:
71c7e04e-219f-5dd7-b9fd-38e962698242 | note | 607.04 (a - d)
25eeb2aa-76cb-5f6c-a39f-fdbde7ac1f4c | note | Piling Operations Work Procedure
b5ac6dce-1073-5653-b08f-bae7037c0cf5 | note | – – – – – – – – – – – – – – – – –
3f6a9713-4ac9-5269-a6b1-280f887ba7f1 | note | ACCEPTANCE CRITERIA:
369ce681-dbd0-5a93-8575-c5fad3402ba8 | note | • Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity.
576383c3-35d6-5223-b606-2acd065600ee | note | • A full account of the changes shall be submitted for approval to the Nominated Authority:
bcf8c6ed-018a-5ac5-8d43-8122c1f91de1 | note | • Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
4d45158b-59ad-579c-98cc-06228cceae80 | note | – – – – – – – – – – – – – – – – –
2e037ad5-f085-5a02-9771-2cebebdf4241 | note | METHOD:
7fe612b5-c064-530c-9c7a-7984070cf3e7 | note | • Measure
6ce4b377-19af-5925-8a21-c5f7245347d5 | note | • Document Review
632bc1dd-7505-58e2-9569-64dc570b3475 | note | – – – – – – – – – – – – – – – – –
184d1af8-8201-5cbe-9706-f8baa8932722 | note | FREQUENCY: Where applicable
87f69df9-003a-5c35-8ba7-b8aa41ea3ade | note | – – – – – – – – – – – – – – – – –
b778d35e-7f6d-5712-a9b7-dfb7bd71b18f | note | CATEGORY: HP
a3cfc03a-813a-5b34-b832-faf00a80e306 | note | – – – – – – – – – – – – – – – – –
0f075fb2-8eb4-55a2-a1b2-da052abd3f10 | note | RESPONSIBILITY: Geotechnical Engineer
13b37d69-50b0-591c-90db-10dd95c560d2 | note | – – – – – – – – – – – – – – – – –
5797aefa-a794-56d7-8e7d-e9f4d9b7c6c8 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
62f1e31e-48a1-593c-8304-0cbf06cfb97e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.6 Weather Conditions & Evaporation Limits
ae0c29d3-aa4e-5418-b8f8-c866285802f8 | note | REFERENCE:
1e4423e9-f903-5bbf-a21e-9562dffe212a | note | Hot and/or Cold Weather Concreting Procedure
5c8cb70e-b527-5173-803f-f63af5af7fec | note | 610.17
5066f9bb-29c2-5d14-aa39-e32287a06c0f | note | 610.17 (a) & (e)
5c7a8d98-9e18-5e47-85a2-62c4abbf8639 | note | Table 610.171
8cd017f2-7721-5d92-a380-41d8fcedae2d | note | – – – – – – – – – – – – – – – – –
6ca1427a-264d-5aeb-ab1d-3681881d5c2d | note | ACCEPTANCE CRITERIA:
439ccf99-836b-5a20-854d-61a0e6e35d8c | note | • All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
eb303a5b-5422-5766-8bdb-69be56a1991c | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
c75d1bd1-94c9-5462-9d47-a9e1e125dbd9 | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
fd01ecd5-8240-5d64-bd71-aa45525d3ab4 | note | • Record: Required information on the Concrete Pour Record.
2c83067c-601b-52c2-bac4-75d1e7a041cc | note | – – – – – – – – – – – – – – – – –
5912be87-7efe-5580-82d2-833fad139b0e | note | METHOD:
39f932e5-5bbb-5db7-9d37-7ad9ff9060dd | note | • Measure
4ad23dc0-0a6f-5d48-97a1-d0641d57d432 | note | • Visual
1f584f6f-72b3-58a7-8df7-7409bf28883c | note | – – – – – – – – – – – – – – – – –
fabded33-5ef7-5195-bc39-16b7567e3a49 | note | FREQUENCY: Each pile
519358c4-953c-514c-81cc-487036dc626f | note | – – – – – – – – – – – – – – – – –
b00227e8-f367-5790-856c-ae4bbe45af68 | note | CATEGORY: IP
7ef9aa49-1211-53b1-9700-c61614103741 | note | – – – – – – – – – – – – – – – – –
bdea8d1a-6c5a-5269-bbd0-17df9e119840 | note | RESPONSIBILITY:
23150932-2c09-5134-8794-fe04d1e14037 | note | • Foreman
745eda9d-ad46-5cae-a503-e089c7bfa6a7 | note | • SE/PE/SPE
f238c93c-132c-567a-859f-3e5bb595d1c9 | note | – – – – – – – – – – – – – – – – –
5b0f68cf-9085-5f13-a72d-7ae9ebbc4887 | note | VERIFYING DOCUMENTS: This ITP
f5f62cf1-d161-539b-9b74-50a2b94a626d | date | Date Completed:
| checkpoint | 5.7 Concrete Testing - Sampling Frequency
7967d8be-3f57-5bb9-8a06-b25832a3f251 | note | REFERENCE:
56b5cb11-2918-5c6b-a7fc-e6ad049322e4 | note | Site Sampling & Testing Procedure
19f965dd-fff0-518c-8f30-fd0a30393a22 | note | 610.16 (b)
2bd06326-37a1-50b0-bb63-590b22db6db8 | note | Table 610.161
475ffe7f-8364-5409-938c-2d82ec3190de | note | – – – – – – – – – – – – – – – – –
c68e842d-3664-5d16-8fc4-51c863ec9908 | note | ACCEPTANCE CRITERIA:
f2710a07-d46f-539b-8f14-2d9ac7a7d5f1 | note | • Concrete cast in one continuous operation to be tested at a frequency as shown below:
2b40e9b9-19ab-52c0-99d5-b7be9e4e86b3 | note | 0m3 to 10m3 = 1 sample
0986ea46-fe81-55bf-bd4c-4986160cf962 | note | 10m3 to 25m3 = 2 samples
71e54ada-afcf-55d7-98f9-148fbd472c63 | note | 25m3 to 50m3 = 3 samples
63ebf705-414d-52e1-b3a3-5c4d1f2f01f8 | note | 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
1d9daf79-4272-5e23-bfec-1ee823b5e453 | note | ○ For each additional 50m3 and additional sample shall be taken.
f305a696-c919-5881-965b-ecc06059f342 | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
54012a0c-cd2d-5767-a760-1ed21fdc5dff | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
2198f436-e4ef-514b-87ed-0d1f4c542b75 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
32d2e0c7-3bb9-5d3a-b769-5c3eaaaa9220 | note | • Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
77dad52a-d886-538c-aa71-8e81f0dfaea5 | note | • Record: Required information on the Concrete Pour Record.
c2df939c-cf73-56b9-99a6-6aca6d1bb0f5 | note | – – – – – – – – – – – – – – – – –
374909e6-96f7-5f5a-93dd-e86e4e731e3a | note | METHOD: Test
5161e2c5-b1c6-5f6b-b4e4-eea719c5a3b2 | note | – – – – – – – – – – – – – – – – –
be6f720a-2f56-5f56-be82-db8c958e57e9 | note | FREQUENCY: Each pile
54a7c94f-8e47-50ea-b87d-9299f00fdaf4 | note | – – – – – – – – – – – – – – – – –
e52a3e8c-c948-5cd0-af47-9159e5c38d4d | note | CATEGORY: IP
0640c8fc-8741-59a2-a798-dcdafeb1b2eb | note | – – – – – – – – – – – – – – – – –
ac3f5774-7c35-52a1-8d52-4cfd022d587f | note | RESPONSIBILITY:
097df871-4080-58fa-aebf-8f521c535b67 | note | • Concrete Tester
5953449c-b379-5857-ae53-07984ab93ad0 | note | • Foreman
1831fdba-04ed-5c95-8f2e-0655c217d0f7 | note | • SE/PE/SPE
edeb24c7-0be0-58f3-bdff-f21bc6ced4e3 | note | – – – – – – – – – – – – – – – – –
159f0875-3416-574e-b2c9-6d81d410c560 | note | VERIFYING DOCUMENTS: This ITP
a667bdd8-f43f-5732-a346-e6f18416a77c | date | Date Completed:
| checkpoint | 5.8 Concrete Testing - Spread, Passability & Viscosity
d5e355c3-22f9-52cc-b809-f4c1ed76585f | note | REFERENCE: 610.13 (b)
ecff2e8d-026c-5151-b80f-eadcf3e8e0fd | note | – – – – – – – – – – – – – – – – –
bd0de7cb-a5c8-5c1d-a884-230cf704e170 | note | ACCEPTANCE CRITERIA:
00d2db4e-4341-5b13-aafa-b6e42e952acc | note | • Spread range = 550mm to 750mm
000c2286-64c6-577d-b251-38b809c434e9 | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
28021447-fb10-5e4e-9c56-65c4e2377f7b | note | • Passability = ≤10mm (aggregate height differential)
7db46fee-0622-51dd-b812-7911d526f4bc | note | • Record: Required information on the Concrete Pour Record.
a0520175-9d5b-5b14-868a-c5d981fabe8d | note | – – – – – – – – – – – – – – – – –
815c7f3c-9344-51fb-bfa8-8c77b8a38f8a | note | METHOD: Test
8a77633e-1840-57fb-b887-7a9f8d6f2973 | note | – – – – – – – – – – – – – – – – –
02ae2ee9-286a-5b4e-b4ad-4d78f3fee441 | note | FREQUENCY: Each sample of Self-compacting Concrete
192bdff0-8e4d-5c7c-b4ee-de4c3f958cf8 | note | – – – – – – – – – – – – – – – – –
0bb5974c-1f0b-520b-a18f-84d4225344e1 | note | CATEGORY: IP
93a69d61-fe63-5291-9ce0-e7ab74f5b682 | note | – – – – – – – – – – – – – – – – –
bb6ddc24-8bde-585f-a7a5-26530198548a | note | RESPONSIBILITY: Concrete Tester
6d6ed1b8-77c2-5de8-af6d-dd676abfb44f | note | – – – – – – – – – – – – – – – – –
d16bbabb-4f8e-5517-8d5c-e42af874dfb5 | note | VERIFYING DOCUMENTS: This ITP
eb3c5250-7317-5a0d-92bf-f543cb7b2ebb | date | Date Completed:
| checkpoint | 5.9 Concrete Testing - Compressive Strength Cylinders
f596f955-3d1d-5182-a9f2-1ec1b1a1ec83 | note | REFERENCE: Site Sampling & Testing Procedure 610.16
939ed0e4-4e99-5dff-8c7a-b0a72bd34979 | note | – – – – – – – – – – – – – – – – –
197a5ff2-cf1c-5fd4-90d4-7a40c462c3ad | note | ACCEPTANCE CRITERIA:
4d932947-d527-57e9-9da5-db917263027e | note | • Correct quantity of cylinders manufactured per sample.
d79dfd7e-9754-5db1-8a42-f030f2283c3d | note | • Record: Required information on the Concrete Pour Record.
5190d5ec-7672-531a-a00a-110b3923f9d4 | note | – – – – – – – – – – – – – – – – –
c7bb4aed-9674-5ac1-9f77-9c55233c5843 | note | METHOD: Test
c0d861aa-f6af-5172-b64a-6968078be6ee | note | – – – – – – – – – – – – – – – – –
7c003c06-7956-570a-90ff-4b098f85e492 | note | FREQUENCY: Each sample
998e5ad6-c4f6-5a73-9779-a21aa679162b | note | – – – – – – – – – – – – – – – – –
63e066a4-f27e-5f2b-bced-524794556e33 | note | CATEGORY: IP
87aea465-b9dd-5ecf-8850-50e98fc6156d | note | – – – – – – – – – – – – – – – – –
463d5e38-b224-56b1-872b-e07e4886072f | note | RESPONSIBILITY: Concrete Tester
d203b627-5522-5180-949f-81877647550f | note | – – – – – – – – – – – – – – – – –
b2f49e6a-fd81-5e13-a44f-c2958c239f66 | note | VERIFYING DOCUMENTS: This ITP
37d4856a-e143-5915-98f5-cf558e8f5175 | date | Date Completed:
| checkpoint | 5.10 Concrete Placement & Compaction
0ec5fa26-0da7-576c-a858-0edf998d907d | note | REFERENCE:
f69b9d2e-1f89-5db6-aa87-081193826c69 | note | Piling Operations Work Procedure
bf071714-e565-5fb0-8088-0b66570c0553 | note | 610.18 (a) & (b)
f53fdbf8-af6c-545c-ad04-d9842e93eed9 | note | 610.18 (d) (i)
25fc0217-47d9-51b7-b802-aeee4060c0a4 | note | 607.04
6e77fbc1-8ecc-59cd-95a4-f3472516e993 | note | – – – – – – – – – – – – – – – – –
de388217-acb1-58cb-94e3-3e19f1615c31 | note | ACCEPTANCE CRITERIA:
f7e0cff1-0e3e-5d75-bfc1-50f2cd45e3cd | note | • All concrete batches are traceable.
9a1956c3-2f9d-5f1a-91cc-0874b5bbd9f7 | note | • The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted.
8382a9b7-75ca-5c1a-a3ec-992d41afca41 | note | • The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions.
4fe5445f-badb-5a55-a9ee-be5829addf33 | note | • Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete.
c7fe3dd3-4f0b-57bd-9386-5560e4817e37 | note | • Concrete shall not be dropped freely from a height exceeding two metres
d84088ac-76bb-5f96-9af1-18459bafaac4 | note | • Record: Required information on the Concrete Pour Record.
0c7a8c59-20b8-5787-bedf-853edbac8a57 | note | • Attach: Concrete Pour Record
cd33c132-d30a-5130-bec5-c9da5e8c790c | note | • Attach: Concrete Dockets
86051b19-70c2-5fbd-8837-dacbf5805d98 | note | – – – – – – – – – – – – – – – – –
e70d4b0c-4533-56f5-8ec3-a3336341bbd1 | note | METHOD: Visual
a4754f56-37db-5641-9b61-34529fc7eab7 | note | – – – – – – – – – – – – – – – – –
8b8e45c9-3473-5e9b-8ecb-32130947876c | note | FREQUENCY: Each load
8723953f-eda8-5384-baca-943f459af1a1 | note | – – – – – – – – – – – – – – – – –
47efc508-9a07-5895-9800-e2b354fe070c | note | CATEGORY: SP
60ac7446-428c-5ca7-9370-b1d8b6fbd9f7 | note | – – – – – – – – – – – – – – – – –
ab6a4a8d-5808-58f4-8ddf-cfa713d6834f | note | RESPONSIBILITY:
337cd787-cc13-5f3b-aff6-130e48442ea7 | note | • Foreman
1a53db02-61bb-5abb-a3f2-f51cb8cc411f | note | • SE/PE/SPE
ea4972cc-9421-5951-94ef-831ef1594ef7 | note | – – – – – – – – – – – – – – – – –
4c6bf13d-c485-5b23-b1d2-00a41cc02e14 | note | VERIFYING DOCUMENTS: -
3cf4ff1a-7a68-53eb-ab7b-ef8495a2bf4d | date | Date Completed:
| checkpoint | 5.11 Reinforcement - Placement
1cb698d0-16ea-5d2b-87d5-f76d74477aad | note | REFERENCE:
afb08fd3-376b-5bc0-80af-bb238b3acd20 | note | IFC Drawings
9e680f1a-666c-5edd-ace5-7da0068e2c6c | note | 607.04
43faab1a-d765-595e-b929-d02705d875c8 | note | – – – – – – – – – – – – – – – – –
8b7560fa-31dc-525c-b042-e696c8c8a96c | note | ACCEPTANCE CRITERIA:
dcc03959-ee8e-5c56-8744-7067baacdeb6 | note | • The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
1407a344-42aa-5c25-8faf-00ff1c2a9786 | note | • Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
38726d7f-acdb-5baf-a2fb-3d0432b17f2e | note | • If the cage cannot be positioned into its final level, the pile shall be rejected.
1c6a29d5-8c62-58b5-a325-8ed459f1e8fd | note | – – – – – – – – – – – – – – – – –
8e376135-1b57-5307-b7c6-51c39fb85741 | note | METHOD:
4d48fdfc-5ef5-573e-ac53-fafb82903dd7 | note | • Measure
baae46b1-becd-592c-85b3-ccc05352b4c9 | note | • Visual
5ce2e790-b230-5e4a-863c-f02b75b87509 | note | – – – – – – – – – – – – – – – – –
7e20dbd2-3bfd-5d2a-b698-1f68f31c9453 | note | FREQUENCY: Each pile
e763bbfd-2310-5b6b-8ae8-bd00496ecd94 | note | – – – – – – – – – – – – – – – – –
8f3341e3-2116-560d-aadb-24ced8b28117 | note | CATEGORY: IP
f6a43967-6328-5305-8292-50a77b05c2e5 | note | – – – – – – – – – – – – – – – – –
0d9c4cb2-59c2-5a89-83be-4796dffb1218 | note | RESPONSIBILITY:
5c5c9e9a-55b8-5d3a-b085-3ba808850a84 | note | • Foreman
1386bda7-f2fa-5c01-a23f-a07b3cc6fd68 | note | • SE/PE/SPE
752d8156-2365-5770-a14d-d43a93afbff5 | note | – – – – – – – – – – – – – – – – –
706b675f-1c2d-5c4f-9ca8-05b627b41991 | note | VERIFYING DOCUMENTS: This ITP
012ab89c-3272-5e94-b7e3-ef40ba19c058 | date | Date Completed:
| checkpoint | 5.12 Cast-in Items
e7de76c3-770d-505a-ab50-d7510b8078b6 | note | REFERENCE:
2c6525f8-507e-5303-9172-5399a2b5f742 | note | IFC Drawings
ceca86a3-8a3a-546f-a48e-17833f75c57a | note | 610.46 (a), Table 610.462 (November 2018)
7732b4c7-df30-5179-8416-1d80bb625441 | note | 610.47 (a), Table 610.472 (March/June 2019)
c01f0ec0-9ed3-5e72-8753-4eb4770b795b | note | AS3810.1 Table 3.3.6.2
c4320404-6aa6-5ade-b36f-f3287bd6e3fd | note | – – – – – – – – – – – – – – – – –
ef1bd43a-2ab8-5f02-9c85-74e51ebfb455 | note | ACCEPTANCE CRITERIA:
483dcf48-f027-5bb2-b11d-0b52f3391436 | note | • All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement.
9e49a545-a47d-5f02-842e-4d62bab7798e | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
7c04f32e-a147-5dd6-858f-d561ee43ed1e | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
5cf0d91d-a586-50ab-9524-561c751d683e | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
93d31c42-4e0c-5518-aa0e-5e5cc0641806 | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
98c9cca6-cb96-504b-ae76-0891c577acdf | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
0bb35c35-6759-5dc6-9adc-901f77c2bb7b | note | ii. Running dimensions of a group of the above = ±6mm
f53fb823-f6b8-5a0f-b67f-b7e3bf1aeedd | note | iii. Ducts and conduit location = ±12mm
e4298a1a-ab6f-545f-9902-1d7783f06bed | note | iv. Diameter of ducts and conduits = ±3mm
a6936804-f4ed-5473-aefc-c65774bdca8f | note | – – – – – – – – – – – – – – – – –
751b549e-703a-51aa-8e13-08be24130edd | note | METHOD:
ba874f29-db59-50e6-bce3-6ead5058d2f2 | note | • Measure
72682f0e-1ad2-5ab2-a3ff-c62041b02bbb | note | • Visual
e08d3602-c4c7-5da6-986c-02894d8170d2 | note | – – – – – – – – – – – – – – – – –
0fa2d6ba-dbfc-5629-8a6a-4a67a26b168d | note | FREQUENCY: Where applicable, each pile
fb74863b-f70d-508d-90df-3ee6c2276316 | note | – – – – – – – – – – – – – – – – –
9a9bf514-3be1-59f9-b699-57652e9e0eac | note | CATEGORY: IP
b47689bd-1883-5307-929f-19e439b6ea13 | note | – – – – – – – – – – – – – – – – –
fd0694e6-3eea-560e-9682-bea2a2d8c5f0 | note | RESPONSIBILITY:
22a32e95-d2e5-5170-929c-a554cee3b332 | note | • Foreman
da9e6e84-0196-5740-87d3-0863871d1169 | note | • SE/PE/SPE
94eac999-fda0-5b0b-9171-22cf13eaaa83 | note | – – – – – – – – – – – – – – – – –
b39b4ce0-c3f6-5f8b-a33c-6cd09b23ea38 | note | VERIFYING DOCUMENTS: This ITP
6c11d63e-9f75-57c5-832b-db96418f0277 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Pile Trimming
82bd880c-d9d8-5726-bc10-4e2056cccfa1 | note | REFERENCE:
09c73800-63b6-5979-81cb-fd961726ec01 | note | IFC Drawings
a0593b7f-2020-59b8-a675-3d5d7f640b8e | note | AS2159 Clause 7.2.2 - 3
ae7a6d23-16d7-5faf-8638-230052fcd703 | note | 607.04
456ec6b1-b425-5fbe-918c-6ca2e78f9547 | note | – – – – – – – – – – – – – – – – –
8f5d9a85-d326-5c47-8d42-4ed7fbe0d5a9 | note | ACCEPTANCE CRITERIA:
cac0dff9-e1c6-58f0-8136-7f8f03a69cf1 | note | • Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
b8739967-9753-50ba-9594-b43ac82a52de | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
36a10a42-fd7b-51ee-97ec-4af28f9d2010 | note | • Any weak or damaged concrete shall be removed back to sound concrete.
9cfe4231-2910-53f2-a551-922c902229b8 | note | – – – – – – – – – – – – – – – – –
aed9b7a5-9984-5943-b633-8da9c090b4f1 | note | METHOD:
b6473fc2-0fed-5146-ac6d-5c50748905c8 | note | • Measure
5717891c-854d-5e1b-8463-72ffdd11dd4d | note | • Visual
7e41eb21-2ed8-5980-9478-5263b982c540 | note | – – – – – – – – – – – – – – – – –
ea1e29a3-cbd2-58db-a5eb-724bf6af3959 | note | FREQUENCY: Where applicable, each pile
6de5062c-d9ad-5a68-a589-bfccb1116ed9 | note | – – – – – – – – – – – – – – – – –
5e874c96-15f9-5624-88e4-219fb6441073 | note | CATEGORY: IP
cb994f1b-605d-5d9f-99e9-165423037d48 | note | – – – – – – – – – – – – – – – – –
6a2fa62f-a4b8-5b89-8ec1-cb14517e7ac5 | note | RESPONSIBILITY: SE/PE/SPE
b154257a-7e4d-5063-aaa5-ba8bf72b8aa5 | note | – – – – – – – – – – – – – – – – –
9ccc8c54-15dd-5677-9b89-aeaeff2be9fa | note | VERIFYING DOCUMENTS: This ITP
e47ea150-51f9-5b35-8901-9103d6a4bdad | date | Date Completed:
| checkpoint | 6.2 Compressive Strength Test Results
af471017-df3b-55fc-bb09-d3733561516b | note | REFERENCE:
8aa23041-53ac-5c97-bb49-124338dcc74a | note | IFC Drawings
0d86b191-5a16-5e8c-879d-fe7837973f31 | note | Table 610.05.051
304c27d0-0b95-57c6-a35b-ea4dede68dae | note | 610.16 (g)
7b28e8a1-22c6-5081-9303-1cac6a1bd853 | note | – – – – – – – – – – – – – – – – –
c19fc38f-5c20-5a94-a8a8-f398d926036d | note | ACCEPTANCE CRITERIA:
851ada47-8a1c-5c56-a0c2-a0b3041f90a9 | note | • 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
d2a784cb-a72d-5067-924c-b213c66cd269 | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
0b898c91-f3ef-54f4-85e6-11c0a05a2deb | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
25d4360f-d89c-507b-936c-5b3a9d37a5f6 | note | • Attach: Compressive Strength Test Results
f5499451-bde1-5ff5-9e1a-078e878edd14 | note | – – – – – – – – – – – – – – – – –
259189d0-0fdb-58c2-98ca-264e69165285 | note | METHOD: Document Review
e9d6b5d2-8932-5b32-8eea-38012180606d | note | – – – – – – – – – – – – – – – – –
a024356d-8df6-558e-b2e6-93b7d2faa7a3 | note | FREQUENCY: Each cylinder
b8beb025-c470-51f6-a44d-820373d33c93 | note | – – – – – – – – – – – – – – – – –
8a727588-8b73-5612-90e1-a98d2bee2a81 | note | CATEGORY: IP
728ec606-f936-5c99-9de5-0c56e82e6ed8 | note | – – – – – – – – – – – – – – – – –
d9e5d656-9705-5c70-a046-0e0b580ccf53 | note | RESPONSIBILITY: SE/PE/SPE
878055bc-3262-5ccc-88b3-e73c3ea8ed0f | note | – – – – – – – – – – – – – – – – –
6f283d6b-dcca-59c6-8369-26a49bd8be87 | note | VERIFYING DOCUMENTS: This ITP
b7f264fd-0351-5b40-9639-e49be0dd80d0 | date | Date Completed:
| checkpoint | 6.3 Pile Integrity Testing
30c45b8f-4c5a-5e70-a883-c1a898c9c447 | note | REFERENCE:
00431c98-bcaf-5f0f-9860-2f9b78659d26 | note | 607.07
6880e675-d994-5d1d-a7b6-499c606f4095 | note | AS2159 Clause 8.8
5bf6e88c-2144-54e4-93e1-5d78dd0eae3c | note | – – – – – – – – – – – – – – – – –
bfc8d353-f54e-57ff-b59d-bd28db43c2a3 | note | ACCEPTANCE CRITERIA:
fab6b7e3-3799-5beb-8f0c-fb7a494f40aa | note | • Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
607e08b6-49e5-5cd6-82ea-6349b9e1f0fb | note | • Cross-sectional area = ≥90%
c048a9a2-8f67-5b85-8a53-261150a30f10 | note | • Attach: Pile Integrity Test Report
b8852c2f-7b5d-5251-b42c-7a9afb9406d9 | note | – – – – – – – – – – – – – – – – –
46d54237-8b21-59a2-9d9d-82a381f092ce | note | METHOD: Document Review
c20bcba8-985c-5880-a6c4-e6fb1886a48d | note | – – – – – – – – – – – – – – – – –
1700e520-132c-596b-9bc2-5788819b453f | note | FREQUENCY: Each pile
a9abe824-a6b8-57e8-91ca-8722002243fb | note | – – – – – – – – – – – – – – – – –
fbe72c67-5ae6-530d-a709-544e29c81e6d | note | CATEGORY: IP
2c9f90ed-153d-53db-a146-2aa8afdb0751 | note | – – – – – – – – – – – – – – – – –
2f72e8fb-47ad-5203-a678-7583b7b88b57 | note | RESPONSIBILITY:
4de2e63e-19f2-585e-b3d8-5e59b378f715 | note | • Testing Consultant
20870682-b9fc-58f4-8729-025ec2ca561b | note | • SE/PE/SPE
eb1bbf41-a752-5e22-afe9-b25d0d3aefc0 | note | – – – – – – – – – – – – – – – – –
281b6870-8f1a-584a-acbc-306d653b9dc8 | note | VERIFYING DOCUMENTS: This ITP
66a6190f-ef54-5ce9-9e8c-c5b7d5b48f42 | date | Date Completed:
| checkpoint | 6.4 Dynamic Pile Testing
aa903e34-0384-5d85-a1c1-0f5a6430e7b5 | note | REFERENCE:
f45c19bd-6f7a-534b-b4a5-0b22e6132d18 | note | 607.07 (b)
0854a456-1f17-5a0e-91df-9ecf92038b3a | note | AS2159 Clause 8.7
25001f79-e485-5a05-a0a4-4b89f29c0995 | note | – – – – – – – – – – – – – – – – –
62e6ba13-8957-5fa0-9f19-7ee099d6beab | note | ACCEPTANCE CRITERIA:
3e545087-18b5-5aa7-a538-bfb39339c126 | note | • Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
0487dfe9-407a-5d9f-bd92-875aa88186d9 | note | • Measured Ultimate capacity = ≥ values on IFC drawings
5046b69a-46a1-51c7-9320-081169d2cac9 | note | • Attach: Dynamic Pile Test Report
0abba7d0-f500-59ba-93a9-7d0e3a1aaab6 | note | – – – – – – – – – – – – – – – – –
7aa6f84f-7dc7-5730-b491-7b43518b172d | note | METHOD: Document Review
ac22590a-22dd-5a55-93d0-22f5078b1bf4 | note | – – – – – – – – – – – – – – – – –
02c066a4-e840-5f9c-97cf-77923de04da8 | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
b31bf7e8-e774-5171-a0d3-3d97eb77de40 | note | – – – – – – – – – – – – – – – – –
18f101cf-e60d-5372-987a-d1c294fdf636 | note | CATEGORY: IP
147e0887-49e8-5bd6-b7ae-cd0e87e6ce6f | note | – – – – – – – – – – – – – – – – –
a6087886-a7f8-5c16-9a7a-ce559df1fe73 | note | RESPONSIBILITY:
30d10fd0-a141-5567-ac6c-2e0c4ca75c7a | note | • Testing Consultant
be709147-ef28-55ef-ad49-c1c827eec6c9 | note | • SE/PE/SPE
70258f9a-ceb5-54de-b55f-482873159124 | note | – – – – – – – – – – – – – – – – –
0c7ee861-30d1-57a2-91d2-b757c48dd30b | note | VERIFYING DOCUMENTS: This ITP
3618b106-4261-55e8-9489-62de5a72142e | date | Date Completed:
| checkpoint | 6.5 As-built Survey
65f3a90e-3c25-5cfe-9935-a5f6d5795ebf | note | REFERENCE:
d2dfc16a-f709-5b69-b5a7-a0723a84b310 | note | IFC Drawings
f03a8b4e-6279-5634-87fa-579b1957ea70 | note | 607.06 (a & b)
ec00adde-b345-57a4-8348-c227fe87db75 | note | AS2159 Clause 7.2.2
c98eec6b-a9e6-5880-8a5b-36050df736af | note | – – – – – – – – – – – – – – – – –
b073c97b-be1b-5b1c-901b-618f69e74aca | note | ACCEPTANCE CRITERIA:
a2d39406-9e8f-57a9-9a3f-0efefc977e55 | note | • The following tolerances apply to piles:
a8fd3f9b-3f05-59e0-aae8-b0da18f722ed | note | i. Centre of pile head plan location = ±75mm
f34313fa-b0e7-535b-a868-24b7c4541478 | note | ii. Variance from vertical or rake = 1:50
41a28fc2-957a-51c6-a7c1-c2e9c95a6d91 | note | iii. Irregularities in straightness = 1:100
8b861926-1af4-5f19-a48b-5e6095321bbe | note | iv. RL = ±25mm
879cc518-6e2d-5be5-bf00-c8fa3e70234c | note | • Attach: Survey As-builts / Survey Report
e060c0f8-72c8-5dab-81be-e3318b31e6d8 | note | – – – – – – – – – – – – – – – – –
3d42751c-3195-5c0f-9ae5-8182f9fede7f | note | METHOD: Document Review
f0d64098-e671-500a-85fd-1f4c889948f7 | note | – – – – – – – – – – – – – – – – –
5c86c900-0e2a-5b59-8c76-979a7bb5d039 | note | FREQUENCY: Each pile
1a578bc1-377a-5290-86bf-db86e51906cc | note | – – – – – – – – – – – – – – – – –
188fe300-e28d-5ba1-87d2-5e0042b9f5ba | note | CATEGORY: IP
30ce56f9-a385-5336-86a5-1b14770601d3 | note | – – – – – – – – – – – – – – – – –
ab248bcc-1a96-53a7-b5b0-3f05c4bc26e1 | note | RESPONSIBILITY:
51de8547-3225-5b03-9544-a05d867bb37c | note | • Surveyor
8c18e31f-5592-55ef-907a-f58227e2d8e9 | note | • SE/PE/SPE
99faf69c-25f8-5cfa-ae74-923b2c3b9ae0 | note | – – – – – – – – – – – – – – – – –
3af3cb09-72eb-55ae-a720-52a817d4f23a | note | VERIFYING DOCUMENTS: This ITP
7e8f2162-2ed5-51d9-99de-1c61a367f2d8 | date | Date Completed:
| checkpoint | 6.6 Non-conformance Report (NCR) Closure
829edf49-6b0c-598c-8902-b25319af2de3 | note | REFERENCE: MRPA Quality Management Plan
ded89642-63c9-50be-9d48-b140c230e69a | note | – – – – – – – – – – – – – – – – –
7895ba42-8f35-5704-b18a-2473ec8099e0 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
2e97aa56-cda3-5655-afc6-f3345854e92b | note | – – – – – – – – – – – – – – – – –
ae9a14d9-5f16-51d5-a836-4d0dafd82530 | note | METHOD: Document Review
92f01a70-f1b7-5e18-8f52-5dcff51e4ab9 | note | – – – – – – – – – – – – – – – – –
46603636-1513-5519-9f06-e1fbae93f456 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
d2db17aa-dd73-5915-beaa-a4f86c9cb8b6 | note | – – – – – – – – – – – – – – – – –
ff1361ef-3f08-536a-a8b9-c2950301dc16 | note | CATEGORY: HP*
407241dd-58cc-591a-8153-b735b9a69352 | note | – – – – – – – – – – – – – – – – –
cac8e338-73fd-5e96-adf0-d5d24b861094 | note | RESPONSIBILITY: SE/PE/SPE
fd36a17b-065a-568e-b715-7c7a5728e5ac | note | – – – – – – – – – – – – – – – – –
11e821e2-4a07-5ae5-a47c-db419cdbb221 | note | VERIFYING DOCUMENTS: This ITP
f731fdbe-b344-57ff-9c58-7838c5848fed | date | Date Completed:
| checkpoint | Metropolitan Roads Program Alliance Final Inspection
e1420f2c-78d3-5b3b-ba7a-1cdd08d7d278 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
6ad3d4db-5758-5799-adc6-c68a1311ebe6 | textbox | Name:
d67a933e-3ebf-5859-8190-fb9719da2fb0 | textbox | Position:
ffd24bed-16b9-57e3-a900-431932d2e06d | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-011-CIV-Horizontal Directional Drilling-SEW Rev 0 | itp | ITP-011-CIV-Horizontal Directional Drilling-SEW |  | 332c00dd-19de-4c57-9867-94146d38bbaf
| section | Referenced Documentation
| checkpoint | Referenced Documentation
594202cd-753b-5596-9863-0bb6960a7a4a | note | Document Title: ITP-011-CIV-Horizontal Directional Drilling-SEW
2537f71b-7e3e-5e8d-a6e0-93f79e7123e1 | note | ITP Description: Camms Road Horizontal Directional Drilling-SEW
358409e2-c10a-5728-8883-367fdc6c2812 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
cbc62f4b-5f42-5e2d-9d34-5b9698fad27f | note | Discipline (e.g. CIV/STR/RAIL): CIV
3a41fccd-d231-5c59-9b6c-ec0c0db376f4 | note | Revision Number: 0
1710aec5-d79a-5e7f-9061-daa68fcf2e60 | note | Revision Date: 19/10/2022
9a819ced-bfee-5246-bcf0-69b23a06da50 | note | ITP created by: Michelle Lim
907cfa7d-9421-5a51-ac4b-60be5b3eefef | note | ITP approved for use by: Victor Mira
cec8e546-510d-5b0a-b8e6-e54fdb5f9916 | note | 1.1 - Non Dependent
066a2041-b978-5836-8f65-fee1884afee9 | note | Reference Documents:
8b1b0b6d-bc9f-597a-8506-a0052467461c | note | • IFC Drawings:
4d2e2828-35ae-51c3-989f-9c51209fdfad | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
| section | Preliminary Works-Materials
| checkpoint | 2.1 Encasing Pipe
f27dc97a-465d-5b65-a8da-19527d9695d9 | note | REFERENCE:
b486b0c9-74ff-5f55-b5bc-9bd16b25e384 | note | IFC Drawings:
b19a9169-897d-582b-9778-3042552d041b | note | MRP-052-C-SME-DRG-64-MPK-CUT-1041
27c4b792-9f0f-5d71-bf1a-07683f75c575 | note | – – – – – – – – – – – – – – – – –
b76027bd-55e5-5357-8acd-47c83f7db264 | note | ACCEPTANCE CRITERIA:
d6d94163-4bae-523b-9f00-ec49b7141974 | note | • All pipes must meet project specification
56654f91-6d06-529e-ae8e-aefbc6e964cf | note | • DN 450 PE100 WSA PS-207 PN12.5
c57dc0d5-1125-5a3a-a5a3-705d2dedd498 | textbox | Reference: Material approval in Teambinder:
c950936d-3493-5bab-bbde-8d09a6b63c95 | note | – – – – – – – – – – – – – – – – –
bfe08a55-643a-5ed7-b201-bd7399e5be76 | note | METHOD: Document Review
25c39180-e0e5-5ed3-90f3-1737363a6611 | note | – – – – – – – – – – – – – – – – –
c241a703-6b7d-522e-961a-cc8074b13bb4 | note | FREQUENCY: Prior to commencement
66ada1ad-bb0a-5a02-9b6e-9c9f0dc98dbf | note | – – – – – – – – – – – – – – – – –
050e52a4-bf5d-5b88-b4fa-513111892406 | note | CATEGORY: HP
4492e1c4-8444-51b5-bf5d-01ef722f318d | note | – – – – – – – – – – – – – – – – –
27119c0f-84d9-5ec9-a6c2-12197698058b | note | RESPONSIBILITY: PE/SPE
459a4dd1-1897-53e7-8c60-528c3bf8dad2 | note | – – – – – – – – – – – – – – – – –
04cd85f5-2208-5a1b-a35a-c785aca3ae48 | note | VERIFYING DOCUMENTS: Material compliance certificate
54a5aea3-436c-5136-a598-2f35c70dbf5a | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Carrier Pipe
1befb960-40e0-5a6f-961e-950186c996a6 | note | REFERENCE:
151e937b-135f-5287-955a-b84df52fbaee | note | • IFC Drawings:
32560fc8-68e9-5585-9b77-d30362285386 | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
5f819ae6-a6c1-50ad-aee7-5ffe8e42381f | note | – – – – – – – – – – – – – – – – –
f3fdbe16-a13b-58c7-b017-9d897adc293e | note | ACCEPTANCE CRITERIA:
b69e4949-6e95-53a4-a9d1-6bc6f5aee3a6 | note | • All pipes must meet project specification
ff93fea9-fe21-539e-8d4b-f9c8ac214d88 | note | • DN 280 PE100 WSA PS-207 PN16
0323cfe3-26a0-5fe9-b628-d9d905bd9034 | textbox | Reference: Material approval in Teambinder:
48266a9d-6afe-54c3-b966-7375908dd36c | note | – – – – – – – – – – – – – – – – –
2e43a314-dbfd-5648-99a5-a492a1b328bb | note | METHOD: Document Review
a06c9042-ebc1-553c-93bc-7bb08afaed5b | note | – – – – – – – – – – – – – – – – –
70cfe2b6-2cde-5805-adcb-590602de46bc | note | FREQUENCY: Prior to commencement
0529d6e3-42d0-5d92-9ae6-d2c61577df36 | note | – – – – – – – – – – – – – – – – –
921353ea-dfb3-553c-832d-5fb0ec2c6491 | note | CATEGORY: HP
099b39ea-6e82-50ba-9d2c-01c49a76cac8 | note | – – – – – – – – – – – – – – – – –
d375b4b5-8ace-54ed-988a-08fec1ec6aa3 | note | RESPONSIBILITY: PE/SPE
a4983a64-1d80-5a81-9ea3-34ceb4263daa | note | – – – – – – – – – – – – – – – – –
a455e8c3-85b5-563d-bf2e-6435789c9b08 | note | VERIFYING DOCUMENTS: Material compliance certificate
3202d9ea-7455-59fb-b1d8-e938d8004196 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Grout
b33d0c7f-eb01-571b-a0d1-e6b1a37f54e4 | note | REFERENCE:
5f6db095-9b25-5e0a-8fb5-3b1b31a0eb5e | note | IFC Drawings:
61b41ca6-6a3f-53fb-a2bd-bccb7f4dbc39 | note | MRP-052-C-SME-DRG-64-MPK-CUT-1041
f283cd0a-2839-5ae7-b556-489704b68ebd | note | – – – – – – – – – – – – – – – – –
8243181f-4881-54f3-8490-0d89348de683 | note | ACCEPTANCE CRITERIA:
ba33b3d8-e3bd-561b-b286-592c1dbdbe8b | note | • Review and approval of grout specification
f8855979-fd96-5d59-9465-347a0d126231 | textbox | Reference: Material approval in Teambinder:
a15b09d7-f3b6-5560-a9d4-a30991d85e27 | note | – – – – – – – – – – – – – – – – –
679923e0-6864-5b1b-9656-3ebe4d5f1a94 | note | METHOD: Document review
5d0d09e3-434a-575e-8647-25ce08e29ad7 | note | – – – – – – – – – – – – – – – – –
bb7c7d6d-7a37-58da-af0f-8f55c65844ad | note | FREQUENCY: Prior to commencement
0e2df113-2403-5876-91df-1255b3184622 | note | – – – – – – – – – – – – – – – – –
493d73e8-f734-52f5-8b4a-f412e63844ca | note | CATEGORY: HP
569850e2-5b71-5509-a27e-afe14c4802ca | note | – – – – – – – – – – – – – – – – –
c6acce66-962a-5155-98ec-aee29c1cad0f | note | RESPONSIBILITY: PE/SPE
83553e16-22b1-5108-a805-da18d00e7084 | note | – – – – – – – – – – – – – – – – –
65242605-46e1-57e5-a395-fadbfe79329d | note | VERIFYING DOCUMENTS: Material compliance certificate
188bf3ba-6aaa-5f75-acbd-253e9680efde | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminary Works-Procedures and Documents
| checkpoint | 3.1 PE Welders Qualifications
4dca9fd7-06a2-5b53-8fdb-f53c08b41f6f | note | ACCEPTANCE CRITERIA:
20508239-a87b-540c-afb4-5cc94e642a43 | note | • PE welders are to be pre-Qualified
f476c1d9-de59-54c3-9675-8af1987005e6 | textbox | Reference:Teambinder Hold point release number:
7a5153b8-f8bc-5ddb-abb3-17097886d42b | note | – – – – – – – – – – – – – – – – –
099925fb-2e79-537a-ac63-1815dd43b745 | note | METHOD: Document review
340bcbb0-1389-5a51-bf48-43dba8a3c2f9 | note | – – – – – – – – – – – – – – – – –
7cd5c0dc-8acb-5452-a007-b93b81cf6d31 | note | FREQUENCY: Prior to commencement
b13657b8-46e6-5496-8802-3fbeb0669420 | note | – – – – – – – – – – – – – – – – –
2fad386f-d2ae-59b9-9427-747d0d16d3d3 | note | CATEGORY: HP
9921bff7-ee10-5131-97cb-b23cc064f546 | note | – – – – – – – – – – – – – – – – –
e69dd4fb-4ffd-5993-9c7c-4573d38b16b8 | note | RESPONSIBILITY: SE/PE
217af1d9-6cdd-5c23-8476-22126784da54 | note | – – – – – – – – – – – – – – – – –
3036a08e-ad90-59e4-854f-9a952dde079e | note | VERIFYING DOCUMENTS: Teambinder approval number
762d2bc4-3eec-5229-a318-21678d7198fc | note | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Check that current revision drawings are being used
a2f8ea2b-f915-51bc-8c54-95b47552e3a4 | note | REFERENCE:
15272c7b-21a2-5841-8b56-152a2316890e | note | • IFC Drawings:
2e68038a-f333-5898-b1f6-95aaa2272272 | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
b696da9a-fc28-506e-b419-124b462943d4 | note | – – – – – – – – – – – – – – – – –
c960b9c4-3a63-5067-bb6c-efd67aea9544 | note | ACCEPTANCE CRITERIA:
7b2e62a2-832a-5d50-b751-e3d3f510b822 | note | • Drawing revison must be confirmed with the design manager
2ae58921-ccc6-56d8-88c5-d2cbb64f68dd | note | – – – – – – – – – – – – – – – – –
f5d65023-22d8-56c1-8600-d4f4eb78e2d1 | note | METHOD: Document review
ad9a53e2-a247-5941-ba94-87b96ba54eb3 | note | – – – – – – – – – – – – – – – – –
07e5c8b8-3a61-5406-ab9e-6c213dedc8e2 | note | FREQUENCY: Prior to commencement
813bf685-3cde-5084-99f7-4b914cdc101d | note | – – – – – – – – – – – – – – – – –
bc3dab5a-82e9-55af-ab68-d0734f00f6db | note | CATEGORY: HP*
59ce0d43-3347-5490-b36a-8e8838ea3cd1 | note | – – – – – – – – – – – – – – – – –
c5118c6d-bb92-5304-bbd8-c4d7f0bf2190 | note | RESPONSIBILITY: SE/PE/SPE
5ca3e899-c508-5dfa-aade-4983e80c56fa | note | – – – – – – – – – – – – – – – – –
b8ee6e6e-f40c-57ee-8684-aec9f07f680c | note | VERIFYING DOCUMENTS: Design drawings.
7b0e5ab9-120f-5125-852d-ed7449d9109f | note | Date Completed:
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set-out
81925f84-9ba5-5f88-a0c6-b74cb1a4ccfe | note | REFERENCE:
0bf5c138-a201-509b-89be-4c58a7420892 | note | • AS 4799-2000
e092658d-b826-5e1d-81bd-a09fe6789493 | note | • IFC Drawings:MRP-052-C-SME-DRG-64-MPK-CUT-1041
1774d723-a28d-5b99-8e3f-532d534d02c8 | note | • DBYD Asset owners responses and requirements.
f29c9fbc-7713-58d6-81bb-c9b8de68184f | note | • MTM: L1-INF-PRO-001
c654265b-d5f2-5575-9074-1e13f26a7b6c | note | – – – – – – – – – – – – – – – – –
d31496d5-e439-51b7-aaef-327d19dd519a | note | ACCEPTANCE CRITERIA:
3ee7f4f1-cba9-5634-8b7c-5ac47f82a871 | note | • Set out line and level of drilling works.
e0f58ae4-711f-53d2-a5bd-f274cdb34f9d | note | • Survey to mark out existing services.
caf47d9d-c3ce-54e8-b607-443aa84b8a15 | note | • Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
a92d5347-fa6e-506d-b3f1-705c78890d4e | note | – – – – – – – – – – – – – – – – –
dcb28227-6ea2-510e-aa11-f0185c0772d5 | note | METHOD:
9752359e-ddc6-5ed8-9741-d29d57e54a9c | note | • Measure
9212176d-caa3-5cde-87a1-13832d3099a7 | note | • Visual
5bcea817-c8b2-5c79-9b13-a2d492a7c9db | note | – – – – – – – – – – – – – – – – –
baa7f63c-fd53-5f59-9040-a08e6e2cc135 | note | FREQUENCY: Each element
d5a8f3d6-0eb9-5073-ad2a-33f6f11d3afc | note | – – – – – – – – – – – – – – – – –
8964c69e-45fa-51a2-84ec-6c43533aa9fb | note | CATEGORY: IP
5df1efbf-f06d-5092-bd98-9c4fcb0fea20 | note | – – – – – – – – – – – – – – – – –
6d3fae94-420f-5c8c-ab85-ce12ce06c24a | note | RESPONSIBILITY:
559f05e3-d9e7-5d52-ad30-1aa96a062b83 | note | • Surveyor
4395640e-1a6a-55c1-8ec8-6dc4aed86598 | note | • SE/PE/SPE
2da80737-a1cf-572d-8dd9-f4b8a69468f0 | note | – – – – – – – – – – – – – – – – –
c97655ee-d80a-57c7-8323-1c2f244a2333 | note | VERIFYING DOCUMENTS: This ITP
bb0842ff-47e2-5849-b34c-b8c22fd32749 | note | Date Completed:
| checkpoint | 4.2 Pipe welding
c5164130-de0b-573d-a552-3531e28ff7a7 | note | REFERENCE:
d65f2cfb-6c62-551e-8a42-066984948d96 | note | • IFC Drawings:
3b5f76ab-e32d-5151-bd93-83c1ff53c2e5 | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
a183cc98-ed38-5778-93ba-37fa453e79df | note | – – – – – – – – – – – – – – – – –
310f2324-8e13-57fa-9429-3aa08e8c06b2 | note | ACCEPTANCE CRITERIA:
21d85847-ef00-54c1-bdf2-59e6f64fe114 | note | • Joints are to be butt welded.
8b39d3b3-f145-553a-b0db-662fb44a0c03 | note | • Butt Welding records to be supplied.
012b21c2-61a8-54c9-9b6d-26bff825a234 | note | • ATTACH: Welding Record
c023b849-3929-58c4-b307-500653759347 | note | – – – – – – – – – – – – – – – – –
17d940c2-19c1-53d4-a496-171ca31958b5 | note | METHOD: Document review
192f0664-f681-55ae-bbf8-c1bdd9f3145a | note | – – – – – – – – – – – – – – – – –
caf3a73a-2018-53b0-bda4-7d39632c5acd | note | FREQUENCY: All Joints
ccc8031d-70fc-5226-8eb4-5783fe90c8cf | note | – – – – – – – – – – – – – – – – –
275d49de-5e01-55a0-872f-86eb4fd41bee | note | CATEGORY: IP
4605fea5-392e-53f0-85ac-3b4f142f7202 | note | – – – – – – – – – – – – – – – – –
58d53df4-1132-51ea-a706-ccd917ceba6c | note | RESPONSIBILITY: SE/Site Supervisor/Survey
5fe30491-e7e5-52da-a9fd-8dddad89f2fa | note | – – – – – – – – – – – – – – – – –
2b6bf1a6-e473-5c80-8997-e8ebf47594a7 | note | VERIFYING DOCUMENTS:
e02a3cee-0d06-58b6-b138-f395756b5e63 | note | • Sign ITP
2b57f5b0-472f-5588-b51b-59568a30a01a | note | • Butt Welding Records
c0dc88e9-8abb-5487-b9d3-8ab0e0a6978e | note | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Drill rig setout
ca198b3e-3330-5b0b-b320-90f3255af96a | note | REFERENCE: Drill Shot Plan
60af4ff3-5c69-5695-9fc9-bc1dc490b178 | note | – – – – – – – – – – – – – – – – –
54d1e2ce-7b8a-5589-a84f-0e521bc37d44 | note | ACCEPTANCE CRITERIA: Location as per current Drill shot plans
e6a944cf-9ca9-53ba-80c3-65278f770130 | note | – – – – – – – – – – – – – – – – –
f8bef584-428e-50bb-91fd-dfb633ada44a | note | METHOD: Visual
dbdc74eb-3579-5ab1-a2d8-ec9450dcf256 | note | – – – – – – – – – – – – – – – – –
79d91c7f-8379-549a-a6c6-1cb9f1b0ae26 | note | FREQUENCY: Prior to commencement
4fc8711d-287c-52c3-9f99-52f05e41becc | note | – – – – – – – – – – – – – – – – –
df60d1cb-3b0d-5852-99f7-f76b123f520e | note | CATEGORY: SP
78a1ae66-9d5f-5948-aef1-40fa65841bc3 | note | – – – – – – – – – – – – – – – – –
d1bff473-ff49-5fc9-9d61-d05ffb7a907f | note | RESPONSIBILITY: SE
e65f3255-2dcf-5b87-b34b-95770fd2dbb2 | note | – – – – – – – – – – – – – – – – –
b608fe5b-8da0-56e9-ae69-153ed02e09c0 | note | VERIFYING DOCUMENTS: This ITP
dcd32bde-6d11-5b1a-b901-a8d003fa744a | note | Date Completed:
| checkpoint | 5.2 Installation of Pipeline (Trenchless method)
950309da-42a1-51eb-b977-9cd83a372479 | note | REFERENCE:
6e6985fe-e114-57b6-a5a2-aed7c3719971 | note | • IFC Drawings:
4961e4ae-53ec-5b96-9a3e-72bf8c9eec05 | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
530c2be0-9ea9-553e-8af1-b07a7d584c6f | note | – – – – – – – – – – – – – – – – –
92391f99-98cd-58f5-8ae0-19956661e8a5 | note | ACCEPTANCE CRITERIA:
12545a48-5452-51ac-aadb-bfb771509473 | note | • Drill to be installed as per the survey setout.
7d87cbc3-099e-536c-bf46-45759bdc8b49 | note | • Bore longs to be supplied.
5d810578-ffc3-5d6e-b448-d998d40163c4 | note | • ATTACH: Bore Logs
f16c687f-383a-5058-850c-30542aae41a6 | note | – – – – – – – – – – – – – – – – –
8c75a063-3dad-560c-b065-41b00bfb0ffa | note | METHOD: Document review
adec6c1b-d466-51fe-aabb-b52e60634a9c | note | – – – – – – – – – – – – – – – – –
3e97917a-28d8-5ce5-84cb-476d6ee71c91 | note | FREQUENCY: During pilot bore
495438da-b8e5-59d1-8ad0-56aa9f6b219e | note | – – – – – – – – – – – – – – – – –
3cc63faa-5eca-5b6c-a820-be8d6e753db7 | note | CATEGORY: IP
ecd706a2-c73c-5959-b0d3-7efd9621e588 | note | – – – – – – – – – – – – – – – – –
90e46edd-2f1a-51a1-bda7-2415219e449b | note | RESPONSIBILITY: SE
787a3658-a0f8-57a1-b20b-9b8ac932e321 | note | – – – – – – – – – – – – – – – – –
310bfe9f-9a4a-5a0f-98ba-ad38519c244c | note | VERIFYING DOCUMENTS: Bore logs
996d0d75-1331-5096-a06b-91a765fb64a0 | note | Date Completed:
| checkpoint | 5.3 Mixing of grout
9db30508-fbdd-501c-8b31-31997af9d048 | note | REFERENCE: Grout Manufacturer Technical Data Sheet
e871a985-fc21-51b2-b3f7-ea99d87dfc18 | note | – – – – – – – – – – – – – – – – –
4f11ec8a-9173-5c6f-9ef1-4aa2750f9d3a | note | ACCEPTANCE CRITERIA:
67bf306f-7779-5984-8172-50a3fa7cc3f1 | note | • Mixing and proportioning of grouting to take place as per Technical Data Sheet provided with product.
0ce1f4c9-4d9d-5d8a-8de3-51b064b625ac | note | • Only whole bags of product shall be used.
4398a09b-e9a2-5e02-8488-f726dc78f233 | note | • Grouting shall not commence when temperature is below 5 degrees Celsius or above 35 degrees Celsius
917677a6-eda8-5256-8830-1d9b0e8c53b7 | note | • Grout mixture should be mixed adequately and free from lumps
f20e1f01-55a4-5146-a78c-766f9fa3b8e4 | textbox | Grout Volume Used
b41212d3-ebba-5f2e-acd0-16bd3a8ef3f2 | note | – – – – – – – – – – – – – – – – –
5e2a00de-8b51-52e3-9463-0f3da076c80f | note | METHOD: Document review/Measure
bc72fbb7-a47a-5f7e-898a-0343db585e60 | note | – – – – – – – – – – – – – – – – –
8b8eff9c-275e-5e5c-b10c-056e025d09f6 | note | FREQUENCY: During grouting process
6dc8c19a-1550-5dd2-9693-c5c891c895e5 | note | – – – – – – – – – – – – – – – – –
74b3cb0a-c274-51af-acb2-5b0940d23559 | note | CATEGORY: IP
1cb31917-2400-56a7-9997-9e66330e9b9d | note | – – – – – – – – – – – – – – – – –
bb622d29-b2a9-5c9e-820d-2518042753c3 | note | RESPONSIBILITY: SE
787bf020-a954-5c22-85a1-f0894baf39de | note | – – – – – – – – – – – – – – – – –
d30200d0-7115-5fc2-bba7-ec59afbe9df8 | note | VERIFYING DOCUMENTS: Sign ITP.
17579022-ba7e-5997-8674-375212647634 | note | Date Completed:
| checkpoint | 5.4 Clean surrounding faces and remove excess grout
04eb82ed-13c5-5a2e-9089-49cee7e9825d | note | ACCEPTANCE CRITERIA: Area free of excess grout and spillage
4562dc7d-e3ad-5653-84fb-9d8fda7ed60c | note | – – – – – – – – – – – – – – – – –
071a445b-c6b6-5f4a-99eb-fff9176a0e2a | note | METHOD: Visual
9ded60c8-3fce-581b-b677-13e93657b89a | note | – – – – – – – – – – – – – – – – –
ecd7ab3f-b4f2-5acc-b79c-1301a43f444a | note | FREQUENCY: Each shaft
375bb4d9-0a0b-5b3d-b3b7-2b0293f4ad78 | note | – – – – – – – – – – – – – – – – –
5d1c7ef9-b6be-5c9c-b509-91cedcb284cd | note | CATEGORY: WP
6d9da102-e3fb-5edd-be82-dbbb9489735b | note | – – – – – – – – – – – – – – – – –
63230b97-da5c-5b7f-bf82-c78e1155bd56 | note | RESPONSIBILITY: SE
4b4fbb0a-8cc1-5b44-bd3e-9cbf4a58cf69 | note | – – – – – – – – – – – – – – – – –
7f212852-d647-5967-af5b-69616eb4d24f | note | VERIFYING DOCUMENTS: Sign ITP
3e014d06-1ac5-5edc-9912-a5f5be29d3cb | note | Date Completed:
| checkpoint | 5.5 Curing
1107e5f5-1375-5f6f-92e8-58e32cf98391 | note | REFERENCE: Grout Manufacturer Technical Data Sheet
3808c881-0830-54a9-b345-ac38fe09909c | note | – – – – – – – – – – – – – – – – –
d45c4e82-ca6a-5e57-9c2e-2a6183738939 | note | ACCEPTANCE CRITERIA: Curing in accordance with TDS
5843d4bb-1eed-5ea8-970e-c428e365a78d | note | – – – – – – – – – – – – – – – – –
cc9df75e-d5b0-5d51-b72a-ff9554716f58 | note | METHOD: Document review
209215c5-14a2-5b78-a232-f49ba4e8839e | note | – – – – – – – – – – – – – – – – –
bb7ffd13-5804-5fc5-a997-675917adf21d | note | FREQUENCY: All pipe
245a2d41-b64f-5b61-b79d-096992745599 | note | – – – – – – – – – – – – – – – – –
800d86d8-f6ce-519c-ac99-94ff3389c9c6 | note | CATEGORY: IP
ca7f872d-d36f-501f-a27d-31e3bd827ba5 | note | – – – – – – – – – – – – – – – – –
7755aad7-613a-5478-8549-532ded782ae2 | note | RESPONSIBILITY: SE
5e3baa93-cf75-5edd-b4da-e07763680a27 | note | – – – – – – – – – – – – – – – – –
c6d8845d-af86-52f7-bf37-4bc929e82920 | note | VERIFYING DOCUMENTS: Sign ITP
beadbb23-fcb9-5317-bad4-50a04f6ddd6e | note | Date Completed:
| checkpoint | 5.6 Auditing
8d17e61a-9357-59e3-9139-3a4a8a726247 | note | REFERENCE: IFC Drawings
45b2b9f8-95a5-50e7-a2e3-ce29f401f7b6 | note | – – – – – – – – – – – – – – – – –
f4fa4e4c-2e52-5d6d-9d57-fae1f57a3332 | note | ACCEPTANCE CRITERIA:
04c8a3c4-47d6-56b4-aedd-3633316dc4a4 | note | • Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts.
2bc29c96-73af-5ae8-8870-d0c05c41e5fd | note | • ATTACH: Audit report
42cd9895-37c9-5503-b72d-d0ea2e234637 | note | – – – – – – – – – – – – – – – – –
018758f4-14be-59ec-8df2-ee94405b3edf | note | METHOD: Record and Review
ef21f3fc-9457-52e4-a615-2f5de08199c1 | note | – – – – – – – – – – – – – – – – –
0e79791b-4844-515f-9d12-6196a38a4ee6 | note | FREQUENCY: Prior to backfill of exit/entry shafts
6c8c069f-2118-58ff-a0be-336d337a8e74 | note | – – – – – – – – – – – – – – – – –
3a5deebe-7807-5c01-9649-11371dfe5f65 | note | CATEGORY: HP
b08e8626-8b05-583c-a42d-b1afd2ab319a | note | – – – – – – – – – – – – – – – – –
8407faad-fe99-5281-a6c2-6b1665e1d4af | note | RESPONSIBILITY: Nominated Authority (SEW)
b86b6029-0104-5c87-bdee-506a682270cc | note | – – – – – – – – – – – – – – – – –
9b96fb1b-b13e-56b0-9f62-c04ab2a2ab04 | note | VERIFYING DOCUMENTS:
9841058c-4bd9-580e-b5fd-b23d3543fbbc | note | • Sign ITP
622ac85f-99cc-5ace-bdcf-38e43929c27a | note | • Auditing Report
f82c2662-dadb-5541-9fab-46f8ae5fd1b4 | note | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.7 Reinstatement
28935bf7-2072-54a5-ab66-7e476edc5924 | note | REFERENCE:
5fbfcd2b-25fc-5f99-bfcc-1fe697c80964 | note | • IFC Drawings:
1b6ed5ce-a905-531a-a01a-400bec0d4b31 | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
8eca3a04-fd0f-5729-9fc9-66224c1ad0f2 | note | • MRWA-W-201 Table 201-A & 201-B
0c7e7815-f49f-5912-9209-0a94b69be761 | note | – – – – – – – – – – – – – – – – –
514c1f69-f0b8-5127-8376-a2cdde16db83 | note | ACCEPTANCE CRITERIA:
fd3395ca-0356-5a00-bc66-4417970535a4 | note | • REINSTATEMENT OF BORE SHAFTS SHALL FOLLOW MRWA BACKFILL SPECIFICATION MRWA-W-201 Table 201-A & 201-B;
87dd418b-347b-581c-91ef-417f9ea89b2a | note | • Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified.
98fa1ce4-82c4-5420-bda6-f756834c9943 | note | – – – – – – – – – – – – – – – – –
a88b8de7-041d-5a18-aa6e-46cd501a6ea1 | note | METHOD: Visual
e47897ea-47ce-5152-83e2-979b2adb7721 | note | – – – – – – – – – – – – – – – – –
500a549a-417d-56bb-bae9-8a392b8703a3 | note | FREQUENCY: Each shaft
4c5c3e00-a888-5484-b5b8-7fae6b0bc3d4 | note | – – – – – – – – – – – – – – – – –
ca78556b-8d05-504b-ba9a-871f1b1dd6d9 | note | CATEGORY: IP
aed93e4e-811d-57af-9162-463ec7d025c1 | note | – – – – – – – – – – – – – – – – –
36fb1be4-a0d8-5f1c-b969-a40b749c1787 | note | RESPONSIBILITY: SE/Site Supervisor
b8eb4b2d-3ddc-5f5b-99a5-d54cddd03e6c | note | – – – – – – – – – – – – – – – – –
5fc0f876-6de0-5c97-a5d1-f320325e3822 | note | VERIFYING DOCUMENTS: Sign ITP
6ba38a78-7ad4-5c98-9af1-1232279b1de8 | note | Date Completed:
| checkpoint | 5.8 Subcontractor ITP
3d0474ca-8ede-5c05-970e-ca004062474d | note | REFERENCE: N/A
ec8532ac-08f7-52fb-970f-911028415f17 | note | – – – – – – – – – – – – – – – – –
20fb4c92-dcd3-5736-aa0c-c7573e70a22f | note | ACCEPTANCE CRITERIA:
6d65d288-049f-5e16-b5c0-0bb4ab8c5db7 | note | • Acceptance and closeout of subcontractor ITP
9ab9bdac-ffc7-5044-a3ec-96682ee8e6f3 | note | • ATTACHED: Completed and Signed Subcontractor ITP
22a5af48-4e6f-59e4-95cc-8d2bc8e8b29c | note | – – – – – – – – – – – – – – – – –
e2a050ff-67b9-55d0-8cea-fec89c02b3d7 | note | METHOD: Document review
bf789d76-144b-5b36-829b-884be41d08bc | note | – – – – – – – – – – – – – – – – –
c2c33ad5-2f00-52c7-8aa1-7df2459d020a | note | FREQUENCY: Each element
5cee562f-4791-54e5-847c-97f2f9d4e71a | note | – – – – – – – – – – – – – – – – –
d6bb1a7a-eaf4-5054-9a6f-676656a41923 | note | CATEGORY: HP*
ea807eb1-ba9c-5582-a443-d770b5561c4d | note | – – – – – – – – – – – – – – – – –
37c12ab1-16df-5bb9-a301-c6c251804a6e | note | RESPONSIBILITY: SE/SPE
63928657-0fa0-5095-b054-018573ff975e | note | – – – – – – – – – – – – – – – – –
9419710d-e3d7-5546-bc4c-1ad473700bdd | note | VERIFYING DOCUMENTS:
d9b02aa1-eee4-5be3-809b-c53d8fb8f900 | note | • Subcontractor Signed ITP
34cbcacf-28db-5604-a03b-4e3dd0d39893 | note | • Completed
5f4797c7-3fe1-5756-8303-6a2ee26b7a5a | note | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 Non-conformance Report (NCR) Closure
ed77b383-9afd-5445-a88a-59b2f6dde804 | note | REFERENCE: MRPA Quality Management Plan
9b372559-fa82-537a-97dd-d64605787674 | note | – – – – – – – – – – – – – – – – –
843dc03b-4666-5bca-a546-7909e4b53078 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
da01ccb1-acbc-5435-a925-3b014c6602a0 | note | – – – – – – – – – – – – – – – – –
2729d196-9e8e-5ce4-9275-5cc6dec3d6df | note | METHOD: Document Review
5be44998-113e-59f2-a297-f4163a911d8f | note | – – – – – – – – – – – – – – – – –
7eba0c3b-9830-5232-9dde-d86a08ffc15a | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
2fe01a24-ce75-5f79-891f-7b8ffbbd83de | note | – – – – – – – – – – – – – – – – –
b17d3002-c15d-5443-996d-aacbcbbe4142 | note | CATEGORY: HP*
47d15316-bd32-5b79-a481-ebbfe4c2acb7 | note | – – – – – – – – – – – – – – – – –
f3380249-61f3-570a-ab24-9e2ce44b4a2d | note | RESPONSIBILITY: SE/PE/SPE
9ebb0d7e-f9e6-5a8b-b9e5-b9f9740e18f1 | note | – – – – – – – – – – – – – – – – –
a703bc0c-bdde-50fb-9fdd-30c7f49a4455 | note | VERIFYING DOCUMENTS: This ITP
9841c41d-4989-5458-9a94-9fa7eceb349c | note | Date Completed:
| checkpoint | 6.2 As-built Survey
171690da-27ab-5517-9c0c-0c02446418f0 | note | REFERENCE:
d0a60653-ae5a-5b2c-9c04-5a5541c7195a | note | • IFC Drawings:
a465dd06-ce20-511d-bfd6-6ad378a7df18 | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
767dc9f4-696f-5e47-bf77-54eb5707e92c | note | – – – – – – – – – – – – – – – – –
860d64d9-d4fa-5ad1-81ec-65eae70bbd37 | note | ACCEPTANCE CRITERIA:
adb3440a-82a7-5332-a9a0-9b2dd76ac5d7 | note | • Survey as built report to be compiled.
32c1f56f-2213-5cc9-935c-d0d6e4dc8f0f | note | • Borelog obtained from subcontractor
cc0787b3-7748-5ed9-8a55-fec486ecf974 | note | • Autocad and PDF reports are to be supplied.
dd8ef055-31e8-5215-a9a4-466ae6398084 | note | • ATTACH: Survey As-Built Report
5b12c7f5-f902-586a-9e12-11e060115c8b | note | – – – – – – – – – – – – – – – – –
12b78f14-494c-53db-bf18-35e142b7deac | note | METHOD: Document Review
90ccf9ed-b0d3-5b66-9f8c-47b7a02fa60b | note | – – – – – – – – – – – – – – – – –
31e60aee-da0b-52d6-b109-6fab7ede0034 | note | FREQUENCY: Each element
81963a14-10e8-55c5-aeae-b110b6452aaf | note | – – – – – – – – – – – – – – – – –
5ddc6d32-4b47-57cd-92ff-8a63ad420c00 | note | CATEGORY: IP
b86633a4-a74b-51e4-a32f-735f93a43ca2 | note | – – – – – – – – – – – – – – – – –
818307c3-8d34-5068-bccd-f27af1ff7434 | note | RESPONSIBILITY:
5ea08cbb-4dc1-5bc7-8794-3a63d2b446ee | note | • Surveyor
45f02f97-a58a-5b67-9584-3adda4258ec7 | note | • SE/PE/SPE
c92cffe6-c983-5067-bfa3-0c64a2d442f2 | note | – – – – – – – – – – – – – – – – –
d150ff4a-5bc2-5ed5-9d7a-fe8bb378e54c | note | VERIFYING DOCUMENTS: Survey As Report
4d02fd2d-5f0d-5791-a4de-62d3da29cf66 | note | Date Completed:
| checkpoint | 6.3 Red-line / As-constructed IFC Drawings
7e25e6b8-03e9-5213-8703-527758880c03 | note | REFERENCE: MRPA Quality Management Plan
30138de3-d288-5cbb-a1d6-ba24bdc823f4 | note | – – – – – – – – – – – – – – – – –
3ecf4149-407c-5bd6-bb50-a016298caea5 | note | ACCEPTANCE CRITERIA:
93140037-d863-5865-a497-d1553c245f7b | note | • All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
7e97ed1b-5e72-5e0e-afc0-494b6621f3c8 | note | – – – – – – – – – – – – – – – – –
1aaa41cf-a026-552b-b5bf-8a7e2d293099 | note | METHOD: Document Review
03471765-4b60-5a0a-9f29-6712b725cb65 | note | – – – – – – – – – – – – – – – – –
f0d925e8-5c37-5989-aa95-78e3915beffd | note | FREQUENCY: Once, after construction of the design package
69fa3425-e8aa-5c63-ba21-cd44a911d260 | note | – – – – – – – – – – – – – – – – –
30007985-af9f-5d99-85b7-aab60723f2e2 | note | CATEGORY: WP
df3398b8-7d79-51d2-b0c1-ad4ee0d9cf40 | note | – – – – – – – – – – – – – – – – –
b3878b90-29d0-52e4-92cd-45df7df196de | note | RESPONSIBILITY: SE/PE/SPE
55d502f7-7bfc-5d4f-83fd-32139500bad0 | note | – – – – – – – – – – – – – – – – –
68cdcb72-8070-5353-8bcd-f7e46afe6726 | note | VERIFYING DOCUMENTS: This ITP
7cdb9fe5-aba4-5a35-9d81-d49e9d4d8dfa | note | Date Completed:
| checkpoint | Metropolitan Roads Program Alliance Final Inspection
48cd75a8-1d9c-5b4a-bcad-2add2460a467 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0e2c2a88-5eee-5aa9-99e0-fbf6553b2cd4 | textbox | Name:
55b01236-1702-5672-8bd0-b183ccfec4b1 | textbox | Position:
92c17c32-0d4c-5a7b-bb58-7ed6b3f94864 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-012-STR-RSS Wall Main Rev 1 | itp | ITP-012-STR-RSS Wall-Main |  | cff17963-117f-4710-9ec3-3daf3faa28a7
| section | Referenced Documentation
| checkpoint | Referenced Documentation
5a3c858d-f28d-5a26-a500-cc3ccd289b49 | note | Document Title: ITP-012-STR-RSS Wall-Main
81e6080e-17b6-50a5-9007-811886e5a1b0 | note | ITP Description: RSS Wall-Main
10c7818b-bed6-5b3c-ae83-424d6ac42aee | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
ea799ef0-a113-59a5-8e54-c79b86433a9a | note | Discipline (e.g. CIV/STR/RAIL): STR
498af1db-14e3-52ff-b944-57a29aa971ed | note | Revision Number: 1
6242921e-876c-544e-9f2f-ac537052c48f | note | Revision Date: 1/05/2023
79df7bf9-0549-59c1-ae10-a0131f8a60bf | note | ITP created by: Victor Mira
2f2c2240-1f4b-5584-aea4-e76720b09432 | note | ITP approved for use by: Victor Mira
147c6ce6-a448-540b-81b2-8b6396f4ed00 | note | 1.1 Non Dependent
00a30657-d2d0-5182-9580-e3f1bf8c454d | note | Reference: VicRoads Section 682 November 2018
48faceb2-6dcc-538c-93b4-9b862336b697 | note | 1.2 Non Dependent
84d4e5dd-f2d2-5b91-9285-cc8ec4df3022 | note | Reference: VicRoads Section 204 December 2015
8c45244a-453f-5f98-a4de-7c839e660b6a | note | 1.3 Non Dependent
0003dad2-c909-5638-8e58-cc337f9b5d93 | note | Reference: IFC drawings
| section | Preliminaries-Materials
| checkpoint | 2.1 Concrete-Leveling Pad
ac6e6da8-dfc7-5fbd-a5c6-cd5ea2b452e2 | note | REFERENCE: IFC drawings
e52c053b-6646-56c9-871e-246989d9df76 | note | – – – – – – – – – – – – – – – – –
2e3e43b6-0a5b-520d-86a6-ddf81de9207f | note | ACCEPTANCE CRITERIA: CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS;
e1d913ef-72e0-5001-b24e-90a1ad47f37b | textbox | Reference: Teambinder MA number:
cf8e5207-4ebd-5eca-842f-ed0f7ed8716e | note | – – – – – – – – – – – – – – – – –
17dbc5f6-89f3-5d41-b45c-2f473438863d | note | METHOD: Document Review
3bd87415-233e-53e2-bf41-8c7984c80b71 | note | – – – – – – – – – – – – – – – – –
1763229c-2a85-5470-b43f-b0326ad14288 | note | FREQUENCY: Each element
e4f72307-66d6-5faa-b854-22111c158f44 | note | – – – – – – – – – – – – – – – – –
dc07650c-b347-5554-b8fe-159901d40fee | note | CATEGORY: HP*
eb483f7a-ba76-5f7e-8f68-50b77cd21337 | note | – – – – – – – – – – – – – – – – –
dda970fc-b7d7-5411-8e43-aea331a03894 | note | RESPONSIBILITY: PE/Nominated Authority
6ccf35c6-a5b8-580b-9c04-69e75857281d | note | – – – – – – – – – – – – – – – – –
7d1711a2-562b-53f5-b318-f95c160839d7 | note | VERIFYING DOCUMENTS: Material approval
839571de-373e-58e8-b39b-01735f0d9355 | date | Date Completed:
| checkpoint | 2.2 Select fill
a16c16e1-651e-5f63-aa99-33a4a8f863db | note | REFERENCE: IFC Drawings
b60f344e-a05f-57fe-a3cb-cfa5b801b74e | note | – – – – – – – – – – – – – – – – –
9e6acb6b-967a-5087-a334-f1a4a9a055ec | note | ACCEPTANCE CRITERIA: Select fill shall comply with the requirements of the RSS designer:
1ce20ea9-aaa3-576b-9d14-db784fad7e0c | note | • UNIT WEIGHT: 22 ± 2 kN/m³
de3aada8-5ab9-5fd8-a6f0-906678e2834e | note | • INTERNAL FRICTION ANGLE ≥ 34.5°
7c436b6a-d2d0-51df-8fb5-7cca9f406982 | note | ○ Gradation:
529f86fd-741c-5f05-bc70-5f1b4f17845f | note | • 150mm: 100% PASSING
1484a270-60e7-5e3f-9d3e-80064e9d0c35 | note | • 37.5mm: 60 TO 100% PASSING
4f7d50dd-4d92-5e18-b4d8-212213b5b50c | note | • 9.5mm: 25 TO 100% PASSING
e0f62b97-6261-59fb-af81-afda8d770742 | note | • 2.36mm: 15 TO 100% PASSING
13475b85-6a63-59e0-9a6d-8d4ce6ae4371 | note | • 0.6mm: 10 TO 100% PASSING
9951afd5-575d-56c8-b319-1afa017119fd | note | • 0.075mm: 0 TO 15% PASSING
baab5bfe-bfaa-5698-85db-1e831a6de5a7 | note | ○ Electrochemical Properties:
d97e3a73-7176-5426-b13c-39562a7248cf | note | • RESISTIVITY >1000 Ω-cm
057062b8-cab0-5792-9a75-375923fd3104 | note | • CHLORIDES <200 mg/kg
d310a8ed-d230-5a05-b540-5ce5bfd7ae7e | note | • SULPHATES <200 mg/kg
e0002a05-caf5-530a-8e87-e39ace8b8f70 | note | • ORGANIC CONTENT 0%
24bf6a1f-9cb2-5048-9572-82a9466c9df1 | note | ○ Structural Properties:
c446fcb9-2056-59c8-abe2-f2fbe4de6926 | note | • COEFFICIENT OF UNIFORMITY ≥ 5
2f69d07d-e8a3-5af6-a12c-da001c7a6597 | note | • LIQUID LIMIT ≤ 30%
395b2a51-bcf3-5c99-a950-b62a1738aca1 | note | • PLASTICITY INDEX ≤ 12
10daa424-35a9-5070-bff5-47c50c6bc3c5 | note | • The select backfill must meet the minimum requirements of Vicroads Type A filling
5ff27ccd-6ed0-5f2b-9bbc-62043614a8cf | textbox | Reference: Material approval in Teambinder
76697044-1b1f-5854-9fb7-c6f3d398c50f | note | – – – – – – – – – – – – – – – – –
1848b70e-4d6f-5cc6-b353-5daaffb7ba0e | note | METHOD: Document Review
de263bd7-ecdf-54cd-a93b-6fcd7acc0782 | note | – – – – – – – – – – – – – – – – –
c59a7622-d7c7-5e60-8495-daacd4b9b9e1 | note | FREQUENCY: Each material specification
a6d902ba-0fb7-54a0-8b54-1d6890ce558f | note | – – – – – – – – – – – – – – – – –
40bf56a7-78ac-589e-bc6f-e910b25059ec | note | CATEGORY: HP
20e58292-a9a5-5365-80ef-32c028bf3631 | note | – – – – – – – – – – – – – – – – –
d5d9791c-fd78-50cb-b9ce-5b29c0abe554 | note | RESPONSIBILITY: Nominated Authority
33088e73-7560-5967-97af-115e80542c20 | note | – – – – – – – – – – – – – – – – –
fc955469-8f6f-5597-8640-b930ec4ebbeb | note | VERIFYING DOCUMENTS: Material approval
d7c56057-a830-5666-ae5d-97c026ad739b | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 General fill
8bd0d95d-de6d-557b-ae31-aa170b2bfb27 | note | REFERENCE: IFC Drawings
a2ffb24c-edc3-5382-83db-adedfff4ccb8 | note | – – – – – – – – – – – – – – – – –
1619791e-09e6-5487-a4a3-e89a5c8c09b8 | note | ACCEPTANCE CRITERIA: Backfill behind the reinforced block shall be Vicroads Type B or better and:
caee2742-4dac-5dc7-9e9b-13d254fa6b77 | note | pH > 5.5
0369705b-3524-5854-9dac-30ebe695c128 | note | CHLORIDES < 2000 mg/kg
3f48facc-31ef-51cf-bfb2-7ad2cb2ea2c6 | note | SULPHATES < 1000 mg/kg
9a98bb7b-fdc9-5d16-9297-da997a66f075 | note | Reference: Material approval in Teambinder
784da485-ce68-55b9-9cac-cf107e270242 | note | – – – – – – – – – – – – – – – – –
1918d7ee-963a-5ff3-92a6-b436b089037d | note | METHOD: Document Review
7ad90829-ace8-591d-847e-ff9bc01f3f8e | note | – – – – – – – – – – – – – – – – –
f94a0441-5b95-5798-b7d9-1e402aa50895 | note | FREQUENCY: Each material specification
6a2ed8ff-c4ad-5095-8575-e21352b65d93 | note | – – – – – – – – – – – – – – – – –
c5a24104-ab2b-501c-aadb-e0266ef2c4a7 | note | CATEGORY: HP
11a077ff-d8c1-51c5-9084-d8cbd4fe0c4e | note | – – – – – – – – – – – – – – – – –
3d762842-defc-5300-addf-f7d55e10149d | note | RESPONSIBILITY: Nominated Authority
b70eb4ec-9d67-50b4-8581-63a1fcfd10cd | note | – – – – – – – – – – – – – – – – –
a143be08-120f-538a-8312-ebee7a90059e | note | VERIFYING DOCUMENTS: Material approval
9956eb0c-575e-566c-ae88-1416f3de1c6f | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Perforated Pipe-material
34745e42-9122-53c7-aba6-3ba3dae16027 | note | REFERENCE: IFC Drawings
055b6ec5-b85a-5b32-a021-2ec8a6cbcd68 | note | – – – – – – – – – – – – – – – – –
85875f8f-e864-50c5-b385-e7cb2c4028f9 | note | ACCEPTANCE CRITERIA: Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
aa570f89-96a0-5e8d-96bc-481c17d9d795 | note | Reference: Teambinder MA number:
a7981b7b-e1fd-5f92-8286-b7a6c77c9e3a | note | – – – – – – – – – – – – – – – – –
07b63b0f-11b5-5d6a-ab6a-31d871f0fe81 | note | METHOD: Document review, Measure
84ae4048-9931-5224-92d4-f3dc050cafc3 | note | – – – – – – – – – – – – – – – – –
ac56a61e-1e8b-56a1-a39e-495388e16b50 | note | FREQUENCY: Each wall
4412f8c2-1804-5c79-b964-f313d1f28a8f | note | – – – – – – – – – – – – – – – – –
f3c92df9-6dfd-5063-83b1-30eac54119f5 | note | CATEGORY: HP
128f450f-203a-51cc-9b25-427473450dbe | note | – – – – – – – – – – – – – – – – –
73b7424b-105f-5004-955d-724f8ba6532b | note | RESPONSIBILITY: Nominated Authority
f45aaa6e-707b-5946-a17d-2074f6bab417 | note | – – – – – – – – – – – – – – – – –
9d9da0c2-59bc-5230-9b5d-3575ae1c8922 | note | VERIFYING DOCUMENTS: Material approval
8a6d41c9-c2a8-552f-baf0-b160bf4dbfbd | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries-Documents
| checkpoint | 3.1 RSS Panels
32247d12-6be9-5589-9cd7-84c7aae0906c | note | REFERENCE: IFC drawings
be4bfe9b-84f7-5a8a-a42f-ced2dd881ac9 | note | – – – – – – – – – – – – – – – – –
3d3d1746-65c6-5b46-804e-e27bf32b419a | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
15f0200b-6a0e-571f-a552-80dae142aecf | note | i. Certificate of Compliance / Birth Certificate
e8f0da02-ec27-5cd8-a702-d75be59cbc16 | note | – 1. Concrete strength;
b56f33a3-8b71-55c5-819b-ffe2a9d1e291 | note | – 2.Date of manufacture;
21f1bf95-5259-5cd4-8103-b29e59c67816 | note | – 3.Unique Identification number;
40238426-c029-5689-8a7c-c429e543fe92 | note | – 4.Mass;
79c9c8dc-ad1a-5800-a2ef-c680360a58c5 | note | – 5.Confirmation of number, type and capacity of lifting inserts;
a8977833-4791-502f-9a3b-40d7ea05c71e | note | – 6.Quality assurance sign-off.
f55f1066-9d4f-5cd4-929b-bcdcfdb60178 | note | ii. Compressive strength test results
2c2c9c90-6f5a-514c-bb9f-365642de7bca | note | iii. Precast Lifting Design
bba556cf-3786-5bd5-b705-d85461031403 | note | iv. Pre-pour check sheet / ITP
0689a20a-e77e-55f9-a41b-5e304d8483c1 | note | v. Post-pour check sheet / ITP
af4e7666-ee88-5604-9925-b222b91612e8 | note | vi. Covermeter check record
551ed00c-228f-5d0f-9ac6-a56c70eb49e8 | note | vii. Record of dimensional measurements
cc596442-105a-5107-a40b-bc7b5e38b50a | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
7e7a0789-2525-523c-a951-d1b2aecbab77 | textbox | Reference: Precast panels MDR Lot in TeamBinder:
50a4513f-98de-5163-8848-106a86d43fbb | note | – – – – – – – – – – – – – – – – –
d9050164-57b0-53f3-87a6-5060e7cc2cd4 | note | METHOD: Document Review
bb13552e-f9a5-5e3d-b26d-433a2e085f03 | note | – – – – – – – – – – – – – – – – –
176d88de-5335-567c-8408-dae1374d6788 | note | FREQUENCY: Once for each type of panels
a2a02159-5c33-54e0-be53-0d42106781f8 | note | – – – – – – – – – – – – – – – – –
4fc2306f-7aa4-55c3-911d-87dcea54a83b | note | CATEGORY: IP
2b794935-44fb-51c6-8fff-2d9535904f64 | note | – – – – – – – – – – – – – – – – –
917b70dd-dbfd-526f-a24d-66d601dfbef5 | note | RESPONSIBILITY: PE
c1f25768-fe07-5207-91d7-0f03b3f5247e | note | – – – – – – – – – – – – – – – – –
0c875e0c-c87d-5fc6-8978-240a71c0caf1 | note | VERIFYING DOCUMENTS: Precast panels Birth certificates and MDR Lot
1fd39627-ef5c-5955-b8a1-8240a47782d8 | date | Date Completed:
| section | Pre-Construction Activities
| checkpoint | 4.1 Foundation
a0116b19-efcf-5193-9f0b-674f6c6c9975 | note | REFERENCE: IFC Drawings
0b8bbfc6-110f-57e9-aa97-51c6010d9241 | note | – – – – – – – – – – – – – – – – –
90729cf3-3e42-54a2-92c1-69296a130c58 | note | ACCEPTANCE CRITERIA: The foundation material beneath the RSS fill shall be inspected on site by a qualified geotechnical Engineerto ensure that the soil conditions meet the assumed material properties:
c9924684-2e56-5aac-8f6d-785b8036f286 | note | • Description: Stiff Clay or better
a3d2c97e-63cc-5b5c-8998-da70d2015ece | note | • Unit Weight: 18 kN/m3
327b9dbf-d987-50f1-99ad-2761b6ba3945 | note | • Effective friction angle: 28°
cadcbeb8-0849-5ead-8579-b8cff1010c40 | note | • Effective Cohession: 5 kPa
0f9bf4c9-71fa-5bff-a88d-3152eb10eeb1 | note | • Undrained cohesion: 80 kPa
d3f838b6-3448-5ddd-99a8-56bf1c8bc011 | note | – – – – – – – – – – – – – – – – –
6963087f-69dc-5414-a611-5be62b59b877 | note | METHOD: Test, Document Review, Visual
e5edea3c-6829-5319-afb3-990ad355647f | note | – – – – – – – – – – – – – – – – –
b787244a-fc10-5992-8fd8-615da0224c05 | note | FREQUENCY: Each retaining Wall
ec63b8b0-eef6-5141-a4c1-2b1651600bf0 | note | – – – – – – – – – – – – – – – – –
9bb756bb-a71a-54e2-8e2e-abb4addfc25c | note | CATEGORY: HP*
dbcc25bb-09a0-52ec-9587-2cd37d354019 | note | – – – – – – – – – – – – – – – – –
7f12c942-89e2-5285-a7dc-5b446ab0a6dd | note | RESPONSIBILITY: PE/Geotechnical Engineer
0eb432e6-2d06-5809-973d-ef727e5a48ab | note | – – – – – – – – – – – – – – – – –
09401ba6-f5b6-5e74-a9a1-07a8cee9d635 | note | VERIFYING DOCUMENTS: This ITP, Test results
c402da48-1e79-52c4-8ad4-e034e4bf0126 | date | Date Completed:
| checkpoint | 4.2 Foundation
c2882d09-ab08-53ab-9cec-4d27b5a2ffe1 | note | REFERENCE: IFC Drawings
e80b350f-e6fe-525d-bc51-1df4e8af971d | note | • MRO-052-C-SME-DRG-32-MPK-CSW-2053
889bde63-e6f1-5442-a6f7-bb81b1814e43 | note | – – – – – – – – – – – – – – – – –
fde2dcc0-0b73-5add-a2cd-2b36abce5dca | note | ACCEPTANCE CRITERIA: Where the foundation material does not meet the assumed material parameters, the existing ground shall be replaced with VR Type A fill Compacted in accordance with VR 204
07cb888d-c6d5-5f0a-a924-32ee9cef53da | note | – Ground improvement works shall be keyed into surrounding material at minimum 200mm Bench width
25432280-bf9a-5154-9f4a-91e2a2af9e6e | note | – Ground improvement works shall extend beyond either side of bridge approach to detail show in IFC drawing
97f29d86-0967-52f9-96bb-60f06153ceef | note | – – – – – – – – – – – – – – – – –
c99a64c9-08fd-535a-b85c-797da0c5bbfc | note | METHOD: Visual
685c0492-c679-59a6-a366-e4956e2296c3 | note | – – – – – – – – – – – – – – – – –
e2a1985a-3c98-5e55-900d-b3c8f7a196bf | note | FREQUENCY: Each retaining wall
c569b4b3-075a-5874-b83d-351b53fadc00 | note | – – – – – – – – – – – – – – – – –
448205d6-3368-51e4-a989-1cadee3ef3f0 | note | CATEGORY: IP
a96a9a70-e490-554a-bd2d-cd41f82874ff | note | – – – – – – – – – – – – – – – – –
6e74f9cb-c918-55cc-ac52-af1ad8bfd33e | note | RESPONSIBILITY: PE/Geotechnical Engineer
61f422fe-2e0f-5baa-802e-e2507b0b678e | note | – – – – – – – – – – – – – – – – –
695ee52a-e9a6-5c37-9d3f-69dd77791e70 | note | VERIFYING DOCUMENTS: This ITP
b6aa5dcc-a326-5932-9616-3b68c945de63 | date | Date Completed:
| checkpoint | 4.3 Foundation
a640911d-32c8-558c-9a10-0b496616c3d3 | note | REFERENCE: VR 204.12, VR 204.11
ada6a7cb-a1cf-5ad0-af3e-1562470f82ec | note | – – – – – – – – – – – – – – – – –
421593ff-bb51-56d6-a025-6ea89a603ced | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
f87f56a2-9e16-5dd6-b0bb-351f5496eeab | note | • No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
980b81b4-cf88-5706-914a-54d98bc5b0b0 | note | – – – – – – – – – – – – – – – – –
38a4faca-74c7-5c08-9913-c0bc694e6b00 | note | METHOD: Visual
6a9e4e1e-7438-5a9b-b7be-0a58bc639c33 | note | – – – – – – – – – – – – – – – – –
075201d1-cbe8-5e48-92c7-3dea21af538d | note | FREQUENCY: Each retaining Wall
3ce740a0-9d6e-53c5-9c37-e48158166573 | note | – – – – – – – – – – – – – – – – –
5bf2a16a-2326-5fbd-968a-68c178b876c1 | note | CATEGORY: HP
1216795e-0818-5d92-94f0-d8e92507756e | note | – – – – – – – – – – – – – – – – –
7985e3e2-6b80-5ea0-a8ba-b3c16e485301 | note | RESPONSIBILITY: PE/Nominated Authority
c6c8f491-f6a0-5748-a82b-8b584242ddcc | note | – – – – – – – – – – – – – – – – –
1447e74f-604a-5325-b99c-903353bb33b6 | note | VERIFYING DOCUMENTS: This ITP
3355bb81-8a17-50e0-ad98-903a8eeb852d | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.4 Levelling Pad-Survey Set out
fa0a5fc6-09b3-5cbf-99c5-7a514c9ac2c5 | note | REFERENCE: IFC Drawings
374a8b6e-b695-535e-9bc0-ac9ae1e1fc97 | note | • VR 682.20
aeecf6bc-72c0-5134-8d0c-a2f6ff585c98 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
13560fd3-6c04-5b95-83b1-27cb13f2c73b | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
fe9f9ebb-3219-5f47-a7d8-c38aad92668c | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
c5206c13-6690-51c9-b57b-75b03ff8c144 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
b947a681-cd4d-59b0-8384-68a0ca404c20 | note | – – – – – – – – – – – – – – – – –
fe923ac7-d6bc-5344-82c7-d338178660cb | note | ACCEPTANCE CRITERIA: Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the tables in IFC Drawings and Vicroads Specification
6bfedb58-3733-54e0-8069-c9c018f43486 | note | – – – – – – – – – – – – – – – – –
06e1e88e-40f5-58cd-baef-ced02a9de161 | note | METHOD: Measure, Visual
f5cd6d09-1606-5883-8087-37595bda66b7 | note | – – – – – – – – – – – – – – – – –
8438e244-b059-528b-b909-3f7567091c50 | note | FREQUENCY: Each retaining Wall
5ea2c970-54c3-5422-acd1-ad505d7dcb16 | note | – – – – – – – – – – – – – – – – –
bd3b15de-dd87-520c-a01e-198623a2ec80 | note | CATEGORY: IP
ab817e67-2d53-5513-805e-39cde127abaf | note | – – – – – – – – – – – – – – – – –
f074bb4e-1e08-5ad1-a4af-c99587baed7b | note | RESPONSIBILITY: Surveyor, SE/PE
76aa1f8f-852a-52d7-8b50-794788f40763 | note | – – – – – – – – – – – – – – – – –
baa4d394-b0c5-5ecd-9064-fbfcad8c2df8 | note | VERIFYING DOCUMENTS: This ITP
a19b1cb9-4669-5d06-8775-2d3bd60cf0ff | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Form Levelling pad
7e641105-3464-5a1c-827e-b9894205c7ef | note | REFERENCE: IFC Drawings
6cabbf5f-bb96-5732-959c-8936ad0717cf | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
97579fea-1412-566c-b684-35e371f865e3 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
a54055f3-47df-5470-ba51-212351af451d | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
8dcabae1-db21-5434-8ba4-64d0c79f49b5 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
d712c7b3-3490-5ec7-9015-508339083ce8 | note | – – – – – – – – – – – – – – – – –
04ae5e2a-c425-5d70-b5db-64f9fb71e469 | note | ACCEPTANCE CRITERIA: Form timber shutters to edge of levelling pad
339841b0-c61a-5ff0-b731-dce35db3f202 | note | – Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
55ac77f5-fe6f-5eab-a846-1217983c8eef | note | – The leveling course level shall NOT deviate from the specified level by mor than ±3mm.
f71a9181-33c1-5fb3-a5c9-c416921ad48e | note | – 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
48493c3a-9ddc-5753-97d3-78eecd78c939 | note | – – – – – – – – – – – – – – – – –
9ecf6c46-9040-53f7-908c-2fa028d8cfc3 | note | METHOD: Measure, Visual
48f071cf-3a9c-5d33-be73-538d8a44bd82 | note | – – – – – – – – – – – – – – – – –
0b59787a-82b1-5ebd-b80f-a28077cc9e65 | note | FREQUENCY: Each Lot
4cda596e-30b0-57c5-9c2b-629cdd4208c8 | note | – – – – – – – – – – – – – – – – –
9daf4cbf-659f-5af1-8a14-bc21e2517e5f | note | CATEGORY: IP
5c541a1a-c1cc-57e6-a6ed-7cad5d7587d0 | note | – – – – – – – – – – – – – – – – –
245af2d0-6c47-5a22-b821-dcd3608fcf14 | note | RESPONSIBILITY: SE/Site Supervisor
5d9c6c54-7c1a-5b76-bfd4-8a71ed870153 | note | – – – – – – – – – – – – – – – – –
ee0a0ea0-d38b-5369-bedb-9eb0d23e2856 | note | VERIFYING DOCUMENTS: This ITP
2e8cbf88-4a69-5850-affd-f0ff8f7f01e2 | date | Date Completed:
| checkpoint | 5.2 Leveling Pad Concrete Pour
4ad6e7f0-6939-5c8a-a97d-6a2f0e69c832 | note | REFERENCE: IFC Drawings
ddd4b9a0-7b4e-5675-98eb-d6648889da21 | note | – – – – – – – – – – – – – – – – –
30052cf0-7fb5-593e-a76f-354f6d9328ef | note | ACCEPTANCE CRITERIA: Concrete to be placed in accordance with 610.
e9f69702-1518-517f-935f-18c3a7c89364 | note | Attach: Concrete Delivery Docket
50242171-8918-5689-a34d-b9b4c91bae28 | note | – – – – – – – – – – – – – – – – –
18858e5a-0c5b-58d0-9f5d-79d72cd99c8f | note | METHOD: Visual
0db85466-c697-5498-a8dd-5172848a613e | note | – – – – – – – – – – – – – – – – –
c75f7239-ec12-5cde-bacb-ed1fe25148b0 | note | FREQUENCY: Each Lot
4e0f21ab-ee4e-57df-879f-09ce0b9f9f47 | note | – – – – – – – – – – – – – – – – –
807eb993-e420-5357-aaee-e8d956a46c09 | note | CATEGORY: IP
1ebaf005-a5cd-5b25-9164-6b818b4aca2e | note | – – – – – – – – – – – – – – – – –
db108f6c-6da1-54f0-9968-485ea898db77 | note | RESPONSIBILITY: SE/Site Supervisor
c138ed25-d184-5e36-8ed0-207befefbd12 | note | – – – – – – – – – – – – – – – – –
49078a7a-7594-5e47-8ab5-e9a9af83209d | note | VERIFYING DOCUMENTS: Concrete Pour record
5a6bc732-33e4-5b38-a2dc-d7a99cc5402e | date | Date Completed:
| checkpoint | 5.3 Leveling Pad Concrete Testing
40835630-7066-508f-ae44-3657d2de9b5d | note | REFERENCE: IFC Drawings
5f754176-89ec-57c0-89d2-8a51d9cd5dee | note | – – – – – – – – – – – – – – – – –
7542ec66-472c-5d94-879d-964648cb4705 | note | ACCEPTANCE CRITERIA: Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
09ab71a0-c7cf-5036-a148-8306153f5b07 | note | Attach: Concrete test report
6bb78d82-069b-561e-92d6-a950d140d858 | note | – – – – – – – – – – – – – – – – –
62841cdf-66d9-5f82-a718-d0441a35a57a | note | METHOD: Document Review
eff81849-1ed3-5636-bc0d-9d3d4b0b15e6 | note | – – – – – – – – – – – – – – – – –
4b3b08b6-08c0-5c56-82ca-cc2c21614dde | note | FREQUENCY: Each Lot
203b1545-faee-5ec2-bf05-497c826998cf | note | – – – – – – – – – – – – – – – – –
7bf2a98c-d573-5a15-9caf-276fc978e521 | note | CATEGORY: IP
b9be637a-a672-5491-aa4a-448394ba9097 | note | – – – – – – – – – – – – – – – – –
e997eda9-485c-5b0a-aef2-7e21d4f18e30 | note | RESPONSIBILITY: PE
a0eed67c-9c56-5e9c-854f-5916f292793d | note | – – – – – – – – – – – – – – – – –
dc691f4b-7dcb-5734-b6bf-0a27a4e4f49d | note | VERIFYING DOCUMENTS: Attach Concrete Test Report
5b1d8a29-e4cb-5d28-abfb-dd0a07fd8e51 | date | Date Completed:
| checkpoint | 5.4 Levelling Pad-Post Pour Survey-Levelling Course
bc47cd65-126b-5bf8-af56-a6b2a3e606d1 | note | REFERENCE: IFC Drawings
178e5558-9471-56a4-ad21-66d0fa3094b6 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
0b7130e7-d3bb-5ead-8187-17360f9de90e | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
80e93925-d849-5ca0-8852-dfbd29201ef9 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
bc154f4b-cbc1-57fc-862f-a1407b72ee98 | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
6be26861-25bd-5ff8-aa39-1254121aea02 | note | – – – – – – – – – – – – – – – – –
55c2f01e-6aeb-5518-813a-8c300dbbb433 | note | ACCEPTANCE CRITERIA: Levelling course level shall not deviate from the specified level by more than ±3mm
dd89458a-8a86-584c-b1ff-c894f3182bd0 | note | – Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
90f9e0e3-5c38-5971-837b-7c14f456f161 | note | – – – – – – – – – – – – – – – – –
b77e9577-7573-5f47-9ce8-25f738c2b1ea | note | METHOD: Measure, Visual
b24b6d71-9126-55fe-b392-5ac09947e8bb | note | – – – – – – – – – – – – – – – – –
fbb379d9-0f54-56e1-9179-c35e1c5dcc5f | note | FREQUENCY: Each retaining Wall
626dc986-f16d-52a3-bd8a-71e664ad5dda | note | – – – – – – – – – – – – – – – – –
24061947-9d5d-5705-b44f-c58fa5625f7b | note | CATEGORY: IP
5fc0959c-0b6a-527f-a95d-05dbfd8579eb | note | – – – – – – – – – – – – – – – – –
355fffa2-45b9-5b02-b424-2cadced7b4b7 | note | RESPONSIBILITY: PE/Surveyor
35a85de8-2c23-558d-9d6e-604a1f5e872f | note | – – – – – – – – – – – – – – – – –
4f4a9085-14aa-56ca-97bc-5522e46f44c0 | note | VERIFYING DOCUMENTS: Attach Survey Report
54bdddde-d885-5400-8b82-4d16cb73f187 | date | Date Completed:
| checkpoint | 5.5 Wall Panels Installation
d9430ba7-885f-539d-b270-e9847d08f538 | note | REFERENCE: 682.17
29f834ab-cade-5d88-98c1-da5295932b1c | note | – – – – – – – – – – – – – – – – –
55da4019-4819-5c7d-9189-e1874c00f279 | note | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
ed24a67c-b1b0-5d23-83dc-d6510dfee4fb | note | • The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
6ef96ee9-dab7-58eb-80df-71d5658a0c1b | note | • Refer to checklist for each course of panels
5a9ffbba-f84c-5391-8318-e93f0ad4340d | note | Attach: Lot map
e7782e90-bddc-50cc-867e-1ff3d29e791f | note | – – – – – – – – – – – – – – – – –
7597ab4d-e3a7-5f03-98aa-434b0e4b4595 | note | METHOD: Visual, Measure
84006bc2-141e-5f51-b37f-b42076a90d73 | note | – – – – – – – – – – – – – – – – –
cbdf47da-ba6e-5b4b-aa6c-e27cda7b59c9 | note | FREQUENCY: Each course of facing panel
85b88bb7-cc04-5134-b699-5f3d006af61b | note | – – – – – – – – – – – – – – – – –
963cc402-d37c-544a-b44d-01812c6bf8dc | note | CATEGORY: HP*
b78ce687-534b-5e65-84f5-574b7f19168a | note | – – – – – – – – – – – – – – – – –
49d7644e-b6cf-5b48-a03e-a4e4a8ee266a | note | RESPONSIBILITY: PE/SE
a9a8c962-1293-5d25-b595-1ba9e9aff0e2 | note | – – – – – – – – – – – – – – – – –
d87fa261-895f-5401-8e2c-3f7b73b09147 | note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Pre-cast panel installation
1244326f-fcd3-5ff3-b48f-65252f65a27a | date | Date Completed:
| checkpoint | 5.6 Drainage-base of the Wall
a9f67426-017c-5cfe-991b-ca37f59149fa | note | REFERENCE: IFC Drawings
676d306b-8c88-5c29-bbd0-bdca0292e3fe | note | • MRP-052-C-SME-DRG-32-MPK-CSW-2053
ffa1f531-7716-5121-b457-d0c079f3a6a2 | note | – – – – – – – – – – – – – – – – –
7e37173e-6c59-5fd7-bd38-076a3087fa01 | note | ACCEPTANCE CRITERIA: To install 300mmx300mmGranular backfill in Geotextile BIDIM A64 around 100mm Dia. Perforted plastic pipewith 0.5%min fall to 50mm Dia weepholesin RSS panels.
83761097-6d35-55e8-b4bf-34c543f1c923 | note | – Geotextile BIDIM A64
b22197c3-69d4-5415-a581-e1097f9165bb | note | – 300mmx300mmGranular backfill
68a4fca3-4152-5edc-9f48-5b37768561b3 | note | – 100mm Dia. Perforted plastic pipe
06a3ece2-31d4-52aa-85cd-21d3c16dd995 | note | – Perforated pipe to have 0.5% mnimum fall to 50mm weepholes in RSS panels
7397ad7b-58aa-565e-98dc-5b0185e152ae | note | – – – – – – – – – – – – – – – – –
9c916166-feb4-58e3-b2c2-1b9d1e11a2e9 | note | METHOD: Visual
f7588021-a980-5947-b4b3-60986a9b74b4 | note | – – – – – – – – – – – – – – – – –
b917d173-5bae-526b-8685-0662ec5b5183 | note | FREQUENCY: Each wall
d842f95e-ef12-5c76-82dd-da783d56c3b2 | note | – – – – – – – – – – – – – – – – –
e8171655-f4a4-5000-9c19-6182ed846395 | note | CATEGORY: IP
60d2347d-610d-55c4-a671-4a8e459de077 | note | – – – – – – – – – – – – – – – – –
bdcb89a3-679b-5e0b-adf1-5b7a73925208 | note | RESPONSIBILITY: SE/PE
fb52f4ef-ad85-51ca-b89e-761be1bab63d | note | – – – – – – – – – – – – – – – – –
a2ed0717-c4d9-5b6b-857a-2b54e203b23d | note | VERIFYING DOCUMENTS: This Checklist
809e944c-b42f-50ce-ae14-7f1b148e807c | date | Date Completed:
| checkpoint | 5.7 Fill
62a62d9d-a43e-5f0b-8eaf-f26a6a565b42 | note | REFERENCE: 682.16
cfcc6013-5450-557a-a800-4b92ae353a39 | note | – – – – – – – – – – – – – – – – –
7873cbd7-4fb1-584e-bc36-1469fb2f81a5 | note | ACCEPTANCE CRITERIA: The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance.
b6f21b1b-c19b-57de-99eb-614bb37f3e4e | note | • No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted.
da899c96-65cb-52ae-bd0e-662ec6ef66d3 | note | • If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
a06f36a1-4e57-5511-a4bf-4f59189f7171 | note | • Refer to checklist for each fill layer
7770c051-0934-5439-9bb8-26c8f5499b91 | note | Attach: Lot map
01f0f818-1c24-5d7f-af94-ec373d5883a8 | note | – – – – – – – – – – – – – – – – –
4d583ce4-ad4f-5081-a55c-a2486f9c2cff | note | METHOD: Visual, Test, Measure
19a1c731-7e2e-5c7c-81fa-a4a1446a158e | note | – – – – – – – – – – – – – – – – –
81e06d14-1fba-50a6-a552-e8750dc97ed3 | note | FREQUENCY: Each layer of fill
297279d1-57ef-5521-b083-42139c61669c | note | – – – – – – – – – – – – – – – – –
1cb477cd-eaf4-54cc-8bd5-2f702cb84048 | note | CATEGORY: HP*
09047e11-9ee6-5d3a-bcfe-36cb451a38d4 | note | – – – – – – – – – – – – – – – – –
4008c3e9-7e09-51fd-ba49-6d13196efda5 | note | RESPONSIBILITY: PE/SE
7f8805b4-5c53-5deb-89a3-4d0a48c0c470 | note | – – – – – – – – – – – – – – – – –
27819e84-2558-5d82-88a8-0af7a0aee03f | note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Fill installation
34c523ee-1d2e-55f6-bd56-6ae3c1bbb4ea | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 As-built Survey
f83ed84f-2e6a-531c-811f-b58c7563695f | note | REFERENCE: MRPA Quality Management Plan
6208878e-cb65-58ff-a435-f36915a0f7f8 | note | – – – – – – – – – – – – – – – – –
c2071648-ce3e-51ca-a778-7f29bebe27d7 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
1d26bd10-ed46-5430-9343-f01ba0b6b871 | note | Attach: Survey As-built / Survey Report
e24d4d9f-a889-5d65-87f8-d5be6da63b5a | note | – – – – – – – – – – – – – – – – –
b38d854b-fb04-5726-bef6-3e29b153773a | note | METHOD: Document Review
6fd74c38-bcc1-58a1-9829-5a8b1b69f46e | note | – – – – – – – – – – – – – – – – –
dea735bb-d47f-54b5-be90-758c58d1bd78 | note | FREQUENCY: Each element
7497ce90-9022-53a7-82bd-cbd81a798ac7 | note | – – – – – – – – – – – – – – – – –
6482d1e5-37c4-52b0-a586-b964d538d652 | note | CATEGORY: IP
206fc87c-fae2-5769-8eba-ba8f95b57359 | note | – – – – – – – – – – – – – – – – –
29405fa9-4ebb-5f18-b05d-12f9e34e6b18 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
f14d97a9-1919-59cc-b931-7b7ecc3185c5 | note | – – – – – – – – – – – – – – – – –
8755cc80-2527-5762-877c-76d7530135b9 | note | VERIFYING DOCUMENTS: Survey Report
67d840cf-0a4f-5037-b7b7-6404a7de116d | date | Date Completed:
| checkpoint | 6.2 Wall Post construction monitoring
a65625bf-aee8-5f6c-a0e8-16d5e7e37325 | note | REFERENCE: VR 682.20, VR 682.21
7605cae5-6cda-5f7f-87fc-7fab84685eb1 | note | – – – – – – – – – – – – – – – – –
75ababa4-0ab2-595c-ab04-62800855845c | note | ACCEPTANCE CRITERIA: The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
cb253744-4a57-5836-9c84-83d755130676 | note | (a) plan position shown on the drawings, at base of wall shall not exceed ⌖15 mm;
704a83af-c296-5167-8062-da057ef3b838 | note | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
c25e087f-2af1-5ce3-853e-5b738c371d6f | note | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
2096018b-5787-5109-a0fd-ad6c7b28c623 | note | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
cd5ec6ec-2bd8-5f1f-b746-cf291d3f8d6f | note | (e) the wall level shall not deviate from the specified level by more than 20 mm;
4c935e00-e4cc-503d-b65d-8e280e55fb59 | note | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
d0a1af76-3611-5e5a-9d72-805fd9450879 | note | The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey.
e5701a2e-f0b2-53f5-b38d-72c2dda9afb1 | note | – – – – – – – – – – – – – – – – –
cdc88886-3d45-58d3-a007-0403ec48085b | note | METHOD: Measure, Survey
131c124c-495f-5070-8986-712a6940380a | note | – – – – – – – – – – – – – – – – –
644dc79a-c2d7-5ac5-84d7-79a0665127b8 | note | FREQUENCY: Each wall
378ba654-eac0-592f-a94d-427915658754 | note | – – – – – – – – – – – – – – – – –
bb280a9b-d99f-59bc-8ac1-299a25015455 | note | CATEGORY: IP
876e4f1f-b69f-540a-8f53-4f2f2c8ac740 | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
d0d71591-0d61-57b5-8ad1-536ea2dadc8c | note | REFERENCE: MRPA Quality Management Plan
47386c30-b6c4-56c2-be26-6e9285c64137 | note | – – – – – – – – – – – – – – – – –
811205d1-d5e7-5956-bfb8-98186ab259d0 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
1544313f-2e81-55c8-86d5-c43a9c69e0db | note | – – – – – – – – – – – – – – – – –
1a33c899-2f58-5f5f-b30f-edaa774cbe8c | note | METHOD: Document Review
3aac46f6-e882-5ca4-8171-06f61272cb63 | note | – – – – – – – – – – – – – – – – –
8482e1d0-934e-53c5-b891-77cbd9c38e64 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
bd4b41cc-9927-51ea-bc53-f0a5ae629755 | note | – – – – – – – – – – – – – – – – –
bcc35338-726a-5bd0-8aa1-ddffdb0d0d43 | note | CATEGORY: HP*
c3526f81-803a-50ec-a41b-c47c8c8ad9c2 | note | – – – – – – – – – – – – – – – – –
99aefe98-0b66-555e-87f1-d1318c0c8bef | note | RESPONSIBILITY: SE/PE/SPE
aafa504a-eb8c-5d3c-90b6-069bde4e1c72 | note | – – – – – – – – – – – – – – – – –
7820860c-cafa-5691-99d5-73247d373abf | note | VERIFYING DOCUMENTS: This ITP
9ee3d3d5-9fdb-5e2d-b3d1-54160afe7997 | date | Date Completed:
| checkpoint | Final Inspection
6b7e3044-01da-5c12-a8c8-1d03dd83d8d0 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
6bffcc49-da08-5266-a16c-bf686edaf980 | textbox | Name:
ee7ac50a-fa59-52bb-8199-cb595d7936b6 | textbox | Position:
90ff8abf-e3d5-5df0-88a2-b4e3489783e4 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-013-STR-Pile Cap Construction Rev 0 | itp | ITP-013-STR-Pile Cap Construction |  | e29a5e1b-8f35-4a6c-aaaa-644d6ccc31e4
| section | Referenced Documentation
| checkpoint | Referenced Documentation
9537e0d6-10e6-5017-a771-0286fc3d36cc | note | Document Title: ITP-013-STR-Pile Cap Construction
39e76b87-b4df-5933-9711-6cc693e2e6aa | note | ITP Description: Pile Cap Construction
b36e25c6-b26a-58bf-a2df-d9af4aa3b601 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
548fe2b6-45c0-5e55-a006-4310dfc64007 | note | Discipline (e.g. CIV/STR/RAIL): STR
301ed352-43a1-5945-bcfb-8919ae0df611 | note | Revision Number: 0
499deaa6-ac9a-503e-b9f9-78247084b9be | note | Revision Date: 01/12/22
db1de2cf-bef8-538c-8ea4-c58101742a73 | note | ITP created by: Victor Mira
e094fef1-1793-5707-83c0-a3fa7c9768ef | note | ITP approved for use by: Victor Mira
d7afed2d-2342-5000-bc66-86e84d768526 | note | 1.1 Non Dependent
9fda75b7-e628-521f-8df2-61904b584a56 | note | Reference: VicRoads Section 602 October 2007
452cfbd9-edc0-5f32-b1ad-42be068b887f | note | 1.2 Non Dependent
f17613fc-1a91-5070-9e1f-fd8b733637e1 | note | Reference: VicRoads Section 610 February 2020
c85d8da6-5e6f-55b4-a8c1-79667fd1b7bd | note | 1.3 Non Dependent
96380b3b-dbde-5005-9fc3-c447196238f3 | note | Reference: VicRoads Section 611 November 2018
df4f3ad9-383d-5d4f-bf06-2eb92a8dbf6b | note | 1.4 Non Dependent
0052eacb-88cc-5a80-9f4f-0153f446471b | note | Reference: VicRoads Section 614 June 2017
1dd5b02c-b293-509c-a0ab-1b33ae031005 | note | 1.5 Non Dependent
106f9158-6bdb-543c-b230-2b804ebdfc0e | note | Reference: AS3810.1 2018
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
77840da2-3cbe-52b4-a7a8-86e106a9984a | note | REFERENCE:
8bf686c7-4ecf-5808-b2f6-60160d22fe3b | note | 610.07
5900934b-475c-57a2-a18b-2f2b6d169f9f | note | Table 610.071
4aae9b62-df11-5e99-a598-0be4740779df | note | IFC Drawings
996cc973-f52d-5655-b739-c13000343e93 | note | – – – – – – – – – – – – – – – – –
0d808b45-2a1f-5c6b-b770-994f4e34ed3d | note | ACCEPTANCE CRITERIA:
c9e95c98-e1ad-51b5-b34d-3fd6fa37f667 | note | • Concrete Mix is Registered with VicRoads.
e84023b0-1827-5c69-9cee-0e1926a65f29 | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
486b9f5c-6026-597a-b623-f74c3752b5d0 | textbox | Enter: Teambinder Material Approval number
bf894c69-9df9-5bf4-ad96-165c4171e059 | note | – – – – – – – – – – – – – – – – –
c1503edf-d4a7-5e35-b77f-ed104d2c1ce8 | note | METHOD: Document Review
034ecb16-3638-5e26-9752-45d0e0b035e0 | note | – – – – – – – – – – – – – – – – –
25d85e4a-9f90-5e3b-a487-b7a503f412a8 | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
6b8e7c31-5317-573e-a635-20090eaa37cc | note | – – – – – – – – – – – – – – – – –
faacc0ed-d23c-57f0-a55e-25b9ca20a154 | note | CATEGORY: HP
16c7c894-531e-55f1-9328-d8d04eff0e70 | note | – – – – – – – – – – – – – – – – –
73c476f7-27a3-5e8f-bad6-d5896cb7f118 | note | RESPONSIBILITY: Nominated Authority
f90986ad-d2b9-5632-849b-58634b19e24e | note | – – – – – – – – – – – – – – – – –
ed78c1da-546c-5585-9f16-fc7174023a03 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
4763dc47-dd24-5113-b2b8-1de0948a9c79 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
81a7e293-eb20-5f8f-b3d6-b0c69594876d | note | REFERENCE: 611.05 (a)
a781f34f-b69c-54f2-9277-48afdc7adb10 | note | – – – – – – – – – – – – – – – – –
8d98135f-c205-5841-9777-7d736d14145e | note | ACCEPTANCE CRITERIA:
d415f1dd-e647-5b23-b41d-1782069844f6 | note | • Current ACRS certification for materials and for bar processing.
0bed4fe9-2d1d-5909-bd0b-759ec7a76cc2 | note | • Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
47c74bce-7d91-5c71-8eea-ea945bb74efc | textbox | Enter: Teambinder Material Approval number
a2d532a6-6f7d-5ba6-814a-fe28543bf34f | note | – – – – – – – – – – – – – – – – –
42643542-026e-5bf5-b0d2-fb78df2a2448 | note | METHOD: Document Review
6cb07bc7-ea02-5aa9-bf9d-5bb4d6aaf57b | note | – – – – – – – – – – – – – – – – –
9430b6c0-9bd4-5483-bf0e-75f37e58ab5a | note | FREQUENCY: Once for each supplier, 14 days of award of contract
ba185520-4ce7-5a10-b01e-e9dfcb318f4a | note | – – – – – – – – – – – – – – – – –
c99e59af-e153-5512-944c-b4c97331af8b | note | CATEGORY: HP
7b76b7a1-362f-58a5-bdd3-b4fde7957047 | note | – – – – – – – – – – – – – – – – –
03f962cd-9866-5968-8d12-56179b5ba365 | note | RESPONSIBILITY: Nominated Authority
4647b8c9-1027-5e02-a82c-8388749f686e | note | – – – – – – – – – – – – – – – – –
1c9df22c-672a-5acc-a64e-576c31c264bf | note | VERIFYING DOCUMENTS: This ITP
a4516bd0-2f9a-5e30-85f2-8faea10fd560 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros Certification
e30df8fd-d0a8-503c-a5ff-7113032df71d | note | REFERENCE: 610.26 (a)
797e454c-d125-51b3-9f9b-515378730d36 | note | – – – – – – – – – – – – – – – – –
171d7509-4395-516e-a0db-c0b4c7b5958a | note | ACCEPTANCE CRITERIA:
3351d11f-b1e5-5775-948e-4f129dcd4822 | note | • Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
fc2ea57c-4ba8-57a9-9d1d-14e15488241b | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
9ffdbed2-6db7-54c0-8a11-e27868a30c2d | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
c759c006-0919-5f9a-9382-7433dfa75baa | textbox | Enter: Teambinder Material Approval number
4097a1eb-5a36-5df1-92ff-666abaf8a6f4 | note | – – – – – – – – – – – – – – – – –
19d9e1a8-7f48-50f3-ab52-fe403239e07a | note | METHOD: Document Review
9f2aa242-0712-5fbf-8378-33b925df56af | note | – – – – – – – – – – – – – – – – –
8c48164b-ade9-5d05-97ed-02102b6f81c4 | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
82280f6f-eb73-5be0-8f96-ee9f26864715 | note | – – – – – – – – – – – – – – – – –
fa238b83-7459-5f3d-b098-555eb6281c3f | note | CATEGORY: HP
b72eb3f4-b68f-5987-bc23-0016de7162b9 | note | – – – – – – – – – – – – – – – – –
803c782c-03f7-5c4b-99ad-d271f7d62d05 | note | RESPONSIBILITY: Nominated Authority
51eb03f2-fdf9-5fb7-8315-7a95f414c7a7 | note | – – – – – – – – – – – – – – – – –
1568d4cc-0073-5395-b690-746afd11381b | note | VERIFYING DOCUMENTS: This ITP
ea24d8d6-ce2e-5126-9a80-337757c41e84 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Evaporative Retardant
5baecc5e-3a30-5ab2-ae63-7f147bf5323f | note | REFERENCE: 610.17 (f)
4bfbf535-b4fe-50aa-bbaf-07ed453c7b47 | note | – – – – – – – – – – – – – – – – –
ba1fa5dd-ffd4-5030-b377-52e50907e893 | note | ACCEPTANCE CRITERIA:
97b7839e-9c53-59a8-93fc-3d9b11662f6d | note | • Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
7cd0b209-e05e-583e-899f-08691d2e06b0 | textbox | Enter: Teambinder Material Approval number
3c5a5845-0726-5f97-a3b5-e65042c0db77 | note | – – – – – – – – – – – – – – – – –
2594326a-eff5-5aa2-982a-2499055e9db6 | note | METHOD: Document Review
1803432e-5879-5104-8275-b68494668738 | note | – – – – – – – – – – – – – – – – –
2a6c0e74-008e-5d5e-a029-9b76996c14d0 | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
064ecc01-0810-5b14-a502-30c5dbaeeec1 | note | – – – – – – – – – – – – – – – – –
d99a5b5c-8c4d-5b82-b59f-d9722c783e53 | note | CATEGORY: HP
61317cb3-d735-516c-8e36-63b338ac6c3a | note | – – – – – – – – – – – – – – – – –
28ccddef-1f15-5a93-95df-e11bb1110656 | note | RESPONSIBILITY: Nominated Authority
06960362-f7cd-500e-84e7-2edd541adb18 | note | – – – – – – – – – – – – – – – – –
f3c73957-e34e-5499-96a0-ce4c70dc6cdd | note | VERIFYING DOCUMENTS: This ITP
1c700ecd-159b-56e7-b932-feb752194e81 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.5 Curing Compound
6639e5da-4af4-5d75-9d78-7c13fab06341 | note | REFERENCE: 610.23 (d)
3f523261-666f-5360-b4b6-3f080bd7260c | note | – – – – – – – – – – – – – – – – –
3bd69980-f38c-5aa9-b154-f041669c1bd6 | note | ACCEPTANCE CRITERIA:
3ef89396-c644-5620-9031-f9ba8e99434d | note | • Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
e74c98c8-1fac-5d88-b81b-10115649f161 | textbox | Enter: Teambinder Material Approval number
c8c26647-ad7a-56ea-a86c-c943ebdf2a48 | note | – – – – – – – – – – – – – – – – –
5d81fd21-51b6-5eac-b0be-137d4aa69e66 | note | METHOD: Document Review
ca59e8b8-2e0f-58a8-9880-912306c9b560 | note | – – – – – – – – – – – – – – – – –
e9780934-1cd8-5843-90d1-9ce4fb731ca1 | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
0dc4b7cc-8a75-5e9f-8108-8d8f42d66957 | note | – – – – – – – – – – – – – – – – –
69dccb87-f0bf-58e6-af99-6e249b686e3a | note | CATEGORY: HP
b99af72b-82fb-5348-b0fc-c8f36e60d259 | note | – – – – – – – – – – – – – – – – –
a5194b14-34dd-5bf8-8ab9-3a8cc44a313d | note | RESPONSIBILITY: Nominated Authority
03cf607d-c46c-5658-80c2-4f0f976f9649 | note | – – – – – – – – – – – – – – – – –
960fc029-df24-5242-a4a7-a885d1c0a701 | note | VERIFYING DOCUMENTS: This ITP
e96c8b4b-ea5c-56ae-a02b-56d45bc387c8 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
56033bd8-92bd-5796-8c35-c40831f14d26 | note | REFERENCE: 610.18 (a) (i)
35e6b3c0-b877-5e96-a3ff-f69e9559f9e8 | note | – – – – – – – – – – – – – – – – –
7b90a47a-812e-52bc-b38b-751b04068132 | note | ACCEPTANCE CRITERIA:
a54bb344-117e-53aa-a7c2-fefd6dc1e492 | note | • Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
8684a9b7-12d5-56d5-9d45-db7c126d4bdf | textbox | Enter: Teambinder Approval number
b181179a-f67d-5e1a-85dd-6c733837f0ce | note | – – – – – – – – – – – – – – – – –
f62964ae-0ac3-59b1-b26e-1d9cd85c50b0 | note | METHOD: Document Review
4b10acd8-b4ea-5c4d-9bb3-0890e6bd2dda | note | – – – – – – – – – – – – – – – – –
9d85f99a-cf85-5a2f-8d08-fd7469e22347 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
5c78c291-9a53-5388-9ab4-d13ebcd4b648 | note | – – – – – – – – – – – – – – – – –
5c27cfea-ab5b-5633-b01a-2ad2e8fc485c | note | CATEGORY: HP
d935d828-8061-56a2-87d9-6973c22b3513 | note | – – – – – – – – – – – – – – – – –
36132bea-d192-5d31-b560-d191ea84d975 | note | RESPONSIBILITY: Nominated Authority
6c98a61b-9c34-5ee0-9703-98c31202668f | note | – – – – – – – – – – – – – – – – –
e383aecf-d2ab-5d65-86d4-37981485c631 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
28fd0526-6e8a-5366-b90f-a1939238b36a | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Concrete Sampling and Testing Procedure
9bf97174-a24e-5a7f-8ef2-03eada6000ae | note | REFERENCE: 610.18 (a) (v)
a805eb1d-8e9c-57d8-90d1-d5b9add5db1c | note | – – – – – – – – – – – – – – – – –
f829bbc3-e103-5b66-952d-cc699a984ef3 | note | ACCEPTANCE CRITERIA:
9045fa32-0310-5cc5-be53-b1fd7e13acf6 | note | • Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
cfef85b2-b3da-55d0-803e-d8ac23714bda | textbox | Enter: Teambinder Approval number
1c4fbc93-1269-5efc-b872-04fe5351202d | note | – – – – – – – – – – – – – – – – –
4bed68ee-fe9b-58ad-a6b2-7bd9c225e4e7 | note | METHOD: Document Review
831ad3fd-4021-50b5-b024-1e47b1e15357 | note | – – – – – – – – – – – – – – – – –
5a57d245-9c1b-5d73-b2ff-2fadda27ccb4 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
bfd37efe-69a8-5daf-ae97-88d65b0b7a03 | note | – – – – – – – – – – – – – – – – –
4e23c772-2a6b-512d-bdc2-fe1d241f3311 | note | CATEGORY: HP
8adfba96-a46f-53e6-8d44-bb716f6b0eb5 | note | – – – – – – – – – – – – – – – – –
f1bfa603-acdb-56d2-92a7-a749fd40df8f | note | RESPONSIBILITY: Nominated Authority
4cdbd056-d66e-5d5c-b7b7-bd7898796e8d | note | – – – – – – – – – – – – – – – – –
7c77ac64-7090-52a1-8bfc-e956749d5181 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
e871b1e3-f88c-56cf-9e79-a59735fc75d3 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
caae385c-daf1-5096-80d5-6e76fcf3803e | note | REFERENCE: 610.18 (a) (iv)
205ea65c-59d0-5d1a-b924-3c305216d072 | note | – – – – – – – – – – – – – – – – –
63e828c8-25f4-5ca1-9487-202138abed08 | note | ACCEPTANCE CRITERIA:
25c4fd32-9872-505b-8ae3-3794b219eac1 | note | • Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
70c7d522-dabe-5f3a-8f60-ca1e238a3cb6 | note | • Minutes of this meeting to be submitted to the Nominated Authority.
5e124d36-c34b-5f73-952f-0a29d9018fa5 | textbox | Enter: Teambinder Approval number
f1ab8116-e6cb-55f7-8050-b4e8b05e98a0 | note | – – – – – – – – – – – – – – – – –
7c250af0-74af-5183-94f8-4b8f31439b2d | note | METHOD: Document Review
8414664e-b0bf-59e1-b87c-d911bc2ca7ac | note | – – – – – – – – – – – – – – – – –
c83c280c-3cdc-5a32-8411-213c718d7547 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
7dd82aa8-a08a-5521-948b-d6f2bf5f28be | note | – – – – – – – – – – – – – – – – –
0f8f92c7-8b40-5b8f-a23b-bfd72ee3f645 | note | CATEGORY: HP
e05626c8-a85a-5493-aabc-d930b98b9b6d | note | – – – – – – – – – – – – – – – – –
6f40aa42-7fce-5965-bdb5-65a85c6b8196 | note | RESPONSIBILITY: Nominated Authority
117e5e8a-7dc8-5efe-bbaf-800a125da239 | note | – – – – – – – – – – – – – – – – –
e4ca6508-470b-538a-afa8-a14867092c44 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
935de38b-875d-58dd-b167-779cfd24228b | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
7b079b2a-e460-5fa5-ad9b-a3bdace03df9 | note | REFERENCE: 610.17 (a)
6f3e4406-d02a-50b4-898b-c7c7479ce32b | note | – – – – – – – – – – – – – – – – –
920db9ed-9329-5cc4-af7a-70bc146dc982 | note | ACCEPTANCE CRITERIA:
0a4024a7-4e2b-5af9-890e-bb420112e6ff | note | • Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
e055efc8-ef2a-5582-8eaa-209305554684 | textbox | Enter: Teambinder Approval number
932a8aaa-497e-54b9-a6ff-63857f99eaf9 | note | – – – – – – – – – – – – – – – – –
6804e185-8a41-5c20-9530-da731d18374e | note | METHOD: Document Review
a8758758-8069-5ea1-93fe-14a4da69d239 | note | – – – – – – – – – – – – – – – – –
406b67c6-26ad-509c-8b38-1865531e387a | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
f33d510c-2f6c-5824-9e58-3d82647b3fe3 | note | – – – – – – – – – – – – – – – – –
647e3d4e-41ab-50bc-99c5-9fd6b661995d | note | CATEGORY: HP
476130d3-a3db-5124-8bc8-b693e66bbed9 | note | – – – – – – – – – – – – – – – – –
af68356f-ac24-5ebf-8bd0-b77e4b28c142 | note | RESPONSIBILITY: Nominated Authority
b3101959-9b81-5da1-a0e6-1045951ca3b9 | note | – – – – – – – – – – – – – – – – –
8fe8d31d-41c0-56f3-8e6e-b9222b95d899 | note | VERIFYING DOCUMENTS: This ITP
0f9b0c2c-8121-598c-818f-876d6d8f130e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
8d1d5327-2f3d-5cf7-b9c0-159c304803f0 | note | REFERENCE: 610.23 (a)
a2fae9ce-8829-53f9-9600-69f764db72ca | note | – – – – – – – – – – – – – – – – –
647b5494-9ad6-5f0c-9607-6f498389c039 | note | ACCEPTANCE CRITERIA:
395fe7e0-0f1a-5ac3-bc15-44028df73a0b | note | • Curing methodology/procedure to be submitted for review to the Nominated Authority.
5d9e38c2-2e22-59ff-b1d1-3bb2331228c8 | textbox | Enter: Teambinder Approval number
5d66bebe-2585-54ae-91c8-c74d0261bc1e | note | – – – – – – – – – – – – – – – – –
a1f1ed26-7e2a-560a-8191-24bb6674e5b2 | note | METHOD: Document Review
65934380-80fc-5908-ad01-58f43aa7209e | note | – – – – – – – – – – – – – – – – –
32551c8c-e3b5-50af-9f9a-ba64cbabf626 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
664442af-3b00-58f5-904c-ddd5dee2581c | note | – – – – – – – – – – – – – – – – –
1a271b99-68b5-5d00-94af-77c7ee40b495 | note | CATEGORY: HP
1d4438f7-5fb6-520d-b4b5-d0eb063f87e2 | note | – – – – – – – – – – – – – – – – –
ec5231c3-7416-5fda-a132-0bf015154085 | note | RESPONSIBILITY: Nominated Authority
ada5b814-f946-5ab1-b287-eb7b3069c487 | note | – – – – – – – – – – – – – – – – –
7c1acb6b-5183-50a7-aed8-04f948882459 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
64fd3522-7d64-523f-941f-205602481d63 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.7 Concrete Drilling Procedure
17343267-381f-5726-a936-f4cef22fa69d | note | REFERENCE: 610.46
77edfcc6-c0ec-5af0-80af-753e3a52b2f5 | note | – – – – – – – – – – – – – – – – –
f159cfaf-8dea-522a-b680-fcfef2dc24d7 | note | ACCEPTANCE CRITERIA:
21a3b103-bdb9-57e1-ab21-6dc927f6077e | note | • Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
f4016fe4-9acf-50fd-b258-225dbf67ae38 | note | • The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
b9e15548-a459-5a87-91eb-5c79dde545c0 | textbox | Enter: Teambinder Approval number
acc62fa3-0ffa-5105-9bed-2609e763ea35 | note | – – – – – – – – – – – – – – – – –
6073fc64-af40-5f94-8bd3-512f1e5c7a88 | note | METHOD: Document Review
b494b93c-aa64-56a3-8318-6f412082f51e | note | – – – – – – – – – – – – – – – – –
b8e5889c-c01c-547a-bb16-ebca825d0d91 | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
ea740f62-d13f-5d7e-a27e-4528e5a6f790 | note | – – – – – – – – – – – – – – – – –
4b19292a-060f-55e5-adc6-12c4cc12d640 | note | CATEGORY: HP
3711cfc5-cca1-57fe-b97c-6174e9396a22 | note | – – – – – – – – – – – – – – – – –
816b6a07-9cf5-5c96-b08b-e20d9160982c | note | RESPONSIBILITY: Nominated Authority
363ef277-cfd1-5916-b9bf-67141f8bf46c | note | – – – – – – – – – – – – – – – – –
36a51185-c15c-55a2-ad2c-1656720a4980 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
cc6922bb-50a5-53eb-ade1-5ef73ba7f9f3 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.8 Temprature difference measuring-Calibration
855ed2c6-f89f-5826-a206-5b43c52db918 | note | REFERENCE: MRPA Quality Management Plan
948f3be3-f84e-5300-88ed-445694ca49a0 | note | – – – – – – – – – – – – – – – – –
ddeff652-a29d-5534-8ed8-259f287deee2 | note | ACCEPTANCE CRITERIA:
89df13bd-69e7-55da-9a79-0e270ebfe342 | note | • Calibration records are valid and up to date.
1c0c6ae6-a3af-599b-8463-6ce49acd7d6e | note | Attach: Calibration certificate
233555c0-2479-502b-a05e-a2a33dcf946e | note | – – – – – – – – – – – – – – – – –
a21ea0d1-f238-5f5f-b3dd-cecb9f7a8ff2 | note | METHOD: Document review
4e157ca7-5d65-54f0-9f2d-d7b7e3c0552f | note | – – – – – – – – – – – – – – – – –
8eb2fb9d-9d91-5d02-85ae-7866afb64228 | note | FREQUENCY: Where applicable
e7350344-2f3d-5254-86bf-17c42fed9e0c | note | – – – – – – – – – – – – – – – – –
e1074c1c-6958-5796-a564-07ac06274422 | note | CATEGORY: HP*
0ed01805-89b9-5ee2-866e-010660664010 | note | – – – – – – – – – – – – – – – – –
7f9a8e8f-8409-5e90-8273-4475ab9f06d2 | note | RESPONSIBILITY: PE
513e80d6-6145-5212-a06d-ea5a924b68d1 | note | – – – – – – – – – – – – – – – – –
3c546660-4785-505b-9e17-f803891bde9e | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
1bf25038-4545-512b-8450-177fb45be54a | date | Date Completed:
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
8ba0feac-b66e-59b4-939e-7d10bb7486fc | note | REFERENCE: MRPA Quality Management Plan
b753b8d3-af69-5ea9-87f5-6a588b823999 | note | – – – – – – – – – – – – – – – – –
03f9870f-1883-5c74-8a4a-7b1511494891 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
f14d70bf-f0da-5b41-856f-0ae628e1bb23 | note | – – – – – – – – – – – – – – – – –
6d3843b5-48c7-575a-81c0-0be6899e4f39 | note | METHOD: Document Review
6bfdfa72-318e-5124-9dc2-ca2fec9bc05c | note | – – – – – – – – – – – – – – – – –
7faa375f-d12a-5321-9725-d7434c8431ed | note | FREQUENCY: Prior to starting Works and at regular intervals
49fc630b-0600-512b-a67a-e93a1a06894f | note | – – – – – – – – – – – – – – – – –
36dcf768-12fb-52c1-861d-831251476edf | note | CATEGORY: HP*
6aefb2ef-9c05-51b2-b8d2-49ed49f9773d | note | – – – – – – – – – – – – – – – – –
ee7117fd-405c-5d03-86b8-30bb0d874f9e | note | RESPONSIBILITY: All
0435f20d-060b-5a68-9334-ddcb7447312c | note | – – – – – – – – – – – – – – – – –
d853ab1b-6278-5e8d-9419-8cb8c733aad5 | note | VERIFYING DOCUMENTS: This ITP
847fb292-a8b6-5af9-a5fd-ee5835de75c6 | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
f27cbe1b-aecd-5bbe-9664-90757d11167d | note | REFERENCE:
44650ab4-667f-5800-9133-95b5f9248d32 | note | IFC Drawings
53c5d341-e358-533d-a635-15133a642183 | note | 610.47 (a)
42553cf0-cf67-57c8-bbc1-2d079988c890 | note | Table 610.472
b97ac717-9fa0-559f-99f8-9d736e185ca8 | note | – – – – – – – – – – – – – – – – –
e9d39b0b-0950-58c3-ae1d-5d9da2e722c0 | note | ACCEPTANCE CRITERIA:
e133fb56-1b87-58f8-af12-5f8440654cb3 | note | • Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
fe448c4d-ccf7-58d1-9015-2bde51327ec8 | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
ac3e5a97-814d-5160-9710-e035024d82f0 | note | – – – – – – – – – – – – – – – – –
f8cc10bc-dcc4-5a9b-bc29-8e9c455873e7 | note | METHOD: Measure, Visual
1fc955f4-2443-5b76-897d-c8b1e91b247d | note | – – – – – – – – – – – – – – – – –
65e2526e-4f90-5130-8848-ffcbcdb52ee7 | note | FREQUENCY: Each element
e435584b-00c3-5c26-87a3-6c83d3c2299e | note | – – – – – – – – – – – – – – – – –
d6582612-9b52-51ac-bd4e-90270b30fc3c | note | CATEGORY: IP
1d760725-d4c9-5442-aa73-e50a80628f7a | note | – – – – – – – – – – – – – – – – –
de51f7f3-5cf7-598d-9fca-3ca793a11967 | note | RESPONSIBILITY: Surveyor, SE/PE
54d9bd50-c626-5781-bfea-c3ec4c19e4e7 | note | – – – – – – – – – – – – – – – – –
08a7ee06-e84c-595d-9288-d7a2ad1c050c | note | VERIFYING DOCUMENTS: This ITP
fe398c0d-78d7-5cd7-8ff7-2d4824c47369 | date | Date Completed:
| checkpoint | Piles
ddd20467-8bfe-5c6a-a89a-106c92be1d88 | note | REFERENCE: IFC Drawing
946c46e3-1415-50d8-98cd-19eea09dc610 | note | – – – – – – – – – – – – – – – – –
66fdd58c-2e50-522f-aac3-17aa4ed105eb | note | ACCEPTANCE CRITERIA:
ef1b9b07-f773-5349-972a-28e77b2528ad | note | • Related piling Lots are closed.
084c0f97-076b-5217-a5b0-6121468a6e45 | note | – Pile design strength is achieved.
de3b62c2-4e1b-5a42-8618-d2367041de5c | note | – Integrity and Dynamic tests performed and interpreted.
ad4a6fb9-88d2-5bb5-a932-3cb191e065e5 | note | – Pile is broken back to the design level.
f9d032d9-f66f-5e5f-8d18-85b20894804f | note | – As-Built Survey performed.
a80ee40e-cddc-5701-9920-e9c48085da00 | note | – Related piling NCMs are closed.
bf88119f-2d95-5679-8180-86332f1661bd | textbox | Enter: piling Lot numbers:
f75f2dcb-17f3-55d8-83dc-ccb27dfef6df | note | – – – – – – – – – – – – – – – – –
9851cf31-db1e-5ba4-b1ce-6d9dbd6e52be | note | METHOD: Doument Check
d6071318-41d8-5dd8-960e-af3b74ab36b6 | note | – – – – – – – – – – – – – – – – –
2cc2324e-d52f-5722-8d1f-4d9e5c0b607a | note | FREQUENCY: Each Element
0bf71792-9da9-543f-93ff-1e8897e133e7 | note | – – – – – – – – – – – – – – – – –
5802dc25-8566-5857-9a56-e0e1db3b2c85 | note | CATEGORY: HP*
940ef90f-136d-5abd-bbfe-1ee65d8ef3ce | note | – – – – – – – – – – – – – – – – –
9072513f-1d38-5342-89f4-505b220050ef | note | RESPONSIBILITY: PE
f61e508e-4b04-58ee-9ea0-59fff0d2df1b | note | – – – – – – – – – – – – – – – – –
b24d9dcd-b013-5c3d-9151-bb36946232f2 | note | VERIFYING DOCUMENTS: Piling Lots
860a69f3-4d8f-5c11-976d-f6b692f7117b | date | Date Completed:
| checkpoint | 4.3 Excavation support
e1b01e5f-7aef-5a33-ac61-182605089b62 | note | REFERENCE: 602.02
f17d13cd-6acc-5de5-ab5d-7024468de96e | note | – – – – – – – – – – – – – – – – –
c3f578f9-4b52-5091-b34b-743964f09d58 | note | ACCEPTANCE CRITERIA:
a154ebf1-471e-529d-b4e7-7ec5d618b8b4 | note | • For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
cf644a87-2fa6-55ae-a36b-d123b3276780 | textbox | Enter: Teambinder Approval number
f6621765-7deb-58c6-9e91-ffb0ca40d073 | note | – – – – – – – – – – – – – – – – –
612ac64e-5c03-5dec-99cf-87e47f605802 | note | METHOD: Document Review
43738dbb-0da5-542c-9c95-a85b39d21970 | note | – – – – – – – – – – – – – – – – –
0372bfda-7421-5b5e-8e07-bfea56701950 | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
7322e95f-b1eb-5b4c-9455-5afb75073f06 | note | – – – – – – – – – – – – – – – – –
945aaa14-8092-5c62-a599-2e69292f1e11 | note | CATEGORY: WP
5cdb349c-9947-5954-826e-f03d076a5742 | note | – – – – – – – – – – – – – – – – –
cdb6ce8f-0da2-518b-83ef-1e0a8a8be17e | note | RESPONSIBILITY: SE/PE/SPE
cf1bf5d5-5d41-5b31-989b-4cca237cc585 | note | – – – – – – – – – – – – – – – – –
86c40481-5925-574a-8a3b-a95879ae6d6b | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
1a0c2238-2853-5d87-ab9b-50cfc7910b93 | date | Date Completed:
| checkpoint | 4.4 Excavation Inspection
d886ccb2-1955-547e-94b6-6afb781e2119 | note | REFERENCE: 602.03
a27ed158-8fbf-51ea-b545-bdebcd8ddea7 | note | – – – – – – – – – – – – – – – – –
9e255c37-dcea-57e1-b77c-e45da9fb6457 | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
3397f3d3-2545-52cf-9e2c-5dc3b6ba6076 | note | – – – – – – – – – – – – – – – – –
014fc285-a637-59c6-8e72-1fe71edccbe1 | note | METHOD: Visual
a1057273-f4fb-5225-be79-7a224ba4f80f | note | – – – – – – – – – – – – – – – – –
2d591db6-2b3a-55ab-9e4b-3a042f61a30a | note | FREQUENCY: Where applicable, prior to placing blinding concrete
161a862e-67d9-510b-99df-071a63d7f727 | note | – – – – – – – – – – – – – – – – –
8d1f508c-a882-5b43-87f2-427d8b81d99a | note | CATEGORY: HP
ee61aa3f-9521-5d47-ad75-cb99b4d9e8d0 | note | – – – – – – – – – – – – – – – – –
064db2df-4a20-5468-ac14-6ed2692dd7cd | note | RESPONSIBILITY: Nominated Authority
afe9a744-0055-5aa0-ad70-1936f4452c0b | note | – – – – – – – – – – – – – – – – –
39a6aa2d-73a7-563b-b8b0-e724bf7b68e2 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
5767be11-91b6-5365-b741-93a4718f7cc5 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Construction Activities
| checkpoint | 5.1 Formwork Design and Construction
f989043c-a888-5fea-9c7e-9cbe8ae78563 | note | REFERENCE:
225bc97b-5721-52d4-8034-3bbadc309547 | note | IFC Drawings
9ec08803-66ac-57f6-8a09-f55203642feb | note | 614.04
39e6699b-ccb9-552a-967c-4fb263951423 | note | 614.05
934dbe8c-169d-5f85-a46b-21ccdcb7ea31 | note | 614.06
312d84a7-f950-5c5f-b317-b50a325bf7b9 | note | – – – – – – – – – – – – – – – – –
0299bbb2-b569-5f9c-9544-2c50aa30cee9 | note | ACCEPTANCE CRITERIA:
7907d739-3bfc-592b-b36b-cb8dfefd26c4 | note | • Designed and constructed in such a manner so it can be removed without damage to the concrete.
dcc4e3cf-41e2-5d75-89a7-7de97a78f25a | note | • Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
3051bd3f-635c-5f9c-925e-472b09676885 | note | • Formwork shall not be placed where steel & fixtures cannot be inspected.
425b575e-1805-58cb-9ab6-9da60ce912c8 | note | – – – – – – – – – – – – – – – – –
c555b353-6195-549b-bd31-a2d0c2686486 | note | METHOD: Document Review, Visual, Measure
5353c29f-fe92-515e-9c1d-5a1561ab28ad | note | – – – – – – – – – – – – – – – – –
07efec0b-f68e-5d3c-b789-6fbc8e29e10d | note | FREQUENCY: Each type of element
144bab4e-15f7-50dd-bbcd-cf027e63d2f4 | note | – – – – – – – – – – – – – – – – –
bab9036a-ef98-5f2c-adec-0bb7b3174779 | note | CATEGORY: IP
3937d2b2-6e77-5a1a-85e9-883216487af7 | note | – – – – – – – – – – – – – – – – –
4e0ba5aa-c2c3-5319-a233-f10a482ab31b | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
ebc8675d-8cde-5474-8a87-0c476fac7464 | note | – – – – – – – – – – – – – – – – –
9f9c4298-1d1d-5fa8-bf05-389ea71fea76 | note | VERIFYING DOCUMENTS: This ITP
0a7062ad-69fa-5266-ad9b-74c8b2d41e76 | date | Date Completed:
| checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
e0fcfe68-a581-5abc-bfe3-d3546aaf3371 | note | REFERENCE: 614.08
9964a3b2-569e-52a4-b82f-601e3749902f | note | – – – – – – – – – – – – – – – – –
e08f99eb-c19f-5a83-8601-9f3e2b0b61ed | note | ACCEPTANCE CRITERIA:
313efdac-cb4f-5c08-b47e-bc56fae6a1b9 | note | • The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
8d83ac28-748c-5b02-ad7f-b165d16ebe14 | note | • Pile caps with heights greater than 2.0 metres
62b106ea-1262-5daf-8074-7f50ec390b7f | note | • Any member for which self-compacting concrete is proposed.
475d3dca-b7ca-55d3-8cc0-86b5343090ce | note | Attach: Attachment A
43ad4170-69b1-59ab-8538-38840a803846 | note | Attach: Attachment B
fddf2cb5-0f69-5d43-adbc-8b665c1fa6f5 | note | – – – – – – – – – – – – – – – – –
01a1924f-1740-5db2-9907-f1dff9187e67 | note | METHOD: Document Review, Visual, Measure
5458ee80-9e29-53d0-b409-5ecf040e1d04 | note | – – – – – – – – – – – – – – – – –
07c83501-d41f-5369-8b37-7608f7abec2f | note | FREQUENCY: Each element (where greater than 2m)
eef2a5fc-2be4-501f-a68a-9af88a2f254b | note | – – – – – – – – – – – – – – – – –
5e7bdc60-6c9e-573f-9634-4e59a6b4f521 | note | CATEGORY: HP
94524740-a166-5ac9-96cf-1d22a72d7dd5 | note | – – – – – – – – – – – – – – – – –
aaa188cd-aa66-59ea-9c43-89d4917fdf41 | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
94d4427b-aba3-5201-904c-70f195bbd6e6 | note | – – – – – – – – – – – – – – – – –
984043e0-2959-52bb-86e5-5284ef600921 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
ca1d067a-37d5-5aa0-b1e1-2492d6c4e0f2 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
8533ddc2-cbfe-5ad2-b9dd-0dba4b1ad828 | note | REFERENCE: 614.08
d3d30b71-1b76-5ced-bb34-d70716af06ba | note | – – – – – – – – – – – – – – – – –
cdb48712-4f35-5593-8d59-150b118a4c4c | note | ACCEPTANCE CRITERIA:
04458d77-ca8a-5c97-ba2a-954a3324e395 | note | • The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
c641968d-06bb-59fe-8ed3-62cfeae83f43 | note | • Pile caps with heights less than 2.0 metres
4ab4b83a-ca1d-5350-9f32-f8283908b83c | note | Attach: Attachment C
88865b05-f395-5a9c-94da-88aabeb2d48b | note | – – – – – – – – – – – – – – – – –
ed636648-d3a2-5f49-b94d-584db1eee48d | note | METHOD: Document Review, Visual, Measure
9f805cc6-339a-5d97-9a0d-6d7161c020cb | note | – – – – – – – – – – – – – – – – –
5c528937-cad6-5b3c-befc-ed4ed8cdaeef | note | FREQUENCY: Each element (where 2m or less)
b15f0711-44b7-5db6-aced-10d3bdcf8817 | note | – – – – – – – – – – – – – – – – –
0a9bfa5d-ba02-5153-a959-ad44904011a0 | note | CATEGORY: HP
e54dd52b-1367-5caa-ac51-9993dfa56b60 | note | – – – – – – – – – – – – – – – – –
b8a93224-619f-5426-a7b6-210363ecce49 | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
56b2d3d6-1589-5763-a8bc-101f0976bdf5 | note | – – – – – – – – – – – – – – – – –
d26c9106-d6e0-542e-adbc-7fce02ff3fd4 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f9e8a1b3-e9d1-59bb-ad2f-bb693f3b9824 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.4 Pre-pour Survey
e2da9334-2255-5c8b-b7ee-d75f00d8a313 | note | REFERENCE:
f5881060-ef34-5ac6-954c-5ff4d84d2606 | note | 610.47 (a)
264e9db8-e178-5d8c-910d-7dc83977075d | note | Table 610.472
f47f9c17-59d1-5ae6-b843-c950b6273195 | note | – – – – – – – – – – – – – – – – –
bef58e38-821b-54ff-af2e-77a3a44cd706 | note | ACCEPTANCE CRITERIA:
2b894aff-08e2-5b5c-ae26-851afeccc642 | note | • A pre-pour survey carried out by a surveyor.
69c4e856-a22b-5505-a1ff-ffda3d9ee1b5 | note | • Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
a8afea04-b18e-56b1-aa17-d9cfe7644f5b | note | – – – – – – – – – – – – – – – – –
3d80ea93-709f-5b11-9305-5751e09a1a7d | note | METHOD: Measure, Visual
f90fac72-027f-57e0-a50d-0a51fc70be07 | note | – – – – – – – – – – – – – – – – –
1ca91f2b-f160-5b4c-9827-65c9bae6ab37 | note | FREQUENCY: Each element
ccd5ba4a-d85e-5f79-8872-b951a625b5b9 | note | – – – – – – – – – – – – – – – – –
7855acd7-4f97-53e5-a817-085f570030f9 | note | CATEGORY: HP*
755a2c93-44d2-566d-ae90-22ec0941002e | note | – – – – – – – – – – – – – – – – –
97ecbd8c-adf0-5ed5-8936-006b9f5204be | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
df858dac-b1a0-5a85-aa0d-68fa06d27166 | note | – – – – – – – – – – – – – – – – –
4b13eb06-f99b-5048-9957-6345c475cb6b | note | VERIFYING DOCUMENTS: This ITP
e5acf8c2-f406-5797-9445-d3ee66f404be | date | Date Completed:
| checkpoint | 5.5 Reinforcement Placement
946334a3-fbc6-5467-b276-f85d24ff0a32 | note | REFERENCE:
8d625f43-d333-5a35-b53b-aa79b32345b2 | note | IFC Drawings
f4846816-7eda-51da-9fd4-36196006940c | note | 611.06
f5a45f27-fcb6-533b-84ab-02b10756c37e | note | 611.09
905d251b-cfab-5a44-b487-0c353f24a694 | note | 611.10
531cbeeb-8306-5780-8b3c-8d05eda6b3f1 | note | 611.11
d0e3c5e6-2ef8-5a19-b0f6-658e0d89453b | note | 611.12
7a788079-4991-5d0f-92e8-1aff26712351 | note | – – – – – – – – – – – – – – – – –
eff62d22-7c38-54e9-be0a-db7a6eb1676d | note | ACCEPTANCE CRITERIA:
379eaca9-ef85-5dac-938f-55baaae530e5 | note | • The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
13cf7a8d-dff6-5046-96e7-132e9f957c62 | note | • Projecting reinforcement is the correct length and location.
5e51e022-0028-54f4-8805-8570afa0b158 | note | • Splice lengths achieve the minimum length and are in contact for this length.
62d61194-84af-5f3f-8eb8-7a71e2cfff4f | note | • The reinforcement surface condition is free from dirt, debris and damage.
ec75959e-be82-5fc3-abb3-c74a154c5a8b | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
31597d6b-f5cb-5603-bdbd-b9270ecd3d5f | note | • Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
c20b77ee-cb69-5a2b-8345-27d91f9c8946 | note | – – – – – – – – – – – – – – – – –
0d959bc9-1e60-58f5-bf1b-07027bd65d2d | note | METHOD: Measure, Visual
7c021ee0-426c-53a1-a8cf-31c64ab3176b | note | – – – – – – – – – – – – – – – – –
224c947d-c41d-50f5-baa7-c0727b356d58 | note | FREQUENCY: Each element
04a01851-8309-554f-87ec-48bba7fda981 | note | – – – – – – – – – – – – – – – – –
ff4055ff-d7d8-5d3c-8a03-3111cbafa43e | note | CATEGORY: IP
58a0d69e-a905-5513-be92-8a2dad6a7e87 | note | – – – – – – – – – – – – – – – – –
d514293b-fad4-53e6-bc27-854bba6b531e | note | RESPONSIBILITY: Foreman, SE/PE/SPE
7c5ead58-6e21-5fc7-b2bb-8603f86a826d | note | – – – – – – – – – – – – – – – – –
d6cbaecc-f60c-557b-a0e4-6a220f60386d | note | VERIFYING DOCUMENTS: This ITP
ace4e8d2-cf74-5c41-80d5-c0bf0b580ee1 | date | Date Completed:
| checkpoint | 5.7 Cast-in Items
867cd10e-9fa1-5126-aec3-f69c72b256d6 | note | REFERENCE:
b8749262-2713-5814-8b7a-c8e08854a61a | note | IFC Drawings
52c108bb-fc94-56e7-8f96-76c7e39da906 | note | 610.47 (a)
fcf0d529-1cc4-5b40-8dc5-4dc061bb9955 | note | Table 610.472
eab73f90-f7a6-587e-9bed-7bca0adfa7ee | note | AS3810.1 Table 3.3.6.2
3a68e729-61a7-55e5-8498-1514c4b015ca | note | – – – – – – – – – – – – – – – – –
25c466ef-51b3-5911-b327-d3796665406f | note | ACCEPTANCE CRITERIA:
b7338832-9226-5bce-a052-cb4726d79475 | note | • All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
a5bf10ae-eb56-50c0-a6e2-2a18c4d3d6ab | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
38d02f77-5f3d-505f-9165-86eddac98571 | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
f8648265-6675-59df-84c1-e1555b939944 | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
681485d4-da3a-54d7-8b32-c6a05fac4e06 | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
381e3254-5a0d-5d6d-8316-734789d9c303 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
b7ccb225-8645-5f29-acd8-87a5011d69b7 | note | ii. Running dimensions of a group of the above = ±6mm
a45ffd1b-1d71-5a85-99a2-82c498ca147e | note | iii. Ducts and conduit location = ±12mm
ce23c99f-63b1-5f33-885e-bc6e34f94f65 | note | iv. Diameter of ducts and conduits = ±3mm
25b0497e-b2d6-59c8-8c17-833d8b8905fb | note | – – – – – – – – – – – – – – – – –
0360ec34-6d47-59d0-b54b-f9a8b988d5ff | note | METHOD: Measure, Visual
b9fa1471-a31e-5173-9e41-05ef2f4863f5 | note | – – – – – – – – – – – – – – – – –
6272cf5b-191f-55d5-b48c-25b43cf93fdc | note | FREQUENCY: Where applicable, each element
f985c651-6dba-5bca-b354-06a0a7c0e621 | note | – – – – – – – – – – – – – – – – –
82782dc1-0ba4-5cd6-b469-71737a08a887 | note | CATEGORY: IP
5b40996d-7ef1-57e1-83e3-1c6028b061c1 | note | – – – – – – – – – – – – – – – – –
0b4cda05-bbbb-5b60-8b83-586d77bf1af0 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
641161a9-6db2-536b-a155-e367156c3134 | note | – – – – – – – – – – – – – – – – –
b82b3d02-0202-5dbf-9e00-35f498cffabe | note | VERIFYING DOCUMENTS: This ITP
e0b8b495-b1cc-51a2-b989-4a7ff7ae63ee | date | Date Completed:
| checkpoint | 5.8 Thermal Differential Monitoring
bb04dc58-efbb-50a2-951b-b6f8d90646d5 | note | REFERENCE: 610.22
2e775b28-5b8f-5bcf-9367-d9272e671733 | note | – – – – – – – – – – – – – – – – –
ab406813-69d6-5023-9392-a77e7ca624df | note | ACCEPTANCE CRITERIA:
a19c79af-bb29-5c1a-826a-9aed6f1a0b5c | note | • Thermal differential monitoring thermocouples installed.
d97cd9d7-64f0-5675-8aa4-119f67ecbc11 | note | • Only applicable if the element has:
1b32eb0a-3d19-5286-9654-b9a8f34a5f6b | note | i. the smallest sectional dimension exceeding 500mm
4bf64596-e249-5224-810e-7fccd1ef9b97 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
4659e61c-49da-52e5-aed4-14630a3d2fbb | note | – – – – – – – – – – – – – – – – –
79116c33-1704-5fa8-9463-f278aa0d8a82 | note | METHOD: Measure
d855ecbd-d9b8-5b41-8a5c-0456043d667c | note | – – – – – – – – – – – – – – – – –
db8b5cb6-e0fa-58ce-9095-262a9e334e0f | note | FREQUENCY: Where applicable, each element
82a86f7d-de8a-511c-9647-1cd6a3c1c123 | note | – – – – – – – – – – – – – – – – –
c14e4684-9ecd-5e62-a698-00591e776e0a | note | CATEGORY: IP
85fd0daf-202b-522c-8a3a-bda4bd4eef71 | note | – – – – – – – – – – – – – – – – –
f0dc3358-3d95-5882-9665-acbc01d7d8cc | note | RESPONSIBILITY: Foreman, SE/PE/SPE
00cf5eb1-01e8-5a74-ad7c-ba4318123a23 | note | – – – – – – – – – – – – – – – – –
9d178f9d-1769-50aa-bf77-2fcd9c90c410 | note | VERIFYING DOCUMENTS: This ITP
6fe9a628-8965-576d-8ef9-c3190f3d936a | date | Date Completed:
| checkpoint | 5.9 Pre-pour Inspection
e280bf7d-1f46-5dc5-8dac-88ed5cfa1b75 | note | REFERENCE:
c863f2a1-fd3b-5bab-a852-663592acfbb5 | note | IFC Drawings
c9d06aae-0ff3-5dd3-92e5-01d8eacdc9cd | note | 610.18 (a) (ii) & (iii)
701d1f97-eb22-5fcb-a789-a5e283122816 | note | – – – – – – – – – – – – – – – – –
ea3fb228-a655-575b-b607-2e4f107d98c2 | note | ACCEPTANCE CRITERIA:
1fb586fe-5db3-52f6-b260-2292d4898faf | note | • Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
ab4e2a15-425f-57e9-9fee-dcdb750cd443 | note | • All foreign material has been completely removed from the forms.
a2ab0acb-29b9-55f6-aa69-0c2cd6f6ee24 | note | – – – – – – – – – – – – – – – – –
f22ea55e-73e9-5bf4-bf35-694bf120569f | note | METHOD: Measure, Visual
31207fa7-67c8-589e-b67d-dec9e6b8a733 | note | – – – – – – – – – – – – – – – – –
0538fb70-86ae-5ff2-b904-c493a2ab187d | note | FREQUENCY: Each element
4661ddbd-a134-505d-9620-321ff44698e8 | note | – – – – – – – – – – – – – – – – –
5b243b78-9456-5c7d-a519-81d9d2298605 | note | CATEGORY: HP
caa873f6-2533-5ae2-be3f-38ea3beba202 | note | – – – – – – – – – – – – – – – – –
491b9d42-c770-5125-9624-b4d5991d31d0 | note | RESPONSIBILITY: Nominated Authority
2a0be196-46d4-5639-b096-1f83d6e7ad54 | note | – – – – – – – – – – – – – – – – –
6c364b38-4938-52eb-baf2-7efc7bd6f576 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
b4e0e1c5-78c6-5890-8961-e58f0b10bbb8 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.10 Weather Conditions & Evaporation Limits
6a6b66b9-11c8-5bbe-9380-98975f264607 | note | REFERENCE:
7e778dbd-0fe2-5dd9-9e0d-3cfd16a8e382 | note | Hot and/or Cold Weather Concreting Procedure
b992e6b7-4a9b-5895-ba36-ec10eb1403b6 | note | 610.17
71f948cd-5a1d-5033-a53d-d93d87df9b78 | note | 610.17 (a) & (e)
b2d7b4ca-003f-547c-a741-b4e3f12940de | note | Table 610.171
8fd85287-6d6f-59b9-92ad-90888b74a524 | note | – – – – – – – – – – – – – – – – –
8c9ec6f5-aa7e-511e-bf6e-7da142956de0 | note | ACCEPTANCE CRITERIA:
2786a2e5-83fe-5437-abbd-c38230b66157 | note | • All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
86fdb993-4769-5568-b3bb-9085193b96e5 | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
c92f416d-f8d7-5d51-a051-da60e0792e4a | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
a7dfdafe-8cff-58da-9645-4783b1730e73 | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
da93e4af-f1d2-5908-be1e-66a0a6426e34 | note | Record: Required information on the Concrete Pour Record.
c1c81973-89ee-5e72-bfd1-f4e44b82d147 | note | – – – – – – – – – – – – – – – – –
820f6d86-93b4-5537-99fe-d8268b5fc094 | note | METHOD: Measure, Visual
0861ada3-9f2b-530d-9523-2cce9e7b7a06 | note | – – – – – – – – – – – – – – – – –
8b80e31b-f382-5f1b-af0c-425de5f6b90c | note | FREQUENCY: Each element
25faeda0-5465-5560-983a-f80b1243f6af | note | – – – – – – – – – – – – – – – – –
9acd93b1-a42f-5e39-a98e-08cccaa1c785 | note | CATEGORY: IP
43a366ad-10e7-5565-9b3b-db214d009c50 | note | – – – – – – – – – – – – – – – – –
70068ffd-5059-5b52-92d9-8d2af6da476a | note | RESPONSIBILITY: Foreman, SE/PE/SPE
b9e58c15-9726-51b0-a9bd-71f63a951697 | note | – – – – – – – – – – – – – – – – –
e28dbd0b-fb00-5da6-97b0-4972dc26e8cb | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
0b5f8fff-4b94-59d9-9656-f16950bd7459 | date | Date Completed:
| checkpoint | 5.11 Concrete Testing - Sampling Frequency
1452cca1-dc72-57d7-86df-1b9e35738a50 | note | REFERENCE:
b3aceef1-ed07-5540-813d-cf7eb17017e0 | note | Site Sampling & Testing Procedure
77ec71f7-092c-55f4-bfc8-fe63ada99426 | note | 610.16 (b)
de990f64-8e16-56de-adc9-a0c79673d991 | note | – – – – – – – – – – – – – – – – –
edac4b44-b1f8-5653-af68-e7e1c94185b2 | note | ACCEPTANCE CRITERIA:
b1ef43b6-82f7-5159-9d01-ed78d3a16956 | note | • Concrete cast in one continuous operation to be tested at a frequency as shown below:
ae1f0b4e-15d8-5a97-a34c-2be72805138f | note | ○ 0m3 to 10m3 = 1 sample
b484235e-bd93-5297-bb2c-7e9504bf928c | note | ○ 10m3 to 25m3 = 2 samples
49eb095e-c166-5abb-9f7d-74e7910eaa63 | note | ○ 25m3 to 50m3 = 3 samples
24752c47-ba31-5ba1-b109-c94625b018d8 | note | ○ 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
820e7551-6f72-552b-a01b-131c92c479eb | note | • For each additional 50m3 and additional sample shall be taken.
1cadad57-646f-5da4-bd97-48cd3bfcf813 | note | • Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
d6857fdc-0baa-5fa6-a87a-3baf003f17d6 | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
ebb543af-8d72-59b1-b425-77f1b2aee9a2 | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
f2604a58-3560-5466-b450-41289d44e868 | note | • Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
9c87c8e4-90c0-5cf8-82a2-63037e36fe5a | note | Record: Required information on the Concrete Pour Record.
c6725099-cf05-522a-93f4-4840f210738f | note | – – – – – – – – – – – – – – – – –
bd2ae5bf-e653-52f7-8c9d-7d4fe6d454f0 | note | METHOD: Test
25768238-1f26-5a99-9598-b08419abe6a6 | note | – – – – – – – – – – – – – – – – –
0d6004ba-31cd-5a35-a011-c7be320106c4 | note | FREQUENCY: Each element
096c0802-62a3-5914-959f-a09a39093caf | note | – – – – – – – – – – – – – – – – –
a3df8aff-f5bc-553c-b8ff-787251123c8f | note | CATEGORY: IP
e4c31a74-8be0-5363-8a53-23e5806a302a | note | – – – – – – – – – – – – – – – – –
7b1e685b-9ac8-5493-91a3-1d562e6ff637 | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
a07abac0-3ffa-5fdf-8ca0-0bd1709de2af | note | – – – – – – – – – – – – – – – – –
7fe2ece7-533c-57bf-a2e1-cf631f9b9e98 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
89c641c6-3d27-5e6e-b88b-76a275374e4a | date | Date Completed:
| checkpoint | 5.12 Concrete Testing - Slump
3ed606ae-8eb9-5202-a415-445af3193c61 | note | REFERENCE: 610.16 (c)
f2f03d88-ca8c-5301-a788-f2a6a270bf16 | note | – – – – – – – – – – – – – – – – –
9132a241-bfa4-5a08-ba9f-a4f0ab85e75b | note | ACCEPTANCE CRITERIA:
8af0e6ab-d1ed-52d0-aeb1-ab6551377fd7 | note | • Slump testing tolerances =
32b74541-e010-5f55-bf6b-6de82399fc54 | note | <60mm = ±10mm
e44cc7a2-0e76-5f81-9a00-2365d3235430 | note | ≥60mm to ≤80mm = ±15mm
4cc8d5ae-e808-51ea-a386-5a8e731ade93 | note | >80mm to ≤110mm = ±20mm
6258816a-05e4-5463-b433-262a0fbcaaca | note | >110mm to ≤150mm = ±30mm
7b33e682-64ef-5620-8ed1-b21e6c56dc09 | note | >150mm = ±40mm
c2498530-2ca1-5674-9316-2710b3796149 | note | Record: Required information on the Concrete Pour Record.
97befe9a-65c8-5949-9ef8-59be5ed55d06 | note | – – – – – – – – – – – – – – – – –
909cd082-9628-5875-9a10-1c93bb0d3b0f | note | METHOD: Test
2d3d8eee-c3cb-5409-9f59-8f1bf1f17feb | note | – – – – – – – – – – – – – – – – –
cdc720da-70e2-5fdf-9198-b7c25a304b11 | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
a090156f-481d-5e75-8ed1-158287b61a0f | note | – – – – – – – – – – – – – – – – –
9acfc5bb-fc3f-533b-bdaa-2231fb83227a | note | CATEGORY: IP
c4e877ac-032b-5a92-b0ff-cfb8d55b239b | note | – – – – – – – – – – – – – – – – –
becc38d4-0d8f-5c0d-874d-10cba0dd66cb | note | RESPONSIBILITY: Concrete Tester
89da971c-5975-58b7-b7b0-992b9e2f74e3 | note | – – – – – – – – – – – – – – – – –
0c7319b9-618f-53df-86a5-8e97e290528b | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
15707944-a36c-5c81-8c00-99a29672c0cc | date | Date Completed:
| checkpoint | 5.13 Concrete Testing - Spread, Passability & Viscosity
964ac323-56ec-5716-a287-08c5c5344836 | note | REFERENCE: 610.13 (b)
e1edf20b-a90a-5f95-999f-83abbee0c2c9 | note | – – – – – – – – – – – – – – – – –
7172fae8-f067-5887-89e5-0163d98f71b4 | note | ACCEPTANCE CRITERIA:
ea33fcd2-c10a-58c2-95e6-ebb08a11c621 | note | • Spread range = 550mm to 750mm
ed6e5811-652a-59ee-8aa9-66c68f778bbe | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
b6a16d87-e02f-54c0-b676-33035907c92c | note | • Passability = ≤10mm (aggregate height differential)
2cadf85f-9196-5edc-8a29-bb7179b95ee6 | note | Record: Required information on the Concrete Pour Record.
10211731-1892-5fd4-8427-03062c8fdbac | note | – – – – – – – – – – – – – – – – –
6687948d-aa5b-5170-a76b-5a55d4536bd0 | note | METHOD: Test
27c6086d-120b-5a23-8ec6-f81d642bb247 | note | – – – – – – – – – – – – – – – – –
61f06bd0-c389-5f9c-bd12-641a71cfbe44 | note | FREQUENCY: Each sample of Self-compacting Concrete
81203724-6d9e-53c7-aea6-1354b5117e79 | note | – – – – – – – – – – – – – – – – –
6c090134-c042-5985-a379-3f907f675c66 | note | CATEGORY: IP
684bd9eb-e14a-5c10-876a-e553a54a8048 | note | – – – – – – – – – – – – – – – – –
f4e783dc-6b9a-5c9a-9f5f-477f8c312298 | note | RESPONSIBILITY: Concrete Tester
2e7c1181-b10d-5075-97be-c44e6cd3aeae | note | – – – – – – – – – – – – – – – – –
fa262b0c-d93f-5615-9b26-26d8a0610869 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
ebf07ea4-09cf-5c56-a288-dafb48e5f45b | date | Date Completed:
| checkpoint | 5.14 Concrete Testing - Compressive Strength Cylinders
d4d16b07-fa0f-54c0-9f3b-eb903a0c7261 | note | REFERENCE: Site Sampling & Testing Procedure
2cb198d8-6769-517a-b96d-53f06eb3a223 | note | – – – – – – – – – – – – – – – – –
7d4c5699-4f49-5525-a931-5d1ad12433a5 | note | ACCEPTANCE CRITERIA:
c31e9627-a352-54d3-b8c3-1f17d9893688 | note | • Correct quantity of cylinders manufactured per sample.
44aff761-7320-5a4b-b331-75ed0c4927c1 | note | Record: Required information on the Concrete Pour Record.
bca6fea0-eb5b-52ea-9d32-b5d8f642fdef | note | – – – – – – – – – – – – – – – – –
4e45590c-7700-535c-966e-1224d66f652a | note | METHOD: Test
a935b494-7df6-57bf-b545-af545c8f1ab2 | note | – – – – – – – – – – – – – – – – –
a0d2f127-494a-567a-ba4c-39cf08d956f4 | note | FREQUENCY: Each sample
2c98093d-3c63-52b4-a55e-3d7604ca4f7c | note | – – – – – – – – – – – – – – – – –
f61e4e65-5043-5bc8-95c3-aaae69df8df2 | note | CATEGORY: IP
41d04a20-b59e-5106-a6ec-19a212c8fd4f | note | – – – – – – – – – – – – – – – – –
6a78ffea-800f-535d-9985-776b649ec151 | note | RESPONSIBILITY: Concrete Tester
24a30eb6-73dc-54bf-b259-157780b51993 | note | – – – – – – – – – – – – – – – – –
f690b7aa-b4cb-50b9-84f1-a80e7aa92cd3 | note | VERIFYING DOCUMENTS: This ITP
47ad1564-5f81-509d-b158-e861f1852689 | date | Date Completed:
| checkpoint | 5.15 Supply & Discharge Rates
5fb3d281-49cf-5e7a-836c-a6531534c344 | note | REFERENCE: 610.13 (a) & (f)
48b85441-3bf9-5f2d-8ca6-702f8f638b3d | note | – – – – – – – – – – – – – – – – –
8bbcdff3-9295-528a-b597-4da7d210a1ba | note | ACCEPTANCE CRITERIA:
81b2aec8-fd8b-5da5-92ae-d1b8b8bf4853 | note | • Concrete is supplied at an adequate rate to ensure no cold joints are formed.
b2753004-47b5-5c36-9cae-86f2be94f089 | note | • No water is to be added once discharge commences.
21e87a76-cb17-5deb-810b-5632d54aca18 | note | • Maximum time between batching trucks is 25 minutes.
f0c62352-1f52-557b-9af9-75530de12c8b | note | • Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
c4190844-30be-593b-ad55-5dc3d5fa192e | note | • Concrete that stiffens or is showing signs of stiffening shall not be used.
4aeecf42-a903-56e0-b686-ae23614e4720 | note | Record: Required information on the Concrete Pour Record.
17dfcb50-cfdf-533c-a6f8-23ec86163b81 | note | – – – – – – – – – – – – – – – – –
e3f2887b-9b1e-5bb2-aef8-bccd58fa5e6f | note | METHOD: Measure, Visual
b6c64d56-48b5-554c-9deb-85f4be729204 | note | – – – – – – – – – – – – – – – – –
ac5714bb-a84c-58ee-b713-3f1ead49f9ae | note | FREQUENCY: Each load
2b486b31-ab25-55f7-a438-ccb78f741ca4 | note | – – – – – – – – – – – – – – – – –
2e1eeca9-a1a5-5c93-8b12-f2bc8a5d4fba | note | CATEGORY: IP
29c1c572-fe13-5068-9a36-bc9a52299c2c | note | – – – – – – – – – – – – – – – – –
a4e791f2-875d-5ca1-8a1b-8609236002b6 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
3a3276ba-7703-5c29-be6b-8570b0394c59 | note | – – – – – – – – – – – – – – – – –
822fcb2a-634b-5ed6-bd12-96e0f571979b | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
173f4b65-f265-5a39-89e9-3542804b079d | date | Date Completed:
| checkpoint | 5.16 Placement & Compaction
0d4f9af7-78d3-5f64-90df-5d0152a99ad2 | note | REFERENCE:
c8e769b7-464d-5490-a1ea-68f6078949fd | note | Placement & Compaction Work Procedure
b5882319-1af3-5665-a52a-cf6db4d15e0d | note | 610.18 (a) & (b)
e63938c0-86cb-54d4-8ed4-fd84d9cf9d3d | note | 610.18 (d) (i)
0ee29b00-ccd9-50b8-8787-63af43a998af | note | – – – – – – – – – – – – – – – – –
b1e5d60d-d63f-5eca-85ae-82a6bbc664da | note | ACCEPTANCE CRITERIA:
031eff1a-ab4b-5640-8a45-297da9cffa14 | note | • All concrete batches are traceable.
bcbac07c-ff86-5da7-a67d-64defa0ef1d6 | note | • Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
b1d4bc77-c44e-5ab9-8f1f-0891b20677f4 | note | • Concrete is not dropped freely from a height exceeding 2m.
df84a8a9-0455-5b3c-811e-19686b95f9e7 | note | • Concrete is not moved horizontally by use of vibrators.
6688d6b3-e9e2-58cf-91da-9e38b0a01192 | note | • Adequate compaction is ensured
688ff7f8-e3ec-5281-a6bf-95c5e573deb9 | note | • Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
59a3aea9-9aa9-596c-b61f-c8e6bad08a86 | note | • Concrete layers are not more than 350mm
e6dd75e7-f622-5a7c-9a4e-2ddc533f4026 | note | • Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
1a5accbf-e60b-5229-bd8c-758205790647 | note | • Vibration continued at each point until air bubbles cease to emerge from the concrete.
277ddb4d-6cce-5fde-a91d-2759da590c34 | note | Record: Required information on the Concrete Pour Record.
394e32b7-75c8-5181-b792-ce7c5d1ee497 | note | Attach: Concrete Pour Record
1770c552-de39-5d0d-b2c3-02ee8e219bdd | note | Attach: Concrete Dockets
4e40b09b-fff2-5fb6-9972-ae4b021c3133 | note | – – – – – – – – – – – – – – – – –
47408aad-08ae-51a9-9e27-177346f7a7f0 | note | METHOD: Visual
2c196314-af18-531e-8ee5-0343e32abb48 | note | – – – – – – – – – – – – – – – – –
3dd4d41e-dd8a-5107-bcf3-2d2bca6b03fe | note | FREQUENCY: Each load
0b539478-52d8-51bf-90d9-34bc27c755e5 | note | – – – – – – – – – – – – – – – – –
618019fc-9f21-5711-8444-1951dcedfa85 | note | CATEGORY: SP
5a342f99-2ca7-5a82-b86a-c2f259081974 | note | – – – – – – – – – – – – – – – – –
60d14922-8fbd-571c-bdb1-8e2f66fa4090 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
1e373b17-cd35-5673-9811-24601276a920 | note | – – – – – – – – – – – – – – – – –
54f270fd-6e69-558e-b07d-f39fa0b4593b | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
93f99e9f-3817-5a7f-b5c9-0c59667afe88 | date | Date Completed:
| checkpoint | 5.17 Surface Finishes
17a07c3b-0c9c-5092-b8e7-5d7ef2440076 | note | REFERENCE:
e2cef093-8321-5ac3-a611-53d8bf9edaa1 | note | IFC Drawings
6c0dab3e-2e7f-5f3e-bab5-d07d87c7ef35 | note | 610.31
8fd2183c-f12d-53f4-bee0-06a89e6f3aee | note | 610.20
20d6eb92-0442-5d03-9116-aaf308382cc7 | note | – – – – – – – – – – – – – – – – –
c411d54c-176a-57c7-be2e-90182feddfb7 | note | ACCEPTANCE CRITERIA:
9d9d3be7-69da-5d0b-a70b-3781c1bca755 | note | • Surface finish as per IFC drawings.
c3ed7cc6-01df-5118-aabf-c407f9edbb2e | note | • Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
67a5ff47-37c4-597f-9a66-569d677b9014 | note | • Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
6ce1c90e-f492-5529-9ca9-1196e5bfe540 | note | – – – – – – – – – – – – – – – – –
c87692a9-c00c-59ff-b8da-253f472063aa | note | METHOD: Visual
402c3862-5dda-57a8-a8a4-b8d3d358dc3f | note | – – – – – – – – – – – – – – – – –
d204fd90-9d44-5a94-b125-f9f2f9d626be | note | FREQUENCY: Each element
0b8b62b6-7744-5ac7-abfb-bcd5451bbe9d | note | – – – – – – – – – – – – – – – – –
ed60af92-ced1-5a03-b04d-9b68e1f7f9ed | note | CATEGORY: IP
af1e20d5-4c2b-534b-82ef-f9709d88f454 | note | – – – – – – – – – – – – – – – – –
ee023a2f-d3ff-5cbe-8b2b-a76fa6d50c7b | note | RESPONSIBILITY: Foreman, SE/PE/SPE
b2f8c654-292a-5585-9fc2-431117476bcd | note | – – – – – – – – – – – – – – – – –
8f28e900-62ca-5520-ad77-7d71f05f09d3 | note | VERIFYING DOCUMENTS: This ITP
d7f93665-f5da-578b-bd5d-c13817fc1fc7 | date | Date Completed:
| checkpoint | Curing-Top Surface
0f59ca59-0855-5195-91f3-e6b3f4a0ccb6 | note | REFERENCE: IFC Drawings
f3a8c7d5-c866-584f-ba26-082ac553f93b | note | – – – – – – – – – – – – – – – – –
83135336-c0d9-52df-989a-d6cffc1af6d1 | note | ACCEPTANCE CRITERIA: Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
cb15502e-b351-5197-a712-c470379e0f0d | note | – – – – – – – – – – – – – – – – –
3ee2a640-e409-57a9-94c0-08f37056f3ab | note | METHOD: Visual
c587fedb-3c02-5383-9280-ac83b8aad24c | note | – – – – – – – – – – – – – – – – –
b2e1b64b-c764-5d15-9879-f46cf581278e | note | FREQUENCY: Each element
232ac7fa-ce98-53bf-ad7c-e4f4ef03edf4 | note | – – – – – – – – – – – – – – – – –
151bc871-f552-5583-adf4-3ed2a6de4927 | note | CATEGORY: IP
3e85173b-7f45-5332-8504-241633f7a556 | note | – – – – – – – – – – – – – – – – –
e26de55e-358a-5e24-add4-03b4854d2780 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
32bf79c4-56b3-5d29-a8c9-4b3b316ddaef | note | – – – – – – – – – – – – – – – – –
a9735ceb-0b84-56aa-9dea-d7cbe1dd7328 | note | VERIFYING DOCUMENTS: This ITP
53aa5c70-ac4d-5699-9940-7498d29e940f | date | Date Completed:
| checkpoint | Curing after formwork removal
f6f11f89-22f7-54ea-93bf-6baa2863f8f5 | note | REFERENCE: IFC Drawings
d86b3c7c-492a-5e88-9f49-3a3cdb708f9a | note | – – – – – – – – – – – – – – – – –
2bec6921-e611-5c27-9cf9-9e0d43a6c20b | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
4d87184e-6d52-59d8-8086-c3255461b2b6 | note | – – – – – – – – – – – – – – – – –
56fc2a62-c96e-572c-924c-e2b3e97411fb | note | METHOD: Visual
e3b195ee-1973-5189-8d0b-8542368aeb94 | note | – – – – – – – – – – – – – – – – –
a64ac6d9-3f14-541c-b9a9-5d37ab7204fb | note | FREQUENCY: Each element
429d030c-0900-5167-b21a-89a2cff2c253 | note | – – – – – – – – – – – – – – – – –
3dcbd85f-e14b-5d51-b187-9b055676da6c | note | CATEGORY: IP
59694591-5214-5a1c-9d1c-784b13918392 | note | – – – – – – – – – – – – – – – – –
9742d88e-cc87-5a12-806a-474f85bf936f | note | RESPONSIBILITY: SE
324052a2-c7c3-58ff-b666-6bca3bdaa285 | note | – – – – – – – – – – – – – – – – –
9aa0d60a-c753-5c98-82c0-25c0e9b618a2 | note | VERIFYING DOCUMENTS: Thip ITP
1344b742-e566-5bde-9b5a-0b484f5d4a36 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Thermal Differential Monitoring
356309dd-0854-5aa7-99bb-5d0be899f125 | note | REFERENCE: 610.22
3a1d378d-782b-5f50-a464-ba0ba53b8fe0 | note | – – – – – – – – – – – – – – – – –
ed121305-a9c2-5107-9a6e-058ca45afbca | note | ACCEPTANCE CRITERIA:
ec241c83-5d3d-5083-86e6-6338ebf6e009 | note | • Maximum thermal differential between the core and exposed surface not to exceed 20°C.
28fb4f87-26b6-5fcd-9e66-7ca7eb267ac3 | note | • Only applicable if the element has:
4d738641-cede-56f7-8582-987bf658f2e5 | note | i. the smallest sectional dimension exceeding 500mm
11582b6a-e8c6-59f6-8d47-608a61da693f | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
434fd5a8-188d-55d5-ba34-31524038cbdf | note | Attach: Thermal Monitoring Report
50074c5b-9659-550c-81d6-588c8cc2c9bb | note | – – – – – – – – – – – – – – – – –
d6264ead-8a8e-5cd4-bb9d-e068b35bfd18 | note | METHOD: Document Review
80c635b0-404c-5b21-a422-ac8ca570e910 | note | – – – – – – – – – – – – – – – – –
7a149964-6c2a-5455-863f-a228545cc1c6 | note | FREQUENCY: Where applicable, each element
b1084a03-96f1-58d7-af4e-a8c87e7fe81a | note | – – – – – – – – – – – – – – – – –
436067ff-2155-5453-b6e5-37d9d3ea9056 | note | CATEGORY: IP
16e06079-300c-5dbe-9714-f5529165d448 | note | – – – – – – – – – – – – – – – – –
d314f234-d118-5e30-be8a-8143ec72c46c | note | RESPONSIBILITY: Foreman, SE/PE/SPE
fb3a9b50-f028-5ee8-9706-7a0eddc7213e | note | – – – – – – – – – – – – – – – – –
3c702d29-ac73-59a3-9d0d-35d758b5e4b9 | note | VERIFYING DOCUMENTS: This ITP
3f014c2b-65a6-5642-b8b9-6e34d5e56540 | date | Date Completed:
| checkpoint | 6.3 Early Age Compressive Strength Test Results - Removal of Formwork
f97cc589-8fec-5062-8fe1-de15750ff948 | note | REFERENCE: IFC Drawings
e6ab1798-70ed-5d4f-85cd-a2868596af84 | note | – – – – – – – – – – – – – – – – –
4899e8d1-d248-57f7-81fe-ef6e496c5ce8 | note | ACCEPTANCE CRITERIA:
30527d45-e8d9-59e3-8bad-65ca8cfd1802 | note | • Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
469a9cba-d5df-5fdf-b745-d02370ce6c26 | note | • Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
a16d936d-78a5-5e5b-8890-f6b8e2b01cfc | note | – – – – – – – – – – – – – – – – –
78a04093-465e-5156-b793-e8c0bfd57edc | note | METHOD: Document Review
596e31f8-c8ad-5526-8de4-74c3000a4f9e | note | – – – – – – – – – – – – – – – – –
e27ddfde-9871-5004-8a5f-3c8db77bdfc4 | note | FREQUENCY: Where applicable, each element
23e2d4eb-8907-5be6-8fe8-943e14e2e74e | note | – – – – – – – – – – – – – – – – –
62923a3e-809d-51a5-a854-a24fd95bc2ae | note | CATEGORY: IP
dbffe1df-7998-5493-abf5-88963a7f6f9b | note | – – – – – – – – – – – – – – – – –
68d281aa-1766-5001-95f0-ef0dccc71294 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
8cba79cd-9494-5a03-b0aa-d7c6a9056173 | note | – – – – – – – – – – – – – – – – –
a191609d-7c5d-5001-a8cd-833a7fe5212e | note | VERIFYING DOCUMENTS: This ITP
ef0dcd2d-42b0-51c7-add5-68e3297794de | date | Date Completed:
| checkpoint | 6.4 Surface Inspection - Cracks
7af2a1ca-edd0-50cf-b4d0-25c8ff806458 | note | REFERENCE: 610.24
9b3f5b88-4753-5f79-9700-e49ae864145e | note | – – – – – – – – – – – – – – – – –
c99fc664-62a4-5d9b-9116-330a97d0bcf3 | note | ACCEPTANCE CRITERIA:
6a6ff5d0-170c-50b8-9d54-5a2d03e0a974 | note | • No cracks greater than 0.2mm (exposure classification B1)
5703a680-b7b7-5fa2-a7ad-83bfec04df25 | note | • If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
8c2403e8-3cff-5c64-8fbe-dd2c49ff0719 | note | – – – – – – – – – – – – – – – – –
242108b2-3c07-5e1d-b91b-145a49991c1d | note | METHOD: Visual, Measure
f231c696-b940-5eef-b0ed-9226e721a9c4 | note | – – – – – – – – – – – – – – – – –
212e4dc5-2b8c-5fce-b09d-5403e6af8bc3 | note | FREQUENCY: Each element
a6fd48ff-a784-5310-a993-8093acb9be37 | note | – – – – – – – – – – – – – – – – –
1ede8642-d976-5d3b-9a79-a1f7deb4509e | note | CATEGORY: IP
40e98d04-108b-587e-8e89-c78ef6a20996 | note | – – – – – – – – – – – – – – – – –
6199c9a6-99c7-5b81-91bb-e1e178264d13 | note | RESPONSIBILITY: SE/PE/SPE
31046137-8038-5021-871c-ea8440770daf | note | – – – – – – – – – – – – – – – – –
fcd1312c-1e35-5c03-9ca1-c0a91bf83d2b | note | VERIFYING DOCUMENTS: This ITP
a72b1611-5160-59af-8458-4ddac403bb37 | date | Date Completed:
| checkpoint | 6.5 Surface Inspection - Surface Finish
e6a402fc-ab6f-5891-952c-78f328e663a9 | note | REFERENCE:
db75d93b-ad09-533c-9665-f9e760e87861 | note | IFC Drawings
4377cc09-261c-5c84-80dd-fee1f5990e41 | note | 610.31 (a) - (n)
afe5f5c2-78c6-5862-bac2-de7d772e749f | note | 610.32
c79b192d-c67b-5142-97a7-84325db9f2f4 | note | – – – – – – – – – – – – – – – – –
792b2c99-730d-5d18-92ea-82f92262ba6a | note | ACCEPTANCE CRITERIA:
a05a05db-7317-5b5e-bcbd-a592788c4f77 | note | • Comply with the IFC drawings and specifications.
8e247ef4-6538-5909-90f6-55ea757698ac | note | • Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
9a2e1b5a-73c1-53c6-9333-84ec9706743b | note | – – – – – – – – – – – – – – – – –
16f057fd-985e-50c2-bf77-fa428d67a481 | note | METHOD: Visual
ec8aed63-ccf6-5415-b58e-82cba0e9f64c | note | – – – – – – – – – – – – – – – – –
ffb3dc50-b88f-5e12-804a-66f32eb94dc4 | note | FREQUENCY: Each element
4047f76f-4ac7-5a73-ae20-fd2f1c01a675 | note | – – – – – – – – – – – – – – – – –
720330b4-4cf8-528b-985c-ffddd05226d6 | note | CATEGORY: IP
2e810ca5-a7f5-56a0-8d3c-cb47c8eaf465 | note | – – – – – – – – – – – – – – – – –
9a3bfce9-5712-5422-918b-b18c6daf927f | note | RESPONSIBILITY: SE/PE/SPE
f589ae8a-8777-5683-88b0-abf07bb9e88e | note | – – – – – – – – – – – – – – – – –
f9995a79-33f5-5bb1-a044-1d63c5a5a3a7 | note | VERIFYING DOCUMENTS: This ITP
09098749-cf7a-50f1-9863-cbefe3109834 | date | Date Completed:
| checkpoint | 6.6 Measurement of Concrete Cover
d90c9a97-a1bd-5ce1-b31b-953a7001895a | note | REFERENCE: 610.34
64fe079f-e963-5d7a-b44b-d0498e581f24 | note | – – – – – – – – – – – – – – – – –
64606b8f-7495-5cf8-97c2-7de09a704775 | note | ACCEPTANCE CRITERIA:
7e6951aa-1f62-5bad-8eee-4a60c50f0d87 | note | • Concrete covermeter check one 3m2 test area for every 25m2 exterior surface area.
e28594b2-7851-5708-b4fa-38d9bd14ec73 | note | • Minimum 10 no. measurements recorded in each area.
fcf90f7a-ba4a-56f9-bbd9-4d07153ce411 | note | • Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
3448decd-38cd-5ad8-bfa0-45de4a255012 | note | Attach: Covermeter Check Record
5d5c3fc0-5b42-5082-96f6-f4f999de3b93 | note | – – – – – – – – – – – – – – – – –
a516d570-bacf-5413-b069-9f0d5de52c2b | note | METHOD: Measure
9f2049a9-f1a9-5829-a66c-86645b7c600c | note | – – – – – – – – – – – – – – – – –
71e9cdab-06d4-5f44-a310-cd1900bd8591 | note | FREQUENCY: Each element
1d61ac57-f022-5380-99c6-a78a8234609b | note | – – – – – – – – – – – – – – – – –
fd45f040-b717-5f67-ba9b-9f038eab4f65 | note | CATEGORY: IP
3872fd87-eabc-5576-9beb-999457bb5aa9 | note | – – – – – – – – – – – – – – – – –
57b3deb8-1b42-5a95-95cb-106a84561b39 | note | RESPONSIBILITY: SE/PE/SPE
e9823746-001d-5e03-9d90-c8def7f44923 | note | – – – – – – – – – – – – – – – – –
c0ff9809-8794-5707-b7d0-cf2b28c7c4a3 | note | VERIFYING DOCUMENTS: This ITP
0dc690be-cce7-5027-b417-c15f0c9084e0 | date | Date Completed:
| checkpoint | 6.7 Early Age Compressive Strength Results - Placement of Fill Against Concrete
0a7ac88a-2c2f-5d4d-8ec8-0ca532e87171 | note | REFERENCE:
3335375b-8e54-5988-9c08-3a691e7b4b18 | note | Early Loading and Trafficking of Decks and Approach Slab Procedure
639c0854-dbf8-5a19-8af3-cd39f3c8d236 | note | 610.35
52b0e50c-3a03-564a-9167-bb07c77e957c | note | – – – – – – – – – – – – – – – – –
f52006cd-023d-5ff9-b2ff-b0019240dda6 | note | ACCEPTANCE CRITERIA:
b4c24037-ba8d-5af5-a36b-e941fba59156 | note | • Fill is not placed against concrete within 14 days of pour.
50b467be-8bcf-56c3-b1a3-7d2fbd8e0dd7 | note | • Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
e2c2bcfc-f99d-5704-a04d-3f5f14c434a1 | note | Attach: Concrete Test Results or Maturity Test Results
6e17f5e7-5cf9-5063-bcf1-4f36d12d10ff | note | – – – – – – – – – – – – – – – – –
35a04116-43ad-567d-a674-989837a91c83 | note | METHOD: Document Review
9b3546cc-da67-5cdb-b386-224d4a5d9359 | note | – – – – – – – – – – – – – – – – –
b00b1924-dfde-5707-8dd8-bc25b83b9d2f | note | FREQUENCY: Where applicable, each substructure element
9b888b61-781c-5235-8b84-9651109270e2 | note | – – – – – – – – – – – – – – – – –
4ae874a2-27fa-5c4b-bfab-c438fa2e7eec | note | CATEGORY: SP
712bca8e-a87e-56ed-8ae1-03d19815d806 | note | – – – – – – – – – – – – – – – – –
f81ca7ae-e75c-5d54-a202-1b87b884c3df | note | RESPONSIBILITY: Foreman, SE/PE/SPE
82dc7313-25f6-52a4-9cb6-4feb84e9de1b | note | – – – – – – – – – – – – – – – – –
1f000f91-cea3-55c2-bd6f-d8d665f269cc | note | VERIFYING DOCUMENTS: This ITP
5cbf1990-a102-59ea-af70-b96de977f938 | date | Date Completed:
| checkpoint | 6.9 Compressive Strength Test Results
373b180e-c399-5edc-a8c4-abb3f61811e8 | note | REFERENCE:
9869a9ce-eda9-5827-94ce-e72550e4bb9d | note | IFC Drawings
098f940f-0afa-59b0-b7e4-9569e3647286 | note | Table 610.05.051
be55346d-e7e8-5c7a-bb27-e3c930897c38 | note | 610.16 (g)
6700f49c-7396-5368-a621-6bc904818859 | note | – – – – – – – – – – – – – – – – –
1d81514e-4e3c-5b93-aef0-0444d34b0df2 | note | ACCEPTANCE CRITERIA:
610b03b6-3b8e-5aaf-aa34-aabf2388e14d | note | • 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
73d90ec9-f250-5611-ae22-250045969eb4 | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
0ab90d7c-2bc2-53b6-ae5c-57930c936fa9 | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
017a3bc0-5288-5669-ae41-f9a378d966fa | note | Attach: Compressive Strength Test Results
4d04eae6-118e-5e2d-b558-707aeb9379f6 | note | – – – – – – – – – – – – – – – – –
865d27f3-fe01-599d-8851-7447ed2fe9f7 | note | METHOD: Document Review
38bb6a54-bb5a-5f92-ad1d-779b11c8957d | note | – – – – – – – – – – – – – – – – –
8e369124-91ed-5a4a-9172-d7e5890fcb6a | note | FREQUENCY: Each cylinder
47b44ee6-ae73-552b-a691-d17f16a85286 | note | – – – – – – – – – – – – – – – – –
a3b6b4cd-dbd5-5221-987e-cefb73adce2f | note | CATEGORY: IP
38ba2c6d-a04b-5903-bc77-6f7e3f124d85 | note | – – – – – – – – – – – – – – – – –
b65358ce-0191-5f0d-ab17-4df2762fe219 | note | RESPONSIBILITY: SE/PE/SPE
42a82826-d716-51f1-951e-3fa4285d904b | note | – – – – – – – – – – – – – – – – –
aa45e722-6947-5e10-bdf8-a4e3c83a5a0b | note | VERIFYING DOCUMENTS: This ITP
bf7d65f5-9dac-52c1-b569-4197022fc37b | date | Date Completed:
| checkpoint | 6.10 As-built Survey
d7e8ff7c-50e7-5cf4-ae8c-30caef91875c | note | REFERENCE:
1599c253-205e-5c2f-98d5-fcac9a04600b | note | IFC Drawings
44c95ad8-95a7-522a-9504-ba03ed72444c | note | 610.47
9137267f-b496-5b42-9148-6e6c469c8735 | note | Table 610.472
35b35e41-235a-543f-95d6-1e75a4cfb7eb | note | – – – – – – – – – – – – – – – – –
6bc27c65-15be-58e9-b0af-b00736193966 | note | ACCEPTANCE CRITERIA:
fa72a6d3-7dcd-55bf-9ae0-1b8a76165ed2 | note | • Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
a38585cc-2b53-5fd5-a638-412b8714c8ba | note | Attach: Survey As-builts / Survey Report
bc890b9a-90cf-5e9d-9a6e-3eeb6b47677a | note | – – – – – – – – – – – – – – – – –
f0cc7762-626d-587c-972f-f96193708d07 | note | METHOD: Document Review
7b877311-d6e9-59db-bf02-525d6cec871f | note | – – – – – – – – – – – – – – – – –
85180d42-702d-55d9-ba6f-4060d963d8da | note | FREQUENCY: Each element
0ba069b7-8b18-5188-8fd7-f9968134d756 | note | – – – – – – – – – – – – – – – – –
47fbf245-1794-5764-b06f-e5dcd8e0adc7 | note | CATEGORY: IP
eada6bb0-f5f2-5cb9-a55f-de282b6da14e | note | – – – – – – – – – – – – – – – – –
e9d5238b-a695-5ca5-b526-ca5684857dce | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
278d7b5a-4688-5104-b20b-5ae2b62c4090 | note | – – – – – – – – – – – – – – – – –
3297b5b4-0e03-5b00-907b-f9e2a70304a0 | note | VERIFYING DOCUMENTS: This ITP
1a8d7f9b-471a-5a79-8a93-3f6d995ff20a | date | Date Completed:
| checkpoint | 6.11 Non-conformance Report (NCR) Closure
4bacd47b-0e8e-56d2-8534-1c2ceb44f669 | note | REFERENCE: MRPA Quality Management Plan
1fc5516a-4c6c-5c6d-907f-23ae916f36f3 | note | – – – – – – – – – – – – – – – – –
471483f7-2a71-5d17-92db-d2206b000461 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
1ab24e33-7231-5ea5-9b88-36e2a2bd063e | note | – – – – – – – – – – – – – – – – –
0df896f4-206e-5f2b-a5b4-a66006a2a6cf | note | METHOD: Document Review
84b6316c-70ab-5af6-89f1-a11ecb983387 | note | – – – – – – – – – – – – – – – – –
fa93e875-9310-5968-a442-9757c30613ba | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
e2692000-6e84-591a-a47f-d6ff9ba05d8b | note | – – – – – – – – – – – – – – – – –
ea7b90fc-8edf-55f0-a10a-d0e631908d4f | note | CATEGORY: HP*
c721f139-be9f-5d60-afa5-4d53a5fea655 | note | – – – – – – – – – – – – – – – – –
048f8b1c-d034-561d-b120-66e8ad92953f | note | RESPONSIBILITY: SE/PE/SPE
15392e12-8f34-5a83-8e86-77841115efef | note | – – – – – – – – – – – – – – – – –
a1505510-008d-5ced-9058-6eb9022f5619 | note | VERIFYING DOCUMENTS: This ITP
41696981-4ed7-5a00-a6a1-217fc4d05550 | date | Date Completed:
| checkpoint | Final Inspection
223c6d4a-d884-5c06-a58e-f662e2e97602 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
fb790ecb-babd-5b44-8ade-9caead5801ec | textbox | Name:
4ea57428-8664-5b98-bc5e-0ee1638c1fc4 | textbox | Position:
98e44f9c-2d50-5830-8b8a-9bdfb0330e1a | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-014-CIV-CAMMS-Footpaths & Shared User Paths Rev 0 | itp | ITP-014-CIV-CAMMS-Footpaths & Shared User Paths |  | 1c60bfb1-c3f7-4777-be91-a1f4d1093838
| section | Referenced Documentation
| checkpoint | Referenced Documentation
fc64aecb-8ca8-5aab-a86c-0bcf339cac52 | note | Document Title: ITP-014-CIV-CAMMS-Footpaths & Shared User Paths
2f108b87-5f93-534b-9c9f-cf7319931abe | note | ITP Description: CAMMS-Footpaths & Shared User Paths Scale C- 1 (Set-out & Bedding)
e25af5ad-7cf9-5d1b-97da-e20ee9463669 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
2cdf6b43-9bfc-5af2-b19d-a7fd09f982f9 | note | Discipline (e.g. CIV/STR/RAIL): CIV
924e088d-1fee-5dbe-b5fe-a42ff9b53af9 | note | Revision Number: 0
1638855d-f9e7-50c4-857b-e143ef552111 | note | Revision Date:
b89d024e-7ab5-5a38-9ae8-1fd27002a672 | note | ITP created by: Victor Mira
ac6c96bc-7dff-5f22-827f-34a7e5332d1a | note | ITP approved for use by: Victor Mira
2cf64137-1eee-51a4-bc41-88d45ce79308 | note | 1.1 Non Dependent
8032ab5b-1907-5f89-a73c-0e2e0d37f108 | note | Reference: VicRoads Section 304 August 2013
8b41f279-4a2d-5f90-869b-aca9513c68e5 | note | 1.2 Non Dependent
323fc24c-aa3f-5062-91ca-a10e50674e80 | note | Reference: VicRoads Section 703 April 2019
4e5f658e-010a-5521-a3d5-66e0cedd0b35 | note | 1.3 Non Dependent
9d447e82-9f7a-54c5-8e5a-d398f9437e7e | note | Reference: Council EDCM 401
e1c12051-86be-5c9a-a3e7-7b50ac01cd14 | note | 1.4 Non Dependent
7776f39b-37ab-5ad9-b8ee-ac53d1b0b8ba | note | Reference: Council EDCM 501
f6c7412d-07d5-5454-9456-b01a0237a513 | note | 1.5 Non Dependent
cb2dad1f-d6bb-556e-b9b5-5821014183f0 | note | Reference: Council EDCM 502
d09b53ed-dfe0-50c2-a6b3-71fd028d10b5 | note | 1.6 Non Dependent
5981a5fc-fb1f-56af-9084-6797a86b5042 | note | Reference: Council EDCM 503
f53ea9e0-ffd6-5962-8ba2-a27b026777bc | note | 1.7 Non Dependent
f726b3c8-e5d0-51de-9c35-7de645e9fb42 | note | Reference: AS 1379-2007
bfe9837b-08f2-5d4f-804e-86308772b95c | note | 1.8 Non Dependent
9b088160-60d9-5331-97f7-703458a58170 | note | Reference: VicRoads Section 812 July 2016
| section | Preliminaries - Materials
| checkpoint | 2.1 Bedding Material Placement & Compaction
6cf8d671-6ddd-5bce-b60b-f09f7076dfec | note | REFERENCE: IFC Drawings:
a8b59300-f6a4-52f8-beba-dbc00c90f7b4 | note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
2a32b19b-7aad-501b-9250-f92ee8ae0496 | note | • 812.04, 703.21
e2f59b3f-bb9c-5cd0-ae82-34c8724a5e46 | note | – – – – – – – – – – – – – – – – –
cf5d6f2e-b5a1-52cb-bc97-7bab6bbe7abc | note | ACCEPTANCE CRITERIA: Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
393da40f-56c4-54bf-bf90-9486498bdc6f | note | • SUP: SIZE 40mm CLASS 3 CRUSHED ROCK
a5d1becf-25ab-501c-be61-4f74627dc1d1 | note | • Material is registered with VicRoads in accordance with Code of Practice RC500.02.
dbf8a31b-6095-5666-b183-be3865024f62 | textbox | • Enter: Teambinder Material Approval number
fefa6539-9f89-5b4d-a8dc-0df05f115982 | note | – – – – – – – – – – – – – – – – –
818891b5-3c35-56dc-afa6-a8c13f520af4 | note | METHOD: Document Review
f967724c-47bd-53a1-a795-deb18644b185 | note | – – – – – – – – – – – – – – – – –
6df591d4-3915-5799-a8bf-f60a9f2f85a3 | note | FREQUENCY: Each Lot
d0f19106-ce40-5274-9d12-b5b242ebc1f4 | note | – – – – – – – – – – – – – – – – –
a1742d23-e519-524b-82b7-1152a6556947 | note | CATEGORY: HP
69d9da30-205c-5159-aad3-7979fbf3d027 | note | – – – – – – – – – – – – – – – – –
b2db3095-9308-5f9d-8cc1-bd59b87ebc94 | note | RESPONSIBILITY: Nominated Authority
aa7d586f-08bb-5287-aa99-c1c09c01471a | note | – – – – – – – – – – – – – – – – –
6cd0fb2a-ed0f-5ccf-8455-e8743f6eb0ac | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
384a9d06-810f-5757-8470-6f8a3584a4a8 | date | Date Completed:
| signoff | NOMINATED HOLDPOINT AUTHORITY
| checkpoint | 2.2 Concrete Mix
587e2ff5-3377-5c6a-9737-4662297424d0 | note | REFERENCE: IFC Drawings:
54bf0276-8bde-596f-aafc-1ec40c7aae86 | note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
d5fcfdd2-85d4-5191-ab69-86de8db6352a | note | • 703.05 (a), 703.07
616ab5e2-336d-5d0b-ad9f-543d68ab435c | note | – – – – – – – – – – – – – – – – –
af8047e4-6c5d-5dd6-8d6e-d79ede21ccf6 | note | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
e8400f84-b5d2-5e60-9cac-44e3b22add24 | note | — Footpaths, Residential driveways and Median islands infills: 25Mpa
f29e11f9-5561-5033-a571-5c8f907d7d24 | note | — Industrial Crossovers: VR330/32 to be registered by Vicroads
b6835f34-a063-5fd0-ae49-fd07d2f7c65b | note | — Traffic Islands: 32 Mpa
2d137bee-d452-526d-8d5e-58d61bd69bf0 | note | — SUP: VR330/32
bb853c93-83a4-5c92-a9e3-6850b99a782c | note | • No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
d61b1f52-8ca1-5188-8b5c-0fb2632ae7b5 | textbox | • Enter: Teambinder Material Approval number
4e27f9c2-e402-5dce-b678-e1874439392c | note | – – – – – – – – – – – – – – – – –
3bfcad8f-fb00-5f83-a945-6c172e4c82cb | note | METHOD: Document Review
dc1fe9ed-9993-5f6a-ad71-04c7ab615499 | note | – – – – – – – – – – – – – – – – –
877e5c40-37f3-5a4f-8280-92d362453608 | note | FREQUENCY: Each Lot
38a5c72e-c740-514e-8392-f3fb5e4d7964 | note | – – – – – – – – – – – – – – – – –
ffe9236b-204e-5616-a520-81e6378005f3 | note | CATEGORY: HP
7fd05cbe-28b5-5f78-834e-5608846c7585 | note | – – – – – – – – – – – – – – – – –
526fd435-6585-5b79-a2e4-ec1fd714a64b | note | RESPONSIBILITY: Nominated Authority
793465d6-aa44-55fa-b046-652549626e49 | note | – – – – – – – – – – – – – – – – –
80cf2e8e-4081-5caa-9563-0579fa646202 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
ec114962-159a-5efa-84d8-cd5135115557 | date | Date Completed:
| signoff | NOMINATED HOLDPOINT AUTHORITY
| checkpoint | 2.3 Reinforcement
58016811-3a75-5396-be51-73931674fd14 | note | REFERENCE: IFC Drawings:
28907ad9-ab70-577c-bb73-c7c959718427 | note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
c4b981cb-e2e0-5d1f-8f61-728aeeb29c37 | note | • 703.16
a493c16b-6c95-526b-8842-959191ef116d | note | – – – – – – – – – – – – – – – – –
e371dd15-ee30-527c-a68c-bb8fd40b5a26 | note | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
01601efe-52fd-5c63-b8c9-235c68bbad09 | note | • Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
eb6919a1-269d-521a-b1f7-08341dce94fe | note | • Following steel mesh requirements shall apply as per IFC Drawings:
2f9cb185-9017-5b6d-8752-b562bacc9683 | note | — Footpaths, Residential driveways and Median islands infills: SL72
2e33393c-5671-59f7-b034-d87a7f737c52 | note | — Industrial Crossovers: SL82
01b616dc-9be4-5e7b-aa56-ec8649077a25 | note | — Traffic Islands: SL72
bec4b9b9-353d-5a23-8c15-95d037ce9f0b | note | — SUP: SL82
929ddc98-2c7d-5487-9fe1-a7599db645c9 | textbox | • Enter: Teambinder Material Approval number
2b1da527-f5a8-516c-b41e-c1bb1e0792c9 | note | – – – – – – – – – – – – – – – – –
8a1d722a-1809-509b-9050-5daf6acc6099 | note | METHOD: Document Review
d0a53be3-365c-57a3-a827-3372719be2a9 | note | – – – – – – – – – – – – – – – – –
f093e72d-922d-56df-a060-ddf83d74ee8d | note | FREQUENCY: Each Lot
17292696-9d23-579a-8beb-1e31eefe5f8f | note | – – – – – – – – – – – – – – – – –
3a885809-8d07-5e0f-b665-7a31f3000068 | note | CATEGORY: HP
4f5be39a-1f7d-5312-a339-15c9ab87cdda | note | – – – – – – – – – – – – – – – – –
4366c40c-eb38-5645-bec9-0d804921f217 | note | RESPONSIBILITY: Nominated Authority
b029ecc8-4e93-51c9-809b-c72892d51a5a | note | – – – – – – – – – – – – – – – – –
bf0d9fa3-4114-5169-a144-ad88827d18fd | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
486a3b30-f057-57a5-ad5f-38505467e521 | date | Date Completed:
| signoff | NOMINATED HOLDPOINT AUTHORITY
| checkpoint | 2.4 Evaporative Retardant
4269db9d-733d-555b-a67e-ad91612d6ef6 | note | REFERENCE: 703.09
0fb45cd7-f885-578c-b37f-fa9e3bab7969 | note | 610.17 (f)
58739c78-a1f0-576f-ac11-50fd592c6434 | note | – – – – – – – – – – – – – – – – –
35068d34-51d6-5753-832a-b62f558d2f30 | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
0bee3d49-44e5-5d30-8e6b-b8539c0ed88a | textbox | • Enter: Teambinder Material Approval number
d7b37cf8-5428-5532-b0db-b075abf4c0d8 | note | – – – – – – – – – – – – – – – – –
a614a7cb-5e5b-5c05-94d1-3e04ee7b1b66 | note | METHOD: Document Review
479eba6d-fc0d-5fb0-98df-1d3172f62f08 | note | – – – – – – – – – – – – – – – – –
a95cd09d-c87f-5918-9a6b-d5be65639d5f | note | FREQUENCY: Once, for each product, prior to placement of concrete
33587df1-4faa-5f3d-9ccb-7fa75c56cb08 | note | – – – – – – – – – – – – – – – – –
190380f8-7e93-5e80-bc65-3d582e2d9634 | note | CATEGORY: HP
71e339ce-3f02-5a61-a0a4-e3b60a34402e | note | – – – – – – – – – – – – – – – – –
24939bdd-7a7f-53c1-85e5-b5cdf9ab4883 | note | RESPONSIBILITY: Nominated Authority
d6b91cfe-28a1-5a23-b0ee-b10469d27317 | note | – – – – – – – – – – – – – – – – –
5deee1ac-d733-5a87-99a9-7a7a4e85461c | note | VERIFYING DOCUMENTS: This ITP
164a9300-3aa8-505b-8abc-8bc3be714a06 | date | Date Completed:
| signoff | NOMINATED HOLDPOINT AUTHORITY
| checkpoint | 2.5 Curing Compound
0220c777-3102-5b5f-844d-d8033d201edc | note | REFERENCE: 703.10 (a)
161dc935-85b3-57d4-9d8c-4ef604edef43 | note | 610.23 (d)
aaeefc51-d650-5e2d-8c79-eb1fb666f5dd | note | – – – – – – – – – – – – – – – – –
2e4289d6-4992-5cde-9ca3-222a479fd965 | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
5fd56e48-ed02-5830-b2cd-78401458c285 | note | • Enter: Teambinder Material Approval number
fc00595b-33d3-5c08-820a-284e9b47faf0 | note | – – – – – – – – – – – – – – – – –
79727f00-b6d9-5573-8006-f013ae3e0992 | note | METHOD: Document Review
c75b9a19-ddd7-515f-b697-b9d4a8171ac8 | note | – – – – – – – – – – – – – – – – –
09dd4130-df4e-5546-8971-fd956d4755d6 | note | FREQUENCY: Once, for each product, prior to placement of concrete
3344a181-9168-5215-b4bf-39585e28b58e | note | – – – – – – – – – – – – – – – – –
c0a43d9e-6f4c-501f-8fe2-9c6b18fa19af | note | CATEGORY: HP
939d6627-5960-5e9b-a72f-8b8da1082031 | note | – – – – – – – – – – – – – – – – –
293663ea-782a-5a3b-b5b3-6592b0498ef4 | note | RESPONSIBILITY: Nominated Authority
0b0ef9ac-0fe3-54f4-9956-4b127650cac8 | note | – – – – – – – – – – – – – – – – –
a0fef5ca-81b6-5182-ae84-c75159d2f570 | note | VERIFYING DOCUMENTS: This ITP
bcdb33cf-4204-5d39-a4c2-6506e0de92a5 | date | Date Completed:
| signoff | NOMINATED HOLDPOINT AUTHORITY
| section | Preliminaries - Documents
| checkpoint | 3.1 Survey Set-out
9d10619c-bfbf-5e79-ac43-05fe6457591d | note | REFERENCE: IFC Drawings
8fdb9dc2-0788-53fb-888c-df916fd7d54f | note | 703.17
d1e1efc6-2cf0-58a5-8612-0019fe71d8ac | note | – – – – – – – – – – – – – – – – –
2e50890d-6661-568a-af96-6fb6c6892468 | note | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
72e27fed-7f33-5565-b571-ca4e653efcfd | note | • The Nominated Authority will review and confirm the set out.
a3618167-790a-525b-befd-2b57748c2c33 | note | Attach: Survey Report
10d33d3b-410c-5c4f-b226-c702ebef23be | note | – – – – – – – – – – – – – – – – –
40a07f72-38c7-565b-9431-261b310a95d8 | note | METHOD: Document Review, Measure, Visual
da6443c3-60c3-501c-8c81-4681760fbe75 | note | – – – – – – – – – – – – – – – – –
601f1a56-7564-5bdc-84f0-362ef92923b0 | note | FREQUENCY: Each lot
572fac93-01c2-5a55-8d16-fc1f50fed54f | note | – – – – – – – – – – – – – – – – –
b2145ba2-74b2-5c10-9176-6ed4097edb84 | note | CATEGORY: HP
afabbe7f-7619-5b7b-a6d4-f1fa3e661805 | note | – – – – – – – – – – – – – – – – –
3ef1a0a3-83b2-5e4b-a972-f0830164bbf0 | note | RESPONSIBILITY: Nominated Authority
dabf51d8-a119-5599-b2b9-59bb919e7712 | note | – – – – – – – – – – – – – – – – –
1b57014e-42ac-562f-b038-766ad0a4e0e7 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
933863a6-e1a9-57d3-880a-3a71510e2b63 | date | Date Completed:
| signoff | NOMINATED HOLDPOINT AUTHORITY
| checkpoint | 3.2 Lot Map
dffd64ad-5df5-520c-bf8d-369836e87256 | note | REFERENCE: MRPA Lot Management Plan
6958710a-48b0-5e85-8b30-f4ea6745366a | note | – – – – – – – – – – – – – – – – –
38156042-48fb-516a-9654-9480f42f93b3 | note | ACCEPTANCE CRITERIA: Attach Marked drawing indicating the location of this Lot
f6950ec2-6676-54da-ab65-4ccf9fe7463d | note | Attach: Lot Map
9232d1c8-0608-5613-9a64-b287e742c2f4 | note | – – – – – – – – – – – – – – – – –
061c9dcd-f887-55fc-a307-cad4e52820bc | note | METHOD: Document
f94b2ae7-de4f-50c1-9cf8-834a5c19e8a5 | note | – – – – – – – – – – – – – – – – –
4b03d937-79ee-5ab3-a3c5-e0142f595345 | note | FREQUENCY: Each Lot
161feabf-050a-5a62-a3bd-dec18600246d | note | – – – – – – – – – – – – – – – – –
d9d3a16f-5b2b-5808-b8d1-5078a4d7aded | note | CATEGORY: HP*
c54e9f94-3b4c-520e-bc8a-f512cd474425 | note | – – – – – – – – – – – – – – – – –
a84586a9-75ca-5c02-9e0a-e9edf28d0472 | note | RESPONSIBILITY: SE/PE
e55e9821-10f2-5396-a934-7783b839a833 | note | – – – – – – – – – – – – – – – – –
aa0d9e8f-c45b-5bfb-ba33-c100fc92fa5e | note | VERIFYING DOCUMENTS: Attached Lot Map
9a3b2bb2-b018-5fce-bf4c-45a2c30f013b | date | Date Completed:
| section | Pre-Construction Activities
| checkpoint | 4.1 Site Clearing & Grubbing
824f16b7-5504-5520-89af-63539b4131a5 | note | REFERENCE: IFC Drawings
63cff46f-6793-52d5-b712-48ee2b886e81 | note | – – – – – – – – – – – – – – – – –
1a01a863-4283-5b9e-950d-dc7c7e0f2e9f | note | ACCEPTANCE CRITERIA: If not completed during the site establishment, the work area needs to be cleared and grubbed.
bcb002ed-c54a-5c84-ba1c-ae74f287f356 | note | • Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.2
d2cbf0de-8864-5800-8cfa-d0da2605145f | note | – – – – – – – – – – – – – – – – –
325530fb-4c85-5b6e-91dd-bac4b82ef227 | note | METHOD: Visual
7002e901-a768-54e9-9c1a-bb3f62283e06 | note | – – – – – – – – – – – – – – – – –
7d6439a6-0f5d-5fc3-a506-9e57b63b5fc7 | note | FREQUENCY: Where applicable
5c66bde4-7c46-59ac-994f-f2b2b63bffa8 | note | – – – – – – – – – – – – – – – – –
28960d9a-a260-549e-9ebb-d595488aba07 | note | CATEGORY: IP
e3c7a306-b7ab-5549-bbf1-a80cd1d7437a | note | – – – – – – – – – – – – – – – – –
02d8697d-cacb-5548-b81d-2777002d7adb | note | RESPONSIBILITY: SE/PE/SPE
e17cdc57-5b41-5b00-a925-96891b510103 | note | – – – – – – – – – – – – – – – – –
2689933c-9bfb-5199-b9c2-12f97092ec55 | note | VERIFYING DOCUMENTS: This ITP
826ffebb-c0fd-5db7-a0e3-8725b1187b50 | date | Date Completed:
| checkpoint | 4.2 IFC Drawings
d2040f26-1129-585d-a04e-9e4dd0594ab8 | note | REFERENCE: MRPA Quality Management Plan
4cbad991-90c9-5787-ab7c-75c19e01a2cf | note | – – – – – – – – – – – – – – – – –
0a3ab6ec-b0f9-56de-a23d-619705a56626 | note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
c4a77406-3caf-5ed8-b646-cee3b83bdb22 | note | — Using the correct and complete set of drawings
f70b89ea-ccfa-5440-a222-c9984d0796d8 | note | – – – – – – – – – – – – – – – – –
bc6149ad-289a-5733-8710-1aa6faaf94fc | note | METHOD: Document Review
ccfec7d7-5cc3-5f1b-ba23-2f0ddb86dc42 | note | – – – – – – – – – – – – – – – – –
06955dc2-3976-53ea-b905-a67fa5ffe86f | note | FREQUENCY: Prior to starting Works and at regular intervals
35a316b2-84d9-5bfd-a0f2-35bf0b5e74bb | note | – – – – – – – – – – – – – – – – –
67dd9aa3-3220-5c84-bf2f-d6dc5b8d7f49 | note | CATEGORY: HP*
4997436b-32c9-50c6-b91d-8186a61d0be7 | note | – – – – – – – – – – – – – – – – –
261831e2-e762-5b8c-ae0d-81bb37a96507 | note | RESPONSIBILITY: SE/PE/SPE
538f1659-0dc1-517d-840c-4265d827e3a4 | note | – – – – – – – – – – – – – – – – –
03c82516-a256-55bb-ba2a-98ecac5d95ee | note | VERIFYING DOCUMENTS: This ITP
3f46b628-6fdd-53b2-8f15-ca12b72bfa76 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Excavation
2edd880e-25ca-5df8-8906-725de4e202d6 | note | REFERENCE: 703.20
ef11e3cc-53ab-5b4c-84f5-ca004fe87580 | note | IFC Drawings
de34e989-22f1-57b1-8409-bda932089800 | note | – – – – – – – – – – – – – – – – –
1d68071d-3414-598f-906b-930f7ab82ab1 | note | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
761171c7-1d45-56ed-9071-3f79e15be6e9 | note | • Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
7f7101e3-7a79-580e-9aad-884f457a3134 | note | • Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
d6a070d6-b3f8-591d-89b6-dd126c4206d1 | note | – – – – – – – – – – – – – – – – –
e71dbdd9-2ed0-5221-99d3-2755ba7dec77 | note | METHOD: Visual, Measure
c2171d5e-0bb8-527c-8efa-fe2d0e7b32f3 | note | – – – – – – – – – – – – – – – – –
386d59cc-3935-569d-b4e1-2798cc0d7b5d | note | FREQUENCY: Each lot
9fb51219-7d7f-5498-a508-b7e5faafe97b | note | – – – – – – – – – – – – – – – – –
1db71cdc-7d19-553a-92b5-47448b584e77 | note | CATEGORY: IP
41b1ebda-2f2b-5a07-ac5d-715a749d1496 | note | – – – – – – – – – – – – – – – – –
283a0864-daeb-5716-939d-a1344e5c3e65 | note | RESPONSIBILITY: SE/PE/SPE
e4ec1cb6-47e0-5675-9873-b9bb345accec | note | – – – – – – – – – – – – – – – – –
e7bb1a59-94a6-5690-ac04-feec752df8ad | note | VERIFYING DOCUMENTS: This ITP
ad0f3720-ca06-5243-827f-5f736248e98c | date | Date Completed:
| checkpoint | 5.2 Excavation-Pavement Thickness Increases for Crossings
91b7ce80-fdca-5f48-a518-516c8215b2d9 | note | REFERENCE: IFC Drawings:
f4606c2e-2225-5251-8d36-453041801df1 | note | MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
1f5a4bd2-383e-5cba-992a-c8788ac64964 | note | Relevant Council drawings:
4fed62d2-4a73-52a9-b5f9-10349528996b | note | • EDCM 501
feffdea7-0b1b-56f7-bd06-a4cb8cd683bd | note | • EDCM 502
42146818-3f06-5882-9145-39fbf9bda4a4 | note | • EDCM 503
e9aa9d49-09d3-5a53-a516-5154db08a05e | note | – – – – – – – – – – – – – – – – –
b0ecc7d8-25a1-5430-bb43-9bc6403af567 | note | ACCEPTANCE CRITERIA: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
3752e101-f1a7-5be3-b163-7d15d5e0ce95 | note | • Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
a99040e7-9699-52f1-b33c-5ec216697087 | note | – – – – – – – – – – – – – – – – –
d4d308d7-2001-5df6-ae5c-1aa908b710dd | note | METHOD: Visual, Measure
a91f635e-07e6-57c4-9b7a-58399b857594 | note | – – – – – – – – – – – – – – – – –
c88c405f-7ee1-58cd-b55e-3536ff7d7f22 | note | FREQUENCY: Where applicable, each lot
139cdefe-7068-5093-b7c3-b9b0cd76b890 | note | – – – – – – – – – – – – – – – – –
448bb1da-2769-5074-be70-06b4995343e5 | note | CATEGORY: IP
b7d27708-9ee7-5edb-84c0-8683c5e88f4b | note | – – – – – – – – – – – – – – – – –
10f7aedf-5638-5131-9d94-3912623aa1d2 | note | RESPONSIBILITY: SE/PE/SPE
9ad9e947-e11e-5353-8d50-b67c84f51cd0 | note | – – – – – – – – – – – – – – – – –
d1e724cf-258d-5383-8b82-4324d3983d07 | note | VERIFYING DOCUMENTS: This ITP
ab0bed56-a63f-53e0-85d9-3c3768853af1 | date | Date Completed:
| checkpoint | 5.3 Bedding Material Placement & Compaction
a62ad7f9-4418-5ca1-928f-c49c2d027057 | note | REFERENCE: 703.21 IFC Drawings
c3ce64b6-83a1-50c2-be61-8a81eb8c9f1d | note | IFC Drawings:
d8b5e32f-7954-53db-a0fc-0111652fa431 | note | MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
8044e6f6-006c-588b-9ed5-fc2371e95a55 | note | Relevant Council drawings:
51233942-2fcd-5e19-b11a-d7587c69d5dd | note | • EDCM 501
3b8c50c7-dffe-516e-8e4f-a01a931f8610 | note | • EDCM 502
c4f3086d-2b93-5627-9ee4-37ca76b0d740 | note | • EDCM 503
0b6eb486-2761-52c8-abe2-33fdf99a07b2 | note | – – – – – – – – – – – – – – – – –
9331c19a-ffa3-5aca-9edf-2d6a5857675e | note | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings:
fc507a4b-5a4a-536f-896c-1311fca9232c | note | • Footpath: Bedding shall 100 mm compacted thickness
2597f2c8-1a7c-55a9-8b5b-a7c03c86cada | note | • SUP: Bedding shall be 150 mm compacted thickness
81060463-04f4-53e8-9507-3e2d267ef39e | note | • Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
5bb277d5-6e48-5913-b873-3adfe7cd528c | note | • The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
f0ce2970-0397-5155-b208-b8cf476225ac | note | • All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
d24c54bf-92ec-54c7-84bf-f9ba8f875019 | note | Attach: Bedding Material Delivery Dockets
ef5f332c-6d2d-5256-b629-050829a7fa98 | note | – – – – – – – – – – – – – – – – –
056d5136-8b52-508c-a956-08dc29cdb080 | note | METHOD: Visual, Measure
1986796f-5434-5afe-9f19-cf7ab9afbc46 | note | – – – – – – – – – – – – – – – – –
db77ab9a-f487-5703-aefa-2ba189dc8e55 | note | FREQUENCY: Each lot
e34b33c7-6cdc-5080-a18a-d1aa3c7e4c67 | note | – – – – – – – – – – – – – – – – –
96d63fab-922d-5a1a-a212-3029f6484d53 | note | CATEGORY: IP
24451a31-0f6e-5db8-b3fb-ca2af48243da | note | – – – – – – – – – – – – – – – – –
5b2d9421-39ec-5824-afb4-2081fb005df9 | note | RESPONSIBILITY: SE/PE/SPE
307a4c9e-4a7e-566f-a689-ce8232778445 | note | – – – – – – – – – – – – – – – – –
70781a26-aee0-5b2d-9d75-644c0c15ad45 | note | VERIFYING DOCUMENTS: This ITP
307c4ad5-0114-5da5-968f-2d4cbba7549f | date | Date Completed:
| checkpoint | 5.4 Shared User Path - Compaction Testing
f7055046-1704-54b5-892c-a9790d05e412 | note | REFERENCE: 703.21
96ff219a-a485-5220-8a92-23859ed2009c | note | 304.08 (a) & (b)
c276e749-4663-5803-804f-0a94cc0e7ba8 | note | 304.11 (a)
02036880-2462-5910-b34c-cd6ba4720664 | note | – – – – – – – – – – – – – – – – –
44906deb-d2c4-57c8-8deb-e0fc1e814f35 | note | ACCEPTANCE CRITERIA: Compaction shall meet the following requirements:
770e0c5d-745f-5624-81f1-3442f2f170c3 | note | • Scale of Surface Level Measurement = Scale C
54baf202-4778-50d9-b87b-a0d7c3f2e867 | note | • Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
faf5aed2-cd01-5c3c-a671-fcaed180ee50 | note | • Mean Value of Density Ratio % (3 tests) not less than 100%
7c93a7d5-1084-57ca-8617-236331b593f4 | note | Attach: Moisture Content Test Results
4ac60631-d0f6-59c9-ad38-372fec2c0910 | note | Attach: Mean Value of Density Ratio
29c08839-6bcf-58c0-89bc-dd6e0e7d3fb6 | note | – – – – – – – – – – – – – – – – –
d7be9aca-0344-5215-9fa5-7d0d9283761a | note | METHOD: Document Review, Visual
f8145038-161c-5a4c-b352-5b95231d43a8 | note | – – – – – – – – – – – – – – – – –
a787436c-eebd-5b64-8478-bd927394682e | note | FREQUENCY: Where applicable, each lot
06fce67f-78d3-5d75-9e81-3975290504e2 | note | – – – – – – – – – – – – – – – – –
deef7d98-5542-562f-934c-a3ee2c166610 | note | CATEGORY: IP
86c6b7f3-19f7-5292-9280-638677a471a5 | note | – – – – – – – – – – – – – – – – –
1763033f-cf33-517a-81ea-c88315d7f593 | note | RESPONSIBILITY: SE/PE/SPE
ccb9236b-9562-56af-8265-51ab8af71073 | note | – – – – – – – – – – – – – – – – –
dcc98a4a-7d76-5b58-8efa-fdd69b6f75df | note | VERIFYING DOCUMENTS: This ITP
d3289d79-b4a5-5819-9eb6-258c58ca6b2f | date | Date Completed:
| checkpoint | 5.5 Shared User Path - Proof-rolling
edfb8fc4-2108-5a60-a01c-21c09d6104f6 | note | REFERENCE: 703.21
5f335392-563a-545a-8778-97331790766e | note | 304.08 (b)
eb13201b-147f-590f-9e17-4e79c1f33f98 | note | – – – – – – – – – – – – – – – – –
b28025f0-967f-5862-879b-dd2774a67dcd | note | ACCEPTANCE CRITERIA: Bedding material to be compacted and proof rolled before any construction.
9d3e24d4-1acd-550d-9ac0-b6ee857a1a73 | note | • Withstands Test rolling without visible deformation or springing.
54916573-a0bd-582f-bc5b-67d34080e7fc | note | – – – – – – – – – – – – – – – – –
b8dac25b-d8af-59b9-b7a1-07ad7300fc4f | note | METHOD: Visual
b5a190da-76a1-5235-b98d-53f5334de64d | note | – – – – – – – – – – – – – – – – –
433ddf4c-d15a-53c8-ba66-c8461794edd1 | note | FREQUENCY: Where applicable, each lot
e6b52f9f-f1a9-5b54-a588-70579cb482db | note | – – – – – – – – – – – – – – – – –
efc08a40-9130-56fe-a353-b68995f3b27e | note | CATEGORY: HP
e8cb9039-bfc2-5db4-b3f9-ae985db55988 | note | – – – – – – – – – – – – – – – – –
76a14fb2-a069-531a-a665-43fe2b564cb3 | note | RESPONSIBILITY: Nominated Authority
64f5b852-408c-5a4f-a488-3b2afc35e65c | note | – – – – – – – – – – – – – – – – –
877c355f-6981-5c62-b084-8ac07c6e820f | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
e3057b95-07bc-529e-9957-5c43f9c05d52 | date | Date Completed:
| signoff | NOMINATED HOLDPOINT AUTHORITY
| checkpoint | 5.6 Formwork Construction & Placement
26993c83-77fc-5452-8e1a-0fe1c08ed83a | note | REFERENCE: IFC Drawings
176c8234-27de-5842-9b43-29b711c3d8af | note | 703.12
a3cf90c9-2709-5c47-82bd-92973de9b538 | note | – – – – – – – – – – – – – – – – –
56e04314-8522-59cd-927b-a73f48d7f9a4 | note | ACCEPTANCE CRITERIA: Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
f7576f40-d753-5b74-9237-9680a8cea8f2 | note | • Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
5ecaa007-bce1-5504-8046-6185c3bb17c3 | note | • Joints in formwork shall be constructed such that loss of mortar is prevented.
bb8b3b60-d586-5a14-8d46-a7f4462b789a | note | • Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
a3ae53be-c8e2-5cea-993a-e9577be979dd | note | – – – – – – – – – – – – – – – – –
9057814d-e7c3-5cec-8464-3e7ba6035cdc | note | METHOD: Visual, Measure
ca6c84c9-6ac3-5462-96b4-df1a7112cc32 | note | – – – – – – – – – – – – – – – – –
17cd11c0-7da2-5968-a241-c0f7e86327ea | note | FREQUENCY: Each lot
23afed9a-5191-54b6-ba5f-5510d7732b8e | note | – – – – – – – – – – – – – – – – –
0fe5d45f-2f94-5a3d-bbf1-dea90642ced8 | note | CATEGORY: IP
9ea62e38-f7e2-51c8-9d16-1fe3cc3c9234 | note | – – – – – – – – – – – – – – – – –
25a0c60d-b1ef-5c94-8a59-79e073928626 | note | RESPONSIBILITY: SE/PE/SPE
d0f3fd76-b833-59b5-b5be-8c374d804bff | note | – – – – – – – – – – – – – – – – –
e21a9ccb-2647-50cf-9e2e-96cf4d0e2a60 | note | VERIFYING DOCUMENTS: This ITP
220abcae-6cd3-5548-9a28-9b5a6bb2c4d7 | date | Date Completed:
| checkpoint | 5.7 Construction Joints & Matching Existing Surfaces
8a8b09d1-8f99-5a05-8c18-ec315f846fea | note | REFERENCE: IFC Drawings 703.24
7bc5cf52-36a7-5147-9915-e99bccb1655e | note | Relevant Council Standard DrawingsRelevant Council drawings:
82e2f162-32f6-5c1f-a31e-ec8227919785 | note | • EDSM 401
6f380e73-1b6c-52a5-8626-f12122f896bf | note | • EDCM 501
83e2cab0-1f9e-5e3a-982b-04ff2763c3d5 | note | • EDCM 502
cf05ebfc-deae-546d-b4d6-6ce32c749274 | note | • EDCM 503
8ceaf1cc-cb2b-5339-87e4-3fe1f9af42b7 | note | – – – – – – – – – – – – – – – – –
49ca563f-72af-5937-9861-5bd3d540851a | note | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
22e95ed1-1dcd-58e9-b520-f6695f7e16bb | note | • Consult the relevant Council Standard drawings for the joint detail, these may require:
53202686-541b-5971-8d5b-fbc109adac5c | note | i. Concrete cutting of a shear-key
c046e412-fc46-5ef5-b891-71594fd70def | note | ii. Surface roughening
b7e24e42-85c7-54a3-bc1e-1b0c4378bc54 | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
b28ac9a4-c874-5c17-af71-1bc7c414ab3f | note | iv. Cutting a groove for sealant
7e98867c-fe98-5410-937f-c6bdbf8bd84a | note | • Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
1de8c9e7-8d37-51fe-82f8-c08e0983fde2 | note | • Transitions between different profiles shall be made in accordance with the drawings.
a09cefe6-aa97-5882-b0ab-07edaf7829ab | note | • Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
974eddfe-bd5c-519c-b238-3eb13a0df08d | note | – – – – – – – – – – – – – – – – –
934846c8-17fb-5a9f-902b-a7d0f1065e4c | note | METHOD: Visual, Measure
76e4d39a-eafd-5933-bcd5-e715c2716b39 | note | – – – – – – – – – – – – – – – – –
f0620072-cafd-5a1d-adb6-de05d497fc22 | note | FREQUENCY: Where applicable, each lot
05fd7679-1671-5d50-9d64-fec32a1f18d0 | note | – – – – – – – – – – – – – – – – –
3736cd6d-deda-57b1-84d4-1204146bbc34 | note | CATEGORY: IP
49edea88-bfdc-5bce-85de-ae2a58d1abbb | note | – – – – – – – – – – – – – – – – –
5814f3a5-c87e-52db-8fd4-f9ae51338a49 | note | RESPONSIBILITY: SE/PE/SPE
cb657ea5-7766-59ca-8a3f-b78283f9f4b7 | note | – – – – – – – – – – – – – – – – –
2deca750-4fcc-5eee-8732-55d48f5865a4 | note | VERIFYING DOCUMENTS: This ITP
8fd72735-aa04-5f2e-ab73-40223899798e | date | Date Completed:
| checkpoint | 5.8 Isolation Joints
ed4496cf-c91c-5951-b62c-9a41cd3a6ddc | note | REFERENCE: IFC Drawings 703.26 (c)
39db067e-43e5-5c21-87c6-ab703339097d | note | Relevant Council Standard Drawings
67a05e49-8378-5c62-ada5-98b4567e9938 | note | • EDSM 401
4ad4478b-5e22-565c-91a5-0784b162e000 | note | • EDCM 501
2a4eb86a-7a25-5d06-bde4-65d63509b4ef | note | • EDCM 502
c9e6b669-f2fe-5154-868e-72e558d1b2e6 | note | • EDCM 503
6d6bbb6e-e00c-5f78-89de-e3ee3c6d28ed | note | – – – – – – – – – – – – – – – – –
c1b0b43c-a59a-51cf-b1e8-ccb4f5ae7377 | note | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
c06e86d1-9774-5ed5-9a86-f67e131f4672 | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
8d8ea595-abf7-5898-87dc-9db659df9000 | note | ii. at any location marked on the drawings
76b68988-7455-5c86-bf1b-a0280ac3710a | note | • The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
4b9c7047-bd7e-5374-81e3-17076ca26e13 | note | – – – – – – – – – – – – – – – – –
5725d20f-eb56-5da3-89fd-b103f9b76d5a | note | METHOD: Visual, Measure
bc6ad154-0982-5f98-b925-ef473be442b0 | note | – – – – – – – – – – – – – – – – –
b0f0c8e4-7346-543c-8a17-88b31e565c78 | note | FREQUENCY: Where applicable, each lot
2c52a4d4-df1c-5910-8931-714633f28a70 | note | – – – – – – – – – – – – – – – – –
a37b60a8-181e-55b2-b63c-c7870c73c765 | note | CATEGORY: IP
a4da6d0f-bbfa-528b-b7f9-ee5180db5c46 | note | – – – – – – – – – – – – – – – – –
2d210148-6b06-5456-88c8-d072ae3c7cd1 | note | RESPONSIBILITY: SE/PE/SPE
efd0419a-3dbc-5aed-86d2-d81832aa773b | note | – – – – – – – – – – – – – – – – –
536a1900-70a2-5bb9-b492-7898a36303fb | note | VERIFYING DOCUMENTS: This ITP
869c6d21-7a72-5d3c-8f77-d3ca7e640ae0 | date | Date Completed:
| checkpoint | 5.9 Expansion Joints
ed79a288-24ac-5453-9387-19dc13db620e | note | REFERENCE: IFC Drawings 703.26 (a) (ii) & (b) (i)
9b72ee9a-8ece-5ca6-a335-8ab6251491e4 | note | Relevant Council Standard Drawings
27c17791-0b8c-5a3d-9c8b-1dc0f7a925f2 | note | • EDSM 401
af2bf872-7619-59f1-bb20-7f554ad26982 | note | • EDCM 501
5d4646a9-f835-5898-ac0c-7d72d39d9684 | note | • EDCM 502
9c2d9834-d306-51ee-9884-e44373b75bfa | note | • EDCM 503
8d581f1c-d71e-5d7d-8787-bb0aad048d3c | note | – – – – – – – – – – – – – – – – –
ffb5831e-9f60-51c2-8e04-55ff2df34c33 | note | ACCEPTANCE CRITERIA: Where applicable, expansion joints shall be placed:
31c85add-85c2-5ca6-9b77-5ac273cfa3cd | note | i. on either side of vehicle crossings
baca2adc-be89-51a0-b16f-9178e023d57a | note | ii. at junctions with existing footpaths and shared use paths
8f5cddeb-abad-5d21-82d4-6cc6cd8c6942 | note | iii. at junctions with bridges
586e2018-eb41-592c-a8b5-e406fe3a2d6b | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
fa9462c5-061c-58ee-804b-c3988f8c791b | note | • The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
99e5eeaa-19a6-5b6d-bbfb-0bf2163dc61e | note | • Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
5c54e5c4-37d7-5e22-96eb-ba972ebc7b8c | note | • Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
2ca08b03-fce5-58e7-b32e-5f96c7081831 | note | – – – – – – – – – – – – – – – – –
5ed258a8-e6cd-5ce3-8cea-e16937398347 | note | METHOD: Visual, Measure
12ac50c8-93f1-56f8-9661-93733a5d7cad | note | – – – – – – – – – – – – – – – – –
123431c6-9920-5476-b5d7-75062c113e7d | note | FREQUENCY: Where applicable, each lot
99a146e8-819a-5f04-a537-d4299f502010 | note | – – – – – – – – – – – – – – – – –
c9cc577f-50ad-5571-93ab-8bf39a003bf2 | note | CATEGORY: IP
1f952491-d27c-5f18-9d8f-f8877939399f | note | – – – – – – – – – – – – – – – – –
da859022-8219-5fd5-bba7-87b4efd334c2 | note | RESPONSIBILITY: SE/PE/SPE
527c57f6-18c2-5ccc-945a-be344114838e | note | – – – – – – – – – – – – – – – – –
5c62ce19-9ddf-58cf-b0cc-ce2509fa0239 | note | VERIFYING DOCUMENTS: This ITP
77c40173-c4c7-58f7-88f1-6518aef8818c | date | Date Completed:
| checkpoint | 5.10 Reinforcement Placement
8a2a3b92-b378-5656-89d7-0b07556c8194 | note | REFERENCE: IFC Drawings 703.13
4133543a-597b-5e10-8f18-e85659481f77 | note | • EDSM 401
600f415f-c2b0-5437-a58d-3ff9dbf0b719 | note | • EDCM 501
784ef684-668f-5601-b7d5-7e71c3645616 | note | • EDCM 502
bb3affb7-c3de-5e7d-aedf-8bf458a69e60 | note | • EDCM 503
803b0eb8-9dd4-5e60-b2ef-a6e5480dffde | note | – – – – – – – – – – – – – – – – –
853353b2-1699-591f-8f75-4f6a86e3f2fb | note | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
e9a52d0f-d019-5352-b57a-f802f4ae1ab7 | note | — Footpaths, Residential driveways and Median islands infills: SL72
90252b38-9017-5414-8802-9cd9eed087be | note | — Industrial Crossovers: SL82
a9c2518a-496b-522e-b370-ff1573272d16 | note | — Traffic Islands: SL72
09868269-99ea-5a3e-956c-f7054f1ae906 | note | — SUP: SL82
8389ccc1-ef23-5bd9-8861-661ee4ca2f9e | note | • Minimum cover of 50mm at edges has been achieved (including tie wire locations).
c2a5e258-0806-51cc-9341-d14bbf14426d | note | • Any splice lengths achieve the minimum length and are in contact for this length.
6e8366ab-ac86-58ec-a127-8efc167d7031 | note | • The reinforcement surface condition is free from dirt, debris and damage.
dcee12c7-5570-56d6-afe6-1d01e1144607 | note | • The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
3d2437c5-bdd5-517c-890a-2d1a495c4c13 | note | • Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
3ac8e3e5-fb71-5785-895f-ff6807a165e2 | note | – – – – – – – – – – – – – – – – –
99791648-1a85-5aae-a056-bebea5652979 | note | METHOD: Measure, Visual
25e7940e-4f80-5fe9-84d4-d92b4ff34543 | note | – – – – – – – – – – – – – – – – –
66429bad-dd09-53c8-bb0a-d27cf41ed5ca | note | FREQUENCY: Each element
bd172e1a-a229-50c0-bf92-99ec507cf49d | note | – – – – – – – – – – – – – – – – –
37e4d7f7-4e03-5932-881a-943657e10666 | note | CATEGORY: IP
8936e843-2ee4-5060-9811-d27925a7ab59 | note | – – – – – – – – – – – – – – – – –
e496d13b-8e06-5e21-9bbf-c274a7c889f4 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
72d36f5a-88e3-5cfe-a573-ac4bdfd84a2e | note | – – – – – – – – – – – – – – – – –
43cdaaa8-a2e9-5e9f-b49c-323af5c775a4 | note | VERIFYING DOCUMENTS: This ITP
8a4feb4a-8138-5b9b-af2e-708ded5bd9bc | date | Date Completed:
| checkpoint | 5.11 Pre-pour Survey
f8cc220e-eae7-5846-9416-914b6d86c92d | note | REFERENCE: IFC Drawings 703.15
c6bfddcb-49c5-50aa-a343-0db2093ca429 | note | – – – – – – – – – – – – – – – – –
7c09b625-1c95-5c42-96e9-51138736d5a8 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
461d5096-1466-5b37-810c-c5406c480094 | note | Erected formwork and base layer within the tolerances below:
5d0c15cb-1c3e-564f-b9a1-75dc6facdc02 | note | • Departure from RL = ±10mm
d13e71e1-48f1-5b6c-93cb-776e6529f309 | note | • Departure from alignment = ±10mm
fc8bac5e-9566-554b-bdfe-5a69479ead9d | note | • Rate of change of deviation from RL or alignment = 10mm in 10m
f3585ed9-c477-5ac6-8c8a-cb5e2d32013a | note | • Irregularities in alignment = 5mm in 3m
d1929f03-1641-508c-9697-bd1798cd059c | note | • Section dimensions = ±5mm
d36b17d3-b832-547b-892b-2ae83733fb4d | note | • Section dimensions (less than 25mm) = ±3mm
b3be4eb2-75a7-5cc6-b5e9-7f3e98421aea | note | • Width of pavement = -5mm, +15mm
84d8ac3b-9ef7-5c63-8b6a-51ebded9a883 | note | – – – – – – – – – – – – – – – – –
c0bbfe2e-592d-52a3-9d62-4e1e0df3d75f | note | METHOD: Measure, Visual
a1ef62a1-cef3-5bb0-b8f9-473bedb5b30a | note | – – – – – – – – – – – – – – – – –
925ed43a-4f3e-5336-96ed-0ac681acf360 | note | FREQUENCY: Each lot
ab9287f0-47fe-5598-948d-744127c1963f | note | – – – – – – – – – – – – – – – – –
b970d517-01db-557b-b406-d9300a8e230c | note | CATEGORY: HP*
04d1b7db-fc98-5975-a28b-32845b025555 | note | – – – – – – – – – – – – – – – – –
8a53c71f-25d2-526d-8301-5c104418755a | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
fbf98017-68fe-509e-bbec-ba83d65d8d4c | note | – – – – – – – – – – – – – – – – –
5544992c-10aa-5128-9ab2-f5ccc28effb5 | note | VERIFYING DOCUMENTS: This ITP
8fb8774a-36a2-51d4-9595-bf9d0b58643a | date | Date Completed:
| checkpoint | 5.12 Pre-pour Inspection
9cb9973d-b01c-5c67-af8d-a952ccf78e7b | note | REFERENCE: Section 703.09
1712d846-26eb-59dd-9378-1c60bc5ba38e | note | Section 703.21
dfff3cce-d9bd-510c-a5ef-75d2697f5a8f | note | Section 610.17a), b) & c)
00a462d1-dee7-5210-960d-301a7168beb8 | note | – – – – – – – – – – – – – – – – –
a127eb97-b110-5ce7-a351-e8c599a69da0 | note | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
d57a7c34-5f20-5f74-8302-140263ac9b4d | note | • Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
241ad0ed-7147-50cd-9642-65e3fbe1ebd9 | note | – – – – – – – – – – – – – – – – –
ec710015-5f2d-57a2-bae8-3f9521421c4c | note | METHOD: Measure, Visual
d7626c04-d88c-5a85-ac66-26117d060a11 | note | – – – – – – – – – – – – – – – – –
3569d93b-5045-56a8-870a-a230c394a659 | note | FREQUENCY: Each lot
161bd7f7-da24-5eb1-86a1-dfa4f99433e0 | note | – – – – – – – – – – – – – – – – –
ab718df3-7cfb-5511-80eb-32fd7b3d7ae5 | note | CATEGORY: HP*
45cccfb2-500a-5825-811c-b351d99358d4 | note | – – – – – – – – – – – – – – – – –
6daf87e7-2071-5717-8a36-34f91b4d565a | note | RESPONSIBILITY: SE/PE/SPE
698830a0-e138-588e-a3a9-ec8b5156d616 | note | – – – – – – – – – – – – – – – – –
7d802580-3d4b-54d8-a857-968bb3a7dd6d | note | VERIFYING DOCUMENTS: This ITP
da944a5c-0008-5681-9259-22ae8a98b0c3 | date | Date Completed:
| checkpoint | 5.13 Weather Conditions & Evaporation Limits
1b7ce114-5047-579b-95f7-909e4ff65cb1 | note | REFERENCE: 703.09
49ee9f3d-43be-5d74-b6f6-5747f31faf7d | note | 610.17 (a - f)
d7b70446-c046-5ea3-bbf3-a7c1eef585ee | note | Table 610.171
9f0c2c67-0acd-5117-a9da-11411fe77061 | note | – – – – – – – – – – – – – – – – –
bba4e4f2-c3da-5a1a-9260-5c93f4def278 | note | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
1b66151b-5f6e-56f6-8033-74005a865b17 | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
b89ca60e-bad1-5827-b3b2-4799aa5028bb | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
601874fd-8b64-5e8a-a13f-d3c025c4c068 | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
c378cc48-e507-5c26-80e9-6aae670ee0a8 | note | • Record: Required information on the Concrete Pour Record.
6962cdcc-0355-5e2a-acdb-f56a5c52a8a6 | note | – – – – – – – – – – – – – – – – –
b02e77ed-c43f-5229-8b36-0ae1eccc18cf | note | METHOD: Measure, Visual
a2a8d1fd-e690-5e89-ba61-3a834496da73 | note | – – – – – – – – – – – – – – – – –
b7c3252f-6a6f-5f13-a520-a01cf480c309 | note | FREQUENCY: Each lot
2f8208e7-6d5c-5c83-a49e-94e97bee422b | note | – – – – – – – – – – – – – – – – –
137db7ff-93ac-5108-a63e-31cf6762676b | note | CATEGORY: IP
cf61b922-48eb-5357-83dd-323e756c8a51 | note | – – – – – – – – – – – – – – – – –
224f61ea-70ee-5096-a915-aa4c8a36cf19 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
87f28a89-c99b-5e09-a325-12551bd26f08 | note | – – – – – – – – – – – – – – – – –
de5bd5f2-476d-5d11-8546-92eff40b9acb | note | VERIFYING DOCUMENTS: This ITP
e9ddba16-afab-5a8b-ab39-658e26363e18 | date | Date Completed:
| checkpoint | 5.14 Concrete Testing - Sampling Frequencies-Footpath
7c822308-28d3-5d9f-8e1d-153738695dab | note | REFERENCE: 703.11
91a6eb39-79d4-5589-bb42-68e89b032363 | note | AS 1379-2007 Clause 6.2
38ce9c3a-d571-5e7a-ae84-06ec2350f0eb | note | – – – – – – – – – – – – – – – – –
38a4dba2-422c-5d00-9a5a-41e416ace718 | note | ACCEPTANCE CRITERIA: The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
2273e34e-7685-5ad4-aea3-7647243663b3 | note | • Correct quantity of cylinders manufactured per sample.
d6bca5d7-78c1-530c-8960-18c3d5262582 | note | • Record: Required information on the Concrete Pour Record.
c3801267-b369-5782-8cac-ef093809ed59 | note | – – – – – – – – – – – – – – – – –
b565ab4f-6af5-5ea5-a807-81bf5a4ad375 | note | METHOD: Test
b608fc54-639f-564a-b3b4-e30bda05c8fc | note | – – – – – – – – – – – – – – – – –
e9b8da59-52f7-57d3-8cf1-f356fd19689b | note | FREQUENCY: Each lot
dbc4fbe7-9ac9-5dfb-a441-aabb3d60436b | note | – – – – – – – – – – – – – – – – –
d9469718-0e8f-5d03-90fc-02c82c40e31a | note | CATEGORY: IP
d9db5702-8281-585b-9b29-e7dd42fe129c | note | – – – – – – – – – – – – – – – – –
27edf007-e425-5fdd-b5ec-0c32d2455a68 | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
6b12c881-92e8-5c15-933f-bf15ab1efb33 | note | – – – – – – – – – – – – – – – – –
9893d0a2-171a-5de9-9526-41fab35c8993 | note | VERIFYING DOCUMENTS: This ITP
cb7bfef7-d9a0-5c81-bc56-81d62a5435da | date | Date Completed:
| checkpoint | 5.15 Concrete Testing - Sampling Frequencies-SUP
cfc2b2c7-e269-599e-a57c-d31045c0afff | note | REFERENCE: 703.11
fef7fa7f-c7ed-5034-9891-815ce8a3dca0 | note | 610.16 (b)
a5738060-fe3b-526a-acd5-83b3c6df7ec3 | note | – – – – – – – – – – – – – – – – –
42bb920f-aac9-5fcc-938e-fdedcf3e6d5c | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
925fc771-c0e7-51ff-8df2-147775ff2690 | note | Shared User Path:
275b4465-e869-5264-b055-0968251bf5ed | note | • 0m3 to 10m3 = 1 sample
ab9ebe12-612f-5b8c-9252-8199e0a6862b | note | • 10m3 to 25m3 = 2 samples
fa5a4c9b-bd38-5a07-91f5-55c332768b7f | note | • 25m3 to 50m3 = 3 samples
c097be04-cbe6-5a39-a000-aef6c5392cfa | note | • 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
ea27dd71-266a-5d40-99d1-40a5c6e16d55 | note | • For each additional 50m3 and additional sample shall be taken.
20a8183e-d0c6-5563-a7f0-570924c2d74c | note | • Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
8a0685f2-4d88-5fd3-8248-8be283f61f1d | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
d8fba83e-7470-5ffe-9424-fa04132b37dd | note | Footpaths:
85354775-fe96-5eef-a58d-5d1bbab2eb8d | note | • 0m3 to 50m3 = 1 sample
3f8e2105-ea7b-5838-899f-2d9bda23418c | note | • Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
be1bd30c-788e-53e8-bcfd-259df13f51a8 | note | • Compressive strength cylinders = 2 no. 28 day strength.
a0add223-7449-5303-aa7c-6ce3b1039823 | note | • Correct quantity of cylinders manufactured per sample.
92c3fdd3-21a2-5fd9-bfc0-882d33da3a3f | note | Record: Required information on the Concrete Pour Record.
44ea6652-ae05-55ec-bde4-28dc2b88f0f1 | note | – – – – – – – – – – – – – – – – –
638979f1-2c74-5154-a632-cc1458c6f578 | note | METHOD: Test
d4d842e8-9007-55df-8058-731e1d3d13fc | note | – – – – – – – – – – – – – – – – –
a3919df6-a94f-56a7-9a15-a23ed450c7eb | note | FREQUENCY: Each lot
f8195f6e-8dd4-54e3-9fe2-a1131157f1e1 | note | – – – – – – – – – – – – – – – – –
523a6119-f186-597a-a542-0e567780eb58 | note | CATEGORY: IP
b85f56b2-1047-57d4-ac46-2395059f1542 | note | – – – – – – – – – – – – – – – – –
df488a7d-a1b4-582c-ab29-b50b37190b58 | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
cb830b48-5ea8-517f-9e25-4d7a9d092b03 | note | – – – – – – – – – – – – – – – – –
442369a9-855a-50cc-82db-4bdc7b45d9fb | note | VERIFYING DOCUMENTS: This ITP
34c3ce19-2868-56fb-80f2-93fcfe8ed2d0 | date | Date Completed:
| checkpoint | 5.16 Concrete Testing - Slump
c7b3a0f5-40eb-5729-a3ee-c2e0402a9987 | note | REFERENCE: 703.11
6aa2443b-18f6-5c2f-a9e7-d59fb8f43649 | note | 610.16 (c)
2370b6bd-d597-517a-86de-f200074407e3 | note | – – – – – – – – – – – – – – – – –
29d847ee-aca0-5632-8b2d-a9fe0141a6a2 | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
ed2570ce-9f86-51f3-953d-dfd12d768aab | note | <60mm = ±10mm
7a94d04a-f5b2-5105-a5f2-54a12272c14b | note | ≥60mm to ≤80mm = ±15mm
76f1cc61-1391-5fc2-8459-7cf6343fee1a | note | >80mm to ≤110mm = ±20mm
adacdba2-65c8-5d76-ba68-2d30448208c8 | note | >110mm to ≤150mm = ±30mm
1be0b479-c11c-5355-a1be-508f3ed21167 | note | >150mm = ±40mm
38ea3944-7620-52fc-aec0-ee27bdca55f5 | note | Record: Required information on the Concrete Pour Record.
02b4bfc4-9900-54d0-a9ad-226d679b13c8 | note | – – – – – – – – – – – – – – – – –
4942f767-ca98-5cb3-8fd2-b99c14ae65f1 | note | METHOD: Test
15ba736c-06dd-54ce-9dd3-e0fe9c01c07d | note | – – – – – – – – – – – – – – – – –
a5771780-07f5-597a-b89c-7544dc1faee9 | note | FREQUENCY: Each sample
8097f330-cb66-5fc5-861f-2d139480fc77 | note | – – – – – – – – – – – – – – – – –
575155e4-fc2a-5af5-86c6-9e625084e46a | note | CATEGORY: IP
f50227fd-c87b-5573-a8fa-cbdeedb46541 | note | – – – – – – – – – – – – – – – – –
dbbe2384-288a-5638-850e-f6903c1b6f2a | note | RESPONSIBILITY: Concrete Tester
ad395592-948f-527e-a59f-f6017760f493 | note | – – – – – – – – – – – – – – – – –
6c121bd3-bab7-5473-9aa0-88544b350642 | note | VERIFYING DOCUMENTS: This ITP
09d8e152-4bfd-5111-949a-5783a927533f | date | Date Completed:
| checkpoint | 5.17 Placement & Compaction
46f369b1-f154-503c-ad9c-e913308877b2 | note | REFERENCE: 703.08
2f1fc36f-0246-5de5-8fed-bbc0de2dbb9f | note | – – – – – – – – – – – – – – – – –
87a1de1d-74af-5bb9-925e-650f6691971e | note | ACCEPTANCE CRITERIA:
f337802c-1557-54d9-a214-7e9096d8b776 | note | • All concrete batches are traceable.
a84247b3-3c2c-5287-9397-4197644eaba3 | note | • Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
35c7ba17-569f-5fe8-869a-86418054d78e | note | • Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
5e4ed095-8e1c-5137-9fd4-23da37fb0d0a | note | • Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
9e5e4642-08d8-5982-9dbd-1f10b12bdb95 | note | • Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
a7edb8d1-24b1-54ca-a561-bbe76adc9b6b | note | • Vibration continued at each point until air bubbles cease to emerge from the concrete.
dc1076f0-45a0-5969-8e2f-323cb04e172e | note | • Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
07d583f6-ab9f-5286-b5d8-2cd1c2b66eeb | note | Record: Required information on the Concrete Pour Record.
b14bc880-71e7-5c5c-b42c-1b76994422e4 | note | Attach: Concrete Pour Record
b4ad7267-2427-52e2-ac54-7bd17ecbf6dd | note | Attach: Concrete Dockets
20564637-3210-5da4-8048-81f158bbc10c | note | – – – – – – – – – – – – – – – – –
572086ba-60f8-5027-8546-35bb30baa9f7 | note | METHOD: Visual
a96cac2b-db13-5046-b253-119ae7ddcc0e | note | – – – – – – – – – – – – – – – – –
7205747a-d00c-5ab6-8eee-78a518ae065c | note | FREQUENCY: Each load
21ae167a-b087-5559-bcfc-3e424222878f | note | – – – – – – – – – – – – – – – – –
3a068867-be89-5044-b557-cf208d2a8436 | note | CATEGORY: SP
86963b1d-5dd7-52f8-bda6-71c6b044ebe9 | note | – – – – – – – – – – – – – – – – –
8c28668f-23a4-5579-97e0-e3843fd8090f | note | RESPONSIBILITY: Foreman, SE/PE/SPE
1effec2d-1027-5bf0-bedc-64141642acb7 | note | – – – – – – – – – – – – – – – – –
6c76c8ef-6094-5616-b509-6d3559a299be | date | Date Completed:
| checkpoint | 5.18 Surface Finishes
d305f8e0-120b-5791-8b38-a6f7af72f6eb | note | REFERENCE: IFC Drawings
133a62fb-ee34-5a44-b770-9800f86993ed | note | Relevant Council Drawings
43a22e9f-1284-5128-9939-e20b617ae9c1 | note | 703.25
f4a604ec-ab96-5615-95e6-9075e852beb5 | note | – – – – – – – – – – – – – – – – –
a570ee28-5449-5221-84d6-d9962a015a9f | note | ACCEPTANCE CRITERIA: Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top.
b95725c2-405f-5323-ac67-ab15a0cffd26 | note | • It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
2e46d909-00b1-537b-8ecf-e08ac0cb9093 | note | • After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
79c1f51b-967a-51e0-9c2d-ace9428f18c0 | note | • Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
e9edaef6-7e39-5b19-9ea0-dcff9ab69a6d | note | • All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
11a7d353-5255-5be0-a49c-59f3db64d5e4 | note | – – – – – – – – – – – – – – – – –
eeaa27b9-bec0-5113-95e8-7ec8cd1fba08 | note | METHOD: Visual
297417e1-eec2-5891-acb7-0c740a1c1fbe | note | – – – – – – – – – – – – – – – – –
0cef983c-8056-5a4d-9074-050959db394c | note | FREQUENCY: Each lot
4145afa3-b1e3-597f-9959-3406daa9b236 | note | – – – – – – – – – – – – – – – – –
6998986a-ea71-58df-89d1-5b06881f2de4 | note | CATEGORY: IP
db4a68ae-6594-56a1-9549-8eaf969bb2df | note | – – – – – – – – – – – – – – – – –
41a8abbe-569c-577b-96b3-d7192956d877 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
7de01627-a8f6-5edb-8e4b-2cbcd5941c45 | note | – – – – – – – – – – – – – – – – –
a7ddc907-2e82-5c81-903c-91783938cc32 | note | VERIFYING DOCUMENTS: This ITP
354ee154-1167-53a6-83e1-2ea782690584 | date | Date Completed:
| checkpoint | 5.19 Footpaths - Crack-control Joints / Weaken Plane Joints
5cf3fab7-d224-5f58-b3e0-b08ec89fbe5c | note | REFERENCE: IFC Drawings
90830ed8-5405-5b86-a1e8-7d570b7dd3d1 | note | Relevant Council Drawings
91b199b3-b9a2-5b9b-b182-c7cdb3bdcd7f | note | 703.26 (b) (ii)
ee62d189-d4b4-50b4-8a51-700980847ed8 | note | – – – – – – – – – – – – – – – – –
826ce92d-caf1-56ca-8068-795b04256c46 | note | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
d44a59a3-966c-5621-8cb0-065abb7d2fa5 | note | – – – – – – – – – – – – – – – – –
22be39fd-fd35-58fc-9611-2cca6fc64f49 | note | METHOD: Visual
f9be2ba4-04c1-57a2-bbff-bfd42451eb78 | note | – – – – – – – – – – – – – – – – –
038f31dc-f99d-5d95-8850-396888698423 | note | FREQUENCY: Where applicable, each lot
bd1243d3-296e-5e5e-8b90-61bb6e12b2cc | note | – – – – – – – – – – – – – – – – –
a31b7a81-f4bc-5e54-b70b-951855a9eee2 | note | CATEGORY: IP
c8337e70-b4e6-53dc-9b1e-fb0684437676 | note | – – – – – – – – – – – – – – – – –
566ba001-b394-553e-bd1d-d7ec2a5a02bb | note | RESPONSIBILITY: Foreman, SE/PE/SPE
67310f25-d900-563c-8f05-aa588ab65080 | note | – – – – – – – – – – – – – – – – –
996e1616-713d-53a8-a8d6-b1b5efb959e1 | note | VERIFYING DOCUMENTS: This ITP
7f41f349-1542-536e-b48a-b3425cc6f6fc | date | Date Completed:
| checkpoint | 5.20 Curing
dd804e12-e8f9-5f14-94c3-8bb9e9bd45f9 | note | REFERENCE: 703.10
c7d5da92-988e-5f8c-851d-e0aeff4f08d3 | note | – – – – – – – – – – – – – – – – –
2e16ec37-3cb6-593b-b8d9-5c2ffd620e76 | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
2ca0f17f-903f-5d28-ab4b-654f9bfccf0a | note | • The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
0a53e1f9-0503-568c-8006-7e027474b69e | note | • Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
c3d9d294-ccba-5804-96cb-f1be78887f35 | note | • The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
45ef870c-5415-5a80-af70-95ed5b8ca5a8 | note | • Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
5cbd600f-3569-5c6a-9614-1122a7b569be | note | • Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
0a56bb5e-8884-5a3f-a620-86f35e93519a | note | – – – – – – – – – – – – – – – – –
43593746-c9a0-5340-bbaa-b447774d4ddf | note | METHOD: Visual
72c23070-e181-5609-a1ae-d87de1b7fd3a | note | – – – – – – – – – – – – – – – – –
bbcdfd17-5b42-5a13-8db9-9280a405c0da | note | FREQUENCY: Each lot
7036eba4-e94c-5ca1-9564-65cd2ff3abed | note | – – – – – – – – – – – – – – – – –
c8ccd703-3ae5-532c-9d88-ddc93e2c0d3e | note | CATEGORY: IP
78c72fbc-3a56-5b26-bda5-eb58eeaf4a4e | note | – – – – – – – – – – – – – – – – –
a4c68d98-130f-58df-8381-91f84bda3884 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
be38fb10-20e0-5a6d-99c1-0c3b7e8f632e | note | – – – – – – – – – – – – – – – – –
adad98d8-b5d6-51de-9a47-402665c6b9e1 | note | VERIFYING DOCUMENTS: This ITP
7bef9f79-b85b-5d87-8e6d-9e7f64db7cf5 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Shared User Paths - Crack-control Joints / Weaken Plane Joints
a793e873-9a4c-51ab-be4d-0beae395eb45 | note | REFERENCE: IFC Drawings
6f456919-ded4-5d34-ac81-f082f54b049d | note | Relevant Council Drawings
10ab3a2f-b313-5265-a6bd-e312e6fd3446 | note | 703.26 (b) (ii)
c3a4477d-5230-500a-b5ad-29e1e02f1b81 | note | – – – – – – – – – – – – – – – – –
2a8564f9-9eb9-5eaa-ba83-ccd099a19fca | note | ACCEPTANCE CRITERIA: Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
f86d15df-96ad-5fa1-a514-23158d8800a1 | note | <20°C = within 24 hours of finishing operations
eb4e598c-bd4e-5716-a1c5-2468982b6840 | note | ≥20°C - 35°C = within 4 hours of finishing operations
ac73e02c-daab-5d12-a7c5-6c9df337787c | note | – – – – – – – – – – – – – – – – –
7b6c9f4f-fbde-5393-a1fc-1df2602a257a | note | METHOD: Visual
0f075842-9b55-54a3-8ff6-867fa6e28235 | note | – – – – – – – – – – – – – – – – –
9418cd10-b914-5b7f-8155-17cd8e7a4c33 | note | FREQUENCY: Where applicable, each lot
a0890c7c-b945-59ca-8c0d-84d59b11f299 | note | – – – – – – – – – – – – – – – – –
277a12ef-7fe6-589b-80eb-8effd69013d4 | note | CATEGORY: IP
a42b8a6a-7dd9-5bcb-a14c-c65c64249dfa | note | – – – – – – – – – – – – – – – – –
c6b54b69-6e26-53b6-a0bb-42271fe92d58 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
6dcac43a-3b09-589e-a394-7da571f5a09c | note | – – – – – – – – – – – – – – – – –
4e0d7e43-f19a-57d1-bb4f-713f84fb69fe | note | VERIFYING DOCUMENTS: This ITP
0ab4bc8c-b4d4-5809-a9ce-791215d5850d | date | Date Completed:
| checkpoint | 6.2 Protection of Newly Poured Concrete
30eec13f-faa1-5bbf-95a7-e7e2b9ce7caa | note | REFERENCE: 703.27
0c73c963-36d0-5e0f-a454-cf6161a3243c | note | – – – – – – – – – – – – – – – – –
a3a2601c-8250-5096-83b2-37c0bfdb43ac | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
bd8c1698-1f5f-5d0d-98a4-cc72acc2472f | note | • Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
388fe6e0-9755-5259-a980-d0d25ac33307 | note | – – – – – – – – – – – – – – – – –
7fe9ffde-44cd-5fb1-82a1-bdd71f555b51 | note | METHOD: Visual
75401d34-ea5c-5f96-872d-ac78dc20a220 | note | – – – – – – – – – – – – – – – – –
f87e895c-9bec-5931-8baf-88a6667ce067 | note | FREQUENCY: Where applicable, each lot
f4b68b52-1594-526f-9fe5-0161755cfb38 | note | – – – – – – – – – – – – – – – – –
a49a3f74-baa5-5253-9410-18bac69af7c0 | note | CATEGORY: IP
0b4a2367-ab8e-5de4-ba5b-360c844f3b60 | note | – – – – – – – – – – – – – – – – –
7e62c314-4a4f-5052-8c8d-a087cd55befc | note | RESPONSIBILITY: Foreman, SE/PE/SPE
7a973b66-5149-52ac-a631-ceafcc97b674 | note | – – – – – – – – – – – – – – – – –
45dbfaca-372d-5757-9fea-c4135735a0ce | note | VERIFYING DOCUMENTS: This ITP
facab81c-b5b9-5779-9042-8ece8c673d88 | date | Date Completed:
| checkpoint | 6.3 Stripping Formwork
5b58007b-839a-573b-8c61-fb7e84ce13d0 | note | REFERENCE: 703.12 AS3610 Table C2
c21b67ae-f9d7-5022-92b6-967b279ea1b9 | note | – – – – – – – – – – – – – – – – –
7a3267cb-c42a-5f3c-a816-933ed82ddf64 | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
fc5d575f-344f-5885-baff-ff9b54630dde | note | i. 2 days for vertical formwork on external surfaces; and
dfc72c9c-0019-5b08-bf02-fbef57829939 | note | ii. 1 day for vertical forms on permanently hidden surfaces
f487b3fa-166d-5673-9af8-987361cc803c | note | – – – – – – – – – – – – – – – – –
de7406d1-7d70-5e0f-a995-d5bc18900ebd | note | METHOD: Visual
573c1feb-67d0-52f0-94e8-e81af959524b | note | – – – – – – – – – – – – – – – – –
84137e56-bdde-5b74-9df2-60edcc42cefc | note | FREQUENCY: Each lot
9c8a6f63-d187-5622-a1a3-6f0de56f31c3 | note | – – – – – – – – – – – – – – – – –
eb5dfad9-64de-5b61-b2f0-fc1c9145977f | note | CATEGORY: IP
c825ccfb-dcc9-5646-bfa0-2ce51babdb0c | note | – – – – – – – – – – – – – – – – –
39fb8dbc-2060-5f12-81bf-8f114e70f850 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
048af16e-1566-5012-813a-4fbf46272637 | note | – – – – – – – – – – – – – – – – –
78899bc3-d310-5aa2-b20d-bb1b68052547 | note | VERIFYING DOCUMENTS: This ITP
538a9a89-d598-57a9-bd29-b4d156c20739 | date | Date Completed:
| checkpoint | 6.4 Backfilling & Pavement Restoration
f022c7bf-af20-5318-98a5-4bcd4c57fc04 | note | REFERENCE: 703.29
d6dc4644-b203-510c-9651-4eb1e6ced30c | note | – – – – – – – – – – – – – – – – –
ffa58ac7-f5d1-5c0f-8d78-2f5929376823 | note | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
17bb3bae-b9dd-5fdc-b168-87fcc3632451 | note | – – – – – – – – – – – – – – – – –
d8109c98-d2ee-5328-8cc2-6aeebaeddf55 | note | METHOD: Visual, Measure
7e35b5de-efa2-527a-a011-7b46c023795f | note | – – – – – – – – – – – – – – – – –
93deeab7-9abc-540e-af9b-eae25dfc18fe | note | FREQUENCY: Each lot
38522e5d-3281-5ca2-a33e-429e0da8dc7f | note | – – – – – – – – – – – – – – – – –
6a754b11-aac2-5e7b-9862-f26347c0baf7 | note | CATEGORY: IP
833599a6-2f7d-54e3-9e48-1623e9f34a88 | note | – – – – – – – – – – – – – – – – –
74fc8989-7835-5829-a971-cfe3e9d398bd | note | RESPONSIBILITY: Foreman, SE/PE/SPE
d4e4c4c0-56fa-56c6-bbcc-1442efdcf61e | note | – – – – – – – – – – – – – – – – –
c0347f91-19f8-5e82-97fb-ee59d54b7960 | note | VERIFYING DOCUMENTS: This ITP
dbfb98f0-02e3-53d2-a620-e013ff678769 | date | Date Completed:
| checkpoint | 6.5 Surface Inspection - Cracks
7ead2397-0adf-50af-bc19-558e3ab8a801 | note | REFERENCE: 703.3
8d7e1631-8cc6-5a4b-a2c0-52c967ca46d8 | note | – – – – – – – – – – – – – – – – –
0be78d8f-77ea-5c7f-b26c-7d6f9c3e1f2b | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
e5f43aee-d5ec-54c6-9c55-71c5393fbc69 | note | • If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
7d5df0b4-8ab3-5117-8421-879397814129 | note | – – – – – – – – – – – – – – – – –
2f088fb5-38e0-5e2e-ad07-8195f841ba1a | note | METHOD: Visual, Measure
2747096f-a7ae-5a8d-ad93-5d45713a027a | note | – – – – – – – – – – – – – – – – –
3c037d7c-3e14-5c5c-8176-28a255f315ca | note | FREQUENCY: Where applicable, each lot
4a37f61c-1909-572c-b006-8879fba2abfd | note | – – – – – – – – – – – – – – – – –
5d72d5c1-4050-5fe0-87f9-50a1341b1c81 | note | CATEGORY: IP
90f7ea5f-a2d1-51cb-b62c-41eab2703f70 | note | – – – – – – – – – – – – – – – – –
84f60089-b222-5e70-91c8-6a3d007fbf3b | note | RESPONSIBILITY: SE/PE/SPE
3f41cca3-13e3-5ade-bfcf-557fe129d1d1 | note | – – – – – – – – – – – – – – – – –
bae3beb4-7ae8-5a71-a6f0-64eaf8ba07aa | note | VERIFYING DOCUMENTS: This ITP
696b55b8-689a-55cf-9e0f-54febfbde79d | date | Date Completed:
| checkpoint | 6.6 Surface Inspection - Surface Finish
499fbfb4-3ea4-5ad5-af52-87c4d794e6a9 | note | REFERENCE: IFC Drawings
e662fd3e-fb7c-5152-b9b6-e0abc34986d2 | note | Relevant Council Drawings
f8db1b73-bc19-5819-8811-4f9fcb9b3828 | note | 703.25
695b57e3-6916-5d81-b938-51f441243a69 | note | 703.10 (a)
6cc4c7fc-f831-5edf-9378-9794bcb86930 | note | AS3610 Clause 3.2
d1ff99ea-b0e9-523b-97b2-622de337439a | note | – – – – – – – – – – – – – – – – –
b2fbffbf-7060-58a6-afad-f7321a0dc19e | note | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
6203a806-4ad7-560c-8992-67a11dc567b7 | note | • All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
eeda3e2f-7ec1-5ea3-801e-80ded35789c6 | note | Class of finish:
1363d064-c007-5467-85fd-5e6a29f7fc64 | note | • Permanently hidden surfaces = Class 4
f5eb1c57-7bd6-5e1d-bfb5-81eb6d7c7254 | note | • All other surfaces = Class 3
adedacf5-d648-507c-806c-e84896ffa913 | note | • At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface
29b77ed9-4632-5ba4-bed4-08738ea01de6 | note | • Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
d70d1d1d-af42-5e2e-986f-34085b23dffe | note | – – – – – – – – – – – – – – – – –
afd53f5d-e2c4-50da-93c0-3e97ef8828e5 | note | METHOD: Visual
24f2b796-8f75-5071-9d23-201bb26cc6ef | note | – – – – – – – – – – – – – – – – –
d9d87fc2-c6e7-5b24-a90a-abcfaea9168e | note | FREQUENCY: Each lot
a0b74965-2716-5220-8fd6-92313ece6377 | note | – – – – – – – – – – – – – – – – –
e1c1a68d-3ec1-5b9f-bb83-3f16187e6049 | note | CATEGORY: IP
1cbc2db2-a684-50cb-a08f-05594bb59c5f | note | – – – – – – – – – – – – – – – – –
a2a8d6c9-9dd9-5ef3-b510-5df9d24c9ed7 | note | RESPONSIBILITY: SE/PE/SPE
1ec6f1c1-5789-561e-8451-67b1eb9f0c6f | note | – – – – – – – – – – – – – – – – –
d1991529-e664-521c-b396-a8b658527ecd | note | VERIFYING DOCUMENTS: This ITP
af1156b8-a9be-551d-86bb-ae9778cba67b | date | Date Completed:
| checkpoint | 6.7 Compressive Strength Test Results
1979e0c8-0727-56b7-bb53-1f1187b5f5b2 | note | REFERENCE: IFC Drawings
d73a5c1c-1dd3-5119-9501-ad99bcfcb94f | note | Relevant Council Drawings
f7a6acee-5381-5d8c-8066-28b307a9c6ba | note | 703.11
0b13d961-da4f-5c37-9538-0b5985421643 | note | Table 703.111
f9a86df8-d46f-5dc4-a8bc-6804cf69f8cd | note | Table 610.05.051
83394bf0-9461-5fe2-a0d2-4b940806e33c | note | 610.16 (g)
0913f9d9-c49d-5a6b-a6ab-7b954c7c790e | note | – – – – – – – – – – – – – – – – –
b85d8dbf-cf18-5e60-8630-f763ebb5f128 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
1f9df7a6-4808-5162-ad4a-535f33ad2685 | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
d0c45902-c465-50d8-8b9d-6a3b57e09385 | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
2dc67c0b-7f54-5caa-a437-978b7b3bb8e4 | note | Attach: Compressive Strength Test Results
ff837007-3a0a-5f08-9127-318668a2a6d1 | note | – – – – – – – – – – – – – – – – –
81bd8b61-a389-57a4-9eb9-316f0749bf28 | note | METHOD: Document Review
6f2e8efc-b499-5eba-adea-c5fb12ccaea0 | note | – – – – – – – – – – – – – – – – –
15707c39-2459-5e86-a8d4-600614ab2fc1 | note | FREQUENCY: Each cylinder
9b532fc2-7747-5e00-9d6c-66a22cf8ba52 | note | – – – – – – – – – – – – – – – – –
96fbf21e-3eaf-5ddb-8b62-5942ffdca4bf | note | CATEGORY: IP
5a548fc2-546d-570f-ac5d-34838c38f876 | note | – – – – – – – – – – – – – – – – –
cc96b10f-107a-56c2-bfdf-787d287ccd0b | note | RESPONSIBILITY: SE/PE/SPE
4a7546c4-62d9-54ba-b8aa-631bdda85de2 | note | – – – – – – – – – – – – – – – – –
9e82bbc2-0fe0-55a7-8019-6a71c9727cf2 | note | VERIFYING DOCUMENTS: This ITP
85a55408-7c5e-5c71-b371-7dc6a28fee1b | date | Date Completed:
| checkpoint | 6.8 As-built Survey
3b1785c8-6b05-5be7-ab8d-7e8739a47dec | note | REFERENCE: IFC Drawings 703.15
072c2520-d478-5aee-af51-8501c4806181 | note | – – – – – – – – – – – – – – – – –
e01ef259-5788-5b24-879e-fe247388baaf | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
20bd3619-dd3e-5c9e-b6f0-370d0ac6de21 | note | • Departure from RL = ±10mm
93523ff4-7ee8-5fa7-8223-84feaf58e107 | note | • Departure from alignment = ±10mm
9e7d132d-56bc-5989-beb7-60fd18eb1505 | note | • Rate of change of deviation from RL or alignment = 10mm in 10m
73722970-6ecf-536f-8a7e-20ae512ae358 | note | • Irregularities in alignment = 5mm in 3m
6f2d9bef-c95c-5965-8ed5-c6fab42a4cd3 | note | • Section dimensions = ±5mm
04c3aabc-9e3a-59d5-a915-221024efc4f7 | note | • Section dimensions (less than 25mm) = ±3mm
f11a0f53-42e5-5b15-86f3-404a70a4b74f | note | • Width of pavement = -5mm, +15mm
02962a01-7d0d-592d-b5e4-f77fab612757 | note | • Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
3d5f971d-a39d-5518-ba27-26ae2a304087 | note | Attach: Survey As-builts / Survey Report
d2b46dfc-2aeb-52bb-8131-016a6a09a48c | note | – – – – – – – – – – – – – – – – –
528efafb-302c-5469-9fb5-2aa827ce21fe | note | METHOD: Document Review
26373794-cb24-5462-afe6-4bdcadea9001 | note | – – – – – – – – – – – – – – – – –
f663d835-f7b7-537e-8002-b91f18f59698 | note | FREQUENCY: Each lot
bcaa0868-0f71-548a-b0ee-558810c1acae | note | – – – – – – – – – – – – – – – – –
35d86f22-684f-58a8-a0a7-31617d809b96 | note | CATEGORY: IP
dbdfa7d4-05ad-54f5-b1b0-f838a00e3b75 | note | – – – – – – – – – – – – – – – – –
9d169127-f349-5524-9b55-f375c6d2088a | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
e16ca35f-0bed-58ab-b2a6-fc9e16f2551c | note | – – – – – – – – – – – – – – – – –
e43a7615-e588-59de-a3ae-b4efcc962982 | note | VERIFYING DOCUMENTS: This ITP
fc7e7174-a872-5d75-ba69-d258f3026f82 | date | Date Completed:
| checkpoint | 6.9 Non-conformance Report (NCR) Closure
0a20346a-b826-5f8d-ba87-5e07547dd142 | note | REFERENCE: MRPA Quality Management Plan
8e75ba50-1f69-5d8d-bd0f-3d568cc41644 | note | – – – – – – – – – – – – – – – – –
ff8fe093-e8be-515c-a5ae-91cb0e1ff260 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
b0989557-e6af-5d1a-b841-19a742bf065e | note | – – – – – – – – – – – – – – – – –
372eaa1a-2aa7-5a49-bf60-d681e0beef63 | note | METHOD: Document Review
82c2c511-aa87-5440-a672-a24bd9c29413 | note | – – – – – – – – – – – – – – – – –
a145d24f-0212-5fb3-9c8a-6cdd9cc6fd8c | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
e08d8faf-c589-5ceb-a3f1-6f3fee477a76 | note | – – – – – – – – – – – – – – – – –
adbec5ba-69be-5c1d-b52b-16be4559f46c | note | CATEGORY: HP*
c3b1e79a-1221-5df5-b8de-35c5d5508a05 | note | – – – – – – – – – – – – – – – – –
0f22f408-48c5-54e8-bb22-69390f219322 | note | RESPONSIBILITY: SE/PE/SPE
23f152b6-0fc5-5ac4-a670-f4dab71d5e2e | note | – – – – – – – – – – – – – – – – –
ebdcf9da-7219-533d-bdfd-7da02b9faea8 | note | VERIFYING DOCUMENTS: This ITP
1739ab08-21bd-5f2f-9fe1-07f6eca7e62e | date | Date Completed:
| checkpoint | Final Inspection
40eeb546-a214-598d-8c67-2b2ba2bcd5f5 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0c1f8dd2-6636-54a9-9036-417480c206f1 | textbox | Name:
3838d519-6712-5bed-9623-c063aa840e77 | textbox | Position:
741215e0-d9ae-5b0d-bc9b-3af2ecbf0546 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-015-CIV-Kerb and Channel Rev 0 | itp | ITP-015-CIV-Kerb and Channel |  | 22fcf66c-a0ad-449a-92df-cae9fe300731
| section | Referenced Documentation
| checkpoint | Referenced Documentation
009b0b85-9846-5614-af5c-6da2e07d8d4e | note | Document Title: ITP-015-CIV-Kerb and Channel
8e4cd3d1-5f7b-5ac9-a1c9-34ed64a1f4a0 | note | ITP Description: Kerb and Channel
279ed2e7-32d4-5936-b07f-d48e25ef4dc0 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
08edf004-81e7-53e8-97c4-7c9660c80106 | note | Discipline (e.g. CIV/STR/RAIL): CIV
30041052-cbf3-55ed-b6ae-b7fbd92a47a0 | note | Revision Number: 0
81f54f9a-eabf-51c6-a1b5-0ca5c5f6facc | note | Revision Date: 16/12/22
b27efb9b-eaec-5d39-8e5d-0f1c68d107b9 | note | ITP created by: Isaac El Zayat
85cb20cc-9585-5124-9f83-14abb38e8d07 | note | ITP approved for use by: Victor Mira
4da3ae0b-4114-51e6-97b5-785a8ac619f5 | note | 1.1 Non Dependent
6a6bfb6c-7aaa-53c0-b742-bc335d701a13 | note | Reference: VicRoads Section 703, VR SD2001, VR SD2102, AS 2876, AS1379
| section | Preliminary Works - Materials
| checkpoint | 2.2 Mix design
5a1e31d0-1433-5127-b719-bb224dbf4fed | note | REFERENCE: SD2001, AS1379, Section 703.05, 703.06, 703.07
8793c194-1e10-554d-baba-46e1a2e2ce34 | note | – – – – – – – – – – – – – – – – –
8eafa027-8be4-55b7-b9ab-3479bc59c5fa | note | ACCEPTANCE CRITERIA:
43240ca2-6ae1-55ba-ab46-b290e6e97c36 | note | • Approved VR mix design to be used.
d209a6f0-4ea1-54c8-8082-85599a7c703a | note | • Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
642f9ae3-9d5d-597a-875f-b277941b7f36 | note | • Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
ecb5dee0-693c-5ce4-8f99-6cb88b2f3f68 | textbox | TeamBinder Material approval number for the Concrete Mix:
8b4e5bef-7cec-557f-b9c2-d28c26d32703 | note | – – – – – – – – – – – – – – – – –
9566883c-5415-5899-b2bf-2f8528c0747a | note | METHOD: Verify
0e1b9cd4-2298-54da-890d-a9da8a433df7 | note | – – – – – – – – – – – – – – – – –
64406640-093c-5ab1-94ca-c198fdfbb48c | note | FREQUENCY: Prior to commencing any activity
6b1bff78-a382-5d8f-941a-1c6bc7402bf3 | note | – – – – – – – – – – – – – – – – –
c277bca8-e2e2-5a74-81ef-03f2fc86fe65 | note | CATEGORY: HP*
d8b9718f-a502-51e9-bce0-52c48db7ea9a | note | – – – – – – – – – – – – – – – – –
9a8b911c-3756-527c-866e-78af2271508f | note | RESPONSIBILITY: SE
dfc5ba5e-77c1-52a0-8d2e-ca67b450428e | note | – – – – – – – – – – – – – – – – –
77d1c512-a251-5e45-871b-f47aa5375d9a | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
8367bae0-fcd3-555a-b029-59899f8e8ac9 | date | Date Completed:
| checkpoint | 2.3 Bedding Material
3f88161f-836e-5002-9fcc-7511fa33b95f | note | REFERENCE: Section 703.21, IFC Drawings
ac6f147d-5a1b-5c89-bc6f-c65b465810db | note | – – – – – – – – – – – – – – – – –
3124cdba-0d58-517f-89ca-34c9d074f356 | note | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete. Or as per IFC drawings.
c09a2139-8a75-5bf7-8534-5be27a59f2e3 | textbox | TeamBinder Material approval number for Bedding:
700d8d35-3f8b-5a7e-b35f-189bfd952f57 | note | – – – – – – – – – – – – – – – – –
d5f75223-6290-56fc-95fa-04b3be68cef7 | note | METHOD: Verify
e0d1da42-71f6-5610-8941-4d3047319a28 | note | – – – – – – – – – – – – – – – – –
8001c62e-9bd4-54d8-9425-fe4b2208f154 | note | FREQUENCY: Prior to commencing any activity
b5f9d8b5-41ab-53c1-8ce9-45f150c78daa | note | – – – – – – – – – – – – – – – – –
08969635-ca1c-5832-aeef-12845160994a | note | CATEGORY: HP*
75af38ea-b85d-5599-8705-40a8f42c1925 | note | – – – – – – – – – – – – – – – – –
04bbaeb1-101e-5abf-a235-ce4040acd89f | note | RESPONSIBILITY: SE
6fcd0518-73de-5aae-8f6a-9ba46514dbea | note | – – – – – – – – – – – – – – – – –
0b5b12d4-df9a-591a-983c-dee10f7e9e4e | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
3fb8d8af-92c0-50a5-8307-2461a9285eb2 | date | Date Completed:
| checkpoint | 2.4 Curing Compound
61f038ff-a538-521d-802a-ec36cf4706e7 | note | REFERENCE: Section 703.10
b1da764f-27d6-5683-bc32-8d054e37b362 | note | – – – – – – – – – – – – – – – – –
60becb14-06d5-51e9-a0cc-9d69b13cf074 | note | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
47ecf238-462b-5c39-9e08-94d6f71087b9 | textbox | TeamBinder Material approval number for Curing Compound:
49538ff9-08ae-5200-b458-c42c5df4c5e5 | note | – – – – – – – – – – – – – – – – –
0b46957e-ca8d-5bb2-ae28-a5de1b125aad | note | METHOD: Verify
0df53f6b-5df3-5a27-8a2a-f5e07f13cf38 | note | – – – – – – – – – – – – – – – – –
68fa5587-8371-50fd-a663-f9c3f51094aa | note | FREQUENCY: Prior to commencing any activity
ee31a341-1b6e-5a46-aae1-389ada6a2143 | note | – – – – – – – – – – – – – – – – –
ea3ab702-60eb-51ea-b466-f56ab6e095d1 | note | CATEGORY: HP*
a2471272-8939-5d84-bdbb-e3c68d5c0a56 | note | – – – – – – – – – – – – – – – – –
2673e2a4-8c75-5d69-89af-008d801cbe18 | note | RESPONSIBILITY: SE
74ade77c-72af-5f7e-a438-018e05965d50 | note | – – – – – – – – – – – – – – – – –
8e18faf4-e444-501c-95eb-892c115520c2 | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
d7db750f-139c-51c3-95bc-b46d2f545483 | date | Date Completed:
| section | Preliminary Works - Documents
| checkpoint | 2.1 Check for correct documentation
b089b2dd-0ed3-556c-8452-7d7c711a1860 | note | REFERENCE: Drawing and Drawing Register
d310df17-1eac-59f8-ac80-664d3456deae | note | – – – – – – – – – – – – – – – – –
d30c3627-8542-574b-9f0c-1f9479c83b41 | note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
15535d57-b1dc-5dc5-9f66-549d32c244b1 | note | — Using the correct and complete set of drawings
eab875e9-ed1e-5661-baf0-7cfddbf2497c | note | — All drawings are the latest version
3496e985-cd51-5836-8ae8-25497a41bdba | note | – – – – – – – – – – – – – – – – –
7bba940b-7573-583a-933b-eb54cce6fad2 | note | METHOD: Visual inspection
e1e5375f-d8e6-5217-ae9a-950206aa9d28 | note | – – – – – – – – – – – – – – – – –
ad6e408a-5f75-539f-8550-2d67e445564a | note | FREQUENCY: Prior to commencing any activity
510557e8-898e-53e2-b0c3-cadcc5e69d7f | note | – – – – – – – – – – – – – – – – –
560153af-ff1f-52c1-b6e4-1dd671530a5f | note | CATEGORY: HP*
b2221f28-849b-5ffe-9768-1f27cbe8fe6b | note | – – – – – – – – – – – – – – – – –
6f409df5-9355-5653-9425-4fac4fa72f02 | note | RESPONSIBILITY: SE/PE
9cc20667-ffea-5efe-a1fc-8b3c1a517a68 | note | – – – – – – – – – – – – – – – – –
d67c355f-b28b-5099-9fba-142a1921e2d5 | note | VERIFYING DOCUMENTS: ITP Signed
4e1f5115-7a9f-527d-82e5-8baca0eeebf8 | date | Date Completed:
| checkpoint | Lot Map
25c6853a-ca66-59ac-8360-4b7b170c585a | note | REFERENCE: MRPA Lot Management Procedure
b07ac09c-3dd2-58f7-a691-f8769256a2a5 | note | – – – – – – – – – – – – – – – – –
858ac52e-8b77-5071-a5c2-dcd7d5bb6a5b | note | ACCEPTANCE CRITERIA: Upload a Marked up drawing which indicates the Location of this Lot:
b91f64c7-b080-50fa-a9e6-0ad3fdb7777c | note | • Attach: Lot Map
0b7343d5-a27c-5d06-a6f8-c456907956b4 | note | – – – – – – – – – – – – – – – – –
8fd4a064-bc41-57c0-acb6-eecd748be9de | note | METHOD: Document Review
4ba919f4-4429-52e1-a2ee-1af0e0854d36 | note | – – – – – – – – – – – – – – – – –
00af3142-1828-5895-83e8-c4380681a228 | note | FREQUENCY: For Each Lot
5f4369f2-e676-50d6-aa7b-61e4cc08ce04 | note | – – – – – – – – – – – – – – – – –
0d75dd56-b586-5b30-8e04-fe641d01648b | note | CATEGORY: HP*
494e161b-c42b-5e4b-b066-8f36ce71fbf4 | note | – – – – – – – – – – – – – – – – –
b4f2fbe0-c030-5e42-ad84-8daeeaee4cb5 | note | RESPONSIBILITY: SE/PE
10acd828-c5a4-5eb5-9a2b-58a7ee12c6de | note | – – – – – – – – – – – – – – – – –
d9e1c5ea-fe89-574c-bb96-9c33c51277a1 | note | VERIFYING DOCUMENTS: Lot Map
4af5d2c5-f998-52c1-b1dc-75ce709ac8e3 | date | Date Completed:
| section | Pre-construction / Pre-installation Activities
| checkpoint | 3.1 Setting out
ee1cd808-b1ab-5de7-abda-bd2942e76034 | note | REFERENCE: Section 703.17
2ea82630-6349-5ace-a425-4dcff0016e85 | note | – – – – – – – – – – – – – – – – –
d4f58911-e05b-589c-bd08-c026cc414f5e | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawing.
a527abec-1c47-59cf-aeea-f5f1a69bc8fe | note | • The superintendent will review and confirm set out.
679a21c0-8e9a-5640-9198-1580ce2ef4b5 | note | • The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
b176c907-217d-5baa-96f1-2d0019832074 | note | • Attach: Survey Report
272bffe1-98be-5648-b25b-5bca165b1ba6 | note | – – – – – – – – – – – – – – – – –
61639091-b4f2-562e-a8f5-54c9b1b463c7 | note | METHOD: verify
b86a650d-92d2-5b1a-b7fb-50faafed41a6 | note | – – – – – – – – – – – – – – – – –
b9e12d7a-9283-59ae-80cc-efa2a9cd6bc2 | note | FREQUENCY: Prior to start
04abb4cd-6f69-56d1-99d9-d0b016486091 | note | – – – – – – – – – – – – – – – – –
e75d6c7d-6bb8-5258-9767-4f3c7fc3f64e | note | CATEGORY: HP
374fa501-585b-5ca6-972e-ff8bb40754c9 | note | – – – – – – – – – – – – – – – – –
cac21d97-d6fd-5507-bbde-174256a8e3d2 | note | RESPONSIBILITY: Surveyor
423d1ee1-7568-5d97-a833-7c37985c2d19 | note | – – – – – – – – – – – – – – – – –
5753d09d-593b-5b1a-891b-c6a460f8b7aa | note | VERIFYING DOCUMENTS: ITP signed, Survey Report
d9dd448a-3d30-5653-b413-63785620a962 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Temporary drainage provisions
afed759f-ef43-5f74-8ac8-91311cdc52c1 | note | REFERENCE: Section 703.18
65195814-84d0-549b-b70d-5e131c58ac6b | note | – – – – – – – – – – – – – – – – –
a975d8a7-7105-567f-8f77-d94a0bf3f357 | note | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
d4888a9b-eeda-5dfd-af28-4d99de92d99f | note | • Need to obtain prior written approval from the relevant waterway authority prior to diversion.
5424461f-402e-5904-96db-e4f883d4d906 | note | – – – – – – – – – – – – – – – – –
2877beca-e0d9-586e-aa4f-b49d5b5882c9 | note | METHOD: Visual inspection
8dbd7bd2-0688-599c-bf9c-1954887680c6 | note | – – – – – – – – – – – – – – – – –
56f1874b-5f7f-5f40-8f1b-5076edd78285 | note | FREQUENCY: If required
21b1b06b-4f0b-5377-ae70-ef1f3e74d4cb | note | – – – – – – – – – – – – – – – – –
29ee0ee9-f4ad-50b9-a28f-7082a28f0845 | note | CATEGORY: WP
69e90580-b5aa-5466-b0fc-f385fd1951c5 | note | – – – – – – – – – – – – – – – – –
9063ceec-b994-5c58-8421-7dcd9c192c72 | note | RESPONSIBILITY: SE
56e94125-92c9-5603-8485-62bbfef69a7a | note | – – – – – – – – – – – – – – – – –
57c5f410-d939-52e0-abce-b5467a1f79bc | note | VERIFYING DOCUMENTS: ITP signed
409adc9c-44f0-578a-ae1a-fd192031a10c | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 4.1 Bedding
762e074b-09b0-5f70-a982-8d4196e3d2b5 | note | REFERENCE: Section 703.21
1f432c39-c800-52ff-bf4c-d4b97bbfd710 | note | – – – – – – – – – – – – – – – – –
6ac67939-de31-586d-be8b-460dfd4371d0 | note | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm.
01c1d797-0791-5092-bc6f-914e4e57e1c2 | note | • Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted .
779bf67d-5b60-573d-b0e8-2451582262c0 | note | – – – – – – – – – – – – – – – – –
c3ae9df2-6a9e-5018-919b-4e8e6e95dd9c | note | METHOD: Visual Measure
fee4b89c-7e7a-5571-8890-6f31e1ec0b20 | note | – – – – – – – – – – – – – – – – –
31820287-2dc3-5455-a253-9d97f69214f9 | note | FREQUENCY: Each lot
7b7702d2-f36a-5f06-b68c-431db18b357e | note | – – – – – – – – – – – – – – – – –
974ffea1-9efe-5b12-b512-d85fbce3e7e8 | note | CATEGORY: WP
82b47de5-51b5-56c2-a135-8b9ee01c830a | note | – – – – – – – – – – – – – – – – –
51da41f6-443f-5562-b683-9583346140be | note | RESPONSIBILITY: SE
a5583990-b09f-52a0-b6b7-747a6adfa500 | note | – – – – – – – – – – – – – – – – –
c903959d-2fb7-5d21-84dc-7a480bf134ae | note | VERIFYING DOCUMENTS: ITP signed
e689c30f-096a-5f8a-8623-11f5f46932a9 | date | Date Completed:
| checkpoint | 4.2 Formwork
a4e581fb-eae2-5f2c-bf70-4f87f2deb2e8 | note | REFERENCE: Section 703.12 AS3610
c2426949-9386-5e76-bc89-2bc6ac81e3e5 | note | – – – – – – – – – – – – – – – – –
7d811fad-11f6-53d6-86df-7dfb2435b51e | note | ACCEPTANCE CRITERIA: Joints in formwork shall be constructed such that loss of mortar is prevented.
7b68ad43-b84e-525b-8869-e9dbd9dc1816 | note | • Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
00b4020f-da86-54e2-af50-77b58619d00e | note | – – – – – – – – – – – – – – – – –
f5a55a3a-da4e-568d-93ed-13a90b3a99d6 | note | METHOD: Visual Inspection
4ac166ae-ef69-56fa-82d4-7f0018da575c | note | – – – – – – – – – – – – – – – – –
b5ba3980-e514-56db-be2b-55d96b4d4138 | note | FREQUENCY: Each lot
abdf5389-c925-5760-9865-a19dc1055804 | note | – – – – – – – – – – – – – – – – –
6e6bf7d0-db77-54b6-8307-42dc1f64aafc | note | CATEGORY: WP
2ae4c4dd-e6d6-5ceb-aae6-1f5416ddf467 | note | – – – – – – – – – – – – – – – – –
a9b399a3-bc6c-54b4-a5e6-be1c73b624d1 | note | RESPONSIBILITY: SE
6bd8b126-7b3f-5121-9558-da2159121c06 | note | – – – – – – – – – – – – – – – – –
f3515dbd-2b91-5e81-8fab-6c8aa52dd635 | note | VERIFYING DOCUMENTS: ITP signed
51a8bc98-68f9-5244-924e-72956176d9d9 | date | Date Completed:
| checkpoint | 4.3 Pre Pour Check
30baf684-2e7d-56f1-a2b8-9be588dc0cda | note | REFERENCE: Section 703.09
06524336-786d-53b0-a173-ee9cf1731a51 | note | • Section 703.21 Section 610.17a), b) & c)
ee0bc2c9-5437-57d9-921a-8494e634ed2e | note | – – – – – – – – – – – – – – – – –
c7eda2f9-47ca-50ba-9379-059346e9f733 | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
0aff6cfe-7592-51d3-83c9-85c7f1e6d16e | note | • Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
2ff43214-00af-59b5-91c8-34898d62a1e6 | note | – – – – – – – – – – – – – – – – –
a8d953e5-f3a7-522a-a210-b8e86066ccea | note | METHOD: Verify
8cbb57f0-ed39-54bd-8bea-61334b0e011e | note | – – – – – – – – – – – – – – – – –
96ca5d0f-f5e3-5c5a-9e20-504e0724dd38 | note | FREQUENCY: Each lot
7a9e86f8-3c13-599f-9024-2fbbb50eae3b | note | – – – – – – – – – – – – – – – – –
4d8723a7-d5aa-5a24-9347-8d6ea4fbe9e9 | note | CATEGORY: HP*
923b0363-8d9f-5708-be9d-eb349fd8ef69 | note | – – – – – – – – – – – – – – – – –
5d394e83-a893-5d69-a796-c04d06770e5d | note | RESPONSIBILITY: SE
10ded6b2-7e61-5acf-afe3-c9e96d310eab | note | – – – – – – – – – – – – – – – – –
3bac01d7-37e2-5b2c-a4bd-3c9587d247c2 | note | VERIFYING DOCUMENTS: ITP signed
8857eb30-6500-5acd-a913-4cac7773ec65 | textbox | • Ambient temperature |  |  | °C
84f4e73d-ae50-5a59-af17-95797e4a3c10 | date | Date Completed:
| checkpoint | 4.4 Concrete placement
97d25d60-2d9d-5ff1-8cc5-2e15b5f49ed7 | note | REFERENCE: Section 703.08
4c67b128-d675-561d-a7c0-d3676ab56b3b | note | • Section 703.23
d1976323-729e-5dee-85cc-402c6e0ad413 | note | – – – – – – – – – – – – – – – – –
a453678e-4d7f-5dbc-9dad-0662b61e443d | note | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
e95107d3-55c3-52b6-84cc-ba60e1b7fdcf | note | • Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
d0dc435a-0cae-5269-8df4-80f8a96e1ff2 | note | • Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
f187b065-aab8-53ac-a948-3ec22cdefd7d | note | • Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
b573af53-3a28-56ec-b7e2-d722e97901cc | note | – – – – – – – – – – – – – – – – –
f93a55ea-918e-55bd-81ed-35ea57823e63 | note | METHOD: Visual Measure
ba191213-2c60-5fcf-9c45-44d431e1c5d2 | note | – – – – – – – – – – – – – – – – –
87b8aa60-9242-59cf-a301-2d4468011640 | note | FREQUENCY: Each lot
984a11bb-2358-5d8e-a9db-5ed68f0bfd86 | note | – – – – – – – – – – – – – – – – –
f8bff205-3d92-59fc-86ce-9b7c2833c3c7 | note | CATEGORY: IP
e4539e86-91bd-5b87-b94b-fece5a5107c8 | note | – – – – – – – – – – – – – – – – –
c06d336f-eada-55e2-b7cb-e3d5b288119a | note | RESPONSIBILITY: SE
2f978d3c-a969-57a9-934b-8b19da5f644d | note | – – – – – – – – – – – – – – – – –
c25bb7be-cb48-54cd-b3df-dbb2fc2ed6dd | note | VERIFYING DOCUMENTS: ITP signed
389eac80-4b90-5616-876b-c820306bfb6f | textbox | • Ambient temperature |  |  | °C
0b9815e2-e554-5505-8d8b-ea8888151527 | date | Date Completed:
| checkpoint | 4.5 Transitions
a70f7862-7afc-5d27-ba2e-647af3c7d687 | note | REFERENCE: Section 703.24
367a3d26-bba8-512d-bd98-d9e047429ba0 | note | – – – – – – – – – – – – – – – – –
868b422b-89f5-55f5-86a5-ba6231419071 | note | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
2f9f3818-52c1-53a7-8221-c187f9ba2be2 | note | – – – – – – – – – – – – – – – – –
82cd302e-1025-5a7a-9621-ceb66d2596da | note | METHOD: Site inspection
ec0bbbcc-b596-5bf1-ae78-e3b904b260ab | note | – – – – – – – – – – – – – – – – –
1cb8a997-e4d1-53f2-8868-a15389d32d4f | note | FREQUENCY: Each lot
3b2a7db5-adee-56da-aa6a-761d60a940c9 | note | – – – – – – – – – – – – – – – – –
5ec20c83-e723-504c-a18c-753aed4171b8 | note | CATEGORY: IP
9dec7131-157d-569c-8402-f29e888c4ca8 | note | – – – – – – – – – – – – – – – – –
e0b9855f-608a-54a8-a74e-7c39e96e565b | note | RESPONSIBILITY: SE
81464237-b855-5d07-94ec-e0471f379bed | note | – – – – – – – – – – – – – – – – –
a8b1c20c-e129-523c-a859-bafaae70a86f | note | VERIFYING DOCUMENTS: ITP Signed
e5af150d-2872-50b6-b682-ee01631f183c | date | Date Completed:
| checkpoint | 4.6 Surface Finish
e2cce273-6889-56f8-92f4-43029d8a655f | note | REFERENCE: Section 703.25
c12925be-f6df-56ab-819b-1cc8f57e9413 | note | – – – – – – – – – – – – – – – – –
cb06741a-4c72-5ca6-98f6-44a2872c45fd | note | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
3e8792a9-8cc4-5727-a16b-de3bdf4a939c | note | • Renderings shall be applied within 30 minutes of extrusion.
5c7d8232-bf6d-5d6d-85af-cc03fc7d668d | note | • Concrete to have a neat appearance and uniform colour.
036b6852-8bda-556f-8d52-c4817df800e6 | note | • Class 3 finish required for external surfaces.
00d6088d-768a-570d-b615-b38b0ce8d6e8 | note | • Class 4 finish required for permanently hidden surfaces.
a4410fd8-ad28-59c3-afb0-1d43fff233c7 | note | – – – – – – – – – – – – – – – – –
9ddc50e0-a96b-5e66-82c8-3ff0d3f34d9b | note | METHOD: Visual inspection
2611502c-2341-515c-a0aa-6b11e45502fd | note | – – – – – – – – – – – – – – – – –
ffd3fe30-e166-5cf8-a4bf-0f630ec2fcba | note | FREQUENCY: Each lot
2b3a7f2b-058c-5e13-9a21-9ba982f9487f | note | – – – – – – – – – – – – – – – – –
48bb5cdd-285e-53b0-95d7-f864b0c32b55 | note | CATEGORY: IP
f2c9f1bd-38ca-5e8c-a59d-57149dedb2fd | note | – – – – – – – – – – – – – – – – –
58e1083f-f1de-5594-b66c-4a5a153f3888 | note | RESPONSIBILITY: SE
e6c3818a-96a1-58be-9efd-c611bf72c2e7 | note | – – – – – – – – – – – – – – – – –
62733df5-2d7d-5b44-9d4e-bffe563d43ab | note | VERIFYING DOCUMENTS: ITP signed
d8fbc71d-57e8-5743-b75f-91ae1931c025 | date | Date Completed:
| checkpoint | 4.7 Formwork Stripping
8cd16c0f-d64d-5c27-8ae0-d0160eab4ff5 | note | REFERENCE: Section 703.12 AS3610
079c25a5-2ae6-5a6c-9794-4eeac559f2a0 | note | – – – – – – – – – – – – – – – – –
f7f521c0-29ba-5a76-b77f-90f959d7d1d4 | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
96cf3f77-42fe-5c67-a270-7655b15cae76 | note | — External faces 2 days
8b9e71cb-7e14-54ab-bb38-f93f4db82125 | note | — Permanently hidden faces 1 day
3f317d8c-103e-5dc8-950d-5385adae7a95 | note | – – – – – – – – – – – – – – – – –
21d4e2cc-50f2-5ec7-b5d9-c95bdae1d5e8 | note | METHOD: Visual inspection
944faf6c-248b-5a69-a353-daddbb58d855 | note | – – – – – – – – – – – – – – – – –
0d415d2c-e161-55e6-aad2-2e77c447ed7f | note | FREQUENCY: Each lot
183e9d0f-ce7e-5c2f-a36d-89b67df6f380 | note | – – – – – – – – – – – – – – – – –
0745439a-7834-5775-b7c0-2bdb3733ad4a | note | CATEGORY: IP
d5296fb9-c7c4-5f08-8dd0-45d96dd871a5 | note | – – – – – – – – – – – – – – – – –
cb36f7ab-8c72-5f1f-8deb-94e3a66f943c | note | RESPONSIBILITY: SE
bb5c6b2f-aace-5248-adf3-0dee630eef34 | note | – – – – – – – – – – – – – – – – –
5d455bf4-5b35-5107-97b0-d426561cb69b | note | VERIFYING DOCUMENTS: ITP signed
dcd2f75e-2a2e-5cb0-ba78-c18d5e249eaf | date | Date Completed:
| checkpoint | 4.8 Tolerance
c3853922-80f3-5e00-9cd6-b5988d626edd | note | REFERENCE: Section 703.15
435638de-3348-5ab4-b3e0-d5c88a3f63a0 | note | – – – – – – – – – – – – – – – – –
2beebf03-c889-5f59-a2ff-29a5980200b6 | note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
cfb08aa2-049b-5afa-941a-c22764935765 | note | • Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
466c0f4a-0b8f-5f7d-ab92-0a3778d61095 | note | • Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
5cb1ab23-4d07-54a5-b346-0e1f1eb6800a | note | – – – – – – – – – – – – – – – – –
4665ba93-f357-5753-aeac-607934073db6 | note | METHOD: verify
156e4141-c22f-530e-b78c-a1c41913bb8f | note | – – – – – – – – – – – – – – – – –
6d26b9a2-93bb-5759-9eb4-a5161e397e75 | note | FREQUENCY: Each lot
b84af3ed-c98e-5353-bf3d-7a2ebbdd0bb0 | note | – – – – – – – – – – – – – – – – –
6e794285-36a2-5f20-9b85-02abb4f31faa | note | CATEGORY: IP
9afed74c-c3c6-5085-9d38-096420c8f94a | note | – – – – – – – – – – – – – – – – –
f58a24d7-8e1c-58d4-b035-179f723eb92c | note | RESPONSIBILITY: SE/surveyor
02ffc599-1b03-5f7a-a91b-bf46c9e3bc51 | note | – – – – – – – – – – – – – – – – –
4333273e-35e8-5f6a-a09d-dcc6cd31c61f | note | VERIFYING DOCUMENTS: ITP signed
7791fecf-236f-55ff-a55e-a4c8df9734e9 | date | Date Completed:
| checkpoint | 4.9 Curing
ebf09df0-ad3f-5597-a52c-43e1019388ed | note | REFERENCE: Section 703.10
2492748a-7e0d-5b62-8d28-1cabc397e541 | note | – – – – – – – – – – – – – – – – –
f9e58fc1-f6b7-5aa0-8425-eeb39c60903e | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
8afbe40c-fc27-5d42-b7cc-dce8872c3e0b | note | • Concrete edgings shall be cured for a period of not less than three days after placing the concrete
ce3bc838-3ec9-58f9-a212-3c24d645ec89 | note | – – – – – – – – – – – – – – – – –
13152c2a-95dc-5719-ad53-d5c775880512 | note | METHOD: Visual inspection
e0fb99c3-8f0a-5412-90c4-67b2173c5bb4 | note | – – – – – – – – – – – – – – – – –
f3393bbd-b7df-566f-9856-60308bb611c6 | note | FREQUENCY: Each lot
91c7a221-c076-527d-aa37-79f07284bc72 | note | – – – – – – – – – – – – – – – – –
cfed0bd8-d7e7-5b03-92f0-7eff30d5228e | note | CATEGORY: IP
a3a08ea3-dab5-5d11-a225-aaacb43aeb3c | note | – – – – – – – – – – – – – – – – –
6c1f6035-dafd-588f-847b-15b524c96de3 | note | RESPONSIBILITY: SE
22667bc1-31d9-569e-b1cc-64ebf92f49e5 | note | – – – – – – – – – – – – – – – – –
76096f2b-7bf6-5d15-baee-06e1d0b98498 | note | VERIFYING DOCUMENTS: ITP signed
e8130cbf-f9a2-5e6d-b48f-5a502abcb9ef | date | Date Completed:
| checkpoint | 4.10 Joints
a0bb2f58-3e6e-5873-82b9-ece37a5919ec | note | REFERENCE: Section 703.26
733ef3cb-67c5-53a4-9163-3cd517af738a | note | – – – – – – – – – – – – – – – – –
3cae0f6d-fd4c-51f7-858c-9b204c83c23c | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
c4d87c0b-8d92-5891-97ee-807cc6942e16 | note | • Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
b09d8351-574c-57f9-97ad-ebd336252a82 | note | • Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
b6b1a498-fa86-5232-90a6-264b6686b6c9 | note | – – – – – – – – – – – – – – – – –
9e5fce19-5968-5463-b362-bb9ed55ec795 | note | METHOD: Verify
402318eb-1302-549b-9d71-19a3f2241917 | note | – – – – – – – – – – – – – – – – –
e7ee3b1f-4df6-540f-9bf7-70bd3868d8c0 | note | FREQUENCY: Each joint
e437408c-86c4-5ae2-8384-5158916c265e | note | – – – – – – – – – – – – – – – – –
6eb3f885-598e-5e4c-8955-87e2846583cc | note | CATEGORY: IP
c7408ffa-65c4-50f0-a968-5d899d018740 | note | – – – – – – – – – – – – – – – – –
70192751-eef3-50b7-8c6a-98769cc33366 | note | RESPONSIBILITY: SE
cad2f531-1933-55ef-957b-dd25accb966c | note | – – – – – – – – – – – – – – – – –
552756b1-ed02-5e65-9269-6ce88839e38e | note | VERIFYING DOCUMENTS: ITP signed
bc8abcd0-a917-5ff6-aeac-b5fbdf9e0e1a | date | Date Completed:
| checkpoint | 4.12 Protection of Concrete
959b6dbc-f3ac-5e35-b527-d1c30c3c4747 | note | REFERENCE: Section 703.27
c9b79e65-4a4c-5850-b30e-84a22c2f51ef | note | – – – – – – – – – – – – – – – – –
468cb98b-54ec-5912-9d10-26c0853e8de0 | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
bdca8787-9673-5e89-8a50-1d3cf111d014 | note | – – – – – – – – – – – – – – – – –
5fdeaf08-9073-5f52-95ab-cc8655c64907 | note | METHOD: Visual inspection
c4406c1f-c0dd-5c42-ae38-cfba8dc04016 | note | – – – – – – – – – – – – – – – – –
9333eb06-61aa-51a1-8574-cec5ae75005a | note | FREQUENCY: Each lot
2c8121c8-2c15-5571-a3ad-26e9c6527689 | note | – – – – – – – – – – – – – – – – –
813d5c6a-c556-5dd7-ad1b-326453b38415 | note | CATEGORY: IP
10f83bf2-0a18-52a8-9732-08d4bf8f5cbe | note | – – – – – – – – – – – – – – – – –
4639477c-bab4-5c56-8abd-3cdf300aadd0 | note | RESPONSIBILITY: SE
892f4fde-4c58-572c-8b17-5ae44c42e64c | note | – – – – – – – – – – – – – – – – –
ba13e856-cf09-52ce-8787-9ab380eb47fd | note | VERIFYING DOCUMENTS: ITP signed
e5559e0c-3b1d-5a35-bdbc-35a34941301c | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 4.11 Backfilling
96243620-d8af-5026-a3e8-22c684be9021 | note | REFERENCE: Vic Road spec 703.29
87daaec3-edc4-5729-9749-0eb9764c1536 | note | – – – – – – – – – – – – – – – – –
34f01fde-79a6-534c-9559-5e7721172357 | note | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
a30e9da3-66c6-5efa-82e6-04f1f436e86f | note | – – – – – – – – – – – – – – – – –
3d7d27cc-9ca0-52cb-a5b5-2b38f8375dae | note | METHOD: Verify
825441a6-079b-57b9-8f77-bfdc38243bed | note | – – – – – – – – – – – – – – – – –
1e040e0b-44e5-58a7-b526-7223c1235c20 | note | FREQUENCY: Each lot
e2a56c45-b0ed-5131-8be4-ad1e817cd65a | note | – – – – – – – – – – – – – – – – –
0be29f85-517c-5697-8f89-d331516ad9d4 | note | CATEGORY: IP
20522701-70c6-58dc-8023-62df75a7b42f | note | – – – – – – – – – – – – – – – – –
b41aff00-9f7b-598e-8c53-cc55fb738205 | note | RESPONSIBILITY: SE
aa3cce91-cd4b-5f43-9baa-c8c262ce4727 | note | – – – – – – – – – – – – – – – – –
568072ef-cab2-5f0f-91a5-3b4c710c92ae | note | VERIFYING DOCUMENTS: ITP signed
d2738909-f493-500c-a210-74278be6cffb | date | Date Completed:
| checkpoint | 4.13 Cracking of Concrete
ce3b039c-fe3d-5b3f-85f7-b57327933b5b | note | REFERENCE: Section 703.30
d8fb20ce-e6af-5768-8b5d-bfa7e8d41021 | note | – – – – – – – – – – – – – – – – –
9df8d181-a87a-5a65-9249-ebf76de0209e | note | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
0291f27c-6ea3-5ee2-a774-89232d96b77a | note | • Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
f0d337ed-50b3-5a80-883f-0345054f5252 | note | – – – – – – – – – – – – – – – – –
5081422d-1071-5bd6-a9a0-fcff59140841 | note | METHOD: Visual inspection
99719de9-a20b-5ed0-88c4-21c82daa072d | note | – – – – – – – – – – – – – – – – –
e328e7db-4e24-5365-be0d-dd2c8d17f3e3 | note | FREQUENCY: Each lot
92ac3266-6315-5b82-ac74-55e0d8041f9a | note | – – – – – – – – – – – – – – – – –
38d32c31-22d9-5f71-bf6c-5625fef12e71 | note | CATEGORY: IP
3d2abd5d-dbfc-50e0-8325-1ed0614c3ce9 | note | – – – – – – – – – – – – – – – – –
1dd766f1-84be-58d8-b010-628f6a212902 | note | RESPONSIBILITY: SE
9ef08ed0-ad3d-572f-8726-f8cf71523b99 | note | – – – – – – – – – – – – – – – – –
fb690325-b569-5f74-9e9f-0006cdf26706 | note | VERIFYING DOCUMENTS: ITP signed
d3debc66-acac-5800-a133-342282f4112f | date | Date Completed:
| checkpoint | 5.1 Survey Conformance
48f386d9-e891-56b0-b48a-4130ebef8ea8 | note | REFERENCE: Section 703.15
d0cde9ff-d7eb-577a-8c81-2389fe200a56 | note | – – – – – – – – – – – – – – – – –
212fa810-0edb-56b0-9be4-d673b80d497f | note | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
908eff10-dc74-5615-bc30-e9e067eaa990 | note | • The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
a66b95da-ba89-5b84-bcf9-03285b16f05b | note | • Attach: Survey Report
82a7a7df-3920-5950-b4d4-691a6e87a490 | note | – – – – – – – – – – – – – – – – –
b76f4d81-6966-5877-a4ea-4ce052ba65b5 | note | METHOD: Document Review
97cf5121-552e-50aa-9217-6ed19b1e8d82 | note | – – – – – – – – – – – – – – – – –
7529e5f3-71c8-5887-a7a1-b39569f9fefd | note | FREQUENCY: Completion of each lot
8828a3cd-5602-550a-92fd-d30f144630a4 | note | – – – – – – – – – – – – – – – – –
b5df1611-b2a5-5d8c-a802-db7e2fb4291c | note | CATEGORY: WP
2e8947d8-87e1-51be-908c-0efc3f9dc70d | note | – – – – – – – – – – – – – – – – –
413e8387-5863-5a84-a547-8eb44eb11754 | note | RESPONSIBILITY: PE/Surveyor
55e01e22-2108-5570-aaf6-e70f1496463d | note | – – – – – – – – – – – – – – – – –
21217774-bc07-5336-a4c7-76a8dddd62cb | note | VERIFYING DOCUMENTS: As-built survey records
8738316f-9035-5a07-aa07-353b4ac60f8b | date | Date Completed:
| checkpoint | 5.2 Non-conformance Report (NCR) Closure
e63f7585-6d92-5e3b-8e04-0743155b9476 | note | REFERENCE: MRPA Quality Management Plan
32fd29ee-3e7d-5842-8022-711df6208df5 | note | – – – – – – – – – – – – – – – – –
b8fd2f27-dc9e-57da-ab25-d90874e511f6 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
2dfad744-b8f5-5f37-a717-1bc72c3239f9 | note | – – – – – – – – – – – – – – – – –
2f2539de-9689-5dc2-990a-dffd492ddb64 | note | METHOD: Document Review
8640e715-861a-545f-95ff-4df95d71dae8 | note | – – – – – – – – – – – – – – – – –
9af60c05-0e22-5b15-9ebc-d8cc63ad5a9d | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
8e47ec21-3b6b-50e1-8e3b-199a1965be49 | note | – – – – – – – – – – – – – – – – –
f6aee78f-c149-521d-b195-e1a5010f7292 | note | CATEGORY: HP*
34cf2938-d5e6-535f-afc1-0477abb95559 | note | – – – – – – – – – – – – – – – – –
752bddc7-82f6-5f35-9ce7-10e7ae754737 | note | RESPONSIBILITY: PE/SPE
abbf31a0-f7f9-5da1-91bf-ddbb7deb2b8f | note | – – – – – – – – – – – – – – – – –
3627b31b-b6cc-5936-bfd0-ff5e60a2f675 | note | VERIFYING DOCUMENTS: This ITP
ddce8c90-b6a9-58fd-acc6-7797f8635757 | date | Date Completed:
| checkpoint | Final Inspection
0927ae82-0d62-5e42-887e-da772c788e52 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
46f07742-a894-558c-9d53-37f89eb49b2a | textbox | Name:
03fd852b-f6d1-5d0b-a5ba-1082c30f747e | textbox | Position:
2302becd-6551-58f6-8a4d-cb3b25790f67 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-017-STR-Structural Concrete Rev 0 | itp | ITP-017-STR-Structural Concrete |  | e3141fb2-2c58-41ba-b75d-43f2e0859876
| section | Referenced Documentation
| checkpoint | Referenced Documentation
8e3fd827-23da-528b-a230-20c3c2c89aaa | note | Document Title: ITP-017-STR-Structural Concrete
ddb77cab-ae24-54ea-8b73-23664de396f5 | note | ITP Description: Structural Concrete
19ed3a55-0a41-5052-93c9-179f2b029aad | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
a71119bf-b777-50f7-954e-ba2ca6de553e | note | Discipline (e.g. CIV/STR/RAIL): STR
d27bf423-c337-55ef-925c-671faa7f8e24 | note | Revision Number: 0
7317f4b8-8f41-5ea5-9237-f6eb860fc18a | note | Revision Date: 01/12/222
7669651d-bbbd-5ae7-9114-81e9e0410d7d | note | ITP created by: Victor Mira
26fa0fbd-f335-528c-b9c3-9d306cf79ddc | note | ITP approved for use by: Victor Mira
2305510d-d3cd-55ff-8a8a-b8aa1f3abe70 | note | 1.1 Non Dependent
08da34f5-e5fc-56b2-84d8-171ed92875b2 | note | Reference: VicRoads Section 602 October 2007
63be11af-f157-5dd6-a93e-b9bb7cfcdbbe | note | 1.2 Non Dependent
490e0a0e-0aed-5f32-b5ad-643122ae5b16 | note | Reference: VicRoads Section 610 February 2020
54abfd2a-61b7-5f50-8ce5-152fd9457965 | note | 1.3 Non Dependent
1ee8208b-c713-5ef4-add8-2767f3e36b71 | note | Reference: VicRoads Section 611 November 2018
777f1f43-713f-56d5-86da-bf51790f65ea | note | 1.4 Non Dependent
e6d5ca89-5bba-546d-9052-16ccb886f3e5 | note | Reference: VicRoads Section 614 June 2017
2c97e495-7c0b-510f-af7d-2475e4addfea | note | 1.5 Non Dependent
dc7d2331-3fd4-5d15-8c4e-2454a19e43a6 | note | Reference: AS3810.1 2018
| section | Preliminaries - Materials
| checkpoint | 2.1 Concrete Mix
e28f92aa-9a59-57ea-9ce7-d2e7aef3119a | note | REFERENCE: 610.07
dea212d4-5959-5eba-b529-23c27edde3fb | note | Table 610.071
10b8e4cd-0a94-5481-8200-da1ed91383b5 | note | IFC Drawings
59293ada-3eb4-5f21-8ac9-dde06e670471 | note | – – – – – – – – – – – – – – – – –
f43e83e1-2e53-557b-98b2-9b07173b66d1 | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
e009e038-bd8c-5b95-b3d7-f84f80614218 | note | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
53da3fd5-3a85-5a36-b29a-337d72ad46e3 | textbox | Enter: Teambinder Material Approval number
930101ee-f8f1-55bd-8fa9-41bc077285c4 | note | – – – – – – – – – – – – – – – – –
aa1dad1c-f88d-5cf9-b503-796b5acc197e | note | METHOD: Document Review
a136ba88-62ec-5b95-80fb-b15fc7f12936 | note | – – – – – – – – – – – – – – – – –
a1ce5216-c1d2-5982-9f87-e4842d3413dd | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
56a3f1a3-a17b-52d5-aede-c3528fb034d5 | note | – – – – – – – – – – – – – – – – –
ec0042a2-5207-593a-b6a1-c470888d5b70 | note | CATEGORY: HP
db4baf20-1c84-5615-9789-d376e1ee016d | note | – – – – – – – – – – – – – – – – –
c7aa5e4f-0423-58f0-ab25-008bcd2abd28 | note | RESPONSIBILITY: Nominated Authority
0ece13c6-b2e8-51e1-9bad-2195c28f44a5 | note | – – – – – – – – – – – – – – – – –
9533b8c5-605f-5568-be0d-359d8b6bfe98 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
957e21fe-1ede-523c-9325-3a7ecfefef87 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 ACRS Certification (for Reinforcement)
a8d2e2a4-10a7-5d7c-81cf-7909bfd4f53b | note | REFERENCE: 611.05 (a)
76414d22-7218-5f97-a553-af55ba5d3797 | note | – – – – – – – – – – – – – – – – –
13efe343-b8b3-5509-ac26-31ac3437b9b6 | note | ACCEPTANCE CRITERIA: Current ACRS certification for materials and for bar processing.
d2ae9937-e219-5feb-a6a9-1d4a1421af06 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
5cb1d591-587f-518e-88a5-62990b2535e1 | textbox | Enter: Teambinder Material Approval number
08d087aa-8b86-5eb3-8a19-7f5908b58ec3 | note | – – – – – – – – – – – – – – – – –
4816a714-e406-5c17-823a-5b42809879a3 | note | METHOD: Document Review
a8e54af3-af8e-504c-92a8-5c0489321ff8 | note | – – – – – – – – – – – – – – – – –
be907d7d-faf3-5ff2-a286-a62dc101a20f | note | FREQUENCY: Once for each supplier, 14 days of award of contract
eac016c3-5d03-5922-bbe2-20d9aff91614 | note | – – – – – – – – – – – – – – – – –
b7ffb5fc-e94c-56c4-a173-f00f8a90b621 | note | CATEGORY: HP
58c5d631-be7b-5655-b51b-b37623337383 | note | – – – – – – – – – – – – – – – – –
ed2d3bd8-1b9a-5cd5-a9af-b144361abab7 | note | RESPONSIBILITY: Nominated Authority
b1c067f9-3811-5b93-a4ba-2154b37300e5 | note | – – – – – – – – – – – – – – – – –
dfce3f5e-9861-5067-b266-dc9a58877520 | note | VERIFYING DOCUMENTS: This ITP
bf3150b8-95a6-50f5-988a-c62f3cea2894 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Bar Chairs/Aspros Certification
93390d74-08e4-5ba0-92b2-44e28bdf3c79 | note | REFERENCE: 610.26 (a)
c8c9abc2-8d8a-5f49-a53e-1b257209c261 | note | – – – – – – – – – – – – – – – – –
e150b8fe-9681-59b1-a4c5-4abc740133ea | note | ACCEPTANCE CRITERIA: Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
b45580ea-e7da-5ca1-9411-9f1de1547d17 | note | Concrete aspros require annual compressive strength and soluble salt testing is required.
aca9455f-93d6-53bc-8eda-13bd52895c08 | note | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
50c97631-a1f8-5bc9-bb2f-95f9ee1f6465 | textbox | Enter: Teambinder Material Approval number
7e0ce8a5-c86e-50ea-958f-302d1ef67595 | note | – – – – – – – – – – – – – – – – –
6429cf95-b3dd-59ae-a29e-7595adb1925d | note | METHOD: Document Review
61bfe108-e108-5722-935e-e925a2acdc46 | note | – – – – – – – – – – – – – – – – –
686085e9-944b-53c5-ba2c-abc0139a4b7f | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
dddf55f6-dc1c-582c-9603-1e70346bb9fc | note | – – – – – – – – – – – – – – – – –
439d1376-5458-5f4e-8b1b-f9de4fe1f213 | note | CATEGORY: HP
25d670b7-4ef6-5792-a8ae-f85bf491f22a | note | – – – – – – – – – – – – – – – – –
319654b2-d8a8-581c-92d4-57f406806404 | note | RESPONSIBILITY: Nominated Authority
cc6e72c3-2b30-5cf2-a20d-f087fc27d7bc | note | – – – – – – – – – – – – – – – – –
b3019efa-f86b-5a2b-b050-4199251b4170 | note | VERIFYING DOCUMENTS: This ITP
2256dceb-cc55-5596-aba2-956cab1bcd0f | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Evaporative Retardant
bdface88-9c2d-5e01-abe8-e01c981ba9ec | note | REFERENCE: 610.17 (f)
461affea-941c-54b8-842c-d4464821b93d | note | – – – – – – – – – – – – – – – – –
146e0438-0422-58c7-a7ed-a1f9d6e446b1 | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
f2b0775c-258d-5b1f-b82b-1430bbd7993d | textbox | Enter: Teambinder Material Approval number
3d1862ce-0d43-5e6f-98d0-d07fa8879b84 | note | – – – – – – – – – – – – – – – – –
96a42d5b-5a3f-517e-9358-cf3f9ea65347 | note | METHOD: Document Review
83ce725f-89fb-51d2-a3bb-3df3fad4d5d4 | note | – – – – – – – – – – – – – – – – –
1b71b441-9197-5f1c-87fa-089836e6975f | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
4ccf8a44-c78b-567c-8daa-02a3b0e3e7ff | note | – – – – – – – – – – – – – – – – –
2d8d8f4d-61cf-51a4-8b0b-d5129c245c4f | note | CATEGORY: HP
bf8c6b15-78f4-5232-86d3-79a5ba26f9bc | note | – – – – – – – – – – – – – – – – –
c15ad1f3-4b2b-5eff-baec-2c4c1b5d52e6 | note | RESPONSIBILITY: Nominated Authority
91dc398c-876c-5f76-9c7a-f8907b2618c4 | note | – – – – – – – – – – – – – – – – –
a3095cc5-134c-53b7-83c2-5c4383673433 | note | VERIFYING DOCUMENTS: This ITP
5e28b783-849c-5c8e-b66e-a2265d179f32 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.5 Curing Compound
4de5eff7-0d32-5c01-9622-ecb262814c2c | note | REFERENCE: 610.23 (d)
1181e2ab-ad63-5fd7-b7a3-b57bbf910e94 | note | – – – – – – – – – – – – – – – – –
13abb926-f58e-5644-af61-720f6e76f5e1 | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
e2aaa0a8-6e61-506e-809e-24861c32c781 | textbox | Enter: Teambinder Material Approval number
12eab585-9b5d-5a92-9a66-5d5a20b4129f | note | – – – – – – – – – – – – – – – – –
e76aa8e7-89c1-517a-af54-39498bf93674 | note | METHOD: Document Review
af2c0685-089f-5ec2-86e8-8af01b084c98 | note | – – – – – – – – – – – – – – – – –
706613e3-131a-5379-816f-50084d5fbfb8 | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
7622dcee-249b-5d2d-9db0-509b5fd6b3c9 | note | – – – – – – – – – – – – – – – – –
09fdde4f-b8ba-598b-891f-1cf52884df66 | note | CATEGORY: HP
f50f8fda-eb66-51ad-a14e-e4c10d73618b | note | – – – – – – – – – – – – – – – – –
7144d828-8804-5e92-b5f2-a72f622d3007 | note | RESPONSIBILITY: Nominated Authority
6f1478c8-cbae-51b1-9c95-1c802e1c0f4c | note | – – – – – – – – – – – – – – – – –
a35c1ea6-f6bd-551a-a861-777d09a8c120 | note | VERIFYING DOCUMENTS: This ITP
50f9c480-b986-5398-bb0f-6f811bebe065 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
1279a74a-8556-53d2-877a-3ce9537a2e67 | note | REFERENCE: 610.18 (a) (i)
1a6b49fe-28b2-59e4-b23e-53fac00476f0 | note | – – – – – – – – – – – – – – – – –
70f3573d-c374-5345-a00a-1ead12cd6f49 | note | ACCEPTANCE CRITERIA: Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
50c0dc0d-326f-5521-afe2-50da57368db4 | textbox | Enter: Teambinder Approval number
6e196461-0401-5c6e-bb1f-2834da31d05a | note | – – – – – – – – – – – – – – – – –
956c014f-643e-5af1-9a40-b4559ec738f7 | note | METHOD: Document Review
9fce6246-45f4-5514-8221-62b54de0a25f | note | – – – – – – – – – – – – – – – – –
b6e0aa30-92d5-53e5-9b41-c1195c3a2e12 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
73054d29-5293-5c1f-b549-11cc3e87353c | note | – – – – – – – – – – – – – – – – –
d14d3530-c2a5-5a50-b6fe-ce5408dc20f0 | note | CATEGORY: HP
71488272-e67f-55fe-84f5-1d5f61c681a8 | note | – – – – – – – – – – – – – – – – –
67a4cc33-9df6-5344-b0d1-9f33ca73dc90 | note | RESPONSIBILITY: Nominated Authority
ae34d12d-09e6-5d6b-bfa6-543c6291bbc9 | note | – – – – – – – – – – – – – – – – –
e2e2957a-f1af-50c4-b0f2-c453c0d28ac4 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
3ad41ef8-38ff-5a8c-a246-0594ba013757 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Concrete Sampling and Testing Procedure
d15b4003-1313-5860-baa3-c4ac11d89d15 | note | REFERENCE: 610.18 (a) (v)
24154d72-b622-5c02-8a58-08f1bbb242cb | note | – – – – – – – – – – – – – – – – –
60003287-8501-55b1-aed4-7930fba608c0 | note | ACCEPTANCE CRITERIA: Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
70ad205b-7867-5db9-a2af-0fa24aaffb3d | textbox | Enter: Teambinder Approval number
70664fc9-510f-5bd1-a90d-a3d44c0adc57 | note | – – – – – – – – – – – – – – – – –
7403751c-f582-55eb-8605-ecc11f3bf937 | note | METHOD: Document Review
5795eb22-edcf-54ca-9ab8-a9d35d48f9ec | note | – – – – – – – – – – – – – – – – –
9e5804df-c5ee-513b-adce-60604ae374a1 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
59803fd4-838d-5075-a9c9-906cb72e28ee | note | – – – – – – – – – – – – – – – – –
491fe38e-06a3-5921-8155-31a6e8fc8253 | note | CATEGORY: HP
aeddf62c-89d1-5392-836e-bd7be06b9332 | note | – – – – – – – – – – – – – – – – –
fa62beaf-b1c1-5b18-a09c-075738160596 | note | RESPONSIBILITY: Nominated Authority
6d00aa41-fbed-5a0d-9cb9-ccd6b97f535d | note | – – – – – – – – – – – – – – – – –
38c163f3-dd0e-528d-b3d8-2b7647988b0d | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
bfc56018-dc53-5df1-98cd-f6caf1f91c7a | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
7352ccb9-783e-5bdb-ad61-9f5c415e54fe | note | REFERENCE: 610.18 (a) (iv)
e06b6b06-c173-5ec9-8524-a772da335898 | note | – – – – – – – – – – – – – – – – –
f4f7722d-ab39-5468-a21b-c07a2b1ddc5a | note | ACCEPTANCE CRITERIA: Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
5744d018-b6f6-5cc0-8c0e-2944a80f08a6 | note | Minutes of this meeting to be submitted to the Nominated Authority.
95e60c3f-71c6-5d4e-80d3-b67e628c53ca | textbox | Enter: Teambinder Approval number
8e6f27b8-2002-5643-9cd4-52ac40caa189 | note | – – – – – – – – – – – – – – – – –
c40679e5-dca2-52eb-89f6-21f6d0f9411a | note | METHOD: Document Review
af3fa568-fa15-527f-a212-3c87f312b3d4 | note | – – – – – – – – – – – – – – – – –
a47f56c3-8191-51ab-a686-0b1cbe2e6467 | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
963f49e6-8a95-5b90-9164-cdab925313fa | note | – – – – – – – – – – – – – – – – –
a0277409-15d9-5efb-b3b1-0bdb1725d5ac | note | CATEGORY: HP
a1255b58-3696-5ecf-9561-b480144c34c9 | note | – – – – – – – – – – – – – – – – –
a88d7e20-dca8-5b11-ba3d-a6f2ab2ee239 | note | RESPONSIBILITY: Nominated Authority
d7bd0758-4bda-5c59-9062-c8ccdb24f4e4 | note | – – – – – – – – – – – – – – – – –
cfc2c948-1ede-5f76-8174-171f9be216a5 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
67802979-5b9d-5c5f-bb4e-8bda9c02e5c1 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
053f2459-b848-5d25-8a16-440e09ba448f | note | REFERENCE: 610.17 (a)
1ab5a6f2-c32c-5bb2-9946-cde730c70438 | note | – – – – – – – – – – – – – – – – –
d7e1a5e1-534c-5a96-824c-51e2c785194c | note | ACCEPTANCE CRITERIA: Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
e85da90b-9387-51c6-81dc-b65ceb1a4d93 | textbox | Enter: Teambinder Approval number
dbca611f-34b1-5e5c-a2f5-fa21a966fe71 | note | – – – – – – – – – – – – – – – – –
1cf78d76-8400-5ca5-92cf-ff7c3eb3a229 | note | METHOD: Document Review
55f752be-62a6-5804-bbcb-36760516dbf1 | note | – – – – – – – – – – – – – – – – –
738bfac4-b9b4-5329-9289-b11d632a16ec | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
1f2e4541-60ea-51ba-aa49-a6005eab86cf | note | – – – – – – – – – – – – – – – – –
436881c4-bcff-5314-b755-90fc96c7bcc8 | note | CATEGORY: HP
d73b70b2-acda-5ba7-8ebf-d8eedf4e2254 | note | – – – – – – – – – – – – – – – – –
a939d355-4db9-5e72-8a4a-34508f0dd9e8 | note | RESPONSIBILITY: Nominated Authority
0e450db3-5744-58bc-ad3e-c37f3a2738d0 | note | – – – – – – – – – – – – – – – – –
9cdc5357-18c4-5a60-9fd9-3f1a75aeab5b | note | VERIFYING DOCUMENTS: This ITP
0e5ee7c2-97d3-54f0-88da-1bac2e680a89 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
aeaab3cb-5b59-57fb-b5b8-91859e4ae6fd | note | REFERENCE: 610.23 (a)
996c6f9d-e59e-565b-9c27-735901e36e65 | note | – – – – – – – – – – – – – – – – –
5dcbfc79-48f7-5959-9957-6ff375ff5319 | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
2d89f432-b9bb-5ab0-98aa-79e4e512084c | textbox | Enter: Teambinder Approval number
26076933-0c81-5789-8d16-5f01c411aea1 | note | – – – – – – – – – – – – – – – – –
f0d357f6-2e40-5b41-bb72-0063047c9cda | note | METHOD: Document Review
516610aa-08a9-5e1b-9dce-1913b08c1ba0 | note | – – – – – – – – – – – – – – – – –
3a89eb44-6a5f-549d-975c-fca5224d5bea | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
70777884-b38b-5a7d-9823-d500a1e1adbd | note | – – – – – – – – – – – – – – – – –
90bb445b-1bdd-5ede-bd77-eca96c368263 | note | CATEGORY: HP
f9dcf478-2cd4-56e4-8254-a8f7893104f8 | note | – – – – – – – – – – – – – – – – –
b1c6f7e3-0a72-5a38-a0b9-52e1381f5254 | note | RESPONSIBILITY: Nominated Authority
98b528fa-ba26-5ed0-b1ec-968b597dc32f | note | – – – – – – – – – – – – – – – – –
e4d2362c-6e2c-5374-855d-deb74778d247 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
05cf3f72-892b-5f18-b037-ae0ac9ec6c29 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.6 Concrete Drilling Procedure
d939f2b1-3f05-585a-9607-5869372dedc8 | note | REFERENCE: 610.46
1890c4e1-ade9-5e1c-a9da-2886defad72d | note | – – – – – – – – – – – – – – – – –
57d605bd-39b1-575c-9241-b4f37e88a402 | note | ACCEPTANCE CRITERIA: Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
12119cac-e7a0-5edd-806c-59ab4ec54784 | note | The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
fb21f1ef-931b-5f21-af15-d787ec71af42 | textbox | Enter: Teambinder Approval number
708f735a-ec0f-50d3-9fa9-41c506eccffa | note | – – – – – – – – – – – – – – – – –
17e2f0b4-601e-591f-b3b0-48b97835d7e8 | note | METHOD: Document Review
9d08155b-9d49-514a-ace5-5ffc80ee2a8e | note | – – – – – – – – – – – – – – – – –
9a548087-9e39-5afa-bed0-aa38bbe11d9a | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
dab300a0-46da-5e71-b564-569a81d2a47f | note | – – – – – – – – – – – – – – – – –
904e9a32-aa69-5933-b0e4-f2d4bbdc1124 | note | CATEGORY: HP
a3849c64-daa1-5016-9d12-79f334e8c675 | note | – – – – – – – – – – – – – – – – –
3fbe237d-2d42-5f92-bc80-45aed66e01e7 | note | RESPONSIBILITY: Nominated Authority
6530dedf-219f-5120-ab37-a5f4d31c1493 | note | – – – – – – – – – – – – – – – – –
aea96922-6979-5921-a062-e25373c469e0 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
d87b7ffd-726d-515c-a00f-d2754174b612 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.7 Temprature difference measuring-Calibration
c0a17f4d-2828-58cd-a3f4-1f873e4fd84a | note | REFERENCE: MRPA Quality Management Plan
26bc0725-2e99-5214-bf52-55a79b2c0df8 | note | – – – – – – – – – – – – – – – – –
7aed2314-7767-5961-b739-77f7a9616917 | note | ACCEPTANCE CRITERIA: Calibration records are valid and up to date.
60df07da-5b5a-5c44-8843-6ec8a27a1dda | note | Attach: Calibration certificate
7d8cd0f6-f494-546f-9ddc-6a63ecda251d | note | – – – – – – – – – – – – – – – – –
8fb08665-1d6b-5df3-b8f8-d70c9b4e3ace | note | METHOD: Document review
a6a94883-741f-543a-826e-ba2f3a5522bd | note | – – – – – – – – – – – – – – – – –
4921e93c-6c33-5bba-b814-efd4b1b1161f | note | FREQUENCY: Where applicable
dafad8c0-5920-55ef-9798-b9ab7af53982 | note | – – – – – – – – – – – – – – – – –
f12b12cd-3b1a-520c-a62c-7043de3116bd | note | CATEGORY: HP*
8cac72b0-ce6d-51db-894a-266de7def5e8 | note | – – – – – – – – – – – – – – – – –
7b9675a5-5e75-501e-aebd-8162ead7e5a8 | note | RESPONSIBILITY: PE
fbd45182-2226-5704-84bc-76cad26ed27c | note | – – – – – – – – – – – – – – – – –
ed27b032-1b17-5794-94d6-3c76d7a8c8bf | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
1d098dbb-0616-5f70-8b4b-d4b86a9e4352 | date | Date Completed:
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
484ddb9c-9df2-5ec2-be72-b07985c0693b | note | REFERENCE: MRPA Quality Management Plan
0898020f-0efb-5a74-92ed-eb23789329d6 | note | – – – – – – – – – – – – – – – – –
8041162f-51c3-5a76-9ff7-d53f15e5a3fc | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
838ecba3-356c-567a-b302-710fad01da0c | note | – – – – – – – – – – – – – – – – –
5134b801-6ee4-5bcb-9f5c-17ed8c32c8a9 | note | METHOD: Document Review
810fc4a5-badc-5337-86c2-c22f617bcc5b | note | – – – – – – – – – – – – – – – – –
f64ac3f8-4b91-5e82-bffc-4718a0ece842 | note | FREQUENCY: Prior to starting Works and at regular intervals
552841af-76c5-577c-912f-da2109a05bbd | note | – – – – – – – – – – – – – – – – –
2f218139-da7a-569c-86bc-1cac29c1f8ed | note | CATEGORY: HP*
9efee202-e59e-5409-8666-6b97e79ab3bc | note | – – – – – – – – – – – – – – – – –
9f124fed-59ed-5782-9f73-d44c405581fc | note | RESPONSIBILITY: All
5333c8bf-6e42-5196-8b39-9ce3e957ca82 | note | – – – – – – – – – – – – – – – – –
99b1c984-3ce3-5528-bdda-52511292a083 | note | VERIFYING DOCUMENTS: This ITP
e16690cf-be5b-5b3e-9d1b-8137dae0eebc | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
1c5306f3-0827-5e92-9647-5333aea5f7be | note | REFERENCE: IFC Drawings
a80221e0-060d-575b-970e-d13c62108266 | note | 610.47 (a)
f28b5b6e-21d1-5572-9643-09bcf4008feb | note | Table 610.472
6e8d9b3a-0421-5abb-857b-57a12ff1d656 | note | – – – – – – – – – – – – – – – – –
d3635884-03d7-50fe-b3d7-413c4fb5c393 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
564b06e1-8888-5182-b660-98c444bb5249 | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
23114c33-b0a6-538b-aa40-c7c4337d4d6d | note | – – – – – – – – – – – – – – – – –
bcb50610-65fb-5371-a8e0-786b7935b8d2 | note | METHOD: Measure, Visual
89f2d7fb-bbe4-5b8b-ac1c-1cba285c135b | note | – – – – – – – – – – – – – – – – –
4f019e30-f98d-58ef-ab06-971910e8dbbf | note | FREQUENCY: Each element
e3f77f27-77ad-5f82-bf51-1937c59525e3 | note | – – – – – – – – – – – – – – – – –
17641360-f11e-59cd-99c9-770046df4dcb | note | CATEGORY: IP
4c2cf59a-adf7-5cf9-8b25-7785e5325fcc | note | – – – – – – – – – – – – – – – – –
3b7649a4-7496-5f75-8ff6-0fb81516df67 | note | RESPONSIBILITY: Surveyor, SE/PE
25ddacde-f8d2-5ae4-8415-a98edbce3067 | note | – – – – – – – – – – – – – – – – –
b6a70018-069d-5b4e-9832-2ccaa43023c8 | note | VERIFYING DOCUMENTS: This ITP
fbbcb94e-a78d-5511-a99b-afcc5d5a40f6 | date | Date Completed:
| checkpoint | 4.3 Excavation support
904c053f-6cbc-5c7c-b30f-e8399fe690ca | note | REFERENCE: 602.02
24389be5-15c1-5567-9c5c-abe99d66405b | note | – – – – – – – – – – – – – – – – –
3410e730-c35b-5b1a-98ff-f21bf4cf5405 | note | ACCEPTANCE CRITERIA: For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
15829932-e27c-5deb-b5de-ebd1c439020b | textbox | Enter: Teambinder Approval number
c3d1d254-66e7-5192-9ecd-1ec39f46dae8 | note | – – – – – – – – – – – – – – – – –
8beb6976-cc51-532a-8b62-1caf289e1bb4 | note | METHOD: Document Review
0ff1aac9-4d88-5211-b019-5ed4439f13dc | note | – – – – – – – – – – – – – – – – –
5931ee51-006b-57a0-ae8a-c496d721f1bb | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
10583164-ca17-5d5d-9c98-11334a4984e5 | note | – – – – – – – – – – – – – – – – –
9ac2b9c9-9ed4-512b-a249-ffed687a3ee9 | note | CATEGORY: WP
d17a20e1-6342-55bd-a318-32dc84173300 | note | – – – – – – – – – – – – – – – – –
ac57ad92-eb0d-5f9f-9380-89982a3afc51 | note | RESPONSIBILITY: SE/PE/SPE
c4949eed-ea98-5a34-adaa-843e02b5ec5c | note | – – – – – – – – – – – – – – – – –
2657fdab-3aef-5043-bee9-a33407f5903b | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
521e3b54-d3db-5dd5-9b62-7db1a3fb08f3 | date | Date Completed:
| checkpoint | 4.4 Excavation Inspection
77ba54a1-62b7-57a8-88b1-2c2f81741d40 | note | REFERENCE: 602.03
0d36f603-b3e4-598d-ba51-e469cb535302 | note | – – – – – – – – – – – – – – – – –
db3e7228-1095-5324-988b-d7fa8a061702 | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
7f0c91c5-b464-5924-8d09-2cf603440bd7 | note | – – – – – – – – – – – – – – – – –
f9a2b4c4-84fb-5175-849d-620d53053683 | note | METHOD: Visual
c8f0986e-3a73-5dfb-802b-f7508e53817e | note | – – – – – – – – – – – – – – – – –
4bde44ca-5948-54c8-9630-13aadf5e7b0e | note | FREQUENCY: Where applicable, prior to placing blinding concrete
b81c9885-a7d8-5d48-88f6-2d78247ff639 | note | – – – – – – – – – – – – – – – – –
68a0a414-d66d-58eb-bb28-8ecde8b41c16 | note | CATEGORY: HP
e1072d2a-5857-55c1-86e8-5d40f2fafcdd | note | – – – – – – – – – – – – – – – – –
9e0be892-9fea-5a80-9075-5395659b7568 | note | RESPONSIBILITY: Nominated Authority
77061b3a-202a-55e4-96b2-f98cd5f7fec3 | note | – – – – – – – – – – – – – – – – –
719aa59b-927a-5316-a54d-cdc5a6e4ba8b | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f844dc06-d51a-5b9d-b1be-0b75954dd1a9 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Construction Activities
| checkpoint | 5.1 Formwork Design and Construction
df508126-df03-55de-9dc7-e917273da6fd | note | REFERENCE: IFC Drawings
b38c5740-963f-5915-bf81-85c37671ddd9 | note | 614.04
ee42a8e1-1f3c-5a03-83c6-41145d150548 | note | 614.05
f567aaec-0c24-5a22-8f7e-52589e7d8d1f | note | 614.06
3caa1a5a-a3d9-55f8-9f4e-bec2edbb2555 | note | – – – – – – – – – – – – – – – – –
c7ef406f-a6f4-5b51-8d2e-3d53976d06ac | note | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
3bc45c19-668f-571f-a391-446edf3a3895 | note | Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
a383ad9e-36cf-5976-adfe-b7470ba05dec | note | Formwork shall not be placed where steel & fixtures cannot be inspected.
27408afc-a169-50ec-97ad-647d0546f1b1 | note | – – – – – – – – – – – – – – – – –
d6e409c2-c358-5d19-95d6-c347d43197e8 | note | METHOD: Document Review, Visual, Measure
51ac8429-8e91-5af2-8aca-f058537b7271 | note | – – – – – – – – – – – – – – – – –
bded8db6-9635-5d56-b8e9-1562f9763c5c | note | FREQUENCY: Each type of element
38929a71-ddfa-5af7-b017-9b7f0892c384 | note | – – – – – – – – – – – – – – – – –
734d4cb7-88df-5707-98ef-43f64277d4e6 | note | CATEGORY: IP
8c5d9459-e071-5f72-9581-acdbf98f12bd | note | – – – – – – – – – – – – – – – – –
c3690a0d-e755-58fc-8c64-301b0d58bfdb | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
de4b26da-e0e8-50b1-8179-7880899f6466 | note | – – – – – – – – – – – – – – – – –
013b090b-405e-5cbe-9d1d-1ba5eca7a4b9 | note | VERIFYING DOCUMENTS: This ITP
518f3b6e-e040-5348-923e-5b1cc53843d5 | date | Date Completed:
| checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
061b38fb-f38b-5cea-b7f5-9a6447b80ba6 | note | REFERENCE: 614.08
0211cb3f-5527-5fe0-b8d7-8df027e9df67 | note | – – – – – – – – – – – – – – – – –
4f460a87-ad96-5921-9148-2c9e95138c11 | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
5153db0d-789b-55e0-94d5-1b8d87e19518 | note | Walls with heights greater than 2.0 metres
70f06a8d-a79b-5084-8973-09102217f7f2 | note | Any member for which self-compacting concrete is proposed.
cbbfcc69-8ade-5ec9-b7af-d488a02b8182 | note | Attach: Attachment A
b82b8523-4d5e-54be-9297-56b372eff5a8 | note | Attach: Attachment B
45f5be41-fb7f-5bfe-8708-ece88e53d8dd | note | – – – – – – – – – – – – – – – – –
099d63b1-bb8e-5bd8-9894-99a840c742c3 | note | METHOD: Document Review, Visual, Measure
4ac4ba6d-1b8a-5012-b8d1-362dd30bfec5 | note | – – – – – – – – – – – – – – – – –
9288b58f-a85b-5a28-b977-8bdf03542080 | note | FREQUENCY: Each element (where greater than 2m)
4253c34e-de27-54fe-a8e4-6959d50fb70e | note | – – – – – – – – – – – – – – – – –
be74cd59-491c-5f82-b2d1-2904f0821918 | note | CATEGORY: HP
4f805b79-2a5c-59ae-8011-4a0917dc70b3 | note | – – – – – – – – – – – – – – – – –
7eabee06-a0ee-5892-91d7-d06bdde4268b | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
27692f3f-cc8a-5cf7-be77-c3cc6ede941b | note | – – – – – – – – – – – – – – – – –
cf40508c-6e96-571a-a967-549638fc52c0 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
5a39844b-3af2-53fe-a186-bffa7069e074 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
81590773-c3e0-5f9f-8f70-1aedb0dc4cd9 | note | REFERENCE: 614.08
d3e4a654-7fa2-5e06-9493-d430e35696cc | note | – – – – – – – – – – – – – – – – –
e518c732-8684-5400-a242-6de484f83138 | note | ACCEPTANCE CRITERIA: The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
c23600f5-99cc-59da-bf7c-cb0363ae8e61 | note | Walls with heights less than 2.0 metres
735d7eb7-4283-5e49-9faf-af6904e9db28 | note | Attach: Attachment C
7f8518a1-f063-5121-bc12-239c6c26fc50 | note | – – – – – – – – – – – – – – – – –
f49a152d-66e6-5420-9710-431fcbc4ea6e | note | METHOD: Document Review, Visual, Measure
4c3eca97-c7af-5b36-9f86-0649294ba72a | note | – – – – – – – – – – – – – – – – –
57fd4e3f-0a7c-52ea-8c7c-1eb5f281a553 | note | FREQUENCY: Each element (where 2m or less)
2005cccd-59be-552e-a1fc-450a7119ddf3 | note | – – – – – – – – – – – – – – – – –
f2fde8fe-94b1-5c5a-80b6-d9d2b3697052 | note | CATEGORY: HP
7584a341-3735-5c0c-8bfd-bc261337cf28 | note | – – – – – – – – – – – – – – – – –
4a7407be-263d-588d-b4da-46cf3b410a5e | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
60828a6d-49e3-5317-891b-e7515b0726e5 | note | – – – – – – – – – – – – – – – – –
1b707cc0-5c6e-5549-af65-32c6f1228a29 | note | VERIFYING DOCUMENTS:
1b34035d-4774-5406-b6df-77f51c7fc65a | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.4 Pre-pour Survey
b4caa24c-06a6-5ad8-9f0b-6e93e29012e1 | note | REFERENCE: 610.47 (a)
f9d3ba54-67c5-5d7a-8884-e9bfca5573c7 | note | Table 610.472
93be031d-2bb3-5cbe-b539-93c0ab0ba2ba | note | – – – – – – – – – – – – – – – – –
eb1879dc-ad72-5cb1-a877-1def691dd182 | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
e0fd125f-a35d-5843-86de-6fcbefb52125 | note | Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
0a333e07-5b62-54bf-865e-c8243f422220 | note | – – – – – – – – – – – – – – – – –
b8f1e137-f995-5f9a-848d-8c3f5bfbc9b7 | note | METHOD: Measure, Visual
71ca8da0-7896-5662-bb93-e5bdda42e4d6 | note | – – – – – – – – – – – – – – – – –
1930a77a-45fe-5a7e-9f50-c555d5e684d2 | note | FREQUENCY: Each element
fb782291-cdbd-592b-8384-3675a10595af | note | – – – – – – – – – – – – – – – – –
8a4a7feb-46d9-5951-9cd3-91f44c85d63f | note | CATEGORY: HP*
4a9c585b-e712-5bd1-a421-d845335d1431 | note | – – – – – – – – – – – – – – – – –
fb277d69-2c14-5c38-ba40-22c68003c070 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
3436026b-5eb8-578a-b58e-e62ecb500761 | note | – – – – – – – – – – – – – – – – –
b9967146-58ee-567f-87de-82abc4b6da37 | note | VERIFYING DOCUMENTS: This ITP
62bea4a4-a0dd-5d19-a9b6-0cd7d098d8e4 | date | Date Completed:
| checkpoint | 5.5 Reinforcement Placement
d6dccae4-7b33-5aad-a62e-48f29e49aa15 | note | REFERENCE: IFC Drawings
6451313c-4b37-5a4e-b6a1-492320221bf4 | note | 611.06
9248db9d-23c2-57b1-b1ce-862c5898a764 | note | 611.09
1fa376b1-fb4b-552d-9c3c-ce8c764868da | note | 611.10
f7e785fc-fd60-5136-a785-4136ae37ad56 | note | 611.11
ab7951a7-859d-5b2a-8516-deb512da6b88 | note | 611.12
fbabbb77-7170-5df8-bb5c-aadf5c887259 | note | – – – – – – – – – – – – – – – – –
06126771-7065-553d-9de9-ce2bfd6b4648 | note | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
ec377d9a-cfa1-5809-8069-931254a1aa14 | note | Projecting reinforcement is the correct length and location.
d02bcee6-9b21-549d-aa14-ab0c22d1b5de | note | Splice lengths achieve the minimum length and are in contact for this length.
a5cb2ca4-d055-5635-a707-b0e23852fd7f | note | The reinforcement surface condition is free from dirt, debris and damage.
d7d7d7e5-626f-5517-9cb3-77049d4aa078 | note | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
af88c269-37f0-59ed-9dae-0151da6e722b | note | Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
ef5257f1-b8db-5b08-8ebc-44aef9c37e46 | note | – – – – – – – – – – – – – – – – –
1c93f0e7-429d-5823-a40b-f97a1aba5620 | note | METHOD: Measure, Visual
883f47e5-4c2c-5178-b63a-79d9e0d1f4f0 | note | – – – – – – – – – – – – – – – – –
d6912561-00d5-5ca9-8818-8d09c5fa3af0 | note | FREQUENCY: Each element
8177105c-486e-5e10-8822-2c30326e2252 | note | – – – – – – – – – – – – – – – – –
943de708-1c4e-5455-890e-2d165e7849e2 | note | CATEGORY: IP
9b0f6a76-dab4-50cf-bb2b-70b056c06dc5 | note | – – – – – – – – – – – – – – – – –
f8a12c13-3c09-54a1-a537-6dba40e968cd | note | RESPONSIBILITY: Foreman, SE/PE/SPE
56c69621-de60-5e0c-820a-49197f055bd2 | note | – – – – – – – – – – – – – – – – –
be130ce8-d549-540d-9879-b727c8d7519c | note | VERIFYING DOCUMENTS: This ITP
d48c78fc-1c99-589f-82a1-c4ba3801c5b4 | date | Date Completed:
| checkpoint | 5.6 Cast-in Items
84041649-23ee-5410-8bf7-39dc4da1587c | note | REFERENCE: IFC Drawings
a596d7a7-132d-5f17-9482-9a1661b0dacc | note | 610.47 (a)
64e229b1-4aec-5e79-9f75-b41b2546b536 | note | Table 610.472
6daaca2e-a81f-59d9-b629-9c488ccffafc | note | AS3810.1 Table 3.3.6.2
2551a06c-6504-5da4-9201-6cb3e774f763 | note | – – – – – – – – – – – – – – – – –
f07d0b11-fa8f-5390-b9a1-22bf28b6f272 | note | ACCEPTANCE CRITERIA: All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
d38c5733-8f95-51af-bb38-e7d60122af63 | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
af27a9c9-19a2-563a-9861-13326afc70e0 | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
882863b6-7b7b-56ae-a0ac-2758e5b78da4 | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
dc31d82c-ea72-5d44-a7b5-9d7d86588539 | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
5c803560-68ca-5811-b1a3-6343c3db495f | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
3ad85b61-a534-5820-8b55-ffac04ec96ba | note | ii. Running dimensions of a group of the above = ±6mm
18089280-70cf-562c-9e86-3080c9ecf583 | note | iii. Ducts and conduit location = ±12mm
4ef6cbf7-8b0d-5962-910c-b50ca0a3e688 | note | iv. Diameter of ducts and conduits = ±3mm
59a5b23d-8725-5743-99b6-600ccf46cc51 | note | – – – – – – – – – – – – – – – – –
e7dfc1a4-66ca-5cf8-b1cb-1849f24d824c | note | METHOD: Measure, Visual
dac1194d-5fdb-5163-8268-0055dc5de6da | note | – – – – – – – – – – – – – – – – –
8130799d-0e50-570f-b0d6-712c1a7e771e | note | FREQUENCY: Where applicable, each element
c09022a2-cd5e-5bb6-844c-f72207c5d744 | note | – – – – – – – – – – – – – – – – –
3b1ee683-0d34-578c-9a58-c568eff4685e | note | CATEGORY: IP
96ba585c-df75-567b-9558-cd84f4a99663 | note | – – – – – – – – – – – – – – – – –
8b3ef175-f45c-5030-b2c8-4d19e3857a52 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
5e0cb299-050c-5053-9633-05692da1a623 | note | – – – – – – – – – – – – – – – – –
1386f2c8-5202-5a14-b71b-d94c228984d0 | note | VERIFYING DOCUMENTS: This ITP
a8dd6890-0a79-5271-96bc-b6eb20b357a0 | date | Date Completed:
| checkpoint | 5.7 Thermal Differential Monitoring
b9048bd2-b0cc-5cae-b3a5-52224fc16194 | note | REFERENCE: 610.22
b3a723a5-891f-593e-934b-3eff75f700b3 | note | – – – – – – – – – – – – – – – – –
2afc67d2-6093-5b71-b4fd-138a6ce7b569 | note | ACCEPTANCE CRITERIA: Thermal differential monitoring thermocouples installed.
93fdf2a0-6a9e-5d1b-a37e-79a9a8891d71 | note | Only applicable if the element has:
c629eb98-09f3-524e-b86e-4af61cf5e7a3 | note | i. the smallest sectional dimension exceeding 500mm
09afb03e-87dd-5ca6-a1b1-6802b319d663 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
b69e6fb3-146f-5fc6-8512-1c60238c023a | note | – – – – – – – – – – – – – – – – –
8bd6f450-a23a-5b9e-8f3f-2dd6fdb4686a | note | METHOD: Measure
c3d9caac-416b-5080-bb85-5df5fddcd1a3 | note | – – – – – – – – – – – – – – – – –
ae665e32-3038-5026-93df-c57f4e3ddbf0 | note | FREQUENCY: Where applicable, each element
8297fe8f-5137-5b4f-9db2-5e0daa14b098 | note | – – – – – – – – – – – – – – – – –
4ef6f72f-1a03-5f6b-92f4-d9342c3b6532 | note | CATEGORY: IP
4eaf2c27-cbb3-53be-b5df-44a05ed39eea | note | – – – – – – – – – – – – – – – – –
ec5ffcda-f53c-55b8-b52b-e54bccae0151 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
18f33142-039e-592e-bfdc-ea6937bc4fae | note | – – – – – – – – – – – – – – – – –
fad4c05b-ee84-59cc-81e9-fa645f3fed31 | note | VERIFYING DOCUMENTS: This ITP
7a5fce71-5601-5752-ad62-a1886a29b346 | date | Date Completed:
| checkpoint | 5.8 Pre-pour Inspection
8db47cad-b2dd-5b9f-807c-977b666181e5 | note | REFERENCE: IFC Drawings
ec933c09-31b9-5e8e-baf6-7395f9efe2e8 | note | 610.18 (a) (ii) & (iii)
d43f409f-0772-5038-80d9-d37893b35d2e | note | – – – – – – – – – – – – – – – – –
983450f6-5ab4-5911-b5d2-b02c58b59ee2 | note | ACCEPTANCE CRITERIA: Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
5965816c-524d-5c5a-b165-d1c8ecb7430d | note | All foreign material has been completely removed from the forms.
44528149-f3d7-5308-867c-e1dcb4067d4a | note | ATTACH: Pre-Pour Checklist
5e4e4a69-fa05-58ae-9e7c-bdcf5d6bc88a | note | – – – – – – – – – – – – – – – – –
d2aa50d0-22d5-5c30-8e96-b1f8b6ce5af0 | note | METHOD: Measure, Visual
f31f5f94-0972-52a0-b5ca-de7a88bcff95 | note | – – – – – – – – – – – – – – – – –
9bca5061-190e-5859-9eec-cfb16858f685 | note | FREQUENCY: Each element
bbcc6701-decc-5cbd-9e2e-56dde231ad46 | note | – – – – – – – – – – – – – – – – –
977321dd-e8b3-5c5b-b4fa-5c4fc782df1b | note | CATEGORY: HP
40cbbd0d-e137-5f88-802e-b9f5c5bb14fc | note | – – – – – – – – – – – – – – – – –
ac271235-e75f-509f-b061-8ca9ef8692ac | note | RESPONSIBILITY: Nominated Authority
7eebb606-fd87-501d-90c2-c9746c216f23 | note | – – – – – – – – – – – – – – – – –
a52540e2-91c4-5015-b8d0-e5abd56c1a24 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
2f628d87-a7d4-51dd-91ff-a406fbac93c0 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.9 Weather Conditions & Evaporation Limits
9fe01274-f36d-5521-b460-10c4a01ec00e | note | REFERENCE: Hot and/or Cold Weather Concreting Procedure
c269f485-5a56-5699-bf4e-a4ff274f2f0f | note | 610.17
96850a35-7fbb-51f0-b6df-306edae96f0a | note | 610.17 (a) & (e)
32dfba0c-7321-5507-a37c-0d1287202c13 | note | Table 610.171
0339cea9-0e8b-5c38-a7ea-039b8255ff76 | note | – – – – – – – – – – – – – – – – –
65bc0234-daf6-55f7-8864-195a0cb88cf3 | note | ACCEPTANCE CRITERIA: All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
074b48bf-b3a8-50d3-9696-1c4d223de788 | note | The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
4d7fe576-a6e1-5532-9139-aa4d477d7447 | note | The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
314c7612-6612-5ae7-8ad6-30ef1c7b1488 | note | When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
03e7681e-389e-5c2f-8c2e-9be54b4413af | note | Record: Required information on the Concrete Pour Record.
e375881e-fa2d-56bb-add6-cec2a014441c | note | – – – – – – – – – – – – – – – – –
e438a60d-3ece-5f1f-aff7-481ec3a1059c | note | METHOD: Measure, Visual
b6330181-f656-566c-93f0-231a20c1a3b6 | note | – – – – – – – – – – – – – – – – –
d80d8457-6a72-51ef-9b52-4af193161e1b | note | FREQUENCY: Each element
645ee66f-057b-50bd-9e01-1f83058bfa59 | note | – – – – – – – – – – – – – – – – –
d29882e4-077b-5f19-9283-ec0f3557d301 | note | CATEGORY: IP
65b9dcc5-9f2d-5c6f-b966-a2f28ed2cdc6 | note | – – – – – – – – – – – – – – – – –
20aab4b0-1bf0-58e5-ab6d-39ea7c516fce | note | RESPONSIBILITY: Foreman, SE/PE/SPE
fc615046-c160-54f2-b1d9-7fcfb2f24d25 | note | – – – – – – – – – – – – – – – – –
ae25125b-3a8d-5631-bbe4-653f6203c047 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
a7f152c9-44bd-541c-b9f1-9e6072342fe2 | date | Date Completed:
| checkpoint | 5.10 Concrete Testing - Sampling Frequency
560d4a4f-8786-54c9-ac72-f83f8033883e | note | REFERENCE: Site Sampling & Testing Procedure
7adfc62e-cf3b-58cf-b70c-ea9c13013670 | note | 610.16 (b)
e594c7b8-e6b7-5c90-a6e6-eab3ff082e60 | note | – – – – – – – – – – – – – – – – –
13c1a868-dcb1-5c12-9ff0-a94db1a30dd3 | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
1b5b1cc1-cc95-544b-ab26-73841cd13c5d | note | 0m³ to 10m³ = 1 sample
3c543000-86c5-5a2f-af45-f13212d4a7eb | note | 10m³ to 25m³ = 2 samples
78485189-1b32-54c6-aff1-fd815c36a918 | note | 25m³ to 50m³ = 3 samples
b23e5365-25ca-52c2-b6fe-291a4232e88e | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
aa7b88f3-0ae5-52a0-b907-3c654d84fb47 | note | For each additional 50m³ and additional sample shall be taken.
cd7ed898-1d67-5854-aeba-b2ab95b80e59 | note | Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
ef989076-f543-5af5-abaf-ccfbdfde981a | note | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
1bebe5d2-f2a9-542a-a3c8-f3e6d1d444d2 | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
9ab2f6f1-9768-543b-b4b1-e2869403f6cd | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
8631f722-90dc-565b-afc0-5495456dc844 | note | Record: Required information on the Concrete Pour Record.
e22f0793-6332-5164-bd0c-6177e586170e | note | – – – – – – – – – – – – – – – – –
11c59a03-f559-5961-a79d-c18dc26971bd | note | METHOD: Test
1e9e82a9-aa46-5536-bac4-4b31b5df66be | note | – – – – – – – – – – – – – – – – –
c3953fbc-f991-5cfa-ba7e-d49d00e2ce75 | note | FREQUENCY: Each element
ec2f2926-6c37-5738-9162-85a0433e0a3a | note | – – – – – – – – – – – – – – – – –
c6ba9ea8-39b2-5aad-aa5a-f4e44bf06949 | note | CATEGORY: IP
d8750f8e-2e11-500d-857c-4a85e41d4fd0 | note | – – – – – – – – – – – – – – – – –
a8b78777-08c0-5d2e-aecb-87d0592eb475 | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
c530e118-6517-506e-bc6e-30a0a3ca6b1d | note | – – – – – – – – – – – – – – – – –
38f613b4-af5a-5a09-806a-b7fa6add4c88 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
cd3bcca3-929a-5079-a87d-6b499172e55d | date | Date Completed:
| checkpoint | 5.11 Concrete Testing - Slump
64c01566-c04c-5f6a-9dd4-e26ac36d6810 | note | REFERENCE: 610.16 (c)
d9a0dd26-c4ad-561a-9138-21707149485e | note | – – – – – – – – – – – – – – – – –
de4d3d82-5ac4-5e8e-bbff-526b7008e11d | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
d4323dc2-5f54-5d63-95c8-185702c2ea5f | note | <60mm = ±10mm
cfc3baf2-49f6-579d-8325-d54e8974c6c6 | note | ≥60mm to ≤80mm = ±15mm
1d6fe1b5-3fe5-5d95-b8df-332fcd5c10c8 | note | >80mm to ≤110mm = ±20mm
d7a211b8-8cd6-57c0-b1a8-3199d27a346c | note | >110mm to ≤150mm = ±30mm
47a10d6f-ea70-5d24-abd9-096d2187d265 | note | >150mm = ±40mm
db5f4dee-77f2-52b9-9682-268e973b8f18 | note | Record: Required information on the Concrete Pour Record.
61f935c2-ede2-509e-b9fa-8e5b988d211c | note | – – – – – – – – – – – – – – – – –
9d5a27f1-ddca-56ea-a128-b179a346353e | note | METHOD: Test
3a1471a5-3292-5d32-bc09-e338e8021770 | note | – – – – – – – – – – – – – – – – –
b4bdb9dd-5a40-5fc5-9302-fed8ce6934dc | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
b776b619-6ca4-50ce-9109-e165dc06eb82 | note | – – – – – – – – – – – – – – – – –
6134328a-d79d-5099-92cf-6b4525d414e6 | note | CATEGORY: IP
bfa9c7f6-fa98-5c20-8a2f-9d8b96079f1d | note | – – – – – – – – – – – – – – – – –
6c83d0d6-330e-5730-9f2e-30edb6e9d3f7 | note | RESPONSIBILITY: Concrete Tester
aa56be29-08a9-5246-94d0-4eb1f4bfd0c8 | note | – – – – – – – – – – – – – – – – –
360f82ac-1493-5718-81fe-d7aaebfc21c9 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
a6dfe133-bd79-57da-9d70-d22414fb8822 | date | Date Completed:
| checkpoint | 5.12 Concrete Testing - Spread, Passability & Viscosity
bf1c99da-cb88-5fdc-b90c-3c634160e78f | note | REFERENCE: 610.13 (b)
b7401421-45f5-5854-97c6-822978115d2f | note | – – – – – – – – – – – – – – – – –
101dd398-f795-5679-8e3f-4a3e030fbed9 | note | ACCEPTANCE CRITERIA: Spread range = 550mm to 750mm
c6b480da-2fe2-56d9-ab96-4bc0884d76ba | note | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
b468041d-69df-5471-a4d0-02cc27e30801 | note | Passability = ≤10mm (aggregate height differential)
a6141834-71a4-5ef5-ac9a-6f12cbd5b583 | note | Record: Required information on the Concrete Pour Record.
04cb53de-530d-506c-acec-327618ae71ad | note | – – – – – – – – – – – – – – – – –
caad693e-1a92-5142-8983-ab50913c0465 | note | METHOD: Test
125f3d1e-00e5-5fa9-8202-18331aa82e78 | note | – – – – – – – – – – – – – – – – –
895dae52-b1dc-5e12-90a8-4efd9a3ddc46 | note | FREQUENCY: Each sample of Self-compacting Concrete
f6083c94-3c19-58ce-b7ca-f8164659a7e2 | note | – – – – – – – – – – – – – – – – –
bebb53b5-3449-56fe-98b8-09a8509a6644 | note | CATEGORY: IP
314daeee-e9e7-5597-97ab-8bcef5ceafb2 | note | – – – – – – – – – – – – – – – – –
ddd7a811-11d2-5686-9dd5-cae0a11294b7 | note | RESPONSIBILITY: Concrete Tester
fb4b3a4c-52f2-5a07-b783-cacebb883be4 | note | – – – – – – – – – – – – – – – – –
a4124beb-96c1-5b3a-bd71-81ac7de70093 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
9f1b720a-1fef-536e-bfd3-99e6b50af669 | date | Date Completed:
| checkpoint | 5.13 Concrete Testing - Compressive Strength Cylinders
6ed3690f-f708-5983-9af8-f944fe5dd2ed | note | REFERENCE: Site Sampling & Testing Procedure
1af961f9-0980-53bc-b0c9-8e1a324fc994 | note | – – – – – – – – – – – – – – – – –
18994062-959d-5a73-85ec-0a50d3247df9 | note | ACCEPTANCE CRITERIA: Correct quantity of cylinders manufactured per sample.
3ff88970-9ad6-537c-a593-dfbe000d6ad0 | note | Record: Required information on the Concrete Pour Record.
3e70ee77-105e-5f12-bb1d-6a2602d3902a | note | – – – – – – – – – – – – – – – – –
d9437383-110f-591c-9092-e228c92b7e73 | note | METHOD: Test
d7233b0c-efbf-5883-a58a-4829f87a7bbf | note | – – – – – – – – – – – – – – – – –
899f5e07-9838-5456-a47a-7e973daaffb9 | note | FREQUENCY: Each sample
72a43b43-8428-5b81-bbfe-0e90957ff5ce | note | – – – – – – – – – – – – – – – – –
a56b97d0-e3de-535f-bc74-36927d3bb7b4 | note | CATEGORY: IP
39db11b8-f1b8-54f9-8c59-b03b78ac0308 | note | – – – – – – – – – – – – – – – – –
9d5bf260-1b0f-51e6-970f-e379aa16fd86 | note | RESPONSIBILITY: Concrete Tester
f36f6d56-250f-5ed4-bf65-a959d236a3d2 | note | – – – – – – – – – – – – – – – – –
97201ca5-e6d2-51b1-b1ea-62b013df6e50 | note | VERIFYING DOCUMENTS: This ITP
f486caaa-1b5d-518f-8a77-31a35b466574 | date | Date Completed:
| checkpoint | 5.14 Supply & Discharge Rates
5129683b-5564-53d2-a4d7-c7b1b5a0140f | note | REFERENCE: 610.13 (a) & (f)
d2c9478c-3535-52c5-bda2-0dcd5798e695 | note | – – – – – – – – – – – – – – – – –
aeafeec6-7f86-5ea8-8229-e4f6b3f76d48 | note | ACCEPTANCE CRITERIA: Concrete is supplied at an adequate rate to ensure no cold joints are formed.
693dcb85-fe1d-538d-995f-6b00ece7b9f5 | note | No water is to be added once discharge commences.
d0f6a405-1e99-5381-92cd-7a8338ec1090 | note | Maximum time between batching trucks is 25 minutes.
6225b39e-4c01-5f57-a6c7-50287734669a | note | Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
bd642174-e45b-5982-8a44-1772c732809b | note | Concrete that stiffens or is showing signs of stiffening shall not be used.
559bdb20-2134-5d89-ad73-b88bae9d0bde | note | Record: Required information on the Concrete Pour Record.
cccd50d3-5b9a-5ff0-a9c9-8804c09a613a | note | – – – – – – – – – – – – – – – – –
e9885db9-8344-58ca-8960-fa7658cf750e | note | METHOD: Measure, Visual
68c11600-ab78-5682-83f1-5b8f0f468c4e | note | – – – – – – – – – – – – – – – – –
d247202b-c93f-520c-8292-dd577c13392f | note | FREQUENCY: Each load
386ef3e0-aeb6-5d0f-a9b6-adde72121f36 | note | – – – – – – – – – – – – – – – – –
ae43ab49-7b6a-51f3-bff7-121d750522cb | note | CATEGORY: IP
8dd7e9db-7c1c-53cd-af4e-657ad5548277 | note | – – – – – – – – – – – – – – – – –
8f3fdf2f-7bcd-53c1-9d5a-fdf85ee6f30f | note | RESPONSIBILITY: Foreman, SE/PE/SPE
a7bc5032-1047-5dd8-9c73-75972f9eda5a | note | – – – – – – – – – – – – – – – – –
97ad2ffc-60d3-5d52-afb6-fc043f2fbac3 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
bf387c79-c7a6-531e-89c8-f2327b21dd5f | date | Date Completed:
| checkpoint | 5.15 Placement & Compaction
ff4b2685-eb86-5261-8b43-2cef2da88a45 | note | REFERENCE: Placement & Compaction Work Procedure
42e6b050-a1b2-54a5-b332-e7a5f35513f0 | note | 610.18 (a) & (b)
53a092ca-b72b-5996-aa97-10602738faaa | note | 610.18 (d) (i)
144e1bb3-ca0c-5c32-b2fe-69e654aafa2a | note | – – – – – – – – – – – – – – – – –
3eac832f-3e39-530f-b21d-2151fdbeea13 | note | ACCEPTANCE CRITERIA: All concrete batches are traceable.
33eb829b-a990-54df-b6e5-f0cdd16e1eb4 | note | Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
86333b35-9482-567e-813f-41d12b009e6e | note | Concrete is not dropped freely from a height exceeding 2m.
89293af6-14c2-5104-b330-111ec9fb475a | note | Concrete is not moved horizontally by use of vibrators.
df02485a-6db9-5f7c-93e6-6723b815f962 | note | Adequate compaction is ensured
5d12c0d9-f3ac-5604-8423-084a77b9d2e2 | note | Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
f3fd8b4f-f214-57ba-9799-bbdebddf2103 | note | Concrete layers are not more than 350mm
3f860a61-9cc1-5fbe-ae8a-db1f2b1833ea | note | Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
775dea2c-4e10-56ec-a592-43c98b031c0f | note | Vibration continued at each point until air bubbles cease to emerge from the concrete.
9f7c274c-6422-55ef-a22e-8c0e402c7045 | note | Record: Required information on the Concrete Pour Record.
c9c73189-6771-51ac-a3d0-b0c2afcaf44b | note | Attach: Concrete Pour Record
d26dff16-2656-55e4-9e41-f3b1f24f9f9c | note | Attach: Concrete Dockets
df26204d-99d2-5541-a189-7d5e49e0e4d4 | note | – – – – – – – – – – – – – – – – –
3e52cce6-fcee-5618-ba2c-46b13ae7eba2 | note | METHOD: Visual
80f9d01d-e838-586a-8ab0-e24bcac18171 | note | – – – – – – – – – – – – – – – – –
27c104ab-a4fe-5bb4-9d21-7e065a206021 | note | FREQUENCY: Each load
2d34961b-7972-5207-8872-b6dd611bbe49 | note | – – – – – – – – – – – – – – – – –
173152ab-abf6-5253-b133-08b8943a5165 | note | CATEGORY: SP
903e214a-e453-5f27-948a-4aaa6872e76c | note | – – – – – – – – – – – – – – – – –
bc2c43f9-4b04-5cd7-87a1-a94dc8929001 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
9c8bb76c-9005-50de-ba74-b103c317d208 | note | – – – – – – – – – – – – – – – – –
a85d65de-2a0f-5aae-8180-4f8ec760ee92 | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
3cb0b954-7540-5a78-a36f-cf6e7191edaa | date | Date Completed:
| checkpoint | 5.16 Surface Finishes
03756d9c-221b-5475-a87e-4c7f1d9541c7 | note | REFERENCE: IFC Drawings
17ca536c-e450-5ac6-90e5-43c2e89e75da | note | 610.31
6db08b58-6101-5eda-81a9-1680cf535af7 | note | 610.20
33a0a9fb-501e-5ebe-9041-554f2fc5e85b | note | – – – – – – – – – – – – – – – – –
b30ad291-d32d-58eb-a4ac-49964c0f002d | note | ACCEPTANCE CRITERIA: Surface finish as per IFC drawings.
cc83ebaf-4300-5c6f-aca0-cb13758f0fb5 | note | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
48cd39d9-9fb3-5a82-8843-368b68aef520 | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
e8e882ac-927d-57d9-ac9f-61e94307cf26 | note | – – – – – – – – – – – – – – – – –
4c1896c3-4de4-5921-9ee1-c66deef8075b | note | METHOD: Visual
3d88c0ad-9342-50b1-925c-7f746187056a | note | – – – – – – – – – – – – – – – – –
e56a080b-090c-51dc-9ed8-11a1fa4ebe55 | note | FREQUENCY: Each element
5c355b8c-7e58-5a06-a9db-69dd155156be | note | – – – – – – – – – – – – – – – – –
9be43de1-8423-5b5a-ba9c-3e63310846f1 | note | CATEGORY: IP
58bb0f2b-9e0d-544b-b5ed-098649c2c7ea | note | – – – – – – – – – – – – – – – – –
421aa8a1-5ca2-504b-aef0-cb3e122d6cc6 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
2295feb0-7123-57ec-bc77-89194c215eb4 | note | – – – – – – – – – – – – – – – – –
3126e3e1-9a9f-5731-9e6f-3a56d2ccac27 | note | VERIFYING DOCUMENTS: This ITP
1d94e937-65c0-58bf-88c4-08073f1011dc | date | Date Completed:
| checkpoint | 5.17 Curing-Top Surface
20c005fe-8894-5b40-9d1a-486dcdf0c403 | note | REFERENCE: IFC Drawings
069ff23e-8edf-56b0-b699-b78efaa107a1 | note | – – – – – – – – – – – – – – – – –
1c71f729-a5dc-5ee3-8075-81fab68020f3 | note | ACCEPTANCE CRITERIA: Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
4e71edfb-80f2-5768-8ea1-299dd12d15d5 | note | – – – – – – – – – – – – – – – – –
52289edf-f778-5251-a3fd-ac90f61be86b | note | METHOD: Visual
53c02ad3-a7c3-5221-bfce-81ce6380acfc | note | – – – – – – – – – – – – – – – – –
84a41063-5591-5c7b-b7bd-71ad9218818d | note | FREQUENCY: Each element
8f4a8c50-1b5e-5a7f-a8c0-7cbc8e121846 | note | – – – – – – – – – – – – – – – – –
33d5bae3-4970-5307-b3a4-f6e1e3b59265 | note | CATEGORY: IP
442a927f-a0c0-54f1-a05a-a3f6c8c2af40 | note | – – – – – – – – – – – – – – – – –
eb68492e-fcb3-59cf-8f64-2154d5931521 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
da5630b5-f295-5c7d-922c-a0f03e7cb14b | note | – – – – – – – – – – – – – – – – –
4b497aff-72c5-56cd-99dd-19747842fdfc | note | VERIFYING DOCUMENTS: This ITP
bd78fe33-87b7-5521-b755-2d350e322d15 | date | Date Completed:
| checkpoint | 5.18 Curing after formwork removal
d9cbcd40-3bd7-5670-9429-664bdf279446 | note | REFERENCE: IFC Drawings
c45de6bc-0135-561a-8d77-98d7c2cff721 | note | – – – – – – – – – – – – – – – – –
aa0943f7-7c65-5882-94a8-313c86afbb0e | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
204cee60-6881-541f-8ce9-340b72c339db | note | – – – – – – – – – – – – – – – – –
43889d07-2d39-5a3b-b4f7-7495f8437d18 | note | METHOD: Visual
c313be1d-e95b-5053-ab97-b0142696074e | note | – – – – – – – – – – – – – – – – –
a185274e-1ad5-5b7b-854d-3c197997bc68 | note | FREQUENCY: Each element
896e4af7-5184-5da6-b82e-aab1fe6bec58 | note | – – – – – – – – – – – – – – – – –
70e6ea2b-33f3-57f3-83b2-19d1a038babe | note | CATEGORY: IP
d384f1bb-c8f0-57ae-918c-a949ee1b638a | note | – – – – – – – – – – – – – – – – –
cf62618a-bd5d-5210-9b6c-0453971b6c61 | note | RESPONSIBILITY: SE
84914b0a-f9f8-5663-b6bc-521ed2b66757 | note | – – – – – – – – – – – – – – – – –
66bfc3dc-3ac0-5659-9f97-34eaf0486f1d | note | VERIFYING DOCUMENTS: This ITP
099b7cc4-f164-5d70-9bc8-23017dffecde | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Thermal Differential Monitoring
5233f3b7-bb10-5c21-bc2d-002891aeadc3 | note | REFERENCE: 610.22
61383814-22f7-599a-8a98-bf6c4b911f74 | note | – – – – – – – – – – – – – – – – –
03a69cb3-7ab9-539a-9ce9-04e1e4b830ef | note | ACCEPTANCE CRITERIA: Maximum thermal differential between the core and exposed surface not to exceed 20°C.
14a96b83-5333-5879-bffc-2585a2e46689 | note | Only applicable if the element has:
42802b70-5bb1-563e-b432-3a614fc58157 | note | i. the smallest sectional dimension exceeding 500mm
6e1bb9fb-6ab0-5511-a8a3-759082381547 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
fddfbadd-e5de-599e-afc2-de7b61f2d2ee | note | Attach: Thermal Monitoring Report
3fad3ad1-87d5-5cd8-9604-0bdf064baf2e | note | – – – – – – – – – – – – – – – – –
2ab3117e-6e86-504f-bbfb-824cee7d49e9 | note | METHOD: Document Review
bca46697-a06e-53a5-b110-74cf13ef4ba4 | note | – – – – – – – – – – – – – – – – –
468b7d1e-514a-551c-a10a-b27ba7612ca6 | note | FREQUENCY: Where applicable, each element
bfeaf98e-48eb-5811-a650-11dd689eb76b | note | – – – – – – – – – – – – – – – – –
712847ed-8f2f-5c78-b8d8-08552c803ded | note | CATEGORY: IP
bc39d707-1f20-51c9-9847-b5517d9288e3 | note | – – – – – – – – – – – – – – – – –
564240b4-27bf-59e7-9cdd-f4f0ad1a4925 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
5370be64-f5f1-57aa-9f6a-aab985766959 | note | – – – – – – – – – – – – – – – – –
fd9d0447-927e-5b19-a1d7-eff5269e2f63 | note | VERIFYING DOCUMENTS: This ITP
59279cf0-3d5d-5af6-964d-4ed791b13154 | date | Date Completed:
| checkpoint | 6.2 Early Age Compressive Strength Test Results - Removal of Formwork
f5af9ef9-3528-5cea-980e-83e39183254c | note | REFERENCE: IFC Drawings
f83e0c92-1283-5996-95b7-94f65703e977 | note | – – – – – – – – – – – – – – – – –
a1416e1e-f786-536d-9570-4730f1e6ff70 | note | ACCEPTANCE CRITERIA: Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
49c84540-9492-5bce-9c77-fa917f1f73b2 | note | Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
4672420f-4676-5e82-b652-66e910cf40f0 | note | – – – – – – – – – – – – – – – – –
6ebf5c01-0e9d-5ff3-a465-1466d1b513ea | note | METHOD: Document Review
4d0b754b-196d-5b04-9a9a-22c2feb81994 | note | – – – – – – – – – – – – – – – – –
fc362f45-0f51-5231-a2e1-e8df94eabf78 | note | FREQUENCY: Where applicable, each element
4dbd254e-8cb5-5737-a037-73a68ec92970 | note | – – – – – – – – – – – – – – – – –
7b8fee1c-ddad-588f-8aff-dd2af6a5580e | note | CATEGORY: IP
94b106cc-f6e2-53cb-bec5-e597e13af181 | note | – – – – – – – – – – – – – – – – –
1ebf1999-a38d-5742-9f13-5e965691ead3 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
5247e68e-ecfb-557e-b1ce-fd793b3cf2ff | note | – – – – – – – – – – – – – – – – –
2e46bc09-b954-5e86-978c-8675c8a94a65 | note | VERIFYING DOCUMENTS: This ITP
540449d7-88e6-5880-9116-39de79050085 | date | Date Completed:
| checkpoint | 6.3 Surface Inspection - Cracks
26bd503b-1a61-58a6-9921-6b5783f153eb | note | REFERENCE: 610.24
9a1a0d66-ba98-5180-8280-cee4187c258e | note | – – – – – – – – – – – – – – – – –
bf46270f-f299-5fc8-95f6-234917052993 | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm (exposure classification B1)
aed59650-b1d6-52af-b624-a18c08ae5517 | note | If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
cc8f2203-843d-5946-9dcf-4a8f0500cec8 | note | – – – – – – – – – – – – – – – – –
6903b658-7479-5af9-92a0-ee886eefd996 | note | METHOD: Visual, Measure
875c617e-4c2d-53f8-a12a-359e57bb544d | note | – – – – – – – – – – – – – – – – –
24b18c10-5ac8-53ed-92af-8a2485b8eb1c | note | FREQUENCY: Each element
9f5ba0bb-4f12-5f32-a37d-64558e4debd1 | note | – – – – – – – – – – – – – – – – –
aa76341f-c7ba-50f6-8a36-33e61f28f7b1 | note | CATEGORY: IP
db7dfb12-7b13-5593-b43f-d2326ae839ca | note | – – – – – – – – – – – – – – – – –
62253afb-dabd-580e-a6f0-0460dd981764 | note | RESPONSIBILITY: SE/PE/SPE
d1351feb-4e63-5d00-865a-9bc7a0f2f253 | note | – – – – – – – – – – – – – – – – –
866de170-5903-5d75-9314-e533c8070938 | note | VERIFYING DOCUMENTS: This ITP
bfffd3ea-b21c-50fb-b18f-7c4a32f88cdd | date | Date Completed:
| checkpoint | 6.4 Surface Inspection - Surface Finish
2e3d1ca2-4ef9-5ef0-b011-4f65df2c4b8c | note | REFERENCE: IFC Drawings
23182c8d-f6d8-515e-926f-61084c06d177 | note | 610.31 (a) - (n)
4b950364-b5b1-55f7-b9fc-4548eea4b64f | note | 610.32
2ca7f63f-e687-58d3-b357-b5d334b8a430 | note | – – – – – – – – – – – – – – – – –
01e0df98-6ef4-5e20-9cbb-f2312be6a471 | note | ACCEPTANCE CRITERIA: Comply with the IFC drawings and specifications.
6a700b98-0874-50f0-8171-3b0e56a10975 | note | Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
c89edfbe-1238-5c03-9aaf-55ff270a2ea2 | note | – – – – – – – – – – – – – – – – –
8fe249ff-9eb6-558b-bced-a806f142f6b7 | note | METHOD: Visual
453491c1-ba36-5a2d-b326-3f527c7a5413 | note | – – – – – – – – – – – – – – – – –
7682fa1b-23d3-5b24-aae2-700dcfdc777c | note | FREQUENCY: Each element
282e2650-d448-5f32-8bd5-fbf171ce820a | note | – – – – – – – – – – – – – – – – –
6c5ddecc-99ec-57dc-91b2-36dcaa88a976 | note | CATEGORY: IP
5bfacdd9-f6b8-5c2f-a496-306f657964c8 | note | – – – – – – – – – – – – – – – – –
c26c04a4-c441-5bf1-9a40-51a6f7805396 | note | RESPONSIBILITY: SE/PE/SPE
c55d8cda-3286-5d5f-9503-fa60fd1b007d | note | – – – – – – – – – – – – – – – – –
e569c712-e16a-56a5-bea0-70cd77c0c88d | note | VERIFYING DOCUMENTS: This ITP
89238ae3-445d-5dd8-af0d-55dc3b611cf0 | date | Date Completed:
| checkpoint | 6.5 Measurement of Concrete Cover
2b911015-d1ab-5674-920e-afa4cb0f476e | note | REFERENCE: 610.34
f4e0537e-ae4c-5a62-9592-64d8d140b637 | note | – – – – – – – – – – – – – – – – –
b6efcf9e-0174-5891-b130-fca5f14376d9 | note | ACCEPTANCE CRITERIA: Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
15256877-ba99-5e1d-91a8-48f521254149 | note | Minimum 10 no. measurements recorded in each area.
9b3ab2ed-eaca-5e11-892f-7f2d429eb4eb | note | Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
74859886-1c2a-59d6-9ded-0f9a15cd95a5 | note | Attach: Covermeter Check Record
e4eb4994-3c67-5036-8737-bc3e3b1c33ed | note | – – – – – – – – – – – – – – – – –
fb036163-040b-56e3-8a59-aff1af6a2367 | note | METHOD: Measure
ad7a8077-9076-59ed-936a-63ac884632c3 | note | – – – – – – – – – – – – – – – – –
75b45957-bbfc-55ac-a02d-f4d1856b1593 | note | FREQUENCY: Each element
530c3deb-dd58-5939-b61e-cac3b6f08064 | note | – – – – – – – – – – – – – – – – –
a88e67bb-674a-5b7e-9410-192359155d70 | note | CATEGORY: IP
db292379-f58d-5d52-b53d-e154566f3a5a | note | – – – – – – – – – – – – – – – – –
aa8555c9-4719-5663-a17c-ba005f4f48bc | note | RESPONSIBILITY: SE/PE/SPE
d6464b7e-e29a-5444-93e5-8d89942f5c0e | note | – – – – – – – – – – – – – – – – –
47be8880-b778-5c11-8d9c-fd428cdc628b | note | VERIFYING DOCUMENTS: This ITP
c460922c-244b-5a08-af6d-13d84ba41123 | date | Date Completed:
| checkpoint | 6.6 Early Age Compressive Strength Results - Placement of Fill Against Concrete
1b54646b-1b29-5a1a-a516-2fadf20096ea | note | REFERENCE: Early Loading and Trafficking of Decks and Approach Slab Procedure
4412e4b2-7df0-5c72-84ce-5888475b6bb8 | note | 610.35
012f6176-156a-5602-9170-d439ba43686d | note | – – – – – – – – – – – – – – – – –
791add12-90c3-5d6b-af84-8e839e26ecc6 | note | ACCEPTANCE CRITERIA: Fill is not placed against concrete within 14 days of pour.
f0449e40-088a-5b91-954a-40bb469eca43 | note | Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
e6eab9bf-6ed3-5ff8-a515-83b83c44fd2f | note | Attach: Concrete Test Results or Maturity Test Results
8af38397-caed-5566-bec8-4f3c48683c58 | note | – – – – – – – – – – – – – – – – –
b2cbe5f5-4815-5803-b4eb-60d6d7ea0311 | note | METHOD: Document Review
779d771a-5f0b-5499-9f62-d658eefaa75b | note | – – – – – – – – – – – – – – – – –
6ef1f64b-1ebd-5c03-b6bf-b320e180f3c6 | note | FREQUENCY: Where applicable, each substructure element
ec167fec-ad2b-512b-857d-c9b277899e21 | note | – – – – – – – – – – – – – – – – –
5f9a015c-9a25-5ea4-b292-2be2e3e0a737 | note | CATEGORY: SP
7bbf1125-caf4-5bf5-995a-00a880cf9357 | note | – – – – – – – – – – – – – – – – –
51c177f1-f9f9-541f-a65b-be89e3fecb84 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
19d7587c-6ecd-5a62-8e62-4bba41eb8c51 | note | – – – – – – – – – – – – – – – – –
d581497a-4ef7-56d6-b8a2-c3feebf4d54d | note | VERIFYING DOCUMENTS: This ITP
cb058c64-f173-5256-ab45-3208ac8dd279 | date | Date Completed:
| checkpoint | 6.7 Compressive Strength Test Results
b5188730-4ce1-56ae-b78f-c3b417134e0e | note | REFERENCE: IFC Drawings
2c66621b-9034-5c2e-a127-cee3fb1657ee | note | Table 610.05.051
a24cf975-89c9-5798-871e-cc9980e3fe95 | note | 610.16 (g)
0affeb42-a4be-519b-acd1-224474895810 | note | – – – – – – – – – – – – – – – – –
01972f3c-6291-59bb-8d4a-4c91bcff0143 | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
061c13b1-6420-57a2-86c1-d8b99b01cdd2 | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
e9dd5f19-a89a-5426-8782-ac6302084528 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
60a41712-0ab1-5e70-b476-4e943f9979a7 | note | Attach: Compressive Strength Test Results
908355dc-bcad-5578-8150-7ebff13098a0 | note | – – – – – – – – – – – – – – – – –
cec44a47-bfcf-5d9b-a8c0-4f1b91aacedf | note | METHOD: Document Review
1275d12f-c204-581a-aacb-c2cc2f0dfd24 | note | – – – – – – – – – – – – – – – – –
992e5e8e-7a77-54dd-808c-4de45fd6a027 | note | FREQUENCY: Each cylinder
24499514-0881-5f7a-853b-5b2fd9bd6813 | note | – – – – – – – – – – – – – – – – –
d400a452-d7a7-5f86-a6fd-4584dd7e237a | note | CATEGORY: IP
aa0777f9-42e4-506f-aff8-510b636b6763 | note | – – – – – – – – – – – – – – – – –
5c8a5adc-df11-546c-9f5a-96b5a1122b20 | note | RESPONSIBILITY: SE/PE/SPE
94be2966-2561-5e3e-9fd5-dad269cc79ae | note | – – – – – – – – – – – – – – – – –
931c5a59-f985-5a4a-ab59-c9474f4a3733 | note | VERIFYING DOCUMENTS: This ITP
b468f25c-6366-5491-8960-324590abaadb | date | Date Completed:
| checkpoint | 6.8 As-built Survey
56894a34-3b58-5fa4-906c-c116c880615d | note | REFERENCE: IFC Drawings
90688c05-f782-53d1-8571-8adaefcf9817 | note | 610.47
b19240e2-c264-5ae5-be37-ba4f2063ad7d | note | Table 610.472
446717e2-0a6d-5988-91b9-3c69ec75cce5 | note | – – – – – – – – – – – – – – – – –
a31f127d-cec9-5578-bdbf-70b76a517a4d | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
f482476c-227b-510c-bfe8-0bd24c591681 | note | Attach: Survey As-builts / Survey Report
67cb4fca-5739-52ff-8df0-903b9b1c2a07 | note | – – – – – – – – – – – – – – – – –
64c08216-50eb-5cc8-86ea-73a140e2ee4e | note | METHOD: Document Review
9ef32fa2-054c-5e86-affa-d2c8229dd4a8 | note | – – – – – – – – – – – – – – – – –
7050ac23-6a22-5758-92e1-f47205c3dd83 | note | FREQUENCY: Each element
b0944d26-8a3e-56b2-98b7-da0317af1171 | note | – – – – – – – – – – – – – – – – –
0c9cf177-85c2-5d83-9817-f56b314faac8 | note | CATEGORY: IP
e40c6f0a-2034-5219-921b-2373d39d2e4e | note | – – – – – – – – – – – – – – – – –
de3fa952-4a9b-5b71-80b7-9d6e13c5a2b1 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
bcdc4f83-fb66-54f1-b306-8690c2a7d353 | note | – – – – – – – – – – – – – – – – –
4bc90829-e99d-5c26-bd67-8e8a08c42532 | note | VERIFYING DOCUMENTS: This ITP
e17dbb7f-e80e-5551-9681-4b07517b14ae | date | Date Completed:
| checkpoint | 6.9 Non-conformance Report (NCR) Closure
e2c46fb7-b0c1-5505-875a-8c9b40034327 | note | REFERENCE: MRPA Quality Management Plan
7ea9266c-ece8-5956-b80d-1919dea34f03 | note | – – – – – – – – – – – – – – – – –
3addc6fe-77a1-5a65-b4d4-e506bd1d158f | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
0ddced91-ed66-5a75-b20a-f1a87e6269f8 | note | – – – – – – – – – – – – – – – – –
a4c5cc64-c274-59bb-981e-907dff8a8fdd | note | METHOD: Document Review
45276387-dbb8-51f8-a798-c3ecc6c52709 | note | – – – – – – – – – – – – – – – – –
9643e8c6-63c4-5417-a47f-74060f3ae05a | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
b2de3941-b4f3-564e-ac34-fdfcfd5b73a8 | note | – – – – – – – – – – – – – – – – –
6797bb66-df86-5eb8-b4f1-4fc1896ef357 | note | CATEGORY: HP*
cdaac92d-bc79-5de9-9442-43725c4b9ff3 | note | – – – – – – – – – – – – – – – – –
c758c11b-7a37-5a6a-a7b2-943fd6ba6d40 | note | RESPONSIBILITY: SE/PE/SPE
69d52d00-19fb-5fc2-a990-5e476c0617eb | note | – – – – – – – – – – – – – – – – –
22d8f8e8-23a6-5a51-8b1e-9edcc5ea680f | note | VERIFYING DOCUMENTS: This ITP
3593df6e-a187-55c8-b778-3ea62d47057f | date | Date Completed:
| checkpoint | Final Inspection
3915d7e8-c45d-52ad-890f-e1b8d3ad1bdf | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
4a737430-4f3f-55b8-b857-1bdfa8bbba25 | textbox | Name:
abf20f02-814a-5752-84a8-ac6c8b6ab06c | textbox | Position:
c481e701-3ffa-5d36-8c56-e4fc29c5fe74 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-032-STR-Precast Basin Retaining Wall Installation Rev 0 | itp | ITP-032-STR-Precast Basin Retaining Wall Installation |  | 8d59760f-bc7f-4b97-ae46-14bc49f97811
| section | Referenced Documentation
| checkpoint | Referenced Documentation
f19a5bea-ffe9-5a1b-b96d-90585c43fe1e | note | Document Title: ITP-STR-Precast Basin Retaining Wall (Supply & Install)
31fd7494-51d8-5ab3-abdf-eab1afe2d52a | note | ITP Description: Precast Basin Retaining Wall (Supply & Install)
64f9d2a7-1054-5e1f-a140-9070c2bd45b7 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
ab831a3c-7097-570b-a2f1-ebc42615445c | note | Discipline (e.g. CIV/STR/RAIL): STR
26db247b-98b5-5987-9f15-c50a9cd0f89a | note | Revision Number: 0
afa21d57-61df-56ea-b944-44ab19a77e9a | note | Revision Date: 01/03/22
c639a0ef-3a6e-53a2-ba13-e2764d3c5409 | note | ITP created by: Michelle Lim
f05239c7-56df-5d7c-804c-ff2abaf24fa2 | note | ITP approved for use by: Victor Mira
ee862f36-a5d5-56f2-9310-29224f3060b1 | note | 1.1 Non Dependent
d7a549a0-177f-5deb-a44e-61a3e88f0bce | note | Reference: VicRoads Section 610 November 2018
d50e4509-71bf-5b5e-8f06-c783b2055a90 | note | 1.2 Non Dependent
23aa4950-0b10-5040-bbfe-b3bac6e2d33d | note | Reference: VicRoads Section 610 June 2019
463ce870-bc06-579b-9b88-19e94f72cbc7 | note | 1.3 Non Dependent
1f3b7733-7fe6-56c5-aae8-7b309a78f8ac | note | Reference: VicRoads Section 620 May 2009
96ca079d-6557-5e56-a60b-27f6371a005e | note | 1.4 Non Dependent
8593b891-ebfa-587d-b599-0ce03358c557 | note | Reference: VicRoads Section 630 October 2013
| section | Preliminaries - Materials
| checkpoint | 2.1 Joint Sealant
184ef14f-c1d3-51d1-863a-05613bec8ae3 | note | REFERENCE: MRPA Quality Management Plan
ab7d4a12-236e-5f5b-a31f-2f5f2caa8592 | note | – – – – – – – – – – – – – – – – –
343b5c6f-8666-5100-934a-24acfc0723f3 | note | ACCEPTANCE CRITERIA: Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
7afee6ad-5d93-5bb0-a669-1802b7638430 | textbox | Enter: Teambinder Material Approval number
72d865cf-5569-5c70-a7e4-f88a17b80eb2 | note | – – – – – – – – – – – – – – – – –
a40fd1e0-1b1f-5530-90c2-c0f848910b33 | note | METHOD: Document Review
b12e13ba-4cc0-5dd8-88ca-dfad3fa74846 | note | – – – – – – – – – – – – – – – – –
0d4a3324-d181-59a7-9634-b62b3fce98b5 | note | FREQUENCY: Once, for each product
650bbf81-8f51-5321-bbbd-8c9103c81779 | note | – – – – – – – – – – – – – – – – –
b6250dac-03f1-552c-93ca-d6ae9e5e9cf9 | note | CATEGORY: HP*
94ee090a-4411-5376-bc1b-ad0f39b6fa5f | note | – – – – – – – – – – – – – – – – –
e47d259b-2bc3-59b5-bcbc-4e2438c8ec57 | note | RESPONSIBILITY: Nominated Authority
e42176ef-6ed3-50c9-b618-3eb80b0ff9f1 | note | – – – – – – – – – – – – – – – – –
abf500b9-db4a-5868-b97a-61b3435e1c0d | note | VERIFYING DOCUMENTS: This ITP
987bee62-f99a-5bbc-8bee-61fa437e7cee | date | Date Completed:
| checkpoint | 2.2 Subsurface Drainage
f3dc55ce-95f9-53fd-ad32-76299d7e75db | note | REFERENCE: IFC Drawings
13ac5831-5225-5788-9918-2ad4f6bbb41f | note | 702.03
eb7edaf0-0c63-5946-91d6-38e330dee722 | note | 702.06
f899a567-b823-5b77-8f8b-91516a2fba32 | note | 702.07
43ca9e63-8238-5f3c-94c8-e1ac65dc8c56 | note | 702.09 (f)
5bde9cfa-a1b5-573d-ad1a-1b5f3fbdbccf | note | – – – – – – – – – – – – – – – – –
6bd0596a-b737-5559-a4c9-d1794ba0b87b | note | ACCEPTANCE CRITERIA: Details of subsurface drainage as per IFC drawings
30761698-70d0-56ce-b0da-19c2b5ef0ec6 | note | 100 dia slotted subsoil drain
7382d35a-b575-52b1-8bae-ed8861a83012 | note | Category 1 (Class 1000) perforated plastic pipe. Perforations max width of 1.5mm and min length of 150mm per m2
cef3fa75-1d26-57e1-a376-4f154d5eb40c | textbox | Enter: Teambinder Material Approval number
be94d185-9e3c-5e11-90cf-f4279522b255 | note | – – – – – – – – – – – – – – – – –
136b9afa-bd20-5ae2-b4a1-88ae2ae40176 | note | METHOD: Document Review
7c57cbf6-c3cd-5c18-8bfb-534bfdcec103 | note | – – – – – – – – – – – – – – – – –
f2da7b21-29d6-5cec-8ecf-5a995efb750d | note | FREQUENCY: Once, for each product
8b0055ea-120f-5099-8082-9f0eb6a8db83 | note | – – – – – – – – – – – – – – – – –
667dac93-0a38-51f5-8844-60f84989b3ac | note | CATEGORY: HP*
39d4ce80-109a-5082-8b42-390d84cdd181 | note | – – – – – – – – – – – – – – – – –
d8c5893b-6ba5-532c-add2-6dc672d0d9ce | note | RESPONSIBILITY: Nominated Authority
503d4210-05d4-53cc-bfe9-87a93b2d24f0 | note | – – – – – – – – – – – – – – – – –
e257653d-41ef-55e9-bccd-fd13eafd2ca9 | note | VERIFYING DOCUMENTS: This ITP
ffc6d78c-f8f7-5b22-b2fe-629ec1ea0eb9 | date | Date Completed:
| checkpoint | 2.3 No Fines Concrete
0a10082e-25aa-534f-a569-23c65fbde7cc | note | REFERENCE: 702.05
d16a948e-d5ac-5391-ab6f-687c1fbc550a | note | – – – – – – – – – – – – – – – – –
4ef37b3c-f257-532f-b486-595f32432ef4 | note | ACCEPTANCE CRITERIA: No Fines Concrete to be used as backfill in geotextile A64 around subsurface drainage.
4e104c4e-fae4-51ba-9cb8-84449b247534 | note | No Fines to comply with 702.05(e)
c7b461a1-c793-536a-bd5e-39c60613b006 | textbox | Enter: Teambinder Material Approval number
2345958b-b69a-561e-91b9-6c7e538e9f9c | note | – – – – – – – – – – – – – – – – –
d7b1d20e-0bea-5bc3-bfa1-643bc0f7fc6b | note | METHOD: Document Review
50b9ba84-8dc7-5678-b4c6-83f3df9e9a3d | note | – – – – – – – – – – – – – – – – –
c0656b71-d9a5-562d-8c74-48428a77be1f | note | FREQUENCY: Once, for each product
90a46967-d31f-5119-a73f-381a4433d7f4 | note | – – – – – – – – – – – – – – – – –
fa30766e-c0c3-5f9b-8e3d-b041d5eb9745 | note | CATEGORY: HP*
076fad31-cba1-5b17-9da1-63c15a6119f0 | note | – – – – – – – – – – – – – – – – –
668d5ea0-d7e7-501c-b147-bd28d182ba3a | note | RESPONSIBILITY: Nominated Authority
a005bc92-587d-5df7-9282-419b6a9a395a | note | – – – – – – – – – – – – – – – – –
a95cd34a-75f1-5c87-ac86-7b4c90f99b5d | note | VERIFYING DOCUMENTS: This ITP
00c21368-6222-58b8-a1e3-b36f26d716ef | date | Date Completed:
| section | Preliminaries - Procedures and Documentation
| checkpoint | 3.1 Precast Elements
951629e8-159a-54d7-b287-a8f87fff715a | note | REFERENCE: IFC Drawings
8e7930f5-780b-5a68-933a-32cbd3a10ab3 | note | 610.46 (a), Table 610.463 (November 2018)
b2b64610-96a2-50ea-a3fb-6f43b1e684f9 | note | 610.47 (a) Table 610.473 (March/June 2019)
f3aa9cd4-45bd-505e-958b-7762c7b89bc7 | note | – – – – – – – – – – – – – – – – –
98d455a1-1274-5dcb-ac77-ea6acfc34d26 | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
8d751498-e66e-54d9-9d0e-af09ce8b1591 | note | i. Certificate of Compliance / Birth Certificate
b2ce0dbe-ee81-5e8f-a77c-ace836bd0fc3 | note | ii. Compressive strength test results
b2d12680-309b-5dda-b987-53ca8108042c | note | iii. Precast Lifting Design
97d10148-9fc5-5e08-909c-810c31d3a522 | note | iv. Pre-pour check sheet / ITP
77f88446-394d-5c2d-ad3e-040e52c0cb12 | note | v. Post-pour check sheet / ITP
e7cf40e5-0b17-56eb-859d-53e6aed85ee7 | note | vi. Covermeter check record
e4c32231-a7aa-5ef5-9cfd-2b38dbc16416 | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
f25c0e18-e919-57f3-8600-3b11c14a20f4 | note | Note: Different revisions of 610 have different clause numbers
6292e597-90b2-57de-9178-7f144bec3482 | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
ec63dcd8-8c4d-5196-a9b5-0d5b16c5424e | note | – – – – – – – – – – – – – – – – –
1866371e-ca26-55fc-bfd2-0bf7311d507b | note | METHOD: Document Review
e456f3f1-1528-5f6d-b319-215d2b8648d9 | note | – – – – – – – – – – – – – – – – –
d7db8e7b-fd70-5975-b98e-5fff2ab98966 | note | FREQUENCY: Each element
7f174dce-1e84-54ac-b7f2-e68ab56805b5 | note | – – – – – – – – – – – – – – – – –
b2b7556e-c48a-5e97-9140-034d23512a9c | note | CATEGORY: HP*
bef86d83-8b8f-5da3-936c-5e29a2a07982 | note | – – – – – – – – – – – – – – – – –
6c6e35fd-1209-5ff9-8eac-3ce4d6c273af | note | RESPONSIBILITY: PE/SE
1860f806-336a-5fd5-9cad-b4444ddca148 | note | – – – – – – – – – – – – – – – – –
17d651db-3a8c-5b7b-beeb-00136eec89ab | note | VERIFYING DOCUMENTS: This ITP
1acaa4e7-58d8-5d84-88e5-f57a3e5b50c7 | date | Date Completed:
| checkpoint | 3.2 Precast Base Slab Founding
1376081f-7348-5c17-b630-09264c91808f | note | REFERENCE: IFC Drawings
b88bf13f-ddda-5639-8d63-d45ad5da2e77 | note | Temporary Works Design
ab2a1ed0-ee48-595f-94ba-b5eb5f0f78fa | note | – – – – – – – – – – – – – – – – –
0ed97020-05e0-5ecc-b6e3-4296776e72ac | note | ACCEPTANCE CRITERIA: Foundation material beneath the precast wall shall be inspected onsite by a qualified geotechnical engineer to ensure that soil conditions meet the following material parameters:
5ded682f-e04d-5555-98cd-70c015abb8c1 | note | – Minimum undrained shear strength 80kPa
d42eb96c-6833-51d4-bf9b-194d39bcec67 | note | Attach: Test report or Geotechnical report
2468cb9d-43df-558d-a455-b31ac77a9688 | note | – – – – – – – – – – – – – – – – –
4732c0c8-4224-5eed-8585-7a1b38e68716 | note | METHOD: Document Review
5a9b807a-6251-5678-b660-7e87de5b984d | note | – – – – – – – – – – – – – – – – –
e82e5c60-c1e6-5c55-81b9-842263c3c731 | note | FREQUENCY: Each installation location
016f9013-9f62-531a-8095-486b77806b36 | note | – – – – – – – – – – – – – – – – –
f83ccb5d-b78c-5e10-bd8f-e266388800f3 | note | CATEGORY: HP
381d0485-fa67-5fa9-b190-c5bcd88d7786 | note | – – – – – – – – – – – – – – – – –
6a218258-cd7a-5843-8b25-43d36eb59642 | note | RESPONSIBILITY: Geotechnical Engineer
54f0837c-dc2e-539b-b858-85be85cadbcd | note | – – – – – – – – – – – – – – – – –
2685e8c3-d707-5807-a8a1-d95ed4ce7cfe | note | VERIFYING DOCUMENTS: Attached Report
dc3a2e6f-e13a-5935-8062-91122731d68b | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-installation Activities
| checkpoint | 4.1 Materials Inspection Checklist
b4eb9e43-b93f-52d0-975a-a7f320cd5f66 | note | REFERENCE: 620.06
136cffcb-abe6-53e7-a400-fdb6711d0430 | note | 620.07
a182bc4d-4a2f-5280-9a12-945f0a590791 | note | MRPA Quality Management Plan
07e67926-1e64-56cd-83dc-71a3ed65cd43 | note | – – – – – – – – – – – – – – – – –
f1367bac-4e9e-5f0a-b001-ac9b94e39a60 | note | ACCEPTANCE CRITERIA: General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
abd73fb7-b2e1-5d71-a72d-5e607d37a92d | note | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
90fc60a5-daae-559d-ab06-cf45b2c4eefc | note | Elements shall have unique identification and orientation marked (if applicable).
681afc7d-f7c4-5368-822c-a99f48ed7475 | note | Complete: Materials Inspection Checklist in ConQA
02d29602-1760-51fe-8f36-8a2a35679e32 | note | – – – – – – – – – – – – – – – – –
200c11e9-ea33-51b4-909b-fe9f8b40b9ae | note | METHOD: Measure, Visual
cca2496e-6b00-557b-b1e8-6f189a1376d8 | note | – – – – – – – – – – – – – – – – –
095e1ee2-92d0-53a8-9bb5-1b954194c976 | note | FREQUENCY: Each element
26c7f4d2-4a40-50c5-ae51-8be236512ddd | note | – – – – – – – – – – – – – – – – –
f8e1adab-9123-56b5-8669-dd5d7391b899 | note | CATEGORY: HP*
ed95de94-f6b5-512d-a2c1-8d13a4af114b | note | – – – – – – – – – – – – – – – – –
3a2c61ff-bc8f-5945-9cf6-c068dd414bca | note | RESPONSIBILITY: SE/PE
9c8f4862-5655-522f-8f4c-74049f5c55b8 | note | – – – – – – – – – – – – – – – – –
39fea7c9-f5d7-581d-93e9-717cdf763546 | note | VERIFYING DOCUMENTS: This ITP
062ec990-8cd8-5e30-a99a-babbcdf49953 | date | Date Completed:
| checkpoint | 4.2 Survey Set-out of Precast Elements
7f72a1f9-a347-57ef-8015-f7335d805239 | note | REFERENCE: IFC Drawings
7357b2c0-136c-5954-aff2-bbdf93e65a4c | note | 610.46 (a), Table 610.462 (November 2018)
179ecec0-a38e-526b-ac75-6a049d3269ef | note | 610.47 (a) Table 610.472 (March/June 2019)
a62ffe8d-fbfe-5b51-8c59-18ab857505f0 | note | – – – – – – – – – – – – – – – – –
79e18867-4b90-5f49-8539-618fd481a922 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
ac4e6d8e-5087-5573-9ada-306f3e2f16ae | note | Where anchor bolts or steel posts are cast in to the concrete, ensure that these are within tolerance.
3fe73320-2f29-5207-a51b-3e3ee48964c0 | note | If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
c4314fde-79eb-5c68-9590-f9a8d15b25c0 | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
ae46bd99-b16e-5d41-9d61-b6cbfb43862f | note | – – – – – – – – – – – – – – – – –
c5084a96-3e40-5752-81fc-2fa40323f9c2 | note | METHOD: Measure, Visual
b6991dfb-22e1-581c-8e12-a4db213bc5f2 | note | – – – – – – – – – – – – – – – – –
abb9a71e-27fd-5a12-8fe0-f34e03f2c390 | note | FREQUENCY: Each element
9fd7fcfe-c2d2-50d7-b2ac-a35579c76735 | note | – – – – – – – – – – – – – – – – –
96442538-8304-5ca6-81b0-10e3c5606702 | note | CATEGORY: HP*
34d2baab-a6d0-53b6-aedc-f5eaa25c62ad | note | – – – – – – – – – – – – – – – – –
2cc3dfcd-0e1f-519f-9e63-d517fa1d5d6e | note | RESPONSIBILITY: Surveyor, SE/PE
d6ba67ea-ad89-5406-9c41-e53599cef23d | note | – – – – – – – – – – – – – – – – –
677fa826-cca9-569b-92ad-945813c63687 | note | VERIFYING DOCUMENTS: This ITP
4dc27164-d227-590c-ac71-317f5787fadc | date | Date Completed:
| checkpoint | 4.3 Shims Placement
565a6c5e-02a1-5f20-b15c-0654c20dae14 | note | REFERENCE: IFC Drawings
077a1912-a82b-5340-a980-af9aefae6f4e | note | – – – – – – – – – – – – – – – – –
a7f2a801-31fb-5af0-a4c4-837a3131cc0c | note | ACCEPTANCE CRITERIA: Place the shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
801f7fac-10d4-516a-804e-f8663a594bbd | note | Packers to allow for 50mm grout under the precast elements
20e37649-db95-5f38-84fd-22cfd47e37be | note | – – – – – – – – – – – – – – – – –
6dee86c7-ea95-54bd-b869-2277b03b807f | note | METHOD: Measure, Visual
9223a16b-7b52-5aa2-b141-dc725d88f74d | note | – – – – – – – – – – – – – – – – –
1362e66e-cc6a-5f00-84ec-3acb5503f14c | note | FREQUENCY: Each element
849893fb-2e1a-5088-9521-2e16bf6c00ed | note | – – – – – – – – – – – – – – – – –
fe0a829f-4686-5803-bc75-62f92b562082 | note | CATEGORY: HP*
3f35dd8f-1fa0-531b-99f9-a56c9ca62fbd | note | – – – – – – – – – – – – – – – – –
abcd392f-c2e9-5616-b7ed-1920dda163b6 | note | RESPONSIBILITY: Surveyor, SE/PE
5d2e16f8-2734-5702-8457-2d34b839a973 | note | – – – – – – – – – – – – – – – – –
40a998f8-be62-5d4f-935b-d44ba103f09d | note | VERIFYING DOCUMENTS: This ITP
32d5a3fb-da6a-54dc-86ca-e22568e6d057 | date | Date Completed:
| section | Installation Activities
| checkpoint | 5.1 Precast Handling
0e0afcfd-dc6e-5993-b9b6-d9041771151a | note | REFERENCE: 620.07
c9356e38-4ac5-5d6a-9d07-9d4d20751042 | note | Crane Lift Study
cc1b23be-c860-517c-b755-c16736b94c10 | note | – – – – – – – – – – – – – – – – –
0c2294d3-a53c-535d-bccb-ce45a82ee105 | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
b3fb9570-27bd-5852-a2ac-97f579a114d7 | note | – – – – – – – – – – – – – – – – –
554a2b28-3807-56af-93d5-680ac9bbc51f | note | METHOD: Visual
b54bc579-86c3-5c27-9469-01463813d581 | note | – – – – – – – – – – – – – – – – –
e8acac12-d917-52e4-85e3-bad31a0c9e38 | note | FREQUENCY: Each element
5c80aac6-5d39-53a4-8651-2fe910e6f3f0 | note | – – – – – – – – – – – – – – – – –
d27f619d-037f-5495-9455-bbad484fd357 | note | CATEGORY: SP
df665423-0aef-5a56-93ff-9744add549e7 | note | – – – – – – – – – – – – – – – – –
e6863670-c970-5243-a66a-71bed764b16a | note | RESPONSIBILITY: SE/PE
c19bbefc-1954-548b-90c3-928746a92f5e | note | – – – – – – – – – – – – – – – – –
ca759824-bcef-5558-876a-ac6cc74c0e37 | note | VERIFYING DOCUMENTS: This ITP
ab46ba79-75f2-53c8-8ec1-75cc5a8ae03e | date | Date Completed:
| checkpoint | 5.2 Precast Placement
44fd0900-704e-5541-9020-4ea17495c315 | note | REFERENCE: IFC Drawings
d9675d00-a031-5e9a-9e48-ed53685356cf | note | Temporary Works Design
3488480d-3437-5c6a-9124-91ae897ddb2b | note | 610.27
812d998a-b3a3-5220-8f41-133dd8447c88 | note | – – – – – – – – – – – – – – – – –
62dbbe55-0a37-5653-b81c-a39ed9e22fd0 | note | ACCEPTANCE CRITERIA: Precast elements shall be placed into location and not released from the crane until any adjustments necessary by lifting the unit and adding/removing shims or adjusting the connecting bolts so that alignment between units, minimum end bearing, overall height and position remains in tolerance.
e637305a-4063-5d85-ae59-4569504fed35 | note | The nominal gap between elements is 20mm as per the IFC Drawings.
b77b3f9e-d6e6-59f5-a0ee-e7f6f924d249 | note | – – – – – – – – – – – – – – – – –
d45dbab3-82a9-5d02-ad0e-4cc0663f27b1 | note | METHOD: Measure, Visual
0889b0a0-e43d-5d9a-8dd0-87c2e3318a57 | note | – – – – – – – – – – – – – – – – –
87988d68-5697-568b-b1e9-47dfd8b21613 | note | FREQUENCY: Each element
d0e1c109-178c-5255-b270-2ec88991e019 | note | – – – – – – – – – – – – – – – – –
7d731c6f-706f-591b-b9e2-eaa303548144 | note | CATEGORY: SP
4f95dd5a-eb16-5ef3-8aca-0e24be7e696e | note | – – – – – – – – – – – – – – – – –
f430929e-1a22-58f1-88a8-4a8637e9a6d6 | note | RESPONSIBILITY: Surveyor, SE/PE
f7488ad8-535a-5f1f-927c-38bf87a67925 | note | – – – – – – – – – – – – – – – – –
45efa3b1-d19b-597e-ae39-a4424d2226ea | note | VERIFYING DOCUMENTS: This ITP
59ea4000-f378-503f-9017-873d4e481064 | date | Date Completed:
| checkpoint | 5.3 Waterstop Seals, Compressible Seals & Isolation Joints Application
eb2700f0-32f7-5dfe-a170-a378cd19a7c5 | note | REFERENCE: IFC Drawings, Product TDS
ece3d4a1-06dc-5ea7-ab53-0da76564f0d8 | note | – – – – – – – – – – – – – – – – –
f7859c53-4e3a-50d8-a3a7-8dd496310435 | note | ACCEPTANCE CRITERIA: Materials shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
d0f46c6b-bbb0-545b-8b89-eba6d372b78f | note | 300mm wide Bituthene placed centrally over joint. Bituthene to cover retained height of upstand and extend 100mm along top of base slab.
196d301a-32e4-5aea-bece-2db2f90d5a31 | note | Compressible filler with backing rod to be installed on both faces
b4d1b93c-141b-55bf-8516-3afb7f989cd5 | note | Fabric Geosheet CS15F or equivalent to be installed over retained area of upstand, and over the 300 wide granular backfill for subsurface drainage, as per IFC drawings.
c8c57cc0-59f9-5358-9b61-cbf74c87e95a | note | Adhere any waterstop seals or expansion materials full height of the structural element(s) and located as per the IFC drawings.
e6c8c303-92e0-5e8e-98bf-0b67077ec0dc | note | – – – – – – – – – – – – – – – – –
bb008825-bbe2-5cc2-9aeb-9d14783d26c0 | note | METHOD: Measure, Visual
44e58812-0f3b-5c62-8662-71efa6ca0427 | note | – – – – – – – – – – – – – – – – –
ce8d1abb-6da6-5dc8-ab88-3b2f59f28229 | note | FREQUENCY: Where applicable, each installation location
7842fc77-1f6d-53b2-99b3-a5cbfeec3bd2 | note | – – – – – – – – – – – – – – – – –
454cc3ac-cdc2-53fc-b1f4-c9d272788f86 | note | CATEGORY: IP
187c1d65-3e89-5893-90ce-b3f831f3ae00 | note | – – – – – – – – – – – – – – – – –
dc7b59e7-ded0-5f56-84f7-43917f8e11ca | note | RESPONSIBILITY: Surveyor, SE/PE
f5778d6a-2c0d-50b2-b3cf-436df39fb137 | note | – – – – – – – – – – – – – – – – –
74c2f94b-e958-57e6-8580-459aab2153ab | note | VERIFYING DOCUMENTS: This ITP
678d9c04-76a6-5f98-bfd6-99b15079fcfd | date | Date Completed:
| checkpoint | 5.4 Joint Sealant Application
48d9701d-55f4-53bb-9fe7-3687dcb3985e | note | REFERENCE: IFC Drawings
0f25d8e1-10b3-55ff-a89a-f9fa55103b4b | note | – – – – – – – – – – – – – – – – –
2ff843b5-c0ad-5818-b7a8-b8694572363f | note | ACCEPTANCE CRITERIA: Compressible filler with backing rod to be installed on both faces.
e7f2e7ad-bee1-5a9c-a818-77213a001c98 | note | The gap between each precast element on the retained side to have 300mm wide bituthene placed centrally over the joint. Bituthene to extend the retained height of the upstand and extend 100 along the top of the base slab
3d41f669-f263-51c0-8c87-0ff3ace7ca81 | note | – – – – – – – – – – – – – – – – –
2d909ed0-03f4-5cfb-b005-e25d8000867b | note | METHOD: Visual
5d7edd37-aaed-5329-8f3d-5bdb19508727 | note | – – – – – – – – – – – – – – – – –
1074150e-3c7e-5304-8cca-a225da68ed1e | note | FREQUENCY: Where applicable, each element
cd7dc012-a109-5a55-846c-40c2ab8c47bc | note | – – – – – – – – – – – – – – – – –
259a388d-7aa5-5e93-99d5-0ce47d936294 | note | CATEGORY: IP
101d3244-4bb6-500b-85ba-757ae33039ca | note | – – – – – – – – – – – – – – – – –
e0216b6d-c593-5ae0-b289-ed986b480e36 | note | RESPONSIBILITY: SE/PE
b2ef51ad-8900-5cbf-92ba-21fc5406b77a | note | – – – – – – – – – – – – – – – – –
5afa04bc-fd1c-570c-9527-0a3fed73991f | note | VERIFYING DOCUMENTS: This ITP
d23be74d-4cfe-540b-96f6-219c503bcc4a | date | Date Completed:
| checkpoint | 5.5 Subsurface Drainage
4ad14a4d-4abd-5b18-a01e-c41df16f2d80 | note | REFERENCE: IFC Drawings
043d0a07-6f1f-59ef-be4b-2cffca8b2350 | note | 702.03
be5d5f8a-c44c-58b7-8e7a-d1dd8b80893d | note | 702.06
1368083f-ac49-5956-aaef-6353af1c8ea5 | note | 702.07
bb1f10ff-2feb-505b-b4c6-dceb2671fc22 | note | 702.09 (g)
164f30f6-1548-5aec-a231-09239fa86243 | note | – – – – – – – – – – – – – – – – –
8b2ad0f4-aa31-515a-b14a-31b2cf32fcba | note | ACCEPTANCE CRITERIA: Subsurface drains shall be the type nominated on the IFC drawings - 100 dia slotted subsoil drain.
c8cae151-9c3b-59f8-9f4f-c6018d092f64 | note | The drainage shall be backfilled with 300mm wide No Fines Concrete in Geotextile A64 as shown on the IFC drawings. No Fines Concrete to be compacted within 1 hour of mixing
872c2881-354e-509b-a06d-7dfc092edf7d | note | Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
a5b88326-b436-59c6-93c5-2fe8f51373ca | note | Weep holes shall be checked for obstructions.
0c509faa-c576-5fde-8dc9-2e5c04f9f8b6 | note | – – – – – – – – – – – – – – – – –
03cb299b-cc49-5cdf-a47b-3ed6e2c0dc20 | note | METHOD: Measure, Visual
15fa05f7-5564-513f-a45a-bb0b0f5190a8 | note | – – – – – – – – – – – – – – – – –
6cc06d88-6af0-5763-8398-13ab66258a16 | note | FREQUENCY: Where applicable, each installation location
5e5e1f88-7508-5f4a-8583-b379f0a76e74 | note | – – – – – – – – – – – – – – – – –
3dd48f4b-441e-5cb0-bb00-347a78945021 | note | CATEGORY: IP
2b3e241d-b7a2-57dc-94e4-81c15415a7fd | note | – – – – – – – – – – – – – – – – –
57f85a23-e056-5132-996d-9ed8c8b37f7c | note | RESPONSIBILITY: SE/PE
7f759b35-4d49-5897-bcb0-354393c8952b | note | – – – – – – – – – – – – – – – – –
cbe358fb-8387-569c-b8a7-f5f89974742a | note | VERIFYING DOCUMENTS: This ITP
b2116ad8-270f-5ef0-a153-40a9454a9ab4 | date | Date Completed:
| checkpoint | 5.6 Flowable Grout Pour
f165213a-c790-5040-8d90-72782a00b864 | note | REFERENCE: IFC Drawings
9eaa1c84-526d-522b-91cd-794888731d37 | note | – – – – – – – – – – – – – – – – –
d5daefc0-8fbe-58c6-bc69-06992e9dbd00 | note | ACCEPTANCE CRITERIA: Grout shall be poured in the gap between the bottom of the precast element and blinding layer below. Utilisiing shims to ensure 50mm thick of grout.
2094e041-d448-54aa-9907-c87ede6a2086 | note | – – – – – – – – – – – – – – – – –
b5988ba5-6f3e-5e34-a054-ff0c2f06ed4e | note | METHOD: Visual
b455e59e-a3f3-5c33-8b94-135c341dfb17 | note | – – – – – – – – – – – – – – – – –
eb216b0c-ad94-5778-ab36-dfb54b2636c9 | note | FREQUENCY: Where applicable, each element
cbedf4b0-5056-5ff3-a50b-2dff549d695f | note | – – – – – – – – – – – – – – – – –
8124068f-7eb9-5be8-b9f6-c70eba220426 | note | CATEGORY: IP
b4ebb81a-a7d1-5bb5-8058-a11dec49f95f | note | – – – – – – – – – – – – – – – – –
116cfe0d-b8e9-5789-b504-74b127e3a854 | note | RESPONSIBILITY: SE/PE
4b4c8f4e-25f9-58d2-9fa9-3de97fa308e1 | note | – – – – – – – – – – – – – – – – –
11761de4-612d-5537-a55e-a6733c52438f | note | VERIFYING DOCUMENTS: This ITP
23c9e9ce-b504-5cf6-bbf6-34b7c5799c8d | date | Date Completed:
| section | Post-installation Activities
| checkpoint | 6.1 As-built Survey
f029ed52-8b9d-5336-b442-db08868929ad | note | REFERENCE: IFC Drawings
8d6192cd-b9c5-5189-b497-562f22fe816a | note | 620.09
f4a3c3fa-4ae0-5b95-8e6c-f509c92dce0a | note | – – – – – – – – – – – – – – – – –
34e27a33-7e5c-5eb3-967b-27a291c3e12f | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
c92d4366-3f67-5556-bb8c-9e6d4759f58c | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
64ff28c4-993d-5e08-9366-4c4d6f6f16d7 | note | Attach: Survey As-builts / Survey Report
3a49f297-4e27-5518-b6c4-3e145df74447 | note | – – – – – – – – – – – – – – – – –
1726f8c3-edb4-5e57-a14d-8410871d9450 | note | METHOD: Measure, Visual
387ee268-d140-5abc-b080-a135d61ff35c | note | – – – – – – – – – – – – – – – – –
5ba1d262-2647-54a1-9e56-8258d2a8a090 | note | FREQUENCY: Each element
2d2fe9be-f9cf-54dd-9bb7-ab735970f217 | note | – – – – – – – – – – – – – – – – –
0517266b-7989-5718-ac0d-e81cb2833aea | note | CATEGORY: HP*
170aba6e-b589-533a-bc75-8e2967430875 | note | – – – – – – – – – – – – – – – – –
e1d13410-eed2-56a4-88e5-be6a957a0502 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
e7e536c2-f887-562f-92fb-507b73555523 | note | – – – – – – – – – – – – – – – – –
7f7b38cb-89a6-5fd6-8c10-5ff30d7ed626 | note | VERIFYING DOCUMENTS: This ITP
a60e349a-86a4-5009-80d0-976b728d55ec | date | Date Completed:
| checkpoint | 6.2 Non-conformance Report (NCR) Closure
c48c67d3-2eeb-5f6e-a419-baf1bdacfb43 | note | REFERENCE: MRPA Quality Management Plan
bdca0272-ccc6-5f20-be48-e54a56336443 | note | – – – – – – – – – – – – – – – – –
173b9883-098a-5baa-9d0e-32cce59333f2 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
a140084f-7316-55d9-99b6-acfdab4fa3fd | note | – – – – – – – – – – – – – – – – –
4ae278e8-54ff-5968-b6d3-2fcf08843e5d | note | METHOD: Document Review
51fcf64a-1300-5698-840c-ef6f8b82d92b | note | – – – – – – – – – – – – – – – – –
9301b6a3-e7f6-5f85-8dbd-f175163492ed | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
222328c0-976c-5756-9ba0-1ac9a5c610d9 | note | – – – – – – – – – – – – – – – – –
d192fe65-afd1-5e1a-ab51-d86367e370c2 | note | CATEGORY: HP*
130d8069-d0fa-51ac-879b-eded4ffab1a5 | note | – – – – – – – – – – – – – – – – –
a126c0e3-2a54-5061-ab8e-70599084706d | note | RESPONSIBILITY: SE/PE/SPE
0fad674f-7ef3-52e0-8b4d-f33d970021eb | note | – – – – – – – – – – – – – – – – –
3ecf732a-bc58-5dea-be05-b26634f0ac57 | note | VERIFYING DOCUMENTS: This ITP
5dcfc125-234e-55a5-94ba-7e132f6e78ff | date | Date Completed:
| checkpoint | Final Inspection
2dd42f16-9df5-53c5-b183-39b920c5bf45 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3989c7f3-620d-50c4-a4ab-ec768fd813ae | textbox | Name:
5f52c0c8-ce50-5e2e-8b0a-a4aaa53b2aef | textbox | Position:
3c110bac-b190-5424-b753-49abd7f24c4d | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-033-STR-Grout Pedestals & Bearings Rev 0 | itp | ITP-033-STR-Grout Pedestals & Bearings |  | d0373c2e-faa9-453f-b57c-058673c5d718
| section | Referenced Documentation
| checkpoint | Referenced Documentation
60a3a4e8-3beb-5718-b371-56264f827a0b | note | Document Title: ITP-STR-Grout Pedestals & Bearings
d1168e38-c2e7-5f3a-8fac-c333e2751345 | note | ITP Description: Grout Pedestals & Bearings
90a315a4-f44c-5782-a0e6-60d7b774bede | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
fafcfd14-ea4c-500d-8c98-2d32347c28b5 | note | Discipline (e.g. CIV/STR/RAIL): STR
22152999-5668-5155-80ec-876ddec9337e | note | Revision Number: 0
2955195d-8190-54dd-8cca-6a053e2df598 | note | Revision Date: 14/04/2020
97a6216c-3776-521d-b7a1-bac2021cd415 | note | ITP created by: Mike Freeman
526c565d-0f9e-5f6b-8013-badc02aa04f3 | note | ITP approved for use by: Victor Mira
439412bb-3375-5fb6-8edf-db9bffbd6671 | note | 1.1 Non Dependent
2e687fe8-9045-59fb-a978-c2e201bb6d39 | note | Reference: VicRoads Section 610 November 2018
4d3ba989-5bd7-5f10-b3f4-a0244d33fced | note | 1.2 Non Dependent
2470da3b-cbe4-5d14-b0d3-b644f96ca697 | note | Reference: VicRoads Section 610 March 2019
6e3c39d7-afd1-5de7-868f-273238f2617d | note | 1.3 Non Dependent
ed1977dc-2075-5e72-8eaa-2859c103d838 | note | Reference: VicRoads Section 610 June 2019
| section | Preliminaries - Materials
| checkpoint | 2.1 Product Selection
8af14082-b525-5f70-abc9-069d565d8164 | note | REFERENCE: IFC Drawings 610.28 610.33
6004356d-2d8b-5f56-bc11-6de99949180a | note | – – – – – – – – – – – – – – – – –
dcd18a39-6f6c-58c8-9374-ea0c8ab5b9b9 | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
07abeef9-5936-5812-858b-4fb01a89b9df | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
1cdb140a-9d28-53ea-9848-0abe88a80b9c | note | ii. have the required strength at 28 days as noted on the IFC drawings.
65369d41-255c-559c-b1c3-a6f365edde69 | note | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
b0b751ab-9fe6-575f-a5c3-2bba95fbc612 | note | Note: Pedestals 200mm or greater shall be constructed from concrete - use ITP-STR-Structural Concrete instead
48bb5756-e9a2-5329-917e-792e8a3aab1b | textbox | Enter: Teambinder Material Approval number
2a5bf788-b729-5510-8b63-df6f461192e1 | note | – – – – – – – – – – – – – – – – –
a54fdd5b-07e3-549e-965d-b19fcdeae5f5 | note | METHOD: Document Review
ec201b45-453c-5e75-8a88-4d3b65c2bb89 | note | – – – – – – – – – – – – – – – – –
31df7d49-e534-5fcb-93ff-c4ea8715cc9d | note | FREQUENCY: Once, for each product, prior to placement of product
7f566be2-c785-5b39-92ce-40996d03dcb2 | note | – – – – – – – – – – – – – – – – –
da3161eb-e9e4-5cd6-a1ba-307be4c724c0 | note | CATEGORY: IP
78a2478b-c08a-5e12-a65a-4af74f3aa1a4 | note | – – – – – – – – – – – – – – – – –
d3b4a431-b022-5415-ab46-2210f5c0bc26 | note | RESPONSIBILITY: Nominated Authority
593c610d-bcb7-5687-8600-bb5a265957f1 | note | – – – – – – – – – – – – – – – – –
e909fd7d-9fa8-5d61-ae81-e6a7624a7b83 | note | VERIFYING DOCUMENTS: This ITP
bbf5c02b-a019-572d-a067-5bb1af0aeb3e | date | Date Completed:
| checkpoint | 2.2 Curing Compound
3b6592b3-6efe-5009-bf6f-8f61c5e5d55a | note | REFERENCE: 610.23 (d)
338adf53-3e21-5419-b3fd-f8197c2da158 | note | – – – – – – – – – – – – – – – – –
91ab0ee2-abbb-573b-84f7-ae99702a36ee | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
7186e716-1199-588f-a1dc-f87ecaa4ca1d | note | Note: This may be the same product used for the concrete curing
528d281e-92e4-57df-89e0-0a7959d81243 | textbox | Enter: Teambinder Material Approval number
88e61c4d-525c-5098-a3cc-1fd27aa0d593 | note | – – – – – – – – – – – – – – – – –
2415156d-4930-52c0-bf6c-f41ff825db26 | note | METHOD: Document Review
5fef31d3-bc4b-5e5b-8aaa-e045b7a95632 | note | – – – – – – – – – – – – – – – – –
fcf8c8e3-8c25-515e-aeee-3d3c64da44ef | note | FREQUENCY: Once, for each product, prior to placement of product
4cf1a894-a5dc-5eaf-aee1-b8e9250ffd65 | note | – – – – – – – – – – – – – – – – –
cd3a0525-399f-574a-beed-0239e18018d1 | note | CATEGORY: IP
bc3a835e-32e3-5249-a516-3b59c633c573 | note | – – – – – – – – – – – – – – – – –
63722781-833c-5c1e-b712-13fa9bdb7f7a | note | RESPONSIBILITY: Nominated Authority
ee61bcae-850c-5088-8842-745870285757 | note | – – – – – – – – – – – – – – – – –
d9c388ac-4ef9-5992-a7c6-7f593bb04fe5 | note | VERIFYING DOCUMENTS: This ITP
c245cc8f-5a13-56df-ae88-153733e78ba7 | date | Date Completed:
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Curing Methodology (for Concrete, Grout and Mortar)
4d3cb866-f017-5da9-ae57-264298a06db8 | note | REFERENCE: 610.23 (a)
c87f6e56-bf91-53a3-8561-276fb7f3be7b | note | – – – – – – – – – – – – – – – – –
e3874b67-7419-5cbd-8806-4031f1154e1d | note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
81e85b09-7e5c-578d-8b0b-2188849f834c | note | Note: This may be the same document used for the concrete curing.
233923bb-6be3-560a-a8d1-496c59f220b0 | textbox | Enter: Teambinder Correspondence Approval number
b548907a-575b-5dd0-9afc-13459b70c529 | note | – – – – – – – – – – – – – – – – –
270f76d4-ad9d-5fb9-8e76-6269f092114a | note | METHOD: Document Review
f7b4dd78-036b-5a8c-b4ce-e1f9c63ba788 | note | – – – – – – – – – – – – – – – – –
08fc678d-b012-5cae-8b27-1e7247e485b6 | note | FREQUENCY: Once, 4 weeks prior to placement of product
dfef7a16-7ef8-5466-a8b3-cf2eba653aae | note | – – – – – – – – – – – – – – – – –
5c344477-9f9c-5cf0-a7e6-275261acec64 | note | CATEGORY: HP
d5f8e221-88b1-58aa-a308-0ee54e91491b | note | – – – – – – – – – – – – – – – – –
6bb9ed21-92b9-5989-bc05-c0a4653de4c1 | note | RESPONSIBILITY: Nominated Authority
de1d971f-9db6-5439-a695-6089dbfc9aae | note | – – – – – – – – – – – – – – – – –
4abc0eda-9b62-5b2a-af70-3aff1dc21d79 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
3fc89285-50f5-54d6-adfb-b256c581f3b2 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
a46b9502-6417-562e-9ac6-08b617ba76d6 | note | REFERENCE: MRPA Quality Management Plan
9cc20bcd-d032-5f3d-a26b-69cd72fb78f6 | note | – – – – – – – – – – – – – – – – –
8abc2fff-6f0a-56e3-80a1-373ae005a606 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
16a38ffa-473b-5704-a12a-85e6d78db485 | note | – – – – – – – – – – – – – – – – –
11c8299a-2648-549a-b1bd-ce326bb06e85 | note | METHOD: Document Review
18957363-436c-5d76-b9f8-6865fc1ffc67 | note | – – – – – – – – – – – – – – – – –
a72591f5-aaa7-5146-9d6f-ad6d2b6f17fb | note | FREQUENCY: Prior to starting Works and at regular intervals
b88d318d-9ce9-59d8-9d81-c47c7251ace2 | note | – – – – – – – – – – – – – – – – –
b8818fed-10c6-5f09-a7d2-74d045f476d4 | note | CATEGORY: HP*
f6f6cf4a-168e-511b-b08f-aed805003584 | note | – – – – – – – – – – – – – – – – –
84ee339a-25a7-565d-a023-2297dddf0112 | note | RESPONSIBILITY: All
a1b16513-2cc8-590e-b2d3-e1656b0628ca | note | – – – – – – – – – – – – – – – – –
2eecb76e-8f74-5be9-a033-547f17292afb | note | VERIFYING DOCUMENTS: This ITP
f05a9f26-d3f6-5ab3-9e32-05ce928b290a | date | Date Completed:
| checkpoint | 4.2 Survey Set-out
f3a1dccf-4f49-5049-9061-955dd902c0f3 | note | REFERENCE: IFC Drawings
2fbba19d-d917-55ea-a0b7-ed53b80cf43c | note | 610.46 (a), Table 610.462 (Nov 2018)
28d3fdde-4d70-5556-8c3e-9428ca0e5f92 | note | 610.47 (a) Table 610.472 (March/June 2019)
27f28553-2334-5bc4-9ad9-522b5cce456c | note | – – – – – – – – – – – – – – – – –
1de93eb7-e4c0-5fd3-bdba-58fdc8a137ba | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
9982f677-59bd-53d2-bad4-0a429801230f | note | Note: Different revisions of 610 have different clause numbers
e5d40ff6-9a89-5180-835a-5d82b28313b0 | note | – – – – – – – – – – – – – – – – –
d166c60a-a110-5b03-bba5-6ede5d4c662c | note | METHOD: Measure, Visual
d0204710-7615-5f5b-8aae-a908a0438b50 | note | – – – – – – – – – – – – – – – – –
c209b9c8-7d83-58a3-b35b-06df7ffc1aa2 | note | FREQUENCY: Each element
616a974a-7295-5e22-808a-081fb54df511 | note | – – – – – – – – – – – – – – – – –
e79edd80-d6b7-586f-8a34-27c5b9e70f32 | note | CATEGORY: IP
69eed20e-85da-5012-a834-a9a6a80bcef8 | note | – – – – – – – – – – – – – – – – –
8cbc50ad-4556-5e5a-b525-207d1c98e3e7 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
50442971-f077-5328-a8f7-15d81e535a61 | note | – – – – – – – – – – – – – – – – –
96c36ee8-ceff-561c-84e7-7d2de47ea4d8 | note | VERIFYING DOCUMENTS: This ITP
a040fdf4-1422-52a6-8ce0-2c3de8659fc8 | date | Date Completed:
| checkpoint | 4.3 Construction Joint
ef08e578-0632-5032-ade9-569a5f56e3d9 | note | REFERENCE: IFC Drawings 610.20
a1362b2e-2ce2-507f-b4d0-1dddc4c00dd5 | note | – – – – – – – – – – – – – – – – –
57678532-ea3b-571b-afff-901a741d1e5e | note | ACCEPTANCE CRITERIA: Existing construction joint rebate is roughened / scabbled and set to 20mm minimum below top of the crosshead / abutment.
ceefce32-94c6-5583-bbff-927a1415f85a | note | • Concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
45d613a8-507a-5655-bb95-819f005cff06 | note | – – – – – – – – – – – – – – – – –
a8e861c8-291d-5e7c-9915-2de99f0e918a | note | METHOD: Measure, Visual
9c400e0d-14f1-55a0-bccf-6757e9148276 | note | – – – – – – – – – – – – – – – – –
45a4d496-b2a9-59f3-a6e7-9020563c3730 | note | FREQUENCY: Each element
4d1c8dcd-36b1-5574-8a92-02da8b0b79a2 | note | – – – – – – – – – – – – – – – – –
f35dd333-207f-5a23-9315-4ff49eacf01d | note | CATEGORY: IP
b39bd908-a46c-5cb1-8f1d-fca27d2e207c | note | – – – – – – – – – – – – – – – – –
c6ebc091-0fd3-5912-9d53-a99261e8f8b0 | note | RESPONSIBILITY: SE/PE/SPE
e6f824a3-ea98-5e92-b074-80ca2e5e0219 | note | – – – – – – – – – – – – – – – – –
bde9b8b4-e898-5bfe-9280-abeb442c9639 | note | VERIFYING DOCUMENTS: This ITP
27311040-529c-5119-a8a2-6aa2d501a209 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Formwork Construction & Placement
ece8280d-0823-573f-9771-e67abede504b | note | REFERENCE: IFC Drawings
dccd40d2-9555-55c8-9de9-4dafc8619b08 | note | – – – – – – – – – – – – – – – – –
f4c3c1fa-1e64-5be3-8c31-9178e43d7ac5 | note | ACCEPTANCE CRITERIA: Dimensions in plan as per drawings (typically +50mm all around).
7805b2a3-44fc-5ec3-899a-b16111ee9862 | note | • Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
18597e88-929c-5cd5-bb0b-b9a99cad1caa | note | • Any cast in componentry (ferrules, conduit etc.) secure.
4c7b5a71-894c-5d40-802f-664abe8822b3 | note | – – – – – – – – – – – – – – – – –
de2f1649-8845-5cf5-a2f9-c7d04e70e56f | note | METHOD: Measure, Visual
0a183a37-8f38-50dc-bf29-7b69e5f4f8f0 | note | – – – – – – – – – – – – – – – – –
0569928d-109a-5fd2-9798-47f4ea57800e | note | FREQUENCY: Each element
d678338d-1ef3-5a44-993e-933b6498fde1 | note | – – – – – – – – – – – – – – – – –
e2f9c196-4bbe-5c60-b5de-ac11dd7dd7de | note | CATEGORY: IP
0194e909-46fd-5579-8627-48cf892d20d7 | note | – – – – – – – – – – – – – – – – –
6aede03f-f1fd-501e-bf87-30e87e60e197 | note | RESPONSIBILITY: SE/PE/SPE
3512fe93-1094-5c3d-96cf-aff104b5797f | note | – – – – – – – – – – – – – – – – –
41fd0194-ce24-5e08-83be-e96dd0221e84 | note | VERIFYING DOCUMENTS: This ITP
ccaf94f0-9f1d-53cc-ad91-09211da46c5e | date | Date Completed:
| checkpoint | 5.2 Pre-pour Inspection
2943e191-dae6-58be-b1c7-72a1d51e4099 | note | REFERENCE: IFC Drawings 610.20
93911069-4a5e-5ffa-a2d4-9b75309e95f9 | note | – – – – – – – – – – – – – – – – –
d4f9c232-4146-5d62-bdbb-31c2b05b9194 | note | ACCEPTANCE CRITERIA: Formwork location and RLs comply.
307dd6d3-62b4-5546-a9ab-f89fefb83b65 | note | • Any reinforcement has the required cover.
2f1dac6d-a255-5de7-9fd4-fc4ddb71c5cb | note | • Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
f526c809-0aa3-5b0a-a207-2b8d3e84dc2e | note | – – – – – – – – – – – – – – – – –
78bd615c-a9bd-5074-a66a-fab105b74ac8 | note | METHOD: Measure, Visual
996ed0f1-b078-5d82-874a-cb15133d6b98 | note | – – – – – – – – – – – – – – – – –
3db24b42-af13-510f-b090-0ed7f21b914a | note | FREQUENCY: Each element
26457328-27a8-5f51-954f-d84ed014e34d | note | – – – – – – – – – – – – – – – – –
9d8f6174-01a2-5d5a-ac26-41d7f061335b | note | CATEGORY: IP
43e5846d-c624-5761-b953-d473b52e72ef | note | – – – – – – – – – – – – – – – – –
58ef245c-90a8-5be0-9ae6-294c4c5db2f8 | note | RESPONSIBILITY: SE/PE/SPE
c8c3759c-99e7-5e0a-9d81-e01a61bcb441 | note | – – – – – – – – – – – – – – – – –
4085c8a9-2558-533e-ae76-dd57e33fe731 | note | VERIFYING DOCUMENTS: This ITP
66552718-a67b-5434-80bf-6a39c2dbc57a | date | Date Completed:
| checkpoint | 5.3 Weather Conditions
9f420ec8-9a0c-5031-a979-514890f75710 | note | REFERENCE: 610.17, 610.17 (a) & (e), Table 610.171
995de2eb-bdc3-556f-82dc-8c9a4b056c66 | note | – – – – – – – – – – – – – – – – –
dcc16b88-8a59-58e1-86ec-2a1eff45a7f9 | note | ACCEPTANCE CRITERIA: All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
e8520d58-a89a-5315-a896-b1c9fb8d7bca | note | • The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
19ef1bda-d86f-5c08-ae44-87bc2fa41bb6 | note | Record: Required information on the Grout Pour Record.
71b2461b-38c1-5e73-a61b-59ffa98806da | note | – – – – – – – – – – – – – – – – –
7d9dcba0-8812-5413-9b48-911019357d28 | note | METHOD: Measure, Visual
0621ad08-317a-5795-968a-91e80732e9b2 | note | – – – – – – – – – – – – – – – – –
5d750814-546d-5c34-a0f4-6a821ef9ae4d | note | FREQUENCY: Each element
2f8a9453-9e6b-508c-841e-ea8139035c41 | note | – – – – – – – – – – – – – – – – –
ae94bf5d-8a3b-5ccb-9afa-3050155a2f6f | note | CATEGORY: IP
53837178-32cf-5c4e-a521-f119678cb610 | note | – – – – – – – – – – – – – – – – –
be532401-6bdc-5164-a545-f4b6fb5dbce9 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
7ab0f61d-46bd-5c4f-804a-b4eaf9bd2a6a | note | – – – – – – – – – – – – – – – – –
050361c0-32f6-5833-a637-ea42d7899f00 | note | VERIFYING DOCUMENTS: This ITP
cd6fbf60-327d-5bc6-9b3f-6f07b1c0fefb | date | Date Completed:
| checkpoint | 5.4 Mixing Product
30d87baa-4a66-5e8b-9b2c-b8d6ca185f83 | note | REFERENCE: Product TDS 610.28
639cf6a8-5f36-58b6-b6ff-905f2bca7ca1 | note | – – – – – – – – – – – – – – – – –
ce9783d8-b7da-5a4d-b5b8-db16c24d25cf | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
d97917a3-1c41-5a2b-b55b-b37907f9e25c | note | • Only whole bags to be mixed with potable water.
a036c255-a672-5c35-91dc-c7cfd5239ac3 | note | • Volume of water matches the required amount for flowable consistency and accurately measured.
7a92148f-776c-58c0-a514-502d60d2e2d6 | note | • Product poured into the mixer slowly.
4cf06414-117a-5101-8f14-2facecf89e64 | note | • Mixing time as per TDS so that a smooth, even consistency is obtained.
4079fd16-54c3-5e42-82e1-6226a63d2615 | textbox | Enter: Required information on the Grout Pour Record.
393007c6-34f9-5798-8db6-eff10b7b53a0 | note | – – – – – – – – – – – – – – – – –
2bdfd8fe-5076-5bed-a8b1-7877c5275ca6 | note | METHOD: Measure, Visual
d9b3c1b4-74f1-534b-b5e3-c6bc6096b886 | note | – – – – – – – – – – – – – – – – –
2e918aff-d0b5-5514-91a6-9972f7833fff | note | FREQUENCY: Each batch
ab97406b-2d4a-5506-827e-029fe265c451 | note | – – – – – – – – – – – – – – – – –
db1350ca-4c9d-5bde-9a83-db7aae96314b | note | CATEGORY: IP
9d510b93-73b9-500e-87ef-8795033c9de8 | note | – – – – – – – – – – – – – – – – –
12deb436-60db-5e47-a979-d4669635e30c | note | RESPONSIBILITY: SE/PE/SPE
3fefd126-57a8-54ae-a21c-1e8aa4449f19 | note | – – – – – – – – – – – – – – – – –
461207cf-78dc-545d-90fc-38142d51c439 | note | VERIFYING DOCUMENTS: This ITP
d39bff96-334a-5c31-99b1-f017268750b5 | date | Date Completed:
| section | Construction Activities (Continued)
| checkpoint | 5.5 Product Testing - Compressive Strength Cubes
94c74fff-eb13-53e3-a3ae-8f0efc3a62c5 | note | REFERENCE: 610.28, 610.33
c8350169-c21f-5f24-a15b-dd718450531c | note | – – – – – – – – – – – – – – – – –
ae3ca094-b8c0-5923-8e79-dcb935f70929 | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
d475c6bb-be3f-529b-bfd9-642c23c441d1 | note | • Testing is be in accordance with the following frequencies:
20785c39-5e28-505e-acef-7a492bbed24c | note | • First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
716fe519-3b02-58d5-bb51-a76c5e042e84 | note | • Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
e8f49cdb-5a0d-52f2-9a83-87dab094ecad | textbox | Enter: Required information on the Grout Pour Record.
4b22c361-5a80-5f8a-8ceb-21ed3e1487e3 | note | – – – – – – – – – – – – – – – – –
9f2bbe0c-f1c2-5254-a1aa-ae77c1270c99 | note | METHOD: Test
608db77c-af8e-5b8f-8cb3-3562f5c3c051 | note | – – – – – – – – – – – – – – – – –
1168c84f-9d56-5d00-b95f-848fbd2862dd | note | FREQUENCY: Each element
d09cb06a-b7d4-5318-bc9a-391a2b391ea3 | note | – – – – – – – – – – – – – – – – –
bdbc0bc3-b504-534d-b70c-1b48e43a549c | note | CATEGORY: IP
9d1d9990-77e6-578f-8aa9-d7aae39bee5f | note | – – – – – – – – – – – – – – – – –
04653a17-5dc4-5cd6-95e8-b20326fd1987 | note | RESPONSIBILITY: Tester, SE/PE/SPE
ef802324-87e0-5038-838c-cf8b20e8af40 | note | – – – – – – – – – – – – – – – – –
a94dd1a0-eb61-5115-b26e-08579215ea33 | note | VERIFYING DOCUMENTS: This ITP
1cb9111b-4629-5ecb-b676-4dcf72ce919d | date | Date Completed:
| checkpoint | 5.6 Placement & Compaction
cff3d42a-71b5-54d8-9871-913271d0b93c | note | REFERENCE: Product TDS
d0037862-25cb-5216-ba31-dc57332915c7 | note | – – – – – – – – – – – – – – – – –
ebf39aa0-6b09-5d2d-a2e9-a87c34d52d57 | note | ACCEPTANCE CRITERIA: All batches are traceable.
c7cd77fc-2a44-5af0-a1c7-dc5095661e10 | note | • Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
8dbb0b89-b330-5880-8a9f-54faded9f32e | note | • Product should flow to all areas and self consolidate.
e53f90e5-39f8-5a5d-a19f-4b3bfa2eca67 | note | • Product that stiffens or is showing signs of stiffening shall not be used.
876fecba-9f71-5669-8837-7ab64d1f5591 | textbox | Enter: Required information on the Grout Pour Record
3b4b1931-ada5-5f42-91df-face82777f10 | note | – – – – – – – – – – – – – – – – –
46b85755-0f79-527e-a578-2bc8fc1e0171 | note | METHOD: Visual
9a6ab97c-cc0f-59cb-8e68-d70858333539 | note | – – – – – – – – – – – – – – – – –
11a80116-81a9-5681-9ac5-f774ae05c47e | note | FREQUENCY: Each element
ec2e9329-796e-5057-b899-c8750899880a | note | – – – – – – – – – – – – – – – – –
9372a69e-3dff-532a-8080-c0806db4b1df | note | CATEGORY: IP
be1e70e7-87b7-5f7b-ac03-c50c7dc7e0da | note | – – – – – – – – – – – – – – – – –
86adf0ff-a528-595f-a286-911b2781e8d2 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
5e4d1ae2-7c70-57e1-bca3-dcb6cd424389 | note | – – – – – – – – – – – – – – – – –
7a4ae0b0-ebd8-574e-9e73-00034e4af551 | note | VERIFYING DOCUMENTS: This ITP
9ee5179e-8367-546e-8db6-51bc5db2a74c | date | Date Completed:
| checkpoint | 5.7 Surface Finishes
044ce5cc-1231-51b7-8b06-9596651140ed | note | REFERENCE: 610.28
b4126b99-8155-5916-9eaa-676b2380c4ab | note | – – – – – – – – – – – – – – – – –
765feedf-1ed0-5781-a381-0022abcea9fb | note | ACCEPTANCE CRITERIA: Surface finish shall be flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper.
1353faad-ae48-5a77-b8ce-d5b3327d0e5b | note | – – – – – – – – – – – – – – – – –
ce04472b-0c19-5f7d-8bec-9e74c339b3de | note | METHOD: Visual
5e015469-5804-52cd-8234-bc7389a4a53a | note | – – – – – – – – – – – – – – – – –
7f77954f-f019-5ffc-9cf6-90bcbca7ad09 | note | FREQUENCY: Each element
4332d488-1cce-5310-b290-d72540895f5c | note | – – – – – – – – – – – – – – – – –
c680e972-3225-5a47-9953-e24da8bb80c4 | note | CATEGORY: IP
caf613d0-0499-5e17-b459-c7ee215738ed | note | – – – – – – – – – – – – – – – – –
8878c60d-6a27-5761-98b0-0c0388a68621 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
970c0260-50ca-5321-872e-e3d8b88bdda2 | note | – – – – – – – – – – – – – – – – –
181cccf8-5f91-54d1-ac69-ca391b7c33b7 | note | VERIFYING DOCUMENTS: This ITP
77f8d9cf-d248-50fd-bbe4-978843977d61 | date | Date Completed:
| checkpoint | 5.8 Curing
a019c691-387e-5066-8f33-1f5e8cdf5ee1 | note | REFERENCE: Curing Methodology 610.23 Table 610.231
baf9616e-8d7d-5ba1-a3a2-53e4754c0833 | note | – – – – – – – – – – – – – – – – –
77fca5b4-a6ae-5e2b-bb5c-6822c239e2cf | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
409c4f4c-5477-5f9c-aa8d-eeba749fc03f | note | • Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
a0f9c48d-e88d-5b52-862a-733d29044c25 | note | – – – – – – – – – – – – – – – – –
9aeab052-985c-52dc-89a9-76fd71adadc8 | note | METHOD: Visual
a6853d3d-b0eb-5b29-be9f-fee72f0fc466 | note | – – – – – – – – – – – – – – – – –
efa3e3db-d6b1-53f1-8d06-a357b7c02c66 | note | FREQUENCY: Each element
e426b241-80c8-51b1-8203-6c2e21be4331 | note | – – – – – – – – – – – – – – – – –
c765c6eb-ea58-5275-ab6f-7b50fa7fe8dc | note | CATEGORY: IP
54eeb532-e543-5920-8faf-4ebd5275ded5 | note | – – – – – – – – – – – – – – – – –
5e675f13-1bf4-567e-92ef-e068d103ebcb | note | RESPONSIBILITY: Foreman, SE/PE/SPE
831d65d0-fa20-5639-8700-0c9d452eb8a1 | note | – – – – – – – – – – – – – – – – –
f591089c-c7f9-5fba-862f-003962721734 | note | VERIFYING DOCUMENTS: This ITP
e7b3d232-893e-5cf4-91f3-4eeb992328e0 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Compressive Strength Test Results
adf115c0-390a-5a86-a0e4-80d4ea9e86fe | note | REFERENCE: IFC Drawings, Product TDS
64f15634-dce7-5ed0-98ad-d22b9c1437ce | note | – – – – – – – – – – – – – – – – –
6c117eea-a6fa-58dc-827b-8cd735b5c88f | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
e882b0cd-fac1-51f3-aba6-3bbe992eb51f | note | • 28 day compressive strength per sample comply with the design strength.
8b718294-e284-5377-ae6f-e9bfcfbc6527 | note | Attach: Compressive Strength Test Results
2fb7b1cd-1b96-5176-8107-d19848a50f66 | note | – – – – – – – – – – – – – – – – –
058c80b5-001a-5667-a383-85e20d8e8bbb | note | METHOD: Document Review
77c91b55-710e-51fd-8b8a-1c52e98ddd47 | note | – – – – – – – – – – – – – – – – –
64cef770-ba91-5827-8fc5-02616a6b7198 | note | FREQUENCY: Each cube
cce49b0b-1fe6-58bb-9446-9bfc0ea72732 | note | – – – – – – – – – – – – – – – – –
f089ff72-fad8-5937-936c-7b08c49811c8 | note | CATEGORY: IP
652deb9e-5195-5851-bad9-01a09686d9a4 | note | – – – – – – – – – – – – – – – – –
3909cd7c-716b-542a-9df5-715ff4bcc9bf | note | RESPONSIBILITY: SE/PE/SPE
6800cc0a-c416-53e1-aeb5-8ad2c4ac6b18 | note | – – – – – – – – – – – – – – – – –
1d2e07e7-0033-54eb-aa92-bf86d31eb91c | note | VERIFYING DOCUMENTS: This ITP
972a6dc6-068d-5d3c-89a4-56374c693d04 | date | Date Completed:
| checkpoint | 6.2 As-built Survey
022bf9b8-5160-56a8-95e2-b7bf4bfbea50 | note | REFERENCE: IFC Drawings
50e2bd30-11c6-5f53-a51f-be010569db4a | note | 610.46 (a), Table 610.462 (Nov 2018)
e911221a-33d6-5a5a-8991-136b0e058964 | note | 610.47 (a) Table 610.472 (March/June 2019)
f55d9a99-771d-56bc-899a-227715b106b3 | note | – – – – – – – – – – – – – – – – –
4aceba84-89af-500a-b8ad-67602355d714 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below:
5edaf789-d07f-5f8a-8384-822f337771e5 | note | • Reduced level ±2.5mm
f516f56a-f189-5603-b06b-451aa60b2d54 | note | • Variation from grade across the width of individual pedestals shall not exceed 1 in 200
29e67264-4b36-5181-8c33-dc72cdeb6f8e | note | • Deviation from flat surface ±1mm
41330aa1-6692-593c-be39-8fcc0a8961ac | note | Note: Different revisions of 610 have different clause numbers
dc911d99-cc25-57be-862d-9a497710a5db | note | Attach: Survey As-builts / Survey Report
dbfdc535-9558-50e2-8619-76f9b014c744 | note | – – – – – – – – – – – – – – – – –
ef649933-c86c-5d32-b540-10e913fa72d0 | note | METHOD: Document Review
9cb88343-58a2-5f3d-9880-94c58b09e138 | note | – – – – – – – – – – – – – – – – –
c8617aca-2f90-5bfb-acc3-393b0c887e70 | note | FREQUENCY: Each element
3ec7b393-c262-5ed9-bcd0-874125fa2952 | note | – – – – – – – – – – – – – – – – –
3201e900-0549-5a83-a262-1f0f7316503f | note | CATEGORY: IP
5a1b1e71-250c-56bc-9423-1839ccbb9b8f | note | – – – – – – – – – – – – – – – – –
dd6480ab-4f19-5886-85e6-223d377c1a74 | note | RESPONSIBILITY: Surveyor, PE/SE/SPE
738787b9-e1fa-5c15-bd0a-4d0951a0cbbc | note | – – – – – – – – – – – – – – – – –
ecaa4bdf-3a6a-5db9-ae67-1c6f03dcb266 | note | VERIFYING DOCUMENTS: This ITP
38620732-ff49-5f14-919a-d13ccaf184bb | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
58b3ebe0-00fe-58b5-a7a9-d04ea6ce0c61 | note | REFERENCE: MRPA Quality Management Plan
280cd43a-bcb1-54cd-a4a7-9af4c5b9f9fb | note | – – – – – – – – – – – – – – – – –
5a7911f1-7fd1-5677-8855-8492dc815206 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
24035e1a-0f3d-5a1f-8ab7-5c767d365262 | note | – – – – – – – – – – – – – – – – –
7d60f900-ac2c-598b-85ed-8eb04b6e87dc | note | METHOD: Document Review
93d604f9-4332-5c0d-abfd-7efaf67dc51a | note | – – – – – – – – – – – – – – – – –
2b70a4d0-f470-5309-bad8-4e6fdb1986fe | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
6e2eaa47-3538-5a2f-8215-6cfefcd79eea | note | – – – – – – – – – – – – – – – – –
fa13a7b8-1c29-52c1-aeb5-be9fcfbe4b43 | note | CATEGORY: HP*
db43960e-73ff-5148-8399-cd62cb435b57 | note | – – – – – – – – – – – – – – – – –
5f40ccc9-7ed8-5554-b880-5671091cff50 | note | RESPONSIBILITY: PE/SE/SPE
91539dd8-dd82-58ef-b55c-e8e28c77f684 | note | – – – – – – – – – – – – – – – – –
4c598597-0244-5874-9efe-2e86298d33d8 | note | VERIFYING DOCUMENTS: This ITP
0af0e0ba-c65f-55e4-b6b5-b0f1ada7765f | date | Date Completed:
| checkpoint | Final Inspection
24ec4667-573d-5b7d-beb5-e703902b02a2 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
291f208d-34f1-554e-a274-0b1d2f22455c | textbox | Name:
48424a93-ea07-5f53-8283-a5491f3c716d | textbox | Position:
6f6c2d08-de72-5a0c-984b-f576bdfafa27 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-034-STR-CAMMS-Precast Crosshead (Supply & Installation) Rev 0 | itp | ITP-034-STR-CAMMS-Precast Crosshead (Supply & Installation) |  | 9ea3dbe5-2268-4e1f-b814-2658ef3b787c
| section | Referenced Documentation
| checkpoint | Referenced Documentation
c5c03ab1-d197-5303-8d19-5138e0ce08ba | note | Document Title: ITP-STR-CAMMS-Precast Crosshead (Supply & Installation)
94aabaec-4876-5a81-8cb8-1e7b6df8b3b8 | note | ITP Description: CAMMS-Precast Crosshead (Supply & Installation)
7d41edda-a077-5082-a619-c6044d6f1c19 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
8b952032-83c7-5bf1-878a-376f25513f48 | note | Discipline (e.g. CIV/STR/RAIL): STR
3363a0e5-dec5-5f20-8900-523f8990de6b | note | Revision Number: 0
3f22834d-592d-5461-9841-c4e94a8d8c34 | note | Revision Date: 17/05/2023
0081e997-b10d-51f8-b892-98c51b3544c2 | note | ITP created by: Isaac El Zayat
a33b731e-1780-51c4-9429-67f7091d70f0 | note | ITP approved for use by: Victor Mira
fe804b0c-1742-57b1-a9ca-0a6ab74757bc | note | 1.1 Non Dependent
8e11113a-7ace-5f5b-8ebf-73412ea7f4e0 | note | Reference: VicRoads Section 169 July 1993
563eaa2a-42b8-565f-af1e-5c48307dc185 | note | 1.2 Non Dependent
a4a011d3-d9b4-5d9f-b2d5-93a148f1aaeb | note | Reference: VicRoads Section 610 March 2019
c2474c16-16a4-5597-9b19-5912a226c91c | note | 1.3 Non Dependent
4e66217b-a240-5701-a012-0ae7cdbdc80e | note | Reference: VicRoads Section 611 November 2018
a379f600-47fb-5d9c-bf81-7ada16def388 | note | 1.4 Non Dependent
c572895e-3637-599f-b837-2661a7955530 | note | Reference: VicRoads Section 613 June 2017
d84de799-748b-5c25-a532-3222fb8cdb8f | note | 1.5 Non Dependent
84a99e07-49a3-5dfb-9952-3d6da75c992f | note | Reference: VicRoads Section 620 May 2009
| section | Preliminaries - Materials
| checkpoint | 2.1 Grout - Product Selection - Epoxy Grout
8c4a8ea5-5a55-5874-952a-ab7686e29566 | note | REFERENCE: IFC Drawings
0d5d2544-8714-554d-96a5-8b056adcb265 | note | – – – – – – – – – – – – – – – – –
a244e292-0b8b-5335-809a-76205411535f | note | ACCEPTANCE CRITERIA: Details of the materials and the proportions of grout mixture shall be submitted for review. Product to be selected based on the following criteria:
3d4c2e3d-ade8-5cad-903e-3147688799bb | note | i. have the required strength at 28 days as noted on the IFC drawings.
b3d1c5f6-faaa-5cdd-bf2d-b150a057cf2c | note | ii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
8afcd50d-daae-58b9-b197-f29e68867c89 | textbox | Enter: Teambinder Material Approval number
4e5fbfed-020d-585c-a83f-ee44a94577cf | note | – – – – – – – – – – – – – – – – –
06f193b4-eb8e-5081-95e8-139fb49f3565 | note | METHOD: Document Review
589084bf-9c9e-5b64-8e14-44a8a4a07e9a | note | – – – – – – – – – – – – – – – – –
cdef794f-d6b4-563b-a50a-93bad80bca64 | note | FREQUENCY: Once, for each product, prior to placement of product
593556b7-90cc-541b-9b36-6d9811669fcc | note | – – – – – – – – – – – – – – – – –
c374ffe1-33ae-58ce-bf14-ef40e2373863 | note | CATEGORY: HP
ed978fed-09ca-5b66-90a8-c6ee140da117 | note | – – – – – – – – – – – – – – – – –
fa63254c-f3e6-51dd-9c16-144054c675a3 | note | RESPONSIBILITY: Nominated Authority
20a649c6-88c3-563c-bfb5-148b1bb5f15d | note | – – – – – – – – – – – – – – – – –
ef534fe1-5fb2-5f13-b40d-3826349b9033 | note | VERIFYING DOCUMENTS: This ITP
0a0932c1-71f8-5815-b5a1-77db349223a1 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Precast Elements
d296d252-da59-566c-8fe6-0589e56b8781 | note | REFERENCE: IFC Drawings 610.47 (a), Table 610.474, 620.09
2e521ea3-33a1-5e16-a2e7-3df9c79fd114 | note | – – – – – – – – – – – – – – – – –
dae11110-fbc0-5cdf-b217-53286208dde6 | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
d891c980-def3-5d90-8085-0ca605ccfa3a | note | i. Certificate of Compliance / Birth Certificate
8d69f072-0e07-51c6-aa21-5f2ef22118ca | note | ii. Compressive strength test results
99df3633-7285-51cd-b854-23eb0451ff8d | note | iii. Precast Lifting Design
6581e9e8-23f0-5fa6-9565-d42b6faa13fd | note | iv. Pre-pour check sheet / ITP
daed7544-369b-50c5-b01e-cdf61211881a | note | v. Pre-stressing check sheet / ITP
fd081031-2d1d-5b5d-a272-5e5c2082160c | note | vi. Post-pour check sheet / ITP
7d79754d-ad46-58a4-8361-891601dac273 | note | vii. Covermeter check record
609cb606-8d2b-546e-8eef-7c78b9ffee68 | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (where applicable) shown on table 610.473
84716f81-b50f-5fbf-a817-9394a9fd2821 | note | Note: Different revisions of 610 have different clause numbers
ba025fd8-6c0c-513d-8a12-aca34806b8ec | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
e93fba8c-2cfd-50b1-8ee7-d3eeae7a7807 | textbox | Enter: Teambinder Approval number
e4a30398-3116-50a3-95f4-a00a6209aec4 | note | – – – – – – – – – – – – – – – – –
eeb934fb-74cc-5ea1-88a4-baf59bb7008e | note | METHOD: Document Review
08107416-5592-5801-9a94-7f62f08bf19c | note | – – – – – – – – – – – – – – – – –
ae85dfb7-be4f-540b-bffa-5eebde1c7221 | note | FREQUENCY: Each element
e77a7bec-2874-5f5e-8bf8-afa20fc1f814 | note | – – – – – – – – – – – – – – – – –
fbabd57a-d931-5e83-85cf-17f04a7aa1ff | note | CATEGORY: IP
d5be34a9-0ebc-573d-b10f-fe0a2dc229d6 | note | – – – – – – – – – – – – – – – – –
89a562ae-eb8e-5b3f-b1d7-90e1678d2e6a | note | RESPONSIBILITY: PE/SPE
9df77762-f3fe-5906-95a9-1a2b5f910e76 | note | – – – – – – – – – – – – – – – – –
fe3f1964-ec95-5c93-a181-3f3020fadede | note | VERIFYING DOCUMENTS: This ITP
88e94eb4-f63d-5869-b128-23d31158b984 | date | Date Completed:
| section | Pre-installation Activities
| checkpoint | 4.1 Precast Element - Minimum Concrete Compressive Strength
d39222f4-cf50-5256-a014-6bbabe9a8516 | note | REFERENCE: 620.03, Ancon Lifting Design
c3549342-c8cc-573a-bb83-5b38a170ffc1 | note | – – – – – – – – – – – – – – – – –
f92bada4-02cd-585e-85d3-8a0d7b6a95ab | note | ACCEPTANCE CRITERIA: Lifting of precast units to be minimum concrete compressive strength of 20 Mpa.
b4d08ed9-bd39-529e-8170-57992a108c13 | note | • Ancon lifting design requires minimum concrete compressive strength of 30 Mpa.
11148c5e-044f-5083-942e-ac1d143ed340 | note | • Verify compressive strength test results prior to lift.
a159e537-f6a8-5b86-bbd9-397eb5c81e0b | note | – – – – – – – – – – – – – – – – –
58266641-9009-587a-8d46-d4a2e299e595 | note | METHOD: Document review
cb892667-2451-5cd1-a483-12ba3442eed3 | note | – – – – – – – – – – – – – – – – –
cefe0045-a6b0-5522-9c95-7eb2547d71bc | note | FREQUENCY: Each element
78b71789-a00a-5633-a0ce-93c18ad6953f | note | – – – – – – – – – – – – – – – – –
69dc8b75-8158-5b79-856c-87a03b3f1bba | note | CATEGORY: HP*
d01c7fa7-e6df-545a-bb1c-270b495a51bb | note | – – – – – – – – – – – – – – – – –
7aeb2797-ec2c-5cd3-8240-5a21db583c3d | note | RESPONSIBILITY: SE/PE/SPE
7ac7de11-d179-545e-ba72-1039a926e77e | note | – – – – – – – – – – – – – – – – –
9c0175a0-b980-57c9-983c-91d00c139bac | note | VERIFYING DOCUMENTS: This ITP
384af615-d192-5f0d-9981-e0d7266a2a28 | date | Date Completed:
| checkpoint | 4.2 IFC Drawings
99a589af-b18c-5c22-bcfc-ba6918eb32b8 | note | REFERENCE: MRPA Quality Management Plan
e39fc129-0e4f-5a51-a0a6-19c7143797a4 | note | – – – – – – – – – – – – – – – – –
847f5b42-9ceb-59b3-bed9-90de7dae63c6 | note | ACCEPTANCE CRITERIA: Revision of the IFC drawings are current as per the drawing register (on Teambinder)
4f70ada3-82c7-5b1d-a286-82064fb8273f | note | – – – – – – – – – – – – – – – – –
404da320-83fa-5e00-bef0-395b369af30f | note | METHOD: Document Review
5dc36d1d-b131-52a6-918a-f870a201ce4a | note | – – – – – – – – – – – – – – – – –
c89cef88-c667-51eb-afba-e38026814c4a | note | FREQUENCY: Prior to starting Works and at regular intervals
c8a621b1-6bff-5906-a3ba-7c4c35a88e74 | note | – – – – – – – – – – – – – – – – –
d48c2366-31d4-5692-8709-280f1403aba9 | note | CATEGORY: HP*
d32fd8e4-d7f9-54e8-b233-86f19ae14be7 | note | – – – – – – – – – – – – – – – – –
5e6b0251-71fa-55e6-8f49-471902cc519f | note | RESPONSIBILITY: All
9494412d-7d84-572c-be76-5032da4c697c | note | – – – – – – – – – – – – – – – – –
d0c6f342-1000-5c22-b5de-d3b6c99e8762 | note | VERIFYING DOCUMENTS: This ITP
8c66c683-60b6-55e0-a417-f5adf7a66dd2 | date | Date Completed:
| checkpoint | 4.3 Survey Set-out of Precast Elements
7e1a5490-785d-5a35-9f15-266066decbaa | note | REFERENCE: IFC Drawings 610.47 (a), Table 610.472
e51c8805-37bc-5bd7-afa1-2132e509283c | note | – – – – – – – – – – – – – – – – –
a5cb3588-6a5b-5d8d-8880-16399c2a6408 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the Table 610.473 as applicable to the element.
2ae5a4fd-454e-52e0-b851-3f5923de2b70 | note | – – – – – – – – – – – – – – – – –
2593f2e1-a90f-5083-bf16-826a240d3111 | note | METHOD: Measure
0e7e5e26-298a-5410-b612-af13d8e9b53d | note | – – – – – – – – – – – – – – – – –
701f7acb-5fdc-509a-af03-2c25c69fbbb7 | note | FREQUENCY: Each element
fed068fb-f4ef-5887-af2e-4c88937f31ad | note | – – – – – – – – – – – – – – – – –
0d4bad25-723c-5e7f-a609-7a7aa5f892f3 | note | CATEGORY: IP
65b1c31f-1619-56cb-8778-2dcee6c5636d | note | – – – – – – – – – – – – – – – – –
358ed924-1337-5216-bce7-d94a41bada14 | note | RESPONSIBILITY: Surveyor, PE/SPE
3f0637a2-5541-5022-8d27-05feef5e726d | note | – – – – – – – – – – – – – – – – –
d0c11c34-6d7a-534d-886b-831117bfafb0 | note | VERIFYING DOCUMENTS: This ITP
1cdc370f-3054-59f9-b0c0-d43a381b3daf | date | Date Completed:
| checkpoint | 4.4 Scabble (Green Cut) Column
b9d412cc-d8d7-59d3-99fd-a0d4e5192bc2 | note | REFERENCE: 610.2
77d12098-446b-5ca0-8b1c-da6307dd591a | note | – – – – – – – – – – – – – – – – –
0f013922-ee8c-556b-88ed-dfc2de91ae2c | note | ACCEPTANCE CRITERIA: Construction joints shall be prepared to produce a well-bonded interface between hardened concrete and freshly placed concrete.
615d8057-2596-5cee-ba4f-f300a121d213 | note | • 3mm of coarse aggregate to be exposed.
ae7d6831-388f-5faf-861c-a3b2a538d3de | note | • Surface to be moistened, with excess water removed.
8a6be621-9a78-5439-84b2-5f94a2a7a853 | note | – – – – – – – – – – – – – – – – –
406f0d35-226e-5956-b934-ebc1294c5770 | note | METHOD: Visual
990ab891-9bae-5873-91fa-233bec362875 | note | – – – – – – – – – – – – – – – – –
8d973082-4b42-59be-93e8-6f8ad7196b44 | note | FREQUENCY: Each element
d1c40093-0639-5e58-9f5d-b6d50d81c223 | note | – – – – – – – – – – – – – – – – –
40867c07-b56f-5b65-ab14-fa99834b1235 | note | CATEGORY: IP
437f1c68-5174-573e-b12f-386b1e959d49 | note | – – – – – – – – – – – – – – – – –
a5fbcd78-bce5-551d-a8a6-c5f5d65378e9 | note | RESPONSIBILITY: SE/PE/SPE
7c322145-be8d-59be-96e6-7454aaff03f6 | note | – – – – – – – – – – – – – – – – –
c4a6b9b6-54e3-5dda-aa0e-7c3435bba564 | note | VERIFYING DOCUMENTS: This ITP
6b77e98d-999b-5f27-bb50-3f4cf3389d51 | date | Date Completed:
| checkpoint | 4.5 Install Packers
f11a361c-7490-5526-985d-6a22bbe3404c | note | REFERENCE: IFC Drawings, Temporary Works, Table 610.472
49af8700-17db-5054-b485-d6b0580bfeb1 | note | – – – – – – – – – – – – – – – – –
c0125aab-37df-5ecc-840e-a01db73e8dbc | note | ACCEPTANCE CRITERIA: Place packers to the survey marks at each column in accordance with approved temporary works and tolerances.
0a3c7220-0148-52a2-a4c0-36a1d8a1099c | note | • Scabbled surface to be levelled where packers to be placed.
020f8aea-eb79-5911-8077-ddd389d3dc01 | note | • Packers to be checked for survey tolerance of crosshead reduced level. (±10mm for reduced level for piers as per 610.472 (ix))
f35b2a44-c186-547e-aa3c-2d69cfb5da3a | note | – – – – – – – – – – – – – – – – –
64e59584-a421-5b33-baec-4d8bfa69028f | note | METHOD: Measure, Visual
98e06c92-8cda-5953-a26a-945dde4f66f5 | note | – – – – – – – – – – – – – – – – –
d76ead67-6097-5500-ae80-6fc89de36a32 | note | FREQUENCY: Each element
286b6afc-b3c4-5998-aed8-203a4558558d | note | – – – – – – – – – – – – – – – – –
ffe8b812-2578-5043-9e71-37b223cc1b4a | note | CATEGORY: IP
4c7fd559-d990-578e-8e16-6106e9e572fe | note | – – – – – – – – – – – – – – – – –
d85a0f23-f8b3-5851-8b4d-4f6c7cf102cb | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
febb8ad9-00fe-5424-8025-d3831ded24e7 | note | – – – – – – – – – – – – – – – – –
2985e565-a0f7-5ea1-a9ff-bc4c06169d8f | note | VERIFYING DOCUMENTS: This ITP
c5b96d23-f4e2-5d5d-ac20-5e3507649f31 | date | Date Completed:
| checkpoint | 4.6 Bleed tube
85819e6a-a8a4-552a-89c5-c802960684a6 | note | REFERENCE: IFC Drawings
2b76e5c2-3706-58fc-802e-6125b581b0e8 | note | – – – – – – – – – – – – – – – – –
33df8160-94cb-54fc-b8c8-55ef268500fd | note | ACCEPTANCE CRITERIA: Minimum 3 No.Bleed tubes per pile are installed
ac3cda62-b969-5eef-be13-2a858dd787a2 | note | – – – – – – – – – – – – – – – – –
f577052d-a4ab-528d-91ca-7a2feca23e64 | note | METHOD: Visual
71dcaded-d13d-5a53-977c-e2c553f450e3 | note | – – – – – – – – – – – – – – – – –
a7a28e55-340a-5046-9de0-c7d9ba1cc946 | note | FREQUENCY: Each pile
85f75a82-a6ef-56cb-b431-3244a50fa784 | note | – – – – – – – – – – – – – – – – –
0005b791-e6cf-539a-9cfb-4bd7cd7c8249 | note | CATEGORY: IP
984563db-66c8-5476-8b5e-e4088af277db | note | – – – – – – – – – – – – – – – – –
2e62b3bc-345b-5e06-94f5-043f84fe0026 | note | RESPONSIBILITY: PE/SPE
45bd67c6-d421-58b5-ae8f-91b69ee992a8 | note | – – – – – – – – – – – – – – – – –
b96cd6c7-2c8e-5ba0-bb3c-7d8cd107f2ed | note | VERIFYING DOCUMENTS: This ITP
001177f5-74b9-5a44-a684-f75deffcec7d | date | Date Completed:
| checkpoint | 4.7 Sealant & Bleed Tubes
7c11c951-10f2-50a7-bd21-9de2f5fa4047 | note | REFERENCE: IFC Drawings, Product TDS / Application Guide
cd1e28a3-5cbe-5aba-89db-311c4d1e66d7 | note | – – – – – – – – – – – – – – – – –
b0589bc8-8104-509d-aea9-b537d07376fc | note | ACCEPTANCE CRITERIA: Seal perimeter of column, excluding 3 No. min bleed tubes per column to be equally spaced.
0fb43ddf-f925-527d-a03a-0dd97379ccde | note | • Thin layer of wax compound to be applied to forms to minimise grout sticking.
6e53a636-6cc6-5441-baca-743f837a1f90 | note | • Do NOT pre-soak when using resin based grouts.
7734465f-7b1a-5b66-8db0-22fe905feb60 | note | – – – – – – – – – – – – – – – – –
c18ac9d8-55cb-57aa-8dcd-1e2551dd9049 | note | METHOD: Visual
8b17dab8-a3e1-5aaa-a382-54d12e973e4d | note | – – – – – – – – – – – – – – – – –
5d5a94ae-7d6f-5d73-91f4-7abb5a62b7f8 | note | FREQUENCY: Each element
124a14e5-3ac6-5e8d-802e-29fc30278f7f | note | – – – – – – – – – – – – – – – – –
12122738-d667-5efa-b79d-f70a2545a7ed | note | CATEGORY: IP
fb3d3d8b-ff19-58cd-9581-76d03922e452 | note | – – – – – – – – – – – – – – – – –
4822f1e5-b6f8-5918-9907-8b6d20798315 | note | RESPONSIBILITY: SE/PE/SPE
f579e0e0-5dc9-5873-9333-6a56d3c3138e | note | – – – – – – – – – – – – – – – – –
87141861-4e08-5cf0-b768-cd1001058df0 | note | VERIFYING DOCUMENTS: This ITP
338a7c3c-0db9-58fa-b8cf-2128feeefa16 | date | Date Completed:
| checkpoint | 4.8 Grout tubes
86c6fb2d-787a-577f-aa51-d42ef7bed24e | note | REFERENCE: IFC Drawings
8d2c75cd-93f9-5fb9-955d-009e55153d04 | note | – – – – – – – – – – – – – – – – –
9f851ae8-5677-5690-b362-fae50a334eb0 | note | ACCEPTANCE CRITERIA: Grout tubes are inserted to the bottom of the corrugated sheath (Duct)
88d7ab24-1106-5df1-a605-7b47c1a863f6 | note | – – – – – – – – – – – – – – – – –
c30ca5db-eef7-5415-948d-8cf94aedd524 | note | METHOD: Visual, Measure
a3933093-c785-5dc2-98fd-6e393cfc53e9 | note | – – – – – – – – – – – – – – – – –
2357cc05-a66b-524e-b32c-3383dfd91dbb | note | FREQUENCY: Each Duct
44809ac7-3708-5cbd-a25a-ab56304d979f | note | – – – – – – – – – – – – – – – – –
7b6ac86b-b4b8-5a21-9f9f-e11fececf3cb | note | CATEGORY: IP
fc7b5b5e-db51-5319-b917-537ee88e1235 | note | – – – – – – – – – – – – – – – – –
eea0f3c1-4f33-5119-8942-9a671a65d511 | note | RESPONSIBILITY: PE/SPE
c5ae3c3f-1731-5b3c-9db3-2d2f48998560 | note | – – – – – – – – – – – – – – – – –
1bfdd34c-4eea-5b3d-8a92-d7d1e77475a0 | note | VERIFYING DOCUMENTS: This ITP
1e29e203-a40e-58a7-a44a-e38e8c1fed13 | date | Date Completed:
| section | Construction/Installation Activities
| checkpoint | 5.1 Precast Handling
9d9dcd92-b440-5ce2-b13c-5dc6c3e9158d | note | REFERENCE: 620.07, Crane Lift Study
6f27fa8b-ba7a-5342-8618-9f8aac31f422 | note | – – – – – – – – – – – – – – – – –
3df147d0-2e38-51b4-8e79-3df73075a008 | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
c877b6c0-8b80-552e-8443-912d9b48aac4 | note | – – – – – – – – – – – – – – – – –
83c1624b-edd6-5156-a888-e11a890a732d | note | METHOD: Visual
d754bd79-ff60-5673-8f14-a48d47eb47da | note | – – – – – – – – – – – – – – – – –
675cab33-2cdb-5b63-9130-8d79a7aefcd5 | note | FREQUENCY: Each element
12b24854-ecc6-5255-92e7-539edef6b461 | note | – – – – – – – – – – – – – – – – –
91e1c0e0-4446-5a4e-9462-ddd1421edc3b | note | CATEGORY: IP
f3694a8f-bb18-542f-9935-bcc6826b0278 | note | – – – – – – – – – – – – – – – – –
d150f188-5958-587c-b04d-7bdb85b2e838 | note | RESPONSIBILITY: PE/SPE
be91df35-10af-568d-8830-bd6c505d403d | note | – – – – – – – – – – – – – – – – –
717f2b50-02c0-5a42-a328-af62679e1693 | note | VERIFYING DOCUMENTS: This ITP
de8c720d-0a1f-50d8-b2f6-36033a9365c9 | date | Date Completed:
| checkpoint | 5.2 Precast Placement
fa8468ce-a9fe-50e8-be7e-ef747890a287 | note | REFERENCE: IFC Drawings 610.27
3856bf33-f765-53ba-82af-ab2568173fc9 | note | – – – – – – – – – – – – – – – – –
31e30e80-39fb-5ea4-805b-73bb5d009e15 | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
e8c40e8b-2a3d-55e7-8f99-a2b08cd7047d | note | ○ The Gap between precast crosshead and pile
6f5060d2-15d7-51b3-a1f5-0f28be4e6b7c | note | • Min 15mm
0c964363-a53a-5ce2-a099-f93756056e3a | note | • Max 30mm
caca5ccd-0913-58f6-aa78-0177617225da | note | – – – – – – – – – – – – – – – – –
7710aa4e-25f4-5778-a119-ffa55fb731f7 | note | METHOD: Measure, Visual
02d0c886-edc6-5a96-90e3-aa01761da8cd | note | – – – – – – – – – – – – – – – – –
5990e65e-4442-5e35-b987-4af084e051b3 | note | FREQUENCY: Each element
94008207-59fe-5db7-b416-dfaa08aea734 | note | – – – – – – – – – – – – – – – – –
a04ac06d-d3cb-53ea-89d7-c8b58d22b564 | note | CATEGORY: IP
de18b2eb-41d5-5c2d-874d-5c5eeddf0f1a | note | – – – – – – – – – – – – – – – – –
72f3fb77-685d-53f5-97aa-09ea61f77a77 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
eba68601-cfde-5b5e-81d1-ff0bc45b4655 | note | – – – – – – – – – – – – – – – – –
c183db0b-ff29-5927-82b7-1f0e79e1ce30 | note | VERIFYING DOCUMENTS: This ITP
6eefb79f-65ff-5ce2-8882-aebc0e3cadbe | date | Date Completed:
| checkpoint | 5.3 Grout mixing
d67740d1-7e86-5ff5-9ad2-e1089f8f785b | note | REFERENCE: Manufacturer Instruction, Product TDS / Application Guide
dc4e60a8-d1ba-50ce-908f-39f92b8d9303 | note | – – – – – – – – – – – – – – – – –
1b98d2c6-e197-5b4c-b79f-1f5cc6827074 | note | ACCEPTANCE CRITERIA: Pour the entire contents of the hardener pack into the base container. Mix the hardener slowly into the base using a slow speed heavy duty mixer.
d9a08801-d611-58f6-a876-51cb1cadd738 | note | • Once combined the product should be mixed at 350 to 400 RPM for 2 to 3 minutes until a uniform mix is obtained.
7e29bf9b-26f5-537b-8ed6-89a11e573316 | note | • Pot life @ 20 degrees celcius: 30mins
36b8ff31-2bea-55b8-a005-bf40cace68ed | note | – – – – – – – – – – – – – – – – –
ab6207a0-50ac-5cd7-a773-926968740bc5 | note | METHOD: Visual
706e74dd-451b-54c5-afd8-9629185eb1b1 | note | – – – – – – – – – – – – – – – – –
e95bba7a-ae18-5d04-8690-daf02a3814db | note | FREQUENCY: Each duct
fb8a13f5-cf27-5328-9859-d74bfe348473 | note | – – – – – – – – – – – – – – – – –
0381cfdf-50b0-569b-a93c-5b4b218d138a | note | CATEGORY: HP*
852c8463-1366-5ef6-b61c-fdfc30de16ed | note | – – – – – – – – – – – – – – – – –
6d1db5aa-5e1d-5b2c-a99e-1e4b9b7bfcda | note | RESPONSIBILITY: PE/SPE
a4c5c95c-8636-5244-ac1e-ff7157507ad3 | note | – – – – – – – – – – – – – – – – –
4d8878a7-3b73-5310-95f1-5cde75ad41f0 | note | VERIFYING DOCUMENTS: This ITP
57849088-b8a8-5ee1-b190-f13a6c00af74 | date | Date Completed:
| checkpoint | 5.4 Grout injection - Bleed tubes
24c8e96c-c128-56f8-9489-8241b88ab6c3 | note | REFERENCE: IFC Drawings
ed4034d0-b9ed-5952-a104-a732bd7915f0 | note | – – – – – – – – – – – – – – – – –
176d24f4-3b30-5906-b0d4-11c74d9aea17 | note | ACCEPTANCE CRITERIA: Grout allowed to flow until all bleed water is expelled and grout flows freely from each bleed tube. Then lock off bleed tube.
626af2ea-4c65-5984-b163-ed8bfae1623d | note | – – – – – – – – – – – – – – – – –
afeeb3a0-4f22-52e9-ad2a-b1260e6d1760 | note | METHOD: Visual
ad88ac73-df8f-5b19-9738-cc172ca05fd0 | note | – – – – – – – – – – – – – – – – –
5411c318-ca78-5962-9482-218422213b08 | note | FREQUENCY: Each duct
9a259ca9-27cc-51b1-8ec8-246eabe67f01 | note | – – – – – – – – – – – – – – – – –
66b76ed3-80e9-57a2-b1e1-0838e4af2235 | note | CATEGORY: HP*
a6c21cd3-3c83-5778-9182-7cd2adac26b7 | note | – – – – – – – – – – – – – – – – –
3f4145b6-ce67-5cf7-89fb-25bd4828aa1a | note | RESPONSIBILITY: PE/SPE
f04dc13f-2db7-57dc-a2bc-274e907d8dea | note | – – – – – – – – – – – – – – – – –
e07ea46a-8ddc-50b2-9c73-06d57c5cd6dd | note | VERIFYING DOCUMENTS: This ITP
d6d7a425-594f-58a4-85a6-4ac6be9b018d | date | Date Completed:
| checkpoint | 5.5 Grout injection - Ducts
9f6e1714-1955-591a-bb79-127f55b9b21d | note | REFERENCE: IFC Drawings
4d58d944-e990-569e-8b4c-7fdc7772da79 | note | – – – – – – – – – – – – – – – – –
706ac581-4a36-549e-b563-6f07bcbb7a93 | note | ACCEPTANCE CRITERIA: Grout injected in a continuous pour until grout emerges from the top of all ducts
6674cde3-c688-501f-a8f3-79a81344bfdc | note | Attach: Completed Grout Pour Checklist
aa2b8c1e-4c3c-57fd-a061-b9b842357898 | note | Attach: Completed Grout Pour Record
fdc0aa96-ae23-5ec9-b548-628b0ebc74b8 | note | – – – – – – – – – – – – – – – – –
c41e1350-e00e-57a3-a9b5-009744953de1 | note | METHOD: Visual
347e91b1-daeb-5ab0-83ef-442f9d4e8d65 | note | – – – – – – – – – – – – – – – – –
ccef69b9-889e-55a6-8e2e-8eb86edff793 | note | FREQUENCY: Each pile
b28e81f4-7f18-529d-a7ff-1e673c244b25 | note | – – – – – – – – – – – – – – – – –
a07380b5-ce0b-5961-8301-8a05000c28bd | note | CATEGORY: HP*
c1062077-ba45-5ef9-b2b8-bafb5fe5ef3e | note | – – – – – – – – – – – – – – – – –
0a066296-a0ab-5b62-a2b7-6aeab36c4cd5 | note | RESPONSIBILITY: PE/SPE
6f7a98d5-7a6c-5b34-a4b6-19d78ae28e4a | note | – – – – – – – – – – – – – – – – –
96783f2b-6709-52a9-926a-8ef6692a606c | note | VERIFYING DOCUMENTS: This ITP -Grout Pour Checklist
28e89b86-454b-5e34-a463-129269e8eaf0 | date | Date Completed:
| checkpoint | 5.6 Testing - Sampling Frequency
58c35a9e-693b-5ef9-a71a-39c09c435e3f | note | REFERENCE: IFC Drawings 610.28, 610.33
739ca2c1-a46e-5293-8e65-a5e1549b88ce | note | – – – – – – – – – – – – – – – – –
2d081cd9-0010-5245-8931-3cf934d8a23b | note | ACCEPTANCE CRITERIA: Three (3) 75 mm test cubes shall be taken from the first batch of material mixed.
42fb201c-a5c6-5f82-84b8-16cd21c873c7 | note | • Three (3) 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength.
f49dcfcb-dd4e-5007-bb78-e92b7dd3fda0 | note | • The cubes shall be cured for seven days under laboratory-controlled conditions
ac55cc8e-f0d8-56ba-92f5-00b6e731ed5a | note | • Test cubes shall be made in rigid steel moulds, cured and tested in accordance with AS 1478.2.
b18955af-0834-5b5e-ac49-c612babf4e8f | note | • The contact face of the concrete shall be flat and have a surface roughness between an amplitude of 0.5 mm to 1.5 mm, with a surface presenting similar to Grade 40 grit sandpaper.
d00ee945-61ca-51c8-9f6d-06bfa44d83b7 | note | – – – – – – – – – – – – – – – – –
3adb51a1-b6ea-56b5-aa0a-6d15c72bdc88 | note | METHOD: Measure, Visual
152873ae-bcd3-5d21-a181-89b0e1c05853 | note | – – – – – – – – – – – – – – – – –
aae3787f-d3cb-5919-8e41-129809c79de5 | note | FREQUENCY: Each element
f47298d3-d3e9-5687-b4e3-f5e3abac3e51 | note | – – – – – – – – – – – – – – – – –
381099f0-d099-5de9-9aaf-d0fb4856cceb | note | CATEGORY: IP
2dd0706a-9147-55d0-81de-d26a35e9b6d1 | note | – – – – – – – – – – – – – – – – –
8907d6dd-e021-5d64-a761-9ced6764b613 | note | RESPONSIBILITY: SE/PE/SPE
a6659eee-912f-5734-ac0c-2e234dece909 | note | – – – – – – – – – – – – – – – – –
7c12f06a-62d3-5d02-bcbb-4cef810a0b4d | note | VERIFYING DOCUMENTS: This ITP
dd302582-aa87-58a9-aabf-0ae456d7dace | date | Date Completed:
| section | Post-construction/installation Activities
| checkpoint | 6.1 Grout Compressive strength test results
b989a703-14f7-557d-bbc8-05c0f2b6f516 | note | REFERENCE: IFC Drawings
c7230165-e3c1-5d2a-af03-7deeaf6a1b96 | note | – – – – – – – – – – – – – – – – –
e845b254-1f4f-5b73-b900-77700eef9c61 | note | ACCEPTANCE CRITERIA: Two (2) cubes shall be tested at seven days and the third cube at 28 days to confirm compliance with the minimum compressive strength requirements.
3198c39f-974e-575f-914b-f79184224f4f | note | • The minimum compressive strength of test cubes shall be50mpa At 28 days.
b4040cfc-874c-568c-be48-7d1a0ec3af04 | note | ATTACH: Complete Test Results
f227546c-06cd-59b5-82fa-397eadb8c6f9 | note | – – – – – – – – – – – – – – – – –
4e02c2ef-587a-51b3-92ec-6429702b57e9 | note | METHOD: Document Review
dba90b80-568e-5a05-ad67-dc40722f9bbe | note | – – – – – – – – – – – – – – – – –
65cf630a-974d-5dcd-9833-7d2ebc5188c6 | note | FREQUENCY: Each element
a1b1c34e-c4e6-52d5-8c02-5ade7b6e8118 | note | – – – – – – – – – – – – – – – – –
e8812486-0d18-5657-86e0-bfae10ca9463 | note | CATEGORY: HP*
bcd90af3-2005-5a72-b94c-9ce09c2f0c5c | note | – – – – – – – – – – – – – – – – –
f7ffa0f4-b5dd-577a-9dab-26f1a4f9ffb7 | note | RESPONSIBILITY: SE
ae7553b9-001e-5546-b804-2f1488e59038 | note | – – – – – – – – – – – – – – – – –
eb3a10b1-a73f-52f6-872a-35c31f3f2811 | note | VERIFYING DOCUMENTS: This ITP
93ca194c-de39-5e82-acb6-64480f86fa91 | date | Date Completed:
| checkpoint | 6.2 As-built Survey
5cf89e1a-a8a7-5f5e-96b4-7a171adb8d6e | note | REFERENCE: IFC Drawings
3a4040c1-9870-5685-bc1c-2e2288e46652 | note | • 610.46 (a), Table 610.462 (November 2018)
dca5c941-5d04-5c98-8901-31ec4fb0c701 | note | • 610.47 (a), Table 610.472 (March/June 2019)
aea10af9-31a9-52b8-b23e-0a784abc5369 | note | – – – – – – – – – – – – – – – – –
faa2aebd-7763-507c-b05b-2c89536febde | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
3d85a6f8-e327-54f9-a042-581a3a3c4cab | note | Attach: Survey As-builts / Survey Report
8b900112-b4a2-51f6-989e-7ee4ef341785 | note | – – – – – – – – – – – – – – – – –
94dfe17a-6a63-52ba-8eb2-f4d1a72e74b9 | note | METHOD: Document Review
8bf5cbd8-a9cb-5aad-a390-e77c0f4ff13d | note | – – – – – – – – – – – – – – – – –
9f776141-3265-511f-a502-3800e4ce6a98 | note | FREQUENCY: Each element
3ccd45ef-e0f7-50b3-b6e9-4d4783637ff5 | note | – – – – – – – – – – – – – – – – –
58f1f571-5cba-53e6-8e32-21ad272a8f08 | note | CATEGORY: IP
85020d8e-4c8a-5222-a330-9559dd1606f3 | note | – – – – – – – – – – – – – – – – –
28e0af10-c6c6-5ca8-b20c-30b329e94510 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
ace9e20b-76c4-5ca1-b927-ce461877c975 | note | – – – – – – – – – – – – – – – – –
716ab93a-bb9e-59f6-a105-02429afe219e | note | VERIFYING DOCUMENTS: This ITP
372432c6-91b3-5fe8-9f1a-bb0b395d62a4 | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
78fd717d-d2a2-5685-a1e2-1a16fa3eaac0 | note | REFERENCE: MRPA Quality Management Plan
249a8c7e-71ae-5bcc-8142-5daf55eaed92 | note | – – – – – – – – – – – – – – – – –
1eeb387e-a55f-5e71-9b49-a98d35da8030 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
038a3026-e42c-55cf-a268-301e2a71d336 | note | – – – – – – – – – – – – – – – – –
f688388f-7c68-576a-86d5-ec497a7166ed | note | METHOD: Document Review
968e25a7-1fad-5095-b6fc-fc45fdd12c01 | note | – – – – – – – – – – – – – – – – –
27884cb6-be06-52d5-b369-d1e80b1a8b3e | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
739facba-695c-546d-9941-01fe7cd59ab7 | note | – – – – – – – – – – – – – – – – –
4c42d02f-d747-552c-ac8a-5fcf449f3359 | note | CATEGORY: HP*
ed9464ce-3b8e-5124-b89a-51bdba8677c3 | note | – – – – – – – – – – – – – – – – –
c616ce7e-2243-5f87-9404-3eab4db549bb | note | RESPONSIBILITY: SE/PE/SPE
4402b19f-92bb-5105-aed7-8f992899393c | note | – – – – – – – – – – – – – – – – –
dedf9533-a88e-59d0-82b0-a890bedecde0 | note | VERIFYING DOCUMENTS: This ITP
8eeefe2e-b238-59f9-be3b-fded92f800a8 | date | Date Completed:
| checkpoint | Final Inspection
78537981-6868-5a70-a4d7-7031bc1e39d3 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
01d412ab-087d-5c77-980f-4d0951e3892f | textbox | Name:
783b58c9-ab04-5282-9d0b-52cee7e9c7e1 | textbox | Position:
1e6593e6-7780-5b9a-b9a6-19ac8ceec9b2 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-051-RAIL-Camms-OHLE Installation Rev 0 | itp | ITP-051-RAIL-Camms-OHLE Installation |  | 719c114a-2d82-408a-a18b-050f89595db2
| section | Referenced Documentation
| checkpoint | Referenced Documentation
f148c6ff-1371-5f00-896a-01ddd5188889 | note | Document Title: ITP-051-RAIL-Camms-OHLE Installation
57a56c1b-be2a-566e-b4fd-1b51e2526b28 | note | ITP Description: OHLE Installation
511735c1-f04b-5e87-af97-73850b598a39 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
23e86770-576b-523c-8386-5533a894bf65 | note | Discipline (e.g. CIV/STR/RAIL): RAIL
194179b7-caa6-54c1-9e68-924e4d1e26f6 | note | Revision Number: 0
2079d6b1-5f4e-5347-b1c1-621a4a92ef84 | note | Revision Date: 26/06/2023
aea3f43b-51a2-596c-868a-e75295553369 | note | ITP created by: Nikhil Siram
73abc8c6-195b-589a-b8bc-e192b47cd1c3 | note | ITP approved for use by: Victor Mira
68bfffee-6160-59f8-94d7-664460539645 | note | 1.1 Overhead Line Electrification
dbbd69fc-51e7-5074-b454-28f5b1e7b977 | note | Reference: L1-CHE-STD-011(1) MEST 000002-02(1)
4c1a583b-d586-533d-8e27-c10ba615122b | note | 1.2 Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
a658c7ee-7b38-55fa-aaed-9267d1eee959 | note | Reference: VRIOGS 001 AS 4100
0fd157e5-fd78-554c-ba76-7da5ca42038a | note | 1.3 Electrical Networks Standard Electrical Networks Principles and Performance
53dceb2d-9af7-5b9a-9c9d-05a050e1bb52 | note | Reference: L1-CHE-STD-015(1) MEST 000002-06(1
a931dbb5-bba7-585c-8076-12a524f8735f | note | 1.4 Fabrication of Steelwork
5f466119-f37d-563f-9935-0f4258ae8b08 | note | Reference: VicRoads Section 630 January 2023
60560439-0c0d-5013-9033-63abcf699c45 | note | 1.5 Electrical Networks Standard Electrical Networks Principles and Performance
fc9379e3-9248-554e-b653-590e39b92cee | note | Reference: Structural Steel Work - Fabrication and Erection
| section | Preliminaries - Materials
| checkpoint | 2.1 Structural Steel Components and Fasteners
fbcb4dc7-0d3b-5a28-b086-060719619070 | note | REFERENCE: IFC Drawings
689e7c0f-9889-500a-83c2-88331d011e52 | note | – – – – – – – – – – – – – – – – –
01914ccf-9b51-50f8-a715-d351e1644e1f | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
134c65e3-a25a-5c6d-bb78-0e9bbb0b58e6 | note | • Typically this consists of but not limited to:
d8b969d7-82a8-597c-8564-293f07cd0215 | note | i. Completed fabrication ITP
f1289c81-eefc-56b3-ac9e-e23a17e51ef8 | note | ii. Weld Procedure Specifications
9771b0be-7328-5529-bac1-5daad79f3519 | note | iii. Weld Procedure Qualifications
743f3d7c-4e8f-524e-9292-098c5f1cae3c | note | iv. Welder Qualifications
a310748b-4fb6-5a4d-a7b8-b0c039279d39 | note | v. Material Certificates
73863369-df07-57a5-8517-75a1ac3e3d4e | note | vi. Coating certificate(s)
113a0f26-ac7d-533f-aad6-5b5c58ad4f03 | note | vii. Non-destructive Testing (NDT) Reports (if any)
bbd7924d-945e-5952-aae0-2b538ca475a7 | note | viii. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
b76528ec-91fd-54da-89f6-6a049adbbf47 | note | • Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
0ec8d898-212f-5f76-a7f2-d363b015e781 | note | • Bolts, nuts and washers for Property Class 8.8 bolting shall be supplied in accordance with AS/NZS 1252.
48e02010-9bee-5e9f-9af8-10275f018c49 | note | • All bolts nuts and washers are hot-dipped galvanized.
3405b7b7-12b4-532b-8923-e95683be4a47 | note | Collate: Structural Steel Quality Assurance Documentation.
ef7ddfd8-b951-5ec0-920a-59a75b22c23a | note | Attach: Collated QA documents in ConQA
d897f512-fce3-57ca-a294-1ad344c6eab8 | note | – – – – – – – – – – – – – – – – –
3bdf263d-938a-590e-8f92-663728735757 | note | METHOD: Document review
ecec0a85-d9c1-5d38-b965-4f17da5e2763 | note | – – – – – – – – – – – – – – – – –
965f8ab6-c527-51cc-95a2-e60664c117be | note | FREQUENCY: Where applicable/ Each element
9f499bc8-c6dc-5c99-b453-e0532fc93199 | note | – – – – – – – – – – – – – – – – –
f4c56df5-df3f-57bd-b693-cbfc80e31772 | note | CATEGORY: HP
475f96d6-7c7d-5b6f-93c4-9680639578d1 | note | – – – – – – – – – – – – – – – – –
0e033c6a-6cb3-5de3-b163-338726567399 | note | RESPONSIBILITY: PE
b4ab439c-041a-52fb-a261-e04b21918d6d | note | – – – – – – – – – – – – – – – – –
d0d701c7-1d59-508a-bb61-6ee89be7df36 | note | RESPONSIBLE PERSON: MRPA Engineer
ddf6ecc5-4fd1-5ebd-ab7d-90b20da17c89 | note | – – – – – – – – – – – – – – – – –
75e6a616-cd37-5d84-978f-5202c621b2c1 | note | VERIFYING DOCUMENTS: This ITP Signed Off
cac6a215-631d-5d30-96ad-697b0b52eb56 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Bolted Connections Using Direct Tension Indicators (DTIs)
73755e4c-b627-5510-80b3-3c9cc3b03efb | note | REFERENCE: AS4100 Clause 15.2.5.3 (a), AS5131 Clause 8.5.7 (a)
d0a1c30e-73e1-53d8-91e5-462446650c01 | note | – – – – – – – – – – – – – – – – –
43035170-8f89-5c68-826c-ec60cf62cb5e | note | ACCEPTANCE CRITERIA: Direct tension indicators (DTIs) shall not be used unless approved by the Nominated Authority and accompanied by:
7d266c1a-f719-5325-aa94-4e87f1aa031e | note | i. technical data sheet or information on the product
a3330375-da55-57c7-8bf6-30328c342698 | note | – – – – – – – – – – – – – – – – –
13c2ef29-5a29-5b22-9787-ecb42a160e15 | note | METHOD: Document Review
7c59498b-4dff-5e33-bb90-bef8632dec4b | note | – – – – – – – – – – – – – – – – –
4293e658-709e-58c7-a673-9531ad248baf | note | FREQUENCY: Where applicable/ Each element
ac36f416-c91a-5ed4-8e87-7ada1a00bbcb | note | – – – – – – – – – – – – – – – – –
f0d46cbc-7e49-5686-ba71-8070fba1076d | note | CATEGORY: HP
191211d7-2799-51c7-9046-9b1ca880f381 | note | – – – – – – – – – – – – – – – – –
5c8c52e2-878e-5e32-9aaf-e024803dbdae | note | RESPONSIBILITY: PE
868a651e-e316-50b2-a596-e94755e76102 | note | – – – – – – – – – – – – – – – – –
f478616f-d9db-56a8-b7bc-735c0f49dbe3 | note | RESPONSIBLE PERSON: MRPA Engineer
ee88d529-a989-5ffb-80fe-c341d198910d | note | – – – – – – – – – – – – – – – – –
dc5e03f1-7df2-5266-b130-c472564ef1f3 | note | VERIFYING DOCUMENTS: This ITP Signed Off
2a668106-bca6-59ee-897b-2a6c5cf0dbaf | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Overhead Wiring Small Parts Steel and conductor wires
93af7a57-5207-5377-9d52-122312b61b4f | note | REFERENCE: Relevant MTM Standard Drawings
ea77361f-98c0-5d14-82af-c2944d722fe2 | note | – – – – – – – – – – – – – – – – –
f6d22dc4-efd2-5617-aa0e-9a1e7ac15b1b | note | ACCEPTANCE CRITERIA: Overheading Wiring Small Parts Steel to be procured as detailed in the drawings and as per relevant MTM Standard Drawings.
72e6e9e4-85be-5efb-818a-38c6d4929b6c | note | • Deliveries are to be inspected to match the purchase order
0897717f-2b88-5624-b16e-37742b20d4a6 | note | Attach: Purchase order/Delivery dockets/Certificate of conformity
60faeab6-56f2-5156-9798-a4e9ddf17257 | note | – – – – – – – – – – – – – – – – –
53dad715-103d-5150-88c7-57466fcccb37 | note | METHOD: Visual Insoection and measurement
17261e2e-e998-5b68-9d4c-5c23617fa7a6 | note | – – – – – – – – – – – – – – – – –
26e5388a-9aec-528f-ac7c-0b0ddd1776a2 | note | FREQUENCY: Upon delivery
4910e533-23f5-5897-8dce-cd47d8f9019c | note | – – – – – – – – – – – – – – – – –
83b8c716-d5e8-5084-9abc-abbf208ca015 | note | CATEGORY: IP
1b80cd0b-c51d-5a63-b2e0-89ccaf17c227 | note | – – – – – – – – – – – – – – – – –
3dbb3ec0-b355-57e8-8dfc-865d1fdf51ad | note | RESPONSIBILITY: PE
2744148a-5fa0-503d-adae-4c7216203bd6 | note | – – – – – – – – – – – – – – – – –
a4dba2b1-ada8-578b-917d-660b276de25b | note | RESPONSIBLE PERSON: MRPA
931081bd-d8dd-54ef-8d5b-8083bc0576d4 | note | – – – – – – – – – – – – – – – – –
661f4c24-259e-52d2-be4a-df367e29a8d4 | note | VERIFYING DOCUMENTS: This ITP Signed Off
00f5c0ac-dae4-53c2-96d1-dedf2c9e9340 | date | Date Completed:
| checkpoint | 2.4 Grout
9efad30c-0bcd-51c0-9967-9b4a43ace209 | note | REFERENCE: IFC drawings
5d5beec6-fc92-5ff8-8f95-59137c06751e | note | – – – – – – – – – – – – – – – – –
18706576-b524-57df-83d5-60dbd4c9a240 | note | ACCEPTANCE CRITERIA: All grout under base plates shall be CONBEXTRA C or equivalent as approved. Approved grout to be Flowable shrinkage compensated with minimum 50 Mpa compressive strength.
07dd74a2-eb4a-5bfc-968b-702061477fc7 | textbox | Enter: Teambinder Material Approval number
5839b8ff-97db-5c3d-a923-f32663d6c6e0 | note | – – – – – – – – – – – – – – – – –
09faae26-bfd4-53b6-9525-5a8460c5d68b | note | METHOD: Document Review
6d1f1d44-2c3a-5767-a09e-cc2f7ed1ad3a | note | – – – – – – – – – – – – – – – – –
c2233edb-2f69-5584-819d-88230534debe | note | FREQUENCY: Where applicable/ Each element
5249284f-ec8b-5301-a18b-f305e0860218 | note | – – – – – – – – – – – – – – – – –
54364178-b125-5bd4-afa9-d170b1aba8d5 | note | CATEGORY: HP
bd3c7478-4264-56b4-8291-1f5961dad0b7 | note | – – – – – – – – – – – – – – – – –
7166194d-6ede-50c7-8fdb-579e7724535a | note | RESPONSIBILITY: PE
5ba488c3-2df8-55ea-9b87-1cc148de1174 | note | – – – – – – – – – – – – – – – – –
4befb3f7-cd23-50fa-aed5-c59834226522 | note | RESPONSIBLE PERSON: MRPA
0e8ea198-6550-55c2-9893-ef4e0443bc31 | note | – – – – – – – – – – – – – – – – –
db6a9834-e1c7-5057-8a33-536277b9fc0a | note | VERIFYING DOCUMENTS: This ITP/Material Approval
ac51e167-87b0-5578-ba98-c6feffe8c861 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Installation Methodology & Works Method Statement
26bce41e-0b0b-5366-9304-a1b3f7fc2db9 | note | REFERENCE: AS5131 Clause 11.2.3
95d032b0-77a1-5163-8eab-50ccb699a010 | note | – – – – – – – – – – – – – – – – –
a80e3a95-4c89-52f2-be0c-5fe0ff8b5691 | note | ACCEPTANCE CRITERIA: Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
4fe0dd0a-cb65-58eb-b618-b47c9ee37518 | note | – Transported to site;
4d75f571-3e36-5ee6-b961-19caf5eb4b9e | note | – Handled on site;
d1cfd0db-5771-53a9-8f19-85093ed5a1ac | note | – Installation Procedure (subcontracor ITP's);
4610eb20-1e43-5767-8940-41d1a4e31234 | note | Submission of Work Package Plan and MRPA approval and acceptance.
473a9a18-bec2-5da9-a316-fc570c37a774 | textbox | Enter: WAP number
28939581-06aa-56ed-a11a-748694479566 | note | – – – – – – – – – – – – – – – – –
2f4067f1-15e6-5652-a8b7-51f0ec9d5484 | note | METHOD: Document Review
3672f576-7d5b-55e9-a2b8-558b013fb6ed | note | – – – – – – – – – – – – – – – – –
e304c6b6-7282-5a91-809f-120edab2b961 | note | FREQUENCY: Prior to Works Start
22199418-bf33-520c-a1d9-d7e30701a089 | note | – – – – – – – – – – – – – – – – –
28e0598f-0ceb-5900-ae01-5f39182129c2 | note | CATEGORY: HP
e1488ac1-ad6e-5899-82d9-241f5cff888a | note | – – – – – – – – – – – – – – – – –
e7714f38-0729-57ef-a5d9-25e9e8a64840 | note | RESPONSIBILITY: MRPA/CAT5
8822d25e-38eb-52a0-9ad1-4fb00815dd13 | note | – – – – – – – – – – – – – – – – –
a6db77e2-de64-503a-b21a-304ea3dffa4c | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
f154165b-abce-547b-82e5-6cf734e4853b | note | – – – – – – – – – – – – – – – – –
78c248c3-729e-5c46-b28e-e7d57234b854 | note | VERIFYING DOCUMENTS: This ITP Signed Off
db3cd2fb-1baa-5f08-a773-7e3bba657520 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 Approval of IFC drawings
4aa35f90-22ca-5497-8cd4-4a09c8ffbf0e | note | REFERENCE: Contractor Design Management procedure.
77203aa5-78b8-54d8-9cdd-77bbec0166cc | note | – – – – – – – – – – – – – – – – –
5f2ee7ce-9938-51f5-b090-ab815fa3881a | note | ACCEPTANCE CRITERIA: Ensure correct and most recent revision of IFC design drawings are used for construction.
306db17a-ca21-596d-9f80-e4062332d2a9 | note | – – – – – – – – – – – – – – – – –
858967b9-7e26-53a9-b0e7-74724cc61304 | note | METHOD: Document/Drawings Review
a6cca0fc-98bd-5b5d-85db-8499d901b8da | note | – – – – – – – – – – – – – – – – –
4b2f8bdf-6abf-59da-8f47-d79e840979aa | note | FREQUENCY: Prior to Works and at regular intervals.
a436c7b2-a7cc-5295-96b2-90ef1e63f773 | note | – – – – – – – – – – – – – – – – –
51247041-412f-5151-9cd4-8fe8e2c9226d | note | CATEGORY: HP
1a3a53c1-17a0-5162-b15d-ea9de48729a9 | note | – – – – – – – – – – – – – – – – –
f2826148-acc8-5824-9b68-7e1bd3cb1943 | note | RESPONSIBILITY: MRPA/CAT5
1b8a17fd-bfbf-5453-8879-71b4f46f3bd9 | note | – – – – – – – – – – – – – – – – –
293ac7c1-898c-5f37-841e-5c2684329322 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
9ae31d18-60ca-5317-a15c-3b3ba50dea5c | note | – – – – – – – – – – – – – – – – –
71288c5e-272c-59f5-9390-2e281351d90f | note | VERIFYING DOCUMENTS: This ITP Signed Off
d3fe8bce-b08a-5863-bfab-214a0340b178 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.2 Cantilever assembled.
1389d1df-6c57-5b61-a96c-a25497729bc5 | note | REFERENCE: Cantilever assembled as per IFC design.
27eb4424-b4e2-599c-b9bd-4fd24ec2418a | note | – – – – – – – – – – – – – – – – –
eb5aa959-dc44-56fe-a915-23c30885ed51 | note | ACCEPTANCE CRITERIA: Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
1a7b6c77-20d0-501c-a71b-40027658cfa8 | note | – – – – – – – – – – – – – – – – –
ddc5b205-c19e-5039-944e-c564d825ecda | note | METHOD: Visual, Document Review
eac94b56-bff7-5b72-a433-73531e681880 | note | – – – – – – – – – – – – – – – – –
7ae4b055-38b7-5ebd-b424-f28214fc45ad | note | FREQUENCY: Each Task prior to works start.
af5bbc08-f725-5b1b-b1f9-f4a6dc6c01b8 | note | – – – – – – – – – – – – – – – – –
5f8ccff5-8401-5a20-903f-1fdd023644a3 | note | CATEGORY: IP
dd723a24-b898-5ec0-8e07-22c5c6e14aa3 | note | – – – – – – – – – – – – – – – – –
abf66213-317b-5701-951f-a848d82245b2 | note | RESPONSIBILITY: CAT5/MRPA
802659c6-cbde-5176-86fe-ad7a88346e64 | note | – – – – – – – – – – – – – – – – –
153ad09b-90e0-570c-89de-3505271b8aac | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
67121522-1531-5a6e-9ff2-9a73eb2d26ee | note | – – – – – – – – – – – – – – – – –
eb21b2f0-1ccf-5091-b030-2507b6dea9ab | note | VERIFYING DOCUMENTS: This ITP Signed Off
e805d018-bcb7-5c36-a328-5a3b29990fc0 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Mast Installation
405d76c1-3e59-5ca4-b3f5-014f172f4202 | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
d76502ce-373d-52df-88da-07015569aba3 | note | – – – – – – – – – – – – – – – – –
4b055cc3-11a2-5936-9327-88aae6515321 | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
d989fb05-dd8a-54d0-9f2b-6f9912f15a6b | note | – – – – – – – – – – – – – – – – –
071583ee-58d6-5638-8046-d01d2769293e | note | METHOD: Measure, Visual
347b0895-7e36-564a-9793-7c1faa9e4f8f | note | – – – – – – – – – – – – – – – – –
c32b5552-a311-5929-87a8-f2f7247696d8 | note | FREQUENCY: Each OHLE Structure
5905c547-ac5b-58c4-8b0d-1ef257861dae | note | – – – – – – – – – – – – – – – – –
99d98c80-a03a-5ace-b116-026607fe2084 | note | CATEGORY: IP
50e42cba-f27e-5c06-97b3-17c3b92cc483 | note | – – – – – – – – – – – – – – – – –
074dcde2-d08a-54f4-aa3a-55d726af960e | note | RESPONSIBILITY: CAT5/MRPA
0bc79dc7-686d-5600-880c-e1ef2b0972c3 | note | – – – – – – – – – – – – – – – – –
9b2b0d8a-7e98-579e-8e40-923d388a9054 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
bba3fd11-d728-5850-be46-97a6965dc24b | note | – – – – – – – – – – – – – – – – –
777c05f5-dbc7-5c06-86ab-c3d11dc8f6f7 | note | VERIFYING DOCUMENTS: This ITP Signed Off
9bc542da-dd2f-558c-b61f-ca2c000aaa40 | date | Date Completed:
| checkpoint | 5.2 Cantilever installed.
78cab06d-60f6-5788-8cf3-424a7905b229 | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
f5637112-97ec-54c3-bd80-774a393e8ae3 | note | – – – – – – – – – – – – – – – – –
705fa245-1412-5a32-af68-a129b39f75d7 | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
9ddbfe73-c2f6-5e80-9e57-124af4f1d1f0 | note | – – – – – – – – – – – – – – – – –
bfe108db-2c56-5d1b-a10b-690c70654dba | note | METHOD: Measure, Visual
56cee73b-e20a-5825-948f-1913cfe9293b | note | – – – – – – – – – – – – – – – – –
2ec1631d-2493-51cf-aa87-cad2a1b137d3 | note | FREQUENCY: Each OHLE Structure
a74e4de1-e148-51cc-9b2c-ee062d768ee9 | note | – – – – – – – – – – – – – – – – –
f72c6957-cd26-50d7-b1e7-2a2e9046d0ed | note | CATEGORY: IP
0eeb5c90-90a9-5f95-9847-29e973589cc4 | note | – – – – – – – – – – – – – – – – –
032629e2-be66-5b66-bcda-37ffa29711d7 | note | RESPONSIBILITY: CAT5/MRPA
b698a03d-20bd-5dd4-8b6e-30aa48621839 | note | – – – – – – – – – – – – – – – – –
36b4a5bf-a6c0-5a12-972a-b1ed1390f9cd | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
0eeb48cd-b313-51b4-9600-5b14c30f9beb | note | – – – – – – – – – – – – – – – – –
6e237519-b156-5220-8607-c1a1e225794c | note | VERIFYING DOCUMENTS: This ITP Signed Off
85d1c19c-7692-57aa-8ffc-b8fa09d08340 | date | Date Completed:
| checkpoint | 5.3 Bearing type Joints TB Friction type joints TF
eb573cab-4d0d-5baa-a929-6381304a0bb2 | note | REFERENCE: IFC Drawings
0c846858-ccee-5b07-b7c8-15c1bc472831 | note | – – – – – – – – – – – – – – – – –
08045599-9dd2-5d9f-b647-4b334d8dc912 | note | ACCEPTANCE CRITERIA: BOLTS DESIGNATED TB & TF ARE TENSIONED AS PER AS 5131 and Table 8.5.6
7c990232-5045-5f22-b9e9-d37bb60f36ed | note | – Bolt mark ups (in case of partial tensionening) should be visible for inspection
eed43c0a-d99d-51e8-bb26-5bdc700ad0e0 | note | – DTI squirts are to be visible for inspection
594abf7b-c299-5e9e-86fe-06ac95d91509 | note | – – – – – – – – – – – – – – – – –
815062d2-d587-5974-9f0d-1f40b15363c7 | note | METHOD: Visual
bfeae9b2-d572-5884-b543-1dc8b7371f9e | note | – – – – – – – – – – – – – – – – –
d5c11207-f1f5-57dd-b006-4d25810b05dd | note | FREQUENCY: Where applicable/Each element
d1e70388-7848-50f0-a0e6-3619ad63d1e5 | note | – – – – – – – – – – – – – – – – –
8963735a-b63e-5a11-a41e-f4625010e145 | note | CATEGORY: IP
4ff0be49-a62f-5a41-97be-aaa2500568e1 | note | – – – – – – – – – – – – – – – – –
0510c9e9-87f4-56f4-830f-06359b9e314a | note | RESPONSIBILITY: PE
91c2e4fe-a48f-57cd-a0ad-43d8462d60c6 | note | – – – – – – – – – – – – – – – – –
39331307-fa75-584e-9523-0ac628d17d51 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
c11bab12-1484-5728-8be4-bd280a42c4b1 | note | – – – – – – – – – – – – – – – – –
ba4a3b93-7b83-573a-9111-7dc6ffd0308b | note | VERIFYING DOCUMENTS: This ITP Signed Off
55dccc35-2544-5db2-9af1-38688e6cc31f | date | Date Completed:
| checkpoint | 5.4 Install SPS to correct height / position relative to track
58e02560-ac6b-5aa8-a740-d7e50d219c79 | note | REFERENCE: Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
6243ac03-e5cb-5fc6-a25d-75052017aa66 | note | – – – – – – – – – – – – – – – – –
9a5880a2-45ed-570d-ae30-9c08b2784042 | note | ACCEPTANCE CRITERIA: Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
e77214fc-0440-5b6d-94a9-1186e8ecaf6e | note | – – – – – – – – – – – – – – – – –
75add6ef-704b-5e4f-a23f-abdeab4f91d4 | note | METHOD: Measure, Visual
9521ff7d-d339-56eb-80ea-d359260bf3b6 | note | – – – – – – – – – – – – – – – – –
6da6578c-c0a3-58bf-81bb-0bb584500b9c | note | FREQUENCY: Each OHLE Structure
c83cad90-5e06-5d89-8477-1dedc504fa7c | note | – – – – – – – – – – – – – – – – –
8d63a6aa-1073-58e8-9154-543dad4acf69 | note | CATEGORY: IP
8a55561e-ffc0-582e-9734-4cff9eb86375 | note | – – – – – – – – – – – – – – – – –
fe75da46-7b20-59f3-b9f0-58830ae47b29 | note | RESPONSIBILITY: CAT5/MRPA
b49e0d6d-4e0f-522c-8478-05f231360ec8 | note | – – – – – – – – – – – – – – – – –
a79f4fc1-7b97-5c95-9ba5-3fde5c4eb75d | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
9156d195-50f7-58e9-a0a5-aa6f4d48080d | note | – – – – – – – – – – – – – – – – –
9900457c-57fd-5ef4-895b-d87c80f1d945 | note | VERIFYING DOCUMENTS: This ITP Signed Off
9b03d926-cf6e-5b47-9834-33388cab2165 | date | Date Completed:
| checkpoint | 5.5 Cantilever checked once installed.
f57ddaa7-72be-5b54-8b44-a26b28a51478 | note | REFERENCE: Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet.CAT5/OHLE/CHK002
b062b12d-622f-5002-bb42-ed37da7693a9 | note | – – – – – – – – – – – – – – – – –
706e6243-3eae-57a9-8d39-bd63f46bb8a4 | note | ACCEPTANCE CRITERIA: Supervision checking to ensure that equipment is installed correctly.
e7fcea10-91dd-53b1-b6b8-77240993bba6 | note | – – – – – – – – – – – – – – – – –
27c97b9d-0bff-5223-bdef-047fba64f514 | note | METHOD: Measure, Visual
3198d02a-4f31-5576-9be7-6ca1375b5b74 | note | – – – – – – – – – – – – – – – – –
b6261b59-8995-5fa9-95fb-d682b684a619 | note | FREQUENCY: Each OHLE Structure
773699aa-2da1-5177-b2ed-09b204da4958 | note | – – – – – – – – – – – – – – – – –
0239746e-0170-5aa4-a042-35ac132d8353 | note | CATEGORY: IP
c0cc045c-fa6d-571c-825e-9740846b6c35 | note | – – – – – – – – – – – – – – – – –
63a2552e-ced6-54b1-991d-ebfcb7b89178 | note | RESPONSIBILITY: CAT5/MRPA
722c6851-f9b3-5a5f-8743-0654e6963549 | note | – – – – – – – – – – – – – – – – –
5f988979-cb36-5947-bb00-ae56cbf9a796 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
7182c053-8397-5fe7-963b-2822b344e601 | note | – – – – – – – – – – – – – – – – –
5dbc3395-106e-52fe-ba0f-1a8d02757909 | note | VERIFYING DOCUMENTS: This ITP Signed Off
1f0db19a-8b93-5c71-840d-dcc74883575a | date | Date Completed:
| checkpoint | 5.6 Base Plate Grout
f7fa42b5-6fe3-5227-b83c-e8baf2cae45e | note | REFERENCE: IFC Drawings
bb5ddb38-a839-5a86-80b0-e83305d04bd6 | note | – – – – – – – – – – – – – – – – –
120e633b-fa46-586b-afa0-f2e8e220da2b | note | ACCEPTANCE CRITERIA: Grout to be mixed as per manufacturer TDS.
4f77e87b-c6f1-54bf-9325-cb4fe105f0af | note | • Grout to be poured under base plate as per IFC drawings. Grout over pour is to be 6mm and cover area with Nom 50mm offset around the base plate.
b3bde0b4-d973-5815-af9e-55d5301b3a28 | note | – – – – – – – – – – – – – – – – –
336abeff-79c7-572b-8165-6c33fdff4d72 | note | METHOD: Visual
851dfee7-b4c4-58f2-8d46-cc4bbaa5c512 | note | – – – – – – – – – – – – – – – – –
fdfaffdd-678e-5e63-a2bd-04bf3e74ec64 | note | FREQUENCY: Where applicable/Each element
7ce796a7-4e61-503f-a994-42d9844605e5 | note | – – – – – – – – – – – – – – – – –
692a7b97-c5e2-5bd5-8a0f-8f9d78f7fe2d | note | CATEGORY: IP
a5b61d7e-a612-523e-b9de-e7f04744c590 | note | – – – – – – – – – – – – – – – – –
0b2a5793-e89d-5306-a5a3-6e8c93b37278 | note | RESPONSIBILITY: PE
605a92bf-f14a-54ec-a34e-fd06c56bd70c | note | – – – – – – – – – – – – – – – – –
648eacf9-478d-58a0-9b17-03471a0bdd61 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
f2822ab2-8703-5b79-8545-2ba873fdda6a | note | – – – – – – – – – – – – – – – – –
9316538a-ccb8-58bf-b099-d4de0aaa7878 | note | VERIFYING DOCUMENTS: This ITP Signed Off
02ce2d65-008a-5fda-801f-2909c9a7d19d | date | Date Completed:
| checkpoint | 5.7 Installation of wire supports at the correct height and stagger
f113f664-64da-5d7d-a878-13fada443392 | note | REFERENCE: Install as per design
f5e76fd5-559d-5af4-9550-3d6db871165a | note | – – – – – – – – – – – – – – – – –
bf9d0c99-8804-54a3-a026-92a4be1643a0 | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
26675dd8-d7cd-532b-8cfe-21ad73a05e7b | note | – – – – – – – – – – – – – – – – –
80eade78-5c33-5aac-9677-d52c1b7b91fe | note | METHOD: Visual
ebbc6076-35cd-5071-b6ef-e661f178df3f | note | – – – – – – – – – – – – – – – – –
42b8390e-bce7-5ca7-bd7c-968939a83d2f | note | FREQUENCY: Each OHLE BWA Structure
95176ab9-567e-55e1-8629-63dfadf7ca23 | note | – – – – – – – – – – – – – – – – –
0d3d8e2b-c0c6-5024-a626-82f78e0364f0 | note | CATEGORY: IP
0d3c7294-604e-5e78-bef8-606bab95ae38 | note | – – – – – – – – – – – – – – – – –
86e30e2d-4a65-5bab-9353-13cd8b4ff333 | note | RESPONSIBILITY: CAT5/MRPA
cbc6ef85-8b9f-53d1-a7b5-9f52af6d7193 | note | – – – – – – – – – – – – – – – – –
f0e42900-b547-5316-b560-fc0c5c935292 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
b29de4b5-b532-57f7-93ec-a3604757462f | note | – – – – – – – – – – – – – – – – –
9c052b69-cf6b-5b01-ae7e-13de4eb239c8 | note | VERIFYING DOCUMENTS: This ITP Signed Off
9a56bd0f-7c56-522f-964f-5a32d045838a | date | Date Completed:
| checkpoint | 5.8 Install to correct tension
f225a121-cddc-5e67-adc2-e79d56966dc4 | note | REFERENCE: Install as per design
adb94fb9-40d4-5818-83a3-a8608620a2b2 | note | – – – – – – – – – – – – – – – – –
662a84e8-0ffc-5acc-9fb9-e43222381975 | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
bc755784-79a4-529b-a587-12a200167dc0 | note | – – – – – – – – – – – – – – – – –
86722245-2d6a-5459-9b66-c8e4dbd89629 | note | METHOD: Visual
0469da7d-5b8f-5766-bb9f-1bd54c34e992 | note | – – – – – – – – – – – – – – – – –
4f1a17d5-9d7a-515a-8170-6b685b150025 | note | FREQUENCY: Prior termination
4308e12d-69e9-54b2-beca-c730555f494c | note | – – – – – – – – – – – – – – – – –
2c234d91-7ed4-5048-bf4e-9b09ba37d6da | note | CATEGORY: IP
50daf694-b027-51fe-82fa-4fa8403f0465 | note | – – – – – – – – – – – – – – – – –
08a64f94-eb2e-5cfe-ac52-6ab17b72dda1 | note | RESPONSIBILITY: CAT5/MRPA
199be1ba-502a-5600-ab35-7d9c0a36de10 | note | – – – – – – – – – – – – – – – – –
02665dd5-61f5-52a5-abb9-c5fb5a585da9 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
5c87e806-85fd-52d8-b1e3-9b8c2ed821d8 | note | – – – – – – – – – – – – – – – – –
d8fee63c-383c-57d3-827c-578dbbbf332c | note | VERIFYING DOCUMENTS: This ITP Signed Off
e23f4b19-e5e6-5e71-8ea1-7b37609fe12d | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Defects/Temporary Works
896b7b69-83b6-55a5-a14b-ea72c05f9bf1 | note | REFERENCE: IFC wiring layouts, cross sections and design drawings.
ad21956f-fc9e-55f4-a581-7901316634b3 | note | – – – – – – – – – – – – – – – – –
598781b0-a20b-50e3-9898-60f719decc7d | note | ACCEPTANCE CRITERIA: Ensure all Defects/Temporary works are capture and closed out correctly.
1d0f9b8a-9b16-5d99-92ac-c4d1ba93382f | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
b439b2ff-2ba7-522d-80e7-a62751d86c03 | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
945d32c5-6154-5978-b06a-16610edaf2f7 | note | – – – – – – – – – – – – – – – – –
aa0ab4ff-df71-5777-bb61-1796050afea5 | note | METHOD: Document Review, Visual
11792a19-935e-5a54-990c-debeba665871 | note | – – – – – – – – – – – – – – – – –
30e138fd-b52a-5684-a5c4-35b42a4ab606 | note | FREQUENCY: Each OHLE Structure
a6427bcd-a952-58bc-9ab9-ac1b2871f499 | note | – – – – – – – – – – – – – – – – –
bd5338ca-3fc0-5491-90f0-b74b4f7bbc3c | note | CATEGORY: IP
05badb6e-0de6-5c0b-b72d-6fc056638141 | note | – – – – – – – – – – – – – – – – –
d18df339-52a7-5f6f-8023-abb99a0511ce | note | RESPONSIBILITY: CAT5/MRPA
f748293f-f956-5ec9-ba18-aba23cead3e4 | note | – – – – – – – – – – – – – – – – –
901f73ef-a722-5a2a-b79e-b81da98847b3 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
0e9d31e6-78a0-58aa-ae69-7034dc658158 | note | – – – – – – – – – – – – – – – – –
547e0712-aebf-51c2-aaec-0d8abad4ef93 | note | VERIFYING DOCUMENTS: This ITP Signed Off
041ba95b-97ff-562a-8763-ee309cc1c601 | date | Date Completed:
| checkpoint | 6.2 Relevant documentation readily available. (As-built Survey)
4fd8a86e-5e05-57d5-becc-42d92991ad9a | note | REFERENCE: As built drawings and check sheets to accordance to MTM Design spec.
c4465d09-da87-54bf-8b26-bdf87ecd1dbd | note | – – – – – – – – – – – – – – – – –
8af26945-d80e-5ad0-a926-a224dc15b9aa | note | ACCEPTANCE CRITERIA: Ensure delivery of relevant documentation to client.
4e22902e-110f-5371-948e-83c6463996d9 | note | • As built drawings and check sheets. CAT5/OHLE/CHK/002 check sheets.
dbd918e7-d25d-58a0-83f4-ab64c1ae3202 | note | – – – – – – – – – – – – – – – – –
71f4846f-20c4-5216-b529-58ec763f415b | note | METHOD: Document Review, Visual
c29bc638-5648-5396-9042-55ef111e8d11 | note | – – – – – – – – – – – – – – – – –
dcb19017-7fa1-56d4-ae02-d2b32690a7fe | note | FREQUENCY: Each OHLE Structure
5851a3ff-100e-5573-9c86-84c5ac235891 | note | – – – – – – – – – – – – – – – – –
b8e7253b-2643-56ac-8a1a-522fea5d8096 | note | CATEGORY: IP
445454ad-99dc-5373-844e-cea5f43c93cb | note | – – – – – – – – – – – – – – – – –
3ff08a8e-3bb0-5b0d-a8fd-59a537013644 | note | RESPONSIBILITY: CAT5/MRPA
382cfcd1-10b0-5679-b16c-1aa878e7850c | note | – – – – – – – – – – – – – – – – –
5cd59216-a59d-5928-9147-6d981ec52a2d | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
b851a33b-eee2-50d8-a985-1e61b213aef9 | note | – – – – – – – – – – – – – – – – –
bc4cd2c9-fc09-50e4-aa9e-9b075fbab064 | note | VERIFYING DOCUMENTS: This ITP Signed Off
411640f0-9872-58e7-8cc1-20ca9f86974e | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
68d3e125-9644-57c0-826e-14101f1b77af | note | REFERENCE: MTM Quality Management Plan
63d29d17-91bd-5191-8975-58a563a16202 | note | – – – – – – – – – – – – – – – – –
506b4b40-36b8-5904-9e12-495ad3e9607e | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
7206e493-44c1-5224-80f8-7b7d12529ff5 | note | – – – – – – – – – – – – – – – – –
bd1e0970-d2b4-58ed-90b7-9555aa6fc001 | note | METHOD: Document Review
89df3e34-f660-5467-8523-fc3b09c27a4e | note | – – – – – – – – – – – – – – – – –
05366cd7-4262-5e1c-8cbf-4e5565ac5f07 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
49c9c494-b917-563a-b6c1-317b558504b1 | note | – – – – – – – – – – – – – – – – –
15975b89-420b-52d7-9532-e33b6b3e6d86 | note | CATEGORY: HP
db0b257c-0fea-5161-ad5e-657f50c098df | note | – – – – – – – – – – – – – – – – –
b3f724c3-efea-523c-b66e-ec53776b1849 | note | RESPONSIBILITY: CAT5/MRPA
3e0fb0c1-ddc0-5191-b962-aafe29ab77c9 | note | – – – – – – – – – – – – – – – – –
9370e3e3-aa65-5d8b-aee3-8164a77e103c | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
d957aa5c-5fd2-5cfe-8397-9ed8eba542e6 | note | – – – – – – – – – – – – – – – – –
41a607af-24d1-5809-aab7-2b72ee5faf88 | note | VERIFYING DOCUMENTS: This ITP Signed Off
fba7245e-e102-57fc-910c-849207081156 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
e4a8498f-5a32-577a-9f00-98cd5ef9e4ef | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
33c64d2e-eac9-59d8-b7c5-ba7e328cc64b | textbox | Name:
70722abd-c6a2-554a-a640-9b5cb2bb81bb | textbox | Position:
2ba33d73-94bc-5994-afeb-0cf1936027bc | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-052-Camms-OHLE Wire Regrading Rev 0 | itp | ITP-052-Camms-OHLE Wire Regrading |  | 3e069579-dc44-4076-b921-92ca4956219e
| section | Referenced Documentation
| checkpoint | Referenced Documentation
7f037e8b-a44e-5d5a-9603-a374ec135f78 | note | Document Title: ITP-052-MRPA-Camms-OHLE Wire Regrading
53043bed-9cbf-5b5a-9430-04d13084b9fd | note | ITP Description: OHLE
47c525be-d9fd-5463-881b-85fb39336694 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
625f96c4-711b-51f2-958e-6d9a84516fe6 | note | Discipline (e.g. CIV/STR/RAIL): OHLE
ee8392c1-c456-531a-865e-b76c4c993345 | note | Revision Number: 0
91d12b99-afa8-5005-9a4f-7cbe1eccf5ed | note | Revision Date: 26/06/2023
f658f12c-2925-56f1-89ea-ff347d293415 | note | ITP created by: Nikhil Siram
8ebf8754-aee7-57a0-a2b1-04bb6a3da88f | note | ITP approved for use by: Victor Mira
72c02d52-e105-50bd-8216-014278ad6451 | note | 1.1 Overhead Line Electrification
a8b0f882-0c97-5ff1-a35d-1fa8ede9d886 | note | Reference: L1-CHE-STD-011(1) MEST 000002-02(1)
08bb6f67-5920-506e-9783-3840d474ead9 | note | 1.2 Structure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
0b5c4120-5516-54c9-802f-f58c9fed04f4 | note | Reference: VRIOGS 001 AS 4100
c36fbe0e-9a38-5025-b07e-c6dfea626ab2 | note | 1.3 Electrical Networks Standard Electrical Networks Principles and Performance
b98945f5-d15b-5899-b407-5c16f3fffc37 | note | Reference: L1-CHE-STD-015(1) MEST 000002-06(1
| section | Preliminaries - Materials
| checkpoint | 2.1 Procurement Materials delivered/collected to stores/Site.
b915d0b2-cd73-5fa7-ac26-166d45c7cf2c | note | REFERENCE: Contractor - Site Material Control procedure.
38833b4f-b7e9-59ba-a7fa-0d7848c79ab8 | note | • Cat5 Material received -Camms and Camms Tracking sheet
be89df3d-905c-538d-bf29-1c0034f544cf | note | – – – – – – – – – – – – – – – – –
2ed993e1-982b-55b4-bcdf-d6e85a258556 | note | ACCEPTANCE CRITERIA: Ensure materials are delivered/collected as required. Certificates of Conformity provided by MRPA
32216e13-dc06-5758-8c03-f120ec2eb3be | note | – – – – – – – – – – – – – – – – –
957893bf-7f7c-5782-b06d-266457ccaff0 | note | METHOD: Document Review
fd5c785b-22ce-5ec5-aff7-94a6b35164ca | note | – – – – – – – – – – – – – – – – –
c428cd55-f0a3-5e1c-a34f-416da412ccaa | note | FREQUENCY: Once for each supplier, prior to works start
d1ea52d3-a854-5562-b39e-7cd55267c5c1 | note | – – – – – – – – – – – – – – – – –
84a29e99-10e4-5e82-be88-f55624f936c5 | note | CATEGORY: IP
c4867068-de9c-5392-8e04-29cb61eb8814 | note | – – – – – – – – – – – – – – – – –
e32b1cc7-6492-5870-9664-f97439087249 | note | RESPONSIBILITY: MRPA Issue, CAT5 Receive
c41a05e3-b5b8-5c66-8ff9-c14580d6b40a | note | – – – – – – – – – – – – – – – – –
759a5f40-c084-5a31-8776-9d4b52388653 | note | RESPONSIBLE PERSON: MRPA
91d4340f-68a7-57ab-8a2c-2f38b181a5e4 | note | – – – – – – – – – – – – – – – – –
312dbf83-a94c-5e53-ab37-90325eb0b587 | note | VERIFYING DOCUMENTS: This ITP Signed Off
47fed2d5-f6de-5513-a2bc-8ae5ab6140b3 | date | Date Completed:
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Produce Work Package Plan
f7dda7e1-5f8e-5974-b5d9-d9e266e64352 | note | REFERENCE: Work Package Plan WAP_BR_184
3c1ea572-63f7-5b46-9f1a-55a0ae3a2aad | note | – – – – – – – – – – – – – – – – –
0738ccbc-2ca6-538e-a328-b1fa0c56e323 | note | ACCEPTANCE CRITERIA: Submission of Work Package Plan and MRPA approval and acceptance. Ensure work is carried out in a safe manner.
e3f82f64-1767-5457-82cb-238b709d2769 | note | – – – – – – – – – – – – – – – – –
c23a1a4c-6a68-54de-9192-0857a2fe3146 | note | METHOD: Document Review
2c62436c-4d0d-5751-b0f8-f0de5e080ad5 | note | – – – – – – – – – – – – – – – – –
ba37ec5f-a934-56c1-8a98-07314c55e806 | note | FREQUENCY: Prior to Works Start, TBC in accordance with MTM Standards
e6a25559-04da-5d9a-9834-d07e97255e4a | note | – – – – – – – – – – – – – – – – –
9c536746-3427-5f6e-a1d3-62b59b69851a | note | CATEGORY: HP
b8550e56-e6a0-5bd2-ae38-b874f0172448 | note | – – – – – – – – – – – – – – – – –
364d40dd-ecb3-5d14-aaf6-994379f1cc9c | note | RESPONSIBILITY: MRPA/CAT5
b1592a37-9bd9-5898-afc3-1c6c96836bc5 | note | – – – – – – – – – – – – – – – – –
6e3db35b-24c4-516a-a9e2-5a2dc520a1c1 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
492800d3-9ef4-5218-9d62-7b74d66e97b0 | note | – – – – – – – – – – – – – – – – –
f3508e5d-1929-5881-a88e-bc51d04d1037 | note | VERIFYING DOCUMENTS: This ITP Signed Off
3d54628b-ed28-545f-a9c7-ddcf73bd1ea9 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 Approval of IFC drawings
daab2dc2-2aed-51c3-b213-88e0e797ac25 | note | REFERENCE: Contractor Design Management procedure. MRP-DPK-089-00-ETN
a7f2f744-7855-58f0-b53e-531372b719e6 | note | – – – – – – – – – – – – – – – – –
cccb2177-5819-5e36-84d9-2c44b1fa8a50 | note | ACCEPTANCE CRITERIA: Ensure correct and most recent revision of IFC design drawings are used for construction.
b6870423-34fc-565f-af0a-d4b5b0e8ed4e | note | – – – – – – – – – – – – – – – – –
015f9e3e-e603-5731-bb31-b0209137c562 | note | METHOD: Document/Drawings Review
cdca1ab1-6792-5cb9-bdfe-040f2db1cecb | note | – – – – – – – – – – – – – – – – –
e1a50e6c-e614-5f6f-b0f8-c70d57d66b11 | note | FREQUENCY: Prior to Works and at regular intervals. TBC in accordance with MTM Standards
e7cf17b1-eb7a-599e-bd63-a2319292b595 | note | – – – – – – – – – – – – – – – – –
4164e0b3-50f9-5cea-8120-2b5939957bb4 | note | CATEGORY: HP
d4e9218b-2e8b-5bcb-9256-9302e2c07d56 | note | – – – – – – – – – – – – – – – – –
71f01712-bfb3-590f-b535-adb04e1f6c76 | note | RESPONSIBILITY: MRPA/CAT5
15d9f55d-e96c-589c-9457-3a3f1f20c6ab | note | – – – – – – – – – – – – – – – – –
4ba7541a-75f2-5268-8f4c-356de02935e8 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
3d9cd67c-25e8-561c-aba0-7750c17dccc5 | note | – – – – – – – – – – – – – – – – –
4d17844e-5bec-5dcc-98f9-2a5aa1862d7c | note | VERIFYING DOCUMENTS: This ITP Signed Off
dc1590f4-d914-56dd-ac85-ef9f48b65ff5 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.2 Task Specific Permits
a808d0b8-aa5f-52eb-bb55-758c634db23d | note | REFERENCE: Working at height permit. Hot works Permit, Permit to dig. OHLE SWMS
bead0857-905f-566a-9e08-39499fd01f95 | note | – – – – – – – – – – – – – – – – –
094081ce-9cb1-5ecd-881b-bde34674b09f | note | ACCEPTANCE CRITERIA: Ensure all task and activities have relevant permits issued and received.
95d4028c-79e4-5766-9146-e381ed40f719 | note | • Task Permits to be generated and signed off by appointed person.
e7f90e76-d86d-5b71-9c64-cec3ff1224f0 | note | • Task specific documents - MTM to issue permit to enter/Isolation permits etc.
80c11bb6-ee93-50a7-8b8f-ae5af84f5707 | note | – – – – – – – – – – – – – – – – –
d082b57b-8388-5991-bf9e-138e52d52e3f | note | METHOD: Visual, Document Review
828110d4-0118-5ca8-b864-504a6f16826a | note | – – – – – – – – – – – – – – – – –
e2d9d51f-9c47-552f-b774-4ecb322a5ba1 | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
dbf625f0-38f4-553a-8365-e71799eb3993 | note | – – – – – – – – – – – – – – – – –
5e322afc-0925-5e25-9744-aa64441b4247 | note | CATEGORY: IP
e70fefbe-c4c9-5034-b50a-392f197a0c0e | note | – – – – – – – – – – – – – – – – –
b5aa28b4-f368-521d-b673-63c3efa8d01c | note | RESPONSIBILITY: CAT5/MRPA
97252ea3-6a2a-5094-a75c-92e3a5bc267a | note | – – – – – – – – – – – – – – – – –
79ad0ba1-ca6f-5d03-a14c-0f93e04b1149 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
c40b0d11-dd78-5c0e-a23a-29b5ebad50d9 | note | – – – – – – – – – – – – – – – – –
a16ad815-6ca3-57d1-9f7a-c01f91de63b6 | note | VERIFYING DOCUMENTS: This ITP Signed Off
701222c5-a8da-5053-97d9-e5ae57d700a4 | date | Date Completed:
| checkpoint | 4.3 Cantilever assembled.
82682ea8-eac1-5ffd-a28b-2ba320c9fd00 | note | REFERENCE: Cantilever assembled as per IFC design.
e93646ee-9aa6-5ea2-8207-b5cbd2265519 | note | – – – – – – – – – – – – – – – – –
8791b9f0-d88f-505c-8e32-8dc9d7489877 | note | ACCEPTANCE CRITERIA: Relevant checks followed and adhered to-Cantilever Fabrication Check sheet.
c6626f11-fd00-5451-8d27-8cde469dd7cd | note | – – – – – – – – – – – – – – – – –
273c7330-b499-5368-9b94-d73d42877db6 | note | METHOD: Visual, Document Review
2eac80c8-2b26-5c2f-8639-39ebc8604c6d | note | – – – – – – – – – – – – – – – – –
957ef78a-150c-57f4-9bca-d88bf2c55e47 | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
b9f39006-85a1-5ad1-b045-dc7f590b54bd | note | – – – – – – – – – – – – – – – – –
cf0cfa87-bd51-5f49-954a-d4bd4c73e1fc | note | CATEGORY: IP
83b9f923-19e7-5367-9967-a39716089705 | note | – – – – – – – – – – – – – – – – –
25a44824-3c70-58ac-a5b0-a3572caefdae | note | RESPONSIBILITY: CAT5/MRPA
399fa014-5f00-50f8-97b7-0aed6575a214 | note | – – – – – – – – – – – – – – – – –
88278720-ecfc-5a4a-a7c5-c956c3bdf696 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
a9a93280-2e44-58bb-9de9-92ade7f0f8f5 | note | – – – – – – – – – – – – – – – – –
743d75fe-9895-56ee-a8a7-b50f3e2bb9cb | note | VERIFYING DOCUMENTS: This ITP Signed Off
48b61c1d-2662-55f9-aad5-bf5eff091374 | date | Date Completed:
| checkpoint | 4.4 Pre-Installation check
008719b5-3a53-5155-888a-5c14600ee012 | note | REFERENCE: IFC wiring layouts, IFC cross sections and BOQ. Engineering Drawings Management Policy (IFC/As-built) L1-CHE-MAN-001
42c04ab1-4d8b-539f-aa8b-7b21ad7b8169 | note | – – – – – – – – – – – – – – – – –
5e171dd5-bce9-58c6-a8b9-db0a41114f58 | note | ACCEPTANCE CRITERIA: Ensure that locations matches most relevant IFC drawings
4522dd04-3965-5424-8d21-43e9eaf7c77a | note | – – – – – – – – – – – – – – – – –
617ea455-e148-5877-baba-af6348ccbdd1 | note | METHOD: Visual, Document Review
f6500899-b549-5fca-a2fd-0e3dce75fcb4 | note | – – – – – – – – – – – – – – – – –
0feab0e1-999a-5006-accd-6794aa3f3634 | note | FREQUENCY: Each Task prior to works start. TBC in accordance with MTM Standards
331c84f8-ff0a-5a83-a122-f66ada9ed036 | note | – – – – – – – – – – – – – – – – –
05897bad-f57c-58be-9b6d-4fbec5e2fc17 | note | CATEGORY: IP
b7b05c6d-b610-53f9-8f97-32a0549c6c79 | note | – – – – – – – – – – – – – – – – –
08e9dc80-7a64-5f16-9550-4e2f6e745092 | note | RESPONSIBILITY: CAT5/MRPA
456db8f1-c810-54b1-a198-f5e7f18b9d81 | note | – – – – – – – – – – – – – – – – –
5d3cbece-bd97-52a3-84d5-84b42cc37caf | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
220aa530-c9ab-59f7-b2c7-37c349cae5d0 | note | – – – – – – – – – – – – – – – – –
385e5964-a7ed-553c-ab20-fe8641954384 | note | VERIFYING DOCUMENTS: This ITP Signed Off
f4700221-cd3d-5521-b38d-f74c58b1cae7 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Cantilever installed.
b655e08a-d10c-5b3b-b19e-18a5271e9d65 | note | REFERENCE: Overhead Line Electrification L1-CHE-STD-011(1) MEST 000002-02(1)
b7e372a0-17d7-508e-ac1f-bcc496322509 | note | – – – – – – – – – – – – – – – – –
4f56830a-1f89-597f-ada8-a80e321e3586 | note | ACCEPTANCE CRITERIA: Work instructions in accordance to IFC design
a6464319-40e6-58c4-aed0-8d8683c1ab9d | note | – – – – – – – – – – – – – – – – –
c5700654-3324-531d-803d-34c0d1823b9b | note | METHOD: Measure, Visual
7e9e2ec5-0e44-5061-83b4-5e74cf41c217 | note | – – – – – – – – – – – – – – – – –
50528d9d-8801-5311-a853-180696539ba7 | note | FREQUENCY: Each OHLE Structure
2280b815-5adf-51fa-9bc6-0141a56b62d4 | note | – – – – – – – – – – – – – – – – –
6eb8d0b5-85ba-5386-b207-3cd6e96d7caa | note | CATEGORY: IP
e6ddc833-9811-5e84-885d-4720742885d9 | note | – – – – – – – – – – – – – – – – –
206d02c7-2c90-5fc6-9cf8-d0b9c45b3f93 | note | RESPONSIBILITY: CAT5/MRPA
c6e6c0b0-d5ad-5b47-8119-e69fdd03247a | note | – – – – – – – – – – – – – – – – –
a4469103-9cfc-5592-95da-f030161bc8fb | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
87e3ad8b-766a-5f6d-877b-a08c5c82775e | note | – – – – – – – – – – – – – – – – –
00b5a61b-fd20-5305-93a9-f22851ee6109 | note | VERIFYING DOCUMENTS: This ITP Signed Off
2454fee9-b5c9-59e6-8741-3980486f880a | date | Date Completed:
| checkpoint | 5.2 Install SPS to correct height / position relative to track
b9ceb6bf-6c7f-5d71-9556-dd13c681e6db | note | REFERENCE: Design drawings, IFC cross sections &S tructure Gauge Envelopes – Minimum Clearance for Infrastructure Adjacent to the Railway
a6525e78-ce89-50ab-9a23-33109072429b | note | – – – – – – – – – – – – – – – – –
a16ff898-5fbc-5c1c-81b2-0ff5ef55901f | note | ACCEPTANCE CRITERIA: Ensure SPS is installed as per IFC design drawings/MTM design range. Supervision / checking to ensure that equipment is installed correctly.
687a0a09-507f-54fc-b5c7-435ff15b6149 | note | – – – – – – – – – – – – – – – – –
5f7c9c99-338e-5ca6-9c56-4ab70f0a5c6c | note | METHOD: Measure, Visual
50a8aa95-bbdc-5f5f-87f8-c239ae2fa9f8 | note | – – – – – – – – – – – – – – – – –
ecec2481-866b-53c2-8a9d-92c1f843daa9 | note | FREQUENCY: Each OHLE Structure
b3a7a143-d37e-5c6f-bdbb-7363618bc5ad | note | – – – – – – – – – – – – – – – – –
f68d0f5c-0ca7-5e6b-965d-be750dd22a08 | note | CATEGORY: IP
8b183e01-89f5-561b-a439-14b33fc9c40c | note | – – – – – – – – – – – – – – – – –
9299f6d5-3e4b-5ad6-adb0-b78ef4ffc81e | note | RESPONSIBILITY: CAT5/MRPA
073442c5-0eed-51d6-ba33-6b55c7e6ded4 | note | – – – – – – – – – – – – – – – – –
4142f8b9-1c96-5760-ad66-058cd0e7e29a | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
c3ca1f90-b682-5d99-8cc4-42ca5471b319 | note | – – – – – – – – – – – – – – – – –
6ca1b428-9103-5da3-b015-b2177c576956 | note | VERIFYING DOCUMENTS: This ITP Signed Off
e1091334-a650-58d8-aecb-08442d71ecf8 | date | Date Completed:
| checkpoint | 5.3 Cantilever checked once installed.
15250df2-9ee9-5601-bf60-120eb6dbe1dc | note | REFERENCE: Cantilever checked as per IFC design drawings/MTM design range. Completed check sheet. CAT5/OHLE/CHK002
66bf0ab2-468e-517e-8e73-464cbf403e66 | note | – – – – – – – – – – – – – – – – –
93231bf7-63d7-5c04-87fa-b89c5ee9e86d | note | ACCEPTANCE CRITERIA: Supervision checking to ensure that equipment is installed correctly.
068427c2-4b8b-5d5b-9146-6324dd35add7 | note | – – – – – – – – – – – – – – – – –
322cbb2f-823f-56d1-9d87-dd79e49d4a97 | note | METHOD: Measure, Visual
add3e80d-0cd0-51af-be70-21c1161a2692 | note | – – – – – – – – – – – – – – – – –
5c52cdbb-ed71-52c6-90e5-f3e1302a4d52 | note | FREQUENCY: Each OHLE Structure
e62a5da6-8207-5d8c-b406-10bdd2978f17 | note | – – – – – – – – – – – – – – – – –
f85cf3d7-ac7c-5156-8b7a-2225afa21ef9 | note | CATEGORY: IP
b71e627e-c0c6-5ae4-b6fe-97fe840c43bd | note | – – – – – – – – – – – – – – – – –
fe7bf8db-6dae-5a52-9b67-a5c48ff8c37d | note | RESPONSIBILITY: CAT5/MRPA
92cf09b7-1def-5108-b254-67e8537eb6bc | note | – – – – – – – – – – – – – – – – –
3d603d75-9b8b-57c5-92e4-9ddb0e4e956a | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
27dc2827-9d17-5ee1-99b3-d90f546d16c4 | note | – – – – – – – – – – – – – – – – –
1dffedf7-1f23-5b8a-b2d2-eb21f7f9d785 | note | VERIFYING DOCUMENTS: This ITP Signed Off
b570491b-f830-5ae9-be51-d0c2c1308e2e | date | Date Completed:
| checkpoint | 5.4 Installation of wire supports at the correct height and stagger.
39cec311-4f6a-50be-9a3d-6cfebae96b43 | note | REFERENCE: Install as per design drawings.
3f793b06-3ee1-5218-9667-24d9c7b6cb28 | note | – – – – – – – – – – – – – – – – –
cfe32586-4407-5f7e-9cf3-9e28173b863f | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
c733b666-05fa-5441-b29c-79f0cf84aaa6 | note | – – – – – – – – – – – – – – – – –
87db0936-97f9-54da-9d9b-55a7b9b6e72d | note | METHOD: Visual
53d8f9e5-ac8d-51eb-8519-dc5c9da91b98 | note | – – – – – – – – – – – – – – – – –
89ebf06a-3099-5cf4-9c59-701f8eadd4a8 | note | FREQUENCY: Each OHLE BWA structure
92e71d3f-ea6f-5800-8c18-dd2d65386ff5 | note | – – – – – – – – – – – – – – – – –
90d56878-3d43-5c1a-b160-40e4e8254ffd | note | CATEGORY: IP
9f01578f-7c3a-5d68-9dc7-e6d2deb7e230 | note | – – – – – – – – – – – – – – – – –
8990cf0a-31e0-5ca2-aff7-7e9830191951 | note | RESPONSIBILITY: CAT5/MRPA
95fe7077-f667-56b5-b465-466eac0d3595 | note | – – – – – – – – – – – – – – – – –
c2dc6271-e043-5ef8-a87f-dfdeeb3d83d1 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
3dd2a51f-974d-5ff3-91db-224738b4a1f0 | note | – – – – – – – – – – – – – – – – –
7c85d623-2e01-540b-afc3-94806c9776b2 | note | VERIFYING DOCUMENTS: This ITP Signed Off
34ca3eb1-5d7c-5f24-a513-15242fecd520 | date | Date Completed:
| checkpoint | 5.5 Installation of small parts
89dbf4ae-f221-5251-9178-12ad2ddec806 | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
547163e1-1dbe-5a77-800a-a24dfe97229a | note | – – – – – – – – – – – – – – – – –
18c78d7e-6c1b-5c36-a76a-a653220e9ee8 | note | ACCEPTANCE CRITERIA: Engineer checking to ensure that equipment is installed correctly.
895720b3-ce04-5244-a0a1-e6cc91359aec | note | – – – – – – – – – – – – – – – – –
99037496-7b4f-51f0-a0fb-00fc2bbebf8e | note | METHOD: Measure, Visual
8ec6eb79-8caa-558f-9133-0ba7e9e9dc94 | note | – – – – – – – – – – – – – – – – –
8e8ebdb6-ddb2-5e80-96c7-5ecb7735bc7a | note | FREQUENCY: Prior termination
9ee91cb2-f8e4-54dd-b9f9-0167d8917f24 | note | – – – – – – – – – – – – – – – – –
ef6709a8-490c-5c92-9ea1-e26143088e0d | note | CATEGORY: IP
904744dd-88e8-5a45-a581-599c47e455d7 | note | – – – – – – – – – – – – – – – – –
183e3647-d825-556f-a172-3927b7037ac4 | note | RESPONSIBILITY: CAT5/MRPA
8485e1b8-4f6b-5cbe-9591-c328f0666417 | note | – – – – – – – – – – – – – – – – –
7c09ce64-4044-58b3-8a03-360f9c4a8bb8 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
b447d557-d283-55f7-a578-6411998654b6 | note | – – – – – – – – – – – – – – – – –
bf4c814c-c948-5ecc-b4c9-ec4b7069ef25 | note | VERIFYING DOCUMENTS: This ITP Signed Off
9a884449-bd96-5bbf-a87b-4868422621f2 | date | Date Completed:
| checkpoint | 5.6 Complete Clearance Checks
44be5dfa-59d5-54d1-8d27-cd4ef267ffae | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
8c401aa5-9ea8-57c4-a816-ff39bd33f697 | note | – – – – – – – – – – – – – – – – –
e5b49eee-a4eb-5f8d-9c92-0895b185827d | note | ACCEPTANCE CRITERIA: Visual inspection for clearance and wire staging from Hirail EWP
15d9299f-55af-59a2-878c-d07e7ccea1b0 | note | – – – – – – – – – – – – – – – – –
06d1cce7-975b-5c19-9b27-a0166171e8e1 | note | METHOD: Measure, Visual
c0a53bb4-e0c5-5130-bd2a-ef1b3c2e8037 | note | – – – – – – – – – – – – – – – – –
1642612c-7bad-52f0-a69e-0c7ac867fb82 | note | FREQUENCY: Prior termination
57191d1d-7298-519b-97b5-c2d0d3a1f287 | note | – – – – – – – – – – – – – – – – –
6669ac8f-0d57-5e1f-8da8-57de4d05fea7 | note | CATEGORY: IP
c80c2d3a-e537-5e6f-b370-35837757b1f5 | note | – – – – – – – – – – – – – – – – –
911164aa-eb8a-5272-b276-9adaa5c400a2 | note | RESPONSIBILITY: CAT5/MRPA
d0fafb12-19ed-5d4c-8788-6fe9bb494e4e | note | – – – – – – – – – – – – – – – – –
7bef70f8-b115-55af-b3a9-e3fe388346eb | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
94f8bac1-91bb-5cc5-87ef-ea195ad71a77 | note | – – – – – – – – – – – – – – – – –
b2239774-035d-52af-a474-a00d73b5db5a | note | VERIFYING DOCUMENTS: This ITP Signed Off
c26c48b3-a1f9-5bc7-b579-33e824652a9d | date | Date Completed:
| checkpoint | 5.7 Comnplete Pan Run Test
bbf62334-33a1-585b-aea8-1daae39c818d | note | REFERENCE: Install as per design, use span/ambient temp. tension charts.
26f399eb-c7d6-5c1b-a525-b31a548fd3b5 | note | – – – – – – – – – – – – – – – – –
664fd989-293c-504b-82fe-9f0f8ee1716a | note | ACCEPTANCE CRITERIA: Check for wire take up, clearance, stagger limits and pantograph interaction to the contact wire
2403e822-f8e1-5c16-8183-2ff504bf8e23 | note | – – – – – – – – – – – – – – – – –
4df8c84e-b55e-5097-8b23-0a507713ff7f | note | METHOD: Measure, Visual
53285d54-f76b-58e3-a763-d3717e5f7d2a | note | – – – – – – – – – – – – – – – – –
74de396a-5e30-5306-a596-c46bcb1f2bbd | note | FREQUENCY: Prior termination
276ff33b-a2a2-59b3-bf8d-adac1d5b0f48 | note | – – – – – – – – – – – – – – – – –
54e5b85b-6f1e-57c4-a3e1-41565bcacc1f | note | CATEGORY: IP
ffe18dee-153c-50eb-8752-91dabfae2277 | note | – – – – – – – – – – – – – – – – –
09a051f6-c5aa-547e-af32-336824f55700 | note | RESPONSIBILITY: CAT5/MRPA
625da7bf-dba0-57ae-b9c8-7965b4299edc | note | – – – – – – – – – – – – – – – – –
51153f68-0754-51a2-84da-5cf6d11fef86 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
d49273f1-f9a7-5eb3-858a-e83d3396cee4 | note | – – – – – – – – – – – – – – – – –
3e88eb90-4b86-5fe0-946e-2e11c8d69442 | note | VERIFYING DOCUMENTS: This ITP Signed Off
cc2d6bc9-6c72-58a1-9445-13931429cefd | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Defects/Temporary Works
7b9c7309-6740-5046-a1d4-118a5e730fdc | note | REFERENCE: IFC wiring layouts, cross sections and design drawings.
e5525e6b-77db-54b4-a094-dd3c1ade290e | note | – – – – – – – – – – – – – – – – –
a365e8ce-f6fd-514f-bae9-14bd963ea124 | note | ACCEPTANCE CRITERIA: Ensure all Defects/Temporary works are capture and closed out correctly.
d55e9bba-a8ac-56d0-8782-7b66e9aa9225 | note | • Defect list to be provided at the end of Occo identifying planned work to rectify
cd65cd3c-b9f3-5a4f-8947-baf8c9bb44c0 | note | • Attach Design mark up, Defect list, temporary bond register, and approved TW design
f5f9e784-a78f-57bd-95b0-20e312c2670e | note | – – – – – – – – – – – – – – – – –
3b24d9e7-85ef-5c41-9da4-1e071e6927fe | note | METHOD: Document Review, Visual
dd0e9eb6-939d-55fb-9a5a-d67a658f4d3e | note | – – – – – – – – – – – – – – – – –
d95ee0f7-7cbb-5485-8734-3747dede0290 | note | FREQUENCY: Each OHLE Structure
f0de3209-c97f-54f9-996e-10c96f6ebf1f | note | – – – – – – – – – – – – – – – – –
ef9ced3d-a83e-5611-9e3f-446d2c49b6f2 | note | CATEGORY: IP
368cf96d-8307-5f91-a645-656e432623ca | note | – – – – – – – – – – – – – – – – –
a2b0f75c-a1b3-58a1-b226-44a51a80a311 | note | RESPONSIBILITY: CAT5/MRPA
cc289432-23da-56c7-8233-8b8332f69cbc | note | – – – – – – – – – – – – – – – – –
74efecc3-2b74-5924-8b6a-af233458f03e | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
09ab1626-e632-574b-962e-d2c95b99dc4a | note | – – – – – – – – – – – – – – – – –
9df425a0-d091-5736-bb46-e8543792b16e | note | VERIFYING DOCUMENTS: This ITP Signed Off
6c68e43a-5f2a-51c4-8c25-fb576890d8ec | date | Date Completed:
| checkpoint | 6.2 Relevant documentation readily available. (As-built Survey)
af04dcc4-73ff-5c42-87f8-93d32cc76ca7 | note | REFERENCE: As built drawings and check sheets to accordance to MTM Design spec.
2cc67f1f-a952-59de-a97c-e9e8812c27eb | note | – – – – – – – – – – – – – – – – –
4904c319-99b0-53e1-9ad9-b23ebb2c4fb7 | note | ACCEPTANCE CRITERIA: Ensure delivery of relevant documentation to client. As built drawings and check sheets. CAT5/OHLE/CHK/002 check sheets.
12579014-46ae-5a8e-8803-d055df398069 | note | – – – – – – – – – – – – – – – – –
bef7e962-e822-542e-9dff-0a5ca691e3c5 | note | METHOD: Document Review, Visual
51677779-e4ab-554d-8f3f-2a77576cf007 | note | – – – – – – – – – – – – – – – – –
4b7b1792-4acc-581e-bc31-fb0d4d81385b | note | FREQUENCY: Each OHLE Structure
5f1053a0-9540-5412-be2d-ba70fd7395f8 | note | – – – – – – – – – – – – – – – – –
2c0b0420-07b1-55d3-8c82-304925009eee | note | CATEGORY: IP
c9b92bb2-1b98-5860-ab7c-9acc67ec2c5e | note | – – – – – – – – – – – – – – – – –
33dac561-1109-5bd1-9ead-ccb86f5d7fba | note | RESPONSIBILITY: CAT5/MRPA
97c578cf-e6cd-5750-8bd7-75c58b3794c9 | note | – – – – – – – – – – – – – – – – –
e2deb94f-6051-5f53-b884-cffa55ae5cc4 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
f94d271e-6f3b-50f6-8284-e889005d2f0b | note | – – – – – – – – – – – – – – – – –
dfc785f6-5e49-50c3-bd34-3dd4d97c5d18 | note | VERIFYING DOCUMENTS: This ITP Signed Off
6e81c321-7e57-578f-aaea-ef0f314ab6b2 | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
5d500144-6b31-5380-8222-e47aadfdc0fb | note | REFERENCE: MTM Quality Management Plan
a8f351cf-6512-56b7-9166-1798c0736c0a | note | – – – – – – – – – – – – – – – – –
bbc3a735-c784-51ef-85eb-8b908835cf7d | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
d94d17d8-ce51-5d28-9207-e3a05b8a5ce7 | note | – – – – – – – – – – – – – – – – –
76864d21-f301-5908-a794-25c4eaa6d6ed | note | METHOD: Document Review
5fed554b-8559-500d-8a98-c4a0d062e58f | note | – – – – – – – – – – – – – – – – –
77b4577f-2bc4-5ab6-8d5f-6222b03883c0 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
7f85264d-5eab-5384-9e4e-2efcba1cb8ee | note | – – – – – – – – – – – – – – – – –
740b0f1c-0ac6-56c2-bce9-6ab1d7422f4e | note | CATEGORY: HP
549b3d4e-c593-5a5c-b0b8-9c6e975c5bab | note | – – – – – – – – – – – – – – – – –
dcb2b9c1-a381-5a48-a23d-500eb3cfc7ae | note | RESPONSIBILITY: CAT5/MRPA
2190a9dc-c31f-5d75-aea3-87ce1df711a8 | note | – – – – – – – – – – – – – – – – –
12f69d58-fa0e-5d14-af7f-07d4d3050ab8 | note | RESPONSIBLE PERSON: MRPA/CAT5 Engineer
18d9a169-f6e2-58df-9c27-7e7663f782d5 | note | – – – – – – – – – – – – – – – – –
9d2a06fc-69b8-5d49-966e-1cf7bc40c52b | note | VERIFYING DOCUMENTS: This ITP Signed Off
14c42c22-4397-58b1-8c5f-1881a2356aaf | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
f5d26889-266a-5e18-9fe0-824d714db650 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f15432e8-4726-5aa8-9b8b-7d3a375a2788 | textbox | Name:
bee45e76-87e1-5fd7-9100-21a2627e5db1 | textbox | Position:
2c65977d-b9a6-5274-b320-4d567966eee3 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-061-STR-Camms-Precast Barriers and Kerbs Installation Rev 0 | itp | ITP-061-STR-Camms-Precast Barriers and Kerbs Installation |  | 8ac872e8-5bd8-447d-9eae-c70dfc5acf01
| section | Referenced Documentation
| checkpoint | Referenced Documentation
a53da435-2360-53e2-8790-7ca167c0c5ae | note | Document Title: ITP-061-STR-CAMMS-Precast Barriers and Kerbs Installation
387f4898-3833-5e7a-a99e-12602b82843f | note | ITP Description: CAMMS-Precast Barriers and Kerbs Installation
53cd1d81-13eb-5331-9690-1599a96ed66f | note | ITP number: 061
df134883-4818-5df3-9dba-50316d4bbec0 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
4750af83-57ea-5404-86cc-3d274d1f526e | note | Discipline (e.g. CIV/STR/RAIL): STR
66482eac-d97c-5abd-844e-b5f3f9e26a20 | note | Revision Number: 0
bcbf1a26-7426-59e5-a4f6-776742bf7220 | note | Revision Date: 18/08/2023
d9f246f4-aeb6-5886-b1e4-02bdfeb6848d | note | ITP created by: Justin Kreinberg
bab5ea9a-1b7c-5dc5-b4f6-44b6352f37bd | note | ITP approved for use by: Victor Mira
22037ef7-3527-5bc7-a68c-1e52c1e383da | note | 1.1 Non Dependent
9461b3e0-4eef-5644-816e-90bd34f1349e | note | Reference: VicRoads Section 610 Feb 2020
a58cc799-3967-5cad-b8ca-50ae04ebce18 | note | 1.2 Non Dependent
2462fe35-3d4a-5d31-970b-5299039d6fa7 | note | Reference: VicRoads Section 620 May 2009
2422304c-0ebf-54ba-92d6-eeef4bb7b77f | note | 1.3 Non Dependent
f18fde9f-cbba-533c-b43a-1cbb67c40ebe | note | Reference: VicRoads Section 630 October 2013
cc42f35c-89fc-57a7-a607-a003e01af50a | note | 1.4 Non Dependent
7df45a25-802c-5122-be91-bc310bb721a6 | note | Reference: VicRoads Section 670 October 2013
b70ab8a9-7833-5e45-ae49-56f55534649d | note | 1.5 Non Dependent
4cd3551e-fb52-51c6-8607-c61743bf57d3 | note | Reference: VicRoads Section 671 October 2013
| section | Preliminaries Materials
| checkpoint | 2.1 Grout
8c109616-f509-57d8-b38c-65bc9e3a015f | note | REFERENCE: MRPA Quality Management Plan
a3ee2c98-403e-5ca8-a7a4-02a5e2d0d049 | note | – – – – – – – – – – – – – – – – –
b5b3aaf0-d4a4-5224-b517-e27e484a2328 | note | ACCEPTANCE CRITERIA: Details of the grout to be placed between the precast elements to be submitted for review to the Nominated Authority.
640bf39c-0850-5f74-8897-6536073deee9 | textbox | Enter: Teambinder Material Approval number
255fbe77-f19b-571e-a6e8-0431522be29f | note | – – – – – – – – – – – – – – – – –
efa3d10a-9e40-5351-bd69-ecfe77e41236 | note | METHOD: Document Review
a91eaa03-ae65-55ea-b595-4337144fa04e | note | – – – – – – – – – – – – – – – – –
602de65a-d0bf-5aeb-ae45-b71008ec07e4 | note | FREQUENCY: Once, for each product
046c3c8b-9a5a-56e6-9f2b-5058b18ee090 | note | – – – – – – – – – – – – – – – – –
ff6b5795-425e-5a7d-99b1-285186c93c89 | note | CATEGORY: HP
11050bc9-436f-502c-80fc-02c60897ba9a | note | – – – – – – – – – – – – – – – – –
67938f7c-c8cc-5947-b720-55c4a0196020 | note | RESPONSIBILITY: Nominated Authority
94f45fda-2b51-599d-ab85-8892ad2ca9e4 | note | – – – – – – – – – – – – – – – – –
bf341cf3-d35f-58a6-8c7a-d2873995bb76 | note | VERIFYING DOCUMENTS: This ITP
b348d65e-4336-589e-8ba0-84d75f6d3e7f | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Documents
| checkpoint | 3.1 Precast Elements
06bf8a18-fb9c-5f35-891a-bc90695c3ae1 | note | REFERENCE: IFC Drawings VR 610
7b786dc7-c2f6-55d2-8f3e-bbaa875e7240 | note | – – – – – – – – – – – – – – – – –
6c5200da-61e8-5ab7-90d9-a76bb4b0a19a | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
65ceb7e2-c639-5879-a6a1-48aee334fc82 | note | i. Certificate of Compliance / Birth Certificate
4c22fb57-448a-5086-9523-96394098e254 | note | ii. Compressive strength test results
b798917a-5cfa-5b7e-895e-d774b092e7f0 | note | iii. Precast Lifting Design
43b4b220-d474-58aa-ae0a-0f4c18b3137b | note | iv. Pre-pour check sheet / ITP
2f4d33b1-777b-5888-9c87-0cb10dea7069 | note | v. Post-pour check sheet / ITP
0b0b189a-7a7c-504e-a033-9ee9a0697111 | note | vi. Covermeter check record
c2472efe-41ab-5255-b4dd-98c79cae9aed | note | vii. Record of dimensional measurements
bd11f0ce-c895-57a7-83f2-a54c074299de | note | These documents are typically stored in a MDR Lot in Team Binder.
683dc3a6-188c-5e90-9365-834a9653eafd | textbox | Enter: Teambinder Material Approval number
6d9d8323-b993-50c7-9c93-9e81c827c051 | note | – – – – – – – – – – – – – – – – –
f85dbc13-bbde-5fda-a70a-50b5b347a9f1 | note | METHOD: Document Review
bac69bfb-1773-5433-9a7c-1cc13e67956d | note | – – – – – – – – – – – – – – – – –
14bc92fa-f4a8-52fa-bb35-aa81ba3a36ce | note | FREQUENCY: Each element
37d83823-52e0-54a3-8dd6-b4d644a85904 | note | – – – – – – – – – – – – – – – – –
a39ae726-10d2-5aaa-8988-2762e986e44a | note | CATEGORY: IP
044cde5b-3fc1-5b54-9eb3-058500235404 | note | – – – – – – – – – – – – – – – – –
89217913-79ec-512e-86b1-fae29953330d | note | RESPONSIBILITY: PE/SE/SPE
2434b1de-dd3b-55e2-85ea-f1e7a1c68d9c | note | – – – – – – – – – – – – – – – – –
e330fdaf-b31d-5b63-9f08-3ff67bf45164 | note | VERIFYING DOCUMENTS: This ITP
48683fc4-4ede-57f8-aaa5-9905e1703651 | date | Date Completed:
| checkpoint | 3.2 Bridge Deck / Foundation Compressive Strength
5a512701-0192-50e7-9f9e-e73b54ba0fa2 | note | REFERENCE: 671.03
c846bc91-9a00-52ac-9847-f15e06f28f1b | note | – – – – – – – – – – – – – – – – –
809d91e8-3400-522b-9efe-ac2e01bbedfa | note | ACCEPTANCE CRITERIA: For Precast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
34dffbf5-57d7-53af-8fec-014b513d7a73 | note | – – – – – – – – – – – – – – – – –
42700a9f-9429-59f9-8d45-91d1f0661488 | note | METHOD: Document Review
059cef08-a668-5f9a-aec4-6b7b99c0746d | note | – – – – – – – – – – – – – – – – –
9fa49d35-b210-521e-afff-2ddb9f8aefe0 | note | FREQUENCY: Each installation location
cb2c1480-db0a-526c-830b-d3ece49df9dc | note | – – – – – – – – – – – – – – – – –
232d7792-beb8-56a2-9f60-fd7beff14504 | note | CATEGORY: HP*
3e9f5f5b-8638-5de8-a902-bdfae75babf8 | note | – – – – – – – – – – – – – – – – –
d2347529-6bb1-574f-9415-378eff651d58 | note | RESPONSIBILITY: SE/PE/SPE
a38df15f-f4cf-55c2-aefc-59b65526dca8 | note | – – – – – – – – – – – – – – – – –
05598c8a-53f3-574b-9f90-ae0582063bdf | note | VERIFYING DOCUMENTS: This ITP
3acefe46-5185-55bf-9a3b-c8fd8877911e | date | Date Completed:
| section | Pre-installation Activities
| checkpoint | 4.1 Survey Set-out of Precast Elements
11749285-9d9f-52c2-8b7b-8d313e9fb256 | note | REFERENCE: IFC Drawings
5bfd533b-6ad7-5687-9eeb-0198b70aec08 | note | – – – – – – – – – – – – – – – – –
d3e5a89f-5f9e-51f3-9a46-463e47c4e038 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
12eea823-fcce-505b-8146-cba09cac59a5 | note | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
2eca082b-4bfc-5028-878b-10e3acd8b5ec | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
a7853e3c-19d6-5f5b-a56e-52e0381d8494 | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
f921a761-c84e-5833-87c5-4fc52645333e | note | – – – – – – – – – – – – – – – – –
df31871c-ce97-5b30-be73-95e039862ef1 | note | METHOD: Measure, Visual
ed3b83a9-0ed5-5332-ad31-65d66026b0b8 | note | – – – – – – – – – – – – – – – – –
5e9fe89a-9189-5fb2-8e32-a14ee6eca202 | note | FREQUENCY: Each element
5af914f8-e78e-5eb7-9f51-5dce6c037711 | note | – – – – – – – – – – – – – – – – –
1b530d87-968f-542c-8af1-39aa10b3de53 | note | CATEGORY: IP
60a19e11-5a06-5464-9cde-dccae4f3c961 | note | – – – – – – – – – – – – – – – – –
666549d5-b60a-5173-bea3-7ec24650b8b0 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
e1d3bc2b-ff3b-5003-8efd-deac9029f25e | note | – – – – – – – – – – – – – – – – –
c573923c-fca3-5457-9478-f1a13fe3a7b4 | note | VERIFYING DOCUMENTS: This ITP
6da5fb78-8c57-5309-ab66-bb5e302273a5 | date | Date Completed:
| checkpoint | 4.2 Bearing Shims or Bearing Strip Placement
39576289-6668-55ac-a0b5-ff948bc93c55 | note | REFERENCE: IFC Drawings
ef57a83e-3e4e-53f8-a298-0f6a985cbd0d | note | – – – – – – – – – – – – – – – – –
a5b11f86-119b-573c-9d19-2ea3b8fab857 | note | ACCEPTANCE CRITERIA: Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
99a35fb1-0ac7-5d3e-8acc-2e473c86e479 | note | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
6f82a083-f7ad-5f1f-9c3c-e6477ad2c167 | note | – – – – – – – – – – – – – – – – –
510779bf-9c0e-5098-b2f1-5fe03849b497 | note | METHOD: Measure, Visual
43ee9550-b1bf-5032-b0cf-93453e0d7882 | note | – – – – – – – – – – – – – – – – –
1f1afff9-bd38-5786-8f93-182643274e35 | note | FREQUENCY: Where applicable, each installation location
b1def477-f9d5-5805-ba5c-c8988af35a2b | note | – – – – – – – – – – – – – – – – –
3f0f2170-b039-585a-b00e-c00c769fa046 | note | CATEGORY: IP
3c9a2fcd-fe4b-5822-aa79-4339ae126869 | note | – – – – – – – – – – – – – – – – –
ab599359-e5b6-5882-a5db-fb33ab13a63d | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
bf26ebc8-7d7e-5764-8c1b-a0a0cded0699 | note | – – – – – – – – – – – – – – – – –
6919c848-9c27-56da-9ada-8ff27c611c63 | note | VERIFYING DOCUMENTS: This ITP
84331ca5-5ca7-5591-989d-0a30ae864d5c | date | Date Completed:
| checkpoint | 4.3 Bitumen Board and Ableflex placement
fd5752b6-7438-5862-8a5b-c9bcd1516d70 | note | REFERENCE: IFC Drawings
6b89d76b-59ec-5a9d-9152-344ebe8d88fc | note | – – – – – – – – – – – – – – – – –
a3970bd4-b8be-5529-b2d7-2fa1f92ab24b | note | ACCEPTANCE CRITERIA: Adhere any bitumen impregnated fibre-board and ableflex into the positions shown on the IFC Drawings and where grout or concrete ingress will affect the end use (such as around conduits).
7b64eaa5-7001-52ae-af1e-89a9b6850ff5 | note | – – – – – – – – – – – – – – – – –
33020c6d-f121-5bc8-9526-95ed3cce6385 | note | METHOD: Measure, Visual
c08b1034-056d-565c-bac1-a6a4c47b6b06 | note | – – – – – – – – – – – – – – – – –
1411b4d3-5758-50ee-84ee-74b5feab7bff | note | FREQUENCY: Where applicable, each installation location
41782e8a-9ca0-5214-9914-a0ef98b321d8 | note | – – – – – – – – – – – – – – – – –
387550f3-9045-5978-bb89-13110d983e10 | note | CATEGORY: IP
0f9c6633-bb06-52fe-a663-26c1ad4838a7 | note | – – – – – – – – – – – – – – – – –
bdfa6b67-d0a1-50d9-bbb7-944f80004a98 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
18f6cefb-7c30-599c-9975-f6be1f1ed684 | note | – – – – – – – – – – – – – – – – –
c8f63915-ec55-5a0c-9e97-75905e83ee62 | note | VERIFYING DOCUMENTS: This ITP
955c1855-f42d-5946-8f1f-c9b7066c7ab5 | date | Date Completed:
| section | Installation Activities
| checkpoint | 5.1 Precast Handling
17801aa4-ccfe-550e-884e-48fc4ebdfd9a | note | REFERENCE: 620.07 Crane Lift Study
c2de8f58-9fab-5389-8822-e6f7c28f8b07 | note | – – – – – – – – – – – – – – – – –
f016a1f5-05a4-5e80-be9b-a0258ff8d02e | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
8e4a4a43-6534-54f8-8a49-d9c8fc7cdefc | note | – – – – – – – – – – – – – – – – –
61aad7a8-fffb-5267-82ba-7e8281c362a4 | note | METHOD: Visual
09b3e89f-ce8a-506e-bd92-f860c00fc740 | note | – – – – – – – – – – – – – – – – –
08adf102-b6a2-5e8d-96bb-c7675a0d28f1 | note | FREQUENCY: Each element
b566878c-bf0e-5d6f-af76-3cdace14f25e | note | – – – – – – – – – – – – – – – – –
6d4fcdba-254e-55a9-ad96-60d6ed30ee71 | note | CATEGORY: IP
48f722c6-3848-5a58-838e-3b11a19e80b6 | note | – – – – – – – – – – – – – – – – –
d68684af-0392-5fdd-9b9a-27f5a276482c | note | RESPONSIBILITY: SE/PE/SPE
9ca49572-f29f-5434-a4e3-876521785dfc | note | – – – – – – – – – – – – – – – – –
bb707816-f36c-5a9b-833c-027173a932a8 | note | VERIFYING DOCUMENTS: This ITP
22c527a7-dff6-597f-abab-4ab967fbf240 | date | Date Completed:
| checkpoint | 5.2 Precast Placement
f71cae77-2a2c-5054-9532-6d6b3ce58f9e | note | REFERENCE: IFC Drawings VR 670.05
cb2f0d46-e152-5619-adf5-5fddda73bf33 | note | – – – – – – – – – – – – – – – – –
4a2baf9b-e5e2-56c6-bf54-2b9eb22f5afd | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
617207a3-83c5-5206-bf2e-b4aa11c87ba2 | note | Adjustments to be made to achieve following tolerances:
4e2e566e-d320-5338-8795-5bda66119466 | note | (a) Departure from plan position: 25 mm
08d457fc-2998-5824-807e-679b6862b6c0 | note | (b) Departure from alignment: 5 mm
d01f2829-74ee-5723-94e2-147ef03cf0b6 | note | (c) Irregularities in alignment: 3 mm in 3 m
4dfbad19-e3bf-561d-8bf8-c362150ebd90 | note | (d) Variation in joint gap width 3 mm
cfb19b34-e0c3-5345-8e58-f36bf6e00307 | note | (e) Verticality of posts, panels, balusters and openings: ±2 mm
960e2afe-6d7d-5a23-a8fe-7af1c88f4b52 | note | The nominal gap between elements is as per the IFC Drawings.
a62d8384-5857-516f-9a81-8e246b8e211d | note | – – – – – – – – – – – – – – – – –
d8fcc950-3425-5320-a6fb-533bfd880c2d | note | METHOD: Measure, Visual
95652cd5-85fe-5569-94d9-9755b84411a5 | note | – – – – – – – – – – – – – – – – –
1f24db4c-183d-5318-9afc-4a06a2cc5ecf | note | FREQUENCY: Each element
fb91dcf9-dd73-51af-a64d-01240aac5a9c | note | – – – – – – – – – – – – – – – – –
66dd3b20-21cc-55ab-9f63-c92af546a1a6 | note | CATEGORY: IP
98bceba5-e94e-53fa-ba09-e5ed655edc42 | note | – – – – – – – – – – – – – – – – –
1854a6c2-e821-5419-98d3-38dd5583bc24 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
90910fd9-8fe4-5cb3-8925-e4341a2a1cc1 | note | – – – – – – – – – – – – – – – – –
596a819b-47f6-5edb-b1df-8bf6df9e8424 | note | VERIFYING DOCUMENTS: This ITP
6da4757b-db10-5c2a-920e-f7d3e8b7d354 | date | Date Completed:
| checkpoint | 5.3 Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
153428e4-35a9-57c8-84c9-3597b0787fd6 | note | REFERENCE: IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3
e2fd2540-59e9-5f47-8a5e-930f901fd842 | note | – – – – – – – – – – – – – – – – –
33841e5c-aae3-5535-93d3-92fcac811df5 | note | ACCEPTANCE CRITERIA: Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
a95d5151-eb9e-5fc9-a9b5-d56974a992b2 | note | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
6bbfa7f0-7469-55af-8701-73ebabde1eac | note | ○ Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
7c3045cf-ac58-5adc-9320-ed2c66890dc0 | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
b50a7913-7e44-51ba-b912-40ac6bb4ea13 | note | – – – – – – – – – – – – – – – – –
819e1ee6-6fa5-5c8f-85be-f230d0f8c8bb | note | METHOD: Visual
c77a6bf3-5f2f-5c6d-9f7a-a9f4bfac3ec4 | note | – – – – – – – – – – – – – – – – –
2c915e5f-f464-51f0-a493-e6be2f5c55b7 | note | FREQUENCY: Where applicable, each bolted connection
3cf3089f-3a5e-5d2e-9d13-c92548842ad4 | note | – – – – – – – – – – – – – – – – –
d2b55415-d0cf-5e36-b2ae-6f6af128407e | note | CATEGORY: IP
a0ed5873-8919-5130-aa2a-bb59da7c161f | note | – – – – – – – – – – – – – – – – –
d5660482-752a-558f-b563-c7ba01f219a0 | note | RESPONSIBILITY: SE/PE/SPE
3cff8e74-b4c3-5e47-97c7-27180eb2f575 | note | – – – – – – – – – – – – – – – – –
b00c5784-f4b8-55f7-b84a-cd8a9ec7ebc4 | note | VERIFYING DOCUMENTS: This ITP
0988da81-3a7a-53d2-9011-f3f5ff51d3f0 | date | Date Completed:
| checkpoint | 5.4 Precast Traceability
2600e079-3507-5901-8243-2d484d1b8816 | note | REFERENCE: 620.09
2e7d1c70-596a-5b1e-ba76-2753db3be0cc | note | – – – – – – – – – – – – – – – – –
7e2b6a79-7115-57d2-9b5b-97524bfbcf10 | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
2f1ae554-b19e-59c2-b40f-ba036144f344 | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
0a1c574a-9960-56e1-95e0-162a259ff611 | note | – – – – – – – – – – – – – – – – –
b1b7f35f-1ca2-51f8-a46e-a4b49d75e332 | note | METHOD: Visual
50e942d6-2224-56f2-9d5b-4927c98c037f | note | – – – – – – – – – – – – – – – – –
3c3e3ddd-a744-5b6d-935a-7ddd6d06fe91 | note | FREQUENCY: Each element
a3554819-26b5-5030-b74f-3ddf9538569d | note | – – – – – – – – – – – – – – – – –
f6a8a767-0784-5e3c-a608-6e2041369ebb | note | CATEGORY: IP
ec70d828-3abf-535b-a5ca-209770a25853 | note | – – – – – – – – – – – – – – – – –
92a04c7a-6d8c-503e-99b1-172ee02c6dd9 | note | RESPONSIBILITY: SE/PE/SPE
236706bb-1250-5a6a-adbe-a58375b06d21 | note | – – – – – – – – – – – – – – – – –
866ea223-7b43-56a6-8ec8-d4f29eb1a849 | note | VERIFYING DOCUMENTS: This ITP
2271ebfb-64ac-5ad8-8da9-6c7999a7f913 | date | Date Completed:
| section | Post-installation Activities
| checkpoint | 6.1 Flowable Grout Pour
8a2b9169-1802-5366-affc-63941dd94026 | note | REFERENCE: IFC Drawings
d2b87daf-f6a0-557e-b59e-dbb065bbc41e | note | – – – – – – – – – – – – – – – – –
6001c0ae-569c-5e98-975e-3fbc8da57651 | note | ACCEPTANCE CRITERIA: Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
40aca846-fbe1-59c2-ba14-cd74046eef09 | note | Complete: Grout Pedestals & Bearings ITP
8dd8a388-3da7-5374-b10d-0e39f9ded3a9 | note | – – – – – – – – – – – – – – – – –
27852465-69be-5a23-9b4d-0bd000b6b95c | note | METHOD: Visual
6227237d-18e7-5f6f-873c-7c31a6a3fe35 | note | – – – – – – – – – – – – – – – – –
c3e66e18-ef61-57d0-8564-e5046b8cead6 | note | FREQUENCY: Where applicable
f9804177-dabd-5c73-9eae-4b5699fcf0ac | note | – – – – – – – – – – – – – – – – –
93498ab8-5041-558d-9330-fb10147e06be | note | CATEGORY: IP
181f6728-4d92-530e-bf26-b70bf4869125 | note | – – – – – – – – – – – – – – – – –
3afced7d-6541-55ed-a005-e08cf13c6aea | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
b383cf26-54df-5bbd-af37-aa452ea85bf2 | note | – – – – – – – – – – – – – – – – –
ef98ad04-7b13-5672-894d-3e2005245f26 | note | VERIFYING DOCUMENTS: Grout Pedestals & Bearings ITP
75bdad51-e4bc-51c6-9a01-f61079e2bc12 | date | Date Completed:
| checkpoint | 6.2 As-built Survey
33022dcb-72c7-57e2-af35-b55345ee1fb2 | note | REFERENCE: IFC Drawings VR 670.05
f6cc26b6-8e5e-57b9-9e13-8c5fa39af823 | note | – – – – – – – – – – – – – – – – –
4efee5ab-7f4e-5653-9651-c1711fb1f583 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per VR 670.05
a43ce4b7-5c8e-55e2-8db8-64aa39153a9a | note | (a) Departure from plan position: 25 mm
69e01b93-bfdd-5ef5-a76a-7409549efc06 | note | (b) Departure from alignment: 5 mm
ff5aaa4e-f0c6-5071-88ba-1ed4d76d4b76 | note | (c) Irregularities in alignment: 3 mm in 3 m
603a9d02-b0c0-539a-b862-d64a9ddbdfbb | note | (d) Variation in joint gap width: 3 mm
17c7c613-3237-5b3f-b019-a25a3f0ca958 | note | (e) Verticality of posts, panels, balusters and openings: ±2 mm
9bee831c-5e6c-5d0c-a911-c6607159d05b | note | Attach: Survey As-builts / Survey Report
0aef35c2-b698-599e-ba79-f5cc4820a2e8 | note | – – – – – – – – – – – – – – – – –
a1c2f68c-111e-5b30-90d6-e88ce049f73a | note | METHOD: Document Review
b6e2fcfc-e52f-5d8e-8e99-3b2ab4473b2d | note | – – – – – – – – – – – – – – – – –
336e1da6-39db-53df-b75b-c0356b61b0f8 | note | FREQUENCY: Each element
78bbbd53-3f2c-5db2-9660-e906263234a4 | note | – – – – – – – – – – – – – – – – –
60252a0f-3857-5f06-bb73-20e19fff98f5 | note | CATEGORY: IP
c03f5f11-26f9-59fb-a4d8-94e378713447 | note | – – – – – – – – – – – – – – – – –
9f8f2fc2-47a9-5416-bdd0-b207d1848960 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
68ecacb5-7517-525c-8f90-41ee4cb878ec | note | – – – – – – – – – – – – – – – – –
66c6e53a-d631-5f7c-afb9-e2d2fd5e031b | note | VERIFYING DOCUMENTS: This ITP
098668b5-79d7-5acd-a958-9c2fac70c114 | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
572f0a77-d107-5517-8d78-b6e11cfe6b8e | note | REFERENCE: MRPA Quality Management Plan
abbe9589-f4c1-53de-9104-945dd1a09728 | note | – – – – – – – – – – – – – – – – –
4fda35ff-c77d-5349-bcc0-1f0e71066e2f | note | METHOD: Document Review
a290f0ee-d079-5525-b5fa-1d4238e0e178 | note | – – – – – – – – – – – – – – – – –
8d508aae-7152-5a7a-99e8-4e2f398a1682 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
bada74ce-e093-502e-a38f-d78cbfdd9010 | note | – – – – – – – – – – – – – – – – –
bea508f7-faa9-5699-877d-d1ef02720e53 | note | CATEGORY: HP*
6d78880d-ae61-57c5-b64e-246670da2da0 | note | – – – – – – – – – – – – – – – – –
7dcd1a7e-0b53-5857-8512-8a9136f01ee8 | note | RESPONSIBILITY: SE/PE/SPE
2b6b026a-38a3-5ddc-a8c7-a0c3a76f3aaf | note | – – – – – – – – – – – – – – – – –
a4e2c0f5-0ca3-5480-a81c-6da91e31f7a2 | note | VERIFYING DOCUMENTS: This ITP
260b0cfd-2b0f-509d-af29-f83693e2df26 | date | Date Completed:
| checkpoint | Final Inspection
b6aefe95-827e-5b44-9f9d-a27ed2c14d7d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
763de495-db05-5e3b-afa6-a5cfb2dea804 | textbox | Name:
b92a7c19-7ee9-5e85-9d27-7bbfa1d134a4 | textbox | Position:
049fd50e-9460-5fb2-91b2-6867cc21af1a | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-062-CIV-Camms-Hot mix Asphalt Rev 0 | itp | ITP-062-CIV-Camms-Hot mix Asphalt |  | 50007c25-3069-49d4-b6e3-9de97ba9dbf9
| section | Referenced Documentation
| checkpoint | Referenced Documentation
cd537407-d953-5df5-9489-fd6d5fa20afb | note | Document Title: ITP-CIV-Camms- Hot Mix Asphalt
0674bf51-e583-5c14-9aeb-1b43920245da | note | ITP Description: Camms- Hot Mix Asphalt
344ed78c-526e-50e0-82a8-f08800487c39 | note | ITP number: 062
764db54a-4bf9-5925-b4c6-b1585f09a073 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
ecb7bce8-4433-5237-b191-8a7d884947ac | note | Discipline (e.g. CIV/STR/RAIL): CIV
7e1f63ec-6c8b-5b6d-b30d-d15bb5fb7fda | note | Revision Number: 0
ae2185af-560e-5d94-bb3f-fc8218574449 | note | Revision Date: 31/08/2023
5283c278-b659-589d-a785-31f967aa62f4 | note | ITP created by: Victor Mira
3605730d-df93-5de9-b7a7-cc4aa2539ff6 | note | ITP approved for use by: Victor Mira
b42f2a66-69c5-5165-9bb8-fd073206e778 | note | 1.1 Non Dependent
a6169124-16db-51fc-8f6e-6705f1c3c11b | note | Reference: VR 407 - July 2022
01e468c8-99bf-5327-9bad-6b210fcced5c | note | 1.2 Non Dependent
b6cb1a51-c72d-5dad-9b5c-2171bda86181 | note | Reference: VR 173 - Oct 2008
| section | Preliminaries - Materials
| checkpoint | 2.1 Mix Design
f5d84941-efb1-5bf2-99aa-d995d0b1597c | note | REFERENCE: VR 407.09
1373e354-13d6-53ad-9966-517a3094ae9e | note | – – – – – – – – – – – – – – – – –
009313df-5dae-55a7-8b3a-44bb2be50d69 | note | ACCEPTANCE CRITERIA: All asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport as ‘General’, unless otherwise approved by the Department of Transport. The registration for all mixes incorporated into the works shall be current at the time of their use.
0c2a0a04-8967-5c47-b038-051e2f3532e8 | textbox | Enter: Teambinder Approval number
6c1580e1-4cce-57c6-9c43-8f1119a0ec5b | note | – – – – – – – – – – – – – – – – –
0c3eae2c-e2a3-5356-a44b-238eea6a8715 | note | METHOD: Document Review
7310c9cb-52f3-5e53-8b5a-ec917e49134d | note | – – – – – – – – – – – – – – – – –
43ac833e-604f-5677-82bb-ec6022af18d1 | note | FREQUENCY: Each Mix
56559046-e86f-5fb2-baf1-82739c81d220 | note | – – – – – – – – – – – – – – – – –
1ff63f6e-26e0-5379-a890-1432444ebd29 | note | CATEGORY: HP
e7d12540-31dd-532b-a676-52e0a6e0973f | note | – – – – – – – – – – – – – – – – –
5258e5ea-c0c2-54b2-b0d4-1663b0a44e1c | note | RESPONSIBILITY: PE/Nominated authority
00503c32-573c-50c9-9c0b-0e35257747bc | note | – – – – – – – – – – – – – – – – –
9164c4f8-58a9-5e9f-a13d-9c48ae0c3c13 | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
1dea9a50-bc94-5e42-959a-9b0d0a19557d | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Bituminous Materials-Tack Coat
b1253f3d-f4da-5179-9cec-740bc55067a8 | note | REFERENCE: VR 407.08 (d)
455a07f0-a9d5-5660-96ea-7d3cfa8806d7 | note | – – – – – – – – – – – – – – – – –
2c2188f8-b83e-55eb-8260-cb6a2ecff04c | note | ACCEPTANCE CRITERIA: Tack coat shall consist of a bituminous based binder.
38206b94-cdca-5113-90ec-6b9839c627a4 | note | ○ Only trackless tack coat or a tack coat application system that prevents pickup of the tack coat must be used.
e38b384c-4465-56a0-8fac-42663694bd94 | note | ○ The Contractor shall submit the details of the trackless tack coat proposed to be used in the works.
239c862f-33ef-573a-97f5-f3b2ebb9247e | textbox | Enter: Teambinder Approval number
9413792f-4ff0-543e-aa9f-219e55d9982b | note | – – – – – – – – – – – – – – – – –
78f6a437-f4ca-55b1-9514-4cf08111aea4 | note | METHOD: Document Review
142ac287-c3af-578a-ac63-b1e1f44eda42 | note | – – – – – – – – – – – – – – – – –
9a64a841-e9a4-5dae-a585-7379c7c63c4c | note | FREQUENCY: Each Material
152d9056-a14e-5d08-b87e-f7665d3f7a34 | note | – – – – – – – – – – – – – – – – –
911a7a9a-450d-5fbd-aa3f-83b6ea2cdc7f | note | CATEGORY: HP
c452e0ff-73e5-55c5-b86e-7a59a13d84a8 | note | – – – – – – – – – – – – – – – – –
40187339-9b70-5703-9834-1c247b6a471a | note | RESPONSIBILITY: PE/Nominated authority
9d0f19f0-96ed-5750-9be7-6bfe6b95ba5e | note | – – – – – – – – – – – – – – – – –
c5b48ce5-8334-5362-ac98-863b891ae178 | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
54238ff8-5730-52fd-9c14-a4d6ecf0fd1e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Asphalt Quality Plan
7fc33216-0d32-52cc-8011-f80153b529c2 | note | REFERENCE: VR 407.04, VR 407.11
d90deb5a-1537-5601-a007-73fb3b13ac93 | note | – – – – – – – – – – – – – – – – –
2a6fa307-1f82-5947-8cb7-50e16f091dac | note | ACCEPTANCE CRITERIA: the Contractor shall provide an asphalt quality plan that addresses the following requirements:
980c0e1e-5930-578d-ba5f-53c4eb471b33 | note | ○ RAP Management plan (Approved by DTP)
6a796449-ddb9-55a1-b9af-e4228170d3a6 | note | ○ asphalt loading and transportation to minimise segregation and achieve adequate mix temperature on delivery to site
c984d24d-06fa-55bd-bce2-c1344092484b | note | ○ measuring and recording of pavement temperature, wind speed and weather conditions
e201796f-3105-56dd-b205-8926559811ad | note | ○ achieving a uniform application of tack coat
3322a231-4cfc-56e4-9068-60e21bc4763e | note | ○ achieving uniform asphalt placement including determination of paving speed and paving plans
a29dc359-7d8a-5fb0-bb00-1bd44d3d4098 | note | ○ determination of appropriate compaction equipment, number of rollers and rolling patterns required to achieve density
2a5a53d5-5994-5146-873e-472a33671020 | note | ○ procedures to maximise density at joints.
e382e97d-0f36-5159-99ee-96f51fa0ed4e | note | ○ Production, storage, discharge and compaction temperature ranges for warm mix asphalt shall be included in the Contractor’s asphalt quality plan.
e2d1a194-5a27-5760-881f-794354c24ed8 | textbox | Enter: Teambinder Approval number
dea01140-3491-5948-b3eb-43c228331d3a | note | – – – – – – – – – – – – – – – – –
7cd3ae41-d2f4-5226-9b94-ee510e2194af | note | METHOD: Document Review
5b99f6fb-1823-55b2-8e81-8a5691e7901e | note | – – – – – – – – – – – – – – – – –
e406b754-0a24-5f62-9152-ae80b8bc1f5a | note | FREQUENCY: Each Lot
9631d4ce-cd14-5b84-bb9c-9507cc9077e6 | note | – – – – – – – – – – – – – – – – –
de02eece-e83d-5413-821c-5f2e6e8032c3 | note | CATEGORY: HP
56a56adf-7799-50f2-995f-ed61dc7021ba | note | – – – – – – – – – – – – – – – – –
5e8b9fa6-99b3-551e-9a8d-bb9ee2ea03c3 | note | RESPONSIBILITY: PE/Nominated authority
a5125678-d24c-5ab5-920b-3c06ba405471 | note | – – – – – – – – – – – – – – – – –
b78575ea-0f4c-58c5-82a0-785de0ba78d2 | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
ce2d91d0-9a4e-5b24-b002-774a258dc9de | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 RAP Management Plan
56418b58-c85d-52c6-b785-f34fc68df656 | note | REFERENCE: VR 407.13 (f)
643bed1d-adc3-50f5-b225-41aaed62422c | note | – – – – – – – – – – – – – – – – –
bb1d2f49-565d-5aae-bca2-31acf026d245 | note | ACCEPTANCE CRITERIA: No asphalt containing RAP shall be supplied until the Department of Transport approved RAP Management Plan has been submitted at least 14 days prior to the asphalt works commencing and approval to proceed is given by the Superintendent.
7ea794b8-293d-56e0-9a1d-c32024803548 | textbox | Enter: Teambinder Approval number
eb7e1ef2-9211-52ea-8cc9-dbef504592d6 | note | – – – – – – – – – – – – – – – – –
e7d14fd1-7991-5175-8b5a-df5cdb0653ca | note | METHOD: Document Review
81827c98-262f-55ce-b413-5b05a4cb61d2 | note | – – – – – – – – – – – – – – – – –
77e17331-bd40-546e-a7e9-46dfd85e3ef5 | note | FREQUENCY: Each Lot
e8372f95-0d2c-501c-b60e-881e516bb1e4 | note | – – – – – – – – – – – – – – – – –
e1ba5894-e87a-5735-bf05-144785768bd6 | note | CATEGORY: HP
2880b794-6e60-5c30-bb6a-5954d45a919a | note | – – – – – – – – – – – – – – – – –
89a79a58-bd3d-562f-939a-a8637dcd7c4b | note | RESPONSIBILITY: PE/Nominated authority
2d9b9ea1-5a35-5c12-b5f3-7a906de1aa68 | note | – – – – – – – – – – – – – – – – –
64cba6f8-fbd4-50e6-87f9-d953af3e2f5c | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
b4864b63-44a3-5605-b39a-0adfd3e0131d | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Cold weather placement
eb4d908a-4de3-5d9e-9021-436f67c39b88 | note | REFERENCE: VR 407.17 (b)
1a10e329-61b0-5c4b-85c1-c812db18a723 | note | – – – – – – – – – – – – – – – – –
275d97fe-4c5c-5bbc-8c6a-12722df69482 | note | ACCEPTANCE CRITERIA: Where approved by the Superintendent placement of dense graded asphalt in layers 35 mm or greater may take place at pavement temperatures up to 5ºC below the minimum temperatures specified in Table 407.171.
3ab1e170-0170-5da1-8513-55b53f687bd8 | note | ○ Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
b9139079-f679-56ec-a69f-acae89cb7279 | textbox | Enter: Teambinder Approval number
bd559f22-c004-53b0-b049-b3a6b6b44e42 | note | – – – – – – – – – – – – – – – – –
95225699-533b-5b32-ac68-ce9fd06e08d5 | note | METHOD: Document Review
7baafca7-86ec-5a54-931a-799a9f50ca91 | note | – – – – – – – – – – – – – – – – –
b9f49b3b-c76f-5b83-8cb2-c6bc9f8fe9a3 | note | FREQUENCY: Each Lot
36f0dc34-76a0-566b-98ef-45c094654f36 | note | – – – – – – – – – – – – – – – – –
50994449-89e4-5a77-80ed-5f4c055c921b | note | CATEGORY: HP
34ded333-c5cf-5da2-aabc-6ee5d7848042 | note | – – – – – – – – – – – – – – – – –
9b21e233-dfc9-5671-a34b-8fa715a0bb9d | note | RESPONSIBILITY: PE/Nominated authority
c29569d4-03e9-5672-81ba-3d4af2a2cb5e | note | – – – – – – – – – – – – – – – – –
553447e7-b0f9-58ef-838b-a3f1e368a8de | note | VERIFYING DOCUMENTS: This ITP, TeamBinder Approval
f1e18499-52a5-59e9-976f-67b554812efb | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 IFC Drawings
7acde98e-db51-52c1-a9dc-1ab2f9971d65 | note | REFERENCE: MRPA Quality Management Plan
1ae612e9-8ca0-5405-ba1c-24e9fc7f4496 | note | – – – – – – – – – – – – – – – – –
47708421-dafa-55c3-b1f2-1cb847204952 | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
f3e7579a-4eb5-5ac8-af86-f952118bc326 | note | – – – – – – – – – – – – – – – – –
11fa8990-40ca-544f-bdd0-a5624923743a | note | METHOD: Document Review
12e42ec6-0a75-5cad-aed3-e7d96ef4f809 | note | – – – – – – – – – – – – – – – – –
266e748c-666d-5017-a84e-6201303062c5 | note | FREQUENCY: Prior to starting Works and at regular intervals
c72bde3c-0ddf-53c1-beab-ffffc1225ad8 | note | – – – – – – – – – – – – – – – – –
a5b009cc-b4c5-5806-8139-01c5b632c92e | note | CATEGORY: HP*
075ba898-6864-5fb4-9c5e-8a09ede6901a | note | – – – – – – – – – – – – – – – – –
1f441fbe-bf0c-569d-8884-864a2ece7bd3 | note | RESPONSIBILITY: PE/SE
163ccfc4-4115-5eff-b440-ff24d26d9602 | note | – – – – – – – – – – – – – – – – –
5f1eacb7-2092-51a0-9ce5-3c59905cfcec | note | VERIFYING DOCUMENTS: This ITP
518bf858-c569-5c19-901e-a5289f4c8f23 | date | Date Completed:
| checkpoint | 4.2 Lot Map-and Lot size
950532d9-7d45-5bb2-85cf-092db43615e3 | note | REFERENCE: VR 407.21 (a), VR 407.27 (b) (i)
89be17ed-4bf2-53a3-83a3-0819503a5981 | note | – – – – – – – – – – – – – – – – –
c0a0d889-2e17-532b-b09e-8efbd3b72efb | note | ACCEPTANCE CRITERIA: A lot presented for testing shall consist of an asphalt layer which is placed in one shift under uniform conditions and is essentially homogeneous in respect to placement methods, materials and appearance.
a2351bf3-cf69-5842-88fb-8c47b3b996c8 | note | ○ The location of all joints shall be planned prior commencement to achieve the specified offsets between layers and the position of joints in the wearing course.
92b900b1-4720-5152-a78e-d2454161c3b7 | note | ATTACH: Lot Map with planned location of Joints
e3f9d81b-c3ba-5929-894d-c30af7b7ba5e | note | – – – – – – – – – – – – – – – – –
ee1d7a4c-15c0-57e9-8d74-fe4346954151 | note | METHOD: Document review
38d6c506-6a82-5058-a49b-baa81086230c | note | – – – – – – – – – – – – – – – – –
4dd4b984-fab2-54d2-aba4-737e81fe302e | note | FREQUENCY: Each Lot
f71663b3-8f6b-5cf5-b0fa-3c8928a26765 | note | – – – – – – – – – – – – – – – – –
e1241a24-7858-5a4c-bad9-9d4e6003250d | note | CATEGORY: HP*
14ee7fad-095f-5b5a-af26-d75368283190 | note | – – – – – – – – – – – – – – – – –
a66738b7-7546-5945-aac8-3afe7405ffb8 | note | RESPONSIBILITY: PE/SE
9c69f175-1f8a-5350-9f34-602c2cfa3834 | note | – – – – – – – – – – – – – – – – –
0f95a2f3-621a-5088-be47-35f1b43c5655 | note | VERIFYING DOCUMENTS: attached Lot Map
f4913e8b-604f-5d6a-a258-2a5128dfca4a | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Ambient Conditions-Surface conditions
c76d6cec-ff24-5085-af92-1719b5e0e7e9 | note | REFERENCE: VR 407.17 (a), VR 407.18
b18e2787-bd29-5cbc-b36d-0b348232dc59 | note | – – – – – – – – – – – – – – – – –
5a8168eb-2933-5814-b8d1-23f836f49219 | note | ACCEPTANCE CRITERIA: The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent.
62d1eab0-9089-5ff2-b9a2-a38b4722551d | note | ○ The Contractor shall remove all loose and deleterious material and sweep clean the area upon which asphalt is to be placed.
baa0a31f-a309-5392-9506-832eeb41114b | note | – – – – – – – – – – – – – – – – –
e7a8d085-4ccc-598a-87b3-9ea513c6714c | note | METHOD: Visual
f590f875-e791-540f-9b87-9406272bbb5f | note | – – – – – – – – – – – – – – – – –
2007fcfd-5a45-563d-807b-dac7e92a8a66 | note | FREQUENCY: Each Lot
d7bbf2ec-1790-5957-871c-4ffa2c9a8133 | note | – – – – – – – – – – – – – – – – –
b86969ea-9a2c-5de8-9b6a-4beddc05721e | note | CATEGORY: IP
6b673e8a-ab34-51b7-bd56-960706ad61f6 | note | – – – – – – – – – – – – – – – – –
179af4b1-00e2-5207-8c31-b43b85edf07e | note | RESPONSIBILITY: PE/SE
da1b6631-4957-5068-a7b7-0bdbbd4fa731 | note | – – – – – – – – – – – – – – – – –
6fb0f538-deb3-5f2a-81b2-4d26d53fba09 | note | VERIFYING DOCUMENTS: This ITP
3d8c8ba3-7ba2-5f6c-8db1-60260e82f374 | date | Date Completed:
| checkpoint | 5.2 Ambient Conditions-Surface Temperature
fdd2f5d1-a2f6-5065-b241-31e52ee507ad | note | REFERENCE: VR 407.17 (a)
27f878d6-c466-56ff-b667-b5c2dd870d7d | note | – – – – – – – – – – – – – – – – –
8ccc9597-4a98-592e-a4ee-c3f08f16e200 | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed when the majority of the area to be paved has a surface temperature less than that detailed in Table 407.171 and as below:
e8097eba-ecba-546b-b2be-949cda2163a4 | note | – Specified binder class of C170 or C320:
72dd1413-b31e-55ba-a975-c9b7d137972f | note | ○ Wearing course: 10°C
6bfd6a88-3c07-5c1b-b71f-42413391d590 | note | ○ Other courses: 5°C
d854339b-7537-5ad1-a6eb-6b2e893e4e6f | note | – Specified binder class of C600 or containing a PMB:
b01b0eba-5067-59ed-bed2-efb033bc2515 | note | ○ Wearing Course 15°C
3692ee19-876e-5b2e-8c3c-22acd83e3610 | note | ○ Other courses 10°C
9d7de5a8-4800-589a-bce6-6b85b64cb10a | note | – – – – – – – – – – – – – – – – –
82e83f36-a6d8-5e4d-803d-600bec377f67 | note | METHOD: Measure
6e46e4ef-e7e5-5560-b94d-294a6061a45d | note | – – – – – – – – – – – – – – – – –
1c42d614-e333-57eb-9997-9577a1c9c98b | note | FREQUENCY: Each Lot
8d8ee915-2bfc-542e-ab67-26ab823e93da | note | – – – – – – – – – – – – – – – – –
7002cbe2-efac-5ff7-9102-17e3d28a1088 | note | CATEGORY: IP
6e6f253f-0ef0-573a-a66b-e0d4cf4160b1 | note | – – – – – – – – – – – – – – – – –
bc99cfdf-2b5c-5863-b87d-f826adfd700e | note | RESPONSIBILITY: PE/SE
f6be84a9-a274-590d-8571-aff02d0475ae | note | – – – – – – – – – – – – – – – – –
97a7bf82-e18c-597d-83f9-f57bd2ccfb2a | note | VERIFYING DOCUMENTS: This ITP
8012997f-7868-5ca4-adc0-35dfc88ae71e | date | Date Completed:
| checkpoint | 5.3 Joints and Junctions-Layer by Layer-Transverse Joints
dfa0d220-4b47-59ba-975f-02d5b63297f8 | note | REFERENCE: VR 407.21 (b)
183ea01a-e817-5ef4-8560-46e7244ee6bd | note | – – – – – – – – – – – – – – – – –
80b913a1-d734-5be9-b388-c17e80ea3903 | note | ACCEPTANCE CRITERIA: Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
0105396f-898a-5e79-a50e-b509e941303a | note | – All transverse joints shall be offset from layer to layer by not less than 2 m.
d1108c9d-fdd1-55d8-90a7-6b894a794487 | note | – – – – – – – – – – – – – – – – –
70edbaff-19f9-5e2f-802c-cbdcfd72fb47 | note | METHOD: Visual Measure
a810bed1-491a-59aa-9a1e-8f90b15dc103 | note | – – – – – – – – – – – – – – – – –
5c4e0df7-21cb-5dde-94fb-fee80f4def63 | note | FREQUENCY: Each Lot
65c16432-861f-59b3-bef9-ce63cdd4330d | note | – – – – – – – – – – – – – – – – –
1ccc627d-cb65-5d4c-b20b-a5398ca9fc4f | note | CATEGORY: IP
a18ae20c-21de-5b15-83fd-a10c32bc21c1 | note | – – – – – – – – – – – – – – – – –
e210b838-ee10-504e-9256-59c4c34e264a | note | RESPONSIBILITY: PE/SE
acb24c27-85d3-50c3-9a83-a3881b654c84 | note | – – – – – – – – – – – – – – – – –
9273b358-0e92-5866-b57e-7a07a48cec09 | note | VERIFYING DOCUMENTS: This ITP
f9eca0fe-8c1d-5f23-b377-6d71a200c9c2 | date | Date Completed:
| checkpoint | 5.4 Joints and Junctions-Layer by Layer-Longitudinal Joints
30f57080-2166-56b0-8eac-2ab9f9acedab | note | REFERENCE: VR 407.21 (c )
c7a145ce-1b07-57ba-9c2c-f2b79740def4 | note | – – – – – – – – – – – – – – – – –
25c1f5c5-95c5-5e70-b305-f052e174e52c | note | ACCEPTANCE CRITERIA: Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
9b67a593-370d-5cac-a9fa-681a96a0030d | note | – Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
bb8e5449-092c-5174-9dcc-452a6f552607 | note | – Longitudinal joints shall be parallel to the traffic lanes.
085ef60b-f536-5bbe-906d-5d07daf85c93 | note | – Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
8324aebd-d943-5cd0-bba9-71f8a2bb6223 | note | – – – – – – – – – – – – – – – – –
02d6961c-5b70-59ce-8ad7-1204d1298cec | note | METHOD: Visual Measure
6bd4176e-df14-5924-87bb-289e82ff259f | note | – – – – – – – – – – – – – – – – –
eb333087-88f8-536c-897f-ecf1e5735400 | note | FREQUENCY: Each Lot
a8569118-f406-5d25-968f-86c1ec595acf | note | – – – – – – – – – – – – – – – – –
32cac5ae-4164-5078-8d06-d73187a5798c | note | CATEGORY: IP
1d685d7b-5258-575f-b112-29b312866a79 | note | – – – – – – – – – – – – – – – – –
f777d58e-422c-5920-8937-d1678d7c9131 | note | RESPONSIBILITY: PE/SE
6802e11e-ce7d-5818-9bfb-6075b8733aa1 | note | – – – – – – – – – – – – – – – – –
05df1811-c915-54b7-88d5-9465182a4988 | note | VERIFYING DOCUMENTS: This ITP
f22810ef-5d52-5431-8ab5-41866ea6a026 | date | Date Completed:
| checkpoint | 5.5 Joints and Junctions-Abutting existing pavement
b1a9fa49-a17b-5188-9a65-4a3d0aa7c847 | note | REFERENCE: VR 407.21 (c)
0d33d88f-9ed9-5130-88fb-91bbd55824b4 | note | – – – – – – – – – – – – – – – – –
6df74434-ec09-54e7-aade-672104f2c197 | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
97d1a17f-d144-524e-a467-af68c9b0d8c6 | note | – At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied.
25edcfb4-cd14-572e-89d1-980407dccb67 | note | – – – – – – – – – – – – – – – – –
4e82d951-9e5c-53ba-b682-340cfc1d7e5e | note | METHOD: Visual Measure
6f441771-fafe-5cab-ab5e-d589234bc5b2 | note | – – – – – – – – – – – – – – – – –
944ae2c0-7df7-540d-9201-6ccffdfaf6ab | note | FREQUENCY: Where applicable
0df1abf4-b7af-5d38-b66d-5b1b510f248c | note | – – – – – – – – – – – – – – – – –
1ded6393-e884-53da-b87f-4d9275d99755 | note | CATEGORY: IP
740c0c23-497f-5673-9a37-a761ab7a427c | note | – – – – – – – – – – – – – – – – –
3d0679e6-1875-5cd9-9144-49bb3be99b0e | note | RESPONSIBILITY: PE/SE
44b359a5-ac75-5bd5-befb-b999cad25ae7 | note | – – – – – – – – – – – – – – – – –
6aae4f4e-19ef-5c73-a355-43d84e50b164 | note | VERIFYING DOCUMENTS: This ITP
435413f4-fa24-5ab7-a5ba-2f862ede0bb3 | date | Date Completed:
| checkpoint | 5.6 Joints and Junctions-Junctions at limits of works
92d667e9-6e99-5683-ac39-7a02cf7f874c | note | REFERENCE: VR 407.21 (d) VR 402
a4983ae8-8503-5ace-a7ea-367a781ac709 | note | – – – – – – – – – – – – – – – – –
e02b1c09-7131-5408-9b4d-998b022aad03 | note | ACCEPTANCE CRITERIA: At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
3a473b27-4ca3-57bf-b852-0ab1a40332d5 | note | The chase shall be cut by removal of a wedge of asphalt tapering from zero to a depth of 2.5 times the nominal size of the asphalt from the existing pavement to the minimum length as follows:
2f26761c-a94b-5b69-939c-bfeb23d9fcba | note | (i) at side streets and median openings – 600 mm
ad8532da-fefc-527a-8c9a-9d8ec69a31e6 | note | (ii) on through carriageways with a speed limit of 80 km/h or less – 3 m
1aeb76ce-6cef-5ea1-8c82-bacf3a0a5c18 | note | (iii) on through carriageways with a speed limit of more than 80 km/h – 6 m.
d25460c5-10c2-5425-a7ff-1d3b05869e10 | note | – – – – – – – – – – – – – – – – –
6f190ff2-a9fb-53c5-9434-17058c228c5a | note | METHOD: Visual Measure
62d929ea-7a66-5ec5-9ed3-946ad9c0bcb8 | note | – – – – – – – – – – – – – – – – –
0eeb2196-f649-59c0-80f5-b2d3eb2d3b6e | note | FREQUENCY: Where applicable
3ff373b9-2081-5246-83cf-ccf315ae93e7 | note | – – – – – – – – – – – – – – – – –
30ad62ef-e25f-59a3-9734-ff6837888a27 | note | CATEGORY: IP
964015f8-24fe-5fb3-ba4e-f2a72d43a232 | note | – – – – – – – – – – – – – – – – –
90882e12-c0d3-582b-871a-84a5dd387709 | note | RESPONSIBILITY: PE/SE
3f006ff3-8eff-5eec-b89a-82b6a90e67a2 | note | – – – – – – – – – – – – – – – – –
6f0675a8-4b0d-5166-8222-c1545c0b5387 | note | VERIFYING DOCUMENTS: This ITP
87a6debb-0232-5349-9c76-878e6a58cbd9 | date | Date Completed:
| checkpoint | 5.7 Application of Tack Coat
fccfb4af-996c-5d99-8286-2e6f0ff4bfb7 | note | REFERENCE: VR 407.19
a989cbdc-a25b-552d-b84f-537cf6eddbb9 | note | – – – – – – – – – – – – – – – – –
559bed17-0b4f-5e00-8d1d-98a49015b437 | note | ACCEPTANCE CRITERIA: A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed.
7c0e6acd-96bb-5e85-8032-e15fa9f2076e | note | The application rate for the tack coat shall be 0.15 to 0.30 L/m2 of residual bitumen for joints and chases rates shall be doubled.
217c4f2d-16b4-5b02-a4cd-25ff4a722d63 | note | The Contractor may omit the tack coat where asphalt is to be spread over
a6c1bfd9-e892-5477-83f5-4db8908d2840 | note | – A clean, un-trafficked, freshly laid asphalt, or
1b3a64a5-61d2-5ec7-8a51-47fa8b97df2b | note | – A clean primed surface, or
5078096c-0dd7-52f3-ba70-6faa31a5aae1 | note | – Granular material where the overall asphalt depth is 150mm or greater.
90380a52-ee82-5c15-b1a4-753a610ed7a4 | note | PHOTOGRAPHIC EVIDENCEshall be supplied to show that tack has been applied.
a42d1eb8-400f-58cc-b900-9269a1eefa30 | note | ATTACH: Photographic Evidence
81d78496-4349-5a25-b9d6-c088e299b27a | note | – – – – – – – – – – – – – – – – –
40c66908-fc56-518f-a153-8d201c28a045 | note | METHOD: Visual
2f64bba1-3c50-5c69-89eb-7a596e47f862 | note | – – – – – – – – – – – – – – – – –
7b71454c-f212-56a8-a4e1-b7aa66b35223 | note | FREQUENCY: Where applicable
ad4ae6b7-fb60-59ce-9bc5-d985d5c6a58c | note | – – – – – – – – – – – – – – – – –
1f3f5cf5-2d23-5397-8353-c3081b619301 | note | CATEGORY: SP
c8b1e6cc-256f-5672-9e85-3391ba5bbbec | note | – – – – – – – – – – – – – – – – –
1fa2cff3-939c-59da-8b1c-6ffdab5d7e13 | note | RESPONSIBILITY: PE/SE
58fc4272-915e-576c-b5df-21fb8884f804 | note | – – – – – – – – – – – – – – – – –
ad59bc87-c02d-5201-9e73-8b405d1e0d14 | note | VERIFYING DOCUMENTS: This ITP
b60ec27d-8a13-513e-94a6-22220406dd75 | date | Date Completed:
| checkpoint | 5.8 Joints and Junctions
fd65b00f-fad4-598e-8fed-0c7ea508d47a | note | REFERENCE: VR 407.21 (a)
fdee2718-38b5-5820-b63a-cb18de463f65 | note | – – – – – – – – – – – – – – – – –
e9091c30-7e56-5ba9-948d-f2a354798d99 | note | ACCEPTANCE CRITERIA: All joints shall be well bonded and sealed
63c1530c-3cae-5f23-9335-70996828129d | note | – All cold joints and abutting concrete edges shall be tack coated
9590d250-b6ef-5972-8e4f-1c64287d94f5 | note | – – – – – – – – – – – – – – – – –
0b58c3a1-c4e4-5c14-98d9-ca2bc7486b2a | note | METHOD: Visual
d501bdf3-bcd0-5eaa-80c3-85173e996a83 | note | – – – – – – – – – – – – – – – – –
1d98920c-b9c5-5654-9299-d35327a24d40 | note | FREQUENCY: Where applicable
c5d49af9-9ed4-5a92-8500-0bc59b539eb9 | note | – – – – – – – – – – – – – – – – –
7536a19b-4df5-5bee-8ba6-b62324dfb748 | note | CATEGORY: SP
289f708e-bf1d-5cfc-afa3-40fe99b1e087 | note | – – – – – – – – – – – – – – – – –
d63b2f3c-b630-5def-a77a-3770ade476c3 | note | RESPONSIBILITY: PE/SE
68616d17-e0c3-56ee-9b79-dc900bbfc144 | note | – – – – – – – – – – – – – – – – –
3b9091aa-ef4b-5624-94ec-caf9249467a3 | note | VERIFYING DOCUMENTS: This ITP
29297888-1752-5093-a3da-608b12250e9a | date | Date Completed:
| checkpoint | 5.9 Delivery Dockets
e5874b82-5aaa-596b-ae0e-6e97e8ac08f4 | note | REFERENCE: VR 407.20
8eb0ec58-b2f4-5328-b0f2-0a7d2f5901da | note | – – – – – – – – – – – – – – – – –
9201f8e7-c8b3-5d33-8916-4fb2515177a1 | note | ACCEPTANCE CRITERIA: Asphalt delivered to the site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site.
338e8dc4-dc43-59ff-9842-fcf56ec04dab | note | ○ Maximum Asphalt temperature at discharge from the plant is 175°C
dfb301d9-54f9-53f0-908d-7a6a55af65fa | note | ATTACH: Mix Delivery Docket
e17799a1-f3fa-5925-ac49-f3958fa90f42 | note | – – – – – – – – – – – – – – – – –
a355fa94-323b-5f73-b570-fd2c3100e997 | note | METHOD: Document review
295b66f4-be52-5a56-b16c-b9c06ed27fab | note | – – – – – – – – – – – – – – – – –
315a54d3-9461-574d-88a3-b5ac1500ed00 | note | FREQUENCY: Each Lot
f498333c-9ba4-508e-af92-5827d4c4508a | note | – – – – – – – – – – – – – – – – –
0f234bcc-8e16-5cf6-ad1d-29991b2f4af4 | note | CATEGORY: IP
1dc7b340-2c23-5ac3-bc6b-57a8dd4ddfa0 | note | – – – – – – – – – – – – – – – – –
5a460210-dc55-5689-86b6-f1d8f89cb53a | note | RESPONSIBILITY: PE/SE
83d675d2-7247-5af7-a6f4-3cbb02c40706 | note | – – – – – – – – – – – – – – – – –
1493d9c2-dadb-5321-96ae-453963ea5078 | note | VERIFYING DOCUMENTS: This ITP
ca123bbe-8ce2-5087-92f6-84d4ecd3cb17 | date | Date Completed:
| checkpoint | 5.10 Commencement of Placement
0cbb6bb6-adee-568d-a206-30cd94735956 | note | REFERENCE: VR 407.23
07ca2d9a-da73-5d7c-bedc-0e041c7d0864 | note | – – – – – – – – – – – – – – – – –
130a58c4-916e-54a1-b4f8-6afea591cfff | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent.
c1294e06-7306-50d8-b775-97e040990960 | note | – – – – – – – – – – – – – – – – –
988d2206-0b8a-5292-b3c3-80bb57f9e208 | note | METHOD: Visual
01f14ae0-0194-50cc-8e77-3552cf87dfef | note | – – – – – – – – – – – – – – – – –
e5185e8b-1b7a-5b33-9e6a-b9ae4dc1aaac | note | FREQUENCY: Each Lot
18afff0e-fc8d-5d79-a8ff-57a426f522ad | note | – – – – – – – – – – – – – – – – –
755404b2-b6ac-5880-a135-0b8c53a2d89a | note | CATEGORY: HP
eee84bb1-0c70-5362-a9d9-d0702f44a596 | note | – – – – – – – – – – – – – – – – –
08cfab37-0ba9-54b5-83fe-18bc111ee086 | note | RESPONSIBILITY: SE/Nominated authority
075ba49a-1cf9-5cad-b708-a9bf6d64acb8 | note | – – – – – – – – – – – – – – – – –
c4db0d37-fbf2-5b26-b785-d92c3555b44e | note | VERIFYING DOCUMENTS: This ITP
b4741c3b-7635-5230-a5c0-7db765bdbd02 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.11 Paving of Asphalt
dbb05382-e62a-5393-a5f2-e009091ebfc3 | note | REFERENCE: VR 407.25
dfebb45a-1ef5-54bc-9a35-0e83acd964ce | note | – – – – – – – – – – – – – – – – –
79469d79-8b42-53f7-a6f8-006dde9af96b | note | ACCEPTANCE CRITERIA: Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings.
609af035-f0f4-509b-9e05-a19983529e53 | note | ○ All asphalt shall be spread with paving machine (or by hand if not accessible by Paver) to form a smooth asphalt mat without segregation, tearing or gouging.
55a3b74d-0192-56a8-b220-90259144c43e | note | – – – – – – – – – – – – – – – – –
f68df99a-ba7c-5d7b-8a83-02e2062691fa | note | METHOD: Visual
89462cd1-a933-5643-b431-a2f25bc4a1f5 | note | – – – – – – – – – – – – – – – – –
fbba681b-9aea-5a4f-a075-455749808563 | note | FREQUENCY: Each Lot
7d41f924-5ffa-5e78-8c85-f33f03846c29 | note | – – – – – – – – – – – – – – – – –
60d0b5af-3283-5aa6-90e5-0500ce35931c | note | CATEGORY: SP
5c6339e9-953a-538f-8283-a2b65640a382 | note | – – – – – – – – – – – – – – – – –
0a73cc20-335f-5ea4-a3d3-100d28c04e29 | note | RESPONSIBILITY: SE/PE
b525ffd1-8189-5a55-89c1-1bbbd194722e | note | – – – – – – – – – – – – – – – – –
a16212c4-ea54-5d1e-bfeb-6ff7ca3c9cd7 | note | VERIFYING DOCUMENTS: This ITP
02f4542e-2e7e-5e08-9c5b-26a5737f8ff7 | date | Date Completed:
| checkpoint | 5.12 Paving of Asphalt
466396db-6813-57e3-be96-b86523984614 | note | REFERENCE: VR 407.25
7a62335a-1fe6-5c7d-ab94-f567194d07e1 | note | – – – – – – – – – – – – – – – – –
7c2213d1-6f52-50d5-9455-6d34d0a64025 | note | ACCEPTANCE CRITERIA: If the paver is required to stop and asphalt in front of the screed cools to below 120°C, a transverse joint shall be constructed.
341a407f-88bb-5d87-9b28-98854160765b | note | – – – – – – – – – – – – – – – – –
a7a0655e-e7be-5ae0-ba8f-7bb98cb28765 | note | METHOD: Measure
6612c72e-6b9a-5b86-a445-2e2a461f67b9 | note | – – – – – – – – – – – – – – – – –
53d49ec1-42ce-5ae8-8f58-53cd67763fb1 | note | FREQUENCY: Where applicable
661b6bdd-dd94-5eb6-93be-19b5e4d7ee66 | note | – – – – – – – – – – – – – – – – –
d9fa58d1-bd3c-53d3-86e6-df191c16ecb2 | note | CATEGORY: IP
43dcc8f9-bf36-554c-90e5-dce87d8f6888 | note | – – – – – – – – – – – – – – – – –
1e0cd73c-c1b1-5a66-bb08-3e822976100c | note | RESPONSIBILITY: SE
df52a6f6-3b06-5a01-9036-156eb2c3f218 | note | – – – – – – – – – – – – – – – – –
a47b537a-c88c-5a1d-8167-f7453ff6653b | note | VERIFYING DOCUMENTS: This ITP
77062c5a-5fd2-5946-8d10-06c138fab152 | date | Date Completed:
| checkpoint | 5.13 Compaction
b0a7a75c-b161-5fd9-8c62-dbc661802ff7 | note | REFERENCE: VR 407.26
b969772a-8464-56fd-b5ac-e5ff5f6999bf | note | – – – – – – – – – – – – – – – – –
80243149-d8c2-53d2-9126-15c849fa3bcc | note | ACCEPTANCE CRITERIA: Asphalt shall be uniformly . Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
e8feebc4-fd8b-521c-9bff-c72c398723ce | note | ○ Vibratory rolling shall not be used to compact asphalt on bridge decks.
98e50845-bce4-5013-8544-34b014cd95e2 | note | – – – – – – – – – – – – – – – – –
65609171-bb2d-5671-9297-62ac9e8d37e5 | note | METHOD: Visual
9244d442-6e85-5e6c-972b-95bd692baffe | note | – – – – – – – – – – – – – – – – –
8c9150a9-afb9-543e-ba92-4ba69eda3c6e | note | FREQUENCY: Each Lot
50c040cf-69ed-5adf-963d-1325477d025b | note | – – – – – – – – – – – – – – – – –
7c04a6e0-09c1-535b-b232-3dbd8b96ac31 | note | CATEGORY: SP
a00456ad-21e4-5cf4-8d51-a21559a607ec | note | – – – – – – – – – – – – – – – – –
2b8477fd-f5da-5fd8-8d9e-8eb174435f98 | note | RESPONSIBILITY: SE
c5ad8c5f-f630-5ba5-aec5-44e7ad688f9b | note | – – – – – – – – – – – – – – – – –
ae5bf1c2-228e-5f17-8adc-68b65fcda574 | note | VERIFYING DOCUMENTS: This ITP
bab8bf87-2cb0-5a47-b179-be361740ec8a | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 Compaction test-Lots larger than 500 sqm
6f813c49-db05-5c1d-9648-43c2ca97cfb9 | note | REFERENCE: VR 407.27 (b) (i)
b03268ba-1d20-5e1d-9c91-217bc865cd34 | note | – – – – – – – – – – – – – – – – –
33562f9f-9b0f-5f95-8f3b-111f52d7f6bc | note | ACCEPTANCE CRITERIA: The work (excluding longitudinal edge strips) represented by a lot of six tests shall be assessed as shown in Table 407.271.
5f51d2a2-e4de-5d87-90b3-7284f656718f | note | ○ For lots exceeding 500 m2 density testing of the longitudinal edge strips (200 mm from the longitudinal joint) for the wearing course shall be undertaken and results reported as a separate lot.
d8434e77-6f5c-5d95-88f7-8ce2897326fe | note | ○ The Characteristic Value of the Density Ratio determined for the longitudinal edge strips within the lot shall be submitted for report only
9627baec-0299-53b1-8b0c-a443663241fa | note | ATTACH: Compaction test report
d386923a-253c-52bf-a825-381ac1845a36 | note | ATTACH: Wearing course joint strip compaction test results
76bf6bd0-9389-528e-b47e-ffe5d5c3644b | note | – – – – – – – – – – – – – – – – –
25d91773-1313-53ff-9604-61fc9e59b230 | note | METHOD: Document Review
1a7a1d14-b5f7-5120-9f21-41cee53b54a9 | note | – – – – – – – – – – – – – – – – –
0c09c8bb-fb5f-5dbe-9590-5242e197d10e | note | FREQUENCY: Each Lot Where Applicable
4127ae94-63c7-5e96-a037-2ed8ca438858 | note | – – – – – – – – – – – – – – – – –
d46a49b3-dbe9-5cbc-8cdf-6b6b690f4a6c | note | CATEGORY: HP
5311c2e8-fff4-5e05-8c67-22efc498e079 | note | – – – – – – – – – – – – – – – – –
4d020c22-8046-51f7-a045-2200e754b15f | note | RESPONSIBILITY: Nominated authority
905e0962-96b3-5eb3-a487-fa37461195e8 | note | – – – – – – – – – – – – – – – – –
12affb95-e105-50e0-9c84-d9607b1633cd | note | VERIFYING DOCUMENTS: This ITP
91ac4cfa-cdbd-5e3a-a2ac-91f4e7d400cd | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 6.2 Compaction test frequency-Lots smaller than 500 sqm
06470bff-c7fd-5f3d-b1b6-139001b07773 | note | REFERENCE: VR 407.27 (b) (ii), VR 173.04 (d)
07009b77-9129-57f4-88dd-8add34cb69b1 | note | – – – – – – – – – – – – – – – – –
a22576d1-693e-5a86-862d-7a402003565a | note | ACCEPTANCE CRITERIA: acceptance of the lot shall be based on the mean values of 3 individual tests. The lot will be accepted if the mean value of the individual tests exceeds by 2.0% or more the appropriate compaction scale requirement for the characteristic value of density ratio for a lot of six tests.
153577bb-a7db-513d-8fe3-10dfe88f1c48 | note | ATTACH: Compaction test results
cf35486e-0a0f-5814-a287-0738bef58e61 | note | – – – – – – – – – – – – – – – – –
52a0653b-ad2d-590a-8ddb-6c94fff39013 | note | METHOD: Document Review
f57dfe75-f57a-5128-98b5-c3c50578a190 | note | – – – – – – – – – – – – – – – – –
973e5389-1e63-59d1-9a8f-153afaebc512 | note | FREQUENCY: Each Lot Where Applicable
b348c6e1-4013-5fa0-a921-97b537d975b5 | note | – – – – – – – – – – – – – – – – –
bfb31804-69f6-5be4-8080-0833879fbd02 | note | CATEGORY: HP
2c2d4a67-3feb-5aa6-9b7d-99584d4a9ab0 | note | – – – – – – – – – – – – – – – – –
c5d98eff-8a43-55ed-93f2-ff467e1502f7 | note | RESPONSIBILITY: Nominated authority
ad12d534-3673-5a23-8b54-5f40897607d1 | note | – – – – – – – – – – – – – – – – –
d928a42f-d5bd-5ca5-b10a-250d1c070f7f | note | VERIFYING DOCUMENTS: This ITP
059033c7-85d1-5322-bc5f-cb7132d78d7b | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 6.3 Surface finish and conformity with drawings-Surface Finish and shape
3984ceed-8d78-5542-aa96-ab6fb2be437e | note | REFERENCE: VR 407.29 (a) (i), VR 407.29 (a) (ii), VR 407.29 (a) (iii)
784941fe-0ba2-5a59-9fb2-4a9c3e9902b8 | note | – – – – – – – – – – – – – – – – –
dba28a92-13be-5c27-82b8-0afce1fec009 | note | ACCEPTANCE CRITERIA: The finished surface of any asphalt course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks.
892889bf-b3c0-5997-b9e4-9b630d65ee32 | note | ○ No point on the finished surface of the wearing course: shall lie more than 4 mm below a 3 m straight edge
09ae1fa6-a932-50f4-8192-1c5f06b39f0a | note | ○ For intermediate and base course layers: the distance below the straight edge shall not exceed 6 mm and 10 mm respectively.
c9bb5df8-7058-589c-89c8-de85793b910e | note | ○ Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel
d59810d0-7a76-55a0-81a6-ac2161df1f95 | note | – – – – – – – – – – – – – – – – –
bbdd40b8-b36c-5c83-b9be-80eb7c2d30ca | note | METHOD: Measure
9bb84f08-a366-5387-ae93-d184bdbbcb1f | note | – – – – – – – – – – – – – – – – –
b57fbba1-cbd8-5e55-8d79-bcfb7ca57671 | note | FREQUENCY: Each Lot Where Applicable
fce50d96-8c6a-5c59-b1ef-a9d4856f558f | note | – – – – – – – – – – – – – – – – –
38cd3c92-04dd-524a-bc60-d91bf5ee48bf | note | CATEGORY: IP
f69424c2-55e8-560f-87a5-ae996664ebb8 | note | – – – – – – – – – – – – – – – – –
f3ed35a2-9110-5a3a-803f-2faa8f523bc7 | note | RESPONSIBILITY: SE/PE
4a8da2f5-4621-5d7f-bb82-a165593dced7 | note | – – – – – – – – – – – – – – – – –
1a7981c7-67eb-531a-8cd6-3fae51ca5f41 | note | VERIFYING DOCUMENTS: This ITP
39e084f3-df53-54c7-854f-62546d9509f7 | date | Date Completed:
| checkpoint | 6.4 Surface finish and conformity with drawings-Alignment and width
84bfd0d9-5beb-5166-b79c-aae6c169b114 | note | REFERENCE: VR 407.29 (a) (iv), VR 407.29 (a) (v)
a7be89a5-1b42-5f72-a4ea-c02fc087a3b0 | note | – – – – – – – – – – – – – – – – –
d8d2a7f0-9192-5dc8-8c15-940104a36070 | note | ACCEPTANCE CRITERIA: Where asphalt pavement is not placed against a concrete edging:
2e088f21-442d-51a3-9b07-c26fde334e29 | note | ○ the edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside,from design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m.
9ba5e597-5c83-5ff0-bfc9-2429bc608d98 | note | ○ the width of asphalt layers shall not be less than the design more than 50 mm or greater than the design by more than 100 mm. The average width over any 300 m shall not be less than the design.
69b21af5-aed7-5b6c-97e7-467bbf981cea | note | – – – – – – – – – – – – – – – – –
65087b1f-ddad-5e59-b328-ddadbba3224d | note | METHOD: Measure
5d351e52-0a31-5267-90aa-94d8e7b0f981 | note | – – – – – – – – – – – – – – – – –
04774719-9cba-51c3-8c00-3a609fc10a96 | note | FREQUENCY: Each Lot Where Applicable
e4ff00d6-b8d2-5a0f-a093-afb25de1e07c | note | – – – – – – – – – – – – – – – – –
a1fa7b03-0784-5617-a94a-9bb916712251 | note | CATEGORY: IP
42c053eb-a814-5d11-9b3b-b96f57dc8588 | note | – – – – – – – – – – – – – – – – –
6b14c8fd-8f05-5e51-8836-b211d3128356 | note | RESPONSIBILITY: Surveyor/SE/PE
a709247f-d0e1-505e-b057-62466b6ae63d | note | – – – – – – – – – – – – – – – – –
5fabed27-f765-50b4-87c2-2ac9ec1f299f | note | VERIFYING DOCUMENTS: This ITP
acb6a0f0-a6ab-5865-9d3c-c26e30259381 | date | Date Completed:
| checkpoint | 6.5 Conformity with drawings-Scale A and Scale B
65f47442-a972-5898-ab0e-7d1c14fe04e5 | note | REFERENCE: VR 407.29 (b) (i), VR 407.292, VR 407.293, VR 173.05
ddbc65a4-7701-5bd6-a310-9dbc32e729d9 | note | – – – – – – – – – – – – – – – – –
321c7f0b-9a3a-5c17-8318-644709afa9b7 | note | ACCEPTANCE CRITERIA: the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.05
842169f1-362f-5ba8-9268-947f254e925b | note | ○ Number of measurements and acceptable tolerances are to be as per tables VR 407.292 and VR 407.293
ddfff70e-f472-5306-b4f7-cb8c4f371186 | note | – – – – – – – – – – – – – – – – –
c9d5aa2d-cd98-5aaa-8694-3023ba8009f1 | note | METHOD: Measure
fb96a74d-48e4-5236-9d44-3af8afb93a5a | note | – – – – – – – – – – – – – – – – –
63b2aeab-c2ad-54db-a456-4ed350ef9a79 | note | FREQUENCY: Each Lot Where Applicable
1ab0947b-0152-5487-b1d5-c432daa5d1ba | note | – – – – – – – – – – – – – – – – –
94ddd3eb-981b-5760-b763-210a6dd5d0ad | note | CATEGORY: IP
68a22621-8479-5544-b77e-f8e66794275b | note | – – – – – – – – – – – – – – – – –
34856c0c-18b6-5bd2-8ac6-ca64f2ee05f3 | note | RESPONSIBILITY: Surveyor/SE/PE
429cfffd-1b86-5f9e-a6bb-56b98a2c1da8 | note | – – – – – – – – – – – – – – – – –
771f5e4c-b42d-511f-9c14-c710221ee5d9 | note | VERIFYING DOCUMENTS: This ITP
0b8ebf94-fe54-541a-880c-95822323a3d9 | date | Date Completed:
| checkpoint | 6.6 Conformity with drawings-Scale C
e413365d-4f6c-599c-ae16-2204bd13407d | note | REFERENCE: VR 407.29 (b) (ii), VR 173.06 (c), VR 173.06 (d)
9dead0e8-f97b-5d99-a007-0367a4860eda | note | – – – – – – – – – – – – – – – – –
51f1b9f6-ca74-5418-83f9-8506596c5c9e | note | ACCEPTANCE CRITERIA: the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.06
1f347b48-7122-537a-9143-41e12148c30b | note | ○ The level of the top of each asphalt course shall not differ from the specified level by more than 15 mm for intermediate and base courses and 10 mm for wearing course.
cbd4b5ee-6c07-5af3-a786-dc7e7b4d3ecd | note | ○ For the purpose of this clause, the maximum lot size shall not be more than 4,000 m2 of pavement area.
1575755b-fb5f-56ae-9b3d-c6e6ae4e6687 | note | – – – – – – – – – – – – – – – – –
18a5f75f-6638-5041-857d-8c4072ba1d92 | note | METHOD: Measure
2ea5b410-7ce0-5b25-b10f-b90cf75f1c6b | note | – – – – – – – – – – – – – – – – –
0296dbc3-1759-5fd1-8fbe-1b420be378dd | note | FREQUENCY: Each Lot Where Applicable
52da61fa-cbb0-5211-a1ea-24b112975c13 | note | – – – – – – – – – – – – – – – – –
05250c98-1b04-53b7-8a60-c87cd60861de | note | CATEGORY: IP
8f31c65c-149e-5cca-b3f4-ba513da9daab | note | – – – – – – – – – – – – – – – – –
e99b2d37-c5a3-54e6-8c87-332cf5433647 | note | RESPONSIBILITY: Surveyor/SE/PE
87d6372a-5823-5beb-95b5-2f032133b090 | note | – – – – – – – – – – – – – – – – –
daf7358f-381c-574e-b6a7-87477b7b33e4 | note | VERIFYING DOCUMENTS: This ITP
3f6f5af4-0aae-508b-9b41-4bdde7845431 | date | Date Completed:
| checkpoint | Final Inspection
36b1fa06-5842-52f7-b2f8-f3f9cf43c51b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
21ae3396-b38a-5d59-8219-c241dc3d0174 | textbox | Name:
ccaf0677-7b5d-55c0-a309-fb0e69a1733d | textbox | Position:
2efab7e9-9558-5129-92eb-d8fa89ee2312 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-064-CIV-Camms-Subsoil Drainage Rev 0 | itp | ITP-064-CIV-Camms-Subsoil Drainage |  | 328594a1-b038-4632-841d-abcb4423fa37
| section | Referenced Documentation
| checkpoint | Referenced Documentation
223b0d2c-3ad1-56b8-80ec-58bb7ad19633 | note | Document Title: ITP-064-CIV-Camms-Subsoil Drainage
30270e79-b3d3-5fa1-9137-5ecf3bfc75bd | note | ITP Description: Camms-Subsoil Drainage
6360cc78-4d34-59db-b37d-8f4bcfed3fe2 | note | ITP number: 064
0617ff07-8f9a-5a90-844a-a8e69c7d0acb | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
697068eb-20fc-5c24-8cbf-77ff499c3014 | note | Discipline (e.g. CIV/STR/RAIL): CIV
437327fe-7dad-5a00-9b7d-7fc2524cde01 | note | Revision Number: 0
17308af7-7dd5-5664-b16f-4d6c910c3a6f | note | Revision Date: 25/08/2023
f85bc733-f5c6-5b58-872c-6e91ec6046a4 | note | ITP created by: Victor Mira
9111f9c4-4586-5e75-b95c-6d6770173e82 | note | ITP approved for use by: Victor Mira
49779406-2028-5ad9-9b4a-afa5bd748972 | note | 1.1 Non Dependent
ae0ba8ff-c579-5296-9cb1-72c1c9f25140 | note | Reference: VicRoads Section 702 (May '19)
| section | Preliminaries-Material
| checkpoint | 2.1 Pipes
ad320cd1-d513-5770-baf2-1d5692761d82 | note | REFERENCE: IFC Drawings VR 702.04
7888bd4e-e524-5f18-b2aa-e002ad6298a2 | note | – – – – – – – – – – – – – – – – –
b2e1e87b-67b3-510c-aba8-1ad86478de7a | note | ACCEPTANCE CRITERIA: All subsurface drainage shall be Category 1, 100mm DIA Class 1000 Perforated Plastic Pipe. Perforations shall be max 1.5mm and minimum length of 150mm per sqm
e74f9856-fe8d-54aa-997d-6618c7e1bd2d | textbox | Reference: Material approval in Teambinder:
69dedc43-6a8c-560d-a486-0086769d178a | note | – – – – – – – – – – – – – – – – –
3a505534-3950-57bc-8423-c11efd6af2bd | note | METHOD: Verify, Document Review
29384606-94e0-52e4-bb83-2a0d82be92ae | note | – – – – – – – – – – – – – – – – –
e9cbfeb1-f69f-5fc5-847d-bac3f4bce198 | note | FREQUENCY: When applicable
711c5ad3-d104-5803-9466-fae3980991d1 | note | – – – – – – – – – – – – – – – – –
211bd6c6-3f4e-51ab-9c81-b9ad224d9d11 | note | CATEGORY: HP
8df55bae-1372-567d-b7e2-336cdb907da0 | note | – – – – – – – – – – – – – – – – –
c56baebe-e9d8-52c5-a1cb-e7f5b47227b9 | note | RESPONSIBILITY: PE/Nominated Authority
210ff46d-fab4-5878-b5e6-6d9a644d8f5b | note | – – – – – – – – – – – – – – – – –
0445998d-32b6-5dc3-b39e-ad1b07397700 | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
97b0c6be-fce0-5181-8d56-da57d139e228 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Granular material: Filter Sand
392a48c5-453f-52e2-a206-0cbda7d32509 | note | REFERENCE: IFC Drawings VR 702.05
d671c00e-0e67-5951-a044-46666a8b242a | note | – – – – – – – – – – – – – – – – –
845bd644-d556-58cf-affb-84051d8308a9 | note | ACCEPTANCE CRITERIA: Filter sand to be Grade A4 and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
418322fe-ee6f-569e-8374-eb8d5a59a6f2 | textbox | Reference: Material approval in Teambinder:
4993dbaa-31ef-5985-84f2-67ef4e782d57 | note | – – – – – – – – – – – – – – – – –
d292d8f9-63fc-5cee-9157-b0243cee16a9 | note | METHOD: Verify, Document Review
7bc58052-bc09-5074-b91d-35239ff0d606 | note | – – – – – – – – – – – – – – – – –
d3374012-141c-5986-b6ec-0189225139a7 | note | FREQUENCY: When applicable
f4c44e8a-ad8c-5a8b-9d66-0298ae97e17b | note | – – – – – – – – – – – – – – – – –
7c3fff35-12d4-5ea0-882d-e461bb3ceecf | note | CATEGORY: HP
6f3f33cd-86e3-57ba-a085-2783b130c844 | note | – – – – – – – – – – – – – – – – –
875d8957-e9b5-5395-9e8b-50d18d687a6f | note | RESPONSIBILITY: PE/Nominated Authority
9c9a9703-27ff-506f-a892-7cf12dcab1a5 | note | – – – – – – – – – – – – – – – – –
5adf73e8-8cd4-591f-bec7-d925be689ec5 | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
7ce70ac0-27c8-5b0f-81e3-501ca9caef44 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Granular Material: No Fines Concrete
6aacd5f3-cb35-5d9e-9394-3746fef96829 | note | REFERENCE: IFC Drawings VR 702.05 (e)
a21ee16a-ebc1-5af0-b3f9-5192d22fc0de | note | – – – – – – – – – – – – – – – – –
a8804812-0d2e-53bd-8aff-d9df10522c75 | note | ACCEPTANCE CRITERIA: No Fines Concrete: Shall comply with 702.05 e)
eb1c8c7d-2fb6-5c05-bf72-043a530a30b2 | textbox | Reference: Material approval in Teambinder:
54b8aaa7-ff18-51e6-912d-f1ab7255b292 | note | – – – – – – – – – – – – – – – – –
c1b8771f-4111-5a6a-a3cb-968a51bb37b5 | note | METHOD: Verify, Document Review
b07d1228-19d8-5610-bf62-1d5076c6ea24 | note | – – – – – – – – – – – – – – – – –
4cc1d15c-6ec6-5ef9-924d-f9b6f8c09f14 | note | FREQUENCY: When applicable
10217def-f238-5874-ac6e-f0ecda99dbba | note | – – – – – – – – – – – – – – – – –
c7643d10-6b37-543d-940a-a6e011927c15 | note | CATEGORY: HP
778a2521-88e2-5111-b370-1874d6f1fc97 | note | – – – – – – – – – – – – – – – – –
dd24add1-d439-59cb-a74f-1f08617f9508 | note | RESPONSIBILITY: PE/Nominated Authority
8a8dae74-bb6d-5623-b706-b9e15ac232bb | note | – – – – – – – – – – – – – – – – –
0c42065f-dbde-5afa-9964-e7180171f909 | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
0504269c-fcf7-5608-b075-e64ea6fb90a8 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Geo textile
81778578-aa6c-58ce-9fb6-656220350163 | note | REFERENCE: IFC Drawings VR 702.06
3fe6ea64-d722-570d-b169-50845b8c92ba | note | – – – – – – – – – – – – – – – – –
321385ae-d98d-5867-9b91-d07521c5b949 | note | ACCEPTANCE CRITERIA: Geotextiles: Shall comply with table 702.061
3a2898e4-f608-5921-b2d2-fbde1acec35f | textbox | Reference: Material approval in Teambinder:
36d11dfb-13b0-52b3-96d0-c63d760dffdd | note | – – – – – – – – – – – – – – – – –
cd917559-d63c-58da-af75-9f8e296cf5d5 | note | METHOD: Verify, Document Review
ae1937ef-cb80-5552-860d-7f1b8b3f4f4e | note | – – – – – – – – – – – – – – – – –
c2740d06-0f55-5c37-99f1-0884ede507a5 | note | FREQUENCY: When applicable
d24dbe77-1263-5da2-82ac-1aebc7969538 | note | – – – – – – – – – – – – – – – – –
87d3e67d-4cb3-524e-92c1-72bba099bb96 | note | CATEGORY: HP
a775694e-b20a-5b0d-b2f2-917c59012904 | note | – – – – – – – – – – – – – – – – –
59682769-8944-5c75-9296-179237625c19 | note | RESPONSIBILITY: PE/Nominated Authority
8bde81c3-abb2-5dcf-93c9-c9cde23ae97a | note | – – – – – – – – – – – – – – – – –
a03b1452-3167-5279-8152-dcc423eea80f | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
67ce31e4-1a38-507b-9b91-bde456e2585c | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.5 Subsurface Drain Pits
7166ec74-842a-52c0-8c9e-60414b75784b | note | REFERENCE: IFC Drawings Section 702.04, 702.05 & 702.06
b8cc41f4-2546-54b4-a721-f2e74fb2e680 | note | – – – – – – – – – – – – – – – – –
48f47bcb-5d10-5e9f-bc6b-037e896c121d | note | ACCEPTANCE CRITERIA: Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
61dac00d-25e2-535a-b2fb-bfc8bd7ea1bf | note | Pit Lids:
81a9cebb-de18-58e4-9eec-e941ae8a2f5a | note | ○ Type M3 circular lid (as per SD 1051) for Type S1 pit
a37f48c0-e8e2-5c36-acd5-58c363a40468 | note | Flushout risers:
03354c30-8189-5a95-ac65-44bbf1bbbc29 | note | ○ As per SD 1631
ed03f129-a18d-5fc0-9227-4205581618b9 | textbox | Reference: Material approval in Teambinder:
fddb66f1-20ec-5d56-b882-159f66e379ed | note | – – – – – – – – – – – – – – – – –
b1dbf31b-119d-5c70-b0bf-cceeff3b1687 | note | METHOD: Verify, Document Review
70cb9710-32d7-501c-b3f2-9d5ffabf6773 | note | – – – – – – – – – – – – – – – – –
bb405c9d-2d9a-533d-8512-99ef0c46642d | note | FREQUENCY: When applicable
648780d4-7ebd-5c2e-b87b-8e04896dc93a | note | – – – – – – – – – – – – – – – – –
5a3debd1-da4a-58d4-9a86-77b04e3bfc3f | note | CATEGORY: HP
685308de-3efb-5ac8-a304-cf5fcca5be7e | note | – – – – – – – – – – – – – – – – –
e46f8b0b-56cd-54dc-8e52-7139f0f2d744 | note | RESPONSIBILITY: PE/Nominated Authority
f48488b7-4bf6-5ea2-a036-57462b762266 | note | – – – – – – – – – – – – – – – – –
6c4ed988-6060-5ec5-9006-29a8c8df788e | note | VERIFYING DOCUMENTS: Material approval in TeamBinder, This ITP signed off by Nominated Authority
b51a6027-a6d1-583b-b8a4-850b7ea42e5c | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction / Pre-installation Activities
| checkpoint | 3.1 Survey Set Out
d1b1cf07-5142-5c50-b589-2408fd53c900 | note | REFERENCE: Section 702.03
f44f36c1-f320-5faa-8983-75ad1685264a | note | – – – – – – – – – – – – – – – – –
f883e6e7-1fe8-5075-9c3a-c711e35f456b | note | ACCEPTANCE CRITERIA: Survey to set out Subsurface Drainage line.
20561308-5d86-56bf-aeeb-0081c8d4b164 | note | – – – – – – – – – – – – – – – – –
11fb2c58-10a5-579b-8423-d2b68c306aea | note | METHOD: Visual inspection
cb703ecd-abf4-5ef4-8976-cd89e4ef2373 | note | – – – – – – – – – – – – – – – – –
b2ac7d41-6f5d-5d2d-a58d-431ab2bb0fed | note | FREQUENCY: Each Lot
514e65cf-c49a-5211-a9cd-df5ccd4dc7b5 | note | – – – – – – – – – – – – – – – – –
82701a79-bb10-5d63-8875-d401f5bc6121 | note | CATEGORY: HP*
8b2df9ba-60ef-590b-9a13-675ab9ca41d8 | note | – – – – – – – – – – – – – – – – –
15772541-a9f0-5d60-abba-ecbc497f231b | note | RESPONSIBILITY: SE/Site Supervisor
527bab38-b4fa-54fb-81ef-80add5ce2683 | note | – – – – – – – – – – – – – – – – –
93d6e0ff-7dd0-56d6-a355-ed34864b7842 | note | VERIFYING DOCUMENTS: This ITP
c7f15d8e-93a1-58ca-b207-e46ab550a9f6 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 4.1 Trench Excavation
661fe79b-16e7-5855-bf71-ed761b39edd4 | note | REFERENCE: IFC Drawings Section 702.08
11a8261d-b74e-59f6-b5ae-532101d92d83 | note | – – – – – – – – – – – – – – – – –
67c42339-00cb-5a4c-bd3c-45fc63c843ff | note | ACCEPTANCE CRITERIA: The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
5e8c7609-1033-50d7-bc0a-086b6289e61e | note | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
86c9f432-9bf6-59de-87b1-d45d9c6d8b0b | note | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
cd4a7fef-7ad9-582d-bd0d-9e6cfcd4d342 | note | ○ Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile.
d681045b-d1ea-5597-8e60-629dc51bdff0 | note | – – – – – – – – – – – – – – – – –
17094f5f-d90a-57cf-904c-58ae93d913c1 | note | METHOD: Visual Inspection
324a6958-9bbd-5dcb-a414-194ae7bb80f6 | note | – – – – – – – – – – – – – – – – –
46498051-723d-5876-9b3d-291b24f79c59 | note | FREQUENCY: Each lot
f4ad3f2c-bd58-54da-97ea-e22958a49308 | note | – – – – – – – – – – – – – – – – –
54c487ba-0cc9-586e-b883-9e28779e178b | note | CATEGORY: IP
ae335c79-afb6-5302-a970-7fc93d15b6d9 | note | – – – – – – – – – – – – – – – – –
c30f26ee-7d67-5160-8572-31e105142253 | note | RESPONSIBILITY: SE
a649b776-45a0-5d51-82d1-6beb46204955 | note | – – – – – – – – – – – – – – – – –
7350bad7-51da-5ab4-b28e-9dff8b45ac42 | note | VERIFYING DOCUMENTS: This ITP
29b8e8ba-b9f2-5248-82f0-0d622823bc34 | date | Date Completed:
| checkpoint | 4.2 Trench Excavation
ebb7dc59-9356-5318-9cc2-7433d7b61021 | note | REFERENCE: Section 702.08
90ead8bb-4464-5433-b927-b96bc032882f | note | – – – – – – – – – – – – – – – – –
94252925-0b78-54d3-a88b-14ae542ead41 | note | ACCEPTANCE CRITERIA: The base of the trench shall be inspected to verify compliance with the requirements in VR 702.08 prior to placing bedding in completed excavations. The Superintendent shall be notified at least 24 hours prior to the inspection.
e1d4c714-d07d-58b2-b3a6-40491685a9f6 | note | – – – – – – – – – – – – – – – – –
d0de1a42-45a3-5ee2-a109-761f033c74ab | note | METHOD: Visual Inspection
3470fb73-1c29-5eb2-ac48-badf7c662f20 | note | – – – – – – – – – – – – – – – – –
c8c76721-d00b-57af-87cd-284a0b88b909 | note | FREQUENCY: Each lot
451d11d0-beaf-576b-9d4b-4a1b86629cd9 | note | – – – – – – – – – – – – – – – – –
92540288-1ceb-54bf-a9de-9e3402372714 | note | CATEGORY: HP
84e44b67-17b5-516d-8747-bbe7d4201b05 | note | – – – – – – – – – – – – – – – – –
ae75bb50-18f9-5952-8e32-3dfebe50f722 | note | RESPONSIBILITY: SE/Nominated Authority
fff89529-b6c7-58a3-af96-324148b1b121 | note | – – – – – – – – – – – – – – – – –
9a213ecf-92cc-56d7-841c-7f6dc9d51be5 | note | VERIFYING DOCUMENTS: Nominated Authority sign off This Line
9d110091-7947-5949-8432-a318b90b21c3 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.3 Placement of bedding
6352ef75-873f-5913-8497-823d0d2e0a14 | note | REFERENCE: Section 702.09 c)
f2141dbd-a2cc-500d-81db-02ff8c8d2496 | note | – – – – – – – – – – – – – – – – –
4275028d-5876-550b-95cf-c9418b6772b7 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
7ef4c7b9-cfab-5408-b070-f24b9c901329 | note | – – – – – – – – – – – – – – – – –
535514df-bd81-5752-9c58-9dae8862722d | note | METHOD: Visual inspection
b0880e88-bcf2-548b-9cf4-1779d0a51bf2 | note | – – – – – – – – – – – – – – – – –
2163b7c0-16f2-5026-b77e-28d77486bebf | note | FREQUENCY: Each lot
44aaa6bf-55df-565f-8633-99c19e737be9 | note | – – – – – – – – – – – – – – – – –
cfa4987c-b334-5bbd-a603-bb44901c36e5 | note | CATEGORY: IP
910c0b86-db75-5ca5-a46d-9ec1a1a7abc7 | note | – – – – – – – – – – – – – – – – –
7c31dfb0-3dd9-5346-8f4f-df6f0d4477b3 | note | RESPONSIBILITY: SE/Site Supervisor
efa7d249-c6dc-5347-b357-222c0b771f31 | note | – – – – – – – – – – – – – – – – –
7adcd9de-2990-5b65-b65a-b5bd174d21c6 | note | VERIFYING DOCUMENTS: This ITP
3e4fd575-d9e9-517d-a996-ee24412ae4f4 | date | Date Completed:
| checkpoint | 4.4 Traficable Pavements
83f79c6b-895f-5f7d-87f8-733597ea8980 | note | REFERENCE: IFC Drawings SD 1601 EDCM 201
592ec90a-ead9-519e-aae0-748e7cc3b373 | note | – – – – – – – – – – – – – – – – –
1beb45e8-8c35-5242-98f4-2ff0d4915883 | note | ACCEPTANCE CRITERIA: Choose pass when applicable. All Subsurface drains located within trafficed pavement shall be Type 2 with no fines concrete filter with filter fabric wrapped around the trench in accordance with SD 1601 and EDCM 201
8d80a685-9c7f-514c-9e51-c0e0f0ef599b | note | – – – – – – – – – – – – – – – – –
7bad1aca-7629-563b-a2cb-7810f9285333 | note | METHOD: Visual inspection
ac4d1809-780b-55b4-9b8f-6f18bf8dad3f | note | – – – – – – – – – – – – – – – – –
7b915726-e0f8-5ab3-93ba-16773a4719e2 | note | FREQUENCY: Each lot
142e4ebf-012b-5c00-8f2b-8ff07c426c54 | note | – – – – – – – – – – – – – – – – –
3029b127-23dd-5a95-82ad-273c0a48d166 | note | CATEGORY: IP
cb09e6c3-ca04-56f6-a0e3-bafd58aa8b20 | note | – – – – – – – – – – – – – – – – –
1e5e72be-ec78-5309-b092-22cc78e415fd | note | RESPONSIBILITY: SE/Site Supervisor
864072a7-3b4e-5511-8bc9-380565994add | note | – – – – – – – – – – – – – – – – –
1bf402fc-5ca6-54b4-8531-b9215df55373 | note | VERIFYING DOCUMENTS: This ITP
807ba1e5-fd1d-5761-9bf0-e36ea29360b8 | date | Date Completed:
| checkpoint | 4.5 Outside trafficable pavement
02309151-6e19-5fe8-929d-4e461be58099 | note | REFERENCE: IFC Drawings SD 1601 EDCM 201
1de0aa46-781b-56f0-9071-7a452926dc93 | note | – – – – – – – – – – – – – – – – –
225889c8-3e7e-5370-bc4e-b0be3144b0f7 | note | ACCEPTANCE CRITERIA: Choose pass when applicable pavement drains outside trafficable pavement shall be type 3 with grade A4 Sandfilter and Geotextile wrapped around the pipe with minimum 150mm lapping length
e349a62d-922f-5bf3-863d-ee570df53eaa | note | – – – – – – – – – – – – – – – – –
5db7c435-422e-5c7d-972e-49d6d2431568 | note | METHOD: Visual inspection
caa6096a-3a32-5973-9611-9cd762e37ed0 | note | – – – – – – – – – – – – – – – – –
c377d37c-0926-51c4-91fa-b2b8209e134e | note | FREQUENCY: Each lot
a19e93cf-0666-58cb-aa11-1670f53e38fb | note | – – – – – – – – – – – – – – – – –
f79651bd-af77-50ee-8632-459a2c6cf953 | note | CATEGORY: IP
0d1988a7-7fc8-57e5-9b46-dfe7c03d0311 | note | – – – – – – – – – – – – – – – – –
61b9990e-9a74-5d75-9606-d3473c81d2bc | note | RESPONSIBILITY: SE/Site Supervisor
19c18cc8-c938-5435-8432-b3453851a6b3 | note | – – – – – – – – – – – – – – – – –
f5509942-6160-5f9a-9a72-cc22fae19087 | note | VERIFYING DOCUMENTS: This ITP
1a26727d-aed3-5d78-80bd-071d1276ad94 | date | Date Completed:
| checkpoint | 4.6 Pipe and Geotextile Installation (if required)
7be27a2a-34e9-53f0-a7a8-3c7ce33314bf | note | REFERENCE: Section 702.03, 702.09
8ce6cc77-ad41-5c1f-81e9-50cb4029f5b3 | note | – – – – – – – – – – – – – – – – –
368ef659-8ba2-5231-a250-5330e9afa726 | note | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped (Mininmum 150mm lap)
9e6492b8-9a01-5266-86f2-7d04d8829209 | note | – – – – – – – – – – – – – – – – –
4c673f60-d54b-5f3a-85ac-564022ac5948 | note | METHOD: Visual inspection
7a66df37-82ac-5d62-babf-9724bc9ec498 | note | – – – – – – – – – – – – – – – – –
42b54d67-9b58-5330-857d-3e97bc752a9e | note | FREQUENCY: Each lot
5f0af623-0bb4-54ed-95d3-fdeba88f9a92 | note | – – – – – – – – – – – – – – – – –
8ba322f0-5558-5b90-9916-dbc9d8b67e93 | note | CATEGORY: IP
f374df57-3a23-531f-9bb5-c151c0bd9a75 | note | – – – – – – – – – – – – – – – – –
5be86664-cee7-52b8-acfd-108216016127 | note | RESPONSIBILITY: SE/Site Supervisor
f00f5db1-e16f-5550-b0dc-d7ce8f7d5e9f | note | – – – – – – – – – – – – – – – – –
9741c474-168e-57af-baf2-9f0410438e9a | note | VERIFYING DOCUMENTS: This ITP
73d9d33f-6fd9-56e1-8b89-162deb0cb68d | date | Date Completed:
| checkpoint | 4.7 Backfill Installation (Granular Filter Material)
0aef6f47-19c3-563d-a2e3-0da1fb6f8b7c | note | REFERENCE: Section 702.09 (g)
da015142-4f9d-5d09-9569-a7b3e2755705 | note | – – – – – – – – – – – – – – – – –
74885978-42e7-514a-80ff-d26e12dc56e3 | note | ACCEPTANCE CRITERIA: Material shall be placed moist and compacted in layers not exceeding 300mm. The method of compaction shall be in accordance with the procedures and reviewed by the NA.
32a1d23d-67a1-5e43-ae17-7ea9b0cd1359 | note | – – – – – – – – – – – – – – – – –
c216fd60-4314-59a7-988b-b9fb92c27dc7 | note | METHOD: Visual, Doc. Review
2b3e18c9-56a3-541f-894e-b72d1394f981 | note | – – – – – – – – – – – – – – – – –
01d5e196-0257-5b67-939d-3d5289208e83 | note | FREQUENCY: Each lot
54acd19d-df41-5ff2-b72b-1fbece9c8186 | note | – – – – – – – – – – – – – – – – –
2f3e00e4-590c-579c-a381-daf1e82984be | note | CATEGORY: HP
5400ad1b-387a-5d8d-bef2-e00b093f6943 | note | – – – – – – – – – – – – – – – – –
a367d568-54b4-54c2-b57c-60c944e82332 | note | RESPONSIBILITY: SE, Nominated Authority
49499501-404c-5eb0-b30e-9fc57d16b5bc | note | – – – – – – – – – – – – – – – – –
b74d31f7-4fea-5c8f-aafe-f3afd3397081 | note | VERIFYING DOCUMENTS: Nominated Authority sign off This Line
e1195d99-06e6-5a23-bdc5-b909e7843889 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.6 Backfill Installation (No Fines)
e88650b9-76af-5b70-a1b7-a1ffc1f90998 | note | REFERENCE: Section 702.09 (g)
01993c7f-3cd0-5b61-8d13-27577f4367d4 | note | – – – – – – – – – – – – – – – – –
94cb30c5-3a4b-5fab-80d1-55deda9263bc | note | ACCEPTANCE CRITERIA: All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
327aa2b9-6df1-57eb-bfec-39f56490b50d | note | ATTACH: No Fines Delivery Dockets
3b22ed43-6274-5a82-a0a5-79a07539d44b | note | – – – – – – – – – – – – – – – – –
1e5b7e4d-cf7d-5e74-b003-66e2480d3c94 | note | METHOD: Visual
b570a203-c5af-5a52-b8c9-8b93562c2cd7 | note | – – – – – – – – – – – – – – – – –
e1b341d8-4e1d-58e3-bcec-0fffae354405 | note | FREQUENCY: Each lot
e125e6c7-6905-5899-b9d0-4be2e46b27db | note | – – – – – – – – – – – – – – – – –
1820f737-090e-52d7-85c2-01361b3f965c | note | CATEGORY: HP
4b65adb5-4c10-555b-af37-5bbebf9e499c | note | – – – – – – – – – – – – – – – – –
cd6c7d48-ff96-5336-89d0-0028425ef7b4 | note | RESPONSIBILITY: SE, Nominated Authority
3524a130-48cc-58a2-a0bc-650fb701e5a3 | note | – – – – – – – – – – – – – – – – –
85d4684a-8e75-5839-b608-c6c604807c36 | note | VERIFYING DOCUMENTS: Nominated Authority sign off This Line
efed2f77-05eb-5f28-b365-02761f067055 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.7 Install Pits and Flushouts
a88e01d8-cff9-5c65-b377-d9ef8bee72a1 | note | REFERENCE: Section 702.10
b0bfa166-afe9-56ba-8c99-4c67280f64ed | note | – – – – – – – – – – – – – – – – –
19bf3af6-66fa-51a3-a5a3-789c9cdc8a69 | note | ACCEPTANCE CRITERIA: Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
930a7c73-1ce2-5d4d-973f-fec882dab224 | note | – – – – – – – – – – – – – – – – –
a4fbdf46-3a27-5b18-8bb7-b3f4eaf47402 | note | METHOD: Visual
ef0b20fc-068b-5fb3-8494-bd8eb68ae768 | note | – – – – – – – – – – – – – – – – –
563d07a0-a2b2-590d-9e72-721757dc8eb5 | note | FREQUENCY: Each lot
6b766156-0d85-51ab-aaae-f9d2b3a9fb39 | note | – – – – – – – – – – – – – – – – –
40969138-ab4d-5954-bb2e-13761a8d8078 | note | CATEGORY: WP
86c25fb3-c01f-5740-8130-5d3955cd1fd5 | note | – – – – – – – – – – – – – – – – –
bfc0ccc2-098e-5369-bfd9-e8643745015e | note | RESPONSIBILITY: SE/Site Supervisor
c142f26d-a54c-568c-8819-b852b569dbd2 | note | – – – – – – – – – – – – – – – – –
12b52656-9083-5f71-a56a-c5eb6a45c1dd | note | VERIFYING DOCUMENTS: This ITP
2fb61bd9-d32c-55d7-bc4d-3e990c1f2e68 | date | Date Completed:
| checkpoint | 4.8 Marker Points
d2423496-33f1-56d9-a5e4-02fd85bd27a9 | note | REFERENCE: Section 702.11
879bb2ff-5c09-54cd-b9cc-8b5eadc0bf0e | note | – – – – – – – – – – – – – – – – –
ff644092-90ae-5781-8990-0f0e1743ceb6 | note | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
1aa7c060-1ff1-5cd9-9dcd-040ca0ed2994 | note | – – – – – – – – – – – – – – – – –
390ed56d-dfc7-523b-8b54-ca653ed3778c | note | METHOD: Visual
1debdfad-5370-57c4-bb8a-f1b88266393c | note | – – – – – – – – – – – – – – – – –
0d4decbb-dfce-5b04-9a3e-0b7e07255f7f | note | FREQUENCY: Each outlet
bfe32616-8cf4-5ee2-aefd-33d54248c13a | note | – – – – – – – – – – – – – – – – –
9e6fb235-3827-57b2-b946-d09f8859c9a8 | note | CATEGORY: IP
03e89885-1f8b-5973-9101-74cda6f7e405 | note | – – – – – – – – – – – – – – – – –
2cafc7f2-fd4b-5b65-a241-2a56159934c6 | note | RESPONSIBILITY: SE/Site Supervisor
0f07cd4f-0a24-5605-bf19-8150b2450386 | note | – – – – – – – – – – – – – – – – –
4bb6e1a8-61ef-5c68-99a4-d12696eff1fe | note | VERIFYING DOCUMENTS: This ITP
fd4d50b0-d9c6-553b-abba-18ef49596c3d | date | Date Completed:
| checkpoint | 4.9 Flushing
d9df1078-f742-5f2d-ba05-955234d12b16 | note | REFERENCE: Section 702.09 (h)
b59eb089-7582-51bf-b371-c07f2a28b225 | note | – – – – – – – – – – – – – – – – –
73178e35-db89-596d-8c9d-f192a097e0cb | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
fb9fc945-8256-5d14-9dd8-02f69a15a4c2 | note | – – – – – – – – – – – – – – – – –
7a0c7f96-0f89-565d-9b51-7cec676d77af | note | METHOD: Record Review
a320c0b1-91e3-530f-b57c-a9f90fbacdbf | note | – – – – – – – – – – – – – – – – –
6355fb38-bf86-5b5e-80d2-eb76cfc5f9c7 | note | FREQUENCY: Each lot
7373be6d-1d26-5092-bb8f-828ac76e0d23 | note | – – – – – – – – – – – – – – – – –
6149a29a-81f7-5627-9427-578d865be348 | note | CATEGORY: HP
272a25b9-8708-5bc5-9933-b0a08c6ae1ff | note | – – – – – – – – – – – – – – – – –
798d86e9-bb54-526e-9b21-e0f74a0c0832 | note | RESPONSIBILITY: SE, Nominated Authority
2ccaf1bf-6301-5b64-8b69-cf1503358dc4 | note | – – – – – – – – – – – – – – – – –
74586954-43ea-57c8-a48a-961e64e56505 | note | VERIFYING DOCUMENTS: Nominated Authority sign off This Line
52b4c826-39c7-52de-83da-b942443b45e8 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 4.10 CCTV
a7547f65-32a2-517c-aef2-eb07d691f129 | note | REFERENCE: Section 702.09 (g)
135ab358-38a9-5daf-a92b-b972081d18b3 | note | – – – – – – – – – – – – – – – – –
e58dc51f-f63d-5548-a60a-3a9009dd1073 | note | ACCEPTANCE CRITERIA: Placement of asphalt shall not proceed until the CCTV inspection has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the NA.
ce167f57-f687-5759-ba31-46500d3eec34 | note | – – – – – – – – – – – – – – – – –
6541004b-bdb7-56f1-b9e3-dd6a07507d2e | note | METHOD: Record Review
f010c7ce-ec14-531c-a393-9aa63fe422ff | note | – – – – – – – – – – – – – – – – –
7705da50-5cf2-5759-adb5-681eefbfa1cd | note | FREQUENCY: Each lot
9905d565-e368-5007-b311-f52b582c015d | note | – – – – – – – – – – – – – – – – –
5b600943-db0a-5bf7-937e-bf4d0ea4101d | note | CATEGORY: HP
27a96fad-88cf-5ee8-87f2-0c98666131b0 | note | – – – – – – – – – – – – – – – – –
003bf701-632f-55bb-88fe-1b7834ae462d | note | RESPONSIBILITY: SE, Nominated Authority
db577e83-fc2f-5f45-aa42-2ce3093ba0d2 | note | – – – – – – – – – – – – – – – – –
c7cd57d7-4e1e-5fe6-a577-dea587513376 | note | VERIFYING DOCUMENTS: Nominated Authority sign off This Line
9741bc94-0d7a-58f7-a4ae-d538c96d8b2e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Post-construction / Post-installation Activities
| checkpoint | 5.1 As Built Information
faa8abdc-9a6d-5add-bc91-b63b48193e7c | note | REFERENCE: Section 702.03
65cacae3-26a0-568f-b12b-7f0ddd4221fa | note | – – – – – – – – – – – – – – – – –
dac71a8e-d255-5651-8c95-26427196281e | note | ACCEPTANCE CRITERIA: The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line.
997bdaf9-5b10-5ad6-b140-7daad74c9459 | note | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
6cdc0372-108c-5c3f-bfef-e3c3542acd3a | note | – – – – – – – – – – – – – – – – –
4b7d5497-3605-595e-adca-9b7af961ac70 | note | METHOD: Document Review
a0ba024e-425c-5adc-86f7-542e1fa84537 | note | – – – – – – – – – – – – – – – – –
18872195-5f51-53be-a3af-2aa9595f019e | note | FREQUENCY: Each lot
c138b29d-a61f-598c-9b67-04fd79083329 | note | – – – – – – – – – – – – – – – – –
11458d67-424e-5317-b4e7-b12e8e5cbbe7 | note | CATEGORY: IP
b122b5b7-52b5-5a53-b5d6-d189d052f56e | note | – – – – – – – – – – – – – – – – –
8c0604aa-5206-5623-b528-64c1787ab9bd | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
9ee80fad-f40a-5cd0-a5eb-ed53753e4cd4 | note | – – – – – – – – – – – – – – – – –
4dc84691-88e5-51e9-bb15-2cd7b9137816 | note | VERIFYING DOCUMENTS: Attach Survey Conformance Report
4f64e290-3f82-5f89-b82d-645555a26210 | date | Date Completed:
| checkpoint | Final Inspection
2bee27ed-6217-59e3-b899-5a4c7e3f135c | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
b7973fbc-7efe-5d88-962c-f3fafa68d41d | textbox | Name:
fdcd30b9-b999-50e7-87cd-ab3f41142427 | textbox | Position:
22d1f343-e8eb-5445-9eb7-629e222f43dd | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-065-CIV-Camms-Landscaping-Ground Preparation Rev 0 | itp | ITP-065-CIV-Camms-Landscaping-Ground Preparation |  | 14db3f03-577e-4a26-97c1-4ae9c678aa61
| section | Referenced Documentation
| checkpoint | Referenced Documentation
7433f4e3-0b4d-5b3b-a70c-9e8d8084d345 | note | Document Title: ITP-065-CIV-Camms-Landscaping-Ground Preparation
90c0e363-1230-501d-9d27-2ae70c3439e4 | note | ITP Description: Landscaping - Ground Preparation (Subcontractor)
3496ce38-0d8a-5d1f-8731-76a7c03cdb02 | note | Discipline (e.g. CIV/STR/RAIL): CIV
13739f07-3aaa-56ab-87c3-2c42f8a090d6 | note | Revision Number: 0
f54f0db0-2f0e-54cb-bc0e-658e8bf434ed | note | ITP created by: Victor Mira
09507be4-d119-5349-8095-2f3738ceed69 | note | ITP approved for use by: Victor Mira
63e4f0e1-2536-5bd7-b1a8-4f1bcd704b33 | note | Reference: VicRoads 720 AS 4454, AS 4419 IFC Drawings, Sub Contractor ITP
| section | Preliminaries
| checkpoint | 1.1 Check for correct documentation
919e087d-c5fc-5aa4-a027-9fcd2af48570 | note | REFERENCE: Drawings and drawing registers
5a449572-8c5e-5d14-aa24-10134f6411c6 | note | – – – – – – – – – – – – – – – – –
551f34ce-1f22-51fd-972e-b7ba3546e8aa | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
e2ceb06d-cc35-5f77-947a-167d6aec0439 | note | – Using the correct and complete set of IFC drawings
68b88564-a8b9-5ac7-b52e-3fcd32db1c94 | note | – All drawings are the latest revision
11fc00ce-9c0a-5e49-8a11-a7b68cdfae9c | note | – – – – – – – – – – – – – – – – –
d9cbbd2b-fbb5-52a4-b6f6-06d63e8ce87b | note | METHOD: Document Review
51b451b9-3cf4-5c87-99ff-02e69deccae8 | note | – – – – – – – – – – – – – – – – –
c6f3f4f0-c06a-5138-baf7-ec4e17f229aa | note | FREQUENCY: Prior to Commencement of works
6626ec93-d70a-52df-8ed6-153791592d25 | note | – – – – – – – – – – – – – – – – –
f166703c-cd2e-5ecd-87fa-65a3c2caf500 | note | CATEGORY: IP
6a96e676-d04f-5ed6-be2f-3fe96289dc3c | note | – – – – – – – – – – – – – – – – –
3bffcf8d-dc63-507e-9393-40b22a5b403e | note | RESPONSIBILITY: SE
5ba3c985-02ca-51d3-86f4-9c940b6b70e0 | note | – – – – – – – – – – – – – – – – –
4364747f-d595-55ae-aa45-00f08672a5f8 | note | VERIFYING DOCUMENTS: Sign ITP
89a20d00-be87-586f-a802-a9f5cb9335f7 | date | Date Completed:
| checkpoint | 1.2 Submission and records
b41d1581-39e0-5616-bef0-77aff52aab0b | note | REFERENCE: Section 720.03
f364fff2-22ad-5751-a8a9-4ddcc83aca59 | note | – – – – – – – – – – – – – – – – –
27b2b5ef-b458-507f-bc20-a0485d0bc5d4 | note | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Nominated Authority (NA) at least 10 working days prior to bulk delivery.
fb94a241-f4f3-54f6-8aee-5ffcb847264b | note | Following information shall be provided to the NA:
ae26b5e5-f840-55be-972b-82940200f237 | note | ○ Samples
005de9ab-4d68-58f6-b4e1-7284c2b345d2 | note | – Mulch
939a2553-40db-5a89-a083-d2717cac7521 | note | – Imported topsoil
d65c2882-8a92-5fa7-8409-5c3afbd3b189 | note | ○ Records
7bbf6d01-e495-5eb4-992b-719a16d2f285 | note | – Details of suppliers
4766ae81-53ea-55e9-82a1-286946ca43b4 | note | – Soil tests on imported topsoil
df092aa3-d216-5aa8-a7ce-a3380316a129 | note | – Copies/Photos of fertiliser labels
bea50b1c-86fc-53a0-bcbb-cc4b2a4f06a6 | note | – – – – – – – – – – – – – – – – –
bce642b6-6843-5e61-90aa-f98462a9f154 | note | METHOD: Document Review
1d4b11f9-8cb8-5cd3-9083-e0cdbc71464b | note | – – – – – – – – – – – – – – – – –
2080867e-3133-5fa2-aa01-24d5faf3bc10 | note | FREQUENCY: Prior to Commencement of works
159a205e-1891-5186-96b9-1fb20b656222 | note | – – – – – – – – – – – – – – – – –
2fc47c8f-3e81-5057-89ee-b5e654665a3a | note | CATEGORY: HP
a6068663-5962-5184-bd2b-79e13ffcb445 | note | – – – – – – – – – – – – – – – – –
7bd2a701-29a1-5476-84ab-aa4fe9781e1f | note | RESPONSIBILITY: SE, NA
e1bc9cef-c143-5246-bad4-822d18865f71 | note | – – – – – – – – – – – – – – – – –
ce18993e-6e00-5016-a11e-4a5ff03df3fb | note | VERIFYING DOCUMENTS: Issue to TeamBinder, Attach: Records & certificates
39929b8c-8836-5745-a25a-ab49a8302795 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 1.3 Supply of topsoil
5f8ab166-2f55-5f12-b1f2-55887cb8a783 | note | REFERENCE: Section 720.04 Table 720.042 IFC Drawings
2ab06e5a-6eaa-55b6-a97b-ec78d860d6cd | note | – – – – – – – – – – – – – – – – –
e5cbef91-0961-54b3-b06d-cb5e1e986de3 | note | ACCEPTANCE CRITERIA: Site won topsoil to be tested to establish what soil amendments and macro and micro nutreints are required to be added to the top soil if required by planting subcontractor.
444d16b6-29da-5552-9eeb-d303fd9179bb | note | ○ Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042 and align with IFC Drawings .
bffeca26-2050-57a1-930d-565ac4cf3f8d | note | – – – – – – – – – – – – – – – – –
54668cab-1c67-5348-b043-97555dec44fc | note | METHOD: Verify, Doc. Review if applicable
8c7718b1-cbb0-55e2-acea-b81d827c912a | note | – – – – – – – – – – – – – – – – –
d0ef15c1-5633-52a4-9843-59bdd943d2e3 | note | FREQUENCY: Prior to Commencement of works
8a277a1e-2537-5fcd-a57f-970498324306 | note | – – – – – – – – – – – – – – – – –
3c31c34e-db5c-5947-815a-0fb64740854e | note | CATEGORY: IP
53d651f5-6f4b-5719-a6a1-206ca5fce918 | note | – – – – – – – – – – – – – – – – –
33b2c9cd-b405-5932-80c7-76176738eae6 | note | RESPONSIBILITY: SE
17393ca5-5a8a-589f-8038-3678846ad0ff | note | – – – – – – – – – – – – – – – – –
825b04c4-0dfe-5f7e-a3a7-6bbf13ba3920 | note | VERIFYING DOCUMENTS: Sign ITP, Attach material conformance docs/Test Report
ce69c138-348f-5a24-a4d0-c3add0f59153 | date | Date Completed:
| checkpoint | 1.4 Supply of Mulch
4aaa404d-8a51-5d18-8b64-1dad81a71005 | note | REFERENCE: Section 720.04 Table 720.044 AS4454 IFC Drawings
19b27b27-46b8-586b-bee5-a370f18db5df | note | – – – – – – – – – – – – – – – – –
49d310d5-0b52-5a80-b734-3f444ff9ba52 | note | ACCEPTANCE CRITERIA: Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible, otherwise approved mulch stated on IFC drawings.
c0e057b7-8273-508e-aaad-f7739428114e | note | ○ All wood mulch to be spread in accordance to AS 4454 and conform to required depth stated in IFC drawings .
d833f517-bf19-5090-bbaf-6515b5878646 | note | ○ Imported Wood Mulch shall comply with Table 720.044.
399fbe2e-d5d9-5b96-9ef1-d6226d531144 | note | – – – – – – – – – – – – – – – – –
3d341226-995d-5325-9785-f844f57a58fe | note | METHOD: Verify, Doc. Review if applicable
db736573-b9d8-5412-b937-739787de93ed | note | – – – – – – – – – – – – – – – – –
9e1bfc9d-ecdb-5222-b159-3a257fe7217a | note | FREQUENCY: Prior to Commencement of works
a91d4881-f5d6-577c-9e7c-ba0d3e4fc9c7 | note | – – – – – – – – – – – – – – – – –
8a5a5c03-d6d2-5ee1-b648-ce91f62d603c | note | CATEGORY: IP
144cd455-be56-5aee-ae19-552a45e83af9 | note | – – – – – – – – – – – – – – – – –
2ad34b0e-5d64-57bb-b2f5-6a66f62d6fb5 | note | RESPONSIBILITY: SE
59cf2cda-53b2-5300-9eaf-fc460a5461d7 | note | – – – – – – – – – – – – – – – – –
71a9b002-87b7-54a4-b474-ec301d8f18f6 | note | VERIFYING DOCUMENTS: Sign ITP, Attach material conformance docs (if applicable)
6f741811-a48d-5e19-9602-411de041064d | date | Date Completed:
| section | Site Preparation
| checkpoint | 2.1 Subcontractor ITP
2d728f45-e48e-5b59-9170-b50c3a83df6c | note | REFERENCE: Subcontractor ITP
24f291d8-8961-553b-911d-a1b77aa43272 | note | – – – – – – – – – – – – – – – – –
135090f0-7873-5b1e-b923-7397df19506d | note | ACCEPTANCE CRITERIA: Subcontractor ITP to be reviewed and approved by MRPA.
1273d5e8-ec91-56f3-9402-dfca333214b7 | note | – – – – – – – – – – – – – – – – –
d1b29b95-67ec-54db-b79c-8149be1928ff | note | METHOD: Document Review
3984f205-0267-565a-8a01-da51c7425504 | note | – – – – – – – – – – – – – – – – –
f47cab10-dbfa-57a9-880e-b0f63ed7aa18 | note | FREQUENCY: Each Lot
adb200f9-b7dd-57d7-a099-b41135b8de4b | note | – – – – – – – – – – – – – – – – –
6cde2663-f39c-52eb-8df9-cbbf0b6fa795 | note | CATEGORY: WP
1daa3c48-b105-5de3-be36-c8220e555181 | note | – – – – – – – – – – – – – – – – –
ee5ecec5-ff0d-5c6b-a32c-22e6c5302f7b | note | RESPONSIBILITY: SE/PE
71f2f0ae-bc1f-5600-8963-6a8e0e356a58 | note | – – – – – – – – – – – – – – – – –
e3d98b95-d651-5ca6-95ef-512bdcb573e6 | note | VERIFYING DOCUMENTS: Sign ITP, Attach completed Subcontractor ITP
a8996a13-3fa1-5fa0-b224-6e0fbbbb4b3b | date | Date Completed:
| checkpoint | 2.2 Soil Additives
d4ef3230-4622-5be7-ad33-9c2bef4b34fa | note | REFERENCE: Section 720.07 a) AS 4419
022ce542-163e-5e81-a72f-dfa52c3b3d84 | note | – – – – – – – – – – – – – – – – –
3f642291-643e-5825-b121-fc4786a4a7ea | note | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
43eece76-5833-5d59-b4a2-408156d05f96 | note | – – – – – – – – – – – – – – – – –
4726c274-0533-532a-ba73-a3451b7a7a97 | note | METHOD: Document Review
5991f170-d3a9-5957-a4ce-dc33754d34aa | note | – – – – – – – – – – – – – – – – –
3fafee64-82d6-58b8-ad43-891db6607780 | note | FREQUENCY: Each Lot
62ca543b-0644-51b0-a377-ec8f526f5148 | note | – – – – – – – – – – – – – – – – –
5e369417-fce6-5b25-afa1-fa77c8b9ded4 | note | CATEGORY: IP
8051e7eb-8fae-56cd-9fd8-7b85604a347b | note | – – – – – – – – – – – – – – – – –
993f96b2-1ef2-5fec-b96e-36df34c32ceb | note | RESPONSIBILITY: SE
f334a556-d984-5d87-be3d-8ed369901953 | note | – – – – – – – – – – – – – – – – –
f7e27d7b-1093-5440-b1f7-9694bfd0e01b | note | VERIFYING DOCUMENTS: Sign ITP, Attach: Test Report, Attached Delivery Docket (if applicable)
cce4d432-14ed-599a-836b-9f545910d5ff | date | Date Completed:
| checkpoint | 2.3 Ripping of subsoil
a10e8318-8364-5246-988c-78352266f9c2 | note | REFERENCE: Section 720.07 Table 720.071
8df3a7d4-ecb7-5baa-b232-0987930a9535 | note | – – – – – – – – – – – – – – – – –
4aaf4f30-d646-59b5-bad4-695c9c87c022 | note | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP.
d4895673-e90a-5bbd-9de6-27c5d471ae04 | note | ○ Do not proceed until the NA inspects and acknowledges requirements for ripping have been met.
c277c5a5-c07b-5f3d-ada3-efbe216fc258 | note | – – – – – – – – – – – – – – – – –
4d184348-2091-55cc-a503-622538990098 | note | METHOD: Verify
985685d4-6f08-5165-a6e7-b22c6dc7c503 | note | – – – – – – – – – – – – – – – – –
87255e00-5d72-5132-8ce4-c9937b96359a | note | FREQUENCY: Each Applicable Lot
76bc0d2c-2750-5152-aec1-fdabe183c9f8 | note | – – – – – – – – – – – – – – – – –
603c1b4d-d0d1-55a5-add4-ac1bd3cba46f | note | CATEGORY: HP
a2860379-57f3-5361-9fa1-979eb35384c7 | note | – – – – – – – – – – – – – – – – –
713ed78a-cd29-5438-9f2d-09fca6d714ce | note | RESPONSIBILITY: SE, NA
b8404eb2-ff3f-5de0-95eb-b31de404c8d6 | note | – – – – – – – – – – – – – – – – –
1578aabe-7775-5514-b76e-94a99846f396 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Lot Map/Marked Up Area Inspected
3f613c3f-4823-56d5-bc99-02743ca01862 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Topsoil application
c2bb2abf-5dc9-5174-b65e-ee64db1c2f20 | note | REFERENCE: Section 720.07
ccef6807-1fe3-5e63-a8d7-22b9ea215421 | note | – – – – – – – – – – – – – – – – –
db72493f-edd5-54f6-ae00-b9acb125713e | note | ACCEPTANCE CRITERIA: Site topsoil shall be used wherever possible, in preference to imported topsoil. Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas in accordance with minimum top soil depths stated in table 720.071.
1fb726ab-8edc-53c1-9296-7a2b4f73725a | note | Situation
9544909e-456c-559e-84d7-bae2ea3791ab | note | ○ Planting Areas in disturbed areas flatter than 3h:1v = 150mm Minimum
f2e4f4d8-38b7-53a4-a60e-42199c16a8f3 | note | ○ Planting Areas in disturbed areas steeper than 3h:1v = 100mm Minimum
3317848e-754f-55dc-8b8a-b59723c54bb6 | note | ○ Grassing in disturbed areas =75 mm, except 100 mm in swales
e7206574-470e-5631-94ee-59c3338e1b8e | note | ○ Individual Tree Planting within grassed areas =150 mm in disturbed grassed areas
dc52ddf5-d68d-506c-9a29-0c0ff4ff19c6 | note | Topsoil shall be spread on planting areas and grassed areas.
e499f54e-a972-5d84-8b98-8530466352f4 | note | Note: Topsoil shall not be compacted.
33caa618-229d-5b19-8a3f-a73824ca1463 | note | – – – – – – – – – – – – – – – – –
7f8c4a04-404f-5299-b7e4-3047466dbd05 | note | METHOD: Verify
eb836d11-c894-5959-8bf7-51203cc903b1 | note | – – – – – – – – – – – – – – – – –
29f35fc9-c252-5606-87e0-e77ea0ecc6ec | note | FREQUENCY: Each Applicable Lot
537775e1-26bc-5f7b-ad47-a365d0324c28 | note | – – – – – – – – – – – – – – – – –
94cee79e-b53b-552e-a450-2f03d3407ddc | note | CATEGORY: IP
7526cc96-fbae-5a91-844c-ef40a49af3b5 | note | – – – – – – – – – – – – – – – – –
2f4c5865-9f35-5827-890d-a3c9333b6f14 | note | RESPONSIBILITY: SE/Site Supervisor
b812dca6-299d-524a-ba82-a53e5c2a72a1 | note | – – – – – – – – – – – – – – – – –
e313cf97-2b1b-5061-bd50-ba5af4175dc0 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Delivery Dockets if applicable
ea41cffb-6125-5fe6-a84d-fb579527b551 | date | Date Completed:
| checkpoint | 2.6 Topsoil FSL - Topsoilling and Cultivation
1fbd2165-2fa3-549a-84d7-c270cd5ae127 | note | REFERENCE: Section 720.07
b705f282-a546-5a8e-81b7-ddc15a1d481a | note | – – – – – – – – – – – – – – – – –
33789fa1-bcdf-5afc-82f0-d0ca2aff9db7 | note | ACCEPTANCE CRITERIA: Do not proceed until the NA inspects & acknowledges requirements for topsoiling and cultivation have been met
8c7fd880-2d03-5a20-8d46-645ac3d6f9f9 | note | – – – – – – – – – – – – – – – – –
730f8ca3-a9c4-5970-8eef-306a0863fe2f | note | METHOD: Verify
e263b60d-c994-5bf2-9389-8df57c707187 | note | – – – – – – – – – – – – – – – – –
ea662002-57e4-5c98-b111-6a8963ba0a23 | note | FREQUENCY: Each Applicable Lot
04951636-6b13-5673-9952-47dcaeb8a101 | note | – – – – – – – – – – – – – – – – –
fdfc5a5e-471a-5e59-92bd-204456bbb547 | note | CATEGORY: HP
2d034339-5822-5e08-878b-9bda6b595ab9 | note | – – – – – – – – – – – – – – – – –
3fb727c1-aad9-55ac-abc3-0fc0de21de5e | note | RESPONSIBILITY: SE, NA
6a862ab3-0376-5a32-811a-3f01d88acb85 | note | – – – – – – – – – – – – – – – – –
c6b4e058-b167-59a1-b16e-638908ae64ef | note | VERIFYING DOCUMENTS: Sign ITP, Attach Lot Map/Marked Up Area Inspected
8e4f278d-7cd5-553d-a651-a28ad8a13a8b | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.7 Mulching
b11ac5a0-a0e6-5225-abd8-2a1a3ac0788a | note | REFERENCE: Section 720.08 a) IFC Drawings
1268bc16-9c87-5d90-98b6-1cc14d9f8866 | note | – – – – – – – – – – – – – – – – –
5575e630-d301-5981-ae59-9df673769624 | note | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
448c121c-188a-592d-b30f-c748a24fc7a5 | note | – – – – – – – – – – – – – – – – –
d2b78fb1-b691-50c3-b3e8-aa58ec97e109 | note | METHOD: Verify
aa94609c-6bd8-5922-87f8-f3c2dec3f336 | note | – – – – – – – – – – – – – – – – –
67c9f944-4a7c-578e-a7f6-6df85b96fc22 | note | FREQUENCY: Each Applicable Lot
fd535e35-25d7-5fc1-98cc-7840d4f78022 | note | – – – – – – – – – – – – – – – – –
eb0cc313-0f6d-519e-97c3-67243d16eb68 | note | CATEGORY: IP
6128b5de-dbf5-595f-8145-7954bb56512a | note | – – – – – – – – – – – – – – – – –
8f8cc094-0042-5cfa-973e-6b986c8e1a83 | note | RESPONSIBILITY: SE, Site Supervisor
9190fdcd-87a9-505f-bad6-237d2e38042e | note | – – – – – – – – – – – – – – – – –
b38219ff-9fd7-573a-8453-9457530dfed8 | note | VERIFYING DOCUMENTS: Sign ITP, Attach Delivery Dockets
abe2fdb2-4e9e-583e-a0a1-4a94440748f3 | date | Date Completed:
| checkpoint | 2.8 Weed and Erosion Control Mat
15ad8d98-667d-5f6d-92eb-37997587ae9f | note | REFERENCE: Section 720.04 i) IFC Drawings
0589fc58-8399-53a5-a660-a1882f1a7de3 | note | – – – – – – – – – – – – – – – – –
10dde67a-e5d5-592f-b435-575b83336853 | note | ACCEPTANCE CRITERIA: Refer to Subcontractor ITP
17917dab-4760-592b-97aa-4934e50167e3 | note | – – – – – – – – – – – – – – – – –
66c627f3-ac03-5a26-b6df-a443d2b216fb | note | METHOD: Verify
78ccadcc-3057-5624-a90f-127711484b31 | note | – – – – – – – – – – – – – – – – –
140cbfc7-6e6f-558a-a91b-da96d2d9e7c7 | note | FREQUENCY: Each Applicable Lot
981fd93c-930a-5371-aee0-b0e3c5aac5a1 | note | – – – – – – – – – – – – – – – – –
ee2810f9-d9e4-57f8-89ae-d2b10e8ac5fe | note | CATEGORY: IP
72e25b0a-d6b2-557c-9cd8-50de0c52247d | note | – – – – – – – – – – – – – – – – –
0e4404d6-8609-5a5d-8b00-d9503dd3c944 | note | RESPONSIBILITY: SE, Site Supervisor
81c90a3c-66f6-5c7a-8624-ddc937f18531 | note | – – – – – – – – – – – – – – – – –
c11c60fe-f3f7-5734-a305-346d88d375ed | note | VERIFYING DOCUMENTS: Sign ITP, Reference TeamBinder Material Approval No. if applicable, Attach Delivery Dockets
f171eced-8f66-5728-93c2-a4f9918432b6 | date | Date Completed:
| checkpoint | Final Inspection
3c927c35-b8f2-55ca-a484-0da82588da3d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
51b2cee9-142e-5f9e-925e-8c9110783b5c | textbox | Name:
1acf8840-f2f2-5090-a08d-9940abe3dd5f | textbox | Position:
28c3134a-adf7-5932-8136-a4cd8c4f0387 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-066-CIV-CAMMS-Landscaping-Planting Rev 0 | itp | ITP-066-CIV-CAMMS-Landscaping-Planting |  | 2641a59d-408e-4129-b1f0-f4e4dfd019f5
| section | Referenced Documentation
| checkpoint | Referenced Documentation
11f19110-cf32-51c2-bc04-f0292183c294 | note | Document Title: ITP-066-CIV-Camms-Landscaping-Planting
4583657d-23f3-59d0-8130-e0c77f5d73eb | note | ITP Description: Landscaping - Planting
d8cc5e1b-402c-50cb-9582-acf0c70eba20 | note | Discipline (e.g. CIV/STR/RAIL): CIV
e5720a81-13c9-50a7-9a5a-e76450d01270 | note | Revision Number: 0
648f327f-b7d5-5e75-aefc-2fe5f9af271e | note | ITP created by: Anthony Pearson
34e3201b-50d7-5287-8581-98380a2b6d89 | note | ITP approved for use by: Victor Mira
ecba119f-ea8c-5777-b03b-342c67e26960 | note | Reference: IFC Drawings Vic Roads Section 720 (Nov '18)
| section | Preliminaries
| checkpoint | 2.1 Check for correct documentation
9ff235f3-91e1-5f39-9559-7a9386a854bc | note | REFERENCE: Drawings and Drawing Register
6034f1ae-b5c3-5df1-8625-2357d8ee8bb3 | note | – – – – – – – – – – – – – – – – –
173e5b7b-659d-5aaf-9ad6-0d256ddd77be | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using:
ed64c4d0-115e-5396-a9a5-b4403457251d | note | – The correct and complete set of drawings
2c283d3e-4776-51e2-96f8-d490847ba454 | note | – All drawings are the latest revision
f6be897b-0521-5bcf-87a0-ae1bd3185b90 | note | – – – – – – – – – – – – – – – – –
294baabd-8c95-558a-85cf-0386b47befc7 | note | METHOD: Document Review
0870301d-9ac0-5ffd-bef8-72f806f18d4d | note | – – – – – – – – – – – – – – – – –
d1a1fe73-7799-5b7d-a83f-bcca29fbc599 | note | FREQUENCY: Prior to Commencing works
9d6e6d7d-e2e2-526a-81cf-7b5d1a59a8f0 | note | – – – – – – – – – – – – – – – – –
93ddcecf-1aef-56f5-96b0-ff6dd0ad847e | note | CATEGORY: N/A
c2685484-210e-53df-a320-4dd8feb7029f | note | – – – – – – – – – – – – – – – – –
adfe795d-e629-53a8-bf07-44a491293852 | note | RESPONSIBILITY: SE
d54debaf-f128-540f-978d-2019693fad19 | note | – – – – – – – – – – – – – – – – –
12e438fc-9efe-5c1c-92aa-8b6e283c66d4 | note | VERIFYING DOCUMENTS: This ITP
1868201e-25f2-56ae-b627-49ff0c3cd72e | date | Date Completed:
| checkpoint | 2.2 Submission and records
6b0c7cea-8147-5105-8955-e234e3036941 | note | REFERENCE: VicRoads Spec.
79dd361c-09f3-5b48-a7c0-ca75c594550b | note | – Cl.720.03
b14b179f-4d68-5cf8-a74c-aa0267a138a7 | note | – – – – – – – – – – – – – – – – –
ded1c525-3c98-5d63-895e-27f5411d41b9 | note | ACCEPTANCE CRITERIA: Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
e1ec72d1-ad86-5964-a86c-5b695a233bfa | note | Following information shall be provided to the superintendent:
5ad491ed-36f8-5bba-9c16-103cee8fbeef | note | ○ Inspections of plant stock for all plant species
4be92ae0-8b82-55c3-86aa-1bbe42e11274 | note | Records:
10ae3542-590e-521a-8e12-957b0f6eaa26 | note | – Evidence of origin of indigenous provenance plant material
a8973186-9496-5188-a6e3-25f8e8b0c7a9 | note | – Analysis certificates for grass seed
1e84a52f-724a-54db-9e5f-75a0f0614e6f | note | – Details of suppliers
67c100cb-8dd5-5e17-ae68-ab569f53ea2c | note | – Copies/Photos of fertiliser labels
47ae15e3-bb8c-55fc-bb15-ff0328133867 | note | – – – – – – – – – – – – – – – – –
658c8e96-8d26-5229-90e8-486caad54735 | note | METHOD: Document Review
c46813a1-fae2-5d14-a8e1-b41c5e1a5475 | note | – – – – – – – – – – – – – – – – –
125f3101-e224-5650-b706-a711967f993f | note | FREQUENCY: Prior to Commencing works
9a5cc93c-0f7d-5e8f-9be4-54d533119da9 | note | – – – – – – – – – – – – – – – – –
63a648cd-be1c-5953-bdd0-9acbae0d6333 | note | CATEGORY: HP
e023931b-d28e-5c3c-9b5c-06968dc88250 | note | – – – – – – – – – – – – – – – – –
78bd8b8a-51d8-5f6f-8d9f-61264a46a0f7 | note | RESPONSIBILITY: SE,Superintendent
44876b57-93db-5000-9375-3472566dd899 | note | – – – – – – – – – – – – – – – – –
288673d2-f8df-5eec-9112-b5ce51a7f275 | note | VERIFYING DOCUMENTS: This ITP, Attach Records to TeamBinder Approval Form
8b067b27-5db7-54d0-ac12-de1738e9f906 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Supply of Plant Stock
eb86e741-b7a9-5265-9150-057719e48d62 | note | REFERENCE: VicRoads Spec.
bc3d0099-e0d9-5c72-af95-ecfa7c150abe | note | – Cl.720.04
a73a8713-baca-5567-9afc-56e23e1ee448 | note | – Table 720.041
b2850c68-70f7-5fa7-b8f1-03afbfd2a5bd | note | – – – – – – – – – – – – – – – – –
8a819e93-ead5-5611-a13b-a5420c7f3d42 | note | ACCEPTANCE CRITERIA: All plants shall be of the type, height, container size and trunk caliper specified in the Plant Schedules, Specification and Planting Plans.
32b26700-ceb3-54f4-89a4-bb85d52094b3 | note | ○ Plants are to conform to the supply properties specified in Table 720.041
4d54ec38-305a-51ce-8708-7ecf461b9d21 | note | – – – – – – – – – – – – – – – – –
52ddc0fe-6386-584e-8220-3ab519bf10f2 | note | METHOD: Verify
56cebe22-18d6-5afa-8f84-5b59b2e539e9 | note | – – – – – – – – – – – – – – – – –
87bda438-86b8-5210-be21-cd842eeb89b9 | note | FREQUENCY: Prior to Commencing works
a06e34ca-1a49-5124-acb1-99d5ba20de65 | note | – – – – – – – – – – – – – – – – –
b8afbc8e-21e8-5bcd-9d8f-e53d88101892 | note | CATEGORY: N/A
d1a4c3b3-462a-5831-81b1-089bf426815e | note | – – – – – – – – – – – – – – – – –
d5c50ac1-ec54-5d68-8bff-3bbf78bb1851 | note | RESPONSIBILITY: SE
98d0f219-3d31-53db-bb35-83262ffd8531 | note | – – – – – – – – – – – – – – – – –
bf064bfa-7bc8-5183-9fe3-19d548a26051 | note | VERIFYING DOCUMENTS: This ITP
f75b0c05-bf42-50c6-b326-2c83e4e173c0 | date | Date Completed:
| checkpoint | 2.4 Supply of indigenous plant stock
4bfc43d3-e8eb-597e-85dd-4ac96fe11325 | note | REFERENCE: VicRoads Spec.
a135cb1b-b7e1-5208-a9be-d85bca2a3842 | note | – Cl.720.04
121fd5a5-83a8-5900-93e5-7ba7d3667b8a | note | – – – – – – – – – – – – – – – – –
47c23a78-dd31-5290-8041-4b89acf5eff4 | note | ACCEPTANCE CRITERIA: A species listed on the planting schedule shall be classed as an indigenous plant if the plant is likely to have occurred within 10 km of the project site (pre 1750).
be9a238d-b81f-5f85-b4d2-04794fa73ec2 | note | ○ The Contractor shall submit documentation of origin of indigenous provenance plant material which shall include the following details for each seed lot:
8e542a77-4350-521d-ac09-80cb7d62368b | note | ○ species name
03af84aa-d769-5f5b-9090-6a0dcda36576 | note | ○ storage code
7c79ab75-5c86-5ed2-98cc-aff2ace988cf | note | ○ collection locality - Latitude/longitude or AMG
54317e69-7cef-58ab-baa0-56ca8b3b6009 | note | ○ approximate number of parent plants sampled
d33be879-8da3-5fa4-823e-24901957307f | note | ○ approximate number of plants in that local population
c0798c9f-b9b8-52df-831a-912eeea4b6f5 | note | – – – – – – – – – – – – – – – – –
d10cf825-95fa-5bfc-932f-590e20a4dac9 | note | METHOD: Verify
668c0333-d2fd-584a-85cc-b23ae60f78e3 | note | – – – – – – – – – – – – – – – – –
9f82cbcf-fd6b-544d-ac90-9e435f300ab8 | note | FREQUENCY: Prior to Commencing works
df8576e9-851a-5a8c-8d2f-60f8f46e6348 | note | – – – – – – – – – – – – – – – – –
511133d4-494c-5b78-a3e8-ffe5e7d151be | note | CATEGORY: N/A
524c4d8d-389b-5d07-bb1f-90869304dc0b | note | – – – – – – – – – – – – – – – – –
b3ab2c76-078e-5c09-857a-c59e7510a0fe | note | RESPONSIBILITY: SE
d90ad4d2-42c1-5469-a3a5-927fa839c1ef | note | – – – – – – – – – – – – – – – – –
faeb3377-98f0-55df-ad28-f39ca7aa6ed2 | note | VERIFYING DOCUMENTS: This ITP
9a6b65e5-172d-5f07-aa82-0c12fbb0c6c9 | date | Date Completed:
| checkpoint | 2.5 Supply of grass seed
c42f6a24-a2d6-5b59-a6ff-92cb528364ed | note | REFERENCE: VicRoads Spec.
b1963d3c-31e5-5534-a1ca-17166b629ce9 | note | – Cl.720.04
5dbc26e1-f549-5a8e-b50d-fb8b58536d77 | note | – Table 720.045
f14601a6-5cb4-53df-8625-cd027804a2a3 | note | – – – – – – – – – – – – – – – – –
4886ef8a-68ce-5441-b69e-d49ddd7e86ab | note | ACCEPTANCE CRITERIA: Grass seed shall comply with Table 720.045
21bd2161-b105-5752-82cd-f5ff404e2454 | note | – – – – – – – – – – – – – – – – –
c1ec1e09-c1bc-561c-8003-95b94ebbbe7f | note | METHOD: Verify
fb0d2116-3294-5a6a-9e84-bfa218637d48 | note | – – – – – – – – – – – – – – – – –
fcf05290-25e1-5650-beb2-c0674190beb0 | note | FREQUENCY: Prior to Commencing works
1fb22045-dd72-52d2-a2c3-c172bcd6466a | note | – – – – – – – – – – – – – – – – –
a214fcf8-c5d5-5645-bc3c-cef4ec92a219 | note | CATEGORY: N/A
5b528444-8877-5ece-9d89-bc5ff23ed377 | note | – – – – – – – – – – – – – – – – –
e8a4e453-6e12-5d05-b4a1-f809d6ab6b26 | note | RESPONSIBILITY: SE
eead667c-b509-52e1-93f7-818eeadb2b5c | note | – – – – – – – – – – – – – – – – –
dd0de490-3548-5181-bc79-5bb2a369fc82 | note | VERIFYING DOCUMENTS: This ITP
28a244b6-9d89-5fb9-9e5e-36d17aef64e5 | date | Date Completed:
| section | Pre-Construction Activities
| checkpoint | 3.1 Planting Section Approval
4b044681-492b-5598-a6fb-fb824698d9b7 | note | REFERENCE: VicRoads Spec.
46952b43-da45-5195-a462-59fdfe891a78 | note | – Cl.720.06
af0d475a-7cbf-5c4b-88a5-4830d4260747 | note | – ECO-LANF-005
ac48a074-9899-5340-85b4-fe46e0fb2814 | note | – – – – – – – – – – – – – – – – –
33099e39-7890-55ca-9ed4-afdd5db5c23c | note | ACCEPTANCE CRITERIA: Trial planting sections have been approved by the Superintendent. These approved sections shall be used as a reference for the remaining planting works
6cc46552-6d93-5dcf-a95c-a50e4eca17db | note | – – – – – – – – – – – – – – – – –
fbde3258-fef6-5fda-aea8-0f86725db1d2 | note | METHOD: Verify
3df714fd-3a1b-51dd-9ad1-183c260da7e0 | note | – – – – – – – – – – – – – – – – –
121ded53-07e0-5a15-91db-9c23f9ab0c5e | note | FREQUENCY: Once
d0788e4e-0bf2-5178-b611-4dfb1bbeab6a | note | – – – – – – – – – – – – – – – – –
66a8fd5f-4c58-506d-93f1-fd0487f83f25 | note | CATEGORY: HP
10f1683b-a5a7-5845-89bd-aeb01e5e39e0 | note | – – – – – – – – – – – – – – – – –
557606b7-e10f-5466-b80b-c41e25320149 | note | RESPONSIBILITY: SE
5f4fd7f4-1a9c-5e18-ac6f-8fdbfa8544ec | note | – – – – – – – – – – – – – – – – –
4a014edd-dbdd-53bb-91ef-f59edec18551 | note | VERIFYING DOCUMENTS: This ITP
bd4bf7b6-79b9-5516-9c8d-b8685b910ea7 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.2 Pest and Weed Control
8194afe3-c74c-538f-9e29-604c5a57d65c | note | REFERENCE: Cl.720.05
65576ce2-bc0e-5389-9c0d-1242517aee3a | note | – – – – – – – – – – – – – – – – –
fd1b5fa2-4c33-5ca1-b639-07da10fd1bc0 | note | ACCEPTANCE CRITERIA: The Contractor shall develop and implement site specific pest and weed management procedures to control pest and weed populations.
97a30411-11bf-572a-9f2e-bfe24862e832 | note | ○ Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing.
5249dd94-47a3-5f0a-aefa-fefc592eaafe | note | – – – – – – – – – – – – – – – – –
e0e38ba8-da5f-500b-856d-cd8fd8c4e423 | note | METHOD: Verify
38bce6ec-1427-535b-86db-9b4fa75a309f | note | – – – – – – – – – – – – – – – – –
1b5a5be7-d973-5bbb-afc6-e4e684a7cc2f | note | FREQUENCY: Once
5026f96d-ac1e-5755-a577-7270373b4dc5 | note | – – – – – – – – – – – – – – – – –
b916474a-cfbe-508f-acae-b5a762654a1d | note | CATEGORY: HP*
749f5f32-52f4-5c08-b45d-d06aaa6bfb3c | note | – – – – – – – – – – – – – – – – –
c4eca3a4-db12-5037-abf0-fcdb7163c7b6 | note | RESPONSIBILITY: SE
ab6c3435-a2ff-55ab-aeec-2284111e09f1 | note | – – – – – – – – – – – – – – – – –
c21f1b9d-75f8-5f3f-bfc9-4ad287492940 | note | VERIFYING DOCUMENTS: This ITP
595cfc49-33be-57bf-b867-2022214846e9 | date | Date Completed:
| checkpoint | 3.3 Setting out planting areas
0d0a705b-de69-5fb5-bce6-d6187ab43d94 | note | REFERENCE: VicRoads Spec.
374ade60-08d3-535f-8eaf-08f3bedcab42 | note | – Cl.720.06
47242779-69fe-56c0-b03b-1d98ee8db7cc | note | – – – – – – – – – – – – – – – – –
5e00aefe-01a2-563e-af60-a0d8b1c869d9 | note | ACCEPTANCE CRITERIA: Planting areas are to be set out to the location and shape specified in the landscape drawings.
6a77f3a5-abea-55aa-9891-89f8dd792810 | note | ○ Plant density requiremens and planting offsets established in the plant schedule are to be adhered to.
75ea3a97-7e36-5b36-a496-d795f1dc7acc | note | ○ Individual plants shall be located in accordance with the drawings such that the mature form of the plant will be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements.
21cf7c28-f8a6-5ab9-b05b-b750c23f12ee | note | – – – – – – – – – – – – – – – – –
7253bd68-5631-5e71-af68-db0fd4da931b | note | METHOD: Verify
74e3cd64-a0a2-59dc-90d5-a30d56376f6d | note | – – – – – – – – – – – – – – – – –
b59084ba-5a8f-57d8-bc36-e196eb8ed8e8 | note | FREQUENCY: Each Applicable Lot
2b522758-db52-5a4c-8057-6cbbf13293c5 | note | – – – – – – – – – – – – – – – – –
e4eea159-49c3-544b-8dd1-2301cb223fbc | note | CATEGORY: N/A
9b93332a-f854-56e5-8a05-0a537012d523 | note | – – – – – – – – – – – – – – – – –
f67f6b9d-4434-5caf-b183-e8b464a02c6d | note | RESPONSIBILITY: SE
cb51763c-f78b-5f18-8a9f-cf3b32ca3518 | note | – – – – – – – – – – – – – – – – –
fe2f834f-779e-5880-aa76-b652d0e89267 | note | VERIFYING DOCUMENTS: This ITP
cf088c5f-0432-502a-9314-230a13d193e5 | date | Date Completed:
| section | Construction
| checkpoint | 4.1 Planting
c3b32431-758d-5606-857f-27fbf7d0f0cc | note | REFERENCE: VicRoads Spec.
8944b93f-05d5-5175-a7aa-80bc91315bf8 | note | – Cl.720.09
95c63a0e-4ab6-5506-a988-0c54352f04fd | note | – ECO-LANF-005
72c425e4-3a60-5591-8aac-0fc8373202e1 | note | – – – – – – – – – – – – – – – – –
e04ce32c-4e9f-5430-8579-6d65ffe90880 | note | ACCEPTANCE CRITERIA: All planting will be undertaken in accordance to Ecodynamics ITP ECO-LANF-005
60172cda-c0b7-5aec-b9c1-33fe8196930a | note | – – – – – – – – – – – – – – – – –
e62916ce-19d6-50f6-8899-3512784d52c6 | note | METHOD: Verify
0eacdb95-a604-52d2-bcd3-2df4ea1e0922 | note | – – – – – – – – – – – – – – – – –
53ae9fbf-153e-5eab-85ae-9d925360c66a | note | FREQUENCY: Each Applicable Lot
16b2c26a-6380-56f4-a8d2-0d838e676563 | note | – – – – – – – – – – – – – – – – –
ecafbd94-4eba-593f-b580-25a1c87839bb | note | CATEGORY: N/A
4911237f-10e2-5233-9de3-2ea30a90eb41 | note | – – – – – – – – – – – – – – – – –
c08257f2-03a9-51ba-acd3-c5248f812c99 | note | RESPONSIBILITY: SE,Foreman
17922ff6-515f-56e1-8056-a1dd5c5211e6 | note | – – – – – – – – – – – – – – – – –
4d11dd4b-9c38-59e9-8eff-086a2a15c939 | note | VERIFYING DOCUMENTS: This ITP
951a72ec-a47d-53f7-92ee-805b0a446d2b | date | Date Completed:
| section | Completion
| checkpoint | 5.1 Site Final Inspection
e1f08f83-77f1-5c52-8e7e-f424cb060777 | note | REFERENCE: ECO-LANF-5
105e6a2a-b646-54f6-8a68-62c19ecd6f13 | note | – – – – – – – – – – – – – – – – –
3e3746fa-6250-5f56-880b-f7b1b68bf767 | note | ACCEPTANCE CRITERIA: Ecodynamics ITP signed and completed
0dc8dde7-3851-54b2-a7fa-43a8b300e3d1 | note | – – – – – – – – – – – – – – – – –
7ece298a-6acd-574f-8924-c49d6d3b210d | note | METHOD: Document review & Site Inspection
18a49ea5-7705-5c84-9c63-8f82cc866624 | note | – – – – – – – – – – – – – – – – –
a8f3d2dd-a461-5aeb-9725-ef09a428224f | note | FREQUENCY: Following completion of planting works
8904b976-c482-580e-aac0-a16eadaee5e1 | note | – – – – – – – – – – – – – – – – –
80a437fc-0221-5dc7-95f2-ba1dff707db0 | note | CATEGORY: N/A
565033aa-0a9c-5645-9cfb-d39eccee9d63 | note | – – – – – – – – – – – – – – – – –
a2f9d8ff-949c-5197-821f-8d443e7cd328 | note | RESPONSIBILITY: SE
9cfaecd1-47e4-57af-8861-81f5303ae9c4 | note | – – – – – – – – – – – – – – – – –
9eb3655a-5809-5574-b565-13ffe649adee | note | VERIFYING DOCUMENTS: Sub-Contractor ITP completed, signed and to be attached
7a871f27-dcad-57f6-983e-9966b5abe2d4 | date | Date Completed:
| checkpoint | Final Inspection
321a16f0-60c8-5073-be76-6922f65edc0b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
28f56678-f9e6-5d5b-8483-ef2106101fc8 | textbox | Name:
78149d09-85b9-5c73-a8c8-26fb5d4a2a2a | textbox | Position:
b5dd137f-0d3b-53fe-9eba-a40fc5034760 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-067-CIV-CAMMS-Line marking Rev 0 | itp | ITP-067-CIV-CAMMS-Line marking |  | ed9ffbb7-7306-4a3d-91c2-c8929b64a261
| section | Referenced Documentation
| checkpoint | Referenced Documentation
88264a22-f0c2-5e56-b16d-ea884dd1003f | note | Document Title: ITP-067-CIV-CAMMS-Line marking
bbf9eea8-dbaa-52f6-a6f6-4aad2f5a9ee9 | note | ITP Description: CAMMS-Line marking
044bbbe5-b010-5b9a-a481-f37ce44dcb5a | note | ITP number: 067-CIV
ae3f94e8-023c-526a-b9f3-06c57fe17dcc | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
4ef8e0f3-5003-508f-838e-e991e2d0691d | note | Discipline (e.g. CIV/STR/RAIL): CIV
eee6647c-7bbc-5aca-bff1-b1906ad5f48a | note | Revision Number: 0
814b4b83-4c2e-5407-be82-549ed20eaf3d | note | Revision Date: 13/10/2023
af68125a-63dc-5b4b-9a45-fe56ce49d434 | note | ITP created by: Victor Mira
e6fe9703-05ee-5b51-9706-152c31fc4cb1 | note | ITP approved for use by: Victor Mira
5256cfb7-74e4-54b0-8577-25c55a23212b | note | 1.1 Non Dependent
ef14733c-0a99-5cdf-afde-22d43f979fa7 | note | Reference: Vicroads Section 721 February 2017
7b90b911-96a9-5ded-96ae-e7babceabfe0 | note | 1.2 Non Dependent
092d22b4-a438-5f8b-9c0f-3266250269e2 | note | Reference: Vicroads Section 175 November 2019
65f58373-f09f-586c-99c8-34429f211901 | note | 1.3 Non Dependent
44f33045-cfc3-5fc2-ab58-942531381a2c | note | Reference: Vicroads Section 853 February 1994
| section | Preliminaries - Materials
| checkpoint | 2.2 Type of marking material as shown on design drawings and shall conform to the Standard
3d5c4cd8-49d0-5316-9b84-efd3c7c7feaf | note | REFERENCE: Vicroads 721.A05
f0534e3e-0991-5678-964b-ce30afa14ee4 | note | – – – – – – – – – – – – – – – – –
f189b898-39a5-5b73-8da1-ea98bfd3a20c | note | ACCEPTANCE CRITERIA: Type as per relevant design drawings, obtain Conformance Certificates and test reports from supplier
6e198228-658c-53c4-b272-5661e0f12f28 | note | ○ Provide the principle a list of materials that to be used with a certificate of conformance with associated test report
7f8a2f72-cb3b-5a54-9c69-4d0124f40f2c | note | – – – – – – – – – – – – – – – – –
1431c28d-bf9b-5f21-a69f-42cb1203e326 | note | METHOD: Document Review
0f8c99dd-a7f9-55cc-8780-eee5d20f928b | note | – – – – – – – – – – – – – – – – –
329a6566-f5bc-5fb9-9f5e-1433dd87b0e7 | note | FREQUENCY: Once
8b299750-43a4-5ac9-9667-65dd2767d8aa | note | – – – – – – – – – – – – – – – – –
d861c530-cd01-5ea3-ba68-cd0c7895f1bf | note | CATEGORY: IP
48bd07c8-1196-5163-a7b4-35d9d58e8910 | note | – – – – – – – – – – – – – – – – –
c7f0ec9c-c4b0-5ce1-8d69-07c5b6b2f0fa | note | RESPONSIBILITY: SE/PE/SPE
ef6d14b4-aa8b-5520-a49a-cbbc3f5a0c7b | note | – – – – – – – – – – – – – – – – –
662ffc83-d191-5595-8a44-e613b26f22aa | note | VERIFYING DOCUMENTS: Material certificate
4807e776-67e3-50f9-83e2-861c7d61ce6d | date | Date Completed:
| checkpoint | 2.3 Raised Pavement Markers
b8e36d28-841f-5801-8a7d-4ae0834b6df1 | note | REFERENCE: Vicroads 721.A05
e45bf111-e8d6-56df-992c-aad95c2a17f4 | note | – – – – – – – – – – – – – – – – –
38a865f3-bcab-5a4e-bc3d-e3a38e439ed2 | note | ACCEPTANCE CRITERIA: Raised pavement markers shall comply with the relevant requirements of AS 1906, Part 3 as listed in Section 175.
cdafdfc0-4929-5557-83b0-fb71b8715c54 | note | (ii) Temporary raised reflective pavement markers shall comply with the relevant requirements of AS 1906 as listed in Section 175, and shall be at least 100 mm in width and to a height of 50 mm with white reflective material on both sides and include protective covers for the reflective material
01f9e44f-c79d-5492-aa1a-e2de5a89b2ef | note | – – – – – – – – – – – – – – – – –
76b51fed-9d46-5b14-a9cb-81b1968c258d | note | METHOD: Document Review
e1d7e5a6-c105-57ef-9677-adaf7f5210c6 | note | – – – – – – – – – – – – – – – – –
ffb8810c-da50-5c2e-a0be-1ba47af33410 | note | FREQUENCY: Per Material
a4be4886-6774-5842-b78f-8e98e8be52e8 | note | – – – – – – – – – – – – – – – – –
08ac1612-cf83-5eb6-81ff-9faf4d9b44d8 | note | CATEGORY: IP
7d5fa267-1b0d-546b-b623-c3c062f842bf | note | – – – – – – – – – – – – – – – – –
275f5f76-7533-53b1-92c7-146080fdfbb8 | note | RESPONSIBILITY: SE/PE/SPE
084581d6-6779-503e-b83f-3797fc12bd01 | note | – – – – – – – – – – – – – – – – –
e1e5dbcd-da44-51ea-982f-4e47716b45b0 | note | VERIFYING DOCUMENTS: Material certificate
14a10157-314e-5876-9b4a-a2d3cec25636 | date | Date Completed:
| checkpoint | 2.4 Adhesive
18ad33d4-7992-555e-8a86-8720ff4d453b | note | REFERENCE: Vicroads 721.A05
d3590d0a-0906-573d-9ac1-26d455f9aad8 | note | – – – – – – – – – – – – – – – – –
88663f61-bf5e-54b6-b4c5-50f370fb244b | note | ACCEPTANCE CRITERIA: Hot melt bitumen adhesive shall comply with Section 853 - Hot Melt Bitumen Adhesive for Raised Pavement Marker Installation.
ea00ef43-0eb1-56b9-be00-c79b46e1e3d4 | note | ○ Other types of adhesive materials shall only be used with the approval of the Superintendent
7f3fc4f3-1750-5b81-ab79-a9b7cdb1d3b7 | note | – – – – – – – – – – – – – – – – –
0cf579e8-53a3-50df-bc1d-b22e1d93d928 | note | METHOD: Document Review
6ba6a14b-e007-5f4b-a462-7c5d9c0d2408 | note | – – – – – – – – – – – – – – – – –
48a46eab-9261-570a-b858-1b4bd27f28d0 | note | FREQUENCY: Per Material
e6605968-bf81-58cf-bcbf-a18f97446be4 | note | – – – – – – – – – – – – – – – – –
fd2045bd-89ce-5dff-8df3-2c386fcc00c8 | note | CATEGORY: IP
cb1db447-5911-56f1-bbad-8cf79049c1f1 | note | – – – – – – – – – – – – – – – – –
37c967d5-d67a-5dea-adad-88b72eb12c99 | note | RESPONSIBILITY: SE/PE/SPE
e3171786-4d0f-5b4b-9184-7d27706e6c1c | note | – – – – – – – – – – – – – – – – –
d14885fe-59d7-5aac-a736-b43d9af1873c | note | VERIFYING DOCUMENTS: Material certificate
73cda65b-f35e-51e1-ad76-38ecaf1a2269 | date | Date Completed:
| checkpoint | 2.5 Line marking and Road marking Paint
d89047be-1d9b-56f6-bdd7-c3ac7afc32ab | note | REFERENCE: Vicroads 721.A05
00e2aa43-7778-5592-a1da-54eb79a4d93e | note | – – – – – – – – – – – – – – – – –
3f481817-250b-5d6e-bc64-32a73fafd200 | note | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent-borne paint or AS/NZS 4049.3 for water-borne paint as listed in Section 175.
266196de-383e-5e8b-b52c-d3eab65c576e | note | – – – – – – – – – – – – – – – – –
053374f1-2893-57bf-a852-7897931c6b43 | note | METHOD: Document Review
60877ca9-b6d5-5de5-8b19-1efc2f568868 | note | – – – – – – – – – – – – – – – – –
331bb275-48e7-5a55-9bb2-f5fc27fb22dc | note | FREQUENCY: Per Material
fff418f6-b83b-57a6-a1f9-e0bad64a3a90 | note | – – – – – – – – – – – – – – – – –
9d63d566-0542-545a-8c57-80040587c0d9 | note | CATEGORY: IP
abc1d978-9bba-5aa1-b76b-85ada113874a | note | – – – – – – – – – – – – – – – – –
85c3aec5-aa1e-5828-ae8c-c69a32100998 | note | RESPONSIBILITY: SE/PE/SPE
7a846ecf-7d9c-521b-8122-93c5842f925f | note | – – – – – – – – – – – – – – – – –
12e52f6e-de84-51b6-bfa1-17d83e9024b5 | note | VERIFYING DOCUMENTS: Material certificate
fdf69a54-340b-5faf-8f04-b3f5543dfc4d | date | Date Completed:
| checkpoint | 2.6 Glass beads
c4c7198e-ef82-5c9a-b1a3-233d3ec4cb8b | note | REFERENCE: Vicroads 721.A05
ec59b5ba-cca5-5dcd-83a0-95f2b149fa40 | note | – – – – – – – – – – – – – – – – –
d68dd8bd-46c5-594f-b774-d980d58c0174 | note | ACCEPTANCE CRITERIA: Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
3120f07b-051a-5f29-90ac-2186abfecbe4 | note | – – – – – – – – – – – – – – – – –
fa25a813-93f0-51e2-b746-867b04a69fc7 | note | METHOD: Document Review
73f01a71-0277-587d-9b95-45f7871d35e7 | note | – – – – – – – – – – – – – – – – –
e2e697f8-6001-5675-8986-0b66f0d878b9 | note | FREQUENCY: Per Material
d98c8887-d8c7-51b9-8d8d-a0bdee3cb4ce | note | – – – – – – – – – – – – – – – – –
dc54d889-b5a0-55e4-9bfd-c0cd77b1b8f9 | note | CATEGORY: IP
7c68b3ad-cec2-5df7-8813-66469acd8619 | note | – – – – – – – – – – – – – – – – –
cb2847d2-dca4-569d-8d28-30d3276763f0 | note | RESPONSIBILITY: SE/PE/SPE
ba4a405e-a636-5799-b02f-341b665b10e2 | note | – – – – – – – – – – – – – – – – –
1e6422bc-2ba8-5512-a30e-285a25b78525 | note | VERIFYING DOCUMENTS: Material certificate
27d9d07a-09e0-52a7-b32e-4c20fce83e55 | date | Date Completed:
| checkpoint | 2.6 Glass beads
259143bd-4b7d-5912-aa76-219f6b7982ae | note | REFERENCE: Vicroads 721.A05
a60a7ad9-51da-5503-9961-994e3a48e3a6 | note | – – – – – – – – – – – – – – – – –
1020fdad-3d40-51e8-97f2-5eb26b4d259b | note | ACCEPTANCE CRITERIA: Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
6687541e-b7a7-5e76-85b6-809a990f487a | note | – – – – – – – – – – – – – – – – –
b1dc4c27-cfc1-5e15-af2b-1e632c820666 | note | METHOD: Document Review
8f9cedd0-72d2-51e5-9503-f013bc3a88de | note | – – – – – – – – – – – – – – – – –
f50f6155-5a12-5b18-a515-7fe59be6cd1d | note | FREQUENCY: Per Material
51d7439b-ebb7-52a4-9ce3-fbf148b8b6cd | note | – – – – – – – – – – – – – – – – –
7bb9f6d8-a12b-5e08-80a7-4d8e1e10eba1 | note | CATEGORY: IP
3abc636a-0527-582c-8327-2293fc289e3c | note | – – – – – – – – – – – – – – – – –
e96f3867-1334-58ce-89fd-7c73bc79a056 | note | RESPONSIBILITY: SE/PE/SPE
b518637e-45e1-5123-a44f-b82bf8ac8c37 | note | – – – – – – – – – – – – – – – – –
49cc0cbe-53c5-52d3-a852-19d75aea542f | note | VERIFYING DOCUMENTS: Material certificate
68319b39-c6b2-5c76-afb1-58d87466a9cf | date | Date Completed:
| section | Preliminaries - Procedures & Documentation
| checkpoint | 2.1 Accreditation to Painting Contractors Certification Program
ddbecf78-35e3-5f56-8f1e-e0d10bc5071c | note | REFERENCE: Vicroads 721.D01
4e78a207-6995-5733-9cd3-0071ad4a2893 | note | – – – – – – – – – – – – – – – – –
d2aa9856-6138-5804-84e3-6e8f9e5d35c2 | note | ACCEPTANCE CRITERIA: Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO.
6fdfa379-450b-53c2-8615-4a68e47bb708 | textbox | Enter: Teambinder Approval number
cf9486db-f5d5-5dd6-8171-81937a5d36dc | note | – – – – – – – – – – – – – – – – –
0c0bb230-5076-52e8-95e2-57488c2fb3cf | note | METHOD: Document Review
d0cb92f4-dbc0-5e32-959d-546b87b18815 | note | – – – – – – – – – – – – – – – – –
23945da0-f6c2-57d5-9eb3-23078a4755ef | note | FREQUENCY: Once
87abd3cb-ace5-5a07-9735-4203611e74ef | note | – – – – – – – – – – – – – – – – –
2a0d9ca8-4e18-5b20-915b-ef8334e77dd0 | note | CATEGORY: HP
54fee893-ea54-505b-986d-e218f90439e4 | note | – – – – – – – – – – – – – – – – –
3df96645-fd1d-5d5e-8920-6f115e1eceed | note | RESPONSIBILITY: Nominated Authority
d4c4192b-7a51-5a8b-9945-f1dda9627268 | note | – – – – – – – – – – – – – – – – –
a2ad733c-ba12-5d30-a54e-9c15200d13f8 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, PCCP Accreditation
cdf42a3c-233a-54ed-94b7-3cde5532f8b6 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 3.1 Surface preparation
19d0098c-38de-5711-b185-5afd27bdfa1b | note | REFERENCE: Vicroads 721.A06, Vicroads 721.A09
6762fe2e-398d-5682-b06f-24bf5a031546 | note | – – – – – – – – – – – – – – – – –
5a26f756-4c3c-5141-a2cf-56e0d721677a | note | ACCEPTANCE CRITERIA: The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
a8455a26-c158-5e39-9d99-6bb22b889957 | note | ○ The area around making area is also clean to avoid tracking into the marking area
71c5a4cf-fdbb-5da8-8f2c-a120228b8357 | note | ○ Removal of existing unsound, obsolete or redundant pavement markings
3aa5b007-6c01-5a43-a904-911a7580b419 | note | ○ Removal of any foreign materials and debris within reasonable limits.
41bf68b9-990b-57fb-a66a-2da05cf0a4e1 | note | – – – – – – – – – – – – – – – – –
1e2eb047-45b7-5c9f-b67e-afef2c4da6a9 | note | METHOD: Measure, Visual, Document Review
78648296-ea95-5fa2-a39f-027150e0896e | note | – – – – – – – – – – – – – – – – –
305bbb99-5d71-530d-ade1-3fb47e974ad6 | note | FREQUENCY: Per Lot
29602dd8-80bf-58b3-a1e2-9d2f5ad51ee2 | note | – – – – – – – – – – – – – – – – –
89b1e16c-a3a3-5ebc-9a99-777c167611d4 | note | CATEGORY: IP
b567c19a-1361-5346-ac26-2df460f10bdd | note | – – – – – – – – – – – – – – – – –
92c00167-9df1-5c57-9712-21db0834238e | note | RESPONSIBILITY: SE/PE/SPE
9bd82e77-afdb-5bc9-82e0-391d5b122f43 | note | – – – – – – – – – – – – – – – – –
7d8971c3-bda0-564f-be75-aa7412a922b9 | note | VERIFYING DOCUMENTS: This ITP
8c90fa45-b0ff-5dfa-a1ff-2396264170a7 | date | Date Completed:
| checkpoint | 3.3 Redundant pavement / unsuitable marking markers removal
f5c6ce6a-fc25-5c32-9153-9a939490629b | note | REFERENCE: Vicroads 721.A12, Vicroads 721.A06, Vicroads 721.A08
ccd02e8e-ce69-5f5c-ab9e-98075805f585 | note | – – – – – – – – – – – – – – – – –
722444e3-d2d5-549f-947a-cb29670aa909 | note | ACCEPTANCE CRITERIA: Where removal of existing pavement marking/unsuitable pavement marking to the standard is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
347b1479-7a70-5643-8cc1-ec3e85a30024 | note | – – – – – – – – – – – – – – – – –
57baf991-3227-59e4-8f0b-4b3b83702029 | note | METHOD: Visual /Site Inspection & Document Review
c321414e-1a23-5607-8ea5-ab1edb9b3ff1 | note | – – – – – – – – – – – – – – – – –
1450eddb-ed2d-58e2-beb9-13a2d715ca01 | note | FREQUENCY: Per Lot
abe3372a-c648-513c-a9cc-109269822137 | note | – – – – – – – – – – – – – – – – –
77f8fa36-9ff9-5781-9dda-3b0eac457e7f | note | CATEGORY: HP*
c7c58424-ccea-5b64-9369-58da60fa5532 | note | – – – – – – – – – – – – – – – – –
1e42bf7e-1c93-5276-8477-34a4ace4e1db | note | RESPONSIBILITY: Nominated Authority
0e08d093-f315-58c8-86dc-13b5af099b11 | note | – – – – – – – – – – – – – – – – –
aa1de47f-1913-591b-8c7d-6cfd7608ba26 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
f4841ad6-90a8-59a3-a6a5-db1b1da32e83 | date | Date Completed:
| checkpoint | 3.2 Set out the works for installation of pavement markings / raised markers
f1a31089-153d-548f-91ce-a51deecb3779 | note | REFERENCE: Vicroads 721.B05
ea4ee8fc-8bba-51e6-a6ca-1905e16e5f3e | note | – – – – – – – – – – – – – – – – –
f57f7b89-af3e-567b-aaa2-3f6d255ee6e2 | note | ACCEPTANCE CRITERIA: Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless a written exemption has been granted by the Superintendent
2dcfa4ef-9cdf-5bbb-a5a9-8e38c58ce03f | note | – – – – – – – – – – – – – – – – –
1562d565-6d10-5ebc-8560-7a2bdf2d3303 | note | METHOD: Survey Document Review
b20442fd-dfc2-5bf9-a4a0-196656f6d614 | note | – – – – – – – – – – – – – – – – –
c8381078-5346-5aa8-89b3-78352b1aa3b3 | note | FREQUENCY: Per Lot
ffdc4436-79c1-539a-9682-46497a074cef | note | – – – – – – – – – – – – – – – – –
d96a72d9-4dcf-56cc-9ab9-67f1db0e19c0 | note | CATEGORY: HP
b35e5ef4-0138-5c98-9231-4ef76cd57c95 | note | – – – – – – – – – – – – – – – – –
6384e5bb-15f3-558e-b028-e09b5d4c90bc | note | RESPONSIBILITY: Nominated Authority
8616c346-2762-550d-9c96-b93d044e1635 | note | – – – – – – – – – – – – – – – – –
927be1e1-ee2f-5415-814f-3099aafe9833 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
95b82eb6-9101-5993-82d1-e2e32a4b616a | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Construction Activities
| checkpoint | 3.4 Application of pavement marking / markers
654e6012-100f-56bd-a00e-18cb0fb8716e | note | REFERENCE: Vicroads 721
6fb20234-6571-5b65-8b6d-ace40379d72a | note | – – – – – – – – – – – – – – – – –
a6cdf044-a8e5-5a3d-aedb-125f9387aa55 | note | ACCEPTANCE CRITERIA: Check conditions for application of marking paint & materials.
b75619b5-136d-5822-90b6-ca3ef8e8d953 | note | (i) Paints and markers installed as per manufacturer’s recommendations.
f68fe9f5-b56b-53f6-a6f1-5de0f51d5155 | note | (ii) The same materials used with those nominated in the certifications.
ccd428b3-75d9-5c38-935e-bf88a10adc2b | note | (ii) All longitudinal lines have been applied by the nominated machine unless approved by superintendent
8972cd6a-e370-5302-8f7a-3df4ef290c71 | note | (iv) Verify markings are straight or with smooth, even curves where intended.
4686e30d-3041-56bd-8ac6-4e1217322fef | note | (v) Edges are clean sharp cut off.
565c4959-d2de-58ed-9688-12f2cbc155f4 | note | (vi) Markings uniform in appearance, texture, width & thickness & free from unbeaded areas
b831933c-f049-587b-aee5-17ce4cbd7b55 | note | (vii) Waterorne Paint & Glass Beads application rate conform to the requirements of Vic road 721.E01 requirements.
7c2d4b70-a59e-5e7e-b0a5-e38c6c8df085 | note | (viii) Markings are neat & free from traffic damage or other defects
2c24888c-b5a2-566d-9f8e-a3a95bfe1dfd | note | (ix) Marking protected from traffic until hardened
568c6e74-0632-5dd9-8a87-28fbc3428f50 | note | – – – – – – – – – – – – – – – – –
f62c906b-65a6-5688-b10c-bbb069a3343f | note | METHOD: Visual /Site Inspection & Document Review
bfeb578e-0e7d-580d-ab52-28dfc97a5dfa | note | – – – – – – – – – – – – – – – – –
9950ad89-25ae-5db8-b9b4-7ba5e96fb64e | note | FREQUENCY: Per Lot
6fa598ab-a110-5c9b-8a06-9afbf050214b | note | – – – – – – – – – – – – – – – – –
dada92ad-eb45-5499-b268-5dcc7a95e54a | note | CATEGORY: IP
6e706030-f956-52f7-8de7-90b057f74fda | note | – – – – – – – – – – – – – – – – –
8a5cd7fe-5031-5f1a-9d64-d395366d37d0 | note | RESPONSIBILITY: SE/PE/SPE
a98fd226-b912-5daa-8d45-d59eed668a9c | note | – – – – – – – – – – – – – – – – –
6a2b02dc-a24c-5bf5-95c2-1e523736b2da | note | VERIFYING DOCUMENTS: This ITP
f24c610d-eac7-5e49-998e-78fbe45094ef | date | Date Completed:
| checkpoint | 3.5 Tolerances for new marking/marker installations
014d8c32-4611-5bd0-a1bb-60391b416d4b | note | REFERENCE: Vicroads 721.A10 Table 721.A101
47c32c45-f472-5292-919b-ef4df7353b67 | note | – – – – – – – – – – – – – – – – –
d4e22362-b673-584f-aa4b-8d0e92ef8f2f | note | ACCEPTANCE CRITERIA: Pavement marking :
94355852-e01f-5958-b31f-d8d908af9e39 | note | ○ Distance between the centreline of the marking and the centreline of the set out mark - <30 mm
1a383df7-db1b-5883-8d05-b5995e11daf3 | note | ○ Distance between the centreline of the completed marking and the centreline of the previous marking - <15 mm
7fc6c0bf-3159-57e9-9b72-956963b38d90 | note | ○ Width of completed painted markings - ±10 mm of the specified dimensions
c394d8bd-7af1-554f-bff1-6c1520fd3883 | note | ○ Width of completed markings for long life materials0 mm to +10 mm
036c6c57-c275-5644-9a06-9b19620dc43a | note | ○ Length of completed stripes and blocks - 0% to +10% of the specified length
982d9b85-1c9f-568d-83ee-20d452ee2bde | note | ○ Gap between double lines - - 10 mm to +0 mm of the required 100 mm gap
cebed4ee-87de-5269-9645-e6c9d7b78a7f | note | Raised Pavement Markers:
28b94f64-0ebd-5c27-b28d-a121cb3210d3 | note | (i)Markers in line with broken segments
b3a7160a-f6d4-5016-b74f-dc271d7a1d39 | note | ○ Transverse position - ±25 mm of the centreline of segments
5e5ba1ae-6bab-5f78-a728-bb1fb12d8cc2 | note | ○ Longitudinal position - ±0.5 m of the specified position
a4413542-c051-57bf-aa61-fe7bf2e904c0 | note | (ii) Markers in a longitudinal group
ddcab53a-5f0b-51ef-bc0a-bb65131927b5 | note | ○ Transverse position - ±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
85339573-dce6-515a-a8a6-0abc07a5310a | note | ○ Longitudinal position - ±0.5 m
a8a66043-350c-5c96-ae7d-9242e9ad68b2 | note | ○ Spacing of markers within the group - 50 mm of specified spacing
5dc8666b-d2fc-517f-9be3-078755077a5f | note | (iii) Markers adjacent to an unbroken line
14a35de7-fd41-5ddc-954e-b8106aa01221 | note | ○ Clearance to edge line - ±5 mm of the specified dimensions
58eb32c7-4af2-526f-b096-0b74ed01d715 | note | ○ Longitudinal mismatch between markers in transverse pairs - <25 mm
5562daf7-a917-596d-a63b-49bdd8b0f2f0 | note | ○ Longitudinal position - Lesser of: 0.5 m or 10%
0a032f4e-5d9c-560d-bad5-acc480b48365 | note | (iv) Orientation of reflective markers - Lower edge of the reflective face at 85º to 95º to centreline of roadway or adjacent line
a2b7dca6-4f71-533f-bb49-fe94048d0c41 | note | ○ Thermoplastic profiled lines
dfddc90a-ece2-5c3d-a8a9-be5c02facb4e | note | (i) Tolerances on dimension
b7604007-9dbb-55ca-ad46-e1ff03c97dc8 | note | ○ Line width - +20 mm, - 5 mm
ec991d82-24e1-5f61-a95f-1998804d7dca | note | ○ Line height - +2 mm, - 0 mm
d40e0069-056b-54da-ba8e-f1b49750fe7f | note | ○ Extrusion breadth - +10 mm, - 0 mm
9c7190c6-2f8b-5ecc-a185-36a7f6d239bc | note | ○ Extrusion spacing - ±15 mm
cc40588a-274b-5145-93b9-04a6b60cc457 | note | ○ Extrusion shape - ±25 mm at any point from rectangular shape
9758808a-a035-5b59-a4e0-4b796cdbbb1d | note | (ii) Tolerances on position
bb793b75-4eec-5f1c-99d4-f3778c47a4e3 | note | ○ Distance between the centreline of the marking and the centreline of the set out - <30 mm
6287eb19-8174-51cd-9d27-c133580487b1 | note | ○ Length of the completed lines - - 0% to +5% of the specified length
03a09ab6-f904-53ea-ac4d-a9d9e1027a69 | note | ○ Longitudinal position of individual extrusions - ±50 mm of any previously applied profiled lining
ceaa0e78-449c-5952-948f-7af46aee1bcd | note | – – – – – – – – – – – – – – – – –
72150af7-1cdc-543f-92ee-8a7a1a0b45cd | note | METHOD: Visual /Site Inspection & Document Review
374932e4-828b-5a3a-99c5-79de0809003c | note | – – – – – – – – – – – – – – – – –
70d3ea4b-f772-58b3-8cf5-f834c8fcbbbb | note | FREQUENCY: Per Lot
f12eaa56-b218-50d3-96b9-6e59b13ab904 | note | – – – – – – – – – – – – – – – – –
d4f0d803-9a8d-52af-948d-cc573c448f2a | note | CATEGORY: IP
c9be1fb1-09d6-5983-8356-4ade79e0d358 | note | – – – – – – – – – – – – – – – – –
fe8a186e-f740-5133-9ec0-536cd07c0b92 | note | RESPONSIBILITY: SE/PE/SPE
dd0209a0-e5ea-5595-ab50-81d7c888cd47 | note | – – – – – – – – – – – – – – – – –
ed5ee6c2-ca59-5fd8-9256-e9a9354a1cec | note | VERIFYING DOCUMENTS: This ITP
1c4afe89-3077-5b1e-b027-bfd395b2aab2 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 3.6 Retroreflectivity Report
3aee0fc0-abcb-5584-9097-4976186f1f94 | note | REFERENCE: Vicroads 721.B06 (b)
15cd57e2-696d-5e8e-814e-0f78ffd38745 | note | – – – – – – – – – – – – – – – – –
e936276c-bbdb-56b7-a68d-2e16552b7c6b | note | ACCEPTANCE CRITERIA: Complete and forward Retro reflectivity Report in a form approved by the Superintendent showing the level of retro reflectivity determined for each test lot in accordance with the requirements of Clause 721.A12.
7d89a0af-f118-5c11-b3ad-07fc91eba076 | note | – – – – – – – – – – – – – – – – –
eee5f806-6b19-5d4a-89d0-5028449b4d6e | note | METHOD: Document Review
4207d87f-d197-5132-84b1-8141559e6465 | note | – – – – – – – – – – – – – – – – –
c77d2b66-cbd6-5079-9a37-2a022609f138 | note | FREQUENCY: Per lot
ceacda12-eec7-5957-97e8-19927149ceef | note | – – – – – – – – – – – – – – – – –
99564e49-6274-5cea-8756-2366402c7b51 | note | CATEGORY: HP*
e6a29025-cc54-5013-a60c-76d6851df228 | note | – – – – – – – – – – – – – – – – –
36fa9a79-1092-53c2-9277-a714b73fecca | note | RESPONSIBILITY: SE/PE/SPE
26f5d68e-7128-5192-9b87-14a70160f0ed | note | – – – – – – – – – – – – – – – – –
46b473cb-8a97-59e7-bb08-afd06306d3c5 | note | VERIFYING DOCUMENTS: This ITP
66458b51-b808-5db5-960f-42b6f02a528f | date | Date Completed:
| checkpoint | Job Completion Report
809432e8-2a99-5da0-88cb-f474ec4583b3 | note | REFERENCE: Vicroads 721.B06 (a)
4607aaa8-8db6-5364-9e2f-4b4ba37b7a83 | note | – – – – – – – – – – – – – – – – –
2ef8e1eb-7989-5e65-b279-0aeeb0f2552b | note | ACCEPTANCE CRITERIA: For New Markings the Contractor shall complete and forward to the Superintendent a Job Completion Report (Pavement Markings).
1d4ff86a-4d83-53bf-917a-7208b029d87a | note | – – – – – – – – – – – – – – – – –
90b77f68-8d89-5896-a575-1afb08a6d55e | note | METHOD: Document review
0a410cbd-340e-5bb3-96fd-c70e240a72d0 | note | – – – – – – – – – – – – – – – – –
246b7e3f-b5b3-5029-9127-0490853101bd | note | FREQUENCY: Per lot When applicable
92da376b-6470-5340-a02a-f71f23a18185 | note | – – – – – – – – – – – – – – – – –
a60cc62b-21ee-52b8-acd5-06edb6131141 | note | CATEGORY: HP*
7e384554-f1e7-506b-8a6f-4e30a805e0eb | note | – – – – – – – – – – – – – – – – –
66f67a24-ce5c-5140-8fd9-64a3df2a61ac | note | RESPONSIBILITY: SE/PE/SPE
52637fd2-6a51-51dd-9f16-7d1cc7594eaa | note | – – – – – – – – – – – – – – – – –
0f723e3f-c8dc-5c51-a9ef-c302f9081a79 | note | VERIFYING DOCUMENTS: This ITP
ed6b6b1c-ee23-5b66-9753-7b79a1591df1 | date | Date Completed:
| checkpoint | Final Inspection
d7253df6-206e-5baf-9dcc-ddb3f9886f39 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
e1a83f84-d2fa-5229-8caf-a9f9dc758859 | textbox | Name:
0af60caf-12a9-54be-b1b2-8013ce4af119 | textbox | Position:
56b381fc-894f-54a5-8f49-a73bb39a8642 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-068-CIV-Camms-Rail Delineation Fencing-Permanent Rev 0 | itp | ITP-068-CIV-Camms-Rail Delineation Fencing-Permanent |  | 39bf0162-ac6c-4327-b2c4-cb88edad1692
| section | Referenced Documentation
| checkpoint | Referenced Documentation
a57e6373-6c84-5438-a7bd-fcc223e5ac78 | note | Document Title: ITP-068-CIV-Camms-Rail Delineation Fencing-Permanent
1f3232ef-08c9-5954-a9a6-163c65b9708a | note | ITP Description: Camms-Rail Delineation Fencing-Permanent
0c441597-8c63-54cd-81bb-8fcbdd91534f | note | ITP number: 068
ce63fcb6-f875-58ff-b67e-72b88bfa50da | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
94eb38ea-bc56-5aff-8262-f52e74942c25 | note | Discipline (e.g. CIV/STR/RAIL): CIV
8b0e58d8-c7ec-5ad5-884b-88f5608057e3 | note | Revision Number: 0
553fbc11-0a60-5023-8ce3-c5e6a8f5ca6a | note | Revision Date: 1/09/2023
2d3ade14-ab27-516e-9b79-6070481626a5 | note | ITP created by: Diana Delac
8e1b54c1-5ab8-5061-bcf0-34112ffc9819 | note | ITP approved for use by: Victor Mira
04ffa2de-5165-54ec-8769-a05939ae3c18 | note | 1.1 Non Dependent
dc3eaf52-96b3-5639-9f1a-45756693cbfa | note | Reference: IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025, VicRoads Section 610, VicRoads Section 630
| section | Materials
| checkpoint | 2.1 Concrete
03482413-7877-55f5-a81a-b19e241bc40d | note | REFERENCE: IFC Drawings Section 610.07 Table 610.071
575b9ec8-a122-5acb-aa9a-74aa6ee07414 | note | – – – – – – – – – – – – – – – – –
8eba0b82-dd90-5361-ab17-f2e7fdec530b | note | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
b6cf38ba-7c87-5e70-9f3a-8d5a962194f3 | note | ○ 32MPa concrete to be used as per IFC drawings.
7c07d845-acdb-5a45-9be9-981ab32d759f | note | – – – – – – – – – – – – – – – – –
6446ac3f-fc69-5e6c-bd13-97ba3b6ae42b | note | METHOD: Document Review
2a95a6dc-56b3-53ac-8c81-c9fe2b9870d9 | note | – – – – – – – – – – – – – – – – –
4a627530-1b68-5112-ba75-426fefd7d84e | note | FREQUENCY: Each Mix
a151fd9c-7dcc-5836-97c1-a4e34a97412f | note | – – – – – – – – – – – – – – – – –
9bcd73a0-2dd1-5f65-beb9-6bc03c6492cb | note | CATEGORY: HP
483fe473-264d-5441-992f-38a78ca84d1a | note | – – – – – – – – – – – – – – – – –
3d349b35-3199-5a2c-8995-08660047321c | note | RESPONSIBILITY: SE/Site Supervisor
d9cd75de-d90d-5c48-8846-df63ca2c19cf | note | – – – – – – – – – – – – – – – – –
d8736a69-41b5-55b6-9ae3-f8c8792e266f | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
6c3e6cca-587c-5455-9331-110e43316c52 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Steel Columns, Cladding, Handrails, etc
19b5b0d8-05cf-58e7-b3d1-73c2ce1735fb | note | REFERENCE: IFC Drawings AS41000, AS1163
28dc68f2-c31e-5013-91da-2f17a3d8131e | note | – – – – – – – – – – – – – – – – –
2d0c4e75-35f9-5926-8995-ba554c445b8e | note | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
ba909e5e-208a-53a3-a932-3fc02592616b | note | ○ Steel section sizes must be checked on site.
d8008cad-3ff2-5ff1-95a7-64202a1d03bb | note | ○ Steel posts to be CHS with a grade of C250
136929e9-28bb-5f05-9edd-7cc88de2a691 | note | – – – – – – – – – – – – – – – – –
724bf44d-b6f5-59d8-939f-245fe9d3efbb | note | METHOD: Document review, Visual and Measure
d9c5a5d1-ea9e-507f-ab2f-08396bc9e765 | note | – – – – – – – – – – – – – – – – –
7a1dd9b2-6b7c-58b4-b624-1111b4eb8931 | note | FREQUENCY: All elements
6fdeae3f-a3a7-58ec-908b-60e2ef84ab72 | note | – – – – – – – – – – – – – – – – –
267cf75c-aef3-5ecb-91c7-2708e150d745 | note | CATEGORY: IP
c92ac14c-9103-5dc0-99e2-5f88cd6e5469 | note | – – – – – – – – – – – – – – – – –
996493de-fc60-5a8f-b1bd-2feb4218ea2d | note | RESPONSIBILITY: SE/Site Supervisor
2e429866-204b-554f-aad4-ee4bdcf07760 | note | – – – – – – – – – – – – – – – – –
2a9bfed0-a8da-5d91-bb32-a23f9712dffc | note | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
5843432c-9707-5d72-82a1-929e2411ef90 | date | Date Completed:
| section | Pre-construction / Pre-installation Activities
| checkpoint | 3.1 Survey Set-out
943f3233-04d8-5a02-87ae-3b72fbb4709e | note | REFERENCE: IFC Drawings
be937814-dc20-56de-b537-70c431edee3f | note | – – – – – – – – – – – – – – – – –
a8a390c9-93ab-59b4-a837-5edb6d574f5f | note | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
73e6be46-b648-53af-a08c-68ed9546fa26 | note | ○ Offset checked against the running edge prior to installation of posts.
e83e6502-14c8-596e-b0fc-9c9e624de159 | note | – – – – – – – – – – – – – – – – –
da2f40a2-8708-5af9-a5d2-ca6bc5752af9 | note | METHOD: Measure, Visual
2808c498-ff36-5ac4-80fe-f2068e5a3395 | note | – – – – – – – – – – – – – – – – –
a00f745c-4fd9-581d-8406-574a3bc7fef0 | note | FREQUENCY: Each element
8e4e5bd9-f80b-5bf1-8d71-146a37c420ce | note | – – – – – – – – – – – – – – – – –
4c8bc3f9-6321-5594-be0a-192d1139e9cd | note | CATEGORY: IP
94e6c9b7-da97-53b4-a097-bbd8a34a2a45 | note | – – – – – – – – – – – – – – – – –
219794f9-26b2-52d6-a1bd-e156ca8643d3 | note | RESPONSIBILITY: Surveyor, SE/PE
5a2da160-ff3c-5ea4-a6d0-c927aa346d37 | note | – – – – – – – – – – – – – – – – –
3dc1c89b-3d7c-561a-9f41-4f206dd94af5 | note | VERIFYING DOCUMENTS: This ITP
b31c8904-d1a4-54b7-9c32-122ef9d708a7 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 4.1 Excavation works
be22943f-6191-5163-a813-dcf2eda28968 | note | REFERENCE: IFC Drawings L1-CHE-STD-005
365c99b9-1575-5640-af30-b7f27c245f7b | note | – – – – – – – – – – – – – – – – –
98a13656-cfc4-5070-9700-1a52e0162cd5 | note | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine footing of existing structures.
da5a4a82-f202-58ab-81c0-22caa78c6355 | note | ○ Follow asset owners guidelines for work around their service.
cba62071-249a-5cd1-a39c-16547479b9de | note | ○ Excavation must use Non Distructive Digging in the rail corridor
a540a740-6b1b-540b-a132-5a5bba2f2314 | note | – – – – – – – – – – – – – – – – –
f6fdd09c-eab1-5283-b415-34b587549ab4 | note | METHOD: Visual
a27775b5-d3af-5b32-b82a-149e57519369 | note | – – – – – – – – – – – – – – – – –
6c79df3f-8b8e-5ee8-9003-515930934733 | note | CATEGORY: IP
fb138e74-438c-54c1-b896-80722b6bc5a4 | note | – – – – – – – – – – – – – – – – –
5e197712-25fc-50c1-bd85-aef995edc73d | note | RESPONSIBILITY: SE/Site Supervisor
42bec5b2-5801-559a-8d56-64ef041b053d | note | – – – – – – – – – – – – – – – – –
4c6b1a8f-7be8-50b4-8f8f-1afd19c08a4e | note | VERIFYING DOCUMENTS: This ITP
863b3f46-35fb-536f-8fab-af1d8415b525 | date | Date Completed:
| checkpoint | 4.2 Ground Conditions
9dd176d1-089e-5032-a088-b12c1cf822a7 | note | REFERENCE: IFC Drawings
306a8174-b45a-5e0f-999b-6c899ab04f7f | note | – – – – – – – – – – – – – – – – –
677e3559-fbdb-5c1e-b788-174a59bce7e5 | note | ACCEPTANCE CRITERIA: All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
ebeda8f3-7d68-53b7-9287-aa3b763c01f0 | note | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
369da022-a256-5651-8269-513f3462da6d | note | – – – – – – – – – – – – – – – – –
446e4d2a-a64a-568a-bb20-05166ab8adc1 | note | METHOD: Visual
af307f27-3749-5aad-9177-4724264e712c | note | – – – – – – – – – – – – – – – – –
0e217f49-0596-588c-b181-70e9a5c1204c | note | FREQUENCY: Each post
b1fd1597-7606-5106-ade5-4a3c0d3db1fd | note | – – – – – – – – – – – – – – – – –
bac28b7f-4b62-55be-bcdd-57da3615048d | note | CATEGORY: IP
854db2ce-e79d-5c2f-a1a9-1b78f2c00425 | note | – – – – – – – – – – – – – – – – –
6a8eb069-0963-5b57-a3d1-1a68e5cbc08a | note | RESPONSIBILITY: SE/Site Supervisor
c6762728-a084-5c4f-9429-a6d61cd57cde | note | – – – – – – – – – – – – – – – – –
2a37fd14-e237-5083-b03c-cd4301786564 | note | VERIFYING DOCUMENTS: This ITP
35d09f8a-1846-5e5b-a8c9-b5ab2c8f4c07 | date | Date Completed:
| checkpoint | 4.3 MTM OHW Structures
fc834490-c3b9-52c7-9180-61544e35a902 | note | REFERENCE: IFC Drawings L1-CHE-STD-005
b3211c98-2640-5155-b0b4-7ab0a178e1f5 | note | – – – – – – – – – – – – – – – – –
e696a3ba-cf5f-5fbf-bc03-5db891efe1a0 | note | ACCEPTANCE CRITERIA: Fencing must be a minimum 2m away from OHW Structures.
406b9a2b-045f-55b8-b06e-808555f7a6e0 | note | ○ Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level.
056d7d50-8a5a-5eeb-8af4-2ec67addd809 | note | – – – – – – – – – – – – – – – – –
78118626-7bd2-587c-a85d-36549ca17464 | note | METHOD: Measure
b0797988-fcb9-5b32-a539-ba42a110e5bb | note | – – – – – – – – – – – – – – – – –
be0044c8-c1b0-5be1-a129-5ea02667d860 | note | FREQUENCY: Each Overhead
bd744bdd-48af-5726-ba8d-4b068b89c5bf | note | – – – – – – – – – – – – – – – – –
820b3625-0297-5cbf-bc00-c4a2f30ddcba | note | CATEGORY: IP
c0f47115-b33d-564e-9c0c-df7daf01a848 | note | – – – – – – – – – – – – – – – – –
4ab9d08e-e84a-5f7f-a1db-3e697c9edbb8 | note | RESPONSIBILITY: SE/Site Supervisor
0f4eb9ea-0a9b-5944-b7e8-a8a5a1b588c5 | note | – – – – – – – – – – – – – – – – –
21e8a96b-b882-5a4f-a310-695640b13ad0 | note | VERIFYING DOCUMENTS: This ITP
6d7c513a-8e17-5d2d-8c0c-bdb0cf53dcae | date | Date Completed:
| checkpoint | 4.4 Fence Post Foundation
e69fcf15-0eb3-54d7-93fe-a94d81f406a9 | note | REFERENCE: IFC Drawings L1-CHE-STD-005
ba5969b8-1ce8-57da-b65b-a5df83bcb361 | note | – – – – – – – – – – – – – – – – –
9118114c-5c86-5139-8c42-544c49caf236 | note | ACCEPTANCE CRITERIA: 32MPa concrete.
6c204d28-521b-5cae-a978-890b2ac59713 | note | ○ Footing to be a min. 1m clear from proposed TTC footing
fb0380e3-58a9-57f3-9eaf-97950fb981b7 | note | Typical Footing:
4f1e4824-fbe6-5fff-8e39-4bf4e9d54b7a | note | ○ Footing dimension 900mm deep, cross section 300mm X 300mm
e92e1aa8-5d80-5d74-8fd9-207a5acea8e6 | note | ○ DN80 MS Pipe (88.9 X 4CHS) to be installed full depth.
1bd83c99-f518-555a-a266-78393598ff2c | note | Alternative Strip Footing:
ddf0f96c-dca4-5007-aa95-071a83c154f7 | note | ○ 800x800x300mm thick
0a1b175c-d867-599b-801c-f9fcb03b965e | note | ○ 101.6 x 4.0 CHS sleeve to be cast into footing.
1918c9c4-3b71-5c3a-a71b-9415af5d4448 | note | ○ 150x150x5 thick base plate welded to sleeve.
0476b6d5-548a-55b8-b677-3bfd560d9c35 | note | ○ Refer to IFC drawing for reinforcement details.
e3eba1bc-fc41-5da0-93e2-145727a81971 | note | – – – – – – – – – – – – – – – – –
b4451f33-b24e-5672-b024-effc0e4df43c | note | METHOD: Measure
1f504bff-bcb0-54a4-b787-ac4564b62a1a | note | – – – – – – – – – – – – – – – – –
b2a170bb-781c-5639-bb04-570ebd1da17f | note | FREQUENCY: Each footing
49a55460-ebf4-59ee-bcd4-f9ebc643d881 | note | – – – – – – – – – – – – – – – – –
4bc0ac54-7f5a-5427-a6a2-4b943317a51a | note | CATEGORY: IP
b61c94a4-1bf3-501e-bb96-c14fc9540e23 | note | – – – – – – – – – – – – – – – – –
bf1c3828-1ac5-5795-a3d2-032440acf948 | note | RESPONSIBILITY: SE/Site Supervisor
ab01d0de-f7b0-5ab3-94fa-86d44519a336 | note | – – – – – – – – – – – – – – – – –
666900c3-8b94-5562-95ef-f5e1c03aaa41 | note | VERIFYING DOCUMENTS: Post and concrete dockets
4129ec96-5702-583e-9dae-974bbf7b3262 | date | Date Completed:
| checkpoint | 4.5 Fence Post Installation
6bb64549-92b0-58c6-b2bb-719e12e2bec3 | note | REFERENCE: IFC Drawings L1-CHE-STD-005
fce78729-15b1-5b22-81ae-b2ae5812cd9f | note | – – – – – – – – – – – – – – – – –
b27bd061-e683-5421-9c5b-ef27dce0f423 | note | ACCEPTANCE CRITERIA: Maximum post spacing to be 2.7m ± 250mm, two spans at 1350CTRS at gates, at the ends and at Refuge bays.
5780c8a3-8499-5473-9986-658e904be349 | note | ○ An individual fence space may be increased to Max. 3100mm locally to avois clashes with services.
c3cff7b5-dad5-5b05-b64c-a99ba31e0aad | note | ○ Minimum offsets from centre of the rail to the fence: 3000mm
d891245b-9d8d-500d-b230-cb9a94d2dfe2 | note | ○ Alignment tolerance: +20mm to -0 (- being closer to the track)
b37fc71f-5d31-53a9-858e-cd1348a0dcee | note | ○ Max. post height 1800mm above ground level.
2f06626b-19ee-5372-89a5-5d1fa599685f | note | ○ Vertical Tolerance (Hight Risk Areas): ±20mm from the design line.
ca4e4fca-c5db-5bad-8597-dfe38174b2a8 | note | – – – – – – – – – – – – – – – – –
e0cab40f-e43e-5ea2-82f5-95359b254511 | note | METHOD: Measure
16aedc4d-a647-56d8-b42e-dd432eb3751e | note | – – – – – – – – – – – – – – – – –
f27a8811-3444-50b6-b050-0bd8a645a32d | note | FREQUENCY: Each post
8ae76887-72f1-56ec-9c29-f8e4c9889696 | note | – – – – – – – – – – – – – – – – –
3a572a1d-a11c-5a32-9240-7873abe09e2e | note | CATEGORY: IP
25c20aa9-41da-5b1d-8701-4ff2b1d48986 | note | – – – – – – – – – – – – – – – – –
edf7a07e-1be6-5687-92eb-ac93170d2a95 | note | RESPONSIBILITY: SE/Site Supervisor
527884be-110e-5f56-a7b4-ee7e05ee2cb0 | note | – – – – – – – – – – – – – – – – –
61b6cc04-3f6f-5380-9a09-f84a3116c548 | note | VERIFYING DOCUMENTS: This ITP, Concrete Dockets
07e62123-e888-5ffa-8d63-7642e1ebb2a2 | date | Date Completed:
| checkpoint | 4.6 Chain Wire Mesh Installation
eae15eeb-066a-588e-be6b-384d9dc0577f | note | REFERENCE: IFC Drawings
de66fd0b-6a28-597d-81a0-5404ed73fd39 | note | – – – – – – – – – – – – – – – – –
07277ce1-3ea1-5fe8-affc-7fc1069ed3a4 | note | ACCEPTANCE CRITERIA: Chain-wire mesh 1800x50x2.50 to be fixed to fence post with 1.57mm tie wire.
3a8272bf-169a-5a0c-935b-16f520d72099 | note | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
faf544f3-90bd-563d-99de-00477f399369 | note | ○ 3 NO. W10Z TWIN-STRAND 3.15mm DIA. WIRES TWISTED BETWEEN POSTS. TENSIONED TO 1kN.
3df28dce-c65a-54ee-80b3-8866f7b91f1c | note | – – – – – – – – – – – – – – – – –
1dd63361-fce8-5aef-b8d5-07abd2ce9ede | note | METHOD: Visual
1495472a-49e6-54d4-8dff-5138ff023530 | note | – – – – – – – – – – – – – – – – –
9f6799c8-5a60-5069-a1a8-d88ef59f2647 | note | FREQUENCY: Each element
222c237d-7108-562d-ad9b-98598244c145 | note | – – – – – – – – – – – – – – – – –
c73bedf9-dba5-5ceb-a026-1e709f1f584a | note | CATEGORY: IP
2bf82f74-0d5e-5865-8b89-78115859fef0 | note | – – – – – – – – – – – – – – – – –
0e4102b7-5fea-5bd7-b788-aa42ca43b5ae | note | RESPONSIBILITY: SE/Site Supervisor
7f74e7c7-fd08-53cf-996c-2c170f971ac7 | note | – – – – – – – – – – – – – – – – –
b03177e2-f135-5f61-a2c8-39f868fe5a54 | note | VERIFYING DOCUMENTS: This ITP, Delivery dockets
c8b7855f-d6c3-53cc-b514-b529d828f172 | date | Date Completed:
| checkpoint | 4.7 Bracing
152af2f5-c557-544d-b5c6-dcda60d85479 | note | REFERENCE: IFC Drawings
67a77e66-ec18-5062-8a31-8eca148c0c57 | note | – – – – – – – – – – – – – – – – –
ccf24918-b9e0-59ab-81cf-149854a2e8b9 | note | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
9e43ea7c-e4e0-5775-bf53-b12c964898af | note | ○ Bracing to be installed on both sides of the fence at the fence corners.
0d857e09-e423-57bd-82dc-d489a8b86d58 | note | – – – – – – – – – – – – – – – – –
28668059-7b9e-5f12-a141-bebcb590c8c3 | note | METHOD: Visual
473126a9-b51a-5d12-a89f-71e91636ccaa | note | – – – – – – – – – – – – – – – – –
5e29d34d-d3ab-57a1-b56f-c759385c657d | note | FREQUENCY: Each element
cfa74ad7-4201-5659-b6c4-070212169424 | note | – – – – – – – – – – – – – – – – –
34b115f0-c838-5e7d-a41c-28d37eb16508 | note | CATEGORY: IP
3912b956-fe24-5c9c-82a5-35ee25debd74 | note | – – – – – – – – – – – – – – – – –
04a142e7-a214-5e7b-84b1-ecc23c3a2b93 | note | RESPONSIBILITY: SE/Site Supervisor
1435c5a3-fcb2-5d80-ae33-6013d7804d8d | note | – – – – – – – – – – – – – – – – –
0ed6b7f2-47c6-52e4-b5f9-f832e6df731f | note | VERIFYING DOCUMENTS: This ITP, Steel delivery dockts
bcb839dd-e323-5ccc-a3bd-06b982e730cd | date | Date Completed:
| checkpoint | 4.8 Refuge Installation
177b0340-14aa-56d5-a3f0-91f4b441a82f | note | REFERENCE: IFC Drawings
a50a6e72-ef04-5519-9748-68d8266b0bc1 | note | – – – – – – – – – – – – – – – – –
830bcd4c-f7d1-5fde-bc8f-06d775034135 | note | ACCEPTANCE CRITERIA: Refuge Access to only open from track side.
2d70ca02-3fc1-5f7d-9e88-4866411c1444 | note | ○ No chain wire mesh to be installed at refuge access.
7a6ce0f1-b331-5b06-bb33-b956e6703dc5 | note | ○ Refuge Access to be located every 20m max. along the fence.
cc671801-f7b5-51e1-b517-a9f0657e3d33 | note | ○ 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
db87ef8d-67d9-59ec-aa0a-1e8f9a3cff7b | note | – – – – – – – – – – – – – – – – –
81c1c25b-1044-59fc-a345-47dca3290225 | note | METHOD: Visual/Measure
338b0eca-9c50-52b3-bc1a-acf23536692f | note | – – – – – – – – – – – – – – – – –
79370984-b87b-5e25-b218-aeda6b5c92f5 | note | FREQUENCY: Every 20m Max.
2206273c-1e60-5961-bc6d-bf27421e0e97 | note | – – – – – – – – – – – – – – – – –
1bfc3e0b-ad05-5248-a05e-97d3732ff7ab | note | CATEGORY: IP
eb5c8513-50d5-5477-954f-80f9fc701265 | note | – – – – – – – – – – – – – – – – –
f1ac2919-c58d-5a4b-9d8a-e2fbc53c76a2 | note | RESPONSIBILITY: SE/Site Supervisor
293b6e7f-54d4-552c-ac5c-793e2847a815 | note | – – – – – – – – – – – – – – – – –
406f810b-65b9-5ae6-afec-b102277588b7 | note | VERIFYING DOCUMENTS: This ITP
daeea0b1-ded1-5dc0-b1d0-11ce77255ed4 | date | Date Completed:
| checkpoint | 4.9 Gate Post Foundation
7c807239-272f-5681-af6a-caa114e5ce7a | note | REFERENCE: IFC Drawings
444e54c9-cbdc-50b8-aa1d-7fb31bd6ccf6 | note | – – – – – – – – – – – – – – – – –
b61fea4c-0167-5adc-a7a8-60fd298dbeb7 | note | ACCEPTANCE CRITERIA: 350mm DIA. PILE
603f6bca-08b3-58b3-9035-b391e9bae199 | note | ○ 1300mm DEPTH
b4e65452-3cc0-5869-aa7a-69575df8cbfe | note | ○ 1200mm POST EMBEDMENT
a7f4c0cf-918b-5fcb-aec1-177dfdeb7794 | note | ○ 101.6 x 4 CHS GATE POST.
472350f0-2823-5d40-8e7b-ed9bb2181acf | note | ○ 1200 EMBEDMENT
86d54c53-79cc-50db-b116-3a6920eccf1f | note | ○ 32MPa Concrete
6e3cbf6a-bd73-5afd-ba2f-1fb94f6a4038 | note | – – – – – – – – – – – – – – – – –
8a1f0f87-e3f3-5a40-800b-9cca76d7fafd | note | METHOD: Visual/Measure
4c76021a-201e-5955-9537-a6a2a1930a09 | note | – – – – – – – – – – – – – – – – –
d0840f48-1513-5d71-b28a-54fe56c8b6cc | note | FREQUENCY: Each footing
e399e4f2-1e30-5e87-be61-4a685aa1e66a | note | – – – – – – – – – – – – – – – – –
0822206b-e981-5b5d-8309-611ca55f0dec | note | CATEGORY: IP
1721b3a9-e70a-515c-ab3c-b260eaba1abb | note | – – – – – – – – – – – – – – – – –
b844bbc1-a158-52bf-ab4b-49c9b0331a25 | note | RESPONSIBILITY: SE/Site Supervisor
3344fcf0-ee4c-5b7b-aaf5-9b5b33045d79 | note | – – – – – – – – – – – – – – – – –
b319128c-1f44-544e-914b-5c1057dc255e | note | VERIFYING DOCUMENTS: Post and Concrete Dockets
0ded8955-45c9-5a69-bc93-2ef46b172dd2 | date | Date Completed:
| checkpoint | 4.10 Gate Installation - Post
5dedf914-c935-5547-838f-982493e2fc9c | note | REFERENCE: IFC Drawings
ba73d9e9-9f6c-5938-8367-09126eac0137 | note | – – – – – – – – – – – – – – – – –
9249b28d-baa2-5d8a-a3d8-47f61819a400 | note | ACCEPTANCE CRITERIA: 3000mm nominal clear between the gate posts.
dd1858d7-b77b-5356-a234-d330cd1280ac | note | ○ Minimum offsets from centre of the rail to the fence: 3000mm
fd9fe2f3-e0b4-5e5d-ad53-5194cee6329a | note | ○ Alignment tolerance: +20mm to -0 (- being closer to the track)
7f3c557b-ae2d-58bc-8540-ea2b6e3027ea | note | ○ Max. post height 1800mm above ground level.
0ea65928-5bea-5813-8abf-95a7421f598d | note | ○ Vertical Tolerance (Hight Risk Areas): ±20mm from the design line.
361ad3f8-9c25-5a84-be7f-ba401d38941d | note | – – – – – – – – – – – – – – – – –
fd4e0b07-1fff-5dac-a5e7-331929b58650 | note | METHOD: Measure
3995e8d2-ae3d-5b82-a395-f8afd91a700a | note | – – – – – – – – – – – – – – – – –
0013037f-ece0-5ee5-ae92-b0b4dc1159b0 | note | FREQUENCY: Each Post
ac3c165e-4b83-5fe8-b601-517223b3f695 | note | – – – – – – – – – – – – – – – – –
9c1ca540-657c-5c5c-98bd-40efc585dc3f | note | CATEGORY: IP
770bdd69-53a1-54b6-b455-da27a2af4f62 | note | – – – – – – – – – – – – – – – – –
44d2d5a9-bb3f-5e96-86d2-13af3d22002f | note | RESPONSIBILITY: SE/Site Supervisor
7cc41873-4e2f-52f9-8db7-75bd949c8645 | note | – – – – – – – – – – – – – – – – –
b4bb3a83-8b1c-5690-8c4e-a9226ba21c2d | note | VERIFYING DOCUMENTS: Delivery Dockets
680f408b-7249-5db1-a73d-8a70f1eede70 | date | Date Completed:
| checkpoint | 4.11 Gate Installation - Gate
edb72685-da44-56fb-aaad-d662c2c2c81d | note | REFERENCE: IFC Drawings
5d06e0ec-6244-5929-a7a4-9221850f9a65 | note | – – – – – – – – – – – – – – – – –
9ae315b0-da20-53da-8970-5669e01a6206 | note | ACCEPTANCE CRITERIA: 2 NO. 1800mm (H) x 1500mm (W) ROUND TOP GATE
416df41b-b1cd-5a33-939e-7771e37410dc | note | ○ MINIMUM 2 NO. FENCE BAYS MUST BE PRESENT EITHER SIDE OF GATE TO ALLOW BRACING TO BE INSTALLED.
9b09ff7e-0e60-5ca5-9307-ed49548f8d52 | note | – – – – – – – – – – – – – – – – –
6fad09e5-b58f-5529-8466-75c6bac622ef | note | METHOD: Measure
c8f5bd81-9cd7-5bb3-8d6e-dfc421c5e408 | note | – – – – – – – – – – – – – – – – –
4600f9cd-5a53-5fd8-9f1a-af373488c6e1 | note | FREQUENCY: Each Gate
e244ede1-68bc-5a1b-ad9e-27aa7c29739e | note | – – – – – – – – – – – – – – – – –
fccec112-8d2e-5150-a8d8-6022f9155215 | note | CATEGORY: IP
f25dddf6-ef54-56c4-90cd-99d143709fea | note | – – – – – – – – – – – – – – – – –
d6517d19-8cc8-5fa4-8b0c-4020d8f3c07a | note | RESPONSIBILITY: SE/Site Supervisor
457a176e-204c-5baa-8a43-4cd2b12d89ae | note | – – – – – – – – – – – – – – – – –
d5f20e9f-f8a5-569c-99e2-3766327e0fa9 | note | VERIFYING DOCUMENTS: Delivery Dockets
7d2f7906-d688-55e1-a892-c8780a9b6bd4 | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 5.1 Fence Height and Track Clearance
4999f63c-c05c-5937-8e58-aa606a8f7bf6 | note | REFERENCE: IFC Drawings
161252b0-e8e5-5eef-8a6b-6ea5ce38e471 | note | – – – – – – – – – – – – – – – – –
73456859-2594-54e8-a803-02295df40104 | note | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
050e4e33-ee18-562f-b72c-e0755ebca835 | note | – – – – – – – – – – – – – – – – –
e6717125-fb10-55ce-bdc2-c3e664e19018 | note | METHOD: Measure
bc9bc939-0839-5b51-94f0-c575a1427b04 | note | – – – – – – – – – – – – – – – – –
af45a5af-fa0c-50b9-a6ac-085b53746ad3 | note | FREQUENCY: Each lot
4d06612d-41be-5eec-95c1-1f92215067fb | note | – – – – – – – – – – – – – – – – –
332d683f-2633-59de-b7bb-ca6de7f997f2 | note | CATEGORY: IP
0c5a70ff-d8ea-5287-8e22-7c1a0e3a889c | note | – – – – – – – – – – – – – – – – –
fa3b7cc0-3738-53f3-8be7-0592c1655a98 | note | RESPONSIBILITY: SE/Site Supervisor
294d17c8-b2e7-5325-8eb9-de40fe2c21f6 | note | – – – – – – – – – – – – – – – – –
b1c2a6e2-5fdf-5419-9ead-7f094e2d60d8 | note | VERIFYING DOCUMENTS: This ITP
a507b197-c211-5903-b947-2f3512aaf161 | date | Date Completed:
| checkpoint | Final Inspection
3a793c8f-af61-56f7-afec-be4ea827ba10 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
7f77ff3e-b23b-5e16-9f12-516627622817 | textbox | Name:
05ae69e3-e890-5e54-86d2-6fd587a11dc6 | textbox | Position:
765a7a80-ac34-5ec1-b77b-35e742042f84 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-069-CIV-CAMMS-Signage Installation Rev 0 | itp | ITP-069-CIV-CAMMS-Signage Installation |  | d2c17ea2-3d76-4d14-a0a2-bec3f21a5f11
| section | Referenced Documentation
| checkpoint | Referenced Documentation
e1b7dad7-b65a-5b5d-92f0-1df183efa6e8 | note | Document Title: ITP-069-CIV-Camms - Signage installation
30520f0f-10ec-5433-ba36-ce095da02b36 | note | ITP Description: Camms - Signage installation
e1c71045-1a6a-5874-bf3b-587793180ade | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
6cc3422c-8440-5638-9503-f2863720a016 | note | Discipline (e.g. CIV/STR/RAIL): 069-CIV
aacaea4c-3188-55e2-a459-67ad164bc17a | note | Revision Number: 0
870d7a49-ad73-5976-b1d7-315ccf4fb4c0 | note | Revision Date: 22/11/2023
2ce6a507-f5e4-5ef9-89f4-49d023b5d3b5 | note | ITP created by: Chloe Mitchell
2c2d8919-5a98-5d2f-b9a9-73fd0a52d977 | note | ITP approved for use by: Victor Mira
540f628f-e9cf-51dd-9558-5794536fe11a | note | 1.1 Non Dependent
9e29beaf-05df-57f7-8ba3-5c8b47ffa0cb | note | Reference: VicRoads Section 860 (Feb 2023)
4e448a71-08ca-58ca-9fc4-93b603114ff7 | note | 1.2 Non Dependent
fa79f239-2dce-5dd0-b203-a0a079a18416 | note | Reference: VicRoads Section 714 (Feb 2023)
f9c7fa17-1460-5dda-80ff-fe3737da8896 | note | 1.3 Non Dependent
2f724b04-3d62-5ad5-9979-f378e58c7adf | note | Reference: VicRoads Section 703 (Aug 2021)
30c9fb75-98d9-5da3-b6be-7e929f107a84 | note | 1.4 Non Dependent
f76d1053-56b2-5808-b39c-4023b1a954e8 | note | Reference: IFC Drawings
f8f2da67-1385-51b5-970a-88197eaf8d64 | note | 1.5 Non Dependent
a89fefa9-d5e1-546b-995f-2f10b5c90488 | note | Reference: AS 1742.2:2009
| section | Preliminaries - Materials
| checkpoint | 2.1 Manufacture & Supply of Signages and Posts
2a946d72-c75a-57c9-98ad-d07e12eb5445 | note | REFERENCE: Section 860, Section 860.06, Section 860.07 Table 860.071, Section 714.03, Section 714.06 IFC Drawings
b28c0b03-1a37-5d81-93a1-5ade25c3842b | note | – – – – – – – – – – – – – – – – –
48dde61a-2c4a-5e63-ade9-6c7065cbd7e6 | note | ACCEPTANCE CRITERIA: Signs are to be manufactured in accordance with Section 860 and IFC Drawings
61680c4a-aa11-59e8-bb7f-09f37666a2b1 | note | ○ Warranties for the Signboard and Components, Sign Face Material, Giving of the Warranty and warranty Claims to be in accordance with Specification 860.07 and Table 860.071.
51d3ce2a-9720-589d-937c-80c4ee29e333 | note | ○ Packaging and Storage of Sign to be in accordance with Specification 860.06.
6aec8159-26bf-5892-a41b-96348887975f | note | ○ Signs and components shall be handled and transported so as to prevent damage.
9edf1967-6208-5633-95cb-bf48a68ededd | note | ○ Signs shall be stored vertically in such a manner to prevent damage to the sign face, edges or components, taking into account any recommendations of the sheeting manufacturer.
44f72774-6cad-5e98-b5b0-e98444ae387c | note | ○ Post details shall be as shown on the Sign and Post Schedule and in accordance with the VicRoads Traffic Engineering Manual Volume 2. Steel posts shall be either:
ad980fca-ee78-54ba-8db4-2da2bb2f00d4 | note | – Hot dipped galvanised; or
5dae1bf3-846d-5a4e-ac67-34965bbd75ae | note | – Pre-galvanised prior to forming
2e5e844c-aad6-58a2-b72b-d5f74e8b0825 | note | Attach: TeamBinder Material Approval Ref No
35a5e061-ca83-5c62-a37b-20ebb164f27d | note | – – – – – – – – – – – – – – – – –
d0948653-e3c4-5d89-859c-24c825a52687 | note | METHOD: Document Review
b8a09b72-9c27-59a3-8841-1ed59898c1ed | note | – – – – – – – – – – – – – – – – –
7c75c70b-1634-5517-8f1e-8c541092f5ed | note | FREQUENCY: Prior to works start
e2983112-fa3b-5e24-9ec9-0e0088c6a9c2 | note | – – – – – – – – – – – – – – – – –
45c419f9-4f9c-5227-95d4-36dff3b8bb4b | note | CATEGORY: HP
47098fb4-e4fe-596b-b80a-849dbca7cd19 | note | – – – – – – – – – – – – – – – – –
b8f2535b-e1bc-5307-97cf-3a335b260dc5 | note | RESPONSIBILITY: Nominated Authority
5b735dd1-ec5b-5861-80f8-449d879090f8 | note | – – – – – – – – – – – – – – – – –
e7ed22e9-3c4b-5610-b9a6-3a5a91ea5190 | note | VERIFYING DOCUMENTS: Conqa HP Release
f4e554e9-c508-5873-b3f5-bb2f2491df61 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Check for correct documentation
8e18d433-150c-55c8-aeae-d1240b559510 | note | REFERENCE: IFC Drawings
ae01264a-6ce1-59c3-862b-2f1b34da7e0d | note | – – – – – – – – – – – – – – – – –
3e71a3fa-9c7e-5797-ba8c-2b0d2952c9e4 | note | ACCEPTANCE CRITERIA: Ensure that all employees and sub contractors are:
d8fab467-bb13-5ff7-8682-6851e753b898 | note | – Using the correct and complete set of drawings
f106d45a-704b-54bd-9597-539127178a57 | note | – All drawings are the latest version
47195a30-6608-5b75-a4c1-eb94d4714c65 | note | – – – – – – – – – – – – – – – – –
cebf2be8-e835-5020-bc2a-9e5e05b5ff62 | note | METHOD: Visual inspection
830529ba-62eb-5e8b-a998-8d45c176d59d | note | – – – – – – – – – – – – – – – – –
3810a001-7a05-5fdf-9767-811ca3993eae | note | FREQUENCY: Prior to commencing any activity
2544ea1a-75e7-5ff0-9924-96caae0ec439 | note | – – – – – – – – – – – – – – – – –
5663266b-5f82-50af-a606-c40a08bea47d | note | CATEGORY: HP*
294eafef-0a22-52c8-943b-f38c79ece060 | note | – – – – – – – – – – – – – – – – –
b48a7ecb-b06c-5f84-8922-66dde0545393 | note | RESPONSIBILITY: SE/Site Supervisor
8e772085-4dd2-5684-a281-b795de1a1b50 | note | – – – – – – – – – – – – – – – – –
9454c309-2067-53d1-953f-a94743094a08 | note | VERIFYING DOCUMENTS: This ITP Signed-off
eee33e4d-6a80-5830-98f4-38d0707061dc | date | Date Completed:
| section | Pre-construction Activities
| checkpoint | 4.1 Setting Out - Position of Posts and Signs
1a415743-1ac8-5030-9150-5537e6ccb90c | note | REFERENCE: Section 714.06 IFC Drawings
67a0cd94-9266-5211-ac8e-1e3e22602c13 | note | – – – – – – – – – – – – – – – – –
179cf41a-221b-5313-82a9-10cb198e2e0f | note | ACCEPTANCE CRITERIA: Set out work in accordance with IFC Drawings. The required positions of all posts and signs shall be checked and confirmed by the Supervisor before the erection of posts
ea120cef-cdea-5d4d-8c24-e951ab2e2024 | note | – – – – – – – – – – – – – – – – –
8956b383-f261-5b6f-ad00-8fa19fbddabb | note | METHOD: Verify
55783f20-a7f0-5abf-88ce-57140d51e43c | note | – – – – – – – – – – – – – – – – –
e92fab16-0c01-5a34-9934-6a3cc4692cdb | note | FREQUENCY: Prior to start
157a8469-457c-5e0a-8120-37184a55f029 | note | – – – – – – – – – – – – – – – – –
4a6de858-5e9c-5766-9765-7c572fb87a7f | note | CATEGORY: HP*
bd2669b1-14a7-5f3d-b014-4f7c73a9e966 | note | – – – – – – – – – – – – – – – – –
35818a1d-2ab1-58cb-847e-d8d0c8bd07b2 | note | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
05c4ae3a-b8c5-5fbf-a20e-ff19f3cfcb1c | note | – – – – – – – – – – – – – – – – –
0a3b623a-3010-56b5-bf3b-c00a3571ad93 | note | VERIFYING DOCUMENTS: This ITP Signed-off
934256a5-593d-5a0a-930b-bc44791c74c3 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Foundation
93a0c478-b858-564d-9ddc-28489e9a074d | note | REFERENCE: Section 714.06 (c), Section 703
92d2787c-1b99-5ebb-867d-15ff06f03d4c | note | – – – – – – – – – – – – – – – – –
8a7f4083-eb56-5cfc-9ba6-5ed86b67e30e | note | ACCEPTANCE CRITERIA: All posts shall be set in concrete foundations to depths shown in the Sign and post Schedule and have hole diameters as per the below:
40a82617-d317-572b-be95-38f3a2bb3935 | note | ○ Post sizes 32mm and 50mm nominal bore steel = 225mm diameter
66b174b9-f52f-5d75-8b0a-8505464f58cf | note | ○ Concrete shall be 20MPa and complying with requirements in Section 703.
3e30a115-979b-5428-9e22-f93568fa8972 | note | Attach: Concrete Delivery Docket
e7ec3d88-36d6-5c6d-8c40-45e97cc0dde8 | note | – – – – – – – – – – – – – – – – –
d4e02714-7432-5536-92ba-46591cd96b5d | note | METHOD: Measure, Visual
8482c214-13cb-5ade-9bf2-21be237f73b0 | note | – – – – – – – – – – – – – – – – –
c2ddd00c-5b71-5638-bf45-99e0a8c6da0d | note | FREQUENCY: Per Lot
33a4d6a3-57f5-5c04-8ee1-44d23b95c3de | note | – – – – – – – – – – – – – – – – –
ea109c6b-8d1f-5714-a101-003ead505bf3 | note | CATEGORY: HP*
9cc5c84b-ebb7-5659-9ce2-81ae31b08d81 | note | – – – – – – – – – – – – – – – – –
70b21519-ab8f-5606-a7d1-d8efa24c80cd | note | RESPONSIBILITY: SE/PE, Nominated Authority
df30e450-10fc-5bd6-b5eb-3fae03c0123f | note | – – – – – – – – – – – – – – – – –
10fb4d21-9421-5eea-b6da-00ef28351338 | note | VERIFYING DOCUMENTS: This ITP Signed-off
6da86c2e-2af5-57a6-b593-3ed05364fd25 | date | Date Completed:
| checkpoint | 5.2 Post Installation in Sockets
92ef9999-a7c4-57d3-9a8e-ff6265e7cb73 | note | REFERENCE: Section 714.06 (d) Table 22 of AS 1742.2:2009
9006beec-cf90-5095-93e2-788749d6c474 | note | – – – – – – – – – – – – – – – – –
24916c87-a0f1-5fd6-9138-db7d15580cb2 | note | ACCEPTANCE CRITERIA: For Post Size 50mm Socket size to be 65mm Nominal Bore Tube
941f0d92-d17d-5793-8d54-f852016d4f39 | note | ○ The socket should protrude 50 mm above an earth surface or 25 mm above a paved surface.
440cb27a-20e1-515d-b280-3be49f16d537 | note | ○ The sign post must penetrate a minimum 450 mm into the socket.
9f1de52b-c5a8-5ecc-8b61-eca298b1badd | note | ○ Depth of the socket should be as per Table 22 of AS 1742.2:2009.
3c29dc76-f3ce-571b-a91e-ec3a1c496fce | note | ○ The sign post should be securely fixed into the socket by an approved vandal-proof method.
a7d9a955-df51-5969-a288-9e2d712ef403 | note | – – – – – – – – – – – – – – – – –
5f6928de-e3f4-5c08-a73e-70bf922e8e19 | note | METHOD: Measure, Visual
3083117e-716e-5063-9dcd-cea1eab36fd8 | note | – – – – – – – – – – – – – – – – –
69d61862-4df4-59cb-b959-537ac2321af8 | note | FREQUENCY: Per Lot
3e2f0ec5-67fe-5b2c-b5ca-beb64d3e73a3 | note | – – – – – – – – – – – – – – – – –
cd554459-72c1-52e8-86e9-7940ae950c01 | note | CATEGORY: IP
a6abc405-a993-546c-a1bd-df664d6eaa83 | note | – – – – – – – – – – – – – – – – –
43033069-c873-5bcd-b06c-28c26592808c | note | RESPONSIBILITY: SE/PE
b72c6aaa-51a7-5f0f-b5cf-a1b8b890648e | note | – – – – – – – – – – – – – – – – –
debb8004-8b21-5f5e-967f-d052f12ab5bd | note | VERIFYING DOCUMENTS: This ITP Signed-off
bd9e67be-05a7-54a8-9f99-b265bf59f99e | date | Date Completed:
| checkpoint | 5.3 Backfilling of Post Holes
ce744252-6b8b-53e8-8f99-f95c5d6990fa | note | REFERENCE: Section 714.06 e
222c274a-570d-5466-83ba-0f446239a835 | note | – – – – – – – – – – – – – – – – –
d9e3de0d-13e5-5563-9235-0ffe93dcfea0 | note | ACCEPTANCE CRITERIA: Only relevent where cast in sleeves have not been used.
460792e1-6976-5f90-b73a-099e526e43ad | note | ○ 32 and 50 mm Nominal Bore Steel Posts
feaf4ade-5d6e-5336-9d65-eeccd2689d39 | note | ○ Posts holes shall be back-filled with concrete with a nominal strength of 10 MPa.
1cec09c6-3f9c-5ee1-81c7-e0770e4b3ab0 | note | Attach: Concrete Dockets
77d6ba71-347b-5774-8a86-59bf6f7394b2 | note | – – – – – – – – – – – – – – – – –
a0fb35c9-610e-549f-a47e-635b26e56d28 | note | METHOD: Verify
0eddec3d-a8de-5d03-b4e8-35bf89367853 | note | – – – – – – – – – – – – – – – – –
87f5a8cb-3195-53b6-b8d1-4bed8c9665cc | note | FREQUENCY: Per Lot
3e1df541-8f09-55c2-bf82-ab5135f31070 | note | – – – – – – – – – – – – – – – – –
4c6ad430-e98b-5930-9f7e-9aac950599c7 | note | CATEGORY: IP
47b073c8-4d4e-5f7a-a6b7-35901d82cb90 | note | – – – – – – – – – – – – – – – – –
bbe5ca3b-0745-5908-9592-d5d18241cccd | note | RESPONSIBILITY: SE/PE
ebf76f9f-dec6-5553-98e2-32305d53d440 | note | – – – – – – – – – – – – – – – – –
b8ca546f-a7dd-5ae7-a1a0-f63bfbbd1f66 | note | VERIFYING DOCUMENTS: This ITP Signed-off
3e913563-7269-5948-8da2-33ec68a5a018 | date | Date Completed:
| checkpoint | 5.4 Sign Fitting
34b1d939-eedc-5bb7-b9e8-364ed2695fce | note | REFERENCE: Section 714.07 Design Pack 11 - Signage and Linemarking (IFC)
68f9bb7b-03e7-585b-81c8-61a0a3e79635 | note | – – – – – – – – – – – – – – – – –
43364fc9-9491-57e3-8156-fb37297aab3b | note | ACCEPTANCE CRITERIA: Signs shall be attached to the post or structure using the type and number of fittings as specified in the Sign and Post Schedule, or as follows:
a9873a39-e880-5d8d-a2b4-7ae12ce93a55 | note | – Signs up to 200mm in depth – one fitting per post
d0e2c5b7-68e4-5ff2-95d6-c8544bc2bad3 | note | – Signs 201 to 900mm in depth – two fittings per post
4e1542a8-997a-5146-8d93-6786b8055de2 | note | – Signs 901 to 1200mm in depth – three fittings per post
cb55145c-a923-5150-b4e4-bcbd5f3cd457 | note | ○ One extra fitting provided per post for each 400mm increment or part thereof above 1200mm.
41416618-7705-514f-bb0b-4dee2cdb8f3b | note | ○ For braced signs, the sign shall be attached to the post at every intersection point between the sign bracing member and the post.
2f895054-195a-524d-90d4-bcfccc895b1d | note | ○ When a sign assembly consists of two or more signs, the signs shall be moubnted in accordance with the sign assembly drawings.
3bd3205f-390c-5959-9e57-beac59a007de | note | – – – – – – – – – – – – – – – – –
d8703382-01c3-58db-a0f3-4b5620fc921a | note | METHOD: Measure, Visual
2707f58c-353f-5f67-a27c-4ad3d118e3d3 | note | – – – – – – – – – – – – – – – – –
7e71114f-23b4-59bb-836f-ce689c3ae2d1 | note | FREQUENCY: Per Lot
205ebe4b-ca3b-58ee-8847-71950173ab47 | note | – – – – – – – – – – – – – – – – –
200d1852-f36f-5dc9-b269-002598a131a3 | note | CATEGORY: IP
9306948c-8dff-5544-9ddd-bd2311ffe75b | note | – – – – – – – – – – – – – – – – –
a6af418c-4bc3-5b1f-be12-617d937f2d2e | note | RESPONSIBILITY: SE/PE
a431757e-4371-5896-8b45-9838a6b3747c | note | – – – – – – – – – – – – – – – – –
8aa55225-0ca9-53c9-980c-612c93bcb81e | note | VERIFYING DOCUMENTS: This ITP Signed-off
72e662a1-1b57-5abb-ae44-3b0da98b112d | date | Date Completed:
| checkpoint | 5.5 Mounting of Signs
9154fa87-0ad6-5558-84df-99ce3615e390 | note | REFERENCE: Section 714.07 (d,e,i) Design Pack 11 - Signage and Linemarking (IFC)
b6d1e79c-20f9-51cb-94c4-9e02a9a8fbce | note | – – – – – – – – – – – – – – – – –
fe6fbcba-63e2-5494-827c-8aa25e57b1b3 | note | ACCEPTANCE CRITERIA: Nominal Mounting Height for all signs in 2m from Road level to bottom edge of sign except keep left signs (R2-3) located in median islands, which are mounted 0.5m above ground
525fc7e5-9906-5e18-8dc8-48406e67514b | note | ○ Signs shall be positioned in accordance with the following tolerances:
a5e43a98-a1f0-589b-925d-8aa0e2543d04 | note | (i) +/-40 mm of the height specified in the Sign and Post Schedule measured from the bottom of the sign or sign assembly to the lip of the kerb or edge of shoulder nearest the sign;
f51f1809-265b-58d7-bcb9-5822915cc2a9 | note | (ii) +/-100 mm of the pegged sign location or specified location.
ab28f283-9c2d-5600-ba6f-c1220c8fcb09 | note | ○ Sign shall be installed such that the sign face is rotated away from the approaching traffic to avoid direct reflection (approximately 5⁰), with the exception of signs mounted on structures over traffic lanes.
f6930d41-38fd-53e8-8263-b769ae1f2201 | note | ○ After erection of each sign all stiffening bars are to be removed.
6807df85-cd4f-514c-a817-95e0e7f85c57 | note | – – – – – – – – – – – – – – – – –
f776d3eb-7995-5443-a2ee-a302818c91e9 | note | METHOD: Measure, Visual
98a05ba5-a9b3-516f-a630-3ce558d72f50 | note | – – – – – – – – – – – – – – – – –
f26d3fd7-df9a-5d1b-b45c-1bcaa2683f8e | note | FREQUENCY: Per Lot
14c36d26-b0ef-590f-8600-e47063dd3e5b | note | – – – – – – – – – – – – – – – – –
d5de924e-100d-5953-9b28-b7b8898ea7ab | note | CATEGORY: IP
b419d5f6-adf7-5b85-9248-6e01bf5764aa | note | – – – – – – – – – – – – – – – – –
f537aad5-a347-5ae8-ae8f-85a3ac15d143 | note | RESPONSIBILITY: SE/PE
80912003-e0ac-59ac-986c-e58be27508ce | note | – – – – – – – – – – – – – – – – –
9d858a49-61dc-5a99-aec1-591b297f4ad9 | note | VERIFYING DOCUMENTS: This ITP Signed-off
98252ea0-01c3-58f5-94a9-9bf9258755a5 | date | Date Completed:
| checkpoint | 5.6 Masking of Signs
e65551f3-2101-5341-98a8-68a1e6bc5b21 | note | REFERENCE: Section 714.08
e8d7ff8d-4b31-5807-91ba-2d391fe0fb41 | note | – – – – – – – – – – – – – – – – –
2aa550f1-9d44-5bca-918c-7b075e2f5095 | note | ACCEPTANCE CRITERIA: Where indicated in the schedule, the Contractor shall mask the nominated sign(s) by placing a porous cloth or similar covering that conceals the sign text under both wet and dry conditions and does not void the sign material warranty. The masking material shall be held in position by wire mesh over the sign.
4e91b11b-ac16-578f-abd9-8130e9410039 | note | ○ Adhesive material shall only be applied to the masking material and not be applied to either the front or rear face of the signboard.
d9d08f9e-5f78-516c-a5d9-500218d46ea4 | note | – – – – – – – – – – – – – – – – –
bdcd0bfe-ab0c-56b6-98ed-30f325292280 | note | METHOD: Measure, Visual
9e8d67b9-3faf-5ab4-9182-724210b56e3e | note | – – – – – – – – – – – – – – – – –
533e2c0b-a95f-5201-a2da-609459c5cfbf | note | FREQUENCY: Per Lot
23f2a269-1bbb-564f-8c08-1b7295807be5 | note | – – – – – – – – – – – – – – – – –
6002769b-08af-5d76-ae38-52c7ae9a36f1 | note | CATEGORY: IP
8cf83949-768b-5d40-8c84-289c4da05be1 | note | – – – – – – – – – – – – – – – – –
858ae014-b643-5424-8568-7d8a48069b4a | note | RESPONSIBILITY: SE/PE
b1ca3128-2233-58c2-9716-fbe3c4791e68 | note | – – – – – – – – – – – – – – – – –
98cb856a-6dfe-5522-bccd-c4bf56f2cdcc | note | VERIFYING DOCUMENTS: This ITP Signed-off
6d2a78ce-fa7c-5b55-be1f-dd4854465f85 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 As-built Survey
3b5814d3-f96e-5b3d-8229-e7aec15eab84 | note | REFERENCE: Section 714.05, IFC Drawings
3ea18a99-dde8-5a27-855b-28dd63a87218 | note | – – – – – – – – – – – – – – – – –
80e7e99c-b4f6-5285-a1d1-0159c63155e7 | note | ACCEPTANCE CRITERIA: Survey activities carried out to validate correct construction of signs, components and posts as per IFC Drawings and Section 714.
c35ecfb5-2787-5bb7-a09f-75f6c365665a | note | Attach: Survey Conformance Data/Report
9eac2586-9179-5c63-acc7-b3a39f4061cc | note | – – – – – – – – – – – – – – – – –
fd696389-15bc-5534-955f-aa9acb9c498b | note | METHOD: Document Review
d08be245-b37b-5d8c-aab3-6333709722a7 | note | – – – – – – – – – – – – – – – – –
6894e8dd-4f79-52e5-a60c-19833d541d40 | note | FREQUENCY: Per Lot
6c4fb05a-7290-53b0-bc46-2a441dbad9e2 | note | – – – – – – – – – – – – – – – – –
a3426c78-860b-5cf5-8158-5b250ccd25d0 | note | CATEGORY: IP
041c6ac1-a939-54f6-8c84-62103e6e26bc | note | – – – – – – – – – – – – – – – – –
b274f34b-15b9-59e5-acd8-900bf4c1ff25 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
2fd343df-7b5b-538a-82da-18260dcf69dc | note | – – – – – – – – – – – – – – – – –
737f5c7a-fd1a-530b-818a-146dc9ee1953 | note | VERIFYING DOCUMENTS: This ITP Signed-off
2495ef49-f303-5eef-8d66-2b3a85352700 | date | Date Completed:
| checkpoint | 6.2 Non-conformance Report (NCR) Closure
c7c569de-50b3-5c7e-8be5-0a94d66c30f3 | note | REFERENCE: MRPA Quality Management Plan
f9d5e760-ec71-5646-9e21-ac749eaddfb5 | note | – – – – – – – – – – – – – – – – –
59ac7a05-256f-5c89-8de4-1195d6a2e457 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
07097de5-e5a5-5e6a-b556-ba04528c238e | note | – – – – – – – – – – – – – – – – –
e0ce2253-078f-5f2a-842b-abd8fd8a4745 | note | METHOD: Document Review
330b8780-e88e-5695-b790-bf3233321a61 | note | – – – – – – – – – – – – – – – – –
7ec6cf6b-fd07-518e-b9c8-5a695be4094c | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
8edf5b96-2ff9-5a25-8557-a7ee0bd113eb | note | – – – – – – – – – – – – – – – – –
de4f718a-4334-56df-b3a8-2380be263973 | note | CATEGORY: HP*
95c9abfa-2afb-5391-81fc-07b9637287e2 | note | – – – – – – – – – – – – – – – – –
9737f4c3-9ff1-504d-92d4-e573c8e1e910 | note | RESPONSIBILITY: SE/PE/SPE
1108ccb3-c220-55d0-85d4-1c50bd4d98d7 | note | – – – – – – – – – – – – – – – – –
68517ac5-7a63-5025-a90a-fc4b707c3747 | note | VERIFYING DOCUMENTS: This ITP Signed-off
1b13be30-d3fd-5f9d-aac1-1d85d963dcef | date | Date Completed:
| checkpoint | Final Inspection
06bf0452-acf4-5d14-baad-aa7c167a5e1a | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
627afe22-7391-5b83-92d5-8066521a71e2 | textbox | Name:
3bf7c564-2f7f-53d2-8396-8337be9ff6ee | textbox | Position:
5933fc94-df91-5e1e-97c8-79c4129694fa | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-070-CIV-CAMMS-Tactile Installation Rev 0 | itp | ITP-070-CIV-CAMMS-Tactile Installation |  | 7a9d969e-4d69-4f9a-8306-5453d0fbc3bb
| section | Referenced Documentation
| checkpoint | Referenced Documentation
c733fa19-a456-5a9d-8076-a7781f2a11b4 | note | Document Title: ITP-070-CIV-CAMMS-Tactile Installation
30fff762-05fd-5d2b-a06f-21043da4b4f5 | note | ITP Description: CAMMS-Tactile Installation
6a1efbc2-24ff-52db-a22d-a2e804e3ead5 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
5f1226f8-f440-5390-a41b-5af338a5e76a | note | Discipline (e.g. CIV/STR/RAIL): 070-CIV
668f0f4b-5083-5e53-be74-f7bffc70d228 | note | Revision Number: 0
700c4aee-7d84-5cd7-8015-e4670b410f57 | note | Revision Date: 28/02/2023
7c6ae378-c324-5ee6-a762-cd181dc5232d | note | ITP created by: Chloe Mitchell
e98d67f1-17f1-58ec-b81a-528ed6211a9f | note | ITP approved for use by: Victor Mira
24ff54dc-98a3-5ada-ab44-91a73924381f | note | 1.1 Non Dependent
3345842c-4bec-5d1f-b812-97cb1c88e4cb | note | Reference: AS1428.4.1
e8838594-f812-5148-8e97-06e677095f63 | note | 1.2 Non Dependent
e7270e4b-52bf-5c88-86cf-21154eb77bdb | note | Reference: VicRoads Section 160.A9
be64603c-d276-5d3a-b109-562a825fdc7e | note | 1.3 Non Dependent
aeaa2e4d-d957-5c65-ba6e-ae4f70ab2f14 | note | Reference: IFC Drawings
| section | Preliminaries - Materials
| checkpoint | 2.1 Material Conformance
31ca4175-e8d8-5306-b2d3-adf62fb7d0df | note | REFERENCE: AS1428.4.1 Section 2.2 & 2.3.1
a806e2c4-0048-50f4-9726-e3637d809b12 | note | – – – – – – – – – – – – – – – – –
fdcb751a-f7fa-5b60-a009-1f310f449247 | note | ACCEPTANCE CRITERIA: Tactile Indicators must conform with the requirements of AS1428.1.1 Section 2.2 & 2.3.1
515aed46-242f-5886-80aa-37bfd4f72cc6 | note | Attach: TeamBinder Material Approval Ref No
1476f51d-9ccf-52d1-8b66-ac26b3af0be8 | note | – – – – – – – – – – – – – – – – –
8f5b33cf-f5ce-5544-b5c6-92e1237bd712 | note | METHOD: Document Review
cddd59e5-121b-516a-b301-cfe2119dccfc | note | – – – – – – – – – – – – – – – – –
ca49ffff-2692-5f17-96fe-b78c2e2a244a | note | FREQUENCY: Prior to works start
a224da6a-c163-5437-b566-e7879d04ee5f | note | – – – – – – – – – – – – – – – – –
26926e26-bf81-5989-9bb7-76b27541e928 | note | CATEGORY: HP
7ef382c0-0d92-5963-b7d3-2c9f37603faf | note | – – – – – – – – – – – – – – – – –
e557fc58-5817-58b2-aa6c-69386859560b | note | RESPONSIBILITY: Nominated Authority
d8d5aeaa-2b8e-56a6-9177-a1409ff2058b | note | – – – – – – – – – – – – – – – – –
004d19e7-93b4-50ec-9cde-cfc4a9bcda8b | note | VERIFYING DOCUMENTS: Conqa HP Release
5c7ee6d7-29fe-5b64-80b7-4cae09b9ce3c | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Documentations
| checkpoint | 3.1 Documentation Conformance
ed85f434-d8b5-5cd4-8ec1-749743b37ce9 | note | REFERENCE: DoT Handover Process
293c6478-cfe7-5361-b00b-8cb7f4b25d07 | note | – – – – – – – – – – – – – – – – –
770b5f09-cfc0-5ae4-b292-d8269490da85 | note | ACCEPTANCE CRITERIA: Tactile to be yellow in colour, VicRoads approved as per design note RDN 06-05 and DDA Compliant
40b78f98-58f0-5eb2-abc0-58fd14f2670d | note | – – – – – – – – – – – – – – – – –
185ed91f-6e17-5249-8eaa-cdab3e947558 | note | METHOD: Visual & Document Review
679f1c34-36a2-5052-98ef-cc1ad7e61802 | note | – – – – – – – – – – – – – – – – –
d771f8ab-46e0-5158-9570-0e5c4c956b92 | note | FREQUENCY: Prior to works start
6da6d27b-20f7-5fd7-ab3b-eb580ff526d9 | note | – – – – – – – – – – – – – – – – –
b40dbad4-9ad2-59e4-b385-8398865441ab | note | CATEGORY: HP*
3a9731fb-ad1f-5120-88fc-80c9d020cea6 | note | – – – – – – – – – – – – – – – – –
18257276-d617-5ce5-8459-fed020ede1d2 | note | RESPONSIBILITY: SE/PE
8dd91f1a-3378-55e1-b718-e25077712322 | note | – – – – – – – – – – – – – – – – –
b36920cb-a780-5459-943e-b47c3fcda24e | note | VERIFYING DOCUMENTS: This ITP Signed-off
0494256c-d021-562b-9366-d9ab046a1b7f | date | Date Completed:
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set-out
ac28cfc8-f27c-5d5f-977f-7a810faa8444 | note | REFERENCE: IFC Drawings
dd8594fd-44d6-5fdb-ab8b-71a36a42a2db | note | – – – – – – – – – – – – – – – – –
d255d78f-3a6e-5061-9167-53c2422a1fe9 | note | ACCEPTANCE CRITERIA: The required positions of the tactiles are clearly set out by a surveyor as per IFC Drawings.
55d33c67-e760-593b-922a-1941e73a37ef | note | – – – – – – – – – – – – – – – – –
ce67b873-1f09-5b30-aa4b-9fde95d7472f | note | METHOD: Measure, Visual
ff9ea518-4fce-536a-88e9-d92e7adfe2bb | note | – – – – – – – – – – – – – – – – –
08489770-e22d-5ad4-bc66-85a6a6ebd6a9 | note | FREQUENCY: Per Lot
b69780de-0cf2-5ccc-aa8f-3bb95d300a94 | note | – – – – – – – – – – – – – – – – –
7df3bbc3-02db-5c60-ba11-a5aa52a351bf | note | CATEGORY: IP
23c20f8d-49d0-5d15-a2e0-cd944fa3602d | note | – – – – – – – – – – – – – – – – –
877dcecd-551b-5574-ab59-75d7f618329b | note | RESPONSIBILITY: Surveyor, SE/PE/Site Supervisor
f4934133-7b6e-5ca9-8e13-0c1bd62c9420 | note | – – – – – – – – – – – – – – – – –
1c799afa-8179-54c4-97c9-488e738ff489 | note | VERIFYING DOCUMENTS: This ITP Signed-off
297ddbce-3591-5be8-ad15-82c2ff33ff12 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 Installation
d65d55d4-9753-5ac5-a94d-145475ba9879 | note | REFERENCE: AS1428.4.1 Section 2.3.3
c16f6f03-845a-5a0b-a399-87065246b4f6 | note | – – – – – – – – – – – – – – – – –
05d78311-04b4-59dd-ad62-d91180b3d192 | note | ACCEPTANCE CRITERIA: Notify Nominated Authority prior to installation.
7981d086-d9bf-5ecc-8cf6-729e8f48c54e | note | Warning indicators shall be installed as follows:
62e36c22-a21f-50d2-b625-6ba514fc463d | note | (a) For the full width of the path of travel
8d17e894-234d-5e9e-8f3c-8138a1cc57f9 | note | (b) Perpendicular to the direction of travel when approaching the hazard.
fac700da-4460-50c1-8224-a8416c600a78 | note | (c) Set back 300 +/-10 mm from the edge of the hazard except at railway platforms and wharves.
000f3355-ee65-5c5c-a17e-2d944b79030f | note | (d) Where integrated warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below, over a minimum depth of 600 mm to 800 mm from the direction of approach.
cc3bc31d-3f2d-5af3-92c0-61c9730c0a0b | note | (e) Where discrete warning TGSIs are used over a depth of 300 mm to 400 mm, the arrangement shall be as shown in Figure 2.1 below with a minimum of 6 discrete truncated cones in the direction of travel.
0b571e7b-e5db-5946-a7f4-6945d5bd94aa | note | (f) Where discrete warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below with a minimum of 12 discrete truncated cones in the direction of travel.
0459d0ad-57b9-5cb4-8eef-eb13734c77e3 | note | Where required on a path of travel, warning indicators shall be located at both the top and bottom of stairways, ramps, escalators and moving walks
1689c9b0-08d5-5e5a-9ab2-ef9ab21079b5 | note | – – – – – – – – – – – – – – – – –
1066065c-6f7f-5dc0-bf08-b377dd7e8669 | note | METHOD: Visual/Site Inspection & Document Review
7fe86f47-2b37-50e4-9589-8832f50bd97c | note | – – – – – – – – – – – – – – – – –
0b817436-3dab-5d52-946d-6e3483c0ea69 | note | FREQUENCY: Per Lot
5d0ce74a-ec2d-5935-81a8-2ac1903d0940 | note | – – – – – – – – – – – – – – – – –
e21e226a-9cb7-5f8f-8cf0-e59873ccdcbc | note | CATEGORY: HP
d1af7cda-48ae-5a31-99b5-e32ea2f3d45c | note | – – – – – – – – – – – – – – – – –
44fa8693-c18f-530b-b393-dac8b88320a4 | note | RESPONSIBILITY: Nominated Authority
9a58e888-8e2c-570d-b644-8f1a2d5c02ae | note | – – – – – – – – – – – – – – – – –
35a40eb6-4ca8-5ffc-93ea-b89ed475c3ad | note | VERIFYING DOCUMENTS: Conqa HP Release
0c82ccd9-d44e-5c07-b754-f0b6219f207f | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.2 Laboratory and On-site measurement of luminance contrast
74803b6d-ae64-556e-92eb-73ca7b90e712 | note | REFERENCE: AS1428.4.1 Appendix E
21dd4eea-d46e-57ad-9020-2d55065a883c | note | – – – – – – – – – – – – – – – – –
d0683c8b-5ac5-5579-bff3-055bfa29605e | note | ACCEPTANCE CRITERIA: Submit Test report to AS1428.4.1 E5.4: The following shall be reported:
e8acad4b-6f00-5986-83fc-711d74667344 | note | (a) Full description of the surfaces tested with product details where known.
d0c1eae6-6e3c-557b-af40-f5269f4f2523 | note | (b) The instrument being a luminance meter with a 1° measurement area corrected to approximate the CIE 1931 Standard Observer.
a144f2db-cc69-5bea-932b-1aaa09d25a1b | note | (c) The location of the sample, if on-site.
3a720677-6b73-5c03-9350-d81a4d514517 | note | (d) The location of the sample of the measurements on the TGSI.
378c63f8-39b4-58fb-9794-b595370a652e | note | (e) A description of the light source(s) illuminating the sample, including type, [e.g. fluorescent tube, incandescent, high pressure sodium discharge, metal halide, and colour (in general terms)].
32a2e0c1-707b-5584-b331-380193496ee9 | note | (f) The mean luminous reflectance of the adjacent surrounds to the tactile indicator under the conditions set out in Paragraph E5.3
4e7792b5-b586-5109-a143-5e6ca9026eea | note | (g) The mean luminous reflectance of the tactile indicator under the conditions set out in Paragraph E5.3
c929bfcf-ba51-5fa4-9a20-2fba56cdcd5d | note | (h) The luminance contrast with the surrounds on both sides of the tactile indicator.
c7e7956a-77f5-5559-aaf8-ab0c6b48f9c6 | note | (i) A reference to this test method, i.e., AS/NZS 1428.4, Paragraph E5, Appendix E.
77ead668-0b33-569d-a744-914b8a8cf705 | note | Attach: Laboratory Test report
63ddb05d-a246-5a1c-baf0-67dfa5c597e0 | note | – – – – – – – – – – – – – – – – –
0826b067-3e60-5539-9c08-58916e0908e5 | note | METHOD: Visual/Site Inspection & Document Review
11ea0dcb-c12c-5056-9b7f-f57389f0a84e | note | – – – – – – – – – – – – – – – – –
6fa3be6b-b5a3-5a97-8475-42c505ec5b44 | note | FREQUENCY: Per Lot
95ab54e7-39b4-503a-a1e0-eb64665ba35e | note | – – – – – – – – – – – – – – – – –
fa72a1dc-58c6-5e4d-bcc9-31ae52ba0977 | note | CATEGORY: IP
deb66514-be04-5283-b941-80a296f7e23a | note | – – – – – – – – – – – – – – – – –
be55a3cf-175c-5e66-9a27-41d31a9ab1b3 | note | RESPONSIBILITY: SE/PE
8fc28aa4-ab7f-5b04-bf59-da2dc3befa43 | note | – – – – – – – – – – – – – – – – –
03e19cc0-0605-56f1-9a3b-fdeee23cbb9b | note | VERIFYING DOCUMENTS: This ITP Signed-off
91c078dd-4934-5a42-a2bb-a44f7746e198 | date | Date Completed:
| checkpoint | 5.3 Distance between tactiles and sleeve
b6c8face-d300-5ca6-974c-c805f4606fb9 | note | REFERENCE: DoT Handover Process
1303a600-fb61-51fc-b0a0-92e4cd0d5090 | note | – – – – – – – – – – – – – – – – –
c14c1057-4654-5ddd-8566-fc7831c8ab79 | note | ACCEPTANCE CRITERIA: Distance between tactile and sleeve to be a minimum of 300mm as per note 1 of the Handover Process
05f437c2-3f59-5348-ac61-7f524549643c | note | – – – – – – – – – – – – – – – – –
70358d96-6d39-5604-aef4-822c8c3ce42e | note | METHOD: Visual Inspection, Measure
1727c2f2-fd34-5dc1-8fa3-b84756c41874 | note | – – – – – – – – – – – – – – – – –
7654eaa1-ae8b-5b69-b431-10503d8557fb | note | FREQUENCY: Per Lot
df58170d-65c3-5c89-b7dc-8c7e79dc1e9d | note | – – – – – – – – – – – – – – – – –
785078de-c119-5a8e-8d14-3513882a068d | note | CATEGORY: HP*
bf1a2327-9c71-5525-999a-007233f8b826 | note | – – – – – – – – – – – – – – – – –
f7b21c71-66c2-5f38-ad7d-589ed75712f7 | note | RESPONSIBILITY: SE/PE
8e8ef00e-142c-5b1c-97f7-691579f6f42d | note | – – – – – – – – – – – – – – – – –
cad16a30-2a74-5e53-8c59-6187212f2068 | note | VERIFYING DOCUMENTS: This ITP Signed-off
16f9dae5-6a5e-5219-8be2-be0667389ea8 | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 As-built Survey
2652efb9-d5ca-58e9-9530-935039400f96 | note | REFERENCE: IFC Drawings VR 160.A9
26f6c50c-adb5-5e6d-840a-672b19156a88 | note | – – – – – – – – – – – – – – – – –
7ec7a44e-9662-5ccc-8265-4b7dd19055af | note | ACCEPTANCE CRITERIA: As-constructed’ information shall be progressively documented during the work under the Contract and shall be provided to the Superintendent in a neat and clean format Attach: Survey As-built / Survey Report
df5c2b57-7b23-5187-9256-3737be334436 | note | Attach: Survey Conformance Data/Report
d004d271-1097-59f7-bec5-6df400a24c4a | note | – – – – – – – – – – – – – – – – –
80c3916e-a60a-50e2-a97f-789daca7eec4 | note | METHOD: Document Review
f6872ff7-94a2-52fc-8014-d8ad7c567585 | note | – – – – – – – – – – – – – – – – –
b720a6eb-8cb5-5d35-a50b-e6df6c81d9f7 | note | FREQUENCY: Per Lot
a0d0d52e-f9d4-5eab-bb60-84cc66efdc49 | note | – – – – – – – – – – – – – – – – –
66e02289-c749-5c1b-8dc6-bc43314bbeea | note | CATEGORY: IP
be62df75-73f1-560a-83d6-e489b005df78 | note | – – – – – – – – – – – – – – – – –
6bf2d1e7-c820-59fa-a160-e05075905c13 | note | RESPONSIBILITY: Nominated Authority
5d9aed7b-86ea-513d-89a2-8b8e655a7e37 | note | – – – – – – – – – – – – – – – – –
741bbbda-11b9-5da7-a559-4ca03b0f7cb5 | note | VERIFYING DOCUMENTS: This ITP Signed-off
a2a7c165-e340-59cd-a410-cc75b76404a7 | date | Date Completed:
| checkpoint | 6.2 Non-conformance Report (NCR) Closure
d0ce2057-970a-5baf-a43b-da3f683890fb | note | REFERENCE: MRPA Quality Management Plan
b82db9ce-09fa-5300-a569-aecb873ed5d3 | note | – – – – – – – – – – – – – – – – –
c3fd4ff1-4ffe-5285-8d7c-cb2d51d01824 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
007bd982-65dc-5753-bd99-87e672429493 | note | – – – – – – – – – – – – – – – – –
84cfc80d-9347-5e5b-a556-ada3234dffd1 | note | METHOD: Document Review
16806881-4875-5316-b672-968fb6ccc108 | note | – – – – – – – – – – – – – – – – –
b8d14232-54a9-5242-919b-50fbc10a783d | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
d3468596-5beb-5431-9f05-3e885674c2ad | note | – – – – – – – – – – – – – – – – –
4a3872c4-d40c-56d2-bd36-dc2ffc2532b9 | note | CATEGORY: HP*
30aeff51-71cd-57cb-a059-cbb74398f09e | note | – – – – – – – – – – – – – – – – –
352c64a8-3a83-500c-ae59-70b9a7758acc | note | RESPONSIBILITY: SE/PE/SPE
569b358a-10c7-526d-9b12-3807db662548 | note | – – – – – – – – – – – – – – – – –
b40576be-0d74-5e0f-ba9e-a75d46cd5c23 | note | VERIFYING DOCUMENTS: This ITP Signed-off
b1f0d192-6645-55b3-8092-e6ca80b15ff6 | date | Date Completed:
| checkpoint | Final Inspection
b9485eea-8980-5ed6-b02c-4f2d69c6214d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
caee7128-bce5-591c-b7db-0f8ead648628 | textbox | Name:
449ddbd0-c2ea-5e81-96db-158818d431f7 | textbox | Position:
09265911-c550-5034-be99-3cd0a4bc5330 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-071-STR-CAMMS-Misc Steel Structures Installation Rev 0 | itp | ITP-071-STR-CAMMS-Misc Steel Structures Installation |  | 5882545d-6cd5-4d36-9e59-1c3c830a7218
| section | Referenced Documentation
| checkpoint | Referenced Documentation
0a2e1c47-7340-5b3f-8764-e085ef3ed92d | note | Document Title: ITP-071-STR-CAMMS-Misc Steel Structures Installation
c7ae375f-824c-5c14-a949-51d8ec9704b0 | note | ITP Description: CAMMS-Misc Steel Structures Installation
49c4ca71-7153-5408-bf1a-65dc7b1aa4d5 | note | ITP number: 071-STR
ec7c88cd-c3d8-516d-a2fc-2db74928f840 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
bf9c367c-c461-56ad-9350-facda5257f2f | note | Discipline (e.g. CIV/STR/RAIL): 071-STR
cc08fc7d-c126-5406-922f-ba85f35ed742 | note | Revision Number: 0
a10a735a-4553-5063-94df-a61fac71a44b | note | Revision Date: 19/10/2023
5aed2e42-e571-511d-a777-bd0e01f795b9 | note | ITP created by: VM
81167fd5-5df6-5e0b-be50-33bae7c89c78 | note | ITP approved for use by: VM
f40e625c-c50c-535e-a563-2c80bb59b517 | note | 1.1 Non Dependent
f2a31085-8c43-539d-b846-32b5ea7d771c | note | Reference: VicRoads Section 610 June 2019
8ea4e2de-41a5-5134-a8c7-04db1257211d | note | 1.2 Non Dependent
42990769-e530-52f7-8f81-32e648c5567f | note | Reference: VicRoads Section 630 October 2013
c179ea1f-384b-5a1e-930f-68215b597808 | note | 1.3 Non Dependent
a8367d3f-16c4-5bb4-9ac8-755c8befbc59 | note | Reference: VicRoads Section 631 February 2009
| section | Preliminaries - Materials
| checkpoint | 2.1 Structural Steel Components
3bcbf007-9f50-5f57-a6c8-4a15edaf354e | note | REFERENCE: IFC Drawings, MRPA Quality Management Plan
1ac02e33-3cc4-564f-bb33-74d346389197 | note | – – – – – – – – – – – – – – – – –
19f3a24f-bdf8-51f3-b875-5cfd490c1028 | note | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
49130c6b-044e-5728-a11a-09ecc67a0820 | note | Typically this consists of but not limited to:
36331dfc-ab80-583e-8380-961739931d83 | note | i. Certificate of Compliance
d02d6c41-eb7e-5cb5-b93f-d3029c926e71 | note | ii. Completed ITP
320e1213-c26b-5b34-83c0-9999b311c478 | note | iii. Weld Procedure Specifications
c692bb33-5383-5d6c-a042-0062565afefe | note | iv. Weld Procedure Qualifications
b0446422-5bfc-57d7-ac31-12ce0fbd4e95 | note | v. Welder Qualifications
ba5ae09b-76d6-5c13-b37d-6a7ed919c692 | note | vi. Material Certificates and traceability
779adffb-464e-54ad-b6f6-c067bd86e9ea | note | vii. Quality Assurance check sheets
40b4dc0a-d12a-58a3-a729-1d69784edc26 | note | viii. Welding Consumable batch certificates
82838f74-8c2c-5126-852e-eb252b2360c8 | note | ix. Coating certificate(s)
0a720351-29c0-5832-af84-016a82ef0e4b | note | x. Non-destructive Testing (NDT) Reports
fe8bccf8-5daa-518e-86b8-94db7f117742 | note | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
392266c0-0d18-5879-8631-b10043fa4521 | note | Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
8d959e88-47db-5356-ba11-4b335cfa82d9 | textbox | Enter: Teambinder Material Approval number
3499584d-8888-5a85-8d06-5acbb308579f | note | – – – – – – – – – – – – – – – – –
d17c9c50-8f08-59ea-9c16-28b5e169dcf7 | note | METHOD: Document Review
a5a45326-eabf-5045-ba5e-b3ac92c76494 | note | – – – – – – – – – – – – – – – – –
a09a495c-23a9-562a-8672-fc69f40409c2 | note | FREQUENCY: Each component
f2fffc30-08af-5a27-8b5b-3570fdb4bbbb | note | – – – – – – – – – – – – – – – – –
8722da09-7cef-529f-83d3-c0caf404c0ba | note | CATEGORY: IP
781d1950-0e34-541b-9d86-73f65f83ebd4 | note | – – – – – – – – – – – – – – – – –
f9293f7b-1d7c-5cc9-8847-c5ffaf65d20f | note | RESPONSIBILITY: PE/SE/SPE
86c1a4c9-d002-5058-9694-0dd1eee33131 | note | – – – – – – – – – – – – – – – – –
7f66bfc4-0d32-578f-9afb-cdab4fe861a8 | note | VERIFYING DOCUMENTS: This ITP
877cf115-7e5f-579b-9c8e-fd07ad2eee7b | date | Date Completed:
| checkpoint | 2.2 Fasteners
a962027d-767d-5a97-9e83-95c0a7e94ecb | note | REFERENCE: 630.20 IFC Drawing
e769e3a3-0edf-5f2c-890e-30ead2318f11 | note | – – – – – – – – – – – – – – – – –
ee2c6067-771f-54f2-93bc-bc17327a2aa0 | note | ACCEPTANCE CRITERIA: Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
e929f389-a836-5154-9187-29a180274b86 | textbox | Enter: Teambinder Material Approval number
e131432c-7f1f-511d-b2b9-08ab359b33eb | note | – – – – – – – – – – – – – – – – –
8bdda4a2-1996-57f4-9377-c83c91985256 | note | METHOD: Document review
2829c864-57ce-5585-823d-4830040f8220 | note | – – – – – – – – – – – – – – – – –
b2976db5-3a77-5221-b255-6d5354f80f56 | note | FREQUENCY: Where applicable
7c3428a7-c891-5404-88b1-ae133bdb80b6 | note | – – – – – – – – – – – – – – – – –
baa2c4f4-7532-5ecf-9b5a-4fa3c24fa900 | note | CATEGORY: IP
58f551f7-264c-5fe2-a2e4-59f88f9c9862 | note | – – – – – – – – – – – – – – – – –
0cbcfe19-2be0-5bef-bdba-ad94c90023e7 | note | RESPONSIBILITY: PE/Nominated Authority
2c2ba8aa-a072-584a-90b9-0ce0fc5dc1d0 | date | Date Completed:
| checkpoint | 2.2 Base Plate Structural Grout or Mortar
ff6f6727-4f45-5c91-89d5-a1eca2325d6c | note | REFERENCE: IFC Drawings 610.33
e8b024b3-7427-566f-9e48-bfa1e90e3a9d | note | – – – – – – – – – – – – – – – – –
3b25a756-4172-5ded-abc2-788ad7cafcc1 | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
0b014222-e100-52e3-80b7-9c1957696344 | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
fcb2c206-4931-58d4-9247-22ac01af0f7f | note | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
8ad3ca3f-c77e-5be0-a154-8a65971a7c60 | note | iii. have a flowable consistency
a331578e-a9dc-5ae9-9565-8c6b9374783e | note | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
4d96bfd0-7d7d-5210-9a43-f1045d260f3a | note | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
85ba5378-a69a-57df-a885-b257b66af24d | textbox | Enter: Teambinder Material Approval number
4d0a9fcf-9fba-563d-aca9-cc16d21c58bc | note | – – – – – – – – – – – – – – – – –
fbd0bc1c-ef69-5b29-9087-c179d4a915d9 | note | METHOD: Document Review
0a7f24b3-2de3-5ee5-b95a-0bfb50e2d405 | note | – – – – – – – – – – – – – – – – –
d0861656-2758-5dbb-abdb-9f61e5d715ad | note | FREQUENCY: Once, for each product, prior to placement of product
67f8bae3-e30a-51c5-b0d0-1733c6ed0b8d | note | – – – – – – – – – – – – – – – – –
280d9f61-1cd8-5487-b0bf-9f7fee962a17 | note | CATEGORY: HP
a5c04869-1516-5923-b5cb-aea912c3ad0f | note | – – – – – – – – – – – – – – – – –
4431a47a-a0b8-513c-b321-bb5d60a77301 | note | RESPONSIBILITY: Nominated Authority
e694a03e-6e53-5f36-966d-3a20506c8227 | note | – – – – – – – – – – – – – – – – –
8388878a-81ae-5669-8327-26261484df40 | note | VERIFYING DOCUMENTS: This ITP
079d2cc5-1a21-5594-a514-d4688b74809e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Curing Compound
aaa41da2-9d64-58b7-bd25-c8e61a0ead9e | note | REFERENCE: 610.23 (d)
ac1f99b9-08c7-56af-a0d3-135582738426 | note | – – – – – – – – – – – – – – – – –
f9ea40e0-337b-505c-880f-5765b0a9717f | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
f48eef30-7892-56a0-9138-ecc762a2e664 | note | Note: This may be the same product used for the concrete curing
46fb93fe-91a0-50d5-ac27-d34ca947b11d | textbox | Enter: Teambinder Material Approval number
f0da5e36-8ed9-55f9-be0a-59b747b84b1e | note | – – – – – – – – – – – – – – – – –
83831218-8dac-529e-b55c-9bb809176bdb | note | METHOD: Document Review
17269f30-1994-54a7-b77a-2300f924ca81 | note | – – – – – – – – – – – – – – – – –
3cd729f4-a9bb-5f96-9bd2-3ccb943df45c | note | FREQUENCY: Where applicable, once, for each product, prior to placement of product
84eee047-c476-5721-ad04-077579b06d75 | note | – – – – – – – – – – – – – – – – –
328a75ed-7c14-51cc-b542-d5b7873f576f | note | CATEGORY: HP
94085182-fc66-5668-a7b2-99654a44f1db | note | – – – – – – – – – – – – – – – – –
3a3b0008-7c1b-56ef-ae27-4e7090cbd22d | note | RESPONSIBILITY: Nominated Authority
446825f9-a237-5cef-b0a6-0f7046ec90c6 | note | – – – – – – – – – – – – – – – – –
89bdabb9-2ad5-5ac6-943a-658d3fca8c5e | note | VERIFYING DOCUMENTS: This ITP
fbec225c-4776-5597-a38d-f75fb3a8046e | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures
| checkpoint | 3.1 Installation Methodology & Works Method Statiment
51dc04f2-11d1-5cd0-b6ee-7c0f4111c578 | note | REFERENCE: 630.20 AS5131 Clause 11.2.3
110365cf-32ac-5d0a-b5a7-7b1b05ccacf6 | note | – – – – – – – – – – – – – – – – –
ec71104f-b8e2-5361-bbdf-813be3ad01fd | note | ACCEPTANCE CRITERIA: Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
9593fbe2-2235-5414-b069-66ba2fe607a0 | note | – Transported to site;
710da349-0a41-5e6b-b4c0-5f7d4b22272b | note | – Handled on site;
71596a3f-ceb2-5758-8f63-5780b96ab60a | note | – Installation Procedure (subcontracor ITP's);
4a7ee33d-8eda-5e8b-b870-330767cc8d23 | note | Attach: Subcontractor ITP
2231d431-6861-596f-8234-3a2249472627 | textbox | Enter: Teambinder Approval number
0e266731-3a2f-55c6-8fda-229104700875 | note | – – – – – – – – – – – – – – – – –
978a8541-20fe-5fc7-abc8-e8d75db74a6d | note | METHOD: Document Review
271c49cf-239a-58a6-b4e5-7f50690e6143 | note | – – – – – – – – – – – – – – – – –
9369a1cc-16bf-5c9f-96fb-019c56d5e4bc | note | FREQUENCY: Where applicable, once, 14 days prior to use of devices
67145e40-7e2f-5890-b9cf-e6da3f18c441 | note | – – – – – – – – – – – – – – – – –
0b3b80de-ab1d-5d53-86d2-f5536d9fd2db | note | CATEGORY: HP
9886b822-d68e-5f4e-b988-ec067200bd5d | note | – – – – – – – – – – – – – – – – –
4c0f37b2-1066-5787-8133-2b1298f69b1b | note | RESPONSIBILITY: PE/Nominated Authority
445dde3c-57d2-5ede-9280-6fedb5a1476a | note | – – – – – – – – – – – – – – – – –
bbb87d0d-2af5-5e01-b86b-758e39ee1a0c | note | VERIFYING DOCUMENTS: Subcontractor ITP, ConQA Hold Point Release
0b622732-1767-5cbe-a676-9c3db1ae0a9c | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-installation Activities
| checkpoint | 4.1 IFC Drawings
52654f6a-6fd9-5cab-8caa-a11c12f074d7 | note | REFERENCE: MRPA Quality Management Plan
8ce0fc28-619d-5b4f-90cd-004e03d4d0e2 | note | – – – – – – – – – – – – – – – – –
57779f15-4ce4-5c18-a351-cb65b304e92d | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
9141a7b6-4e4c-50fa-b9e2-5ab73f08945b | note | – – – – – – – – – – – – – – – – –
82ca71b6-dfd5-5465-a94b-908e9011c36a | note | METHOD: Document Review
03bd1db9-6c12-5307-9f72-a96bb583ac6d | note | – – – – – – – – – – – – – – – – –
a63d500b-b8dc-5318-89e4-9fb52322d391 | note | FREQUENCY: Prior to starting Works and at regular intervals
d9b80911-206f-51f2-b93b-02e6ba528262 | note | – – – – – – – – – – – – – – – – –
6b3bcb9c-a6aa-5eec-9f2a-478e871b94a6 | note | CATEGORY: HP*
6da00efd-7168-5073-94a6-2c1e9743720e | note | – – – – – – – – – – – – – – – – –
db3e41cc-1b66-5d8b-926d-6b76ac08ab8f | note | RESPONSIBILITY: All
1bc3ecab-afa8-5418-9803-67beb8e7a546 | note | – – – – – – – – – – – – – – – – –
3275e42b-9ac6-5e5d-8cb0-415489c8ee96 | note | VERIFYING DOCUMENTS: This ITP
f5c4cddd-33a3-5c86-88c7-3be41c9d5f58 | date | Date Completed:
| checkpoint | 4.2 Materials Inspection
9bd2dbb0-0e0e-59db-bd54-6d87e69c2f44 | note | REFERENCE: IFC Drawings VR 630
843ed5a5-af17-5811-84a0-c1e652056be2 | note | – – – – – – – – – – – – – – – – –
bac5ae7d-ac5d-5132-a003-20252764ec05 | note | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
695ae0f7-239b-59da-ade0-0f728fea60ef | note | – – – – – – – – – – – – – – – – –
4a5ae102-d93d-53ee-8a9a-596f08cc5f41 | note | METHOD: Visual
5b1654b0-ffa4-5ec7-a2aa-14509eacc637 | note | – – – – – – – – – – – – – – – – –
3ba94177-ced5-5c1f-bf71-75e198d93fb8 | note | FREQUENCY: Each component
4740e64b-1d0f-50df-a2d1-a85eba9dd610 | note | – – – – – – – – – – – – – – – – –
0999593c-4fdc-5a3c-a6c9-b40c1d343b1c | note | CATEGORY: IP
c09ec2b1-7e5a-5d2b-bf14-2a109bddd4b6 | note | – – – – – – – – – – – – – – – – –
430bc4b8-d6ba-5bfb-8473-f11b49485e6b | note | RESPONSIBILITY: SE/PE/SPE
0491c2be-80a9-5035-b660-1b39ff081d92 | note | – – – – – – – – – – – – – – – – –
deb1d081-1737-5850-9b19-79f9474ad21a | note | VERIFYING DOCUMENTS: This ITP
610621b9-330d-516d-bbac-af1b6bfe2107 | date | Date Completed:
| checkpoint | 4.3 Materials Inspection
209882ea-e170-5b5b-9a63-b120a8a66a36 | note | REFERENCE: IFC Drawings VR 630
4532218a-3cf7-5226-8e7d-71886aabd0be | note | – – – – – – – – – – – – – – – – –
1165988a-8670-5f2d-9b00-919468a01553 | note | ACCEPTANCE CRITERIA: Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
2286699f-a3f0-5f31-b32e-41a8620854d8 | note | ○ Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
d44fdbb7-6ffc-5ffa-b7b5-b6fab11f5f9b | note | – – – – – – – – – – – – – – – – –
83cbcd6d-7a54-5f2c-835d-a4ef3102c180 | note | METHOD: Visual
9ada9ffc-12cb-5e14-8f3a-a026d4ff2c0e | note | – – – – – – – – – – – – – – – – –
c25d5bfc-28e5-53e8-9f66-3808afc05f90 | note | FREQUENCY: Each component
f5a65288-1b26-56cd-a0d2-ca4fa838c8ba | note | – – – – – – – – – – – – – – – – –
038c5f3b-b9f0-5e27-aea1-2b6c79dc0fc7 | note | CATEGORY: IP
76ede48d-ab03-5dcf-8c83-4f5a10ec45f8 | note | – – – – – – – – – – – – – – – – –
c4a38398-79eb-53a7-b65b-12a225f0b567 | note | RESPONSIBILITY: SE/PE/SPE
044dc338-f1f7-581c-8411-90966b8be723 | note | – – – – – – – – – – – – – – – – –
8a2a20be-432c-59f3-92f1-e900b70db791 | note | VERIFYING DOCUMENTS: This ITP
f2c4dbf5-cb16-50d9-a5d2-5a57b023e48c | date | Date Completed:
| checkpoint | 4.4 Materials Inspection
e4c15a54-9cea-5759-a7f9-7d1b7ad39f7b | note | REFERENCE: IFC Drawings VR 631
3882f9a3-5349-5464-9f6d-6410eb5a230b | note | – – – – – – – – – – – – – – – – –
493a2b32-9b52-5315-b844-95f7e16cd06f | note | ACCEPTANCE CRITERIA: Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
f7f5af58-8ae8-5e9f-af39-4812127cca27 | note | – – – – – – – – – – – – – – – – –
c3f480ea-1764-54bf-b19e-820655ac6986 | note | METHOD: Visual
a9f6fbe7-6b26-53db-a7ff-bb45b64686f0 | note | – – – – – – – – – – – – – – – – –
d0ac0203-886e-5f1f-98c2-5e5b2f7b95ef | note | FREQUENCY: Each component
231a5f64-ca6c-5644-b21a-084ca08272f5 | note | – – – – – – – – – – – – – – – – –
677fcd64-2f81-506a-8ba7-055f66ad768b | note | CATEGORY: IP
cd7d13ed-f8a6-5f4e-b383-773c6fef7dd8 | note | – – – – – – – – – – – – – – – – –
cdbe72b0-db78-5ea0-afdd-bd1ad6af6c43 | note | RESPONSIBILITY: SE/PE/SPE
98e14dec-bb4e-51de-9712-b9cbd4ccd417 | note | – – – – – – – – – – – – – – – – –
93ae9f20-e083-54d9-8f39-c6ef03af3aab | note | VERIFYING DOCUMENTS: This ITP
43f04db6-2316-542c-a983-d26911dddac4 | date | Date Completed:
| checkpoint | 4.5 Materials Inspection
b50963fa-40cd-54e8-81ea-ddbd6f020398 | note | REFERENCE: IFC Drawings VR 631
7c8d5246-b6a4-53a9-a0c5-dd5471ff223e | note | – – – – – – – – – – – – – – – – –
70c084a8-5247-5c83-bc88-78dbced05d24 | note | ACCEPTANCE CRITERIA: Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
ed6732ea-73d2-58e5-95d9-f9fb66aebc29 | note | – – – – – – – – – – – – – – – – –
5d49762d-edd5-537b-b81c-48d74ef810f8 | note | METHOD: Visual
a7b098be-a2db-566a-a7c0-b052755467c4 | note | – – – – – – – – – – – – – – – – –
f169f40a-8737-518c-9889-92502341cf7f | note | FREQUENCY: Each component
eb551fa5-ce81-5301-bdfe-2d993c5ea3c0 | note | – – – – – – – – – – – – – – – – –
22ccfd6c-5d0e-5454-9dac-1c6dd20dbc48 | note | CATEGORY: IP
d22d8281-5168-5677-b442-14de671e9f68 | note | – – – – – – – – – – – – – – – – –
f967bcc2-bfe8-5afa-9333-f64edf833579 | note | RESPONSIBILITY: SE/PE/SPE
c8402184-fba1-5228-b099-8fc6b047f7e5 | note | – – – – – – – – – – – – – – – – –
d8e80e69-45f4-502d-a55a-9b8e06fc2f6b | note | VERIFYING DOCUMENTS: This ITP
984dec67-c896-5cde-aeb2-54829e4192e3 | date | Date Completed:
| section | Installation Activities
| checkpoint | 5.1 Bearing / Mounting Surface Preparation
909b39e2-6899-5709-a336-50987c9f81dc | note | REFERENCE: IFC Drawings Product TDS
a0a0e6a8-8424-55ab-b1d4-fcca113099af | note | – – – – – – – – – – – – – – – – –
bf9128f9-ad4c-5cd8-a850-e53e77cba0fc | note | ACCEPTANCE CRITERIA: Ensure the bearing surface clean and free from loose particles that will prevent solid seating of the parts
8691abb6-34ca-555d-a921-f050fc618980 | note | – – – – – – – – – – – – – – – – –
4ba37971-2f81-5322-a0fe-9c5c5331e826 | note | METHOD: Visual
4fb6044d-bb99-5353-8d0a-2e67e90637a5 | note | – – – – – – – – – – – – – – – – –
9611cabc-5d17-576c-8dc1-cfcb39100341 | note | FREQUENCY: Where applicable, each installation location
f022d1e3-deb6-5ff1-99cc-ca5241eb7f5b | note | – – – – – – – – – – – – – – – – –
d43e6027-1135-5b0e-816e-404e7959fadd | note | CATEGORY: IP
7195d153-5052-5893-90a4-472971dc7eb0 | note | – – – – – – – – – – – – – – – – –
f8ccd01c-4fed-5310-b143-6ca578fdd383 | note | RESPONSIBILITY: SE/PE/SPE
be5f15f8-f084-5029-b324-9d1f163794bb | note | – – – – – – – – – – – – – – – – –
e3ce4ccd-8dde-5246-9522-5a56a822ac9c | note | VERIFYING DOCUMENTS: This ITP
f7bc1530-c8cd-5b55-bb70-8de654d1b2a1 | date | Date Completed:
| checkpoint | 5.2 Structural Steel Handling
5b7a2467-70be-58e1-b859-664b30970b00 | note | REFERENCE: 630.09, 631.14
5b60b148-d349-5d4e-b170-ec1aac8db525 | note | – – – – – – – – – – – – – – – – –
725ae0f9-66ab-53a9-b459-38540fa7cbb8 | note | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
fe8aca8c-f70f-5c1b-a5f3-91f592c43da6 | note | – – – – – – – – – – – – – – – – –
1060d1e8-dff3-5456-ab4e-3b5137b9afc9 | note | METHOD: Visual
9fb3c4fa-1b23-5bb1-86a4-3fe5cdd28d8a | note | – – – – – – – – – – – – – – – – –
992306e5-d1c5-5e17-8308-e2dbfee31ece | note | FREQUENCY: Each component
17bc16e2-45e4-5c75-81b0-381fa6c856aa | note | – – – – – – – – – – – – – – – – –
02a2ac09-b9af-5b6c-9f35-f583b540ee58 | note | CATEGORY: IP
982d8e50-7c9d-5709-a945-bed1663aa482 | note | – – – – – – – – – – – – – – – – –
2ee6ac8b-0ffc-5e59-8a09-82441bc37511 | note | RESPONSIBILITY: SE/PE/SPE
cdaf6525-0e00-59ec-9e75-15465ac675be | note | – – – – – – – – – – – – – – – – –
cd4a4ab9-8378-55bb-9f20-fed1a7e0ace8 | note | VERIFYING DOCUMENTS: This ITP
ed66e667-c9ea-5b23-8210-060ebdff7897 | date | Date Completed:
| checkpoint | 5.3 Structural Steel Erection
d906088b-89b1-5233-8aa7-04ae27a33427 | note | REFERENCE: AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
481c6762-21c8-59a8-8e05-47c85fbf7f47 | note | – – – – – – – – – – – – – – – – –
9d4b8aed-390e-5421-88a3-5687a4ef5835 | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
ba256092-a55b-52e0-a5d0-01801ba9523c | note | ○ Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
522b1ebb-6a8c-5bae-8309-a28a1f544e8a | note | ○ Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
bd253ff0-3443-557c-8bcb-49aebc71b856 | note | ○ Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm
1d502d65-ff6e-53ec-92de-386b59a6a944 | note | ○ Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
5557d915-b702-54df-9c0f-4e5590b34046 | note | – – – – – – – – – – – – – – – – –
c4aa6e41-71e5-5e8c-8a6d-88f4fb7d5a4d | note | METHOD: Measure Visual
a065c3e9-6efa-5f17-b265-750c64ae7490 | note | – – – – – – – – – – – – – – – – –
13e6b0ea-da10-560c-9563-61fff52f52a3 | note | FREQUENCY: Each component
b5899223-4fe5-5d5b-82c0-b0efd7e348be | note | – – – – – – – – – – – – – – – – –
6e4e16c5-e581-5c78-9cf9-0579864ddc60 | note | CATEGORY: IP
5e8add9c-1eed-5687-ae00-ce35a07abe98 | note | – – – – – – – – – – – – – – – – –
7041da97-413a-51ff-b012-5c9e3803257d | note | RESPONSIBILITY: SE/PE/SPE
ff1f8a5b-c8d3-5d87-a7bb-6abb115733ba | note | – – – – – – – – – – – – – – – – –
678b6130-20fd-5cba-ba71-a3c0ba02a868 | note | VERIFYING DOCUMENTS: This ITP
389a8162-3f12-5308-9954-4f7d9db1ae1e | date | Date Completed:
| checkpoint | 5.4 Fastener Tightening - Snug Tight Condition
902592f3-466f-5829-b359-14fe71e33a14 | note | REFERENCE: IFC Drawings VR 630
e90bfa9a-a642-51af-ba42-7af7ba37d427 | note | – – – – – – – – – – – – – – – – –
1551de8e-f147-5a57-b27a-b4f8e430ae77 | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
c202ba40-299d-5eb6-88d2-c0cd5140a90b | note | For posts base plates, the arrangement is to be (from the base plate):
a9eda965-2645-5603-8bd8-36ed02068339 | note | – Base Plate
87588c18-96ac-5fbb-8d75-3dbcf528a652 | note | – Washer as specified
c8f28365-07bd-56c7-bf8d-9481d8efb898 | note | – Lock Nut as specified
815901cc-629e-5f79-be81-a42efd1ee006 | note | – Nut
2e32a635-5a46-501b-a21a-e5f81730a099 | note | – Bolt protrusion (1 clear tread)
96cd2534-a091-5038-91d6-16dcc7692065 | note | – – – – – – – – – – – – – – – – –
5235d99c-0edd-5e72-8e04-96fb3d7fc66a | note | METHOD: Visual
4f021e42-22ba-5771-82ab-cdf47f529d92 | note | – – – – – – – – – – – – – – – – –
2dc744e6-539d-5157-b3f6-75fbb91b8ba4 | note | FREQUENCY: Where applicable, each bolted connection
f697e389-9457-5cc5-ba4f-4ad7c4535cc7 | note | – – – – – – – – – – – – – – – – –
6a95fb44-053e-53e6-88d6-a628db9ef1a1 | note | CATEGORY: IP
4e4e03e0-b77c-5fbe-8a29-8a3e57b8e221 | note | – – – – – – – – – – – – – – – – –
dbe39650-61dd-54a6-b011-70273d959c56 | note | RESPONSIBILITY: SE/PE/SPE
7091ead0-1669-5129-96db-0939c189a778 | note | – – – – – – – – – – – – – – – – –
a7d90e46-7a29-5c08-93a9-659408447306 | note | VERIFYING DOCUMENTS: This ITP
5b73cfba-c596-53b6-a7e6-ffca89b7f0c5 | date | Date Completed:
| checkpoint | 5.5 Fastener Tightening - Snug Tight Condition
d9b66b83-6873-5dd2-af6c-162b81a91f50 | note | REFERENCE: IFC Drawings VR 630
39217c04-974f-5e53-9005-1ebfa11a41d7 | note | – – – – – – – – – – – – – – – – –
6c755a7b-f559-5c4a-92d9-14ce2f0928e9 | note | ACCEPTANCE CRITERIA: Washers shall cover the hole or slotted hole completely by 0.5 x bolt diamter.
652091b6-8180-5a80-9fe8-b8ee2d23a975 | note | ○ Tapered washers shall be positioned if specified.
1a6b2788-9743-5ae9-8742-51c745485ee1 | note | ○ Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
86139dc0-7e7f-53e8-8a27-cc362421730d | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
fdcb904e-4b07-561f-800a-8d086638a1e7 | note | – – – – – – – – – – – – – – – – –
14582ed0-99fa-5957-860b-97315e2f950e | note | METHOD: Measure Visual
8a7c959e-94e3-5c8b-89bd-827d6ade9eb5 | note | – – – – – – – – – – – – – – – – –
b0b4c3d2-46a8-5c80-a70a-d27e6babb22f | note | FREQUENCY: Where applicable, each bolted connection
c5c9be4f-ab58-5285-aa54-55bdd934ac63 | note | – – – – – – – – – – – – – – – – –
2413e9b8-0fc7-575b-9f73-77e5affb379a | note | CATEGORY: IP
2245d4cc-15e6-5917-9c1d-6b88ad01e159 | note | – – – – – – – – – – – – – – – – –
a7e70c91-f432-5204-bed5-2ca1a96bc979 | note | RESPONSIBILITY: SE/PE/SPE
63bec8b4-7cbe-5d48-9958-f4696c48e9da | note | – – – – – – – – – – – – – – – – –
5b5c2677-7a6e-5a34-b87c-4e03c5d11810 | note | VERIFYING DOCUMENTS: This ITP
84e46c57-4b02-5762-9054-5dd7c248717c | date | Date Completed:
| checkpoint | 5.6 Survey Conformance
73e8df7f-3bf2-54bb-9005-2caa4203c8a4 | note | REFERENCE: IFC Drawings AS4100 Clause 15.3.1 - 7, AS5131 Appendix F, Table F3
bc2761ce-047e-55b1-9078-e8b3e424207c | note | – – – – – – – – – – – – – – – – –
66f7ba5e-3f66-5959-8e7a-bc01beaa215b | note | ACCEPTANCE CRITERIA: Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
65060cca-94e1-58dd-9f4b-9f1023d3b3a7 | note | Departure from RL = ±10mm
81618609-0afc-5ecf-86d2-ebf1fe3ff159 | note | Departure from plan position = ±6mm
ee2757af-0e00-5c67-ade8-1be417e9a1bd | note | Departure from alignment = ±6mm
894839df-55e4-57e7-a835-139048cef249 | note | Irregularities in alignment = 25mm in 30m
7f716bbf-9ce8-5f91-a018-9931e7bbfeba | note | Projection of bolt = +25mm, 5mm
74b24105-ae2b-5b64-9a67-8c751806bd80 | note | Location of beam = ±3mm
de77c721-9c5d-5b36-9d5f-31cdc4415a6a | note | Location of column = height/500, 10mm max.
46e7ec9b-cb81-5aeb-b202-a252a2d3fa6a | note | – – – – – – – – – – – – – – – – –
677e18ad-5b99-56f8-9648-bcde1ab354b4 | note | METHOD: Measure Visual
ed0ebc8f-718e-5de7-ab3e-ed9b5a462fc3 | note | – – – – – – – – – – – – – – – – –
4a4290b4-f20c-5f34-adf0-21a0ede063e4 | note | FREQUENCY: Each element
18dfde7a-53be-5165-8ddb-fef90a2f5037 | note | – – – – – – – – – – – – – – – – –
d82ed0ab-658e-5bd3-8130-2c3d422a39f7 | note | CATEGORY: HP*
18af9f30-f70c-5588-b979-2ab294c26851 | note | – – – – – – – – – – – – – – – – –
bff0b20f-9e36-52e1-a00d-9712d45fb4b4 | note | RESPONSIBILITY: PE/Surveyor
83c11df8-874f-52dd-9bd7-fb95fb73ab1a | note | – – – – – – – – – – – – – – – – –
56ad6857-94a9-5161-9469-fd3fa98d8562 | note | VERIFYING DOCUMENTS: This ITP
8055f74b-cc25-5b2a-b282-346309c7e84d | date | Date Completed:
| checkpoint | 5.7 Base Plate Formwork Construction & Placement
7494e5af-5a0c-5514-a798-671f79f853f6 | note | REFERENCE: IFC Drawings
ecd263aa-1150-5f6b-a903-2d01b78668de | note | – – – – – – – – – – – – – – – – –
7fbf05ac-025c-5c8f-abf0-2d786e89e506 | note | ACCEPTANCE CRITERIA: Dimensions as per drawings to achieve the profile.
f65bcce2-8210-5026-997b-10aeda6ed54a | note | ○ Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
f461e8ed-4a09-59b8-9fac-5c32365d5dbf | note | – – – – – – – – – – – – – – – – –
52424e64-4251-5652-90b1-8d06bf1d0748 | note | METHOD: Measure Visual
79c53382-ba76-5663-995e-5b2e5d7594b3 | note | – – – – – – – – – – – – – – – – –
e6824297-cda0-5b61-9e7b-dfec9de06c1d | note | FREQUENCY: Each post location
468ca9a8-41b6-522b-a6de-2759abbf8a73 | note | – – – – – – – – – – – – – – – – –
41d3b0f4-d8b6-5cfb-99ba-5f260713de2d | note | CATEGORY: IP
a2ab8af2-48af-5ba4-9629-c58465c13c42 | note | – – – – – – – – – – – – – – – – –
8b9f603b-698a-5f82-bf9c-e74cf2bf8877 | note | RESPONSIBILITY: SE/PE/SPE
10fbf9ce-0080-58b4-961f-a59b5e4b57d1 | note | – – – – – – – – – – – – – – – – –
760be2f9-492a-5a15-b4b4-3e3d6311a013 | note | VERIFYING DOCUMENTS: This ITP
aa8b235c-213c-5f33-8baa-b292ae9d8544 | date | Date Completed:
| checkpoint | 5.8 Pre-soaking Concrete Surface
9bfa0cf8-00b5-5c05-8510-2f762a7dec86 | note | REFERENCE: Product TDS
a46db344-dca9-56af-9d2d-e5ca72f4fa9d | note | – – – – – – – – – – – – – – – – –
3b96d95f-353c-53d5-bfbc-7a621f0894ec | note | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
406e4edf-5de3-5f66-8e02-ec461e1c3df9 | note | ○ Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
87218078-aea9-55ee-94aa-fb5770dbd6c4 | note | – – – – – – – – – – – – – – – – –
1dfec62a-408b-5e44-8552-d8687d27eab6 | note | METHOD: Visual
12ecb538-6ec0-5bb5-8ad3-507a4a5c02d4 | note | – – – – – – – – – – – – – – – – –
3eb08e72-9dd5-55a0-8120-f05ef19de456 | note | FREQUENCY: Each post location
6346d5fe-ec4d-53aa-8a15-9c8f848dabb4 | note | – – – – – – – – – – – – – – – – –
63e914ef-94fe-559d-b471-ef7c1201973c | note | CATEGORY: IP
81a18b99-2d12-5e8d-a120-5b3757cd8e33 | note | – – – – – – – – – – – – – – – – –
c36bf2ee-f52c-5708-9d05-fe77c217af07 | note | RESPONSIBILITY: SE/PE/SPE
ef4113c0-f961-57a7-9e3a-05247536f2db | note | – – – – – – – – – – – – – – – – –
c3084a24-0cbb-5b2c-bfa4-9080e08532a8 | note | VERIFYING DOCUMENTS: This ITP
f7939b1f-da1b-5b32-883d-65d810aa085e | date | Date Completed:
| checkpoint | 5.9 Weather Conditions
de04d12e-39f6-5b86-a411-96ca4735ca4e | note | REFERENCE: 610.17 Table 610.171
db81cf0d-4d6e-5f01-95c4-622da531cd95 | note | – – – – – – – – – – – – – – – – –
3beee39a-dc15-57f5-84fa-671b422613f0 | note | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
ca3d6dc1-37de-548f-8bc7-90e38620d08c | note | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
e6e69aef-750c-56fa-94cc-3d43c2d9ff23 | note | Record: Required information on the Grout Pour Record.
f61345f1-d2ba-565d-b19f-7d7bd33b4508 | note | – – – – – – – – – – – – – – – – –
7e0685c3-6ab3-5662-9ded-1bc8a0ff6089 | note | METHOD: Measure Visual
82c85939-f95b-561a-b4ea-3e217459996c | note | – – – – – – – – – – – – – – – – –
d4808221-00d3-58c4-9d18-ccae79168d24 | note | FREQUENCY: Each lot
ac86092c-43a6-5a8d-b080-05ffcb56b5e1 | note | – – – – – – – – – – – – – – – – –
ffbdb9bb-4c75-5c65-8b78-e2e3499d809a | note | CATEGORY: IP
bf59f8b6-9818-5260-a93a-8b7cff028d9d | note | – – – – – – – – – – – – – – – – –
dbda5b95-a48e-59c0-9cd2-71d3102605fc | note | RESPONSIBILITY: Foreman, SE/PE/SPE
21d2a2ac-89fc-5840-9be8-3a6726e96412 | note | – – – – – – – – – – – – – – – – –
d1b76cba-58f4-5254-b68f-5f09f9c09af6 | note | VERIFYING DOCUMENTS: This ITP
1c493179-139f-5f14-a9cb-ca5ad8daa574 | date | Date Completed:
| checkpoint | 5.10 Mixing Product
9b71886b-8a93-56f4-830a-1833e6c8270a | note | REFERENCE: Product TDS 610.28
849130c5-b500-5ba1-95ce-adbd9f4819f1 | note | – – – – – – – – – – – – – – – – –
5c1d4375-491d-5ab4-a9a4-20d2139741ca | note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
07471dc4-5e29-5833-b525-8fdf9c4e5673 | note | ○ Only whole bags to be mixed with potable water.
417e79df-4e0f-5a56-aca7-e8c95eafaea3 | note | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
6efe9d2c-6bb4-5f2e-a0aa-4e4014d3b4c3 | note | ○ Product poured into the mixer slowly.
c84f7888-fc52-5562-a56c-bf295b72b2a9 | note | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
a3bba657-8b62-5af8-975c-fbd69501b557 | textbox | Enter: Required information on the Grout Pour Record.
e3ccdde1-b46d-5c8e-804f-c8132cce223e | note | – – – – – – – – – – – – – – – – –
c81a303d-0c90-5267-91dc-cabac1b6bb35 | note | METHOD: Measure Visual
b98a401c-0f3f-5d56-847b-e348c2886a92 | note | – – – – – – – – – – – – – – – – –
c4d984aa-91ad-5198-8808-893a1d7dfbb1 | note | FREQUENCY: Each batch
b0c35d06-9c74-5334-8ae0-c91c461e4039 | note | – – – – – – – – – – – – – – – – –
8fa51c16-8160-5363-908e-d8f2cbcdb408 | note | CATEGORY: IP
c261a69c-24ef-5e38-9102-6a185f921a71 | note | – – – – – – – – – – – – – – – – –
ba7552ee-cba4-5b7d-8f9e-2a5052b13cc6 | note | RESPONSIBILITY: SE/PE/SPE
92464402-7965-55ca-a6bb-5472e4e19015 | note | – – – – – – – – – – – – – – – – –
3fb78345-7461-5b0f-864c-846489e99461 | note | VERIFYING DOCUMENTS: This ITP
e432b470-0d4c-574e-9e3f-c2d517b660cd | date | Date Completed:
| checkpoint | 5.11 Product Testing - Compressive Strength Cubes
0d1af1b1-cbc3-51db-a00d-aea50aadcdee | note | REFERENCE: 610.28, 610.33
18a2ea5e-38a8-5b15-bc97-b5e833b22f6c | note | – – – – – – – – – – – – – – – – –
96a71ecb-8597-5307-b5c2-42669e7c3caf | note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
a5596a49-8b2a-5816-99d8-302897ff7221 | note | ○ Testing is be in accordance with the following frequencies:
0a5d1b0f-8416-56b9-aa1e-4fb6a58c27ff | note | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
109d2e62-2f2d-5096-8c29-249188a0a238 | note | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
3297b0c3-93be-5a7b-986e-19067ac6c849 | textbox | Enter: Required information on the Grout Pour Record.
7e6c5a9b-baae-53ac-b7bd-0df192ac4dda | note | – – – – – – – – – – – – – – – – –
b81cdec9-439f-50ef-8948-8e0a44a7e01a | note | METHOD: Test
89a5e3d2-1e48-5af4-8ae4-62c5d489debf | note | – – – – – – – – – – – – – – – – –
e7db39a6-279d-510f-905b-7d77ded4e884 | note | FREQUENCY: Each lot
e238b7fc-1cfe-5ff2-b5c5-1ff57936ede9 | note | – – – – – – – – – – – – – – – – –
bbdd3c9c-7a22-5aad-a051-a6a43fd08c82 | note | CATEGORY: IP
dbb5ce6a-b56b-5da2-a160-0f12ffa5f265 | note | – – – – – – – – – – – – – – – – –
89070aae-3329-5c48-b2d4-dcbb6a50a17b | note | RESPONSIBILITY: Tester, SE/PE/SPE
3c6dcc10-0202-5328-a1f5-e91aad9a914d | note | – – – – – – – – – – – – – – – – –
fa08af79-c597-5934-95c9-ff553c30194b | note | VERIFYING DOCUMENTS: This ITP
31a02fb0-69d8-5bd7-b22d-cc3d0b3a6e7d | date | Date Completed:
| checkpoint | 5.12 Placement & Compaction
55ed5723-fd68-58a5-82df-d058b3cbf68c | note | REFERENCE: Product TDS
b71a7c4a-1f50-5acb-92d5-b1d85947816b | note | – – – – – – – – – – – – – – – – –
cd77e5ac-bace-5ce6-ba5d-fe0a6249ea54 | note | ACCEPTANCE CRITERIA: All batches are traceable.
7a7c1ef0-b9d9-5dfc-b361-816060ee885c | note | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
be1cd4f8-b37c-5cfb-abd5-aba19b9a6ec9 | note | ○ Product should flow to all areas and self consolidate.
3794cee2-8b7f-547b-832f-cae53aa160aa | note | ○ Product that stiffens or is showing signs of stiffening shall not be used.
67b2f3d8-1efd-5625-a62d-771e6f540397 | textbox | Enter: Required information on the Grout Pour Record
3c98ba03-73f1-5d9d-a706-5c671447414d | note | – – – – – – – – – – – – – – – – –
51c516be-486f-50a7-b8d7-01f52d9ad306 | note | METHOD: Visual
3969e6bd-0c8a-5e37-9448-cd0e45270dd8 | note | – – – – – – – – – – – – – – – – –
2ad24021-9281-51a2-ac47-de6cf1115247 | note | FREQUENCY: Each post location
8090aa51-191f-5f90-b616-1355b7efee1b | note | – – – – – – – – – – – – – – – – –
3323d8f0-6d06-5894-86a7-a2b475ef1888 | note | CATEGORY: IP
a505a31d-9154-519c-bc7f-a5cb81949d48 | note | – – – – – – – – – – – – – – – – –
d6a20d0a-a42c-5251-b973-00842680c296 | note | RESPONSIBILITY: Foreman, SE/PE/SPE
38a1093b-492c-53df-9cb5-75d0449151a4 | note | – – – – – – – – – – – – – – – – –
1d9c8c46-cd7c-55b1-b942-57366f8bd397 | note | VERIFYING DOCUMENTS: This ITP
cf06c4a1-77c5-569f-8c02-2821ed1290c1 | date | Date Completed:
| checkpoint | 5.13 Surface Finishes & Protection of Works
c86ec3b0-83e0-5fa7-b026-d2e5498b6dd4 | note | REFERENCE: IFC Drawings 610.17
f58fe14b-1fa7-5471-8ac9-be14052f132b | note | – – – – – – – – – – – – – – – – –
f2482c51-cd7e-51b6-bede-4300c79ff743 | note | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
c9f6763e-ac67-54ba-afab-c0b47889157d | note | ○ All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
83cf87a3-10d2-53ef-8cf2-08abae7fc2e0 | note | – – – – – – – – – – – – – – – – –
b184db20-655c-5fb9-9b58-a6031d66b174 | note | METHOD: Visual
594f1038-1120-5beb-9219-789ecfc7f525 | note | – – – – – – – – – – – – – – – – –
63ff8e40-fe27-581a-9462-2bfa435bc450 | note | FREQUENCY: Where applicable, each post location
e822b1e7-79bd-5e83-bbfe-da666d87be31 | note | – – – – – – – – – – – – – – – – –
73fefb6c-9bc6-536a-85c1-fa486289edb6 | note | CATEGORY: IP
bdbe686c-a55b-51fc-8f86-1e9ae22da449 | note | – – – – – – – – – – – – – – – – –
d3887502-4171-5e4d-9733-0834d101186d | note | RESPONSIBILITY: Foreman, SE/PE/SPE
6f014ad4-6dc0-597c-992f-7de0a672b8e6 | note | – – – – – – – – – – – – – – – – –
0e33ec44-3453-5534-a86b-b77fb3dc83f5 | note | VERIFYING DOCUMENTS: This ITP
b07528f3-8812-56bc-b819-f39a74d5658d | date | Date Completed:
| checkpoint | 5.14 Curing
b7b09716-9d8b-5871-a3d0-119c0c47724e | note | REFERENCE: Curing Methodology 610.23 Table 610.231
1f2761d7-4d98-5735-8d5c-76cb8487dbeb | note | – – – – – – – – – – – – – – – – –
09676e3f-1495-5548-ae6e-87f26f452800 | note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
12520440-5a48-53fd-a1b6-ff119e36fe65 | note | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
7cc29ab7-0415-5fd0-a83c-95141ee2fa02 | note | – – – – – – – – – – – – – – – – –
96ac61b8-7082-578c-bda5-fa7f7ef6949c | note | METHOD: Visual
245cd506-8e97-5a93-8396-1e671ff6b556 | note | – – – – – – – – – – – – – – – – –
967410ae-13c1-5cd8-ae06-0f251e65accb | note | FREQUENCY: Where applicable, each post location
1c5c2034-36a2-57ee-ac47-a6ae9aa480d3 | note | – – – – – – – – – – – – – – – – –
6708c31c-7f2b-58d4-9dfa-8344648dbe6f | note | CATEGORY: IP
3ea3d624-ff25-57b0-adb2-134a940b3d76 | note | – – – – – – – – – – – – – – – – –
9bcdf00d-1a84-5944-b92e-628f4eae56fc | note | RESPONSIBILITY: Foreman, SE/PE/SPE
954b6b94-5fac-5329-b337-0d0be32dcdf5 | note | – – – – – – – – – – – – – – – – –
db1e0631-da94-5338-8d89-6a996f040402 | note | VERIFYING DOCUMENTS: This ITP
2d2fa3ad-c84a-569a-8512-cc4d6d76a680 | date | Date Completed:
| checkpoint | 5.15 Architectural Steel Erection
411f45f4-4456-5c23-a5d3-f9652b99ab6c | note | REFERENCE: AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
5b61c660-e404-5864-a26f-71ae46fa0a29 | note | – – – – – – – – – – – – – – – – –
d5452fff-83d7-5db1-85a7-22880eb3a218 | note | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level and square
474d9227-e2ba-5c83-a645-d6bb427c9103 | note | ○ Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely
993a0480-5979-50d4-83ce-c5fea56d4fbd | note | – – – – – – – – – – – – – – – – –
e28c0195-7b46-5b51-9f70-77a80134ef9c | note | METHOD: Measure Visual
ee421339-abd7-551c-b030-5ec57c785c1a | note | – – – – – – – – – – – – – – – – –
88ce866f-700d-5130-b2b8-381ba79b294d | note | FREQUENCY: Each component
ee007ed9-98ee-5869-a552-ff0f85a39561 | note | – – – – – – – – – – – – – – – – –
9fd83fe1-3c2e-5b0b-affd-54cdf7186119 | note | CATEGORY: IP
43824180-8197-5374-9505-789eb7820027 | note | – – – – – – – – – – – – – – – – –
20093675-30f5-5c02-a6e5-392231784da0 | note | RESPONSIBILITY: SE/PE/SPE
87d02455-48eb-5484-abf5-9567d085d29b | note | – – – – – – – – – – – – – – – – –
460a9a58-7e76-56b4-9b4d-333bb850ac70 | note | VERIFYING DOCUMENTS: This ITP
ebede3b6-ec4f-573f-a068-e269721d2f54 | date | Date Completed:
| checkpoint | 5.16 Architectural Steel Erection-Fasteners
6ecc7b07-67dc-5538-9b32-91d80165db7e | note | REFERENCE: IFC Drawings VR 630
2358f4a5-1391-5228-a2a3-3a6b79c9a988 | note | – – – – – – – – – – – – – – – – –
55bcf192-d99e-5403-92ad-b51ffa390af0 | note | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
68e3f5b4-c044-5e98-ba1e-0526dcf1e560 | note | For architectural/Security screens, the arrangement is to be (from themounting post):
81412b19-93a5-5545-9488-77ef34ca6445 | note | – Post
385ead42-c001-5fa7-a4a0-542d9ec62a60 | note | – Washer (s) as specified
2e062e7e-f451-577c-8604-7d109de86cb2 | note | – Insulating washer
7294e174-8489-56f8-bd53-4e85406e0cf8 | note | – insulating bush
14f9ceca-5036-5906-9022-d700079c0584 | note | – Insulating washer
d6612cfc-d8a0-5763-8583-5cb7066fae94 | note | – washer as specified
c405b4df-2883-5e94-a65f-7e8de537b6a4 | note | – Lock nut
e60667d4-c95f-5e7f-92a3-9f02918a7bb8 | note | – Nut
bead8ac4-09a1-5f73-8816-c066037e5681 | note | – Bolt protrusion (1 clear tread)
4565aae7-89e7-58fc-bcc2-d34abae601e9 | note | – – – – – – – – – – – – – – – – –
6b18fea4-8c1a-5357-9067-21903bf7673c | note | METHOD: Measure Visual
44ecf696-c720-540b-95b9-e60a2284b4e7 | note | – – – – – – – – – – – – – – – – –
94f8ad67-04a6-5f48-b4d5-a4c728a3ab05 | note | FREQUENCY: Where applicable, each bolted connection
150f16bd-d9a4-597c-9e7b-321c92de0f83 | note | – – – – – – – – – – – – – – – – –
7c99ac79-6349-5be5-9492-61eb9364280e | note | CATEGORY: IP
2c85d2a5-0a5d-517f-983e-ffa7384c627b | note | – – – – – – – – – – – – – – – – –
24a11027-06db-516a-acce-8e6bdfc94947 | note | RESPONSIBILITY: SE/PE/SPE
d733ef9b-6ad3-5938-8b10-1087d606118e | note | – – – – – – – – – – – – – – – – –
f4071065-fdf7-5bec-a749-b49c50e10e4f | note | VERIFYING DOCUMENTS: This ITP
1142a3d7-313d-5edc-847f-471ebc8224a9 | date | Date Completed:
| checkpoint | 5.17 Installation of Electrical Isolation Materials
c54ac554-3f13-56c6-8e02-8bee6ec8e504 | note | REFERENCE: IFC Drawings
de5555f6-983e-5ce0-921b-976a5fb464dc | note | – – – – – – – – – – – – – – – – –
b12735fb-70e0-5e92-9c8b-4ca37a3e989f | note | ACCEPTANCE CRITERIA: Installation of Electrical Isolation Material in locations specified on the IFC drawings.
6351b676-71c9-594f-9afe-781b3edddee5 | note | – – – – – – – – – – – – – – – – –
8451ba0b-549e-5306-b42a-fb2a6e10831e | note | METHOD: Visual
0793e2b8-f54e-5483-9e7d-02e69afba980 | note | – – – – – – – – – – – – – – – – –
9cc634af-5531-5f5a-8ec5-cdd2541fcf09 | note | FREQUENCY: Each component
6b5261af-a50b-5667-bf20-c6b2260c741e | note | – – – – – – – – – – – – – – – – –
b0e3755e-001f-5a82-b570-8ad53fe4e2ba | note | CATEGORY: IP
a5e8b8b3-2eb0-543b-9457-6e4060b4dbd6 | note | – – – – – – – – – – – – – – – – –
631f89f4-5fc4-5763-a5b8-c8df635d5e00 | note | RESPONSIBILITY: SE/PE/SPE
46f4475d-94ee-5ac9-929a-fe9ec709e880 | note | – – – – – – – – – – – – – – – – –
d9da9c92-c36f-54aa-acb3-4bcf5a493473 | note | VERIFYING DOCUMENTS: This ITP
4652c51e-ff2a-5117-90e3-65145fac639a | date | Date Completed:
| section | Post-installation Activities
| checkpoint | 6.1 Inspection of Coating
5dd988b3-dd7f-5839-8954-533dde15bbc9 | note | REFERENCE: IFC Drawings VR 630
c8b428a2-5382-5cd6-832d-034ba6b549c6 | note | – – – – – – – – – – – – – – – – –
98889dc3-ffc5-5895-a699-77bae67ff2a0 | note | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
d0bcba86-3fc1-5f2e-ade9-ce669857a52a | note | ○ Where damage exists, it shall be repaired using an approved repair procedure.
73126c07-3af5-5a51-88e7-a5532c2abe8c | note | – – – – – – – – – – – – – – – – –
59732d79-043e-51ca-9b18-6b59f70541a0 | note | METHOD: Visual
c8563ab3-b1ac-5d0e-a89b-d2b771896193 | note | – – – – – – – – – – – – – – – – –
5a733e2a-24f3-5579-b64f-05375319ba2a | note | FREQUENCY: Each component
2146effa-67cb-5a0e-a83e-44ad9b0480eb | note | – – – – – – – – – – – – – – – – –
bbe248b5-d7e8-5b47-9be5-8fbde9e94303 | note | CATEGORY: IP
79d96d0a-0df7-5034-88cb-d59bc77cfd3d | note | – – – – – – – – – – – – – – – – –
4171feb4-38a2-5b42-858b-971b7ad16dfd | note | RESPONSIBILITY: SE/PE/SPE
9bebd783-7cd3-53b7-8cca-84ed5dc703a3 | note | – – – – – – – – – – – – – – – – –
1493dfdd-9dbb-5846-a534-052ab21adce7 | note | VERIFYING DOCUMENTS: This ITP
6ed2feef-af6c-55ae-93f4-90806d64236c | date | Date Completed:
| checkpoint | 6.2 Compressive Strength Test Results
503d5725-55d5-50ae-b788-593ba87cfe23 | note | REFERENCE: IFC Drawings Product TDS 610.28, 610.33
83f01d5d-ef4e-5a6a-853b-2e1ebdecfd74 | note | – – – – – – – – – – – – – – – – –
21454668-ef77-5de5-80fa-ce6d5f500c93 | note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
1fdc4f21-8580-503e-8b75-004c797bfb46 | note | ○ 28 day compressive strength per sample comply with the design strength.
e91ca24d-d45f-57ba-9186-b99e7817af86 | note | Attach: Compressive Strength Test Results
52b2d012-2da2-55fb-abf3-5f32cbd2eee8 | note | – – – – – – – – – – – – – – – – –
be2835a8-b505-5a6b-b455-9e62a419758c | note | METHOD: Document Review
4ea15f57-7bc6-59d7-b207-c872fcd4a28c | note | – – – – – – – – – – – – – – – – –
4853bfdc-1248-54f7-9770-9281edaffe82 | note | FREQUENCY: Each cube
2d00e3b0-23c7-552b-9ad2-48fb990a98f6 | note | – – – – – – – – – – – – – – – – –
f69c02c7-8ecc-5e2f-96dc-4477362caae1 | note | CATEGORY: IP
e2ad6aa5-0e9b-5823-9846-5db7499cdd0c | note | – – – – – – – – – – – – – – – – –
bd03b8a6-385e-524a-897c-587c9423b8ff | note | RESPONSIBILITY: SE/PE/SPE
8b392606-084f-5ea6-9b85-8cb34ed1c8cc | note | – – – – – – – – – – – – – – – – –
55c081ec-711d-50a7-bc3a-9ce8b34cc770 | note | VERIFYING DOCUMENTS: This ITP
3bde3944-476e-50f5-93eb-ac388099dca4 | date | Date Completed:
| checkpoint | 6.3 As-built Survey
b9f9e5be-b38c-5d1c-b210-6b6e4cf690ab | note | REFERENCE: IFC Drawings AS5131 Appendix F, Table F3
bf19be9c-aa1e-5810-9445-6058882b9e7e | note | – – – – – – – – – – – – – – – – –
1df1a46b-ac33-5bb1-9135-848c6e1a9a08 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
80418c72-2ad7-52d7-92f8-80615a19c9da | note | Departure from RL = ±10mm
e01c79db-2b91-5d32-b354-44354d85803e | note | Departure from plan position = ±6mm
93d0528e-5dd9-5326-bd5b-e979a3cd1b4a | note | Departure from alignment = ±6mm
161c214e-b223-53f3-a93e-0eb7b505c6e2 | note | Irregularities in alignment = 25mm in 30m
57395037-c14c-5a2b-a81f-2675b1b4ef45 | note | Projection of bolt = +25mm, 5mm
fb3719df-075d-50e5-8361-f3f673c46dc8 | note | Location of beam = ±3mm
cdeca45a-4f11-57be-b2be-3f0946c05d18 | note | Location of column = height/500, 10mm max.
8f28c26a-016e-56ea-88b4-8b09a025f061 | note | Attach: Survey As-builts / Survey Report
62a28fe5-791d-5bb7-8f53-e259d69fd811 | note | – – – – – – – – – – – – – – – – –
ad742a09-685a-5761-9d64-0d7c8a844685 | note | METHOD: Document Review
e519db12-bfcb-5697-b952-642b8f71e189 | note | – – – – – – – – – – – – – – – – –
c06d6ffe-d873-5651-b8ba-a0061311b2f5 | note | FREQUENCY: Each element
221beff5-de0b-5e14-ab0d-cc44a4f396df | note | – – – – – – – – – – – – – – – – –
5a47b616-0c9d-54a7-b711-f65d73ccff27 | note | CATEGORY: IP
bfc4a7dc-80ff-50fa-a252-f669b7c3825f | note | – – – – – – – – – – – – – – – – –
aaf1e232-e236-54cb-b405-0f6a6a3fd7e7 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
f73fc5d5-8ac6-575a-a7c2-b31c4c69f080 | note | – – – – – – – – – – – – – – – – –
7c7fc7de-2b50-546a-86a6-7381fac8c864 | note | VERIFYING DOCUMENTS: This ITP
970800d8-68d4-557e-8d06-c815ce5ec9fe | date | Date Completed:
| checkpoint | 6.4 Non-conformance Report (NCR) Closure
ee4baa96-a9ac-5fea-a089-6de591fdbbf5 | note | REFERENCE: MRPA Quality Management Plan
5be83803-03bf-5bdb-906c-207757a5d36c | note | – – – – – – – – – – – – – – – – –
496e407c-2004-58fa-a6f7-d1965bb7a931 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
b694aef0-68b3-5e75-aab4-0952fe479cda | note | – – – – – – – – – – – – – – – – –
41bc13d5-d404-58e3-a643-6a19a5b2c643 | note | METHOD: Document Review
6286ef5a-6d36-52c6-a20b-a8f16010f306 | note | – – – – – – – – – – – – – – – – –
36f65f50-33bb-5f25-b160-d469ae528bf6 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
0e0e260e-956d-5868-9980-e72827d4bdbe | note | – – – – – – – – – – – – – – – – –
ed3b0d4f-9598-5032-996b-974df8334f04 | note | CATEGORY: HP*
c55bbae1-6785-5516-a2d9-eda52994979c | note | – – – – – – – – – – – – – – – – –
c6363aab-1242-590b-83d6-6777b0d1b606 | note | RESPONSIBILITY: SE/PE/SPE
cad0c9ef-73d2-55da-ac12-52ed545703df | note | – – – – – – – – – – – – – – – – –
4bfbc9f5-013d-51e5-9f0a-ef8a33671b8b | note | VERIFYING DOCUMENTS: This ITP
91565af6-db4c-51b4-8e38-438c06e3bb00 | date | Date Completed:
| checkpoint | Final Inspection
deec6001-4370-5dee-afb7-6772d6434a7f | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3bdbf6b2-7f8f-5c9f-8168-446f30ff36a0 | textbox | Name:
c1af949e-70b2-50c4-be2d-4a00185fc5fc | textbox | Position:
8589f3c1-86ff-5bc8-abb4-197c6bb96fcd | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-072-CIV-Camms-Guard Rail Installation Rev 0 | itp | ITP-072-CIV-Camms-Guard Rail Installation Rev 0 |  | 54001b4b-9982-4c7e-8d71-3427066ff86d
| section | Referenced Documentation
| checkpoint | Referenced Documentation
82b23b62-3ef7-52f2-943b-c8eebaf58a71 | note | Document Title: ITP-072-CIV-CAMMS-Guard Rail Installation
65b2166f-415d-5dbd-b9d6-3be35907f464 | note | ITP Description: CAMMS-Guard Rail Installation
d4515f5d-5e17-5e7b-871d-871902935459 | note | Discipline (e.g. CIV/STR/RAIL: 072-CIV
aa6f9dc5-7bcb-5f02-8522-9f463af1be79 | note | Revision Number: 0
55ac858b-ea94-5857-9e01-5f61e905c19c | note | Revision Date: 23/10/23
436f7e8d-aa50-5083-9557-7715c2617a03 | note | ITP created by: Romualdo Magpantay
848508c3-009a-5f72-9b27-d949c377556f | note | ITP approved for use by: VM
d2d300e8-609e-57eb-9065-fede9343abf9 | note | 1.1 VicRoads Section 708 November 2018
54564107-6d0a-5fe2-acfd-2a1f3f42c601 | note | 1.2 VicRoads Section 703 April 2019
| section | Preliminaries - Materials
| checkpoint | 2.1 - Accepted Products and material confirmation
94963a06-e7db-575d-bf22-359acc3199c7 | note | REFERENCE - VicRoads Spec. Cl.708.04
d2c7ede0-ab0e-54a3-8ffb-524967c875cd | note | – – – – – – – – – – – – – – – – –
6a3273b0-be02-5c83-84e9-bff4049da44b | note | ACCEPTANCE CRITERIA - Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. Check design drawing for correct type of barrier, transitions and/or end connection and any additional material component requirements
374fb8d0-8d8c-541a-a48a-3a1a1fd56d19 | note | – – – – – – – – – – – – – – – – –
9fc2a447-b94f-584f-a6d9-c79526124e17 | note | METHOD - Document Review
cc1fbb7a-506f-51d5-b647-a9d12f4ea472 | note | – – – – – – – – – – – – – – – – –
79fb14b8-a0f3-57fe-bf24-af1336a16f27 | note | FREQUENCY - Each member material component
9db0e6f7-eb1b-5bc4-add3-71c8c6757d9c | note | – – – – – – – – – – – – – – – – –
59e20f07-c69d-5d4f-94ec-4af1a6e217d2 | note | CATEGORY - HP*
560abb65-c407-5e80-a285-820c032618bd | note | – – – – – – – – – – – – – – – – –
78bfd3cc-2ef8-54e1-b9ff-f4f52711a4b9 | note | RESPONSIBILITY - Nominated Authority
f1d76b4b-4259-5a6a-81a1-4db483ad2933 | note | – – – – – – – – – – – – – – – – –
b2040bb9-809e-5efa-b3e5-aa63fc4f5b51 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
350c2b4d-d8f1-5b0b-9660-7c283c7066b4 | date | Date Completed:
| checkpoint | 2.2 - Identification of guard fence components
a848ce52-c516-5576-a2ee-c04702516d31 | note | REFERENCE - VicRoads Spec. Cl.708.05 (a)
0971fc47-5c53-589f-9bb5-7861e75afeb0 | note | – – – – – – – – – – – – – – – – –
f71a8348-e4df-5e64-af40-1491a8c5174b | note | ACCEPTANCE CRITERIA - w-beam sections, both ends of posts and all plastic components of proprietary end treatments unobtrusively and permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
c4faac22-4a3a-5a73-b325-df915b593bb8 | note | – – – – – – – – – – – – – – – – –
962a1b31-fc40-5c74-907d-21b26cb87fff | note | METHOD - Visual
c2cd7664-fc2c-5125-bc4a-36ae701f7555 | note | – – – – – – – – – – – – – – – – –
e05102ff-66af-55c0-8f09-19923bba335d | note | FREQUENCY - Each member material component
8bf4c5c2-b299-5368-991e-b0e5e40de56e | note | – – – – – – – – – – – – – – – – –
b755ebc7-56d7-50cd-94a7-f03b4130629e | note | CATEGORY - IP
853d0ae8-52a4-5ecd-bfd7-3b506f88978c | note | – – – – – – – – – – – – – – – – –
f7f6c48f-845a-5661-a361-f2e73046b0a8 | note | RESPONSIBILITY - SE/PE/SPE
c9c1316f-d9e5-5cc0-a570-d60a04a21906 | note | – – – – – – – – – – – – – – – – –
0c463bc3-6413-515a-9fc4-e293f0ac5b4d | note | VERIFYING DOCUMENTS - This ITP
36c44c6e-3022-5096-a461-17ea2686988c | date | Date Completed:
| checkpoint | 2.3 - Obtain and submit Material Test Certificate of Compliance for the barrier systems
074950ac-8a17-5c0c-9c2a-035c6b29495e | note | REFERENCE - VicRoads Spec. Cl.708.05(b & c) AS/NZS 1594, AS1627, AS 4680 ISO/IEC 17025 a
3933d5e4-fd9f-5f55-8475-19b43865eba3 | note | – – – – – – – – – – – – – – – – –
17e603b9-984d-532e-8bef-316f1ccc75bc | note | ACCEPTANCE CRITERIA - W-beams and terminal sections shall comply with AS/NZS1594 Grade HA350. Steel posts and blocks shall comply with AS/NZS1594 Grade HA250. Treated in accordance with AS1627- Parts 1 & 4. All test reports shall be endorsed in accordance with the AS ISO/IEC 17025 accreditation for that laboratory.
99d8307d-3b5f-5d80-8b24-520db46390c0 | note | – – – – – – – – – – – – – – – – –
9291cb4d-30af-5e0a-90c0-61efa698390e | note | METHOD - Document Review
1a5eb091-38ae-5192-a910-2da4755485c9 | note | – – – – – – – – – – – – – – – – –
a4171703-1f6c-553e-971b-409f9497825f | note | FREQUENCY - Min 14 days prior to commencing, 1 per 1000m of material
3767b16a-48c9-53fc-9e08-7f7b64865ec4 | note | – – – – – – – – – – – – – – – – –
fefcd163-c6a8-5716-9bd2-c51153c51df6 | note | CATEGORY - HP*
54ecc864-5c35-5269-9748-b82213aa95e1 | note | – – – – – – – – – – – – – – – – –
7d8af2f5-8df3-577c-a546-bea1602a2531 | note | RESPONSIBILITY - Nominated Authority
0c1e2774-d3f6-5bd4-9115-47f51ee11b8b | note | – – – – – – – – – – – – – – – – –
afecae50-3dff-546c-87c3-6ea47b2ab57a | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
9fe066a9-00f8-5ae1-ab9a-c2305f86ade4 | date | Date Completed:
| checkpoint | 2.5 - Verification of Protective treatment/ galvanisation records
e43e4f80-e917-5c9e-bca1-95ce1dcd8705 | note | REFERENCE - VicRoads Spec. Cl.708.05(d)
9c71c6a1-9ef4-5984-b32b-80dc651e0e0f | note | – – – – – – – – – – – – – – – – –
728705e6-57e4-526e-8644-6e71bbcd56d5 | note | ACCEPTANCE CRITERIA - Surface preparation in accordance with AS1627 parts 1 & 4. and finished by Hot-dipped galvanizing in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/ requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform. Hot-dipped galvanized coating on bolts, nuts & washers shall comply with AS 1214
cd5a3d17-d4fb-538d-b274-53a3fb006608 | note | – – – – – – – – – – – – – – – – –
4989bbe5-b541-5920-bcfc-1d834c2a4d47 | note | METHOD - Document Review
d59df069-d04d-5333-99dc-c8ee396ae00c | note | – – – – – – – – – – – – – – – – –
022d5f8d-01f6-533d-a238-530a41cef390 | note | FREQUENCY - Min 14 days prior to commencing, 1 per 1000m of material
20a6ef16-851f-58dc-82c2-8f013656cfa2 | note | – – – – – – – – – – – – – – – – –
a3716d44-287e-5fd7-ae8f-190c2f69ee9b | note | CATEGORY - HP*
da42ecfd-fd3a-5789-8728-88b3ee8daf21 | note | – – – – – – – – – – – – – – – – –
bb5f31ee-fb62-5810-aa0a-e153be500c28 | note | RESPONSIBILITY - Nominated Authority
1f491064-8164-5b52-9556-2ba724732b52 | note | – – – – – – – – – – – – – – – – –
247b2229-1c1d-592f-be00-b1d53d22b0cb | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
a00656aa-590b-5532-a01a-55d71df56d2c | date | Date Completed:
| checkpoint | 2.6 - Concrete mix design
a6943853-ac7f-5788-b3d1-bf4131613c10 | note | REFERENCE - VicRoads Spec. Cl.703 Cl.708.05(g) AS1379
5139b15b-28d6-5d39-81cb-b6b48236703b | note | – – – – – – – – – – – – – – – – –
5936f923-fec6-51ac-91d9-ed92781ced1a | note | ACCEPTANCE CRITERIA - Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either:
f8522860-760f-5701-a88e-3182792645db | note | (i) Portland cement-based concrete, N20 strength grade,
d88badc7-52bd-5b62-8dac-bcd648c68289 | note | or (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
83f7c3cb-21ae-56a1-8d2b-b080e81b2d2f | note | – – – – – – – – – – – – – – – – –
cef55e43-62e3-5029-aadf-a8b6a0fff93e | note | METHOD - Document Review
fe055e4b-7804-53de-99f7-02968e6c3236 | note | – – – – – – – – – – – – – – – – –
2ff6ee62-19be-5568-ae47-5de3c659af2f | note | FREQUENCY - Prior to Commencing
320d38f1-a1ff-52eb-986c-89a69ca39a66 | note | – – – – – – – – – – – – – – – – –
55555545-d88e-5ca8-a37b-015b161378c1 | note | CATEGORY - IP
bb8efd48-135a-520a-a115-e34e251f878a | note | – – – – – – – – – – – – – – – – –
c4e11eb0-31df-52f7-8459-8ea87c565095 | note | RESPONSIBILITY - SE/PE/SPE
adbd36a4-c296-5e65-a5de-114af1d423d0 | note | – – – – – – – – – – – – – – – – –
c105de9f-c101-578e-a7a8-9728d9187650 | note | VERIFYING DOCUMENTS - This ITP
80b64533-e43d-5e81-85c5-f140a1b6561b | date | Date Completed:
| section | Construction Activities
| checkpoint | 3.1 - Survey Set-out
3cdce3e7-f901-57dc-9cfe-1633ece4b46e | note | REFERENCE - Project Spec. Cl.1190.07 IFC Drawings
f55676b6-fed8-5070-87a7-939c3242084b | note | – – – – – – – – – – – – – – – – –
4da8df9b-736c-5459-ac8a-af92adbf676f | note | ACCEPTANCE CRITERIA - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.463 (November 2018) / 610.473 (March/June 2019) as applicable to the element. Attach: Survey As-builts / Survey Report
52f652ab-bec5-5bcd-819f-3c5a7e339d35 | note | – – – – – – – – – – – – – – – – –
5784262a-f21a-5e4c-baab-db3a23d25a32 | note | METHOD - Measure Visual
866395fb-5d53-5d88-aed1-e9f744d949a8 | note | – – – – – – – – – – – – – – – – –
0115bfb4-d2cc-5009-ac06-4f2a3026cab5 | note | FREQUENCY - Prior to Commencing Excavation
9d9d65d4-ad97-5aa5-84b8-93acfe182f47 | note | – – – – – – – – – – – – – – – – –
93a33afc-b96e-5771-903f-4058dcbd70eb | note | CATEGORY - IP
d15625b5-472d-507f-a839-60a6af9da258 | note | – – – – – – – – – – – – – – – – –
89b86516-b40f-5451-b4c6-174fd075dab1 | note | RESPONSIBILITY - Surveyor SE/PE/SPE
c2357cfb-978c-5ccd-addf-a165aeb4fab4 | note | – – – – – – – – – – – – – – – – –
4c31f4b0-b482-5243-a2f6-9b33d42e0f22 | note | VERIFYING DOCUMENTS - This ITP
857657f0-d137-5a20-b7e6-596aff02dc94 | date | Date Completed:
| checkpoint | 3.2 - Obtain approval of location and length
775fb8e4-2af5-5929-909a-83f567f6f42d | note | REFERENCE - VicRoads Spec. Cl.708.08 IFC Drawings
8809f555-2bee-5923-85b8-14eb839ffa78 | note | – – – – – – – – – – – – – – – – –
e2953ee3-021d-5a60-a5c3-d0f031b84f82 | note | ACCEPTANCE CRITERIA - The required location and length of all guard fence shall be confirmed with the Superintendent.
6f053db6-27aa-5ce7-b561-7b53b8cf293a | note | – – – – – – – – – – – – – – – – –
1150ca6f-82c2-5350-9bfc-834d0fa0fde1 | note | METHOD - Measure Visual
81d25978-2a24-50c5-8506-c1121d54460c | note | – – – – – – – – – – – – – – – – –
211c14d3-8a0c-5ded-a5fa-9e83afc06427 | note | FREQUENCY - Prior to Installation
6ceb7af0-1f51-59cd-9e65-dfb50c339651 | note | – – – – – – – – – – – – – – – – –
50a4e27e-491c-5df1-aae4-fa6ab325ffae | note | CATEGORY - HP*
fe9e4b9c-0d6f-5c23-9c71-6f228d736001 | note | – – – – – – – – – – – – – – – – –
903cead8-744e-5d88-9f03-4e732f52d035 | note | RESPONSIBILITY - Nominated Authority
5a6fbbb5-556d-5041-85da-0e0be3e04c85 | note | – – – – – – – – – – – – – – – – –
eb36a0d9-7b34-516c-ba31-b96fd173a6b1 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
68ff2de3-e534-5895-9dbc-3a98af70ebbb | date | Date Completed:
| checkpoint | 3.3 - Install posts, rails and terminations
63322a83-9035-5319-a521-49c5c1fcc15f | note | REFERENCE - IFC Drawings VicRoads Spec. Cl.708 .07(a & d ) IFC Drawings
e5522b35-1ec9-55c5-bf68-20b3449bf7eb | note | – – – – – – – – – – – – – – – – –
99885303-c314-53a7-9528-dfa11837dd8e | note | ACCEPTANCE CRITERIA - Posts shall be installed to the depth, line and spacing shown on the drawings. Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
1e493c91-a2c6-583d-81ee-60f96876b464 | note | – – – – – – – – – – – – – – – – –
48240ff6-65df-54a8-818d-5545d033984c | note | METHOD - Measure Visual
a5927c30-f8cc-5702-8684-97e217f5b761 | note | – – – – – – – – – – – – – – – – –
28d6fda5-244b-5ab1-b6cd-812fee7c649f | note | FREQUENCY - During construction.
92dbd572-9470-582c-b9e5-55827fb187dd | note | – – – – – – – – – – – – – – – – –
07554b30-497f-5bdf-9aa7-3294a11054ab | note | CATEGORY - IP
da26a078-286d-5d73-938f-cbbda1d0da2c | note | – – – – – – – – – – – – – – – – –
200ea55f-cb62-5626-a87b-ec64ce465ac0 | note | RESPONSIBILITY - SE/PE/SPE
9fe44cdb-8a7c-5dc3-9fca-b3a5bddb0bee | note | – – – – – – – – – – – – – – – – –
2e66fcaa-4991-541b-98f3-e5c638a9572e | note | VERIFYING DOCUMENTS - This ITP
918c487d-b3d0-537f-83c9-ea505c7c4f93 | date | Date Completed:
| checkpoint | 3.4 - Construct crushed rock base for maintenance strip
13884c1d-726f-503c-8c39-fa42f65c0f19 | note | REFERENCE - VicRoads Spec. Cl.708 .11 Cl.812
2d16a55b-3fda-5af4-b405-fef952370454 | note | – – – – – – – – – – – – – – – – –
27d81ed4-a6fe-5554-a81d-ac772009175e | note | ACCEPTANCE CRITERIA - Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
b69150ab-6422-5c5c-abe1-1a78b795eb1e | note | – – – – – – – – – – – – – – – – –
1977afef-c4df-51ea-8418-5ee05bd7d474 | note | METHOD - Measure Visual
171cccc2-3d54-5f7e-99d3-098c66a8a5cd | note | – – – – – – – – – – – – – – – – –
bc5c2c13-2e9c-56cf-945e-a413070152a5 | note | FREQUENCY - During construction.
e492ec48-0c9d-5e79-abd2-e5bf2a114a9f | note | – – – – – – – – – – – – – – – – –
ea339fea-eade-5b10-8fd9-4d2f73ad0012 | note | CATEGORY - IP
52c064db-0a54-5f3f-979d-55b97882c4d0 | note | – – – – – – – – – – – – – – – – –
df302e44-18e9-5b19-925f-14434590b196 | note | RESPONSIBILITY - SE/PE/SPE
56b40a33-d7b7-564d-9796-ef41a518dcea | note | – – – – – – – – – – – – – – – – –
b4862ef6-10dc-53f6-b78d-ed44eeb81422 | note | VERIFYING DOCUMENTS - This ITP
97b6c269-9d67-5a83-bab5-3e12b1276c81 | date | Date Completed:
| checkpoint | 3.5 - Construct concrete maintenance strip
9bc2232e-8d56-51f3-9709-e685efc5696b | note | REFERENCE - VicRoads Spec. Cl.708.12a Cl.708.5g Cl.703.11
50c8b30b-6bc4-5300-9d22-99becb764fd7 | note | – – – – – – – – – – – – – – – – –
a21fc973-417e-5e51-a3cb-2103c5e7e266 | note | ACCEPTANCE CRITERIA - Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam, Concrete testing at 1/50m3 per day, expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set
aac44286-0e85-540e-8a0d-065749ce6f60 | note | – – – – – – – – – – – – – – – – –
e94d002b-768c-5a2a-ac07-8075f6900a22 | note | METHOD - Measure Visual
47d8cfb0-506f-5cdd-be78-b691fd17ea9c | note | – – – – – – – – – – – – – – – – –
caca3420-d0d9-51d1-b355-7540b28b42e1 | note | FREQUENCY - During construction.
22227338-efca-5501-a879-bbee654a6d9d | note | – – – – – – – – – – – – – – – – –
ad0eda72-75d3-54f0-af18-5e553edc8bff | note | CATEGORY - IP
77bc2108-9d3a-5c7b-84ef-a5b5b75bd81c | note | – – – – – – – – – – – – – – – – –
3596273e-6851-57bc-a8f9-bfb91b45d3f7 | note | RESPONSIBILITY - SE/PE/SPE
a131608e-267a-5a34-8ae9-0c2252d30e6c | note | – – – – – – – – – – – – – – – – –
ed20ca43-cf51-52e2-8fca-716ed595a932 | note | VERIFYING DOCUMENTS - This ITP
b21d4635-7519-5aeb-ae5b-9797abde91f9 | date | Date Completed:
| checkpoint | 3.6 - Curing of concrete maintenance strip
834939b0-4774-5595-bd27-badd6cca41ee | note | REFERENCE - VicRoads Spec. Cl.708.16 Cl.703
2e82939a-f069-50bf-91e0-4fc89a4c55e2 | note | – – – – – – – – – – – – – – – – –
ab567fe7-649f-5e8b-91de-850d8529da8b | note | ACCEPTANCE CRITERIA - Concrete shall be cured either by water curing,wet hessian,polyethylene sheeting adequately sealed against moisture losses, curing compound or combination thereof. Curing compounds to be in accordance with AS3799.
38c625bb-e20e-5fc9-8e14-eb229a67bbe3 | note | – – – – – – – – – – – – – – – – –
e2012c9f-3b57-5ba7-a454-7f9a0c05307e | note | METHOD - Measure Visual
ddcdbdfd-f347-55fa-92e5-2e009d93b96a | note | – – – – – – – – – – – – – – – – –
8222ca4b-5b2e-5dbf-96ae-27b8961be5a6 | note | FREQUENCY - no less than 7 days after concrete placement
131c94fb-b911-5c9c-828d-7c864d218e50 | note | – – – – – – – – – – – – – – – – –
91a516e1-ff99-597f-943d-fa6801c450d8 | note | CATEGORY - IP
32f14dcb-ed5d-5cd1-9be9-23396af71fa1 | note | – – – – – – – – – – – – – – – – –
a1500bf7-4dca-564c-9d8b-ed4f80401df9 | note | RESPONSIBILITY - SE/PE/SPE
692af370-32e7-583b-9541-1084fd77dbc0 | note | – – – – – – – – – – – – – – – – –
98cae74a-910b-5a3f-a665-c14abf7f0c06 | note | VERIFYING DOCUMENTS - This ITP
c7cd3262-f971-5eab-a4f6-d56d9fbfc27a | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 4.1 - Delineators
0b172b35-56e0-5447-9dc7-41d7d7e54f00 | note | REFERENCE - VicRoads Spec. Cl.708.11 Cl.703.12
0f6c0501-4df5-56a1-8c49-0f4f94be66aa | note | – – – – – – – – – – – – – – – – –
eddeb38e-b347-5e1f-b598-a19ce9cd8249 | note | ACCEPTANCE CRITERIA - Appropriately coloured delineators fastened to top of w-beam at 15m spacings, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2
d7ae0eeb-91cc-5c6b-a4f3-865703cf7003 | note | – – – – – – – – – – – – – – – – –
fbcc816b-9fd6-5ea2-947d-bf17405c044d | note | METHOD - Visual Document Review
686cd750-5b0e-57a9-889b-377bc9eb09bd | note | – – – – – – – – – – – – – – – – –
8cd86a43-e587-5c9d-9171-0ecda9368c99 | note | FREQUENCY - Once, immediately following the installation and prior to any Work commencing on the members
2d22cd5a-d15a-582b-8dc3-f168267731f6 | note | – – – – – – – – – – – – – – – – –
298f847b-9276-5344-91eb-8033e2b6bccd | note | CATEGORY - IP
c75f7561-d8b0-549a-9502-c12319a2af41 | note | – – – – – – – – – – – – – – – – –
c983b847-66f5-54d7-8224-4152fa7d7a4b | note | RESPONSIBILITY - SE/PE/SPE
09d0cd0b-df57-531a-b1db-24b61b6c1096 | note | – – – – – – – – – – – – – – – – –
e991797f-1ff6-5a00-a4ba-d351cd9fe1e6 | note | VERIFYING DOCUMENTS - This ITP
ffc1355a-e81f-5227-96c1-997805fe9369 | date | Date Completed:
| checkpoint | 4.2 - Existing Sign & markings Reinstatement
8abd2aa2-d915-5476-9403-5501235792c4 | note | REFERENCE - VicRoads Spec. Cl.708.17 IFC Drawings
21a306f5-2a0a-5fb2-9208-f412550e1667 | note | – – – – – – – – – – – – – – – – –
d68915a2-5f58-5d81-bc24-a74e5f9eb2c5 | note | ACCEPTANCE CRITERIA - The Contractor shall reinstate all signs to a standard not less than the pre-existing condition and to the satisfaction of the Superintendent
30d89f3f-66f2-5557-8aa2-fcbd48f8e73a | note | – – – – – – – – – – – – – – – – –
266130ac-3085-57a8-99b6-03e35c953730 | note | METHOD - Document Review
65ba85eb-3576-55a5-803c-e7d2a9746ba6 | note | – – – – – – – – – – – – – – – – –
aa217918-9a43-51a1-878a-6c77725d1973 | note | FREQUENCY - Each element
b6184caf-1b17-5b12-841c-833879f1b6a7 | note | – – – – – – – – – – – – – – – – –
70f292e2-9ed0-51ed-838b-6e94800f8e5b | note | CATEGORY - HP*
7ddfac4b-0427-5378-acf8-048fd153792e | note | – – – – – – – – – – – – – – – – –
51397d9a-bb07-59e5-ba70-70cb937262c5 | note | RESPONSIBILITY - Nominated Authority
2ffcb092-7ef9-5448-bb19-9f5239242d70 | note | – – – – – – – – – – – – – – – – –
16a31a1e-4ecf-5a3b-a504-6f34eaa909fe | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
5b85e757-ead1-5a92-a55c-13093cb9a4d4 | date | Date Completed:
| checkpoint | 4.3 - Compliance Audit of Safety Barrier System Installation
36a374a5-fe0f-546e-ae20-8763b0088b69 | note | REFERENCE - VicRoads Spec. Cl.708.10
5449d44e-259b-5e4b-a97c-339ec39d3d10 | note | – – – – – – – – – – – – – – – – –
30cff094-508b-55a0-b8fa-243b9113914e | note | ACCEPTANCE CRITERIA - A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance(CoC) shall be provided certifying that the products have installed in accordance with the manufacturer's installation Manual and specification for each end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
9bb0a481-df85-5c0f-98b7-547d39ff943e | note | – – – – – – – – – – – – – – – – –
4c7e88a0-711e-5de5-8c6b-973003650208 | note | METHOD - Visual Document Review
97b0cbd6-23b4-538d-9944-a45f1f81fd83 | note | – – – – – – – – – – – – – – – – –
e711afeb-b619-54d3-9621-2458277c4256 | note | FREQUENCY - Each bridge beam
904edc75-33c4-58c8-9522-ddfdbc78218b | note | – – – – – – – – – – – – – – – – –
2f2f53dc-33fa-5e3c-8ecf-a60f50896f69 | note | CATEGORY - HP*
b64241cc-ae41-53c7-bd82-4a350f85c46c | note | – – – – – – – – – – – – – – – – –
ede47391-1a1d-5ecd-b7dc-5ef011382260 | note | RESPONSIBILITY - Nominated Authority
0cd428c2-e5b1-5e48-a0db-78f2351df370 | note | – – – – – – – – – – – – – – – – –
9715a0d8-773b-5267-b489-8130b699600e | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
c4f3f2bb-0f4e-55b2-9575-ec5ebd98640c | date | Date Completed:
| checkpoint | 4.4 - Survey data captured for as-built purposes
629d9b3f-bf9d-5a94-8a93-fe6ce3e95c4f | note | REFERENCE - IFC Drawings VicRoads Spec. Cl.708
545a034e-8d14-52c0-9565-fdc291558cf1 | note | – – – – – – – – – – – – – – – – –
1f5e1a1a-c9b0-51dd-b6e0-74265d087085 | note | ACCEPTANCE CRITERIA - As-built Drawings Tolerances as per VicRoads Specifications, Clause 708.
8ee36ae8-d394-5fea-9904-5c18c7e3d92c | note | – – – – – – – – – – – – – – – – –
8088b2bb-9528-5ab3-aa7c-bdc70f9e9d20 | note | METHOD - Visual Document Review
fb6be460-5c87-5a45-86eb-1a81bfe78277 | note | – – – – – – – – – – – – – – – – –
30f56c2f-b48f-5937-9f38-c068bde1f817 | note | FREQUENCY - Where applicable
b1685301-80a3-5c93-b54a-8bd732aea12d | note | – – – – – – – – – – – – – – – – –
5a92c24c-3c07-51ec-a19c-c06828c9f60e | note | CATEGORY - IP
41ba2519-f1e2-5b87-a795-770821be3e91 | note | – – – – – – – – – – – – – – – – –
8596a6fd-8081-56e3-bb28-a926969d1f74 | note | RESPONSIBILITY - Surveyor SE/PE/SPE
6759cdf4-d63c-5a1e-acc7-3c2148891a74 | note | – – – – – – – – – – – – – – – – –
ef8f588b-0b40-5021-8eb6-bd648cd98c0f | note | VERIFYING DOCUMENTS - This ITP
851cc58f-264e-54a8-8fb5-0472bba03832 | date | Date Completed:
| checkpoint | 4.5 - Non-conformance Report (NCR) Closure
20c34106-880c-5db6-8317-affb1ec9a20c | note | REFERENCE - MRPA Quality Management Plan
5b7ab7a8-90c4-5b6b-bbaf-bbc899564089 | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
68ae1207-536a-5229-b0fe-3a53b53752db | note | METHOD - Document Review
7c997f6d-4bcd-5c61-912a-e6f7fce3529a | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
50c61542-6cba-578c-b4a3-12bc7e9515f3 | note | CATEGORY - HP*
ec95e029-d625-5785-be50-67f5d57a9fa6 | note | RESPONSIBILITY - Nominated Authority
a5c64c5c-591e-5a20-ad2e-12955afbfc9c | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
02f46d5c-b07a-5f42-8eb1-fff4717f3a1f | date | Date Completed:
| checkpoint | Final Inspection
880c875d-405f-5c69-aaa7-e3b0381ba932 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
a13b5fef-0dd1-5d06-a7c3-058757147f6c | textbox | Name:
9bbd1a84-07fd-516b-a6aa-4d18ed488629 | textbox | Position:
1e9f7a3b-d55c-504e-8aa6-d99c1f5bd818 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-073-CIV-CAMMS-Lighting-MTM Carpark Rev 0 | itp | ITP-073-CIV-CAMMS-Lighting-MTM Carpark Rev 0 |  | b065e794-ac15-42bc-800f-5b03260c90b8
| section | Referenced Documentation
| checkpoint | Referenced Documentation
eebf3119-9204-55a2-bbaa-55b233db08f0 | note | Document Title: ITP-073-CIV-CAMMS-Lighting-MTM Carpark
46897a91-5fc4-568b-a5c5-ed5bc63748ae | note | ITP Description: CAMMS-Lighting-MTM Carpark
1296070e-1795-5036-af68-7b7f9e510b41 | note | Discipline (e.g. CIV/STR/RAIL): 073-CIV
a25a1004-e8f8-5893-9aca-1c16be781e99 | note | Revision Number: 0
59c9b91a-f228-5d2f-83c1-d0b437314a4e | note | Revision Date: 8/11/23
84ac5183-8bac-55c2-93ba-cadf52713be1 | note | ITP created by: Romualdo Magpantay
411e1881-a842-52c8-a6b1-a8789401345d | note | ITP approved for use by: Victor Mira
6f5e811e-09b1-58a5-96d9-6fb10f329c4a | note | 1.1 L1-CHE-STD-059
7c002317-6ce7-5440-8840-87c79b1126f1 | note | 1.2 L1-CHE-STD-035
f6c12c68-d15f-5d88-bbb4-f3121a129744 | note | 1.3 L1-CHE-SPE-155
f6c8f615-fc1c-5f97-b3d1-91d62326f75f | note | 1.4 AS/NZS 3000
fc27b167-d9ab-5c52-8c31-6f1bab0b06ad | note | 1.5 AS/NZS 1158.3.1 (2005)
| section | Preliminaries
| checkpoint | 2.1 - Obtain and review manufacturer documentations for the supply of materials
b8820342-9a35-54cf-8485-70511fe86cf0 | note | REFERENCE - AS/NZS 3439.1 L1-CHE-STD-035 AS/NZS 2053 IFC Drawings
c38c3674-b30e-58f2-92ce-ac438da1240f | note | – – – – – – – – – – – – – – – – –
2151626d-7c26-5919-a77f-bae03cf223ec | note | ACCEPTANCE CRITERIA - Materials comply with MTM Engineering standard Lighting and Powerrelevant specifications.
95fb78f7-e473-56c0-9167-13a2759f4857 | note | All materials shall comply with the standards and specifications shown on the drawings. All structural steel, associated components and welding consumables shall be manufactured by companies that hold quality systems certification to AS/NZS ISO 9001.
21457737-8fa7-555c-804f-1d08231e6eec | textbox | Enter: Teambinder Material Approval number
20d14040-6033-540d-8a98-878cd351ae07 | note | METHOD - Document Review
ce992482-fb93-5430-9e82-0e9b7f4bf5d9 | note | – – – – – – – – – – – – – – – – –
c29f26c0-3b8f-58d5-92ee-d1b5d002fb4f | note | FREQUENCY - Per Source
d3107bce-101a-5729-a596-ec2b70cacc38 | note | – – – – – – – – – – – – – – – – –
3e1a8907-3cde-5df9-a0b7-d0b5c9aa4f82 | note | CATEGORY - HP*
f488924d-6d3a-5659-8ac4-18085cd6d4e3 | note | – – – – – – – – – – – – – – – – –
19cbb5d6-780c-512b-853b-6404f8057d26 | note | RESPONSIBILITY - Nominated Authority
aeff485c-3854-5fd1-8dbd-3623cf314363 | note | – – – – – – – – – – – – – – – – –
7b753784-754c-589a-8098-3a98b626cc28 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
4b7ada1a-1815-56ea-b887-2e0aef05837f | date | Date Completed:
| checkpoint | 2.2 - Inspect supplied items upon delivery
b980dfa7-a9f5-506c-9c0a-e7c2b7e1f41b | note | REFERENCE - QMP L1-CHE-SPE-155
29432bb4-8185-5a25-8042-00f574ebbd9b | note | – – – – – – – – – – – – – – – – –
6dffdd7f-d0e1-5711-8d1f-321061df4074 | note | ACCEPTANCE CRITERIA - Supplied items are to correct spec, class, size and undamaged
d58df246-673f-5206-8055-7011d71b7b83 | note | Luminaires: At the time of delivery, the supplier shall provide three hard copies of the following:
74f01c0a-b957-5bb1-9b4e-d1e57df9e9e4 | note | Installation Instruction Manual
ed9b08c4-2eb2-59ab-a237-72f5df0d1ee0 | note | Operation Instruction Manual
8c1bc061-3aa0-51e9-bb7d-7e55d65d119c | note | Storage, handling, loading and off–loading instructions
57dd28f8-b6ff-558a-94aa-c951affa9275 | note | Test Certificates
ed7055c5-f4f3-5fab-91a9-a96a7568dfd3 | note | Warranty Information
4f24bed5-39cc-5ff4-99ac-c2bd0dd8314d | note | METHOD - Visual /Site Inspection & Document Review
8a88bee9-3d66-5d9b-95c5-db4b5c04b728 | note | – – – – – – – – – – – – – – – – –
1b1ea5b4-b7d3-5437-9dbb-2bca9869bfd0 | note | FREQUENCY - Per Delivery
32b2a44b-79b1-5985-b7d1-d117f3a29315 | note | – – – – – – – – – – – – – – – – –
c11451eb-028f-5961-aef2-febb981792a3 | note | CATEGORY - IP
f069aea1-6450-5cd5-91c0-05bc287c10e7 | note | – – – – – – – – – – – – – – – – –
a19eac7f-d26f-536a-8040-708dcc319685 | note | RESPONSIBILITY - SE/PE/SPE
618b71b9-d776-5a87-b785-a88ce606649c | note | – – – – – – – – – – – – – – – – –
0fde758a-7ef2-5119-ba27-523156d35eef | note | VERIFYING DOCUMENTS - This ITP Attach records required
bede554b-b558-5add-80f5-de2e7e763787 | date | Date Completed:
| section | Civil Works
| checkpoint | 3.1 - Conduit & pit installation
dca5ec3e-8ce5-51fd-8017-93d456104e66 | note | REFERENCE - L1-CHE-STD-035 IFC Drawings
662b2652-b1ca-507e-b0bb-72d22a084d58 | note | – – – – – – – – – – – – – – – – –
9e88aacd-8c60-580f-a928-fa55016126f8 | note | ACCEPTANCE CRITERIA - Conduit and Pit Installation works are to be recorded under ITP-CIV Pit and Conduit (Supply and Install) - MTM Car Park Lighting ITP in addition to Subcontractors Checklist.
b8b7d60e-a5fd-58ad-ac1c-db19d585b038 | note | METHOD - Document Review
cf67ea94-81d9-52a1-8302-504b046c94ea | note | – – – – – – – – – – – – – – – – –
eeee1963-ab45-58e6-9420-f7d34bfe093d | note | FREQUENCY - Per Lot
05d957e3-1a9f-5a97-bc97-9d53e97a5246 | note | – – – – – – – – – – – – – – – – –
5d7df0df-f5b2-5cc9-92d0-aba3dd17dc3e | note | CATEGORY - IP
42882d18-d86e-5c82-a5e3-199ad901ffcd | note | – – – – – – – – – – – – – – – – –
bba6282c-7b49-53b4-b0ab-e13f38947a84 | note | RESPONSIBILITY - SE/PE/SPE
2291e569-f86f-5b48-9a1c-391e50e3ccfd | note | – – – – – – – – – – – – – – – – –
b6476eb2-83c9-56f6-909d-e8f0a2fc2436 | note | VERIFYING DOCUMENTS - This ITP Attach Subcontractor Checklist
13be4867-96de-5e66-9dc7-6ed65b2b4d46 | date | Date Completed:
| checkpoint | 3.2 - Prepare the plinth foundation(Excavation & levels)
859b0ba9-bb27-56ff-8bdd-f22f0124e15d | note | REFERENCE - Drawings IFC
dbae7f27-9676-5d10-a8a1-d5fe9c2cddd0 | note | – – – – – – – – – – – – – – – – –
853399f7-4876-5e15-9475-69f729df29e8 | note | ACCEPTANCE CRITERIA - Check levels conform to relevant drawing depending on type of pole to be installed.
70db9191-5faf-56a2-8404-b46b42e627f9 | note | METHOD - Visual Survey
4ab569d7-2a06-5099-893d-874b374daf4a | note | – – – – – – – – – – – – – – – – –
377d7dc7-ab8c-56a4-be41-b54cdbbbda6b | note | FREQUENCY - Per Lot
b5187bfa-3cfc-5032-b36c-77d33802c300 | note | – – – – – – – – – – – – – – – – –
f4ad1ca6-cd15-591f-893a-f3a0bcda5799 | note | CATEGORY - IP
242e16e9-7080-52fa-a4a8-581bffd7db1f | note | – – – – – – – – – – – – – – – – –
2ed617f9-8eaf-51be-9550-1b402da13a8c | note | RESPONSIBILITY - SE/PE/SPE
e4719457-cd41-595d-82e7-8d6008542449 | note | – – – – – – – – – – – – – – – – –
e5415c68-14f3-50e5-8a6d-2435b71213a0 | note | VERIFYING DOCUMENTS - This ITP
01911fa1-7611-5239-bbe7-d281d9a8ecda | date | Date Completed:
| section | Light Pole Works
| checkpoint | 4.1 - Installation lighting pole bases & columns
cd4fed9d-18f7-5698-816d-a1b8ba0382fe | note | REFERENCE - IFC Drawings L1-CHE-STD-035
697b0ce1-2adb-5d55-8439-2f11eb8608b2 | note | – – – – – – – – – – – – – – – – –
e8cf8e4b-388f-5904-966f-8e33f1f761c7 | note | ACCEPTANCE CRITERIA - Free standing platform lighting poles shall be at earth potential as mounted in ground or on structure. Light fittings shall be earthed by the earth cable from
a2a4b046-a2c3-5ddc-a6e9-31eea8196b97 | note | Concrete and metallic poles at all new installations and station extensions that support low voltage equipment shall be earthed by an underground conductor that is connected to the earth at the origin from which the circuit is supplied in accordance with AS/NZS 3000.9.5.2
78142869-6c3e-5e19-9786-10e85a89485f | note | Lighting installations shall be LED and comply with L1-CHE-SPE-155
cbfd6035-35ec-5cd5-8ab3-b62f93c93bbe | note | Car park poles shall be located as per IFC Drawings.
24feab04-7bc5-59de-8546-83984a44fd52 | note | Pole access hatches shall be orientated to allow unobstructed access.
6caea65b-5baa-5e55-816e-28305e4704e6 | note | Level formed ground shall be at each pole for access by ladder or EWP.
6a510997-1e66-5354-9ee5-47e3d6b1bede | note | METHOD - Visual /Site Inspection & Document Review
380c2bb0-b422-5032-8f90-a9b80f2e5392 | note | – – – – – – – – – – – – – – – – –
5360ec91-2472-5ad2-9843-d76ee22550c0 | note | FREQUENCY - Per Lot
1a4d31a8-86f4-5ab0-a501-7c9a5a07f307 | note | – – – – – – – – – – – – – – – – –
0909a656-c784-5663-8226-03682ecae352 | note | CATEGORY - IP
91dca009-9438-52c6-aaf1-d36ed4e1a57c | note | – – – – – – – – – – – – – – – – –
5158c810-664c-5fe0-9b63-a6c27b9bb692 | note | RESPONSIBILITY - SE/PE/SPE
15ee7560-83f0-57e3-b0e1-36f1db737fe7 | note | – – – – – – – – – – – – – – – – –
ada2a212-0a9e-5aec-9d1b-4f2a0ec5becd | note | VERIFYING DOCUMENTS - This ITP
bc0475d1-0dff-5e5a-813b-8bef66dbfd15 | date | Date Completed:
| checkpoint | 4.2 - Assembly of outreaches and luminaires
ffdb096c-0c17-5d13-bef7-889280a5a463 | note | REFERENCE - L1-CHE-STD-035 IFC Drawings
fd46bd6f-447e-51eb-bebe-60f215d84cb7 | note | – – – – – – – – – – – – – – – – –
19993395-b2e3-56e1-bdb8-1fcda0977ed1 | note | ACCEPTANCE CRITERIA - Outreach bracket to be installed to the pole spigot using the clamping bolt assemble
aad082f4-7299-59ce-86d4-3e36d58948b1 | note | Bracket and luminaire to align at right angles to vehicle path on road
74266131-a769-5f11-9d4c-bddcf3de31b1 | note | – – – – – – – – – – – – – – – – –
c1e69849-94f7-5dc7-ba73-09bb3abf37da | note | FREQUENCY - Per Lot
c3653656-4c2a-5144-849b-a680f9ad58e3 | note | – – – – – – – – – – – – – – – – –
0dd64302-fd28-5a25-b9b2-e4280997a946 | note | CATEGORY - IP
592a078a-19db-5cfd-beee-f6fa5aaee3a9 | note | – – – – – – – – – – – – – – – – –
dae6b6b5-7b19-5f64-967b-7f6bb1cb9d20 | note | RESPONSIBILITY - SE/PE/SPE
f5f1ad86-f0a7-5499-84ee-54ea8c06effe | note | – – – – – – – – – – – – – – – – –
1728d4f0-52ac-5489-bbc0-24e7bc4606f4 | note | VERIFYING DOCUMENTS - This ITP
32b11e46-42f8-5788-86ae-3df8636bc76b | date | Date Completed:
| checkpoint | 4.4 - Installation of lighting distribution cabinet
1a160110-387b-5444-ab1e-222a6c1a3bca | note | REFERENCE - L1-CHE-STD-035 IFC Drawings
209a5f46-039c-5c6c-b301-cbbb6429df8b | note | – – – – – – – – – – – – – – – – –
c519e058-ce7a-5da5-be05-f2185343686f | note | ACCEPTANCE CRITERIA - The switchboard or distribution board shall be designed and manufactured from suitable materials appropriate to the location in accordance with AS/NZS 3439.1.
b4cca84f-c1c3-5736-ab19-b4c2643af683 | note | METHOD - Visual
be738e11-5402-5b7c-86c8-94af76945342 | note | – – – – – – – – – – – – – – – – –
97c89c3c-3cea-5631-a553-cf54f3010cff | note | FREQUENCY - Per lot
86abc145-3528-5ea7-a4c8-94c6bc99932d | note | – – – – – – – – – – – – – – – – –
9358c237-b4b4-5be0-86b5-8d75254e9e34 | note | CATEGORY - IP
b94d4324-539f-5f41-b54d-b365fda2b259 | note | – – – – – – – – – – – – – – – – –
412ca0ba-2119-5cc8-94fc-cd7b6aeed8fa | note | RESPONSIBILITY - SE/PE/SPE
a26e00fc-f873-5455-8944-c12022bdf0a1 | note | – – – – – – – – – – – – – – – – –
cca8ce08-ee53-5fbc-81e6-0f6a319c8746 | note | VERIFYING DOCUMENTS - This ITP
91c9b8ec-31ea-519e-9965-c59e23a49f8b | date | Date Completed:
| checkpoint | 4.5 - Installation of cabling
3d93c18f-4a39-59a9-b83e-38800d2d1b2c | note | REFERENCE - IFC Notes
6dec2d8d-5a2c-5452-9f6a-f331c3fbcf2d | note | – – – – – – – – – – – – – – – – –
0c4e553d-f015-5d4d-bd04-ec7bb14182d9 | note | ACCEPTANCE CRITERIA - All electrical cabling to be in accordance with the requirements of AS/NZS 3000: (Australian/New Zealand Wiring Rules) Each pole to be cables from the pole circuit breaker
878ccd0c-cbb6-5f6a-9185-55bdf50925fa | note | METHOD - Visual & Document Review
9821cdef-42ed-5fc8-a479-12893d7e232b | note | – – – – – – – – – – – – – – – – –
fb444b6c-c669-533f-b3d1-476f4c11f9c0 | note | FREQUENCY - Per Lot
efe8e37c-79da-5f41-bb80-8480685aa80d | note | – – – – – – – – – – – – – – – – –
dabdbe37-51b5-58fa-b342-fa152606c4b5 | note | CATEGORY - IP
a5c4ec2f-24b1-5f4b-bb61-fedfb3204189 | note | – – – – – – – – – – – – – – – – –
1bb2e4ca-cac5-5729-a7c8-0a4052ee0a1c | note | RESPONSIBILITY - SE/PE/SPE
fe2a1a06-d152-5cd0-8a00-ff62d2909d04 | note | – – – – – – – – – – – – – – – – –
865187f7-9a2a-53c9-bd93-f80c9d5892b5 | note | VERIFYING DOCUMENTS - Test Certificate This ITP
35f6210e-57fa-5f16-9450-afd35e2e53be | date | Date Completed:
| checkpoint | 4.6 - Commissioning & testing
e50a1276-33df-53e8-866e-582669e1b27e | note | REFERENCE - L1-CHE-STD-035
4e9b07e0-3466-5923-a991-d33eccb6859e | note | – – – – – – – – – – – – – – – – –
247bb616-a1e1-5429-b910-5affa75285c2 | note | ACCEPTANCE CRITERIA - Upon final acceptance, the Contractor shall switch on the lighting installation at the distribution cabinet in automatic mode, and record the time, date and meter reading for contractual, warranty and power supply purposes and supply this record to the Superintendent within 48 hours
c6819bba-8f67-50e5-9e48-0d295bba70d8 | note | METHOD - Commissioning & testing
522c8e71-4768-5404-88fe-94497229ee4b | note | – – – – – – – – – – – – – – – – –
91003672-e3ca-5759-ad7f-0aa5a68f15e3 | note | FREQUENCY - Upon completion of each section
7db24f36-b760-531f-9da2-4a41c07a4c5b | note | – – – – – – – – – – – – – – – – –
1568ef2a-fa58-583e-9d22-a1d9f835dccf | note | CATEGORY - HP*
b3a9f90f-d8b3-5931-96d4-41dc12c29ff3 | note | – – – – – – – – – – – – – – – – –
f3318008-416d-531e-aa56-a0a366eaec66 | note | RESPONSIBILITY - SE/PE/SPE Services Engineer
2ad3b6a6-652b-5f5f-afec-6b5bda87ac76 | note | – – – – – – – – – – – – – – – – –
0b958ff5-8adc-5042-a6eb-9f13fdcba9a5 | note | VERIFYING DOCUMENTS - This ITP Attach Certificate
f2aed501-6eca-5752-aa80-bb7af3db8f9d | date | Date Completed:
| checkpoint | 4.7 - Labelling of Assets
8163cdc8-52a0-5098-85e1-8f3717aaff32 | note | REFERENCE - L1-CHE-STD-035 MTM Standard
f813db0a-c243-5adc-9e0f-0b075b6b7af8 | note | – – – – – – – – – – – – – – – – –
01311221-425b-5844-b8cd-6b48d718b2c4 | note | ACCEPTANCE CRITERIA - Labels fixed to poles as per MTM standard. Pole numbering
5a616424-94a5-51d1-87b8-45c182271ec7 | note | Labelling of switchboards, distribution boards, circuit breakers, RCDs and all control devices shall be labelled as per Appendix B in MTM standard.
688ccdfa-5de8-5f15-a198-5758d6638087 | note | Indelible Labelled drawings shall be permanently displayed at the point of supply. Permanent field markers shall clearly identify the extent of the EPZ locations.
6fbf1d9e-1ae3-5289-b6c2-eee88759ddda | note | METHOD - Visual /Site Inspection & Document Review
389e4cb2-5301-5744-a1b2-c156f78dac61 | note | – – – – – – – – – – – – – – – – –
69aa4ac4-3dc4-5e31-a73c-1f2e38b01272 | note | FREQUENCY - Per Lot
d4817ebe-1006-5cad-9d3a-ac772575ec6d | note | – – – – – – – – – – – – – – – – –
1570d591-cc76-52ce-99fa-bede94ce50d7 | note | CATEGORY - IP
a3acbee2-32bf-5bcc-8ed8-7ebda9f58031 | note | – – – – – – – – – – – – – – – – –
bcff4920-e2b3-5a18-bf8c-ccbaa544bfc7 | note | RESPONSIBILITY - SE/PE/SPE
8cebabb9-152b-5416-9f45-0d5035d25846 | note | – – – – – – – – – – – – – – – – –
c03dfeb1-aeb1-5401-89b8-3784fdb372aa | note | VERIFYING DOCUMENTS - This ITP
d90168ed-8873-5cc1-9ce4-dcc4015388aa | date | Date Completed:
| section | Completion
| checkpoint | 5.1 - Attached and verify Subcontractor conformance records/signed ITP including relevant verification sheets
bb3884f5-af59-5ccc-bbb4-3806143c6ab9 | note | REFERENCE - IFC Drawing Note
49c699a3-2934-5f5a-a6a2-5ee9af4df68b | note | – – – – – – – – – – – – – – – – –
e7ddf352-bc21-5362-b2b3-f94a9b04b394 | note | ACCEPTANCE CRITERIA - Check conformance report against project conformance criteria
6adba040-ed7b-5094-9b5f-088aac6b4fdf | note | METHOD - Doc. Review
dd5d1724-d2f1-54e8-8cbd-84c0641acf64 | note | – – – – – – – – – – – – – – – – –
fa72ebe9-7288-548f-9a4b-e40bcf590ff5 | note | FREQUENCY - Each lot
871b61ad-3c77-5ae0-831e-33138c481294 | note | – – – – – – – – – – – – – – – – –
42a8b04f-59bb-5530-943c-859bbc8bdc6b | note | CATEGORY - IP
fe686fe0-46a6-5373-bb3c-7e0bea8b89f1 | note | – – – – – – – – – – – – – – – – –
e052d7c5-3274-585d-bac9-82893a017c46 | note | RESPONSIBILITY - SE/Site Supervisor
22e82484-eb78-52ba-ab75-b2d44f269707 | note | – – – – – – – – – – – – – – – – –
2bb8946f-f7de-5563-bff1-a6b667f6b04f | note | VERIFYING DOCUMENTS - Sign ITP Attach documents
981feaa4-cc81-5b69-ae3c-78299a61cc9a | date | Date Completed:
| checkpoint | 5.2 - As-Constructed Plans
29f31834-77ce-5818-bb09-7b771a96f25a | note | REFERENCE - IFC Drawing Note
9f8d3e01-967d-5e2c-a4ad-be890ec9dcb6 | note | – – – – – – – – – – – – – – – – –
7ec4cbcf-98f3-59f7-a9b3-c8f598fb7e8a | note | ACCEPTANCE CRITERIA - The Contractor shall supply to the Superintendent two copies of ‘As-Constructed’ plans along with a USB drive or other approved storage medium containing the CADD drawing files, and the same shall be supplied by the Contractor to the local distribution company if appropriate.
506866e6-74fa-5c8d-8a64-d15c5b8ef69c | note | METHOD - Document Review
6aa47160-fd19-5910-b9ef-98d6caa05b2b | note | – – – – – – – – – – – – – – – – –
f834b3c1-016f-5155-9a39-65e748b41c95 | note | FREQUENCY - Upon completion/ Work area
92c3f69f-02e0-5f35-9506-e5b2f90cd5d5 | note | – – – – – – – – – – – – – – – – –
84304048-0fb8-5e54-9077-418ec88baeec | note | CATEGORY - HP*
88adc4c8-a45f-57ff-b385-2f0bc0fdac70 | note | – – – – – – – – – – – – – – – – –
d6f55510-fa0d-53b5-afa6-998d305be29e | note | RESPONSIBILITY - SE/PE/SPE
d09eb47c-b240-5d27-b83e-368261a9c428 | note | – – – – – – – – – – – – – – – – –
cfc24c80-443e-5c1a-97c1-20e926010186 | note | VERIFYING DOCUMENTS - Sign ITP Attach As Constructed Plans
dcd423b9-a665-5861-b980-e6b5a0918072 | date | Date Completed:
| checkpoint | 5.3 - Non-conformance Report (NCR) Closure
4a20ec9f-5dde-5b22-8c2c-ad213219074e | note | REFERENCE - MRPA Quality Management Plan
ad05bd0f-c5f5-5143-ae9b-98bc26adc424 | note | – – – – – – – – – – – – – – – – –
f5501924-2d3c-599f-b9b9-bc083d115e72 | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
2476944c-f8ff-500a-bee1-0289c0d698fc | note | METHOD - Document Review
66e78546-a80f-5643-848a-2b7df4148b14 | note | – – – – – – – – – – – – – – – – –
ace47f07-4d94-522a-8443-ba3a4cdd8d59 | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
c0006926-2ffb-5c77-a0f4-1582b0528cf5 | note | – – – – – – – – – – – – – – – – –
297c8f1a-7c0d-521b-8efe-2dc1a8495181 | note | CATEGORY - HP*
bd8bc239-8f7d-551b-884a-c9d8c8c036dd | note | – – – – – – – – – – – – – – – – –
48e3d0f0-0c33-5fb5-9c36-b60db9769b42 | note | RESPONSIBILITY - SE/PE/SPE
16dfad08-66ed-52d6-bae2-27c219e3f970 | note | – – – – – – – – – – – – – – – – –
a64a7712-71a5-5ce0-a2b5-ef76eb545aba | note | VERIFYING DOCUMENTS - This ITP
a2b17e77-4ac6-5144-8aa7-3d54006c3398 | date | Date Completed:
| checkpoint | Final Inspection
c3b13b89-bc47-5377-8c80-af0e417bec52 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
7f5b4465-9bb3-507a-b049-2d49876114e0 | textbox | Name:
0227ae78-9564-576a-83e3-4809e942891d | textbox | Position:
f2b65c71-2ece-5e53-85d0-4c792133fb79 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-074-STR-CAMMS-Precast Super T Installation Rev 0 | itp | ITP-074-STR-CAMMS-Precast Super T Installation |  | 875c7700-6946-41c7-937a-a7aa6ca0640b
| section | Referenced Documentation
| checkpoint | Referenced Documentation
0a48c983-0012-5e5c-9eca-219accacf60b | note | Document Title: ITP-074-STR-CAMMS-Precast Super T Installation
505f944c-96bd-5461-a251-ac3a6d952825 | note | ITP Description: CAMMS-Precast Super T Installation
225a5e9e-6c96-54eb-b2e0-1422828cfa71 | note | ITP number: 074-STR
dcc3cea2-45ca-506a-b09e-e5459ce9ae5c | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
018612b1-1239-574c-88a9-80f59cb46c3f | note | Discipline (e.g. CIV/STR/RAIL): 093-Rail
b6bd430a-cf3f-5d15-b5e0-63dc5f0b6f01 | note | Revision Number: 0
218fdfbf-fe18-55f4-8428-0ab3e31228f3 | note | Revision Date: 5/10/2023
0cc0675c-f8bc-5e01-9420-812b9bdfa5e7 | note | ITP created by: VM
64144f84-d570-59ea-ab36-9d44ebba00b0 | note | ITP approved for use by: VM
c85d3989-e28e-53a5-a187-f278520cdc67 | note | 1.1 Non Dependent
6ecc3324-7c05-5d14-8b1c-d92b08289fd2 | note | Reference: VR 652 June 2010
9efc312d-1491-5101-b7e8-0ba20497450f | note | 1.2 Non Dependent
9e95072d-d99a-5bd6-9187-a344f7d7abf7 | note | Reference: VR 656 June 2010
21962194-f885-5142-ad65-190e90eb6516 | note | 1.3 Non Dependent
d98f51d4-349f-544c-8518-eabc34971400 | note | Reference: VR 610 February 2020
33595337-f5f8-5ccd-a670-539ca1fd5ea1 | note | 1.4 Non Dependent
9b8016ba-8c4a-5ae1-8471-078809773c68 | note | Reference: VR 620 May 2009
| section | Preliminaries - Materials
| checkpoint | 2.1 Epoxy bedding
c8a78e47-0b86-5142-9f3e-93d75f4b6297 | note | REFERENCE: IFC Drawings MRP-052-C-SME-DRG-31-MPK-CBR-1112
e83a48b7-dcf7-5e34-af3b-c2c73402758b | note | – – – – – – – – – – – – – – – – –
30c21991-8021-5605-9223-940409c193f0 | note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
14fcba68-87da-556c-b7fe-dc4ffaa01c11 | note | i. minimum compressive strength requirement as the Expoxy beeding is used to ensure the taper plate fullyengaes with the Girder.
cb9ac87d-dbd1-55d4-b830-b0a4136f24b1 | note | ii. Can be applied in IFC specified nominal thickness (1mm)
9de36c8f-b7c6-506c-9bb0-956199e5f226 | textbox | Enter: Teambinder Material Approval number
3e6742a6-281b-5036-a902-787e7c2a335b | note | – – – – – – – – – – – – – – – – –
8c4d8bd7-7061-5b6c-8944-9ed3d73d08c3 | note | METHOD: Document Review
b1ab674a-3124-5406-acff-9b6e1056928c | note | – – – – – – – – – – – – – – – – –
ad3c3c33-98e3-5c44-9131-97793c03fb1e | note | FREQUENCY: When applicable
b997e147-a6f3-51d0-9d62-0a154effc41e | note | – – – – – – – – – – – – – – – – –
71979815-0905-53dd-8d24-3e9473fa3566 | note | CATEGORY: HP
5bf05e29-62ab-5182-9464-fc9c5ed03919 | note | – – – – – – – – – – – – – – – – –
b743c8c7-3b33-519a-83dc-a4145d158e40 | note | RESPONSIBILITY: Nominated Authority
27d93f02-9f6c-58fa-854b-9e642606859e | note | – – – – – – – – – – – – – – – – –
5e57d048-38d7-59ea-94df-c50ae06e3d3b | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
627fc17a-e163-5f40-9ffd-7b1aff93a90a | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Bolts
c001dbd6-0fe6-5fd0-be1f-52702e897099 | note | REFERENCE: IFC Drawings MRP-052-C-SME-DRG-31-MPK-CBR-1112
de24fa5b-61b9-5d10-bc13-b47ed30e10d6 | note | – – – – – – – – – – – – – – – – –
e427ae9a-0401-5433-a2a7-4a68a2e6d723 | note | ACCEPTANCE CRITERIA: M16 property calss 12.9 Zinc Coated countersunk socket cap screw
6102600e-3dc3-5465-9a5c-289afca6aa4a | textbox | Enter: Teambinder Material Approval number
38583a86-de24-5007-934d-432347b384da | note | – – – – – – – – – – – – – – – – –
58c98ef1-1460-5124-8da6-cb92e663f16c | note | METHOD: Document Review
fc819b19-3a6a-597c-a333-ef24ff3f8c6a | note | – – – – – – – – – – – – – – – – –
2b89c10e-aeae-5578-8a41-38c7334fb1d8 | note | FREQUENCY: When applicable
70192c26-51c7-5a19-a137-2885354b6085 | note | – – – – – – – – – – – – – – – – –
def26c24-b0db-5009-9eda-9f8c608d5007 | note | CATEGORY: HP
81b2d21a-2cc8-5d61-bac4-f86e8779a07e | note | – – – – – – – – – – – – – – – – –
ea42b738-9fcb-59c9-be9b-00568fcb0968 | note | RESPONSIBILITY: Nominated Authority
386918cf-24c0-5150-9192-58c4017205a6 | note | – – – – – – – – – – – – – – – – –
8be3738b-b8fa-5861-96b0-174331d9f9b8 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
1638e4ad-8b9d-5b75-8b6c-9e28e4a10b0a | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries - Procedures & Documentation
| checkpoint | 3.1 Precast Elements
61a754a4-890d-5d39-8553-edad3d1f6e63 | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.473 (March/June 2019) 620.03
adc2ce3b-658a-5f49-91a7-707f75082c66 | note | – – – – – – – – – – – – – – – – –
a239a3d2-52f3-591d-9060-1c4186442836 | note | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
dd97944d-3237-5ba7-9d2e-971dd597a456 | note | i. Certificate of Compliance / Birth Certificate
60c8f89c-37f6-5c08-9eb7-f98319c6ca75 | note | ii. Compressive strength test results
a89c5718-b6b7-54fd-8f4b-53493343fc74 | note | iii. Precast Lifting Design
acb07057-98b4-5d9a-924d-9b20236264ba | note | iv. Pre-pour check sheet / ITP
631f8861-789a-51fe-818f-7920fa1c34e1 | note | v. Pre-stressing check sheet / ITP
c2e0a0fb-9ffe-5c69-8415-35f4662e7758 | note | vi. Post-pour check sheet / ITP
5fbd9c39-1ade-512f-9cbb-6c92cd2dd0ba | note | vii. Covermeter check record
10226c72-cd91-5f1b-87e0-b8e088330303 | note | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
27b9edca-12a4-572c-aa91-662ebe2d7b30 | note | Note: Different revisions of 610 have different clause numbers
47215d29-d386-54ea-bec3-ad56cfee904c | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder
b2031e16-b7ce-5565-a057-d7bfd28ad60b | textbox | Enter: Teambinder MDR Lot number
2d1b5125-9f8f-5019-b1ba-f89d68756d50 | note | – – – – – – – – – – – – – – – – –
da49aa55-d92a-53ff-b354-1c7ae918568f | note | METHOD: Document Review
1c1448fb-a618-58e3-9ddb-9680bed03ba6 | note | – – – – – – – – – – – – – – – – –
8570c1f5-a605-5398-879b-5518eb9fdb66 | note | FREQUENCY: Each element
bd71febc-420f-540f-862f-45e0e3eafd60 | note | – – – – – – – – – – – – – – – – –
d74623a6-9bc4-5973-aace-79155350e423 | note | CATEGORY: HP*
0a438998-ff63-5237-bb20-96de6eceb3b9 | note | – – – – – – – – – – – – – – – – –
a2b2185a-6ed3-527a-b62a-31f7419a7553 | note | RESPONSIBILITY: PE/SE/SPE
542a831d-5db0-541d-8978-06a90eac9ec3 | note | – – – – – – – – – – – – – – – – –
cfbeb12c-fc31-502e-a210-3b4cdcde4eda | note | VERIFYING DOCUMENTS: This ITP
86668b69-de6c-5de0-9924-3b17762c399b | date | Date Completed:
| checkpoint | 3.2 Elastomeric Bearings
44960410-b221-5867-a83e-3be6ed3750b2 | note | REFERENCE: IFC Drawings 652.02, 652.03, 652.04, AS5100.4
1f6ea7ef-b8d7-5af6-a86b-f98281298a52 | note | – – – – – – – – – – – – – – – – –
5b359cd0-a984-5596-a528-d0199bfbc7cb | note | ACCEPTANCE CRITERIA: Elastomeric bearings are to be manufactured to the requirements of the IFC Drawings and AS5100.4.
bd7bc42c-43c2-5888-a047-82e62e1d466f | note | Tolerances:
34c805d3-21d5-5c1d-81ec-2d01ab63dccd | note | ○ Dimensions in plan = +4mm, -2mm
cd062295-d35e-54c8-bc44-6483b85d115f | note | Thickness =
2a919ac0-2c79-5800-834c-e368d26752c3 | note | ○ ≤100mm = ±2mm
efe2a1c7-052d-5860-9959-1a9efec41ab2 | note | ○ >100mm ≤ 150mm = ±3mm
66ed1828-0ba8-50a5-9220-a24187279951 | note | ○ > 150mm = ±4mm
c22645fb-94b1-5920-be6b-37c843cd55d7 | note | Testing:
8ce03773-2d7a-53f3-aab4-a1f02041a72e | note | ○ Each bearing tested under compression
c7fb565c-b45e-5bc6-8308-ca9ba90db540 | note | ○ Batch tested for shear stiffness
a8e8bf74-d052-5baa-9422-2455dd067d9a | note | Attach: Elastomeric Bearing Test Reports
bd4015e6-c72c-5427-9cd0-af03730044e4 | note | Attach: Elastomeric Dimensional Records
f08c0bff-2dae-5dae-94dc-1b0f4657b84f | note | – – – – – – – – – – – – – – – – –
e726e936-0931-5c56-b3c6-443322877257 | note | METHOD: Document Review
ca8b8a50-1783-5add-880e-e6b7a2fdca55 | note | – – – – – – – – – – – – – – – – –
e5d6ab36-9024-5f6f-bead-c4dd4e5cfa77 | note | FREQUENCY: Each element
b8ff6bb7-3c31-5a25-b02e-d5f5808d3546 | note | – – – – – – – – – – – – – – – – –
d7861cfa-5e09-56ff-87d4-3494e5df5a31 | note | CATEGORY: HP
a013569b-1fb4-52f9-a20a-51e62c2ceb14 | note | – – – – – – – – – – – – – – – – –
8d1a5201-d740-595d-a60e-d924eabdb4da | note | RESPONSIBILITY: PE/SE/SPE
f4b22893-0583-5bb1-8c3b-2680ab6c0f04 | note | – – – – – – – – – – – – – – – – –
e2116f17-2e71-572c-b77e-055da46a14c5 | note | VERIFYING DOCUMENTS: This ITP
0f245200-fd54-554e-9a9b-39ecae23a5e3 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.3 Tapper plates
6970fa04-1d92-5d51-ab64-ddceeb9673ca | note | REFERENCE: VR 620.05
9fd9abc4-3acd-5582-a3dd-fedb58a6d7f8 | note | – – – – – – – – – – – – – – – – –
726b0ff1-a28e-56ac-91a7-ed2362a2e20d | note | ACCEPTANCE CRITERIA: Material for sole plates and bearing retainers shall be of structural grade steel complying with the requirements of AS 3678. All surfaces and edges of sole plates shall be finished smooth and bearing surfaces shall have a maximum out of flatness of 0.4 mm.
928c7b81-eefc-5fde-8cb0-6a53011e1bfa | textbox | Enter: Teambinder MDR Lot number
106c8145-9b27-55d9-8293-67e459b19341 | note | – – – – – – – – – – – – – – – – –
14751350-4d30-55a5-b21d-1354ddd26ff0 | note | METHOD: Document Review
916c72c7-258c-5715-9e78-e25efe2e6fb5 | note | – – – – – – – – – – – – – – – – –
2ea2e69f-546d-59fd-bf1d-764aad9315cd | note | FREQUENCY: Each Plate
df5bf641-2a2b-5336-92de-0e73c765b031 | note | – – – – – – – – – – – – – – – – –
0c97b1d9-3d41-5ed9-a4a4-9ab5566f8760 | note | CATEGORY: IP
8cb26604-a3c5-5669-942f-a4a0a557fc78 | note | – – – – – – – – – – – – – – – – –
f9d3df92-2102-570d-8a7d-c3da9ef8857f | note | RESPONSIBILITY: SE/PE
5be94bc8-2bfe-5c47-a4d7-e4c251145959 | note | – – – – – – – – – – – – – – – – –
a7a5a367-fcde-5e07-9d4e-cc0451458952 | note | VERIFYING DOCUMENTS: This ITP
3a0bba32-cf75-5c01-9444-ef41e005c016 | date | Date Completed:
| section | Pre-construction Activities
| checkpoint | 4.1 Bearing Plates-Check
354a2592-1d8b-50a7-bbcb-c823524c643c | note | REFERENCE: IFC Drawing MRP-052-C-SME-DRG-31-MPK-CBR-1112 Note 3
c670975d-fb17-5cdd-b956-0bb8ab2a98bb | note | – – – – – – – – – – – – – – – – –
b988bfee-ef30-5ccf-bb27-2ecff99ce5b6 | note | ACCEPTANCE CRITERIA: Bearing Plates shall be inspected after fixing to girders and prior to the erection of the girders. Ensure the plate and plate orientation are correct
c42ae47e-415d-509a-b39e-5dd30bc2d2ed | note | – – – – – – – – – – – – – – – – –
74ffc893-5c66-527a-b0fc-3b175f612ded | note | METHOD: Visual
29124a02-6f5b-5344-8959-385473b15614 | note | – – – – – – – – – – – – – – – – –
c520c8a5-8a56-5ec7-98e4-2e1fc0cb463e | note | FREQUENCY: Each Tapper plate
87b35cc6-8f7a-53ee-8909-9d081cff2bd1 | note | – – – – – – – – – – – – – – – – –
047d08c3-4240-52f1-86bd-f9e86e13b802 | note | CATEGORY: IP
48a40e2e-60a4-5dfc-94de-ae085e91bea2 | note | – – – – – – – – – – – – – – – – –
05f8b1ae-4d60-5811-a38a-7b59cfc154b9 | note | RESPONSIBILITY: SE/PE
9e82b9a9-fdd6-5299-88a1-b7b6d4081173 | note | – – – – – – – – – – – – – – – – –
9355a67e-1b9c-5614-8ece-c50b1bb88338 | note | VERIFYING DOCUMENTS: This ITP
d8bdcdd0-6cb3-5ffa-ae5f-3aa4ae33ef69 | date | Date Completed:
| checkpoint | 4.2 Crosshead / Pedestal Tolerances
b8ba50c1-eeac-5037-bdeb-2919ffc57876 | note | REFERENCE: Survey As-builts / Survey Report
e47ab6c5-d71e-56a0-94f7-e47d0069e789 | note | – – – – – – – – – – – – – – – – –
e86378fa-9b07-5107-bc26-dcbfc270b79b | note | ACCEPTANCE CRITERIA: Re-check that the As-built dimensional tolerances comply with the requirements below:
98d105a3-eb10-5e3d-b279-784b795367c7 | note | ○ Reduced level ±2.5mm
a83610e5-7613-5611-9ea7-acd6e5a39825 | note | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
a4f14a2c-daff-546b-9f41-cc24994e8e71 | note | ○ Deviation from flat surface ±1mm
b47f6a54-5bbc-5241-87f9-3f2db00322e8 | note | – – – – – – – – – – – – – – – – –
ef6108cc-251f-5f3b-82fa-cb8e5887e9be | note | METHOD: Document Review
50f07ba5-9567-5892-a4a4-911dd00c7fd5 | note | – – – – – – – – – – – – – – – – –
a14d45a3-b5ad-5d6b-b944-c10ce1bd3060 | note | FREQUENCY: Each element
f9d15ed9-25a5-52d6-ae47-6456f1270cfc | note | – – – – – – – – – – – – – – – – –
0d3ad228-5884-5660-af03-d0df7d158c39 | note | CATEGORY: IP
f691f6fe-87ea-5ca9-a71f-bf756a37df11 | note | – – – – – – – – – – – – – – – – –
915b74a0-da69-55fe-b0bc-a9331cb559bf | note | RESPONSIBILITY: PE/SE/SPE
c01f1a39-b5b9-54ff-a2a5-b159a501fa71 | note | – – – – – – – – – – – – – – – – –
ac16b116-a7b9-514d-b9ad-fddebf07af10 | note | VERIFYING DOCUMENTS: This ITP
67128f34-7e65-5b42-a3fd-4be4614eb5f2 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 Elastomeric Bearing Placement
fc709627-f934-5709-968d-b53f53910509 | note | REFERENCE: IFC Drawings VR 656.05
9acb16e5-f5ec-5666-9062-f1bc6031d49f | note | – – – – – – – – – – – – – – – – –
fae6f011-485a-5255-b804-eaa0a16369ea | note | ACCEPTANCE CRITERIA: Place the elastomeric bearings to the survey marks to achieve compliance with the IFC Drawings and tolerances.
b23a9770-300e-508d-98e4-9a8512a6033d | note | Tolerances:
54a01722-6bdd-52ff-b772-427ef66c10aa | note | ○ Plan position: ±2mm in any direction
f0be4a87-a63a-5a19-9f5c-684bc0de463b | note | ○ Level: ±2mm
e5a1a7e5-6369-51ee-b33b-5def166dd409 | note | Record: The elastomeric bearing ID onto the Red-line Drawings or Survey Report
bfea7015-c45c-522f-a01d-2b361295d402 | note | – – – – – – – – – – – – – – – – –
1e51e3ab-5413-5bf2-a1be-98fe09da0378 | note | METHOD: Measure, Visual
3d7d27da-ffbe-5103-b664-66fbf8558aae | note | – – – – – – – – – – – – – – – – –
4ff63eb9-b70e-5a3a-a68f-edd38b5f4df1 | note | FREQUENCY: Where applicable, each bearing location
b75c3a85-a313-5960-9e58-4187408e5730 | note | – – – – – – – – – – – – – – – – –
a1fc238d-cc98-57c0-8391-65fca452aeb8 | note | CATEGORY: IP
85e96bf6-3c15-5b6c-85e0-225246d5ea3d | note | – – – – – – – – – – – – – – – – –
5c4d3e50-0efb-506d-bd5c-27b6cd86f63f | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
6bdc7302-de1f-58ab-8461-13c26b8ec89f | note | – – – – – – – – – – – – – – – – –
628049e4-c81d-58aa-b732-ebd29ff4ca74 | note | VERIFYING DOCUMENTS: This ITP
5e11e5e4-20a9-5c9d-8d0d-1d86a0f21010 | date | Date Completed:
| checkpoint | 5.2 Restraining Blocks-HDPE Packers
4b0f5a8b-966d-5dec-ae1d-8a01f3219e30 | note | REFERENCE: IFC Drawing
e8175e80-02b3-500f-ad35-868b7ba0136e | note | – – – – – – – – – – – – – – – – –
91827ca7-ffbf-5472-85c4-15c49b94c8e1 | note | ACCEPTANCE CRITERIA: 200x200x35mm HDPE packers are to be installed in designated recesses on restraining blocks.
74670c7b-635e-5bc7-b511-3513564783a9 | note | – – – – – – – – – – – – – – – – –
f986b19e-5ffa-5412-b1b8-2adeffa25628 | note | METHOD: Visual
916b0d57-69d1-5c3a-9e07-7dd7e457a0db | note | – – – – – – – – – – – – – – – – –
95217e9b-8e18-50de-89fa-89c33bace420 | note | FREQUENCY: Each restraining block
7376e8dc-5efd-5bed-8205-20e44745ebbe | note | – – – – – – – – – – – – – – – – –
c27acb41-706c-5b96-8d36-2dde83afa740 | note | CATEGORY: IP
f702e2df-9aea-595e-bf0c-cae9947754b4 | note | – – – – – – – – – – – – – – – – –
9be8fa0e-071c-5ace-add1-09b0005f0663 | note | RESPONSIBILITY: SE/PE
71a020fe-1a12-56ee-a7a8-4fd7265aed2b | note | – – – – – – – – – – – – – – – – –
6d2e5ab4-3e62-5af9-be05-3cf7b752ffd9 | note | VERIFYING DOCUMENTS: This ITP
325f6361-b268-5573-ae8c-b226d0780211 | date | Date Completed:
| checkpoint | 5.3 Precast Handling
d282ec04-c672-559a-8d20-f786f13c01d7 | note | REFERENCE: 620.07 Crane Lift Study
707adac6-5a2c-5d75-abba-f35701751378 | note | – – – – – – – – – – – – – – – – –
216e8aff-3293-5a59-8a74-4bbd0eca3bf1 | note | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
097dab8d-f319-5435-88ce-b03b991a0ed8 | note | – – – – – – – – – – – – – – – – –
da527464-9b68-5147-999e-28b54517de81 | note | METHOD: Visual
2b27942b-cead-5252-9bce-3f6cfe6392fd | note | – – – – – – – – – – – – – – – – –
44683602-ee0e-56b9-8444-573f82a144aa | note | FREQUENCY: Each element
c8aea3a4-a2dc-5df0-a609-df50877a2485 | note | – – – – – – – – – – – – – – – – –
cbd1360b-3759-5393-b217-90ccd6c9064e | note | CATEGORY: IP
973db2b6-f180-59f3-a669-3ea4f34f2ebf | note | – – – – – – – – – – – – – – – – –
1b97d93e-679e-5b4e-a935-1f279e622c8c | note | RESPONSIBILITY: SE/PE/SPE
4a488b50-2410-5578-af79-308006d584cb | note | – – – – – – – – – – – – – – – – –
7ee23b41-88cf-52e3-9df5-57cf60fd2e18 | note | VERIFYING DOCUMENTS: This ITP
24df1648-b3fc-593f-91a3-718c95360160 | date | Date Completed:
| checkpoint | 5.4 Precast Placement
53227dca-479c-59f3-8b33-28dfdfee169a | note | REFERENCE: IFC Drawings 610.27
908cf177-5070-52b2-bb10-f9fef27ed0f7 | note | – – – – – – – – – – – – – – – – –
553f2d31-4e51-5738-bd0b-0ce31533c3b4 | note | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
71a5dca7-31b7-519c-b4a0-f36a6126d323 | note | ○ The nominal gap between elements is as per the IFC Drawings.
21c1b393-9296-5ab0-b727-b9b8bca07093 | note | – – – – – – – – – – – – – – – – –
01421581-6cf5-5baf-b2e8-2251ad05669a | note | METHOD: Measure, Visual
cbdc1f04-7fd0-5df4-b75f-6b196b7175de | note | – – – – – – – – – – – – – – – – –
d6ceeeb0-ac15-5293-b16f-9479b2b331c8 | note | FREQUENCY: Each element
50ecec0e-0610-54de-956b-2c98082144ed | note | – – – – – – – – – – – – – – – – –
c08e153e-cbed-5487-b7b7-04164ce6e3a9 | note | CATEGORY: IP
a6a470c2-f18c-5f4e-8e4b-025ec29320ff | note | – – – – – – – – – – – – – – – – –
8a347efb-108b-5e9b-bc0c-f1af66670237 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
57f16d85-d084-5f54-828c-61f2edc4a574 | note | – – – – – – – – – – – – – – – – –
d5116e4c-9bc1-5fb4-840b-5aab616b216c | note | VERIFYING DOCUMENTS: This ITP
d466ebe6-3594-59aa-8c97-de48e7f5d75d | date | Date Completed:
| checkpoint | 5.5 Precast Traceability
beebb05d-f10e-54ba-9066-dfbfa3047085 | note | REFERENCE: 620.09
6197bbc9-4dbb-5b37-89c7-a07646b2dce4 | note | – – – – – – – – – – – – – – – – –
6158d772-7566-5612-b139-944f1064e602 | note | ACCEPTANCE CRITERIA: All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
bd7464a4-8b6b-5093-a8f4-ea1b43de789e | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
d86df572-7bcb-551a-82ac-c65f429d6ffe | note | – – – – – – – – – – – – – – – – –
f711abdf-f89d-5166-9fa4-16880a963d3f | note | METHOD: Visual
345f842f-b67e-582f-ae7c-1a0f8edd296d | note | – – – – – – – – – – – – – – – – –
2dfb6fe3-6bd9-5c2f-b029-39fd32ab2318 | note | FREQUENCY: Each element
f6c5a16f-031e-5f20-8cf5-678e91d45b04 | note | – – – – – – – – – – – – – – – – –
940c9414-a7ac-5413-9a6f-295910b235c1 | note | CATEGORY: IP
a6b2b72d-6628-5d27-9ad5-c64f07e3da7a | note | – – – – – – – – – – – – – – – – –
a303d35d-b4c7-582d-a97c-76070c2871cd | note | RESPONSIBILITY: SE/PE/SPE
1e2f7d9e-2717-577c-80a9-f72cddeafab7 | note | – – – – – – – – – – – – – – – – –
0f851020-62db-583f-bf4f-e7b2e270d17b | note | VERIFYING DOCUMENTS: This ITP
001aeed8-925b-52ec-b867-ce16e40f09b7 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 As-built Survey
52557e39-e6c3-5876-a529-af58119849b6 | note | REFERENCE: IFC Drawings 610.47 (a) Table 610.472 (March/June 2019)
0c12c109-db2b-542e-a33c-d61df342000e | note | – – – – – – – – – – – – – – – – –
fb907f0d-cfad-50b9-91d4-f45c6e35e1f2 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
7f2293d0-8b77-5867-a9ea-c02d77a87c01 | note | Attach: Survey As-builts / Survey Report
81fafe3b-47c4-5882-9da6-bc42324c2bfd | note | – – – – – – – – – – – – – – – – –
bfd68a2c-9d86-5f51-8781-dfdec26d6180 | note | METHOD: Document Review
1e441e99-f36c-5050-ad3c-f14c6cb2885b | note | – – – – – – – – – – – – – – – – –
347ba275-db3e-516b-bc52-2925fde1259d | note | FREQUENCY: Each element
e17583db-e593-5747-89aa-beb56117f52a | note | – – – – – – – – – – – – – – – – –
423d193b-23fd-5384-9d85-53a27b48d12c | note | CATEGORY: IP
75a3da20-afeb-553e-ba3d-c013f95d8a6e | note | – – – – – – – – – – – – – – – – –
8df8623c-080e-523c-b54b-9914e7ac77d8 | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
fd156e82-5b28-56f5-b98f-f4cacfebb1de | note | – – – – – – – – – – – – – – – – –
4312c39e-0175-540f-9f7b-0af87260f68c | note | VERIFYING DOCUMENTS: This ITP
8cc938d7-a239-5e0f-ab46-2b6c73f0a403 | date | Date Completed:
| checkpoint | 6.2 Non-conformance Report (NCR) Closure
cf8c73ce-3923-5e13-9130-9bdd9e921717 | note | REFERENCE: MRPA Quality Management Plan
883a9bfa-17bd-5c63-a8c7-10bec724d609 | note | – – – – – – – – – – – – – – – – –
27ddc896-9aae-5c20-82ad-7ae4c37cfc26 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
55ef7643-b65d-5a2d-9906-170f96242ce0 | note | – – – – – – – – – – – – – – – – –
e8c82db2-54a9-5e57-8ae2-ed6b84807d92 | note | METHOD: Document Review
d865108f-a706-5a9a-bb61-b1025c2300a6 | note | – – – – – – – – – – – – – – – – –
bcc6c418-01df-5e09-865c-1ae42663c38e | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
b8c3dade-3628-5156-a4b3-356b68596b0d | note | – – – – – – – – – – – – – – – – –
74f74944-a7ed-5247-bd34-957d1409e084 | note | CATEGORY: HP*
f86ceeac-fcad-5bb5-b046-4433d99df220 | note | – – – – – – – – – – – – – – – – –
22b3693e-c0dd-5f85-9e94-a46db9b62bae | note | RESPONSIBILITY: SE/PE/SPE
64ce0201-a076-5f30-88d9-7d1e1c6956c3 | note | – – – – – – – – – – – – – – – – –
9df863a9-0dba-52f5-b782-6f15148bfd4f | note | VERIFYING DOCUMENTS: This ITP
4c650473-af2c-5fd1-90c6-29b4292c0fea | date | Date Completed:
| checkpoint | Final Inspection
cfe9e132-9d97-5e6d-9c8a-137e219eca53 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
291487b7-390d-5298-a013-6d683564322d | textbox | Name:
1ddf4c17-c13f-50ed-a517-dc0016b83ed0 | textbox | Position:
8cd8f80d-0aec-5053-a135-499fcdf61b14 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-093-Rail-CAMMS-Pedestrian Crossing Removal & Spot Tamping Rev 0 | itp | ITP-093-Rail-CAMMS-Pedestrian Crossing Removal & Spot Tamping |  | 68492a71-7ef8-41eb-ab68-2b0f9d9ae9c8
| section | Referenced Documentation
| checkpoint | Referenced Documentation
1f26799a-4307-5035-8025-3e9651f16f90 | note | Document Title: ITP-093-Rail-CAMMS-Pedestrian Crossing Removal & Spot Tamping
b14b337e-1d65-53c1-9184-702c92a405df | note | ITP Description: CAMMS-Pedestrian Crossing Removal & Spot Tamping
2dcd2ba4-6643-5c3c-94a3-9e1a36d2e89a | note | ITP number:
efde42aa-1e84-5f8e-a7f3-f13f087c9b8e | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
6a9256a6-1aad-59f5-8cb1-a9ae9ef271f5 | note | Discipline (e.g. CIV/STR/RAIL): 093-Rail
6850776a-4fa2-5ee2-9e97-877511f5059e | note | Revision Number: 0
80bab366-91b6-5455-b9c1-73e65be2b963 | note | Revision Date: 4/09/2023
af8cd854-ecb8-5b9f-9ac5-562bbe2c1a3b | note | ITP created by: Jake Argentaro
99189b79-1e09-5440-9426-ccc67d538fa5 | note | ITP approved for use by: Victor Mira
325ef94b-5b79-5b14-a0c7-b30df631b55d | note | 1.1 Non Dependent
1b1dc24d-04ba-50e2-8bae-2dc781fba55f | note | Reference: L1-CHE-SPE-316 Concrete Sleepers
c6f09485-36dd-5e95-9903-c35763ae5623 | note | 1.2 Non Dependent
1e4dc4f5-ef0b-50d8-bfb6-99251e2d034c | note | Reference: L1-CHE-SPE-003 Heavy Rail Construction Tolerances
1cd677e9-ed04-5056-8fe1-f8ba27460677 | note | 1.3 Non Dependent
60358319-12bc-5007-9080-044ffb55273f | note | Reference: L1-CHE-SPE-064 Ballast Supply
aa101328-59d7-5dfe-be00-fe29c73819ad | note | 1.4 Non Dependent
881c0d19-2849-54bd-b917-61524511d52d | note | Reference: L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
990da862-99ce-59de-9eaa-1bed24a25380 | note | 1.5 Non Dependent
90ee4cf3-16d9-5bcd-86fa-1c748af8ae96 | note | Reference: PTC Heavy Rail Track Construction Standards Drawing F598
374244d4-56a5-53ce-81bb-0bb810971d8c | note | 1.6 Non Dependent
233924c5-2bf2-5cf1-a9f3-1e46fb160d0e | note | Reference: Camms Road Package 52 Design Drawings
| section | Preliminaries
| checkpoint | 2.01 Obtain and submit Material Certificate of Compliance for Track Materials; Track Jewellery / Ballast 60mm Aggregate
01f682f0-9c54-59b3-8b7c-91edcd2e3db9 | note | REFERENCE: IFC Drawing, Track Construction Site Mudmap, Bill of Materials
3e970568-984c-531b-accf-7c935311bbd7 | note | – – – – – – – – – – – – – – – – –
daa559c7-6d96-5f13-8596-c42d8db0f544 | note | ACCEPTANCE CRITERIA: Units to be free from damage, total and types of units for full set validated No signs of discoloration
9d6bfd10-2321-5a10-b421-6c47cb08c2b4 | note | Attach: Manufactuer Certificates of Compliance
db22d78e-18b8-5374-9201-023d50236cc7 | note | – – – – – – – – – – – – – – – – –
eaa893d2-9a15-54ec-a0be-ebd2c2b3aedc | note | METHOD: Review Document
f9b2b8de-7160-517a-9d61-faadabd970c5 | note | – – – – – – – – – – – – – – – – –
ac38bae5-6f2d-5439-949b-0a394acc2556 | note | FREQUENCY: Once
f917dc4c-5dfb-5019-a1b4-54b943f3279d | note | – – – – – – – – – – – – – – – – –
e51247a2-762c-538c-b03b-e9aed05e2ce3 | note | CATEGORY: HP
e32b5f63-86ce-5301-ba47-660d925f9557 | note | – – – – – – – – – – – – – – – – –
f8028b45-e320-51ca-95aa-54c00528c7d9 | note | RESPONSIBILITY: Track Supervisor, Project Engineer
5b45cbc3-c746-552e-a48b-a94324d44104 | note | – – – – – – – – – – – – – – – – –
3355a46b-e005-5c8d-9b0f-ce7552232676 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
a4d05182-d3c9-5be6-8991-ff5cf12edaba | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.02 Submit Asphalt Cutting Plan
635ba5e9-bb31-5831-9af8-78e193e9aa17 | note | REFERENCE: Track Construction Site Mudmap, Asphalt Cutting Plan
30f6e68e-5640-5e2c-bd73-f9e7b765317b | note | – – – – – – – – – – – – – – – – –
9a7e4c28-d8fc-52aa-93d4-66c9aea23f25 | note | ACCEPTANCE CRITERIA: Plant to detail cutting pattern for asphalt required for removal.
bf24534f-bf3f-5dde-a526-197668c73692 | note | ○ Asphalt to be cut to 150mm depth to provide clearance between cutting disc and concrete sleepers/rail jewellery
bc4cf755-881d-5485-9505-0f9f115e432c | note | – – – – – – – – – – – – – – – – –
7b656baf-a4b7-5274-a48b-37dd6592f691 | note | METHOD: Review Document
998d2811-e40d-5c2b-8a5c-0a648b4d8657 | note | – – – – – – – – – – – – – – – – –
498ea975-0bcb-57cc-ada3-94d450361ee0 | note | FREQUENCY: Once
0675bc2c-658d-5d42-afc5-b11108c5e07c | note | – – – – – – – – – – – – – – – – –
66a885ad-757a-556b-a7a5-ccf9bb06a513 | note | CATEGORY: HP
d73fff91-7d16-5fd1-b59d-5398f03d416a | note | – – – – – – – – – – – – – – – – –
90849dc2-be49-5a6a-a07c-86feac27c92f | note | RESPONSIBILITY: Track Supervisor, Project Engineer
aa7dcbc1-08b3-5968-924f-1febbf5a9f73 | note | – – – – – – – – – – – – – – – – –
50bebc5e-0e90-5670-9b75-a7b0f5846b29 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
e4114312-6a18-5d19-8413-73ff27479611 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.03 Inspect supplied items upon delivery
23227df2-b88c-59bf-ae3d-972ca8eb95bf | note | REFERENCE: IFC Drawing
31a05b0a-6bb6-51a7-84cb-b10bcf11a2e0 | note | – – – – – – – – – – – – – – – – –
f6e550d6-77e9-5369-a634-22b673caf9f6 | note | ACCEPTANCE CRITERIA: No damage or rust on components
36e764dc-2808-512d-b747-86f3e7be21dd | note | ○ Validate total number and type of components matches drawing
154dcb05-c133-5553-ba1e-2f327b391b4d | note | Attach: Photos on site;
286a1b2c-1df6-572f-808e-eedb98020f04 | note | – Track Jewellery
c4a20f9e-9505-51e6-96af-0630d77e7076 | note | – Ballast 60mm Aggregate
4a8de085-ffc5-5d8f-bc92-1b37cf7c7fb0 | note | – – – – – – – – – – – – – – – – –
7eb6df63-a8a4-5760-a52a-6484379422cd | note | METHOD: Visual Measure
119667e1-760f-5040-860d-57c2c41c3465 | note | – – – – – – – – – – – – – – – – –
bf240934-8c2e-503b-a031-1a7eea040596 | note | FREQUENCY: Per delivery
23d5203f-4ce4-5c6e-b435-115424eee0f8 | note | – – – – – – – – – – – – – – – – –
80ec4580-8990-501b-bb91-179076260892 | note | CATEGORY: IP
624b084e-93e8-5960-816d-18ab4daf5c75 | note | – – – – – – – – – – – – – – – – –
130250d8-5269-55f8-a3e2-55dc4f995164 | note | RESPONSIBILITY: Track Supervisor, Project Engineer
4d817a4e-bbb6-555e-b650-f48fa4f83265 | note | – – – – – – – – – – – – – – – – –
7ac6e26e-e82b-5b04-b905-c2654b182d18 | note | VERIFYING DOCUMENTS: Material Inspection Report
77d11e25-69ab-5588-9a2c-b5bb22bb73ee | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 3.01 Cut and remove asphalt, Clean track structure of loose asphalt and debris, remove contaminated asphalt as required
1d42ac6f-175f-5869-ae0d-a7a2cd32c704 | note | REFERENCE: Asphalt cutting plan
a9a9907b-012c-5cad-8863-5024de1529cd | note | – – – – – – – – – – – – – – – – –
24b570dd-27c4-522d-bc99-a70bb95e7ccf | note | ACCEPTANCE CRITERIA: Cut asphalt as per cutting plan, asphalt to be cut at depth of 150mm so as to avoid damage to rail and sleepers.
b53fcdb0-81ec-5c54-95b3-9cff490a6b2d | note | ○ Remove asphalt material, clean debris off rail and ballast, remove contaminated ballast as requried.
54f5d971-39df-5d13-9c60-c5a85ce5c417 | note | – – – – – – – – – – – – – – – – –
6cf31cd1-e5f1-5b1d-b8d8-44ebba20de3c | note | METHOD: Visual Measure
4aa07b22-4f9c-55c6-98c5-e1ae83ca9a6c | note | – – – – – – – – – – – – – – – – –
dc9e630d-6722-5671-a234-07c3d5c3a099 | note | FREQUENCY: Once
8949e415-f83c-5ae1-8619-40c08aee5824 | note | – – – – – – – – – – – – – – – – –
3674f1c4-0cb7-5aaa-baf6-270ddff51a95 | note | CATEGORY: IP
4fdb8b6c-d3b6-50d1-a361-f328af71d30e | note | – – – – – – – – – – – – – – – – –
3d808efc-426d-5e70-8508-69106b6e2334 | note | RESPONSIBILITY: Track Surveyor, Track Supervisor, Site/Project Engineer
8bf02ec1-1171-5a6f-819f-0db832fc0191 | note | – – – – – – – – – – – – – – – – –
21e5e4d2-681d-53be-aeca-5a779bd64d9c | note | VERIFYING DOCUMENTS: This ITP
be160695-0f12-5ef9-aee7-7dbdc681a3d3 | date | Date Completed:
| checkpoint | 3.02 Fastening replacement as required
85189a59-a7b3-5458-b5ba-3f5fa87e2f96 | note | REFERENCE: L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
20078840-473b-5128-b586-7ef2af4e3465 | note | – – – – – – – – – – – – – – – – –
fc01669b-0e9e-571d-b961-d582c786c57a | note | ACCEPTANCE CRITERIA: All rail sitting within Sleeper footing with correct sleeper insulators
0bd21416-03df-535a-8557-7e9898424bc7 | note | ○ All rail fastenings installed
25d1b79f-fced-5d02-8dd3-9e0261f78211 | note | Attach Site Photo:
73faeb6c-d1b2-56ff-8e1b-29527b183199 | note | – Installed sleepers & fastenings
c29da72b-1f3f-5d32-800a-5b2d523c7257 | note | – – – – – – – – – – – – – – – – –
d9ccbfb9-4485-5a4f-8c60-f392c51d1db9 | note | METHOD: Visual Measure
62f8c60f-44d0-599d-b7ad-cf38efd3cfb8 | note | – – – – – – – – – – – – – – – – –
fde433c9-7414-5d8e-8db3-24aa4d3c9519 | note | FREQUENCY: Once
805d3d40-7ec8-59c0-b9bc-9244f04d67d6 | note | – – – – – – – – – – – – – – – – –
6e89cf42-f608-56f9-99b4-068b4135625c | note | CATEGORY: IP
0b334ee7-fab0-50bd-b7a4-45db51f2be7c | note | – – – – – – – – – – – – – – – – –
0860407d-dd73-5aae-bc84-d24e8829a2a8 | note | RESPONSIBILITY: Track Supervisor, Site/Project Engineer
7db0081f-33ea-5d70-944c-65d33e92a83a | note | – – – – – – – – – – – – – – – – –
3f6697ae-171a-5000-b28b-2af54af95abf | note | VERIFYING DOCUMENTS: This ITP
d120b85f-4921-5b93-99fa-4ddfa5017d1d | date | Date Completed:
| checkpoint | 3.03 Track Tamping
046744a4-8a7b-5ea0-b426-119d141fad5c | note | REFERENCE: Track tamping alignment as per existing
deaea297-6c30-5b1e-bfd1-9276c3e84003 | note | – – – – – – – – – – – – – – – – –
bc16cfba-9a91-53d4-852b-f1bba45f8353 | note | ACCEPTANCE CRITERIA: Track Excavator Tamped, Ensures Track Geometry Tolerances are not breached;
f02c40ad-d5a6-5b6c-b450-e5e9d8c4c7aa | note | ○ Gauge +3 / -3
8cc3533d-20c8-5ae1-a0af-dcd6700b45b4 | note | ○ Gauge Variation in 2m 4
a5a6b05d-78f9-586c-90c8-6f1555c82353 | note | ○ Line (10m Chord) +4 / -4
1885d887-635b-5161-9a31-c9c4d77e1b80 | note | ○ Twist (3.5m Chord) +2 / -2
50c5a826-adf7-56e7-a291-01a2486eb608 | note | ○ Top (10m Chord) +5 / -5
000b11c0-a5f6-5adb-8850-7c500cfae840 | note | ○ Cant +5 / -5
2ec50e31-f4ba-5e04-8ca7-92aad56f9ffe | note | ○ General Alignment +15/ -15 (note, partial resleeper only requries track to be tamped to conform with local geometry, no survey requirement)
237a92aa-b597-52d6-9a18-a3fd4a22ffa4 | note | ○ A minimum horizontal clearance of 3.0m from track centreline to structure.
20750d01-06ad-5b1d-bd0f-9c08062d5f0a | note | ○ Height and Stagger readings of overhead wire to ensure minimum clearance of 4.61m is not breached
0a6e8c90-1136-5d5e-8e12-d1fc1b378194 | note | Attach;
abd59798-6d79-5eae-ae4c-434c0bb50c65 | note | – Tamping Geometry Recording
87ec04ac-ddfd-57c0-8b09-76a533d874e3 | note | Attach Site Photos:
02e6116e-62d5-5327-a615-7ee330d1c450 | note | – Tamping Activity
2616411a-0eef-5fe7-9b23-61ee0446bb3b | note | – Overhead measuring Activity
cb2cd83d-3c65-50de-8065-31a15b2c05f0 | note | – Structual Offset Measurement
ebd999f9-e115-58ad-b08b-2c0e7cc532bf | note | – – – – – – – – – – – – – – – – –
fbe87477-fb42-54cc-ac6a-e5189688f863 | note | METHOD: Visual Measure
92ea9419-576b-5732-a1a1-e93bc05f5da5 | note | – – – – – – – – – – – – – – – – –
0d52f431-2ebb-5076-adbb-a920f77d24e7 | note | FREQUENCY: Once
c746851c-2597-57c6-9d40-c2772aa42fa2 | note | – – – – – – – – – – – – – – – – –
e616a2f5-70a8-5b48-9628-463c33252a5c | note | CATEGORY: HP
ac3960f6-96d7-5459-b6dd-ccc6e65a4941 | note | – – – – – – – – – – – – – – – – –
71221f33-0410-5589-80c0-4a795705ca42 | note | RESPONSIBILITY: Tamping Operator, Track Surveyor, Overhead Engineer, Track Supervisor, Site/Project Engineer
bc973526-a382-5e96-98b7-e2d0625ad861 | note | – – – – – – – – – – – – – – – – –
67726ff3-b1e9-55da-9039-98712e0bbb19 | note | VERIFYING DOCUMENTS: This ITP
4cc4b95f-1a6c-5113-94f5-e3df8594ba86 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 3.04 Regualting and Ballast Profile
04e68190-22f4-554b-b45f-0fb2272092f8 | note | REFERENCE: L1-CHE-STD-039 MTST 000002-01 Track Design and Construction
c5857e42-6337-5eee-ab6a-2e3ca9e1511b | note | – – – – – – – – – – – – – – – – –
07c6637e-2257-5a49-a807-31a68487aa97 | note | ACCEPTANCE CRITERIA: Ballast has 400m width from outer edge of kerbstone with 1:5 crossfall thereafter
b767f457-1d97-5f4c-b9e1-70fe7b075528 | note | ○ No Ballast to be on top surface of sleepers or aorund rail Fastenings
5452caac-f602-5d8b-8a50-682bfd77b72b | note | Attach Site Photos:
cc29b82f-e176-51c5-9513-e5fa3266ee17 | note | – Ballast Shoulder Measurement
f3d90e69-26c1-5e5f-a42f-f36a848cb1e6 | note | – Rubber Panels free of ballast materials
e11f47f0-d8a0-5853-bfb3-0c9713272c87 | note | – – – – – – – – – – – – – – – – –
e561b3fa-5d59-5ee5-95d6-ee7a6061f404 | note | METHOD: Visual Measure
2df39b37-a80f-524f-9f5c-8c55a756e28b | note | – – – – – – – – – – – – – – – – –
2e883289-ec3e-59fa-8c79-e5d5151b92d2 | note | FREQUENCY: Once
71c7d1ec-b952-5f8e-932b-2b649f6d9cfc | note | – – – – – – – – – – – – – – – – –
f4d292b0-1ecd-5e6c-9be6-13799c249d83 | note | CATEGORY: IP
2c62f4de-a62a-5da5-8f2d-f987c05bb131 | note | – – – – – – – – – – – – – – – – –
ab9012ad-4fcb-5a23-8376-2ce6e47838f2 | note | RESPONSIBILITY: Regulator Operator, Works Supervisor, Site/Project Engineer
fa6f1fc4-55cb-5cb0-9410-24068bcb4c27 | note | – – – – – – – – – – – – – – – – –
75374d99-5fed-5eb4-ac2f-699e035c942c | note | VERIFYING DOCUMENTS: This ITP
126ec64e-b266-52e6-b348-af4d6fba6c8c | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 4.01 Track Certification
44a7fdb8-3986-5aeb-8bc6-c83ac7e0f9a3 | note | REFERENCE: MTMF020000-1 – Track Form A T, MTMF020000-2 – Track Form B
19cbbdfe-9196-5487-b43f-a75e17ab975e | note | – – – – – – – – – – – – – – – – –
b4152570-cb1e-5c8b-b671-199f94d856bf | note | ACCEPTANCE CRITERIA:
6e3e5d1b-0bb4-527c-b45a-ab42dd69c4f5 | note | Attach:
37ceddf4-99ba-55c6-bb54-2b59d748431a | note | – Track Geometry Conformance Certificate
cdf38a20-4cf0-571e-9855-d601a9c9ecaa | note | – Track System and Component
4d643ff4-5e54-5f9c-a00f-425a3fe6c4ec | note | Attach Site Photos:
a8fd7a23-0539-5867-84f4-9b855713bb08 | note | – Before/After Photo of worksite
2d49814a-deea-53cd-82dd-1f687253c0a2 | note | – – – – – – – – – – – – – – – – –
cb636d66-d71e-5cad-829d-383d958932c1 | note | METHOD: Visual Measure, Document Reivew
9a756883-9f27-5866-9927-49c6b1d7dae2 | note | – – – – – – – – – – – – – – – – –
d97692a1-cf02-5180-b34c-9035fc43103f | note | FREQUENCY: Once when all occupation works complete
fe0d38ec-6bce-540a-bd71-d33cabb7b261 | note | – – – – – – – – – – – – – – – – –
9ec135f0-68ed-503e-ad93-332ff6a2d9e8 | note | CATEGORY: HP
b84474ae-ea11-5915-a8ed-db4b57bca988 | note | – – – – – – – – – – – – – – – – –
ed218176-c0b4-5a69-b2a4-26f65edf212b | note | RESPONSIBILITY: Nominated Authority (MTM Infrastructure Track Certifier)
469a9991-3995-5657-9a46-8d43ba25ce0a | note | – – – – – – – – – – – – – – – – –
4b55e9ca-63c8-5f83-8ba3-fb7deb8d2458 | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
783dc45c-e786-5b1a-a4da-006d3cd96375 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
2c335f2b-a7e3-53fb-83be-e89b94edc38d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
763d319d-9093-5271-8627-5aca7b319f6b | textbox | Name:
54c49bf0-1f2e-5ff7-af53-ffe3f227b924 | textbox | Position:
4800fff3-b424-5186-9190-2457a669b644 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-094-CIV-CAMMS-Landscape-Gabion Installation Rev 0 | itp | ITP-094-CIV-CAMMS-Landscape-Gabion Installation Rev 0 |  | 1d065ee2-ab1f-49f1-ba5e-bfb8f96b76c3
| section | Referenced Documentation
| checkpoint | Referenced Documentation
dc8f7f82-1155-5cfb-bfa9-9fa7c3514f6d | note | Document Title: ITP-094-CIV-CAMMS-Landscape-Gabion Installation
5da8352d-2457-516c-b84c-f4e8ecae9989 | note | ITP Description: CAMMS-Landscape-Gabion Installation
ff8af672-2a82-5333-a5e4-ea4eb945b291 | note | Discipline (e.g. CIV/STR/RAIL: 094-CIV
5788765b-aaef-57d4-8ab5-8fb6a8a8aba4 | note | Revision Number: 0
3a46ffb5-3e37-5a22-906a-37aef05417c9 | note | Revision Date: 22/10/23
68d5c53a-7cf0-5370-8fc5-499cdb15f435 | note | ITP created by: VM
36fca933-bf0d-5c8c-89a6-b09e70df02c6 | note | ITP approved for use by: VM
5b2dcfc5-6901-566d-a47c-ed496b12a4ff | note | 1.1 Vicroads Section 715 2013
6694cc88-6538-5b05-a89a-d4883571e9e7 | note | 1.2 Vicroads Section 801 2018
| section | Preliminaries - Materials
| checkpoint | 2.1 - Gabion Baskets, fasteners and braces
dae8219f-d4bd-56cb-a388-d7085cf7c9ce | note | REFERENCE - IFC Drawings: MRP-052-D-SMEC-DRG-71-MPK-AUD-5001
45b5ac7a-0a48-5b81-afb4-d47102142088 | note | – – – – – – – – – – – – – – – – –
0ab65484-5852-584a-87a9-fa444990d5e4 | note | ACCEPTANCE CRITERIA - Gabion baskets are to be Maccaferri 8x10 double twisted steel woven wire mesh with an internal wire diameter of 2.7mm. The mesh shall be GALMAC (95% zinc and 5% aluminium) and PVC coated.
91e8a95d-683f-5e63-9b46-54ede051c157 | textbox | Enter: Teambinder Material Approval number
8ae4409e-6145-5918-a17b-f9e27c723e73 | note | – – – – – – – – – – – – – – – – –
e18eae37-7707-50dc-ab1c-d235379a2b88 | note | METHOD - Document review
ba693890-cb26-531d-8113-56a18fb637b1 | note | – – – – – – – – – – – – – – – – –
9d8965f3-ab6b-5c27-9229-5283bdc16074 | note | FREQUENCY - Prior commencement of work
7a3d8876-b8d8-5913-9d06-044bdd3e4739 | note | – – – – – – – – – – – – – – – – –
1d4f982e-1879-59c8-8102-6da2f6aa07b3 | note | CATEGORY - HP
af2b7f93-0b3f-5866-840e-99e6c1323607 | note | – – – – – – – – – – – – – – – – –
62239a14-2496-5980-9b35-4a780dac3e84 | note | RESPONSIBILITY - Nominated Authority
6e4ee5d6-e2c5-58c4-8f23-38e8e6ba76bb | note | – – – – – – – – – – – – – – – – –
c44f338e-38db-58c0-9764-8bfacbcbbf21 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release TeamBinder Material approval
0a749ab6-fef9-5ce0-9f33-858a2baa577e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Fill Materials
ea354c8a-91a1-5db1-86f4-8c463aa04483 | note | REFERENCE - IFC Drawings: MRP-052-D-SMEC-DRG-71-MPK-AUD-5001 VR 801.03 VR 715.05 (a) and (b)
3c43d4e8-2f7b-55f1-8a92-2c86f42c18b6 | note | – – – – – – – – – – – – – – – – –
11d27b9e-a377-5796-89da-0db41a49052b | note | ACCEPTANCE CRITERIA - Prior to the commencement of work, the Contractor shall nominate the proposed source of rock and supply the specified test results for approval by the Superintendent. All rock used for gabion fill material and rock mattress fill material shall comply with the material requirements for ‘sound’ rock as specified in Section 801 and the Los Angeles Value (LAV) requirements of Table 801.033.
58fdaba6-28b3-578d-86e0-388ee85b13a2 | note | The rock shall have a minimum apparent particle density of 2.5 t/m3 In addition, the rock shall have a minimum wet strength of 100 kN and a wet/dry strength variation not exceeding 35%
47df15c7-63d9-5939-8f77-73910dadea87 | note | Rock Dimension: Min: 100mm Max:250mm
f105f97d-1bd7-5367-9432-a2e080d7b59e | textbox | Enter: Teambinder Material Approval number
41c1e5d7-22f2-5006-bf4f-f49dd5ef0fcd | note | – – – – – – – – – – – – – – – – –
cec8bbab-aa2b-5943-9d4c-5edf87df26ef | note | METHOD - Document review
67d5258a-9813-5482-ba09-bd90397a6bdf | note | – – – – – – – – – – – – – – – – –
80a0bd85-1eac-5ee1-a0f5-3208f639e095 | note | FREQUENCY - Prior commencement of work
215db4ba-53d6-56bc-981f-cdfa44cee051 | note | – – – – – – – – – – – – – – – – –
14bed077-a419-57b6-8ea0-0f9ee413df78 | note | CATEGORY - HP
54ff64ff-96b6-5c61-8cd6-0c61e70f0efa | note | – – – – – – – – – – – – – – – – –
96cf0bfa-ef2a-5beb-a94d-39368f200f81 | note | RESPONSIBILITY - Nominated Authority
97382930-9ada-5c90-90ab-d7dfddfb69b5 | note | – – – – – – – – – – – – – – – – –
4cbea1c2-91a0-5e4f-87d4-b0d2ac7b3926 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release TeamBinder Material approval
338867d2-2907-5538-86ef-75981dc7f885 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Geotextile
5077d9f5-fcb8-5327-aa59-4ef0a7c5f52b | note | REFERENCE - IFC Drawings: MRP-052-D-SMEC-DRG-71-MPK-AUD-500
d6f34e86-41e3-5288-8ffb-afc11b8d07ab | note | – – – – – – – – – – – – – – – – –
4851f91e-e426-595f-ba37-0397b21a6432 | note | ACCEPTANCE CRITERIA - BIDIM A34 or approved equivalent Geotextile
ab268f67-f3b3-51e1-b584-c06c9d4d3484 | textbox | Enter: Teambinder Material Approval number
2683f2b2-a76a-56a4-ba96-6cf49c3cefb7 | note | – – – – – – – – – – – – – – – – –
c66e1457-d1c6-579a-a42d-f3548d6c151d | note | METHOD - Document review
26789f02-56ab-5a10-be4a-96619462b867 | note | – – – – – – – – – – – – – – – – –
134f6fb4-02dd-574f-adbe-4dfb489d0eb1 | note | FREQUENCY - Prior commencement of work
88a24e26-2ff6-5a91-9c2d-e297d3301745 | note | – – – – – – – – – – – – – – – – –
091925c7-a7fb-54e0-a557-5400720ba9c3 | note | CATEGORY - HP
85cae1ed-1abd-532a-bd4d-14eb73a64e8d | note | – – – – – – – – – – – – – – – – –
295a5198-f3e2-5b8d-b466-8ef457ccdef2 | note | RESPONSIBILITY - Nominated Authority
51877171-a372-5743-a455-2d6a315a2494 | note | – – – – – – – – – – – – – – – – –
4c4bbdde-4064-5b85-885c-97f7988bcca6 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release TeamBinder Material approval
cc8b66cf-8420-5036-87ed-c7ce8fc647d9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Granular Material
02a0d020-44e4-5593-b077-183572f57497 | note | REFERENCE - IFC Drawings: MRP-052-D-SMEC-DRG-71-MPK-AUD-5001 VR 715.08 (e )
62eaee7b-9ab3-57e5-b50e-500ec1b55dc4 | note | – – – – – – – – – – – – – – – – –
99b0390d-3869-5ff0-9f87-9132fa78178f | note | ACCEPTANCE CRITERIA - Permeable fill material, consisting of Grade A4, A5, A6, B1, B2, B3 or B4 granular filter material which shall comply with the requirements of Section 702.
964381f9-03ff-5a90-8151-26399def3577 | textbox | Enter: Teambinder Material Approval number
c02c264f-62e4-5c72-aaf2-1b7b82e50c00 | note | – – – – – – – – – – – – – – – – –
8241cd66-8cf1-540d-9a3f-4c2e71e91263 | note | METHOD - Document review
90953cc6-23fe-53ef-93d0-f64da8c8985d | note | – – – – – – – – – – – – – – – – –
8c7e453f-65fd-5da4-b2df-8fedd43c9aaf | note | FREQUENCY - Prior commencement of work
2e1b83d9-02d0-5e7c-a0a5-77143b42d5c3 | note | – – – – – – – – – – – – – – – – –
b2e8f93a-fef5-5c80-a72a-3deb0766388b | note | CATEGORY - HP
5db6ab25-12f1-598b-bc3a-6d7c9573e6e6 | note | – – – – – – – – – – – – – – – – –
96108946-0464-5377-831d-9b0b90f6b638 | note | RESPONSIBILITY - Nominated Authority
ac70e190-ddce-5d5e-acbb-502249f1fcfa | note | – – – – – – – – – – – – – – – – –
4ebdcbed-b079-55da-9bf7-59b25f2c1be4 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release TeamBinder Material approval
9b1ea8b4-9246-532c-aa46-9e22b48b642b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Preliminaries - Documents
| checkpoint | 3.1 - Prefilled Gabions
98eaa892-a39f-5bba-8635-fd9834473954 | note | REFERENCE - VR 715.06 (e )
b62dd403-d0ce-56ac-aac4-5a978d0ab2f9 | note | – – – – – – – – – – – – – – – – –
f5a927c3-5894-5bbe-bbf9-359f16140417 | note | ACCEPTANCE CRITERIA - The use of prefilled gabions is not permitted without the prior written approval of the Superintendent. The Contractor shall submit a procedure for filling, lifting and transporting prefilled gabions for approval by the Superintendent. The procedure shall demonstrate that the prefilled gabions will not vary by more than 75 mm from a 3 metre straight edge laid across the surface after installation.
79eecdaf-1cfb-58c5-8546-b2d0203f1c06 | note | Prefilled gabions shall be installed in the positions shown on the drawings and each prefilled gabion shall be connected to all adjacent prefilled gabions by connecting accessible abutting edges only with fasteners at maximum 150 mm intervals. The exposed sides of the prefilled gabions after installation shall not vary by more than 75 mm from a 3 metre straight edge laid across the surface after installation. Where bulges and depressions greater than 75 mm are present after installation, the prefilled gabions shall be replaced.
a70faaf3-a85e-5e7a-9b31-705fa2df53fe | note | – – – – – – – – – – – – – – – – –
20cd774a-23cb-5623-be5a-9fa1298a4d6f | note | METHOD - Document Review
587a878a-a597-50ab-94ba-a4d17e0aeba9 | note | – – – – – – – – – – – – – – – – –
0ae201ef-6592-563e-943f-dfa10c0ba53b | note | FREQUENCY - Prior commencement of work
8b6c6b57-c8c1-5b4c-aeb8-179d5805834a | note | – – – – – – – – – – – – – – – – –
3c1e22e2-9a0b-570c-b437-f46aa75b1c17 | note | CATEGORY - HP
15652c31-f4a2-5b37-b1ef-c40ea2172e28 | note | – – – – – – – – – – – – – – – – –
53d4e1b7-56e2-52ad-b959-87aeb16f3762 | note | RESPONSIBILITY - Nominated Authority
56ca5e45-989e-5d57-9822-147e01e3c9f8 | note | – – – – – – – – – – – – – – – – –
a32eaf0a-fea7-55fb-95c7-9b52907c23ba | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
c3a9ff46-b92c-5115-8cf1-774d0163b78e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-construction Activities
| checkpoint | 4.1 - Survey Set-out of Precast Elements
473323a3-1eff-5cf0-92ce-fffe2bff192b | note | REFERENCE - IFC Drawings MRP-052-D-SMEC-DRG-71-MPK-AUD-5001
c6caff38-041e-51ed-af41-35852cf175ae | note | – – – – – – – – – – – – – – – – –
8e1d380d-2b6b-5060-ac2e-0cdc0907b93e | note | ACCEPTANCE CRITERIA - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
404e3802-971f-5af6-bae4-2591332ec062 | note | – – – – – – – – – – – – – – – – –
0b14988b-d583-5500-9379-1bf50357a022 | note | METHOD - Measure Visual
103aa95b-b071-56e8-9425-329753a53000 | note | – – – – – – – – – – – – – – – – –
393b1c7c-3a77-562f-89bc-c99a4ac2473e | note | FREQUENCY - When Applicable
a04c692c-adda-5e86-a4be-004c29ee8a64 | note | – – – – – – – – – – – – – – – – –
0f3f085e-67c5-5af9-b534-c718124f6937 | note | CATEGORY - IP
585fd690-40be-5d69-aa47-3823ebe0547a | note | – – – – – – – – – – – – – – – – –
46ae5c05-81a1-5712-8422-103872b28894 | note | RESPONSIBILITY - Surveyor SE/PE/SPE
74fadf98-5e0e-5ac5-a1fc-a5dc1fa4c5c9 | note | – – – – – – – – – – – – – – – – –
3efc1678-1355-53c9-978f-ec3a1bbbb340 | note | VERIFYING DOCUMENTS - This ITP
4011b5a8-fc56-5b75-9daa-6664f0e13930 | date | Date Completed:
| section | Construction Activities
| checkpoint | 5.1 - Geotextile
48e1226b-eb29-5b92-8d28-deef0daa87c4 | note | REFERENCE - IFC Drawings MRP-052-D-SMEC-DRG-71-MPK-AUD-5001
d5a31a34-9421-58e7-8cc9-57039ab7c498 | note | – – – – – – – – – – – – – – – – –
3e43843f-9fd7-5206-8fdf-fb3d41b8a406 | note | ACCEPTANCE CRITERIA - BIDIM A34 or approved equivalent Geotextile to be installed on both side of granular material with minimum 300 lap length
56c60f94-db9f-58d6-8667-576339896883 | note | – – – – – – – – – – – – – – – – –
48fa609c-bdc0-521c-bf42-bf227a68ae71 | note | METHOD - Visual
4811cfff-7a51-5b84-9e69-788cd1d8f59d | note | – – – – – – – – – – – – – – – – –
6c304dc7-e68c-574e-923a-72d191bbef6c | note | FREQUENCY - Prior Granular material installation
cf83f462-fe32-50ab-8b65-abe1b452d882 | note | – – – – – – – – – – – – – – – – –
745f09a2-3f78-5c43-9bd9-7b32ed66cff2 | note | CATEGORY - IP
73bf0a3e-e696-5a4d-8658-28981a2d5040 | note | – – – – – – – – – – – – – – – – –
7e14f22a-caea-5fda-bd19-48fef85e224b | note | RESPONSIBILITY - SE
433c4eed-a087-581c-babe-4c35407fae64 | note | – – – – – – – – – – – – – – – – –
256e2ee1-bd45-5ef4-a38a-298f79b5c480 | note | VERIFYING DOCUMENTS - This ITP
e7e8e689-68f4-5a3e-8ddc-a97df1b39a12 | date | Date Completed:
| checkpoint | 5.2 - Drainage
a843eca0-7991-541d-ae27-03059984496e | note | REFERENCE - VR 715.08 (e )
92d04066-ace3-5919-824f-682566e49600 | note | – – – – – – – – – – – – – – – – –
3fd81bde-ec6f-5e86-a123-697c887cd3f3 | note | ACCEPTANCE CRITERIA - a subsurface drainage pipe shall be placed at the base of the rear of the gabion retaining structure.
0f552095-7a1f-57e7-91fa-8856c0ccb70f | note | – – – – – – – – – – – – – – – – –
755026ab-8623-5d27-9344-475f67617d69 | note | METHOD - Visual
6517d0a4-ebb9-5389-a29c-79267f520b11 | note | – – – – – – – – – – – – – – – – –
a5e7b074-d204-56d5-8fe0-8f303daaf58c | note | FREQUENCY - When Applicable
c3dbb8e3-cccb-5598-8fe9-a8630d50df77 | note | – – – – – – – – – – – – – – – – –
94350136-b226-5a5a-b25b-f7d30a39d169 | note | CATEGORY - IP
5af08818-75c8-5f7b-924c-8dda1d00b26d | note | – – – – – – – – – – – – – – – – –
bcb07cd3-8068-59e8-9470-297c25a308dc | note | RESPONSIBILITY - SE
8ecd38e2-a11a-536a-8017-a4c7556d5862 | note | – – – – – – – – – – – – – – – – –
a006c953-624a-5c74-bd65-4125d60c008a | note | VERIFYING DOCUMENTS - This ITP
e46c565d-f4b8-5e3f-a4b3-58683d62d420 | date | Date Completed:
| checkpoint | 5.3 - Gabion Slope
c9391591-5127-5819-91ce-6565506fba14 | note | REFERENCE - IFC Drawings VR 715.08 (c )
235698da-a2f1-55d4-803b-aeaf7babde45 | note | – – – – – – – – – – – – – – – – –
72b8585d-3faf-5fd3-b964-efaf5cb72eab | note | ACCEPTANCE CRITERIA - the prepared surface for Gabion Installation shall have a slope of 10(H):1(V).
107e34cc-bf95-59de-9d1c-9f5e3d83dca8 | note | – – – – – – – – – – – – – – – – –
9f9bbf39-c56c-519a-8310-a785bec1a01d | note | METHOD - Measure Visual
07d133e1-dce7-5073-8f3a-2653bdccdd89 | note | – – – – – – – – – – – – – – – – –
1b69bbf8-6264-525f-b3b1-7eb75631b26b | note | FREQUENCY - Prior Gabion Installation
89ad19d2-dd96-58f1-a114-b7bfb0e83300 | note | – – – – – – – – – – – – – – – – –
818dbf5b-16a4-5110-acd0-4bc7b019ab76 | note | CATEGORY - IP
2690ab0c-5651-56d0-9c31-2a3be2eb30b5 | note | – – – – – – – – – – – – – – – – –
f1256acc-03df-5d1e-b36f-c118333903b2 | note | RESPONSIBILITY - SE
bd7a91e3-aed9-57d4-80ed-7ce8c0933012 | note | – – – – – – – – – – – – – – – – –
9decc740-4f0e-55a8-a278-136a80768542 | note | VERIFYING DOCUMENTS - This ITP
902a9699-4e0e-5dbf-ba1a-9f63f2859936 | date | Date Completed:
| checkpoint | 5.4 - Geotextile
21236359-b3d0-55d9-bece-86431e6f5958 | note | REFERENCE - IFC Drawings MRP-052-D-SMEC-DRG-71-MPK-AUD-5001
c3b2399c-3df2-5eeb-b52b-065e05192a9a | note | – – – – – – – – – – – – – – – – –
e5231a6e-7535-586d-9430-fe279cf77bf8 | note | ACCEPTANCE CRITERIA - BIDIM A34 or approved equivalent Geotextile to be installed on both side of granular material with minimum 300 lap length
b6f91c62-d65b-5ba6-b255-fb84817262b9 | note | – – – – – – – – – – – – – – – – –
c623aad2-de4c-5b53-9b9b-c977bc90b6c9 | note | METHOD - Visual
3375e852-9678-5d8e-a2e0-fe9371795a3c | note | – – – – – – – – – – – – – – – – –
7f427618-dc4c-5233-853f-583e187079cd | note | FREQUENCY - After Granular Material Installation
e1843df7-2459-5851-9d40-1b50d359462c | note | – – – – – – – – – – – – – – – – –
ab11b3a8-ac98-5aea-a294-78197fa6541a | note | CATEGORY - IP
2ae6dd2c-c08a-5ada-9577-40a3b92f7d69 | note | – – – – – – – – – – – – – – – – –
4d235ccd-06c1-57dc-853a-d56311ec6ac8 | note | RESPONSIBILITY - SE
bb6d6204-7c08-52d7-867a-742b28202660 | note | – – – – – – – – – – – – – – – – –
f4532c54-bbc8-5d78-bcc8-55fbc23b1008 | note | VERIFYING DOCUMENTS - This ITP
edd01852-7b77-53f8-a8ff-9543e78e6f97 | date | Date Completed:
| checkpoint | 5.5 - Gabion Installation
d9d36d42-5c50-5920-988e-5c67e27cd63b | note | REFERENCE - VR 715.06 (c )
1c252a72-e8a2-500e-bb66-b21886b7719e | note | – – – – – – – – – – – – – – – – –
fa118b86-3616-5c4d-8739-e1d02c042ab9 | note | ACCEPTANCE CRITERIA - Gabions shall be installed in the positions shown on the drawings and each gabion shall be connected to all adjacent gabions by connecting all abutting edges with fasteners at maximum 150 mm intervals.
520d592f-b8b5-5c77-951b-2ad5c9b7ef20 | note | ensure the sides of the installed gabions do not vary by more than 50 mm from a 3 metre straight edge laid across the surface prior to, during and after filling with gabion fill material.
f11d243b-d704-5b4e-934e-a9dc6d647d06 | note | – – – – – – – – – – – – – – – – –
7a53ceea-7df8-5874-bd89-d1ac18fdc6a6 | note | METHOD - Visual Measure
60e1ece9-faba-585c-b6cd-048c94a651e6 | note | – – – – – – – – – – – – – – – – –
991b75d9-1815-5d44-837f-36b21f4fb436 | note | FREQUENCY - Prior gabion fill
aaa5cfcf-0456-5b9c-88a3-7832bbb25bf0 | note | – – – – – – – – – – – – – – – – –
4380367d-a6e4-5135-b88c-5382e34d13cc | note | CATEGORY - IP
bcdc3d30-3103-5c6d-92a9-e55237f8f938 | note | – – – – – – – – – – – – – – – – –
0f35e8f6-e500-5be6-b386-10fefc7b43e9 | note | RESPONSIBILITY - SE
f12c795a-82d1-57bc-a052-546df073bb83 | note | – – – – – – – – – – – – – – – – –
fc5a7203-249f-592d-b6cc-797df35b8a4a | note | VERIFYING DOCUMENTS - This ITP
131a1ced-3a1a-533c-be3a-822f6fd80b6b | date | Date Completed:
| checkpoint | 5.6 - Gabion Fill
0f338a56-a415-526d-8539-64dbe9dbe29c | note | REFERENCE - VR 715.06 (d)
7ccdec6f-7ab2-5a9f-a07c-8154215865d0 | note | – – – – – – – – – – – – – – – – –
aa544384-ae66-51b9-9bf4-ef71589fc2da | note | ACCEPTANCE CRITERIA - Gabions shall be one third filled and braces installed at evenly distributed horizontal centres. Gabions shall then be two thirds filled and additional braces installed at evenly distributed horizontal centres. Gabions shall then be fully filled, the selvedge wires on the lids connected to selvedge wires at all abutting edges with fasteners at maximum 150 mm interval.
0dc7d2b3-1ed0-55c2-8442-8d19f6002e6a | note | – – – – – – – – – – – – – – – – –
58ea6881-fb9d-5c7a-9232-d97fd2fa7177 | note | METHOD - Visual
969b4de5-1ba7-52ea-98a8-124dd1ad4edc | note | – – – – – – – – – – – – – – – – –
088e3103-985f-5fa5-a66a-64ff7376c2f2 | note | FREQUENCY - When Applicable
c85ec3e1-c804-5470-8609-abbea3b5659e | note | – – – – – – – – – – – – – – – – –
75b836b2-5ddc-5f74-a007-77017a901dcb | note | CATEGORY - IP
9e673b67-53e7-5768-823b-b6b2366533be | note | – – – – – – – – – – – – – – – – –
04e966f5-3e23-568a-9784-ac8ab6a4fc32 | note | RESPONSIBILITY - SE
7b8ab931-a310-52a7-ad2a-bc0b13f462dc | note | – – – – – – – – – – – – – – – – –
bb450039-a8e3-5ab9-a63f-228ccafed790 | note | VERIFYING DOCUMENTS - This ITP
f79a6ac0-538f-583a-8669-913f8835e70c | date | Date Completed:
| checkpoint | 5.7 - Gabion Fill-Bulges
85728b4c-2430-5224-8331-9a206c4ed9dd | note | REFERENCE - VR 715.06 (d)
cb7a4293-3285-52c2-8d5a-8ba88dcf7181 | note | – – – – – – – – – – – – – – – – –
c0ee6b65-6672-57de-ab5f-646c0daef843 | note | ACCEPTANCE CRITERIA - Where bulges and depressions greater than 50 mm are present after filling, the gabions shall be refilled.
c9544a9a-d716-5f8c-adca-e8db6d16da96 | note | – – – – – – – – – – – – – – – – –
75d6ae74-6559-5a9d-983a-7a7dfe991819 | note | METHOD - Measure Visual
27786386-49a9-5d65-90e3-c2fb845467a0 | note | – – – – – – – – – – – – – – – – –
7723c371-baf6-58fb-9c7d-78bfb3be064b | note | FREQUENCY - After Gabion Fill
061d5c76-861e-5da3-93a5-9d98ada514dd | note | – – – – – – – – – – – – – – – – –
fbdd97a7-497e-527e-b241-e1ec9af5ccad | note | CATEGORY - IP
212f612f-704a-58bf-ba5b-deda1e6568c2 | note | – – – – – – – – – – – – – – – – –
a61b487b-005a-52d9-aac1-df05d9168a0b | note | RESPONSIBILITY - SE/PE
04e6fb6c-bf65-5f7e-903b-8237fbc0bc13 | note | – – – – – – – – – – – – – – – – –
c4c6136c-11a7-5a03-bbfa-0f8f3a46246b | note | VERIFYING DOCUMENTS - This ITP
cc9820fe-6b92-5cbf-bc3e-24db1c84e2ce | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 - As-built Survey
fb7aa274-f0c0-591e-a68a-e45f7cf7ab93 | note | REFERENCE - IFC Drawings MRP-052-D-SMEC-DRG-71-MPK-AUD-5001 VR 670.05
af74a1f5-0362-531e-bce8-d3be4f969e08 | note | – – – – – – – – – – – – – – – – –
00633d25-c6cd-59bf-8a11-ba11e32db93c | note | ACCEPTANCE CRITERIA - Provide record of dimensional measurements face and top of gabions have 1 in 10 slope
e87000d8-23fb-57f4-9844-2796646ee845 | note | sides of the installed gabions do not vary by more than 50 mm from a 3 metre straight edge laid across the surface after filling with gabion fill material. Attach: Survey As-builts / Survey Report
9f5c0252-52a4-5811-9713-94c4b4d8497e | note | – – – – – – – – – – – – – – – – –
e6c8f4c5-6be0-5b99-85cd-fb195a3c8630 | note | METHOD - Document Review
3d4d905f-9a88-582a-b2b4-81554bcbe320 | note | – – – – – – – – – – – – – – – – –
ef392d91-3b4d-5e3d-bc0e-37e51b38b729 | note | FREQUENCY - Each element
adfb2e7c-df2f-599b-93ae-db9add9f87cf | note | – – – – – – – – – – – – – – – – –
3e97f780-ba62-5bf7-8e06-d6e416705fa2 | note | CATEGORY - IP
67380632-8e3d-594d-8ad5-cdb91f27fa34 | note | – – – – – – – – – – – – – – – – –
42bb5961-63f4-558c-9af0-cdcf0be58d5a | note | RESPONSIBILITY - Surveyor SE/PE/SPE
992e304e-74c1-565d-acb5-b663009bf45b | note | – – – – – – – – – – – – – – – – –
b59b1b01-0117-525e-9cff-0b201255a716 | note | VERIFYING DOCUMENTS - This ITP
ff716d70-b4ab-5cd1-8d75-6ff9b73bd23e | date | Date Completed:
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
d2e998fd-c214-55c6-b9b1-7896add91e3f | note | REFERENCE - MRPA Quality Management Plan
9c172bbd-6f59-5ea3-941a-21fc7f20c2b8 | note | – – – – – – – – – – – – – – – – –
ab3b2fc6-0e6c-5848-8ad5-0be4e1975872 | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
7eda5c35-646c-51a2-b1b5-680473c78c35 | note | – – – – – – – – – – – – – – – – –
29224242-ac44-5d29-911a-d0ddc8090041 | note | METHOD - Document Review
03aa3a75-76ce-57f9-a79e-6a15aeb2adcb | note | – – – – – – – – – – – – – – – – –
ffaf3254-48c2-5bf1-a1a1-02c271e761bc | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
d899794d-3942-5e62-b0a2-fb293b017004 | note | – – – – – – – – – – – – – – – – –
f94fec33-f5d4-5000-9267-08617d24c0b2 | note | CATEGORY - HP*
7909221c-a4a5-52a1-a309-33df32b407d2 | note | – – – – – – – – – – – – – – – – –
a4b4843a-3e83-567c-ad6b-e350c1e6d81d | note | RESPONSIBILITY - SE/PE/SPE
2a17fb74-cd29-5f30-8b8e-1522abb7609c | note | – – – – – – – – – – – – – – – – –
45b7db7f-42af-546b-8bf0-847f59d5317f | note | VERIFYING DOCUMENTS - This ITP
24657e7f-071c-5991-a2fd-046923357749 | date | Date Completed:
| checkpoint | Final Inspection
fa63c729-d6d5-5285-9978-e90117550dab | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
aa81e6cc-e842-56c9-8896-976f33fff5c7 | textbox | Name:
7cc29c6e-1bb1-5684-a1b6-79c68527240c | textbox | Position:
caa4ec30-b4d6-535d-b248-b8776dd06099 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-100-CIV-CAMMS-Conduit and Pits-MTM Carpark Lighting Rev 0 | itp | ITP-100-CIV-CAMMS-Conduit and Pits-MTM Carpark Lighting Rev 0 |  | 22315306-c9d3-40c7-8244-b02d4ba8a164
| section | Referenced Documentation
| checkpoint | Referenced Documentation
c8e2573a-f5bb-5533-ada9-262498a56a5c | note | Document Title: ITP-CIV Conduit and Pit (Supply and Install) - MTM Car Park Lighting
c7345d86-4e48-5180-a519-35e968613dfb | note | ITP Description: Conduit and Pits- MTM Car Park Lighting
c819d0ac-c7ea-5b98-bdb6-9f2d0d8ead10 | note | Discipline (e.g. CIV/STR/RAIL): CIV
e8bd6909-564c-5540-b17f-1059a9f6ae74 | note | Revision Number: 0
af16634a-1761-5f8f-be32-594e8aaab8dd | note | Revision Date: 14/11/23
fd1a7f0e-f9e9-5876-8ebf-082ec92547b5 | note | ITP created by: Romualdo Magpantay
8174b1d4-6ed6-5adc-b258-624455261e15 | note | ITP approved for use by: Victor Mira
0d4c80c0-1e23-5bef-9903-29f1c3331c59 | note | 1.1 L1-CHE-STD-035
769a62ae-c2c8-5972-a950-8a36abab8d38 | note | 1.3 AS /NZS 3000
| section | Preliminaries
| checkpoint | 2.1 - Obtain and review manufacturer documentations for the supply of materials: LV + HV Conduits; Communication Conduits; Fixing and Supporting Materials; Pits
1de505fa-fbf1-501b-99ea-44792f01387b | note | REFERENCE - IFC Drawing Supplier Specification AS /NZS 3000
15e5a57f-aa0d-57b7-a823-ecacdec6ae0c | note | – – – – – – – – – – – – – – – – –
5b235efd-9039-5fbc-98b2-7962ca98b491 | note | ACCEPTANCE CRITERIA - Materials comply with relevant specifications.
2d8f1bc2-895b-58b3-9d85-ec42147b5b74 | note | Obtain conformance certificates and submit to the Nominated Authority prior inclusion into the works.
1099f750-658f-5f4d-a399-44309cf655d4 | note | METHOD - Visual
df1b2d48-7d05-5d5d-bb97-3bb240b91a76 | note | – – – – – – – – – – – – – – – – –
b1100ac7-d4fb-5769-946f-5c77fc23d6af | note | FREQUENCY - Once
c99bc3c1-654e-52f0-8d02-2273adec06d1 | note | – – – – – – – – – – – – – – – – –
25d9cd69-89c5-5628-a2f0-23f372fbad9d | note | CATEGORY - HP
1bb64c40-c3ed-5402-8298-1744382f650e | note | – – – – – – – – – – – – – – – – –
42894303-6f14-538f-9746-85e4715ac056 | note | RESPONSIBILITY - Nominated Authority
bf0bd466-3846-5ab2-a411-154b9cb5850b | note | – – – – – – – – – – – – – – – – –
34d0e280-81b7-5961-8824-f1d4eb5521f5 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
9a0c78ef-4715-5f03-b52c-423feebb9f4e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Inspect supplied items upon delivery
e652ba8a-e12a-574d-938e-75042559ae3b | note | REFERENCE - IFC Drawing Supplier Specification AS /NZS 3000
f274297d-d030-5ffb-b382-536cad986eb5 | note | – – – – – – – – – – – – – – – – –
e6b170f9-f8ee-5ef6-8750-8c416e52eaf8 | note | ACCEPTANCE CRITERIA - Supplied items are to correct spec, class, size and undamaged
6e1f385c-dce0-5dd2-b1c4-379dcb730380 | note | METHOD - Testing
e5686f89-6959-5f91-9d8d-48dc9fb3efa5 | note | – – – – – – – – – – – – – – – – –
5765e429-7189-55de-a78d-d5ba8b2314cf | note | FREQUENCY - Once
d8f77548-727a-52f5-b008-a30f27cc5659 | note | – – – – – – – – – – – – – – – – –
0b016d32-0470-5131-9246-18d529c05e0f | note | CATEGORY - IP
f66d76e3-63cd-5c37-8f9e-2a758485942b | note | – – – – – – – – – – – – – – – – –
336de7b3-b32b-51f4-ad6f-614031654240 | note | RESPONSIBILITY - Electricians Site /Project Engineer
6b0e730d-2254-59dc-8eb5-5dca1bb3bae3 | note | – – – – – – – – – – – – – – – – –
7c56bcac-29a2-5234-a6cc-c3bc2f796be5 | note | VERIFYING DOCUMENTS - This ITP
7088d0b4-fad2-5eba-b768-2477864fae09 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 3.1 - Excavation of Conduit Trenches & Pits
6b879a95-965d-5abb-9458-0aeb0ec9ae3e | note | REFERENCE - AS/NZS 3000 clause 3.9 IFC Drawings
c09713ca-8b10-50bb-adea-14bf214642da | note | – – – – – – – – – – – – – – – – –
0a743f2b-a3d9-5827-bc33-88d1083a768e | note | ACCEPTANCE CRITERIA - Install the conduits after earthworks have been completed to subgrade level.
10b34923-1d52-5a55-ab26-28ddb6207a1f | note | Installation of the conduits must be in accordance in the design dwgs.
e7f6267c-e8c6-55c7-800f-7e1ad215bd61 | note | Where the conduits run beneath a road, provide a minimum cover of 500 mm from the top of the conduits to the underside of the pavement; in all other areas, provide a cover of 500 mm to finished surface level.
afff9ad3-b42b-5fb6-a086-adfb9802283c | note | METHOD - Inspection
65af1f46-5b3b-525f-96b2-7aafe923b0d4 | note | – – – – – – – – – – – – – – – – –
6e807a94-dec6-5201-90f7-450ff7150037 | note | FREQUENCY - Once
9a91238d-b936-5d8d-97a2-bc9d37178c37 | note | – – – – – – – – – – – – – – – – –
224b0574-c74d-569a-a76e-d14a4e5b6fea | note | CATEGORY - IP
8c0e961d-0d62-5ae1-9d98-9aca1f188a42 | note | – – – – – – – – – – – – – – – – –
dbfc6af9-4151-5af5-a611-f09508611c27 | note | RESPONSIBILITY - Supervisor /PE/SPE
4b597301-52c3-54f1-b7d6-38db7a58ab7a | note | – – – – – – – – – – – – – – – – –
83f26cb0-dbe8-5d85-a796-bde26eb57623 | note | VERIFYING DOCUMENTS - This ITP
95ce063f-8321-5c66-9cd2-bb101f5e068c | date | Date Completed:
| checkpoint | 3.2 - Sand bedding, laying and backfilling
184a7f5c-9727-5582-8965-bda0a07cc70e | note | REFERENCE - AS/NZS 3000 clause 3.11.4.5 IFC Drawings
3cc1bb38-51ca-5620-836a-85d1e4f67bc8 | note | – – – – – – – – – – – – – – – – –
31d27c48-c18e-5d40-b63a-90aa5a09880a | note | ACCEPTANCE CRITERIA - Use a min. 50mm compacted sand for bedding if not shown on the design drawings.
c3f17516-856f-5c6e-83c3-05be683aefd9 | note | Lay the conduit on a straight grade and line
67127c30-83f3-535f-976c-2f805b7c6abb | note | Compact backfill over the conduits to 100% relative compaction or depend on IFC drawing & pavement design requirements.
8eac3615-e189-5edd-95fa-36e7352463ce | note | METHOD - Inspection
cc5570e1-f085-5130-9e3f-93a0a576b159 | note | – – – – – – – – – – – – – – – – –
0c79e275-50f4-56d4-b8aa-e06ab129faef | note | FREQUENCY - Once
07ceb22e-327d-5ad9-bde8-ae644354517b | note | – – – – – – – – – – – – – – – – –
1bd7b188-4990-5d0e-9a6b-29c21f0e6c55 | note | CATEGORY - IP
5585d1b5-d0f0-5f53-a6e9-83eed53b18bd | note | – – – – – – – – – – – – – – – – –
a94e34e0-cc6e-5de1-bae7-e7e1df76bfdc | note | RESPONSIBILITY - Supervisor /PE/SPE
1056d4d9-b479-5e49-a612-89005795754a | note | – – – – – – – – – – – – – – – – –
afad662c-690d-59bd-a5f9-ff5931fec07d | note | VERIFYING DOCUMENTS - This ITP
6ca79da3-b81f-570f-b4e7-4c1826dc52cb | date | Date Completed:
| checkpoint | 3.3 - Install conduits according to manufacturer’s instructions, relevant drawings and Standards
426941a7-1271-52c7-8728-03abaeed4f99 | note | REFERENCE - AS/NZS 3000 clause 3.9 IFC Drawings
8e4707af-bc9e-5655-9f53-12451238807e | note | – – – – – – – – – – – – – – – – –
03d747c1-797a-55f9-9f71-7596c452ab8e | note | ACCEPTANCE CRITERIA - The works are constructed in accordance with AS/NZS 3000 Wiring Rules and Services and the installation Rules of AS 2067.
0f9b2567-4f58-5d5d-b3c2-7b1ffab369f2 | note | Conduits are joined together with solvent cement, generally in accordance with clause 4.2 of AS/NZS 2032 and all joints are water tight and free of foreign matter
b2d2cd41-dacf-55c9-9ea0-cb789266564d | note | Conduits are inline & positioned evenly
a6a2e318-0ae7-564a-86e5-3e4e8c20c189 | note | Location of each conduit is as per Design Drawings
dce1c70d-da32-5b0d-b44c-86343fd5c364 | note | METHOD - Inspection
fca34d27-ba13-586e-b132-7a6af4e10ebf | note | – – – – – – – – – – – – – – – – –
ed01c251-045b-5807-99dd-32a5c6651415 | note | FREQUENCY - Once
1f4de40d-bf85-54af-94da-a830c3b62f58 | note | – – – – – – – – – – – – – – – – –
8d0902e6-ec28-59cd-b8ea-409779d6660a | note | CATEGORY - IP
7831144d-9abb-5916-8a7a-2a29e59b5aad | note | – – – – – – – – – – – – – – – – –
bcf8dd24-0836-5288-b734-6ef32800560a | note | RESPONSIBILITY - Supervisor /PE/SPE
d3ccadc5-5382-5145-9dc8-5292221da15f | note | – – – – – – – – – – – – – – – – –
99d2a4ce-4bc6-562e-8d37-ad688bef9678 | note | VERIFYING DOCUMENTS - This ITP
fb16c52f-08ca-5017-8345-989a221468d7 | date | Date Completed:
| checkpoint | 3.4 - Installation of Electrical and Communication Pits
01fe9711-59e4-5574-96f3-cf6dc25dd549 | note | REFERENCE - IFC Drawings L1-CHE-STD-035 section 12.6
a4c9f930-fdc6-59e1-b7c9-8870aaa441db | note | – – – – – – – – – – – – – – – – –
fffe7d52-c6f0-5a27-8d01-a079f8983051 | note | ACCEPTANCE CRITERIA - Compliance to IFC Drawings, Schedules & relevant specification:
b319b499-c1c8-5ad7-9274-8df5010ea781 | note | Correct pit as per the IFC drawings
fd3a4bac-d9cd-5ada-899f-1fd44596c8f4 | note | Soil underneath pit bedding is to be firmly packed prior to install
8753bc25-29bd-502c-8908-29fcf77b2495 | note | Bedding according to IFC drawings to be placed
28f5ee6e-a405-58a1-bb20-8dd6720a7b2c | note | Pit orientation is correct
c85f2c37-3919-53fb-ab90-6adec7e6cc5c | note | Lids & covers to comply with technical specification"
acf3135b-bab0-5a1c-8661-b26be3eccb3d | note | METHOD - Inspection
96a1a733-219e-5fcb-8fda-000c750c9bc6 | note | – – – – – – – – – – – – – – – – –
bb208823-a97d-56c1-b52a-ca2a80934c4b | note | FREQUENCY - Once
f541a735-7d1f-5e68-990d-deea652cbf86 | note | – – – – – – – – – – – – – – – – –
6bb916c5-be21-54ac-9902-4d1ad90284f2 | note | CATEGORY - IP
ce71f16e-11ff-554f-96b7-c00be29297fa | note | – – – – – – – – – – – – – – – – –
6460b0c6-7e6c-5a15-9c23-a46b73e5a295 | note | RESPONSIBILITY - Supervisor /PE/SPE
f7d666ab-4c33-5258-a284-d4190f4f28c9 | note | – – – – – – – – – – – – – – – – –
b7f1a222-fc40-5ffc-9615-643897ecc754 | note | VERIFYING DOCUMENTS - This ITP
62e5f6f0-803d-56cf-b4d4-444ed8a8599a | date | Date Completed:
| checkpoint | 3.5 - Marker Tapes
42fb1561-4a38-5256-9d38-3330f47daebf | note | REFERENCE - AS/NZS 3000 clause 3.11.4.5 IFC Drawings
9ed54012-14ab-59d0-93d6-03cc2d1d3925 | note | – – – – – – – – – – – – – – – – –
e27f2ba6-53ba-5792-9503-10649155224c | note | ACCEPTANCE CRITERIA - Wiring systems installed underground shall be identified by an orange marker tape complying AS/NZS 2648.1. Positioned at approximately 50% of depth cover above wiring system or any additional mechanical protection provided that system.
259741ca-6a53-533d-a15f-0db759f446fc | note | METHOD - Inspection
69c677a5-e9a0-5b8a-82be-9f1092d82626 | note | – – – – – – – – – – – – – – – – –
7d1afe7d-eaa7-5dfb-ab6b-f55f360c4eb2 | note | FREQUENCY - Once
c1f60d3e-2744-5c3e-8b60-1ce39f054f2b | note | – – – – – – – – – – – – – – – – –
3b371355-dfb1-5b27-9ccd-ca46fc44ab33 | note | CATEGORY - IP
6e32c0c2-901a-5667-92c8-49f222b3aadc | note | – – – – – – – – – – – – – – – – –
2a8c7e8a-dbca-51ba-abce-13e0aa59db12 | note | RESPONSIBILITY - Supervisor /PE/SPE
53eee367-cd40-5413-b859-ad7c7abf12da | note | – – – – – – – – – – – – – – – – –
6e5ca827-1655-501d-b7c4-5b710f27ff27 | note | VERIFYING DOCUMENTS - This ITP
653e9029-ee51-52a1-b667-79b38a8a0b95 | date | Date Completed:
| checkpoint | 3.6 - Install draw-in rope to all electrical conduits(if applicable)
e095f0e8-6308-5833-88d4-20a3deac4ecf | note | REFERENCE - IFC Drawings QA & Work method of statement
3ddb84cb-91c3-5b2f-8840-5c91bd0ab11e | note | – – – – – – – – – – – – – – – – –
f94c23ea-d530-5737-acf0-c52025244c95 | note | ACCEPTANCE CRITERIA - Polypropylene draw-in rope consisting of one continuous length of not less than 4mm dia. in all electrical conduits or specify in methodology
01230e05-c32c-52b8-9ad9-0cdb79dac638 | note | METHOD - Inspection
7e63ca7c-f9be-5b37-8259-82fbdf63e1f3 | note | – – – – – – – – – – – – – – – – –
d21fa1df-a75b-56c6-904b-0ede6143bc05 | note | FREQUENCY - Once,
a5bfe798-f7af-5d81-85b4-f457b87f4fa5 | note | – – – – – – – – – – – – – – – – –
646f39b8-22ac-50b5-8bdb-e77567baf38a | note | CATEGORY - IP
53aa9af8-bbdf-5004-8746-d78494358479 | note | – – – – – – – – – – – – – – – – –
3d980a71-37cb-5e19-9fc5-e18f5482d4fc | note | RESPONSIBILITY - Supervisor /PE/SPE
a48b6bdd-1cb1-5882-91f6-2c0c2fd9130e | note | – – – – – – – – – – – – – – – – –
a8122057-c507-5ea6-baf9-d79011613927 | note | VERIFYING DOCUMENTS - This ITP
af95bc0c-1ce5-57a8-a6f3-5e733730193a | date | Date Completed:
| section | Post Construction Activities
| checkpoint | 4.1 - As-built Survey (if required)
ab272358-9626-5c42-946d-2da12b764f56 | note | REFERENCE - As Built Drawings Asset Change form
25b94861-1e28-5bce-bcc1-05ac8a5f76a8 | note | – – – – – – – – – – – – – – – – –
57a6b5bb-24f8-59fb-aead-531245bc6a22 | note | ACCEPTANCE CRITERIA - Survey activities undertaken to validate correct construction Attach: Survey Report, Engineering Asset From
312c885d-5c7e-519d-848b-b92c16d66183 | note | METHOD - Survey Document Review
2cf0ccad-a3b5-59bd-8829-9579a25ea1b7 | note | – – – – – – – – – – – – – – – – –
bc4ea126-aed1-5a50-862a-41fc6c7d0c0f | note | FREQUENCY - Per lot
4c5a9646-42db-568b-ba0a-d670913770a3 | note | – – – – – – – – – – – – – – – – –
e3d37258-5882-567b-9279-b8342db1fdcc | note | CATEGORY - IP
f0d1fa1a-b42b-5dea-bc9e-6aa7fa4c9663 | note | – – – – – – – – – – – – – – – – –
4b9c380a-ce6a-5f26-b7ba-70018e9cf44c | note | RESPONSIBILITY - Supervisor /PE/SPE
1ac4158e-7942-5433-ad25-4aa3deb334f6 | note | – – – – – – – – – – – – – – – – –
f7e331ec-76a4-5ca4-ae89-f436805c0879 | note | VERIFYING DOCUMENTS - This ITP
95d99e60-8756-59a7-ba6b-bc462d8f6dd6 | date | Date Completed:
| checkpoint | Final Inspection
fcccf96f-c336-5068-a2d1-b413d0f3fe30 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c075c35a-be26-529f-b116-08839f87947a | textbox | Name:
7b95b945-11fb-5d57-b499-b86af62214f1 | textbox | Position:
5ddacc2b-28e9-51ad-a557-8f5725742be9 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-101-STR-CAMMS-Concrete Coating Rev 0 | itp | ITP-101-STR-CAMMS-Concrete Coating Rev 0 |  | c5b33fb1-59d3-4399-822c-bd36a9a0fb13
| section | Referenced Documentation
| checkpoint | Referenced Documentation
8916acaf-485e-509b-ac5e-fb246aa42d9a | note | Document Title: ITP-101-STR-CAMMS-Concrete Coatings
3d9d2bde-4e2d-5ea9-b80b-5fc82e6d278c | note | ITP Description:CAMMS-Concrete Coatings
b4c0b32b-e4e8-541e-b087-a656c6ca3717 | note | Discipline (e.g. CIV/STR/RAIL): 101-STR
9f2836c8-b616-5e98-a487-e6d006dadf85 | note | Revision Number: 0
d031c039-3c8e-59a0-a53f-d60f8aa4ddb4 | note | Revision Date: 45238
f2e3b3c2-2048-54ac-9667-c9dd1b089f21 | note | ITP created by: Mike Freeman
cfc7899b-0f41-5290-945d-be4540609b36 | note | ITP approved for use by: Victor Mira
d8657910-40b1-5b7a-9dd8-e9af9e331c47 | note | 1.1 VicRoads Section 685 November 2018
d996486f-ce73-52e9-94d9-92126089b7be | note | 1.2 VicRoads Section 686 November 2018
| section | Preliminaries
| checkpoint | 2.1 - Anti-graffiti System Selection
b4ead549-0c26-5a38-ab89-88ad575069f2 | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (e)
fb1930f0-d13f-5141-b516-144b6c6355af | note | – – – – – – – – – – – – – – – – –
608c9251-fa03-5794-9a90-5b0cd85cd0da | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
879cbaee-f077-5004-85fd-5ad4dae88f52 | note | i. be either a film-forming or a penetrant system
3d327b96-ce02-53f0-ab8d-6759ccc687c1 | note | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
22e0f057-ab36-5553-adad-aee5000e94ed | note | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
3b8a6087-ef1f-5662-85d2-228aa8f07980 | note | iv. be non-yellowing, colour-fast and not subject to fading
6d5b8d89-d468-5758-ae3f-4e045bc783b1 | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
f55c158a-a4d4-5ecb-a2f7-1623a66d21f4 | note | vi. application thicknesses (film-forming):
529866ce-408d-5bca-beef-91364b33bd4f | note | WFT total = 175µm min. OR
62ffdbe5-5c25-5bc8-993f-d2f6a49f4718 | note | WTF per coat = 88µm min.
4e12ee63-751f-5ae1-aa0e-8c6996a0d95c | note | DFT total = 100µm min.
fc3c0f60-5942-5820-9357-dfc52bfd0302 | note | vii. adhesion to substrate (film-forming):
0d45d7e1-05ad-5217-9762-e4f4cd1b7808 | note | 0.75MPa min.
01d1ed79-3f9e-50d2-a8a8-a4fe5d963daf | note | viii. application rate (penetrants)
c2bd2c88-ebc6-5bb3-a31d-06f48faba935 | note | as per the minimum thickness on the manufacturer's TDS
e3087bbf-be01-5700-adc1-a2a48f3f2572 | textbox | Enter: Teambinder Material Approval number
c75f5bc9-dc1b-5825-9d7c-fff984960843 | note | METHOD - Document Review
73ca61e3-ee07-54a4-946e-af648f240fe3 | note | – – – – – – – – – – – – – – – – –
ca0cd941-86d0-5596-a3e7-fdad604be1fa | note | FREQUENCY - Once, for each coating system, 14 days prior to application
6bb0d270-b05e-5212-a614-118576b8186a | note | – – – – – – – – – – – – – – – – –
42654b02-1438-5ffe-a7ab-e2805f4fe50b | note | CATEGORY - HP
ee99aec9-b85b-5e28-9dcb-35ddf8bdebb3 | note | – – – – – – – – – – – – – – – – –
b3d0f4c6-043c-5756-984c-df10d75a97c6 | note | RESPONSIBILITY - Nominated Authority
5839d469-6fbd-5eb6-8d1f-b4c778ef420b | note | – – – – – – – – – – – – – – – – –
afe4e622-9a99-535c-836c-5b4295d318b1 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
717b81ea-274f-5fd2-8df5-b85255d77d4d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Decorative & Anti-carbonation System Selection
51f59276-4947-581c-9db6-04de8c2fc854 | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 686.04 686.05 (a) & (b) Table 686.051
9eb820d8-e976-5029-9278-4cb0187d5c86 | note | – – – – – – – – – – – – – – – – –
e8b016d4-a9e0-5b22-b3f8-59398bbffa38 | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
4c715686-50f7-5397-9ff2-7c088573adb3 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
6730c009-55dd-5faa-bc50-63c27300ee9b | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
7b83b536-c62c-5522-af0a-5945840b7cfc | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
f9a6c902-13d8-5862-b81f-ccff87b09531 | note | iv. be non-yellowing, colour-fast and not subject to fading
220b27e0-08b8-50bc-8379-5ba1df6dea66 | note | v. be guaranteed to last for 10 years of outdoor exposure
3d3e7275-30c0-56b3-8da2-66652e10cf68 | note | vi. application thicknesses:
a338418f-fe20-5f44-b341-d178541ca1c5 | note | WFT per coat = enough to achieve the total DFT
c46e2aea-fa86-5b8b-b8a9-ab9dc7c51ef7 | note | DFT total = 150µm min.
f73917d6-b9af-5a98-b83a-20d014f48cdd | note | vii. adhesion to substrate:
9df4889e-83b9-50d1-979f-00eb4f629022 | note | 0.75MPa min.
85102f78-dc10-5d26-9797-09763aa5e7a9 | note | viii. able to bridge cracks up to 0.3mm wide
6d9f4a3e-df9f-5fc9-a899-3f83bdcdb83d | note | ix. able to be re-coated within 24 hours
8e199736-cdd4-548a-a9d0-5ea18d4927d8 | note | x. have a minimum pot life of 1 hour
440343e2-72b7-525d-92b4-cbb4ca77bc59 | note | xi. compatibility to an alkaline surface
74cbdc47-ced0-5d40-96ff-78ea421c4824 | note | xii. equivalent air thickness >150m
4bfd1985-9564-559a-820a-f045d86e7187 | note | xiii. equivalent concrete thickness >450mm
7fd8ae5c-99c5-5dfe-89f4-0b8b6ee01218 | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
44720dc7-33a2-5c60-9890-6109643e90f2 | note | xv. Water vapour equivalent air layer <4m
665e2310-1e49-51a9-b81a-f46770bf3053 | textbox | Enter: Teambinder Material Approval number
cd25079c-37b5-597d-b685-f757501cd413 | note | METHOD - Document Review
1b79a6af-e2c6-59bf-a630-72b1de7cc70e | note | – – – – – – – – – – – – – – – – –
aca5bc10-4766-5f53-ac29-8af39d626aa3 | note | FREQUENCY - Once, for each coating system, 21 days prior to application
bbe8eda8-9cf3-5e09-a195-5f7af1c684d4 | note | – – – – – – – – – – – – – – – – –
e84cda6e-2e8a-5427-aa74-6ecafba5d099 | note | CATEGORY - HP
0b25ef89-7351-5263-868f-72283290ea5e | note | – – – – – – – – – – – – – – – – –
cf3809c5-5ed8-52cd-966a-b57db0f30d59 | note | RESPONSIBILITY - Nominated Authority
e2cd0db7-9731-5297-bca5-820483e50693 | note | – – – – – – – – – – – – – – – – –
757afefd-2767-5c6f-b4af-cdd5f4b68dff | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
f33d5315-b81f-57c7-a98c-620e6484f757 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
fd5c6150-c569-51be-809c-f8352f6cbc08 | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051
cd064036-d5a7-5a2e-bcfe-710c6ce89194 | note | – – – – – – – – – – – – – – – – –
37413969-09da-56e9-b49f-0d37df6f0edc | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
6bbb44e7-8c05-5914-b142-2320eef1dfc8 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
16c8347a-40e1-5601-9a41-9dd1f9288748 | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
9177cae6-dcb9-5d01-8ad9-9b2714b8cb48 | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
4f05bff2-f06b-5e60-99cc-23dfb5bc295a | note | iv. be non-yellowing, colour-fast and not subject to fading
06762084-4878-59c2-a8eb-c2d9ce45756c | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
a82acbee-81bc-5832-8d66-f68e19229f83 | note | vi. application thicknesses:
4f063c50-dda0-54a7-bc0f-f8699bc1beec | note | WFT per coat = enough to achieve the total DFT
604dc424-7488-5740-9eeb-e08c9a39c39b | note | DFT total = 150µm min.
25ee83cb-32b8-5a45-b8de-83609d4d7c94 | note | vii. adhesion to substrate:
76c4a09a-8d2d-5eca-95eb-3823e4877589 | note | 0.75MPa min.
20ab8b28-f717-5fe6-9eeb-4d393bac4a56 | note | viii. able to bridge cracks up to 0.3mm wide
5d454a19-bc0b-580a-82ff-7bfa4dc4a664 | note | ix. able to be re-coated within 24 hours
29c9f71d-439d-5c03-9e75-9fe3dcd93f1b | note | x. have a minimum pot life of 1 hour
d9f9e549-b551-5c85-bb81-bb4039c3b063 | note | xi. compatibility to an alkaline surface
6dff8198-77fa-52c5-a17d-fbee7d9bbeef | note | xii. equivalent air thickness >150m
3750bcf5-04e8-5053-ac00-9a0e76c395a7 | note | xiii. equivalent concrete thickness >450mm
a2788d37-40f2-5da6-be62-1451abbd3830 | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
48459e82-06ab-5eb7-a57b-51bd0edc5711 | note | xv. Water vapour equivalent air layer <4m
c71babab-119b-5127-9aa3-905e672ab88d | textbox | Enter: Teambinder Material Approval number
a45682ea-dea4-56e4-bc35-7d49df49ec2f | note | METHOD - Document Review
f6fd6967-a5f0-5c98-877e-bf535c9f912c | note | – – – – – – – – – – – – – – – – –
fbcd7513-4f63-5d44-b35b-7cbc1f3a3b6a | note | FREQUENCY - Once, for each coating system, 21 days prior to application
51c8ac38-7ebf-5cd2-a2ba-2b61c1bfe2ad | note | – – – – – – – – – – – – – – – – –
6af6da10-27b8-5f2f-96aa-082de4fa4115 | note | CATEGORY - HP
d3ee3bd2-54bc-5f3e-95c9-d3710a36d42f | note | – – – – – – – – – – – – – – – – –
7b9ecb26-eac4-5592-b2eb-d2c8ebe4f931 | note | RESPONSIBILITY - Nominated Authority
ccb0dc19-2c1f-5231-8a69-84d9b581a9cd | note | – – – – – – – – – – – – – – – – –
1df5e442-6516-5282-b785-1c7236977e60 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
9b98baa3-0cae-514d-8c3b-b85f2e07ac61 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
8a0c4451-9837-5099-9d6f-0349de68c952 | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051 686.05 (c) (i) & (iii)
fef91574-9953-515a-ad12-dd910ef0f3fe | note | – – – – – – – – – – – – – – – – –
96634cc9-65c5-5610-884e-de0cf44c017a | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
d9438ece-5611-5bc8-9990-e673353cf205 | note | METHOD - Document Review
e47ca166-2280-5d09-8f42-d7e06f6f2ead | note | – – – – – – – – – – – – – – – – –
c3065801-9190-566d-8d9f-ed317fec9c5a | note | FREQUENCY - Once, for each coating system, 21 days prior to application
fe183c38-13fa-5f19-84cc-97cb855bdc0c | note | – – – – – – – – – – – – – – – – –
9dd6a60f-7baa-5b4e-a5b7-38d197a44428 | note | CATEGORY - HP
0891b304-35e2-5eb4-af94-e7c851e668fb | note | – – – – – – – – – – – – – – – – –
3e9188ea-75c7-592c-9a91-43ec8a535fa1 | note | RESPONSIBILITY - Nominated Authority
b1122cc7-8cd3-5e06-bb95-1a9c62683233 | note | – – – – – – – – – – – – – – – – –
a7e96e17-7b9e-5a4d-9e3d-d91d76f1d431 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
6d87ca6e-6956-5b20-95de-8cec4c17f45e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Work Procedures
16d65438-f75d-5e45-8c16-dea4a1350d86 | note | REFERENCE - 685.05 686.04
2828785c-b435-538a-a5b8-37f6a6e6a6f0 | note | – – – – – – – – – – – – – – – – –
90f7083e-e229-5cf7-852b-b11cc7ba0fa3 | note | ACCEPTANCE CRITERIA - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
46713e36-2f5f-5e1b-b86f-a284cb737ed8 | textbox | Enter: Enter: Teambinder Hold Point number
e101a4f7-c842-5b19-ab42-1313a3017de7 | note | METHOD - Document Review
eccf481c-fc21-5b71-af5a-bd05310d5a0a | note | – – – – – – – – – – – – – – – – –
38eee1a5-f3d2-5b36-baae-72841e153e41 | note | FREQUENCY - Once, for each coating system, 21 days prior to application
ed94faf6-76e0-50cd-8eab-ba4120f463ce | note | – – – – – – – – – – – – – – – – –
d19ece13-3d27-5d9f-99ae-f2aafcb96e43 | note | CATEGORY - HP
58015e80-9610-520a-89ca-19e4edd397f9 | note | – – – – – – – – – – – – – – – – –
227ef28e-d6d4-53a5-9483-7cb836cf8ea5 | note | RESPONSIBILITY - Nominated Authority
a3f74d71-3711-5b77-b1a5-c4f08eec6348 | note | – – – – – – – – – – – – – – – – –
7f244d21-1e96-57d5-825a-cbb2f77fc82b | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
9338dee2-72f7-58e2-b204-b52c4ce8ceaf | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Coating Personnel & Equipment
4ebb8834-c8af-5f93-a898-7861c71dc419 | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.16 686.18
57ffe212-802b-5396-9d2e-2c2add93d79b | note | – – – – – – – – – – – – – – – – –
0f049848-72a6-5f46-a50c-74595bfd5e34 | note | ACCEPTANCE CRITERIA - The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques.
21ae3a89-98b6-5ae6-a61f-43a031fe20a9 | note | Application personnel require 2 years minimum experience.
cdae4b8f-6eb6-522d-9eb9-2e81ce466232 | note | The supervisor shall remain present at all times.
695bf44a-dcd6-5696-9544-d9a0549d14c4 | note | Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
19485621-4487-5568-9393-a86a50078c83 | note | METHOD - Document Review
43730dac-d145-55c1-bcb6-48999c72633f | note | – – – – – – – – – – – – – – – – –
1d347752-d9be-555c-91fa-3ee4c0cb0406 | note | FREQUENCY - Once, prior to application.
6eea68b2-30ab-54bb-ad1a-8eba9cab95ae | note | – – – – – – – – – – – – – – – – –
6392c2bd-6fdb-5df9-b13a-069817dc6c82 | note | CATEGORY - IP
f0b07153-2c7e-5612-a69c-7ba9a10f2395 | note | – – – – – – – – – – – – – – – – –
162410ae-75fe-5c0b-9a38-c82cdc386092 | note | RESPONSIBILITY - SE/PE/SPE
23fabf97-dc7e-5532-897e-24833c8bd887 | note | – – – – – – – – – – – – – – – – –
fd7e27b3-0ac8-5d5d-9b47-a6f13c3c30f7 | note | VERIFYING DOCUMENTS - This ITP
c983613b-215b-596d-8bb2-2337820f6f6e | date | Date Completed:
| checkpoint | 2.7 - Protection of Adjacent Works & Property
1cb29f2f-21ea-5d96-849b-ed3629faad4f | note | REFERENCE - 685.17 686.10
d6db4952-6ca1-5890-b89a-581097142dda | note | – – – – – – – – – – – – – – – – –
018f8158-4727-51a5-9856-d66d27664df8 | note | ACCEPTANCE CRITERIA - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes.
8b36626a-4544-569d-9418-af244f245bfd | note | No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place.
e2686a16-dcb1-5b12-b26a-90a0fbb0f921 | note | Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
a0f63288-f033-5b9b-afdd-abdc2c4fe292 | note | METHOD - Visual Document Review
6de821dd-19d5-5136-93c1-5213c30e485a | note | – – – – – – – – – – – – – – – – –
1cc5227c-0055-5e73-bd51-85195f7130be | note | FREQUENCY - Where applicable, 2 days prior to application.
39e48054-5b7e-5fd0-ac3a-212440693d23 | note | – – – – – – – – – – – – – – – – –
e1b86a0f-341b-50cb-a1b3-92b5632c2452 | note | CATEGORY - HP
a68abdbb-dca6-5026-ae7f-6e258b60e929 | note | – – – – – – – – – – – – – – – – –
4f4f7d97-fde7-5842-9f90-49952c376f33 | note | RESPONSIBILITY - Nominated Authority
2a72bca7-84e1-5566-8fb8-bb1bdc97c16f | note | – – – – – – – – – – – – – – – – –
ce507fc6-ffff-5a8b-9d63-519c3a0be2f7 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
29cc1bb4-63dc-58e2-8963-ad2bd68794b3 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Minimum Concrete Curing Period
56f4afe2-8973-500a-8b12-77fe84194ec0 | note | REFERENCE - 685.08 686.16
164bc062-c4e1-5829-aea5-6c73fdbc5e93 | note | – – – – – – – – – – – – – – – – –
072dc550-36da-576a-b3c7-616d309dea60 | note | ACCEPTANCE CRITERIA - Concrete shall not be coated until the minimum concrete curing times have elapsed:
a122bf96-730e-56ae-adfc-734af0530c47 | note | Standard cured concrete = 14 days & moisture content less than 10%, or 28 days
3a42ad69-72c9-5c22-848e-7e3fa9bc4800 | note | Accelerated cured concrete = 14 days
397c0b50-6149-5b4a-83b6-95accf0dbb0e | note | Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
1ed6c277-0309-5271-ab39-7539a1441bc8 | note | METHOD - Visual Document Review
bd37459f-08fd-524b-9a65-de7675f96c74 | note | – – – – – – – – – – – – – – – – –
b900dc2f-a486-5b32-989f-0b3f87711142 | note | FREQUENCY - Once, prior to application.
6604ef06-498f-5878-aa20-43d54fa7e4a4 | note | – – – – – – – – – – – – – – – – –
b2239c03-843d-5544-9924-71ae4fad87e5 | note | CATEGORY - IP
acf5e8f9-65ca-5501-86de-70dffa58143d | note | – – – – – – – – – – – – – – – – –
27e87c1c-bfa4-5825-ab34-41a57c05f909 | note | RESPONSIBILITY - SE/PE/SPE
3298cf6d-ea14-55ae-b42e-d317ff3b7aaf | note | – – – – – – – – – – – – – – – – –
dba4c6e2-8acf-5c6b-8e13-1625c77c280e | note | VERIFYING DOCUMENTS - This ITP
ae8b927f-8ac9-537c-9914-3fc537eccf95 | date | Date Completed:
| checkpoint | 2.9 - Trial Application (or Past Performance) Inspection
b9f44233-254b-5296-a469-606ee668cc20 | note | REFERENCE - 685.11 686.13
b348a5f9-a974-54cd-b343-b7989d484199 | note | – – – – – – – – – – – – – – – – –
635c7055-0a4e-5e98-84bd-657fb415483d | note | ACCEPTANCE CRITERIA - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate.
1ff071a2-819e-53e5-9b2d-c24c1c9721a2 | note | Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
1cb683ec-8597-5fae-bcff-85708e647d76 | note | Attach: Inspection Photographs OR
692c9471-ce06-5d86-8d49-1c1e845f37e3 | textbox | Enter: Teambinder Hold Point number
a05f8e3d-a191-53d4-b995-bc51d7b0bd7b | note | METHOD - Document Review
2e73ece9-0a2a-5b77-a9ec-347bf32772af | note | – – – – – – – – – – – – – – – – –
abc3704b-e7a5-5b24-a7a7-30c29df2bb67 | note | FREQUENCY - Once, for each coating system, 7 days prior to full coating application
e1ab11ee-08e6-581d-9904-01ab380f2bb1 | note | – – – – – – – – – – – – – – – – –
4606d8cc-d3ce-52da-b985-1fc545752402 | note | CATEGORY - HP
bd37af7e-5ae2-50cc-9da8-51eded9e1068 | note | – – – – – – – – – – – – – – – – –
7ac74573-2e31-5e86-9ce0-a33d2682d610 | note | RESPONSIBILITY - Nominated Authority
19f3ddb3-9994-58d0-9ed9-eb9e2be85070 | note | – – – – – – – – – – – – – – – – –
de8e292e-fa43-5f70-86cb-11d33da43673 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
e6f23566-58ef-520c-8d27-f5dce96921eb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | Pre-application Activities
| checkpoint | 3.1 - Material Records
6b098a2d-5d63-5513-a1b2-738fa5b3980a | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.10 685.12
7109fbf7-891d-5a59-9edf-65c7ac34315c | note | – – – – – – – – – – – – – – – – –
29f354aa-af39-564d-a95d-1ce4b7940a0b | note | ACCEPTANCE CRITERIA - Materials shall be brought to site in unopened, sealed containers, clearly marked with:
139c1af0-4c12-54dc-88d3-db72a6bc4f32 | note | the manufacturer's name & address
13ced07f-8066-52ed-9924-cd6608337f1c | note | product reference
e1ad6875-b013-55af-977a-1913208ccdcf | note | batch number
94a08809-ad89-5171-82d7-8e48f64ef200 | note | quantity manufactured in the batch
801679d8-a9de-5c36-998b-a23b90e3faba | note | date of manufacture
4bfb1057-9079-59a4-a9b0-c34161826581 | note | Product beyond the manufacturer's shelf life shall not be used.
31531eda-cb9d-5eef-bd63-8a2e5ea1144b | note | Each product shall be traced to final location.
c5b15c8a-0f17-5116-9b3c-72f08cea947b | note | METHOD - Visual
14bdd21d-025d-57e2-b00b-13f5ec4a5ea5 | note | – – – – – – – – – – – – – – – – –
768821db-5ca0-589d-82f5-7d59ddfd6c64 | note | FREQUENCY - Prior to application
8e44d889-b159-5791-b98a-a2d1568c511b | note | – – – – – – – – – – – – – – – – –
08a36fd7-43d3-5a88-ac8d-5e4ad1e31f52 | note | CATEGORY - IP
f6cee039-074a-5d7d-90eb-5277c0558234 | note | – – – – – – – – – – – – – – – – –
6d5149a9-f830-5fe6-8092-0deb6c5e0297 | note | RESPONSIBILITY - SE/PE/SPE
d053cd0a-0c77-534d-8c2c-c612cef6b230 | note | – – – – – – – – – – – – – – – – –
edec7399-6c6b-52fe-a0ba-483e8fdbe73c | note | VERIFYING DOCUMENTS - This ITP
2b5deec9-b5b0-5ea8-ad32-c361084a090d | date | Date Completed:
| checkpoint | 3.2 - Weather Conditions
ed219a1a-a555-5847-90e7-0daec43f4de2 | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.09 685.12 (a) 686.11 686.14 (a) (iii)
7f785d0d-b758-51e8-ba41-7e05be1896d9 | note | – – – – – – – – – – – – – – – – –
3156beeb-b749-51be-8ddb-dd7bf3fa397d | note | ACCEPTANCE CRITERIA - Coating systems shall not be applied under any of the following conditions:
225dc430-ce05-5e28-a578-f6eaec46aa6b | note | i. windy conditions where spray/splatter may be generated
5895360a-5b3a-5921-b2f0-79767aae1036 | note | ii. when wind-borne debris is likely to contaminate the uncured surface
c1e37edc-7381-5573-91bb-efb456d77628 | note | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
15f31b15-5da1-5e12-9f57-f52bfae9f3bc | note | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
3ef83ccc-7374-5bc6-9a4e-2b5ee6d2d360 | note | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
2336aeb2-d1a1-5275-ae2a-0eb7c61ddfbd | note | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
e4f14428-d735-5c0c-a73a-8733f158244f | note | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
646d5423-927b-559a-a80d-a2b6ecf24481 | note | Weather conditions are to be recorded.
ee097803-bba3-5c5a-83e8-f13ce2295cd3 | note | METHOD - Visual Measure
2d64f54d-9ed5-5d93-9939-dcbc79b8951d | note | – – – – – – – – – – – – – – – – –
ee6fddcb-3657-5246-951c-e189ab006730 | note | FREQUENCY - Prior to application and every 4 hours per shift
d2deb1e2-2588-5946-a6cd-2a04c835406f | note | – – – – – – – – – – – – – – – – –
7a2eca93-4935-5170-bf83-b0c5811be53f | note | CATEGORY - IP
7ca5d210-3ad0-5e06-ab9e-6647f822f102 | note | – – – – – – – – – – – – – – – – –
635742d3-c2fa-5b25-ac39-0c56785214a6 | note | RESPONSIBILITY - SE/PE/SPE
db032e4a-1d09-5a9f-ae0b-a6ab19a9b4b6 | note | – – – – – – – – – – – – – – – – –
d90e02f2-d45d-56bd-8786-9d96fb44f9da | note | VERIFYING DOCUMENTS - This ITP
698aa470-15be-5b4b-a811-4395adc511c7 | date | Date Completed:
| checkpoint | 3.3 - Surface Preparation
312430ab-4b1b-5f60-8386-c963112e83b9 | note | REFERENCE - Surface Cleaner TDS Coating System TDS 685.05 686.06
fccbe39e-b029-5fa1-ab6b-97e79cac8602 | note | – – – – – – – – – – – – – – – – –
fc1951b5-ac0a-55eb-82fe-b5c0b9f15af6 | note | ACCEPTANCE CRITERIA - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means.
0b792b5c-b716-57a3-b157-3a021f6e376d | note | The surface shall then be flushed with water.
304bef1c-7230-5887-9486-95f99038800d | note | Any concrete defects exposed during the surface preparation shall be repaired accordingly.
484156a1-f6bc-52d6-b875-89369717db62 | note | METHOD - Visual
9ceef4ed-d88a-542f-987e-8b5a3e97ac63 | note | – – – – – – – – – – – – – – – – –
b5fccb9f-07b5-5f2f-a104-1c8f4e1fa0bf | note | FREQUENCY - Once, prior to application.
1b21da9f-3e46-5821-bcc3-a836f1bbacee | note | – – – – – – – – – – – – – – – – –
1ed41a6c-a9ac-5200-b620-bb84b035fcb5 | note | CATEGORY - IP
2979c127-0cd6-5f3a-b36b-5490e6f37146 | note | – – – – – – – – – – – – – – – – –
053d4ba6-dcf2-53a3-b63d-86dc61eec93b | note | RESPONSIBILITY - SE/PE/SPE
6c9cd3a7-bdcc-5355-a0de-f5ea3762905a | note | – – – – – – – – – – – – – – – – –
ddebdbd9-9721-51b6-8308-9920ab53699a | note | VERIFYING DOCUMENTS - This ITP
9ad137ed-3a19-5c9b-a75f-38c42576367d | date | Date Completed:
| checkpoint | 3.4 - Surface Moisture Testing
acf5e39c-4bbd-58dc-917d-60c4e395cbae | note | REFERENCE - 685.12 (a) 686.14 (a) (iii)
f939d28f-b90e-5bb8-8ecc-f135ad8ecb12 | note | – – – – – – – – – – – – – – – – –
ceaa3c80-589e-5e1e-9910-7ee8c9ed7904 | note | ACCEPTANCE CRITERIA - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS.
e727f87a-096c-53c6-94bc-27d7859ff314 | note | Surface moisture conditions are to be recorded.
6343c793-782a-5767-b7f4-971662f302fe | note | METHOD - Test
458f2fe7-8c0e-5be1-82ac-0e5817d3568d | note | – – – – – – – – – – – – – – – – –
4f584bd1-e5cf-53db-b730-df514c35c395 | note | FREQUENCY - Immediately prior to application, 1 no. test every 50m²
6b32fd79-481d-542c-a54a-a91326af2d94 | note | – – – – – – – – – – – – – – – – –
51bcb0ec-57d1-511b-81d9-c880ca3707c5 | note | CATEGORY - IP
06ffc42c-b6c3-5473-87f0-f51af857df54 | note | – – – – – – – – – – – – – – – – –
baf21de4-e6b1-536f-ae7d-3c9d28fbd73e | note | RESPONSIBILITY - SE/PE/SPE
bb53599f-75b1-557a-935c-7aa391c1518e | note | – – – – – – – – – – – – – – – – –
3b89f386-09db-5f98-8ce5-4725c788710d | note | VERIFYING DOCUMENTS - This ITP
b4fdf5ed-0bf4-54f3-a0e7-70341304833a | date | Date Completed:
| section | Application Activities
| checkpoint | 4.1 - Method of Application
fe0fd949-e71a-5b2c-9fa6-6c1b3bec1e51 | note | REFERENCE - Coating System TDS 685.07 686.07 686.09
b7d31f54-898e-50fc-8e61-b9a700538a82 | note | – – – – – – – – – – – – – – – – –
3f4dcdd6-3b3f-5c37-9185-9917df1fcb37 | note | ACCEPTANCE CRITERIA - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved.
13b22c91-a245-53c1-b8bd-d1cbc5c45fc5 | note | Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified.
78309429-c4ae-5797-b9f0-ebb707229c48 | note | For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application.
d5600b94-56f8-5b8f-aadf-02e8a02e50ab | note | Times of coating(s), material names, locations coated and volumes used shall be recorded.
770870ed-78c5-52d7-8978-91d158f3f0bb | note | Attach: Coating Application Record
1e6cf814-416b-5cf2-8e2a-5558fefb2094 | note | METHOD - Visual Measure
fed1d79e-dec5-5fbf-a325-4a99a38562d4 | note | – – – – – – – – – – – – – – – – –
94a2d588-7053-5f1b-be6a-56deb39b7c1e | note | FREQUENCY - Each coat
d1b97df6-9af7-526f-b38e-51e57eca70a9 | note | – – – – – – – – – – – – – – – – –
1ffe2354-fb4f-5495-89ec-5ce8c533e87f | note | CATEGORY - IP
9e24d606-1484-5859-bb02-ae3f46e6b634 | note | – – – – – – – – – – – – – – – – –
02ed7ab2-a091-5287-87a8-75246ab29f58 | note | RESPONSIBILITY - SE/PE/SPE
8f6bd13e-693f-5631-aa07-8c67c01d7731 | note | – – – – – – – – – – – – – – – – –
e8df90df-e454-5284-92f9-f0498a3fb825 | note | VERIFYING DOCUMENTS - This ITP
065a8c5b-4fe6-5e11-8cd0-7c60922cedcb | date | Date Completed:
| checkpoint | 4.2 - Wet Film Thickness (WFT) Testing
5e22c590-f9e3-5a0f-b073-ad7bf02e7d83 | note | REFERENCE - Coating System TDS 685.12 (b) (ii) 686.14 (b) (ii)
97b18963-0144-5efc-b931-6c5459bebfb1 | note | – – – – – – – – – – – – – – – – –
ae30ef65-0255-5d57-a508-2da202e876b5 | note | ACCEPTANCE CRITERIA - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
c2cc001b-bfce-581a-94cb-dc9d527f7a0a | note | Attach: WFT Test Results
ceafa2e9-023c-5675-8428-337674655aeb | note | METHOD - Test
1c3fd5e1-b37c-54b5-a4c0-1df94ce6c7d3 | note | – – – – – – – – – – – – – – – – –
20c08b37-adf5-593b-aa08-1c4bc1e3973d | note | FREQUENCY - Where required, 1 no. test every 50m², 3 tests minimum
0a6683e8-c8ea-58be-8bce-455dde368976 | note | – – – – – – – – – – – – – – – – –
1bbc3605-ebe2-52d1-a1ce-6c182c338f66 | note | CATEGORY - IP
31b6dfd2-4168-5899-b265-595fdfe99ce7 | note | – – – – – – – – – – – – – – – – –
ef59f538-2f8a-5a28-a3d3-cef637710a9a | note | RESPONSIBILITY - SE/PE/SPE
e99b67a5-9f99-5808-9f20-fd32e5dd556e | note | – – – – – – – – – – – – – – – – –
4ad05700-3932-5e29-ba54-48e8550cbe1c | note | VERIFYING DOCUMENTS - This ITP
61c64df9-825f-56d5-9e15-b34ddef95c76 | date | Date Completed:
| checkpoint | 4.3 - Inspection & Defect Identification
9b09bc43-fafc-5591-8c4d-3928732c8283 | note | REFERENCE - 685.07 685.13 (d) 686.07 686.15
c05c15b0-555b-524b-bbe9-6f79fbfd7da4 | note | – – – – – – – – – – – – – – – – –
286bd12e-bb08-571e-8d2f-50e551a82f6e | note | ACCEPTANCE CRITERIA - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats.
e8865e4f-483f-5a23-a44a-0feab06235a6 | note | Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
2ae01cb1-3f56-505a-8cab-ad6a29b78d53 | note | METHOD - Visual
4371bcfa-f0e0-5f80-acd3-13bf8578cc49 | note | – – – – – – – – – – – – – – – – –
e216cf8f-b3d4-535b-98ca-388e4bd73716 | note | FREQUENCY - After each coat
49ffa3d1-e82d-5178-b878-67e41eae7f10 | note | – – – – – – – – – – – – – – – – –
429223fd-5c46-5d3e-94ff-bec2ff53a390 | note | CATEGORY - IP
37b4ebae-f3a2-5b0d-a17f-6b5f3525951a | note | – – – – – – – – – – – – – – – – –
53ebe7cb-f73d-59e7-808a-58332022f141 | note | RESPONSIBILITY - SE/PE/SPE
dd77daa0-5919-5002-b051-1c6eb5061a8e | note | – – – – – – – – – – – – – – – – –
b2875f66-e503-52d9-b82e-28f8f5b64255 | note | VERIFYING DOCUMENTS - This ITP
c5cc7544-90f5-5b9f-9aa0-6e97f5e17aed | date | Date Completed:
| checkpoint | 4.4 - Drying and Curing
0fc4b746-5dd1-584b-acc5-8491e1515c7d | note | REFERENCE - Coating System TDS 685.17 686.10
6582ef00-4ea1-5b44-8f13-49d707b8ce9f | note | – – – – – – – – – – – – – – – – –
0f733304-47fd-572b-ae84-bc3e76004ec7 | note | ACCEPTANCE CRITERIA - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
de888d0a-9293-5238-9e35-049c6466b36d | note | METHOD - Visual
7ff590a2-a686-526e-9d67-a051362b41e7 | note | – – – – – – – – – – – – – – – – –
4d605e34-736d-5b06-bc83-870ea06eeaa5 | note | FREQUENCY - After each coat
ed6106b4-1b23-5c6b-a378-0f45cb5ea5b4 | note | – – – – – – – – – – – – – – – – –
efd0c9cc-b98d-5a8a-86b1-9c03ca060ae4 | note | CATEGORY - IP
ebcd18f1-04ba-5a42-90fb-f32654a0f634 | note | – – – – – – – – – – – – – – – – –
626e979d-50e1-5ecb-8a26-7f392e5f09bc | note | RESPONSIBILITY - SE/PE/SPE
b956ad82-b174-51c8-bdc9-5432e7035fac | note | – – – – – – – – – – – – – – – – –
41d52740-e3e2-5588-84bc-63dde18ce951 | note | VERIFYING DOCUMENTS - This ITP
c00c38e7-ffa2-55a5-9a91-8424314c4779 | date | Date Completed:
| section | Post-application Activities
| checkpoint | 5.1 - Clean-up & Waste Disposal
3bc63e85-9d86-52ac-8fbe-feb9d2243408 | note | REFERENCE - 685.09 (c) 686.10
6a4471aa-1bd4-597f-a46b-9c69bc127e50 | note | – – – – – – – – – – – – – – – – –
491c234c-1a05-5eef-9e72-e55311093d3f | note | ACCEPTANCE CRITERIA - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
51502a97-9ccc-5829-b415-15dcdb4cc54b | note | METHOD - Visual
045b317e-db67-55e9-9578-b3eb41caed1f | note | – – – – – – – – – – – – – – – – –
f8e46d7b-c88f-52dc-8b06-59fde0d8919a | note | FREQUENCY - At completion of Works
4285900d-3395-56e7-ae03-ae7d71e5bfe0 | note | – – – – – – – – – – – – – – – – –
84549586-24e6-5a09-9ae9-d7c3096f84fa | note | CATEGORY - IP
36393cb2-acc4-540f-900c-8d5d593b545d | note | – – – – – – – – – – – – – – – – –
2acb000e-3a91-545b-b73b-4e5caaef2410 | note | RESPONSIBILITY - SE/PE/SPE
53bd4c4e-80b0-513a-b131-1bdff214ba68 | note | – – – – – – – – – – – – – – – – –
4ab433f4-1a59-573d-be8f-36c70170ddf8 | note | VERIFYING DOCUMENTS - This ITP
3d636e15-136a-589d-8c01-40188eabb98a | date | Date Completed:
| checkpoint | 5.2 - Dry Film Thickness (DFT) Testing
fe03938b-24c9-56e7-b8bf-6af5b7b453aa | note | REFERENCE - 685.12 (b) (iii) 686.14 (b) (iii)
47fe56df-9153-5200-b384-6de422213c70 | note | – – – – – – – – – – – – – – – – –
e1298cb1-7eb5-5914-a9c8-8896d84b80c7 | note | ACCEPTANCE CRITERIA - The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
e4062379-7368-5f3e-a17f-0785111591bc | note | i. Anti-graffiti system = 100µm
5f005a3d-1206-5886-bf5c-ec7aa867eb63 | note | Ii. Decorative & anti-carbonation = 150µm
d17e4272-528b-5ae5-af9f-ed3eda81feaa | note | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
aa055f11-b8de-55e6-9f31-74d03952a973 | note | iv. Atmospheric & splash zone (dual protective) = 200µm
455f3568-37da-5206-8057-74f18f857f15 | note | No more than 15% of the readings shall be less than 90% of the required thickness.
4d475e8a-207a-5d02-912c-9547fdbf8b05 | note | Attach: DFT Test Results
79f7c98f-3857-5554-bbe5-a0f5df389e3b | note | METHOD - Test
2a65fcd5-6d5b-5c55-9c17-8cbdd257f98d | note | – – – – – – – – – – – – – – – – –
aa80b24d-0af2-54b0-b6ac-17968b3d003b | note | FREQUENCY - Where required, 1 no. test every 50m², 3 tests minimum
3046bbc7-0519-589d-a56f-62c5676a9e0f | note | – – – – – – – – – – – – – – – – –
1f291aa6-6e84-511b-8db0-88a2eca05da1 | note | CATEGORY - IP
4d601762-257d-5b7e-a488-fb4c327289bf | note | – – – – – – – – – – – – – – – – –
c722cc6b-f69a-574e-89b1-17028dcdd2d6 | note | RESPONSIBILITY - SE/PE/SPE
8fff6794-9d78-5b2b-ac2b-88e2c5c1e59b | note | – – – – – – – – – – – – – – – – –
843fc2af-f4cc-5422-ac52-28616a51e842 | note | VERIFYING DOCUMENTS - This ITP
53c79991-eaaf-5e85-aee1-1a05c62fcb00 | date | Date Completed:
| checkpoint | 5.3 - Adhesion Bond Strength Testing
8f443fe1-e56f-544b-bfe9-f772abb28c97 | note | REFERENCE - 685.12 (b) (i) 686.14 (b) (i)
abc0570d-ff25-59d0-9868-a9e9ff1e50a9 | note | – – – – – – – – – – – – – – – – –
6c300cd0-4be8-58de-b4f5-8f34d320a854 | note | ACCEPTANCE CRITERIA - A minimum of 14 days after application, the bond-strengths between:
ac3cf5e1-b43b-5047-b5ce-adad3376bb9f | note | i. the coating system to the substrate, and
3f77816b-934d-5022-ad95-f7408a6bde05 | note | ii. Separate coating layers
9a848a44-6e7f-52da-bc69-06089598122e | note | shall be tested using 50mmØ aluminium dollies.
71462617-7555-544c-bd52-9673ca6dd384 | note | The subsequent results shall be greater than 0.75kPa.
71a4212e-3670-5a38-adcf-556a2634b2ae | note | Attach: Adhesive Bond Strength Testing Results
54a573b4-dc34-5940-8cb9-7e1571f64896 | note | METHOD - Test
1fb98e75-1b11-5dab-b484-690bd4b3c1ea | note | – – – – – – – – – – – – – – – – –
0b4f1cd0-f60e-550a-862f-4a62d90df8cd | note | FREQUENCY - Where required, 1 no. test every 50m², 3 tests minimum
14e1b01b-1e31-5dc0-8f3f-e3c3c2ab7098 | note | – – – – – – – – – – – – – – – – –
8e470121-2c12-5cc6-a44d-2ef5eb08e341 | note | CATEGORY - IP
0c101dcd-3315-5c67-963d-f543c7ca74f7 | note | – – – – – – – – – – – – – – – – –
64942d5b-3b17-5dcf-ad0c-2ecd0a508f7a | note | RESPONSIBILITY - SE/PE/SPE
95cb01eb-f3cd-549d-898e-4c2ccf55508a | note | – – – – – – – – – – – – – – – – –
b0c52580-8905-5f24-ad3d-b47dab9f57d1 | note | VERIFYING DOCUMENTS - This ITP
5996bbd8-0cb9-5ca1-85a6-92d923873449 | date | Date Completed:
| checkpoint | 5.4 - Penetration Depth Testing
25e88ad6-d76f-57aa-9a3e-98f38babb8ef | note | REFERENCE - 685.12 (b) (v) 686.14 (b) (v)
17d59154-f41a-59be-b6a1-23b1b308467b | note | – – – – – – – – – – – – – – – – –
51fad38a-4050-50cb-b661-74a82676ba12 | note | ACCEPTANCE CRITERIA - Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration.
b652d69b-8771-5c70-96d6-24d7bb608d6d | note | The subsequent results shall be:
6d257bed-4edd-5b3a-bad2-a7da365d58b8 | note | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
94d64a33-a933-51b5-a05b-7fb99037d155 | note | ii. Silane, Solid Silane or Silane Cream = 5mm min.
7c6cfb2e-a2c5-513e-851a-b12d5c193013 | note | iii. Silane-Siloxane or Siloxane = 3mm min.
47e317b3-4aaa-55bb-9311-050c77e4ad8c | note | Attach: Penetration Depth Testing Results
4d401968-0742-5662-a436-4c5a3241987f | note | METHOD - Test
29060a1c-bd69-5391-91b8-70c411bfaf71 | note | – – – – – – – – – – – – – – – – –
14c98c5d-b364-560f-835b-45c6377e7fce | note | FREQUENCY - Where required, 1 no. test every 50m², 3 tests minimum
e485e153-a2c5-56cf-a38d-0fd4e6d4e6e1 | note | – – – – – – – – – – – – – – – – –
a408687f-a06a-5b56-a2e4-dc702ef44b10 | note | CATEGORY - IP
2640a37c-ab66-5f3c-80c0-6bf22b630b87 | note | – – – – – – – – – – – – – – – – –
69846bb6-3b66-50e6-8e5d-d05a73ba9a19 | note | RESPONSIBILITY - SE/PE/SPE
b607f895-5df7-53f8-8266-5802c59629b8 | note | – – – – – – – – – – – – – – – – –
7b87f7ca-2b48-57e7-8a01-bb678b2de70f | note | VERIFYING DOCUMENTS - This ITP
e9365851-f524-50bf-885b-86ecf382ef27 | date | Date Completed:
| checkpoint | 5.5 - Non-conforming Coatings
d7a34510-771c-5a73-9cc0-9c17e63400b8 | note | REFERENCE - 685.14 686.17
b3d68538-eec3-5bd3-8f26-5a7c9f52e4c4 | note | – – – – – – – – – – – – – – – – –
70cc79ae-bece-526e-b15d-0e598614e2f2 | note | ACCEPTANCE CRITERIA - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
70b8aed4-6505-5f79-97ff-c5a873bfb2b3 | note | METHOD - Visual
1cc9a861-046e-580d-a165-9cbb67ddf8e9 | note | – – – – – – – – – – – – – – – – –
134ca011-7332-563d-9adf-d52dbfad5a8b | note | FREQUENCY - Where required
dfdfcfd7-3fdf-5eae-9f98-ecb10fcf93a3 | note | – – – – – – – – – – – – – – – – –
5b20a5d9-9203-5c78-ad7a-fb9b1469ca04 | note | CATEGORY - IP
9f0278a7-d981-5047-9240-cca16bf10434 | note | – – – – – – – – – – – – – – – – –
4efcfa9f-7182-5273-8fad-8739cfec143a | note | RESPONSIBILITY - SE/PE/SPE
7570800a-6457-526b-b431-ec2c9eb9431e | note | – – – – – – – – – – – – – – – – –
bab21829-b0b1-5b40-9470-bde4aa3776ea | note | VERIFYING DOCUMENTS - This ITP
c8597128-da19-566d-9292-0facd2afca1a | date | Date Completed:
| checkpoint | 5.6 - Coating Application Guarantee
84b275a1-f108-5b10-9708-788982e5bd7e | note | REFERENCE - 685.06 (b) 686.05 (a)
3367b534-f689-5553-9c19-8349787eebfb | note | – – – – – – – – – – – – – – – – –
aa1dfa44-3ae8-5761-bad5-ec25f77c15f5 | note | ACCEPTANCE CRITERIA - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application. Attach: Coating Application Guarantee
44d84224-5414-587b-bd86-f82687c92a9b | note | METHOD - Document Review
1f58faa4-8716-50e3-bc89-045a96444022 | note | – – – – – – – – – – – – – – – – –
be4efd42-b62a-529b-ad51-58c408b10dc5 | note | FREQUENCY - At completion of Works
8426f002-bcf7-5347-8a95-4cf12ec87b4c | note | – – – – – – – – – – – – – – – – –
8d89f470-ef10-5117-b785-2c1468cb0ca1 | note | CATEGORY - SP
0ffc7516-d23d-5ad6-b33c-8197adb6f242 | note | – – – – – – – – – – – – – – – – –
b747ca1a-0365-5d4c-b8b5-55deeb1e6997 | note | RESPONSIBILITY - SE/PE/SPE
499708d8-706d-5f91-979d-b916cbac10e8 | note | – – – – – – – – – – – – – – – – –
b0daf211-5b5b-5e8e-90c7-5879a709e006 | note | VERIFYING DOCUMENTS - This ITP
1be9c8a0-5703-5007-88cc-c2148932bd55 | date | Date Completed:
| checkpoint | 5.7 - Repair to Damaged Coating
239a3315-6626-53ab-9c67-4a634dd6df60 | note | REFERENCE - 686.17
f3270985-c685-5320-8db7-a83cd394c97f | note | – – – – – – – – – – – – – – – – –
757d9ea9-a546-5265-b583-c5b1052ffd52 | note | ACCEPTANCE CRITERIA - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
38351f96-42c0-5570-98a4-35c6dd9a45db | note | METHOD - Visual
0945739b-3d09-5ca6-b84c-43aa88237d8f | note | – – – – – – – – – – – – – – – – –
ca6eda3e-9ead-5a6d-8846-da1a1ae7b954 | note | FREQUENCY - Where required
794c427f-13a1-5e45-bd5b-07363caca510 | note | – – – – – – – – – – – – – – – – –
de4b93fd-89ef-5731-bb7f-1ee786ffca0d | note | CATEGORY - IP
52d462aa-5d8a-5f2b-8915-defe3f3df7ef | note | – – – – – – – – – – – – – – – – –
300d104e-1e6e-5e4d-96cd-c8a18f4d3b98 | note | RESPONSIBILITY - SE/PE/SPE
591815dd-9be5-5fd1-858f-14f18950120a | note | – – – – – – – – – – – – – – – – –
6ce3ebf9-374b-5d57-94cf-72a8082249ef | note | VERIFYING DOCUMENTS - This ITP
e03c2b79-e968-5276-8832-1d1985aa27e2 | date | Date Completed:
| checkpoint | 5.8 - Non-conformance Report (NCR) Closure
7c8e4468-700f-53de-88df-eeda502873d6 | note | REFERENCE - MRPA Quality Management Plan
b81fa867-4a3c-5aa7-8c43-4f3781f50638 | note | – – – – – – – – – – – – – – – – –
a4f5b7f0-1bf6-5d4d-95e8-61842c039279 | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
a5d1a2db-87cb-527d-82ab-7352a768c63f | note | METHOD - Document Review
7c5a58cb-4944-5153-9bf1-e8632661ac9c | note | – – – – – – – – – – – – – – – – –
664ec7c3-6b65-59c9-aae9-8cb4faedba85 | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
4f50dbc8-94d4-53fe-ada5-e0c54bc6579f | note | – – – – – – – – – – – – – – – – –
168dad84-4a80-5a00-8280-7da3327face6 | note | CATEGORY - HP*
1c694b51-d40c-5f25-8678-c2d79f83de96 | note | – – – – – – – – – – – – – – – – –
4b129659-1bd6-5231-9902-2ff6f000b443 | note | RESPONSIBILITY - SE/PE/SPE
ffc26814-91bb-539f-b217-9e967ebb2d14 | note | – – – – – – – – – – – – – – – – –
b26d9351-7c8e-566c-92c2-7a7a5dced69b | note | VERIFYING DOCUMENTS - This ITP
c4bd3358-c144-5969-b4f0-68424abcae30 | date | Date Completed:
| checkpoint | Final Inspection
b8f5b572-51a1-511c-bcb2-3dad9ff54434 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2a69210d-6e5c-590d-b731-68b5fa190349 | textbox | Name:
84db1487-ede8-5101-a92b-c1dac3cfd9d2 | textbox | Position:
99d803fa-e42e-5d18-b0ee-d3a983b1e9d6 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-105-STR-CAMMS-Bridge Expansion Joint Rev 0 | itp | ITP-105-STR-CAMMS-Bridge Expansion Joint Rev 0 |  | 87e87c72-a378-447f-a331-ec8cc154175e
| section | 1 - Referenced Documentation
| checkpoint | Reference Documentation
a8027ad4-9952-5bd6-8107-d4cbc35feb49 | note | Document Title: ITP-105-STR-CAMMS-Bridge expansion joints and waterproofing
c2efbaf6-9499-5e88-b7d7-e634710d7990 | note | ITP Description: CAMMS-Bridge expansion joints and waterproofing
1ec4a8e1-b7a7-56e6-b9f4-851311de0056 | note | Discipline (e.g. CIV/STR/RAIL):105-STR
a8a79c90-f8d2-50fe-b3cb-da8ce29d83fa | note | Revision Number: 0
26128c8b-992c-56ce-b621-9c863bc2bad0 | note | Revision Date: 10/11/23
7809fe74-bec1-5b84-8159-f286efbf0038 | note | ITP created by: Isaac El Zayat
281706c1-1c53-5c81-b834-02f447e544a4 | note | ITP approved for use by: Victor Mira
604e9fd3-e314-5216-bb3d-b3b029f55880 | note | 1.1 VicRoads Section 660 January 2018
6c5b92ef-4b13-5a00-9c25-7b8971133b16 | note | 1.3 AC-AR Installation Guide
| section | 2 - Preliminaries-Materials
| checkpoint | 2.2 - Expansion Joint Components
f733d9a6-7c80-5af2-adb3-49830af0a9b4 | note | REFERENCE - IFC Drawings VR 660.03
0d972b8e-f044-5407-b562-8e4d9a4c58e7 | note | – – – – – – – – – – – – – – – – –
fbece130-aa6e-5f5c-9516-27be5ff72fc6 | note | ACCEPTANCE CRITERIA - The Contractor shall supply all expansion joint components including joints, seals, inserts, anchorages, cover plates, waterproofing membrane, drainage system, bedding mortar, nosing, edging and all adhesives and sealants required for the installation of the joint system in conformity with the supplier’s recommendations.
a1a9ca1a-3a19-5910-8387-d8376e6fd746 | note | Attach Delivery dockets/Proof of purchase
103963b3-3a7e-514a-91a6-f77fa1b75b21 | note | – – – – – – – – – – – – – – – – –
f6093d15-7359-58d1-aa84-db89d66efa03 | note | METHOD - Document Review/ Inspection
df7ce7f1-6675-5e72-bcab-8289f233b2bb | note | – – – – – – – – – – – – – – – – –
af13b5f7-093e-5420-b16b-d5a52e3ae2ad | note | FREQUENCY - Where applicable, for each element
8548b200-5a80-5036-b122-e9be9c461977 | note | – – – – – – – – – – – – – – – – –
cc06f59d-7d28-5c92-ac15-4f631d4f25a5 | note | CATEGORY - IP
81f747c1-db94-59e6-a55b-2a6e92076d03 | note | – – – – – – – – – – – – – – – – –
41296d9a-5285-5501-b3ea-6ca923da8d31 | note | RESPONSIBILITY - PE/SPE
933a2e13-8929-5044-b413-82e6ce1e6dc6 | note | – – – – – – – – – – – – – – – – –
9be0df39-ee05-5bad-8ae4-b81b37d94f20 | note | VERIFYING DOCUMENTS - This ITP
5e018f01-b8fc-5af5-a187-199638976a63 | textbox | Date Completed:
| section | 3 - Preliminaries-Procedures
| checkpoint | 3.2 - Expansion Joint Design
b2bde7ce-4df5-5e7a-8a05-ba108a703614 | note | REFERENCE - IFC Drawings VR 660.03
fda6eeef-f12d-56ba-856c-0886ead93648 | note | – – – – – – – – – – – – – – – – –
fca0eb2c-d307-5660-a4c0-6d6fc41cfeb2 | note | ACCEPTANCE CRITERIA - The expansion joint system shall match the drawings. Where applicable, the joint sealant shall match the Drawings and installation manual
fe990c05-4a5a-5c6b-bab2-bbd1a9b251ef | textbox | Enter: Specify the Joint type:
70c33ce1-89e3-53f0-b758-c453495aca74 | note | AC-AR-125D for road P2-100D for SUP and Footpath
8b718c1e-d645-54d3-bdda-139cc8d859db | note | – – – – – – – – – – – – – – – – –
e13b46be-ca92-54d7-946e-d7423291f8b5 | note | METHOD - Document Review
d8b3147c-cc06-5d21-a864-1c552c464113 | note | – – – – – – – – – – – – – – – – –
b650f351-2af8-5d4e-87d9-1b8fe83bceec | note | FREQUENCY - Where applicable, once, within 4 weeks of acceptance of tender
27f121b5-cd64-54de-8774-8dd288ccf0e1 | note | – – – – – – – – – – – – – – – – –
4c32be85-82e0-5e5a-abda-2a06ff19b679 | note | CATEGORY - WP
2c6eace6-7fcc-53da-a218-4d18c4ad8061 | note | – – – – – – – – – – – – – – – – –
a548aa3d-f8b3-5d7c-ab95-699478e230a1 | note | RESPONSIBILITY - SE/PE
1253f4e0-6419-5b95-b2a2-885ebe33199b | note | – – – – – – – – – – – – – – – – –
1386e9c8-48ec-5e66-b888-4a237da3ec7c | note | VERIFYING DOCUMENTS - This ITP
0e54caef-5b4b-5feb-9d46-54f89bfea5c4 | textbox | Date Completed:
| section | 4 - Pre-construction Activities
| checkpoint | 4.1 - Expansion Joint Installation Temperature
cfc555d6-92b4-5b44-9135-bf30b6b067fb | note | REFERENCE - VR 660.04
6da5fb7c-931c-59ba-8636-da0876f1f6cf | note | – – – – – – – – – – – – – – – – –
0087e04a-2bab-5e4d-8c8c-0b9246c396a1 | note | ACCEPTANCE CRITERIA - The bridge temperature shall be measured at the time of installation and where it differs by more than ±5°C from 20°C , shall be adjusted by the calculated values provided by the designers. Installation Temperature = [free text]
f09e5f8b-ab4d-5d71-9243-5e03f61cfcd3 | note | – – – – – – – – – – – – – – – – –
e0739bcb-a29f-548a-94ac-df4e39e4cd38 | note | METHOD - Measure
f720fe5d-94fe-5ba7-b230-f98efea553ea | note | – – – – – – – – – – – – – – – – –
72492033-836d-59b2-9e0f-e3a39d562e68 | note | FREQUENCY - At the time of installation
443395c4-d60a-54f5-9847-c412687af0c9 | note | – – – – – – – – – – – – – – – – –
cafe3d56-e13d-529c-9a3b-a9ab6938b1ef | note | CATEGORY - IP
8fb0f596-73a0-53b3-9e5b-8de6ea6832b5 | note | – – – – – – – – – – – – – – – – –
fa5deae6-1419-5678-8046-27186cc1f4f2 | note | RESPONSIBILITY - SE/PE
18499831-4aa2-5203-86fd-c3e30247648d | note | – – – – – – – – – – – – – – – – –
114aa5ae-e10b-5d90-8ccf-ddf434eed91b | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
3ea2dd36-ff90-52dc-9bad-7a9650ca1bd3 | textbox | Date Completed:
| checkpoint | 4.2 - Post-pour Inspection of Expansion Joint Bearing Surface
d4e4691a-d167-544f-8d3a-37e26577f3d9 | note | REFERENCE - VR 660.04
b877897e-495a-5962-b398-d3b6664d342d | note | – – – – – – – – – – – – – – – – –
b7bb47e9-0de2-5614-ae2b-5a51640dd6f9 | note | ACCEPTANCE CRITERIA - The faces of the concrete under the full length of the expansion joint shall be inspected for the presence of voids and other imperfections.
8660e067-d11b-5df7-8c23-1c17462d59fa | note | – – – – – – – – – – – – – – – – –
b2ca34cd-2893-5de6-9499-3a09d5a237ba | note | METHOD - Visual
8ec6810c-6914-5514-b9ce-d43db6332624 | note | – – – – – – – – – – – – – – – – –
31afb989-ea0d-599f-95b7-55cf0f6cea9f | note | FREQUENCY - Prior to joint sealant (where applicable)
a443f14b-79e3-578c-8e94-7fa3760572fe | note | – – – – – – – – – – – – – – – – –
feabb7f5-6d26-5d6b-8c64-cf1911bdcb58 | note | CATEGORY - IP
3a770eba-c925-56fa-9adc-30529ae12a4d | note | – – – – – – – – – – – – – – – – –
4f35f135-63a1-52f1-b566-774bf5afeaf6 | note | RESPONSIBILITY - SE/PE
0c49d853-26e6-5016-a385-cd81a4ecf0a9 | note | – – – – – – – – – – – – – – – – –
01a6fad6-bfda-534a-b25e-133ca8469bcc | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
f3824843-adc4-53dd-ba58-7227a27fd811 | textbox | Date Completed:
| section | 5 - Construction Activities
| checkpoint | 5.1 - Expansion Joint Placement- Anchor Bolts
1034c829-8814-510c-9270-74b97e4ffc0a | note | REFERENCE - IFC Drawings AC-AR Installation Manual
a7861593-006e-57c1-8156-fbac0c28cc8d | note | – – – – – – – – – – – – – – – – –
ff8d0ccf-9242-5b1a-abf2-a4f643fc6159 | note | ACCEPTANCE CRITERIA - After concrete strength is in excess of 30MPa, the anchor bolts can be tightened via the snug tight plus part turn method or with a calibrated torque wrench. As per installation manual:
52378a50-e26e-5267-9ecb-b26ce6502294 | note | Part turn method: Snug tight + half turn
8a49e581-096d-5e1b-a496-04313b85f2db | note | Calibrated torque wrench: 400Nm
b22df80c-a271-5774-a879-67a8f04f85e2 | note | – – – – – – – – – – – – – – – – –
9e64ed76-3f33-50db-8ffa-8b711c25b260 | note | METHOD - Measure Visual
1e3b6839-8199-574e-8d57-eff9a77e0095 | note | – – – – – – – – – – – – – – – – –
e7bf25d4-3978-58c4-a752-62d9bde92ea2 | note | FREQUENCY - AC-AR 125D (Road section) joints
0b4b3044-071c-5a58-818c-600176381cdd | note | – – – – – – – – – – – – – – – – –
ec5cbf2c-c82c-5d6e-aa9b-ef299143c3c5 | note | CATEGORY - IP
728ff792-c1ec-5e56-abd0-51965d0fddba | note | – – – – – – – – – – – – – – – – –
ce2644ca-555f-5eb0-8708-f4c5c3733faa | note | RESPONSIBILITY - SE/PE/SPE
8980c66b-7d85-577c-a424-90473ba5af59 | note | – – – – – – – – – – – – – – – – –
67fb0abe-9d96-5af3-8f6c-fb7c821f69f7 | note | VERIFYING DOCUMENTS - This ITP
1f032175-d8d1-52b4-b009-7fa10c56b409 | textbox | Date Completed:
| checkpoint | 5.2 - Expansion Joint Placement-Coverplate
957539c2-4e66-5314-9f53-27bb4aebfb14 | note | REFERENCE - IFC Drawing
295461e7-b4e1-5fdf-a9aa-17560e90d0b1 | note | – – – – – – – – – – – – – – – – –
b25d9ef6-8f10-5c41-bcb8-6bf5ba7a660f | note | ACCEPTANCE CRITERIA - Aluminium checker plate is installed with M12 Cuntersunk bolts as specified in the drawings
ab28af66-5e1f-5e0e-a76c-61fe6f706710 | note | – – – – – – – – – – – – – – – – –
d6beb434-ce53-5483-8f36-6bc0b30f3a3d | note | METHOD - Inspection
9d1adc35-71b0-5b51-b568-92af7e1ab214 | note | – – – – – – – – – – – – – – – – –
4508af31-03c9-54ee-85fb-9448fbfb04f0 | note | FREQUENCY - P2-100D (SUP and Footpath) Joints
4fd58c8d-eff7-5450-b4e7-befb066d98ee | note | – – – – – – – – – – – – – – – – –
35d98da6-edf6-5ebe-b0a5-bc81c137f2db | note | CATEGORY - IP
784b8bb6-5f91-5a3f-9f9a-93585216b16c | note | – – – – – – – – – – – – – – – – –
89376a9e-38c7-5ecd-aeec-8f8722833354 | note | RESPONSIBILITY - SE/PE
47a81494-ca85-5339-b142-b5683d3e49b6 | note | – – – – – – – – – – – – – – – – –
36205fc8-de65-50a6-a118-26e8350d47cc | note | VERIFYING DOCUMENTS - This ITP
69ea79ee-2529-5605-a33b-758c949e3d96 | textbox | Date Completed:
| checkpoint | 5.3 - Expansion Joint Placement
cadf3000-2b21-5dbf-84f4-66cf87d18e9c | note | REFERENCE - IFC Drawings AC-AR Installation Manual VR 660.04
f3a8888b-28e8-5706-a5a8-018beb1b3fdb | note | – – – – – – – – – – – – – – – – –
48b3e7de-b34a-5336-b147-fac8eb3ae6ed | note | ACCEPTANCE CRITERIA - Check compliance with the Drawings, installation manual and tolerances:
8241ec59-96d6-51de-a13c-ad6079319d41 | note | Joint gap = ±3mm (38mm is specified on the drawings)
e7712e1e-471d-534f-928a-e7ca563b61bd | note | Deviation from plan alignment = 5mm max.
c5deb94f-cf3b-5839-bd2d-387734bc91d7 | note | Deviation of top surfaces (step) = 0mm to -2mm when measured perpendicular with a 2.5m straight edge
f2bcd940-5160-5196-9f9a-9cb6cdaed340 | note | – – – – – – – – – – – – – – – – –
d0407e5e-ba26-5f7f-bfbc-1183b19d0a40 | note | METHOD - Measure Visual
8b7851f1-40ce-5c67-ab6b-832b3ba1225d | note | – – – – – – – – – – – – – – – – –
f1e18e9f-b3f7-5bca-a472-81081f4feed9 | note | FREQUENCY - Each element
00b4fd4a-20a2-5aac-83d1-b10a2ac93c53 | note | – – – – – – – – – – – – – – – – –
3e6c8bb9-3c8f-57e5-8cc2-e82f0ccfe70c | note | CATEGORY - IP
0617d363-17c4-5012-90d0-b77790373a8a | note | – – – – – – – – – – – – – – – – –
da045b18-929a-524d-942e-f2796a80105a | note | RESPONSIBILITY - Surveyor SE/PE/SPE
c472bee6-6530-5219-8951-d01fc7506b9b | note | – – – – – – – – – – – – – – – – –
cc510cb6-3eb9-5dda-9b15-0b3825579edd | note | VERIFYING DOCUMENTS - This ITP
59206f66-d5ef-58ab-8d44-ee21c7e796a4 | textbox | Date Completed:
| checkpoint | 5.4 - Compression Seals, Inserts and Membranes
b0b5f6a7-ba4d-5371-8b66-7e39043ce02c | note | REFERENCE - VR 660.04
68547c48-4260-5e32-b709-eac814ef1040 | note | – – – – – – – – – – – – – – – – –
99f9ebcc-9a5e-571a-bd56-ad13f0e64a38 | note | ACCEPTANCE CRITERIA - Compression seals, inserts and membranes shall be installed in one continuous piece for the full length of the joint, inclusive of footpaths and barriers.
42f73dfb-8bbf-5d32-90be-13bcaed6e8f4 | note | Completed joints shall be watertight.
b677c57f-d528-5d44-9723-4905a075e1bf | note | – – – – – – – – – – – – – – – – –
833ac32e-0695-5307-8853-3c898b7ebdb7 | note | METHOD - Visual
eb23069e-713b-5bd3-857c-382b5f061150 | note | – – – – – – – – – – – – – – – – –
0d462fd5-604e-5e2b-9214-186230e1c0f0 | note | FREQUENCY - Where applicable, each element
ded599c4-7e83-5d52-97cc-650086badf12 | note | – – – – – – – – – – – – – – – – –
c5ea1475-2fee-5c5f-88e1-4930fe420a54 | note | CATEGORY - IP
e3f9bac8-8516-5dc8-85c7-07d63d2f0486 | note | – – – – – – – – – – – – – – – – –
b52aca00-a073-5789-9317-228db85d7182 | note | RESPONSIBILITY - SE/PE/SPE
86d93929-1b9e-5a25-856f-f5897d39aa06 | note | – – – – – – – – – – – – – – – – –
55f9cdd5-0af5-567a-a2c2-92b31c6a0c30 | note | VERIFYING DOCUMENTS - This ITP
a8c2edcc-20d0-5a32-8018-3e42ff5ba5aa | textbox | Date Completed:
| checkpoint | 5.5 - Final Inspection of installed system including all accessories
7c9d9346-c031-50e9-ac9c-f52897ba6023 | note | REFERENCE - IFC Drawings
f3af8a1a-639d-54e9-a421-fd86666f0580 | note | – – – – – – – – – – – – – – – – –
ff929cef-b52e-5ed6-90cd-6bbddb03d7e4 | note | ACCEPTANCE CRITERIA - No visual damage to the installed system
6f3d32fd-1414-51c6-90a1-71c1fd1c802e | note | – – – – – – – – – – – – – – – – –
27eedf3b-de0d-5ed5-9d75-9a9400e0f164 | note | METHOD - Inspection
30bf8a7d-28d9-589d-8f1d-f96509771531 | note | – – – – – – – – – – – – – – – – –
35dfdf4a-4348-5d86-abff-9a57c0608f27 | note | FREQUENCY - Once per Lot
43aa97aa-2127-57d5-8939-42ae52b96e35 | note | – – – – – – – – – – – – – – – – –
bf7a90b7-0094-5c78-ba32-f743e98152b8 | note | CATEGORY - IP
8d1f73cd-83a6-5ac1-9600-24e45351ae8c | note | – – – – – – – – – – – – – – – – –
c3c28628-d61a-544c-a33c-1aeb9958fec5 | note | RESPONSIBILITY - SE/PE
b4c32e3f-62cc-5a67-bc23-b53e1d6d55d2 | note | – – – – – – – – – – – – – – – – –
0e8320ce-7f6f-5d69-a9c0-fa8a94fa9d68 | note | VERIFYING DOCUMENTS - This ITP
3cdfe8f1-7736-53c0-88af-b9bc64ba01b8 | textbox | Date Completed:
| section | 6 - Post-construction Activities
| checkpoint | 5.1 - Trafficking of Joints During Construction
0579cb90-1224-5062-834f-fe9635ba1f20 | note | REFERENCE - VR 660.04
48d41b7b-c38c-5105-bfba-fef968c7ae60 | note | – – – – – – – – – – – – – – – – –
7f4404ac-c537-5989-8c36-ca7d4e8728db | note | ACCEPTANCE CRITERIA - Joints, seals, inserts and membranes shall be protected from damage due to construction activities and the passage of site vehicles.
88b794ca-1c17-5f24-b1dd-b46310061258 | note | – – – – – – – – – – – – – – – – –
81610df2-b301-598b-a403-b24b5012539d | note | METHOD - Visual
85be5565-d11a-533a-9649-0253fcdc0206 | note | – – – – – – – – – – – – – – – – –
679001ff-9043-5080-9cee-48b27a54f176 | note | FREQUENCY - Where applicable, each element
22c299f7-3979-5075-8b96-148e34e403c8 | note | – – – – – – – – – – – – – – – – –
118206ee-343d-5758-b099-b2b328f08c0d | note | CATEGORY - IP
3c023519-be2c-5efb-a8a6-2dc24b72369b | note | – – – – – – – – – – – – – – – – –
5cfafe2c-cf32-5674-aa2a-cefd99c10080 | note | RESPONSIBILITY - SE/PE/SPE
976c5eb4-5510-5fab-aadd-5a9c2da52519 | note | – – – – – – – – – – – – – – – – –
76bdc6cb-1c6e-5a8d-809a-e6918a4aec55 | note | VERIFYING DOCUMENTS - This ITP
991bdc08-c61f-58cf-aee0-e790c4799d2c | textbox | Date Completed:
| checkpoint | 5.2 - As-built Survey
5c287ad8-fc46-5154-b635-0e155079744f | note | REFERENCE - IFC Drawings VR 660.04
7c90c970-d210-5e20-8563-a9f34b532957 | note | – – – – – – – – – – – – – – – – –
f2a27bc1-76eb-581b-b7f5-6c5c8c97742f | note | ACCEPTANCE CRITERIA - Provide record of dimensional measurements to demonstrate expansion joints comply with tolerances as per 5.3 above.
97338522-6174-5007-8e89-2a86ac20bba5 | note | Attach: Survey As-builts / Survey Report
8a69bce4-48e6-552e-aea0-2145cba11181 | note | – – – – – – – – – – – – – – – – –
40304be0-1049-50f1-a99f-e085ebaac4da | note | METHOD - Document Review
d00d89d5-8b21-5cd0-b1bb-a90ace16c221 | note | – – – – – – – – – – – – – – – – –
8e4ba5b6-c644-5eab-a54b-d0e0a0c5a843 | note | FREQUENCY - Each element
dfe6015c-6654-582f-b772-f3002068cb24 | note | – – – – – – – – – – – – – – – – –
c4819624-df5b-5167-a236-3ca48c920886 | note | CATEGORY - IP
401af768-e710-501d-8711-4de500a2a90a | note | – – – – – – – – – – – – – – – – –
09d33f60-dff5-5784-92cd-b0b39952553a | note | RESPONSIBILITY - Surveyor SE/PE/SPE
1f0399e8-6fbc-5bf5-a761-bd70d76b4d22 | note | – – – – – – – – – – – – – – – – –
53c91829-5660-5c1b-a20b-06c1e78a629a | note | VERIFYING DOCUMENTS - This ITP
fa36db24-a12f-5152-a492-8e2c42d2e233 | textbox | Date Completed:
| checkpoint | 5.3 - Subcontractor Product warranties obtained
f918e8f4-08f9-58a2-bcac-3c51570ae5f5 | note | REFERENCE - Work Method Statement IFC Drawings
f7a2ba92-d4fd-5e39-8f39-63fc0889e93b | note | – – – – – – – – – – – – – – – – –
2b9e2130-1c52-5eda-b380-2e3aa73d848a | note | ACCEPTANCE CRITERIA - Product warranties obtained and are compliant with what is specified in IFC Drawings
f3dbe5c3-e150-55b9-b19f-5f5119077c6f | note | – – – – – – – – – – – – – – – – –
e8265290-7c5f-5f6f-b878-b3dfe097994c | note | METHOD - Inspection Document Review
366441c6-3deb-553e-8140-fd2093e1657a | note | – – – – – – – – – – – – – – – – –
1d664a67-8d38-5011-9191-dbc5e75d5d7d | note | FREQUENCY - Once per Lot
c44e82ad-5af5-5ea2-ac77-c1d48ab42e81 | note | – – – – – – – – – – – – – – – – –
17e0b05b-62f1-57e9-a522-ae9504970e70 | note | CATEGORY - WP
a88fa225-5c44-5a8e-b0df-c25eb0dec2df | note | – – – – – – – – – – – – – – – – –
fb070335-fa46-5683-9d6a-2696fa3a6528 | note | RESPONSIBILITY - SE/PE
94ad8096-2ff9-55b4-8ee1-4b71b8f8d0e9 | note | – – – – – – – – – – – – – – – – –
11a96251-98cc-5949-905a-ff7bf9d05267 | note | VERIFYING DOCUMENTS - Copies of product warranties
d4a040a2-6070-5647-86b2-f73ac1e3ae9c | textbox | Date Completed:
| checkpoint | 5.4 - Non-conformance Report (NCR) Closure
0131e3bf-c6ba-5987-bff6-2fbbeaaef2bd | note | REFERENCE - MRPA Quality Management Plan
a1fd406f-5cfa-515f-8603-4d36783ce686 | note | – – – – – – – – – – – – – – – – –
4d0c605f-d00f-51c1-9d02-67bda189e16f | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
b8b24f6b-65ab-5ed7-8b41-7fa6b417968b | note | – – – – – – – – – – – – – – – – –
0be1861a-03de-5cee-9542-7ac3099ebace | note | METHOD - Document Review
3c80fd14-c9c0-5bf3-a875-ef76989c1335 | note | – – – – – – – – – – – – – – – – –
5e852f1b-6f67-52e6-80cb-cda6afee7cf5 | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
b34ce2cd-a8e5-5f3e-900f-0642d260f971 | note | – – – – – – – – – – – – – – – – –
07618e5e-0817-5a60-ad38-b0d33ccb0113 | note | CATEGORY - HP*
10956934-8963-58a1-b3d1-4ef337968ec5 | note | – – – – – – – – – – – – – – – – –
17d76026-8276-5a63-bbfb-600ca0f2495f | note | RESPONSIBILITY - SE/PE/SPE
debcc40f-58ab-5510-8589-d119ac0fcdb9 | note | – – – – – – – – – – – – – – – – –
6b4bc80a-7be8-50a9-9457-b38cf791ea54 | note | VERIFYING DOCUMENTS - This ITP
33d32882-48f4-54f7-8b47-d361eedb63a0 | textbox | Date Completed:
| checkpoint | Final Inspection
770703e9-75b6-5ff7-98b5-4e209529bee6 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c5a3f4a5-65bb-5ad5-b5d1-abf45c66c849 | textbox | Name:
d936ae23-e46f-575f-860b-386f461eeb80 | textbox | Position:
aaaeef21-5aaf-5605-bf33-3af9339e09f3 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-115-STR-CAMMS-Bridge Waterproofing Rev 0 | itp | ITP-115-STR-CAMMS-Bridge Waterproofing Rev 0 |  | 7ecd2c93-ba52-4407-9c94-282c224589b0
| section | Referenced Documentation
| checkpoint | Reference Documentation
48c7ea56-89a3-5d6a-90d8-1c2cb7c267ce | note | Document Title: ITP-115-STR-CAMMS-Bridge waterproofing
bf0139b3-1dde-59fa-8bfe-36ccf277c08f | note | ITP Description: CAMMS-Bridge waterproofing
cca2741e-3ec6-5bab-8ef5-ac19a4209bdf | note | Discipline (e.g. CIV/STR/RAIL): 115-STR
3007c6a3-af46-5a26-acec-e5b37d90bf67 | note | Revision Number: 0
e260ea69-4627-56e8-ac95-00ab34220b46 | note | Revision Date: 15/12/23
5d981741-e1ce-5699-978e-703c44903060 | note | ITP created by: Victor Mira
c75f776a-a41e-5514-9bcd-f7a35fc2a180 | note | ITP approved for use by: Victor Mira
b45e2264-63d2-5bef-b617-37e83d5abc74 | note | 1.1 VicRoads Section 660 January 2018
7b08064c-bc8c-51d3-bbee-7c22a704414c | note | 1.2 VicRoads Section 691 November 2018
67a70455-454b-57b9-b8ab-4b54fa85df1d | note | 1.3 AC-AR Installation Guide
| section | 2 - Preliminaries-Materials
| checkpoint | 2.1 - Waterproofing Membrane System Materials
e6443af9-6b1d-5386-b0ad-d90a2c86ef18 | note | REFERENCE - VR 691.05 VR 691.07
8c1c4459-d36f-5cc5-b1b2-b486380f4ce0 | note | – – – – – – – – – – – – – – – – –
f4f85e0e-7452-5932-9c18-f224e915cfe0 | note | ACCEPTANCE CRITERIA - Certificate from the manufacturer in the form of a guarantee confirming that the waterproofing system and materials comply with the requirements of this section, including a guaranteed in-service performance of not less than ten (10) years from the date of installation. Submit Certificate of Conformity, including all relevant test results shown in Table 691.071 and Table 691.072, verifying conformity of the supplied materials for every lot/batch delivered, to be submitted for review to the Nominated Authority.
bb183dc5-c69f-5bc5-af8d-ad87a7413a37 | note | Enter: Teambinder Approval Number
7a357e6a-9574-57ec-9b16-28292d2a5e8d | note | METHOD - Document Review
32fcd06e-56e8-53a2-b152-9ebeb097d904 | note | – – – – – – – – – – – – – – – – –
1c538609-fdf7-58b6-b100-2a6cf7991b28 | note | FREQUENCY - Prior installation
ffe93e42-25ca-5d7f-b2b2-f2c12c465b68 | note | – – – – – – – – – – – – – – – – –
c7ae826d-6e6a-513d-826e-4c1564fec24b | note | CATEGORY - HP
e96dc6b1-01f7-59c9-ad62-3094554cc57a | note | – – – – – – – – – – – – – – – – –
7d045d9c-5287-5396-9348-da1af847c468 | note | RESPONSIBILITY - Nominated Authority
b37a9761-5b10-5f75-8ee2-4078b19c8305 | note | – – – – – – – – – – – – – – – – –
a1023d2d-59e0-5387-b315-659acfd201d9 | note | VERIFYING DOCUMENTS - This ITP
43907e7f-cb4b-53e4-b8b0-dc991652d209 | note | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Preliminaries-Procedures
| checkpoint | 3.1 - Waterproofing System installation Procedures
ee1409e9-1537-5c02-8384-b94c4681a5f1 | note | REFERENCE - l VR 691.04
5e5c1df8-797f-52e3-a827-1707b1c726a8 | note | – – – – – – – – – – – – – – – – –
5cc8f2db-9c5f-5927-8552-0969425a97d9 | note | ACCEPTANCE CRITERIA - Details of proposed procedures and surface preparation in accordance with clause 691.08 to be submitted for review to the Nominated Authority. Waterproofing works shall not take place until the Contractor's proposed materials and procedures and surface preparation in accordance with clause 691.08 have been reviewed and accepted by the Superintendent.
8526395a-3f3d-5394-823c-fda593eb18c1 | note | Enter: Teambinder Approval Number
1c156aa2-2ac3-5cf7-b80a-2785ce723cc3 | note | METHOD - Document Review
edc5eaff-d3df-5da6-a677-439a98a4263f | note | – – – – – – – – – – – – – – – – –
c95149fb-8908-5192-b170-8c4252c0baf9 | note | FREQUENCY - Prior installation
f83b1b7d-7953-59b2-a09c-1211b9e3f9e5 | note | – – – – – – – – – – – – – – – – –
70eec19e-ebe8-5256-ae30-86d49856ead6 | note | CATEGORY - HP
1956e430-0b7d-5db9-8aa4-5f0c0447a8ff | note | – – – – – – – – – – – – – – – – –
32feec4f-3345-5b14-81dc-3d713c606d83 | note | RESPONSIBILITY - Nominated Authority
878f2618-5b0f-51fb-93af-7787483258f7 | note | – – – – – – – – – – – – – – – – –
b2479654-dff3-5be6-9b8d-b4d81b25995e | note | VERIFYING DOCUMENTS - This ITP
b922cfbe-5b89-592d-9ef9-f90e25dbf5f4 | note | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Pre-construction Activities
| checkpoint | 4.1 - Material Handling and storage
4d6bdd96-6e9a-55b3-b965-207919e13d0b | note | REFERENCE - VR 691.15
5e362f8a-0497-5cf2-b6d3-d97da9ddd796 | note | – – – – – – – – – – – – – – – – –
34826651-1ae5-5545-af7a-ec428b24359c | note | ACCEPTANCE CRITERIA - Where applicable the joint material including joint sealant shall match the drawings or be an equivalent product All material shall be brought to site in the original preformed rolls or unopened cans clearly labelled with the manufacturer’s name, product type, reference and batch numbers. The Contractor shall provide a certificate from the manufacturer for each batch of waterproofing membrane and primer material confirming:
c62fa845-830b-5852-b786-f902d5b006ab | note | (a) manufacturer’s name and address
dd6fc847-3dc3-5a2c-8b42-871e9ab1debf | note | (b) product reference
9bb66074-fe1f-5d36-b271-6eaff473ec73 | note | (c) batch number of identification
26447a34-3627-5476-be00-7955d53aacb3 | note | (d) quantity manufactured in the batch
794b9a74-a3bb-50b7-a8d7-8430b2b323aa | note | (e) date of manufacture.
0110890f-c389-568d-be87-1c824b185484 | note | All waterproofing membrane materials to be used on the works shall be free from contamination, gelling, drying out, heavy skin formation and severe segregation of ingredients. Attach Delivery dockets/Proof of purchase
3a7e8e49-00ab-553a-9869-68491bed1a24 | note | METHOD - Document Review/ Inspection
9faaad8c-4ca4-5a75-8614-24995ae1f4ca | note | – – – – – – – – – – – – – – – – –
3fa476ba-ece6-5446-b32e-23dde58b05d4 | note | FREQUENCY - When applicable
3ab64058-0cf1-5a04-9912-daddbb6d32db | note | – – – – – – – – – – – – – – – – –
b3ea5fb9-2693-54d9-965c-3e5111d2ba4a | note | CATEGORY - IP
9b1a2089-fce1-5db0-a222-5acdc1241d47 | note | – – – – – – – – – – – – – – – – –
53a7f1e8-b8bf-5e56-99ab-8b7f35384bb8 | note | RESPONSIBILITY - PE/SPE
d7326306-de2a-5f83-b5e2-3c72326e6814 | note | – – – – – – – – – – – – – – – – –
5ed48405-969d-55b0-adfe-db6b0dc2c8a7 | note | VERIFYING DOCUMENTS - This ITP
c030fbe2-55c6-576c-bcc2-9368d10a7cf2 | note | Date Completed:
| section | 5 - Construction Activities
| checkpoint | 5.1 - Surface Preparation
f195744f-ca35-5ffb-9ab1-df0a310e6339 | note | REFERENCE - 691.08 (a) and(b)
3e21b186-c60d-5edc-bde3-65ada5595d00 | note | – – – – – – – – – – – – – – – – –
ed7adcb3-36f5-5fec-b7f4-a801255c9508 | note | ACCEPTANCE CRITERIA - The surface preparation shall be in accordance with the manufacturer’s recommendations for the waterproofing membrane system to be applied and as specified in this section. Concrete surfaces to which the waterproof membranes are applied shall be dry, clean, sound and free of dust or loose particles.
cb2d892c-f80f-5bee-bb87-69a07f3991b4 | note | METHOD - Visual Inspection
fd16e92d-21a7-5cd3-ac68-3e10569c7518 | note | – – – – – – – – – – – – – – – – –
640acd5d-919c-501f-af31-13fae8fec7bc | note | FREQUENCY - Before Primer Being applied
98cbf079-e6a2-5ac1-aa99-28d37971828d | note | – – – – – – – – – – – – – – – – –
204ad66d-07bb-502e-90ab-11a5f00bedc4 | note | CATEGORY - IP
c69ccd26-7ce2-53a1-a369-0b4724c94ee1 | note | – – – – – – – – – – – – – – – – –
f0af1d6f-984c-5383-aba9-e1ccd9ce2570 | note | RESPONSIBILITY - SE/PE
e63dd89e-af0a-5024-bbe3-abae27cbe406 | note | – – – – – – – – – – – – – – – – –
08c6664b-eb9e-59cc-ab55-35f3f2dc294d | note | VERIFYING DOCUMENTS - This ITP
6af443ba-7721-50c1-b40e-c74ca168fbac | note | Date Completed:
| checkpoint | 5.2 - Primer application
7a048959-8987-59db-807f-a6542eddb2a3 | note | REFERENCE - 691.08 (c )
408e83e5-c450-5a2a-8534-3ea06533cf45 | note | – – – – – – – – – – – – – – – – –
08919e41-825d-5521-b083-6fb0ee84b67c | note | ACCEPTANCE CRITERIA - Primers shall be applied by brush, mop, broom or spray in accordance with the manufacturer's recommendations.
2bf97d75-d0e8-5e50-9f44-f94f275e45fb | note | METHOD - Visual Inspection
cc1507be-ff7d-50db-a60a-8e725ee1b803 | note | – – – – – – – – – – – – – – – – –
63235347-3c84-572d-8280-7fdb84683b0e | note | FREQUENCY - When applicable
8834ddbb-b489-5230-a272-f6c56fc5e98a | note | – – – – – – – – – – – – – – – – –
a4e2e054-828a-5b2c-9fd0-36e7a80dcdbd | note | CATEGORY - IP
b8a81c6e-cb9d-52ad-8728-14391e86d687 | note | – – – – – – – – – – – – – – – – –
f22040e5-9ba0-5c9a-badf-9de6e6fc5520 | note | RESPONSIBILITY - SE/PE
6a51dfc6-f190-59ea-8cda-dcebfd2d05be | note | – – – – – – – – – – – – – – – – –
1f3b9291-b13d-5d8e-aeb6-ca0a57051486 | note | VERIFYING DOCUMENTS - This ITP
f8542b01-5514-5947-acc0-8a5849d38f70 | note | Date Completed:
| checkpoint | 5.3 - Environmental Conditions
43ca527c-c742-57a6-ae36-52313ad6606b | note | REFERENCE - 691.14
4eeb9282-15fd-59e0-80b6-4bed5e66070f | note | – – – – – – – – – – – – – – – – –
77d321c2-83d4-512d-8ec4-8968e5221e88 | note | ACCEPTANCE CRITERIA - Waterproofing systems shall not be applied under any of the following conditions:
f21df389-39ec-54ef-90ed-c2591ada9f7d | note | (a)windy conditions where over spray and/or spatter may be generated
7fdbe1cc-a62a-5d50-91bc-a159e7bcb6bd | note | (b)when wind-borne debris is likely to contaminate the uncured surface of the freshly applied membrane
27fd0b91-8811-52be-bdc8-29bf2a081e2f | note | (c)when the ambient temperature exceeds 35°C or is below 10°C unless otherwise expressed in writing by the manufacturer
8a38c3e0-01c5-57eb-b1df-99c220d92d1f | note | (d)when the relative humidity exceed 85% or where it may be expected to exceed 85% during the subsequent 12 hour curing period
4f9d10cd-fd25-5b10-bfdf-5a2b02061b5e | note | (e)when rain spatter contaminating the surface and adversely affecting the adhesion to the substrate
1763346a-5fb0-5c77-9ce0-84dadd57d45f | note | (f)when the substrate surface is wet or damp,
fe148a8a-c970-548a-a046-2957f548e61b | note | (g)the surface temperature of the substrate exceeds 40°C.
8dccc056-09e1-515b-820d-15a98383c8d5 | note | METHOD - Visual Inspection Measure
05061861-4b48-5e66-aff2-e5c9f4efaf20 | note | – – – – – – – – – – – – – – – – –
2c97c706-b554-58ec-95d2-f01100469b36 | note | FREQUENCY - Prior installation
629e8c59-0581-5a77-9536-6b898b8959fe | note | – – – – – – – – – – – – – – – – –
7477b041-2e56-522b-8bc4-eeef520f22c1 | note | CATEGORY - IP
fd98d2de-b515-5c8d-aac7-8dfc3417a37d | note | – – – – – – – – – – – – – – – – –
3e6a5089-00c0-5ac7-a26f-399f516cc081 | note | RESPONSIBILITY - SE/PE
01623849-2033-540b-b6cc-a26002d64c43 | note | – – – – – – – – – – – – – – – – –
0bd5c467-d50c-50e2-8e3d-b22dd99172bf | note | VERIFYING DOCUMENTS - This ITP
2fdc72ec-8bd8-5ace-a05a-a7ab5e9f54f1 | note | Date Completed:
| checkpoint | 5.4 - Waterproofing membrane application
8efdfba2-9e50-5a90-bb4d-53fb17c78c36 | note | REFERENCE - 691.09 (a)
c2eab467-67ea-53cd-8457-5b86af18b273 | note | – – – – – – – – – – – – – – – – –
e7954399-a525-539c-9fdf-0f9f01f1337e | note | ACCEPTANCE CRITERIA - All concrete surfaces to receive a waterproofing membrane shall be dry at the time of application. The waterproofing membrane system shall be applied within 24 hours unless otherwise expressed in writing by the manufacturer after the preparation of the concrete surface. The prepared surface shall be protected against contamination and rain or expected rain if the waterproofing is not undertaken within 24 hours.
f3dc652c-13d6-5cb1-800a-8dab47942100 | note | METHOD - Visual Inspection
e1b920cd-6097-5483-9e27-415e0c298139 | note | – – – – – – – – – – – – – – – – –
d72af173-da47-5774-a86f-71263b771603 | note | FREQUENCY - Prior installation
46b1f223-0477-50dc-bacd-7a400f35232d | note | – – – – – – – – – – – – – – – – –
78b6e667-a941-58f3-9ad7-ad1a18223a5a | note | CATEGORY - IP
943678ba-814f-5b00-9e07-2d6a2d01607b | note | – – – – – – – – – – – – – – – – –
803b88e2-196a-50e1-9cb0-87b8584d3f02 | note | RESPONSIBILITY - SE/PE
5b0d4144-1c08-5d30-98d9-a4b1dcf4e9b2 | note | – – – – – – – – – – – – – – – – –
4df19a08-c265-548d-ad0f-189c00667985 | note | VERIFYING DOCUMENTS - This ITP
0c34ec48-4094-5f80-85a8-a64f6abe0c34 | note | Date Completed:
| checkpoint | 5.5 - Waterproofing membrane application
fcdfc4e7-6d5a-5d35-9c27-997b5055d3ef | note | REFERENCE - 691.09 (c )
810ed977-ba61-54e6-938b-40570274e0fd | note | – – – – – – – – – – – – – – – – –
51a9081d-1987-5e52-bcae-e4e37197385e | note | ACCEPTANCE CRITERIA - Placement of preformed sheets shall commence at the lowest section and proceed to higher sections, so that water does not flow into any joints during service. The Contractor shall ensure compliance with the manufacturer's recommendations for heating method, duration of heating and temperature of oxidised bitumen adhesives.
e2ca7d9b-93a8-5fdb-ba7b-379b12de46b9 | note | METHOD - Visual Inspection
2a6063c0-a903-5d20-9535-7ed306d766aa | note | – – – – – – – – – – – – – – – – –
c88be4a1-9961-567a-9ff4-36faf5ff6bf6 | note | FREQUENCY - When applicable
84610b04-60c6-510f-bfd7-c48ddf6a1115 | note | – – – – – – – – – – – – – – – – –
bd6f6de4-b908-5c87-bef4-941d25771d61 | note | CATEGORY - IP
5525fe08-5d1b-5ea9-9fd6-35b766c3fa26 | note | – – – – – – – – – – – – – – – – –
b43a825f-df61-5bdf-bf5d-a0b50af91936 | note | RESPONSIBILITY - SE/PE
4ea1c404-a368-541c-82e8-d495fdef584e | note | – – – – – – – – – – – – – – – – –
887ada97-8867-5c69-a126-acf99b5fdc3c | note | VERIFYING DOCUMENTS - This ITP
8d7043ac-a2cd-5f4c-a0e2-06c2df8222a0 | note | Date Completed:
| checkpoint | 5.6 - Waterproofing membrane application
d9d29d4f-9516-53a9-abdd-48d000722eac | note | REFERENCE - 691.09 (c )
56291d00-fb92-5e8a-89c7-bebba007063c | note | – – – – – – – – – – – – – – – – –
39d585ca-7bfb-566a-8702-43ffab4acdde | note | ACCEPTANCE CRITERIA - Self-adhesive membranes shall be rolled out and manual pressure applied immediately to ensure satisfactory adherence to the concrete deck.
348852cd-f166-507c-a424-0db54bc5f4d5 | note | METHOD - Visual Inspection
b2733d5f-5dd2-50c2-8c24-b303445a2b54 | note | – – – – – – – – – – – – – – – – –
c20a5c37-4bea-5a72-b3be-a1ee69b3181c | note | FREQUENCY - When applicable
7cecfc28-db91-5a30-9a8d-3023354469e1 | note | – – – – – – – – – – – – – – – – –
abe088c1-00fe-5ffc-8c65-3dd645d3474d | note | CATEGORY - IP
68b6e2d0-dc7e-5fca-b971-407bded5b925 | note | – – – – – – – – – – – – – – – – –
a5cb2c59-9ddb-5288-bbc5-e7c6a610583b | note | RESPONSIBILITY - SE/PE
da073856-d554-5490-a93c-b55a5d07f254 | note | – – – – – – – – – – – – – – – – –
b1bbdfcb-cb70-5220-aef0-9bd4dfd8a2cd | note | VERIFYING DOCUMENTS - This ITP
88af5f95-e040-54fd-9401-9e63f95e35f5 | note | Date Completed:
| checkpoint | 5.7 - Waterproofing membrane coverage
e5461363-a138-57ba-907a-8427b9cfda3c | note | REFERENCE - 691.09 (d)
328bcaba-1ac7-55fa-bde8-70614cecee4f | note | – – – – – – – – – – – – – – – – –
24204e89-e599-5038-bd9b-b4ccf1635a2a | note | ACCEPTANCE CRITERIA - Coverage of the waterproofing membrane must be continuous over the entire deck area, including service bays, between parapets, medians and kerbs. The layout of the waterproofing membrane shall be detailed such that water seepage beneath the membrane is prevented,
d45ea03f-b813-576a-8fd1-87fde1cfbcf1 | note | METHOD - Visual Inspection
eca5c1cd-f336-52c4-9211-233e211221f3 | note | – – – – – – – – – – – – – – – – –
d42527b1-f03a-5a82-97d7-149eb671ea99 | note | FREQUENCY - When applicable
4439f640-c68e-5d06-b677-c347950c8a6f | note | – – – – – – – – – – – – – – – – –
cb33c131-f62a-5ae4-86c2-d62156ca0501 | note | CATEGORY - IP
10bb935d-5dc4-5b1a-93c9-ceb10b2df247 | note | – – – – – – – – – – – – – – – – –
b93d44e8-b814-5290-9ee3-3956d8dbf704 | note | RESPONSIBILITY - SE/PE
b92174e4-6091-574d-9cae-4e4390f5c6a0 | note | – – – – – – – – – – – – – – – – –
befd4d9f-c14d-5cf8-bd7d-aac1def7a23a | note | VERIFYING DOCUMENTS - This ITP
6d5a1a5b-4029-576c-bf86-4c112b8abe7f | note | Date Completed:
| checkpoint | 5.8 - Waterproofing membrane coverage
758412ea-8c10-5e38-be1a-c9a9345409dd | note | REFERENCE - 691.09 (d )
5af724b8-4c5b-509a-8f04-bb6cc15c32a4 | note | – – – – – – – – – – – – – – – – –
a15a00cd-9349-5daa-9646-78e74b4f145f | note | ACCEPTANCE CRITERIA - At the junction with vertical concrete surfaces, the membrane shall continue up the vertical concrete surface, terminating at a level 10 mm below the top level of the proposed asphalt surface.
5d47ff47-e8e5-5f9f-b67d-184df4a2dee3 | note | METHOD - Visual Inspection
54d9c385-749b-5297-a75f-3c224cfc75cc | note | – – – – – – – – – – – – – – – – –
dcfc03c5-6e5c-5926-a30d-9cdb3eedcdb2 | note | FREQUENCY - When applicable
6d0e38b1-e50c-5f5e-860f-638b45a55375 | note | – – – – – – – – – – – – – – – – –
ca8608e2-e51b-59b1-8f55-e25ebd9c3f31 | note | CATEGORY - IP
89e45bbb-aa4c-5739-ac32-4490dfd9dd33 | note | – – – – – – – – – – – – – – – – –
75aa2b00-f4ef-5d5c-aca8-3a8291ea84e1 | note | RESPONSIBILITY - SE/PE
bc24fa3c-fde2-590b-a6d2-db01c6447cba | note | – – – – – – – – – – – – – – – – –
49a1fdb1-2751-5f96-b15d-65d200f7f044 | note | VERIFYING DOCUMENTS - This ITP
0772e8e6-2bb5-5ed5-ba00-986a3b9e4f7a | note | Date Completed:
| checkpoint | 5.9 - Waterproofing membrane coverage
6f456984-b6ef-573e-be6f-f003fce30bb5 | note | REFERENCE - 691.09 (d )
331610b2-7945-5483-800d-889cf44a3b36 | note | – – – – – – – – – – – – – – – – –
c8f3b857-2d9c-560c-8258-3732f3b12166 | note | ACCEPTANCE CRITERIA - The waterproofing membrane shall be applied with minimum side and end overlaps of 100 mm and 150 mm respectively.
f69da80c-6fd1-5592-98e3-ee182f238a46 | note | METHOD - Visual Inspection
2a57c87d-106b-532a-b3de-ab0df69107e4 | note | – – – – – – – – – – – – – – – – –
f5650bab-ade6-572b-95c7-42476ee017a2 | note | FREQUENCY - When applicable
107520f8-7ee7-5cd8-bea5-ce4400ee21fd | note | – – – – – – – – – – – – – – – – –
d400d518-3277-598b-b184-460aa7a17f96 | note | CATEGORY - IP
16689f73-f602-5ad8-9335-363b189ac012 | note | – – – – – – – – – – – – – – – – –
8a638e9b-b79c-5185-ab74-18fca019a582 | note | RESPONSIBILITY - SE/PE
559ea325-9c70-5ddb-8788-77d22e470ae6 | note | – – – – – – – – – – – – – – – – –
9dfc6bcd-c0f0-5d88-9e8b-3404f7fa1249 | note | VERIFYING DOCUMENTS - This ITP
509b1b8d-1beb-5e45-8759-57ba3c7bb2f1 | note | Date Completed:
| checkpoint | 5.1 - Tack Coat
4cb26a72-3ee9-533a-b9fe-bd7f35789986 | note | REFERENCE - 691.05 (f)
511aa82d-1764-56d5-943f-228075439451 | note | – – – – – – – – – – – – – – – – –
8292d6a1-189a-5ca9-b97b-339d7163f1ab | note | ACCEPTANCE CRITERIA - Tack coat shall be applied as required, in accordance with the manufacturer’s recommendations to provide adequate adhesion of asphalt to the waterproofing membrane over its service life. The tack coat shall be applied uniformly to the waterproofing membrane
23e1c5ae-23a8-50a4-a7a1-99dd31e8ad00 | note | METHOD - Visual Inspection
9d2f239a-c7fc-59a3-9382-01bc3779174e | note | – – – – – – – – – – – – – – – – –
1c72c6ea-01f5-5a69-bb23-20a5c168ca5c | note | FREQUENCY - When applicable
3b412336-3c4c-52e2-97f2-29b9f316021c | note | – – – – – – – – – – – – – – – – –
9faad36d-e103-5bd6-a1c5-ea7764927707 | note | CATEGORY - IP
9a965849-b8bf-564d-bbb6-f97eba0476bb | note | – – – – – – – – – – – – – – – – –
248fd980-12d0-5344-ad5b-5ff0c435f391 | note | RESPONSIBILITY - SE/PE
338ae3e8-dc19-5b67-8da6-9d420f699565 | note | – – – – – – – – – – – – – – – – –
5f6b3431-0e93-5ec8-93c3-cbb6e0b25110 | note | VERIFYING DOCUMENTS - This ITP
8bd69f07-0a09-5d2e-8ba9-e85fb97cace8 | note | Date Completed:
| checkpoint | 5.11 - Drying and curing
746a5a04-8a78-55b8-b53e-dbec58db46e9 | note | REFERENCE - 691.13
2145ae7d-6076-515e-a90a-6fa90210b869 | note | – – – – – – – – – – – – – – – – –
6b9a2d93-98c0-5a8c-a3e6-5465bc3e133e | note | ACCEPTANCE CRITERIA - The Contractor shall adhere to the manufacturer’s instructions regarding drying and curing requirements, and overcoating time intervals, for the prevailing weather conditions.
67f443d7-0333-587d-9588-5e61e216ebea | note | METHOD - Inspection
7f1ab5f4-c2c4-5fb4-9c0c-d443f3aaff56 | note | – – – – – – – – – – – – – – – – –
01bd4ddb-521a-55e8-a362-ae9b2469772d | note | FREQUENCY - When applicable
546f0126-f97b-58e0-9940-219c5619c4a4 | note | – – – – – – – – – – – – – – – – –
a7ed359e-1fc9-5cdd-97c6-108d2245cd57 | note | CATEGORY - IP
6289ca30-5201-5b2e-89ce-4491770b7bc6 | note | – – – – – – – – – – – – – – – – –
d9cb70cd-c706-5a93-8063-6816be9d245d | note | RESPONSIBILITY - SE/PE
385e14ec-b920-51c0-8480-77c19f7f67f2 | note | – – – – – – – – – – – – – – – – –
e803ae87-b440-5ae5-8ed9-726b76e11d8f | note | VERIFYING DOCUMENTS - This ITP
19d0841a-4af4-5c9b-a2b5-d21145d5e50e | note | Date Completed:
| section | 6 - Post-construction Activities
| checkpoint | 6.2 - Subcontractor Product warranties obtained
5f6d4d2c-bf1b-54ce-97b1-9b95ef9abadc | note | REFERENCE - 691.05
9c5cfd5a-2469-59e0-8635-884e1a1cc3fd | note | – – – – – – – – – – – – – – – – –
63464d89-78f9-5b52-9cf1-7e9565d2ee26 | note | ACCEPTANCE CRITERIA - Product warranties obtained and are compliant with 691.05
2c3f4038-a28f-5811-9c15-92051eee9cd8 | note | METHOD - Inspection Document Review
f492aa48-794c-599e-94d4-57e8dc7d6cd9 | note | – – – – – – – – – – – – – – – – –
43df31c2-7a82-5ea0-825b-ec8b5d21fd0e | note | FREQUENCY - Once per Lot
da9676b0-ae0a-5bf9-8199-2b38411e14ca | note | – – – – – – – – – – – – – – – – –
b523f155-a71b-5cf6-81ff-6f47dbbf86bf | note | CATEGORY - WP
4915ff4a-17ff-5b60-9964-c3a4cd9af458 | note | – – – – – – – – – – – – – – – – –
a3d13c52-0793-5ec0-8dea-7e89f9b4fa29 | note | RESPONSIBILITY - SE/PE
03ed346e-0d76-5902-8081-dc36c58f4b16 | note | – – – – – – – – – – – – – – – – –
1b95e6ba-227c-5397-9862-035dca6cf978 | note | VERIFYING DOCUMENTS - Copies of product warranties
87f57319-3989-5b79-a9e8-3abafe5667b1 | note | Date Completed:
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
4910e81a-5dea-5bff-97c3-ec03381d8e8a | note | REFERENCE - MRPA Quality Management Plan
08978740-52e2-5913-91dc-5046f1b2750b | note | – – – – – – – – – – – – – – – – –
4f236242-5c36-5283-b576-794940c39e87 | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
7164b3db-fc19-5d22-9c52-e54dc12fe09f | note | METHOD - Document Review
b9506bf4-24d9-5b94-9b5c-571708aae4a9 | note | – – – – – – – – – – – – – – – – –
5ffddfea-d8dd-5521-bacc-7b634f672143 | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
2e590f39-f5ae-59c6-a654-7a0f86598406 | note | – – – – – – – – – – – – – – – – –
d2d2e556-9aaf-5a36-8d03-d5dd4b87fb32 | note | CATEGORY - HP*
b7fc7882-0d43-5131-bccb-4121b760172a | note | – – – – – – – – – – – – – – – – –
a3102b2e-7b7f-5350-bdec-52416741c773 | note | RESPONSIBILITY - SE/PE/SPE
b4226b13-2508-5a75-b370-d10153a009ee | note | – – – – – – – – – – – – – – – – –
7e8ea7c3-5054-58b3-a83e-8ac997f149e7 | note | VERIFYING DOCUMENTS - This ITP
b396923b-b87c-5308-9c79-41b458f70e21 | note | Date Completed:
| checkpoint | Final Inspection
ae63d049-2120-5cc9-87e3-a8a8a8cdfe56 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
0ce98d29-6219-563a-80ea-6048f3603a91 | textbox | Name:
95c643f8-d5c6-5583-9326-19649ce6fdf4 | textbox | Position:
9abcc4b6-9b63-5890-accb-b060db6215cd | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-CIV-CAMMS-Ausnet Conduit Bore Rev 0 | itp | ITP-CIV-CAMMS-Ausnet Conduit Bore Rev 0 |  | ab7ef30d-9104-43f1-81a8-85781b69b393
| section | Referenced Documentation
| checkpoint-no-value | 1 - Referenced Documentation
a26e48ca-b62c-51ca-8723-7ab126cffe3e | note | Document Title: Ausnet Conduit Bore
30c8b4d5-4fe9-5295-adc4-47450294b45c | note | ITP Description: Ausnet Conduit Bore
9c308e30-e4b0-5a8d-b7af-3b006641a8d9 | note | Discipline (e.g. CIV/STR/RAIL: CIV
91b37566-1552-5d58-8638-cde75f95933b | note | Revision Number: 0
e41ffb9f-bd40-5eaf-ba98-7acedefbf593 | note | Revision Date: 29/07/22
dda31d16-1b1e-5b22-85cc-2f96ce9ce57c | note | ITP created by: Michelle Lim
99dbeb7e-3aeb-50ef-90d3-381b7810fa29 | note | ITP approved for use by: Aldrin Guinchoma
| checkpoint | 1.1 - Non Dependent
bc9916e0-20c6-59a2-87b6-1615ffd8efdd | note | Reference - IFC Drawings
| checkpoint | 1.2 - Non Dependant
0b9f5de9-b824-5e8e-9daa-e5f959b24395 | note | Reference - AS 4799-2000
| section | Preliminary Works/ Materials
| checkpoint | 2.1 - Electrical Conduits
2343d2fe-2fbf-58f3-a170-3631321a40fc | note | Reference - IFC drawings
da2bd1ba-c775-5868-a730-b8caf76a41de | note | Acceptance Criteria - Conduit crossing railway to be heavy duty PVC 150mm Id/180mm OD Grade PE100, SDR 13.6
6964125a-a17b-57b2-84af-b8d4d02f7345 | textbox | Reference:TeamBinder Material Approval Number:
29590f1f-f2bc-5bde-b12d-3a36f06a6472 | note | Method - Document Review
e6b2bc50-f99b-5912-8303-16252bef7a44 | note | Frequency - Prior to commencement
fd5d8759-b47e-5c94-b6f8-58e28e24d3ae | note | Category - HP
92bc40ef-ca10-5d7b-b318-4b26bb007cf8 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Grout
75c1fa61-6377-5e69-8af8-4659f9163703 | note | Reference - IFC drawings
91bc332c-dd2d-5b3d-8967-3b49547074e7 | note | Acceptance Criteria - Cement based grout shall be flowable, self leveling and non-shrink
93c779a7-ea85-576e-a5d1-eb8db5984434 | note | Grout of the minimum UCS of 2Mpa at 28 days shall be used to fill the abandoned conduits
850d6ace-d689-570b-91f9-ac9d9bd4cc53 | textbox | Reference:TeamBinder Material Approval Number:
9b099fd6-ff6f-5cf4-ac7f-3055ee1d302a | note | Method - Document Review
9c5d70ed-4d41-5f33-87ae-825287748566 | note | Frequency - Prior to commencement
8735742d-2fa8-5080-81a5-f1777e90bbd3 | note | Category - HP
05b7f63c-347b-567c-b685-c82a50a43146 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminary Works/ Procedures
| checkpoint | 3.1 - Check that current revision drawings are being used
99777746-3b6b-54a3-bdbb-5ad15a4628cd | note | Reference - IFC drawings
81a0fcc0-4396-5285-a79b-d6fa80110be2 | note | Acceptance Criteria - Drawing revison must be confirmed with the design manager
2defc7ca-d5fc-5ab8-b41b-a9fcc8176091 | note | Method - Document review
79e90360-dd08-530d-b5b5-c04977b7b082 | note | Frequency - Prior to commencement
f29d6c3c-0a33-56f9-9361-350e1492698a | note | Category - HP*
b2f0579c-60ad-59ca-ae41-4b2db75f9614 | note | Responsibility - SE/PE/SPE
d6e9d375-5f03-5a22-8960-ca2e2df1acb2 | note | Verifying Documents - Design drawings.
3feb5f7a-9a2a-5c70-b6c8-79e073e96022 | date | Date Completed:
| checkpoint | 3.2 - Grouting Procedure
9b1e0cd3-546d-596b-92b3-ba8e567ce26c | note | Reference - IFC Drawings
05580c18-232e-55aa-9fe8-68ec00e9c65f | note | Acceptance Criteria - Volume of abandoned conduit to be calculated to determine amount of grout to be used. This should match the grout delivery volume.
2db1fbcf-be2c-57bb-a754-95c08875e417 | note | Method - Measure
211d07da-bd4a-5128-8ffd-82449ca17a82 | note | Frequency - Prior to commencement
5056b12d-511a-53d5-a0d3-02a9bc9bbde4 | note | Category - HP*
04bc4de1-a3b9-55ea-bd47-96122e0b65fd | note | Responsibility - SE
9a1906bb-0cfa-587d-902c-5eb73958eb8b | note | Verifying Documents - Calculated grout volume used Grout Volume
d3faaeb5-1f84-5558-8a1f-3e8fa4fded80 | date | Date Completed:
| checkpoint | 3.3 - PE Welders Qualifications
6b508fe2-235e-5971-97ab-47d23ec6882b | note | Acceptance Criteria - PE welders are to be pre-Qualified
ab0b19f9-77e8-539e-8e18-99440450cf9a | textbox | Reference:Teambinder Hold point release number:
72bba6b6-e4c5-5670-b070-aaf34aa7ae41 | note | Method - Document review
c73974b3-ecba-5fa8-84e8-7b573c53de2a | note | Frequency - Prior to commencement
9c03e138-3a75-5f29-a298-4095de4a49c0 | note | Category - HP
23c5c349-ea8c-521d-9726-da87ebea809d | note | Responsibility - SE/PE
8ed28ce6-9254-52a8-a0ba-cf3f32d5c972 | note | Verifying Documents - Teambinder approval number
b7e8583b-73e1-54a5-9da3-7b52dd9e2ac3 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-out
4d6d00cd-1a01-5b44-9945-0dd8607a6d9f | note | Reference - IFC Drawings
f249b66e-5d8f-5788-8871-e67414f2d4f4 | note | Acceptance Criteria - Set out line and level of drilling works.
02910dca-3067-5f70-82b2-0523a89d3633 | note | Survey to mark out existing services.
b0c5b90a-4c27-5b3c-9c43-b3d4694a941c | note | Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
69deff03-f4a2-5285-bb54-5b86de012ee1 | note | Method - Measure
91f73fa2-671d-5a44-82b3-485aa0e8f5f9 | note | Visual
c6f46eeb-67b1-53a0-a4c2-bcee233a7f9b | note | Frequency - Each element
02905057-281d-566f-968f-1c7cae60bf66 | note | Category - IP
3f05978f-76bb-58ed-95f9-27ac8619ab35 | note | Responsibility - Surveyor
126ec3c0-349d-5607-9068-6df1851d725b | note | SE/PE/SPE
a1e9020e-a5bd-5fe8-966e-f984c6c8c817 | note | Verifying Documents - This ITP
d2086e41-55f3-534d-9576-c20ca3859822 | date | Date Completed:
| checkpoint | 4.2 - Draw ropes
6d3e25d7-025e-560b-8480-0acf9a509a32 | note | Reference - IFC Drawings
73bda0f5-5ae9-5693-806c-87416ccc126c | note | Acceptance Criteria - All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
cbd2af81-e826-5ba5-bbd5-3dbd8fcccabf | note | Method - Document review/ Visual
26212195-c1d9-5fb1-9766-41f88c2dd09d | note | Frequency - Prior to commencement
84b81427-ee06-5a10-8160-08eb8ee9e258 | note | Category - IP
a832c7b7-007a-5650-a43b-df369ddd79b7 | note | Responsibility - PE/SE
49499d03-92e7-5ebb-9ee7-f9a5568bb9c6 | note | Verifying Documents - Material compliance certificate
bc6c886e-89fe-5bc1-b561-dcf84650d8e7 | date | Date Completed:
| section | Construction / Installation Activities
| checkpoint | 5.1 - Conduit welding
c3b66b0c-5a24-50d8-8f23-8ebaa0c35d91 | note | Reference - IFC Drawings
671ee394-5dc3-5bf9-bfcd-965aca18d7c0 | note | Acceptance Criteria - Joints are to be butt welded.
fb84f130-03eb-534e-a955-20be59a268ae | note | Weld map to be supplied and identify unique joint numbers.
e87e08b8-b525-50f5-ada6-a48cd434f201 | note | Butt Welding records to be supplied.
db525af3-789a-5e09-9fc6-153329a1b2b1 | note | Method - Document review
e07eaae2-e233-56c0-94dd-fd703e7fb766 | note | Frequency - All Joints
6e99f878-ca45-5faf-86f9-38cb9ddc036d | note | Category - IP
2fb0f31f-5cc7-5864-81ba-78322019f59a | note | Responsibility - SE/Site Supervisor/Survey
bd29357b-b484-5b32-9454-870ce5308fb5 | note | Verifying Documents - Sign ITP
40b1a6f4-32c8-53e9-a817-ab803ae438f2 | note | Butt Welding Records
8dac538c-6b2c-5ba4-8720-d05d1aa50e01 | date | Date Completed:
| checkpoint | 5.2 - Drill rig setout
4098c95a-3395-5fcc-a36c-9add0022ab74 | note | Reference - IFC Drawings
7d7c5e7e-d616-55bc-84b1-2880e0694fed | note | Acceptance Criteria - Location as per current Drill shot plans
a64fceae-7330-5ca4-a8d6-953006539b35 | note | Method - Measure
10cd76ca-f90f-559c-8ff9-d1449e4a1d18 | note | Visual
90920f94-88c3-5b67-b189-480585af60f1 | note | Frequency - Prior to commencement
80aeab88-0469-596e-8b7b-80f8b6387cba | note | Category - IP
9ad8a52c-8435-5db3-8468-311ab2c10cdf | note | Responsibility - SE
d322de80-7236-5626-8d09-1e7422253894 | note | Verifying Documents - This ITP
28999c4f-5db2-544d-b7f4-aae8207efa5d | date | Date Completed:
| checkpoint | 5.3 - Installation of Pipeline (Trenchless method)
11a7b036-bbee-544c-9b00-139e1d0ae2f4 | note | Reference - IFC Drawings
b31777de-dcf3-56a0-9a19-cc38e40d8c7c | note | Acceptance Criteria - Drill to be installed as per the survey setout.
ab965dd5-897a-54ef-b784-0411f61a3288 | note | Bore longs to be supplied.
72f20a54-b9fa-57b1-b2ac-e21047fc946b | note | Method - Document review
7693b7d1-ef10-501c-a9c2-b3d4b3732e23 | note | Frequency - During pilot bore
2e3312e3-9d41-5849-a95c-1fea3b9a483a | note | Category - WP
c6b0fb06-fddc-5358-a26f-d59a948ad16d | note | Responsibility - SE/Site Supervisor
73e9d0e3-4f5c-5763-af0e-984a32dbe654 | note | Verifying Documents - Bore logs
fa82014c-5479-5938-8afa-e3e877e461d0 | date | Date Completed:
| checkpoint | 5.4 - Plug pulling
67f5321e-e58b-521d-8eae-2c9c05f05f90 | note | Reference - IFC Drawings
448d2c5c-314a-5475-97d7-1c648eae780a | note | Acceptance Criteria - Mandrel with 90% of the pipe diameter to be pulled thrugh each conduit to ensure the conduit hasent been compressed.
d10307e6-3b31-5cf0-b366-e5858a6bb272 | note | Method - Record and Review
5560ebe8-4de2-5e36-b15b-e252a20519f2 | note | Frequency - All Pipe
a6fbabd7-bf5e-580b-af0a-a01135cc6b9f | note | Category - HP*
7bf43e90-98df-527b-9154-fb601e10256d | note | Responsibility - SE/SPE
890a60bf-8cfb-5fb1-87c3-8f9df3b7072b | note | Verifying Documents - Sign ITP
53c6dd31-ef14-518d-8464-fdf775628d66 | note | Visual of pipe pull pictures.
1640019e-6d9b-5d24-bd9e-a90b077ecb29 | note | Subcontractor Test Record
58f5e790-4501-56e2-91cd-31f4a1756074 | date | Date Completed:
| checkpoint | 5.5 - Draw rope
b60f5da9-c484-5def-b9e9-bd848fc23ff7 | note | Reference - IFC Drawings
2db17aed-df56-5901-97d3-0dc4ba4c5b44 | note | Acceptance Criteria - All draw ropes must be continious between shafts and have 2m slak in the shaft.
f77b750d-6503-5bf3-865f-93b0983ef0c8 | note | Method - Visual
4703f643-d2f9-55fd-90ec-b0c366ce3931 | note | Frequency - All Pipe
784f2e5a-bb8c-5386-bb57-682cbe52f1de | note | Category - IP
4ddb5923-708a-52b8-bfd4-8e53553979be | note | Responsibility - SE
2d192fba-4d1f-5c96-83fc-d926e03cb8fd | note | Verifying Documents - Sign ITP.
017d9f02-16e0-5095-b649-7944757032b1 | date | Date Completed:
| checkpoint | 5.6 - Mixing of grout
33bca5f9-8c19-548f-9c1e-0843ed57fa40 | note | Reference - Grout TDS
e3174267-d1d6-50f4-91ec-7ae1fe41da08 | note | Acceptance Criteria - Mixing and proportioning of grouting to take place as per Technical Data Sheet provided with product.
7d017c6c-cd41-55ce-afff-3c833e68be01 | note | Only whole bags of product shall be used.
3e7838de-f2b5-5102-9f72-a4bc59952aec | note | Grouting shall not commence when temperature is below 5 degrees Celsius or above 35 degrees Celsius
c57a6119-8002-5cc5-a4c7-775dedbc23a9 | note | Grout mixture should be mixed adequately and free from lumps
e0a4d736-3cd9-5744-b7af-61cab2096126 | note | Method - Document review/Visual
02bf9f2f-4570-567d-afbe-28e330e303ee | note | Frequency - All pipe
5dd592b3-4981-5454-8583-1f19572746b8 | note | Category - WP
484bd8b6-481d-5b7c-b187-0b5bbad93164 | note | Responsibility - SE
c3407150-afe6-5fac-b05f-5a8fc72d052f | note | Verifying Documents - Sign ITP.
467f5742-9aab-5f32-9a0d-fa8444800224 | date | Date Completed:
| checkpoint | 5.7 - Clean surrounding faces and remove excess grout
7d159a76-5ccb-573b-bcf9-4e1fed385f2f | note | Acceptance Criteria - Area free of excess grout and spillage
44756d61-da04-5d1f-a669-e3ccce601413 | note | Method - Visual
b95396d1-334c-51c4-8c10-58a34f14c510 | note | Frequency - Each shaft
5eee597c-182d-519f-a626-f06a1ec9c7c7 | note | Category - IP
4b3167c9-cf1d-50d3-879a-e5d03bc233ef | note | Responsibility - SE
b848cd5f-223a-5d60-bbec-97cb8482ae19 | note | Verifying Documents - Sign ITP
1baffb45-d45c-59ae-b08b-ebb98944ec4a | date | Date Completed:
| checkpoint | 5.8 - Curing
c9e83b02-cda0-5a4f-8eae-22f910b11ffb | note | Reference - Grout TDS
4751d2aa-1264-5796-94ae-f4db9f43bea6 | note | Acceptance Criteria - Curing in accordance with TDS
8446b435-dca4-5569-b002-4dcc0731e346 | note | Method - Document review
39b2d2fe-5f02-560e-a968-af210f08a29b | note | Frequency - All pipe
a4aca60f-2214-528e-bda0-47fe8d83ac1e | note | Category - IP
f39f19b0-54b1-574a-86e0-4aa03c6b0860 | note | Responsibility - SE
ba62e377-a91e-5c52-bbab-14dcdadffbaa | note | Verifying Documents - Sign ITP
55a08de3-95ff-5a85-b1ba-0d433d677674 | date | Date Completed:
| checkpoint | 5.9 - Auditing
be960d36-283c-5a4c-be82-7c453f88155b | note | Reference - IFC Drawings
38a2d4c6-15e3-5ab9-968f-ca7fa741f20a | note | Acceptance Criteria - Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts.
594c9a1e-da59-576f-ba81-8d3943958334 | note | Method - Record and Review
ea463cb6-db40-5926-9b78-5b93ff4a426a | note | Frequency - Alll Pipe
224fa96f-e660-5c4e-b6c6-359ce014a9e3 | note | Category - HP*
e4c878c2-1584-591d-840c-7671f7965be9 | note | Responsibility - SE
7b68420c-237e-5107-96d5-0b38fcbe484b | note | Verifying Documents - Sign ITP
8c85c847-9d91-5aea-be5c-a1edfc54d0ad | note | Auditing Report
70fa33c0-fa63-5290-b98b-e4e5d97d6902 | date | Date Completed:
| checkpoint | 5.10 - Reinstatement
986a0bdc-25d6-5888-b53b-a702b80a2957 | note | Reference - IFC Drawings
e88720c5-dfa4-5968-b168-c01b060d14b0 | note | Acceptance Criteria - Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified.
40624830-4c05-5bc6-b15f-7dc3609c2e4f | note | Method - Visual
3c18a4f0-5b03-56c6-82a0-a3fe6fc19287 | note | Frequency - Each shaft
69948410-d81b-5fe9-85d5-35f6165c513f | note | Category - IP
3e2bc950-50d9-567b-807f-ccb1b71b1aff | note | Responsibility - SE/Site Supervisor
4b9b6efc-ac94-5535-a08e-1ef5750f70c6 | note | Verifying Documents - Sign ITP
aa62c1e9-16d8-587c-98f8-14aec683f009 | date | Date Completed:
| checkpoint | 5.11 - Subcontractor ITP
c1b762ff-1a2e-5df1-b4ec-fd671dd3729d | note | Reference - IFC Drawings
564480c5-0d56-5cbe-ad97-ef798bde1201 | note | Acceptance Criteria - Acceptance and closeout of subcontractor ITP
c0389e95-f04f-55a5-bbc3-f47146a7810b | note | Method - Document review
5dfead6d-e45f-5af8-9b3f-183e9ebaf84c | note | Frequency - Each element
1146556a-28c6-5c6b-84e2-492fc57c0e6e | note | Category - IP
a298705d-17be-57ed-b2ef-afb11a8d12ef | note | Responsibility - SE/SPE
1b9ec0e2-cac7-5c2b-b1b6-63b865f70fd5 | note | Verifying Documents - Sign ITP Completed
96db5df5-7f33-588b-9ea1-e7c7872f41f6 | date | Date Completed:
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 - As-built Survey
348b2a25-5039-597c-9699-2aa5d2a30ee0 | note | Reference - IFC Drawings
a9d7fa61-bb74-54fc-8231-537a2d4e9b34 | note | Acceptance Criteria - Survey as built report to be compiled.
9a095dbc-ba18-5551-b2cc-0cd949ad2606 | note | Borelog obtained from subcontractor
cf4e5a54-ec7e-5fc5-a3fe-e1ab49731c18 | textbox | Autocad and PDF reports are to be supplied to:
0f2c3fa9-23cc-57a7-b494-75aba86ea02d | note | Method - Document Review
81fb97b8-995e-5363-8073-3a52cf383ab7 | note | Frequency - Each element
9e9a1be8-4a74-5bad-befe-ee7280db1635 | note | Category - IP
a6c4ec19-0368-54f0-bbdd-1740c092f052 | note | Responsibility - Surveyor
610ee70e-50a0-5857-8aad-8709b47697fb | note | SE/PE/SPE
065d12b0-da05-5bfd-b234-981e87aa3ba9 | note | Verifying Documents - Survey As Report
12c70a45-bb1f-5047-b37f-1f6748b6e3be | date | Date Completed:
| checkpoint | 6.2 - Red-line / As-constructed IFC Drawings
c4e1e79c-55f6-56a0-aa00-3bfdd7afc265 | note | Reference - MRPA Quality Management Plan
016e02f4-3aba-5a66-b2a6-169febb19de8 | note | Acceptance Criteria - All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
65d9017c-bfda-5921-9b43-babf38628b85 | note | Method - Document Review
f5f691a9-f57d-5d5e-a9a1-5d7d7910b352 | note | Frequency - Once, after construction of the design package
444930bf-552f-5370-aa75-2dea667f9582 | note | Category - WP
34c105df-0c16-590b-a086-ae04a82ee1bf | note | Responsibility - SE/PE/SPE
87844509-bd55-5f80-a132-2fe060fe870e | note | Verifying Documents - This ITP
fecc2c39-f85f-5f31-ba6d-773102a51b5e | date | Date Completed:
| checkpoint | Final Inspection
709657aa-b366-535c-8439-714812c4f713 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
cc5c7067-1a4e-5d4e-878c-c6a4c50777be | textbox | Print Name:
2d9c35a5-327f-5d55-8ddf-e84f32b9c8b5 | textbox | Position:
e29a3a6e-769b-517a-a391-fbd26a88c279 | date | Date:
| checklist | ITP-CIV-CAMMS-Rail Delineation Temporary Fencing Rev 0 | itp | ITP-CIV-CAMMS-Rail Delineation Temporary Fencing Rev 0 |  | 5270c116-1c67-40b5-8e34-ca23d9c50e84
| section | 1 - Referenced Documentation
| checkpoint | 1.1 - Referenced Documentation
0086e2b0-069c-589a-9be8-ffff175534b6 | note | Reference - IFC Drawings, L1-CHE-STD-005, L1-CHE-STD-025
| section | 2 - Preliminaries-Materials
| checkpoint | 2.1 - Concrete
09c1327a-14b7-5d30-9e4f-2b0d44c01611 | note | Frequency - Each Mix
7f42c11d-e549-5e8a-a2cb-3378f5b5ede6 | note | Acceptance Criteria - 32MPa concrete to be used as per IFC drawings.
6f09df4d-6fd3-5751-97bf-b925c7b93f23 | note | Reference - IFC Drawings
e5584958-1795-500e-9983-0b92ba017ff7 | note | Inspection / Test Method - Document Review
95c7e122-33b9-5aa5-bfe4-f33eaf68e18d | note | HP
ce5a7141-ae67-5066-9f75-d2ef4d9140c4 | note | Responsibility - SE/Site Supervisor
412a98b8-2967-5cb4-8448-614ec314ab0e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Steel components
163316ae-2a48-53f9-b716-a782f6800f6b | note | Frequency - All elements
f1df3b1d-11d2-564f-a653-a30d8522ab62 | note | Acceptance Criteria - All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250
7985a2e7-99a8-5554-89ad-a41ac7d1d649 | note | Reference - IFC Drawings, AS41000, AS1163
4be22392-8002-5946-a48d-b249d02f57e3 | note | Inspection / Test Method - Document review, Visual and Measure
faaef798-13dd-51c1-806c-c750a31db5c5 | note | IP
761fde72-2897-5272-81de-2495ff94b6eb | note | Responsibility - SE/Site Supervisor
f789bffb-9db8-5405-920f-4f533fe109ef | date | Date Completed:
| section | 3 - Preliminaries-Documentations
| checkpoint | 3.1 - Excavation works
1b981071-dc0b-5dfc-b34f-ab4747cab6a6 | note | Frequency -
2ba09585-1337-54bc-9213-e39f142c743b | note | Acceptance Criteria - Excavation for post foundation must not undermine track and comply with PTDT requirements.
6d1c9ef3-ade0-56b3-92fa-f84b95bc3f18 | note | Follow asset owners guidelines for work around their service.
75b96e0a-5c62-5791-af6f-273775b2e82f | note | Excavation must use Non Distructive Digging in the rail corridor
c8d3de30-4275-5c0c-ab66-126fe514dc82 | note | Reference - IFC Drawings, L1-CHE-STD-005
a092c613-d32b-5c58-b5a9-50661a135510 | note | Inspection / Test Method - Visual
982b54c3-a0b9-5bd0-90cb-793f0f91d498 | note | IP
ba1447fe-e6b8-539a-b40d-50b7e737dab7 | note | Responsibility - SE/Site Supervisor
b9aa6b10-a341-5192-bc6a-e3b7422b8cdd | date | Date Completed:
| section | 4 - Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-out
33dfe856-f3c6-54c7-8e2f-daa109bb89c9 | note | Frequency - Each element
55cd3fed-ec0f-5726-b22d-b0cc194c92b0 | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays
fb87e010-88b1-5d95-b57d-13f4767e19fe | note | Offset checked against the running edge prior to installation of posts.
978ea0ca-24e0-55d6-be9b-11f219218b76 | note | Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
3aefea3a-379f-5ed7-8971-ea72c58219af | note | Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
3111979b-40ac-58ff-98b3-41f2f0d792a0 | note | Reference - IFC Drawings
fd6b2e49-8a3f-51c0-8ea7-758c5a819481 | note | Inspection / Test Method - Measure,Visual inspect
620d5139-ada9-50bb-ad4b-fb4c136d1dd0 | note | IP
e6bec084-f1d8-50e3-8a13-f38ee96e2352 | note | Responsibility - Surveyor, SE/PE/SPE
cc004d4b-f8da-52fd-a71b-87e846ba37a7 | date | Date Completed:
| section | 5 - Construction / Installation Activities
| checkpoint | 5.1 - Ground Conditions
3b647908-ad1f-5138-97cb-9c07bf0f995a | note | Frequency - Each post
014de3ca-70d5-5024-946d-e6b16d0dcf19 | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
5d503c7f-fe35-5418-b162-f7b4da3317cd | note | Reference - IFC Drawings
015207d6-4103-5ace-86b5-2631625fe05d | note | Inspection / Test Method - Visual
3d33ff62-2377-5851-afd9-6b4c45abdcbe | note | IP
f125ab25-a848-5ed7-8626-2a0e9a132c80 | note | Responsibility - SE/Site Supervisor
2dca586f-780e-5a82-9464-3cd6e089f878 | date | Date Completed:
| checkpoint | 5.2 - Post Foundation
efbee789-59b3-5e81-be4e-b85286d6dbd2 | note | Frequency - Each footing
758a26d3-3759-5fe7-90cc-914a2e714284 | note | Acceptance Criteria - Up track (Alongside central pier): - 300mm Dia, - 2000mm Depth, - 2700mm Typical Spacing
8bf885f8-5906-5a7f-a69e-5d708a83cef6 | note | Up track (Outside central pier): - 300mm Dia, - 800mm Depth, - 2700mm Typical Spacing
58d8f381-f8db-5729-acea-384d0deced60 | note | Down track: - 300mm Dia, - 800mm Depth, - 2700mm Typical Spacing
6162211d-6853-5d34-b78d-cc140ade841f | note | Gates: - 350mm Dia, - 1400mm Depth, - 1350mm & 4000mm Spacing
53d8b440-a441-5108-98b8-4216cc55b442 | note | Reference - IFC Drawings
22c9d0ab-759a-5578-a4ad-f2471910d875 | note | Inspection / Test Method - Measure
53160ea6-6be8-56ca-9108-9fda89a25a30 | note | IP
ef38cdb4-0a89-504c-a2a2-cf1885f81ee8 | note | Responsibility - SE/Site Supervisor
1b827650-a385-5aae-945c-13bc5e4407f3 | date | Date Completed:
| checkpoint | 5.3 - Post Installation
6879d564-32d7-537a-8c91-6a279cbbe56f | note | Frequency - Each post
ef9a6d0f-f836-5e7c-9a21-f85263fae68c | note | Acceptance Criteria - Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
b7ff9f17-187a-54de-bd12-ef5091eb8aa4 | note | Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
34ce9ac0-b48f-5fa0-aa81-6d8261e4ec3a | note | Maximum post spacing to be 3.1m
326cc269-9341-58b1-bcf5-de497b000c4a | note | Two spans at 1350CTRS at the end and at Refuge bays.
6a8af9b1-34c1-5c24-acdd-7d87fdde5bc3 | note | Max. post height 1800mm above ground level.
ac562a8c-2048-56a3-b239-1621c82fc825 | note | Vertical Tolerance: ±20mm from the design line.
0e784094-747c-52ec-b837-1a616ee0520d | note | Reference - IFC Drawings, L1-CHE-STD-005
cc6f6ece-ce87-5c13-a6e5-692d239898b3 | note | Inspection / Test Method - Measure
c36e509d-350e-5704-88f4-cb17721fb240 | note | IP
30eaa3a9-5ca2-5698-bb46-48207b2da5a4 | note | Responsibility - SE/Site Supervisor
963ae305-28be-5f09-b696-9e7a75d16deb | date | Date Completed:
| checkpoint | 5.4 - Chain Wire Mesh Installation
470ab7db-2b49-5b02-9fe4-02b3b333e558 | note | Frequency - Each element
3f0a80b4-ec1a-5df5-9044-740d00b3628c | note | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
8315e12e-9191-575e-b5a7-7e120c08451f | note | Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
a1963063-b220-58d8-af20-6354e3e91caa | note | Reference - IFC Drawings
24e24fa4-1a60-5e7e-926f-e74dc01bb110 | note | Inspection / Test Method - Visual
b530c5ab-ff4f-5c1b-89b1-5f1de151cdeb | note | IP
2f55e57f-79f9-501f-ad09-218d99a5bd74 | note | Responsibility - SE/Site Supervisor
d68013c9-1a71-5296-bd68-d22d2ea49c5a | date | Date Completed:
| checkpoint | 5.5 - Bracing
160a48ed-146e-5ede-88ad-dfb7d85c1a2b | note | Frequency - Each element
72f490a6-fdc7-5a68-b6f7-1ad95fbc200e | note | Acceptance Criteria - 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
9a35470b-0d07-589d-be00-ee119a12c6c9 | note | Bracing to be installed on both sides of the fence at the fence corners
823c0a41-ffb2-5b15-b081-f88bb856b31a | note | Reference - IFC Drawings
c60ae786-ae67-5b21-8088-200ff7d41fb5 | note | Inspection / Test Method - Visual
ebb5177b-7c2a-5174-9eeb-9c870a1c0e7e | note | IP
77979268-1229-55a9-8d55-37d9cba713b6 | note | Responsibility - SE/Site Supervisor
b38a3644-2fd0-5ceb-88d0-6f08a87c8647 | date | Date Completed:
| checkpoint | 5.6 - Refuge Installation
4ae06e8b-772b-52ef-8d69-3688e2b65f20 | note | Frequency - Each element
e76a52b9-fa80-58c4-8041-b854be1496c4 | note | Acceptance Criteria - Refuge Access to only open from track side.
b87f7d02-caa0-59a3-b292-4c783b9259aa | note | No chain wire mesh to be installed at refuge access.
879f7031-7787-5232-8719-f1ec8b8582f9 | note | Refuge Access to be located maximum 10m along down track and staggered from up track refuge.
70b41c8a-2abc-5a05-87a9-194eaa26edb3 | note | 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
7179bcef-ccff-5ca7-8e87-f1ebeffce2f8 | note | Reference - IFC Drawings
1288de59-4202-570b-961c-856e89717308 | note | Inspection / Test Method - Visual
32b970e0-f7e5-5784-a288-b81d8a2f9d61 | note | IP
a654e461-afbf-5895-baa7-92e8a8ba9d2d | note | Responsibility - SE/Site Supervisor
48369f25-0869-5c59-816e-c17790fc45c6 | date | Date Completed:
| checkpoint | 5.7 - Refuge Signage
673c09e5-862e-5d2c-98ba-6413e340a8d9 | note | Frequency - Each element
e5000628-cad0-5684-9b91-87b70291c218 | note | Acceptance Criteria - Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
d9388aaa-5621-538a-ae34-b3ddcc1877fb | note | Reference - IFC Drawings
79acefc3-1e3a-5e2d-996c-8ef68c740bd9 | note | Inspection / Test Method - Visual
562ff33e-5c20-5f4e-8605-12fb6b095923 | note | IP
447301e4-8c61-5df6-8d57-660875cfe6de | note | Responsibility - SE/Site Supervisor
6fcb30fe-1d2e-54c2-a7ad-bef5aef2b176 | date | Date Completed:
| section | 6 - Post-construction / Post-installation Activities
| checkpoint | 6.1 - Fence Height and Track Clearance
47a120ce-b7f4-5aeb-8dee-4e13d065602d | note | Frequency - Each lot
cc40d2a0-a501-50ac-99dd-416b2503904e | note | Acceptance Criteria - Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
76338719-8d67-5316-924e-11c7d1e7978a | note | Reference - IFC Drawings
47871499-9815-5917-8b1e-f62d11d6a238 | note | Inspection / Test Method - Measure
2162d943-628c-57b2-b695-d9436c46ee02 | note | IP
9e3e266f-0a95-59d9-9026-87dc8414f9de | note | Responsibility - SE/Site Supervisor
0a653097-3e0f-5e7d-b7ac-f6f5fb3b3314 | date | Date Completed:
| checkpoint | Final Inspection
2d995c11-3f8d-511c-867e-e8a9a98b9228 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d5b9598d-5fe5-5e89-a571-b32eaa3c0aa3 | textbox | Print Name:
33204aeb-f0cc-5abf-9a3a-03a18e6f926a | textbox | Position:
1ef87d97-d9b6-544d-8671-f34297db17f9 | textbox | Work Completed On:
354353d3-bfb4-5f39-87d2-c14a100016b6 | date | Date:
| checklist | ITP-CIV-CAMMS-Subgrade Preparation-Road-Rev 0 | itp | ITP-CIV-CAMMS-Subgrade Preparation-Road-Rev 0 |  | 056f96e2-dc65-47fe-b608-8999badde738
| section | 1 - Referenced Documentation
| checkpoint | Referenced Documentation
fdd34b50-5bee-5c94-9914-df7b370d3641 | note | Document Title: ITP-CIV-CAMMS-Subgrade Preparation - Road
ab267e6c-7650-5e93-9dbf-96f5e0bbcc51 | note | ITP Description: CAMMS-Subgrade Preparation - Road
764f618d-938d-58f0-99b0-1ca1e9a31b2c | note | Discipline (e.g. CIV/STR/RAIL: CIV
df31e635-9d41-589d-9265-71b3e6459160 | note | Revision Number: 0
2f8fe6df-e5e4-5680-9069-a4cb4de5ada1 | note | Revision Date: 18/08/22
6a71a6a5-00a0-5172-9236-b2060d717c38 | note | ITP created by: Victor Mira
c30e8323-5eef-5d01-92b9-41ad9e8c2443 | note | ITP approved for use by: Aldrin Guinchoma
| checkpoint | 1.1 - Non Dependent
572cb9d4-49e6-5a9b-a096-1198ec098c1f | note | Reference - VicRoads Section 204
| checkpoint | 1.2 - Non Dependent
d3c18019-2bd6-547b-9265-3b4e03e27f38 | note | Reference - VicRoads Section 173
| section | 2 - Preliminaries-Materials
| checkpoint | 2.1 - Non Dependent
| section | 3 - Preliminaries-Documentations
| checkpoint | 3.1 - Non Dependent
| section | 4 - Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-Out
81d017f2-83e0-50ac-8697-820dc8e11a3b | note | Reference - IFC Drawings
094d26e4-b1f2-5bc9-a834-dd3bd3011609 | note | Acceptance Criteria - Area has been set out in accordance with the drawings
a84eb765-f230-59f5-8a8b-c14c3cf72b4c | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
1c19ea32-8c09-5d3a-8cb0-a152b6fd1d04 | note | Method - Verify
9f77a5ca-5bd6-5ff5-a9c3-0c06aa317d44 | note | Frequency - Prior to commencement of excavation
a04909b2-0a2e-53c3-bdb6-96be987a5234 | note | Category - IP
0ac88d0b-9f5b-5473-ba22-909cba1bf212 | note | Responsibility - SE/Surveyor
8bcee0a5-9891-55b4-9a27-fb2ae9150c8e | note | Verifying Documents - This ITP
708c77af-8ce2-556d-8132-2ea1c35c1356 | date | Date Completed:
| section | 5 - Construction / Installation Activities
| checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
b6dcd196-318f-5e9e-95f6-528d4e10ebf6 | note | Reference - Section 204.06 ( c) Section 204.06 ( e) IFC Drawings
83aae0a6-6b9d-5fec-9da1-d405f9dc08e6 | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
5441e849-479c-5468-9fc5-7f2571b2728c | note | In situ material within 400mm of cut floor level to be consistent with IFC Drawings
47245560-ba28-5f1d-849c-221aa56de566 | note | Assigned CBR ≥ 2.5%
b53f8812-ed83-5133-9370-65e49b464bf3 | note | If parameters are met, rip and recompact to a depth of 150mm.
b79a242f-8dfc-5d88-b7cf-86ce8e7b4d3b | note | If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
cc2a3a72-70dd-5922-95c1-53083222d9d1 | note | If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
bcfa0011-b1bb-501d-907f-2907772b26d6 | note | Attach: Laboratory testing Verification:
da42f828-f9b9-568f-a12e-809a15e7e728 | textbox | Enter: Type A fill Lot Number:
4a550785-31e2-56cf-aeed-b4d18c534e5c | note | Method - Verify-Document Review
c69312be-39c4-5c49-ae2c-6dd6f7608d1b | note | Frequency - Each lot
09d988db-9b1e-5185-8957-8711101b590c | note | Category - HP
e0ba499a-eb1c-52d3-b789-58616ecf0d2b | note | Responsibility - PE/Nominated Authority
7bc4a220-0ec9-5e67-a9b8-aa53d01460d5 | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
27c5e308-63d8-510d-8939-a0d47a3fa6ad | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Material classified as silt
5f7f50f0-3b75-5b21-97f4-efd508481491 | note | Reference - Section 204.04 b)
469c2365-6ac9-5e80-8681-473ff9c3ccd2 | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilization to the satisfaction of the Nominated Authority
56adb619-49e2-5c15-99c7-ad29bbc13538 | note | Method - Document Review
265d3519-2b6e-5b10-b5aa-1d97c830b2f9 | note | Frequency - Prior to commencing
d77edc05-21a8-5d90-8e00-923e689a1ee7 | note | Category - HP
65ed1060-76dd-538c-9910-dea9036a3729 | note | Responsibility - SE/Nominated Authority
554f3a84-aafa-53fe-a12d-ac4b7a534425 | note | Verifying Documents - Superintendent satisfied with Stabilisation
bb5187bd-8536-5c0c-878f-b74c686d7edf | note | Signed ITP/ records
0b706f09-71ac-50a9-8393-8258e89b4355 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
dee7a647-b8a8-5c46-a2a2-53512bd56c4c | note | Reference - Section 204.06 f)
0e5faf74-19ff-55d7-9f44-1361a0039134 | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
a6045b83-144e-539d-bb05-39c30462286b | note | Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
da9e087e-80ac-55b9-a791-2176fd2e8e9c | note | Method - Site Inspection/ Document Review
8d9e4cb0-89d7-5d3b-9839-e5064017dfed | note | Frequency - Prior construction of the regulating layer
e9ff3405-2bef-510e-9d06-503be0fa2255 | note | Category - HP
f15bba90-6677-549a-9fa8-736c4681bbf5 | note | Responsibility - SE/Nominated Authority
ca74c18e-6ce5-51ab-b25a-b214115d432a | note | Verifying Documents - This ITP
b76e13ba-472e-58eb-8f8e-051ade86f4cb | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Unsuitable Material
f5762e6a-252d-5eea-a2db-f91ce8194480 | note | Reference - Section 204.07 d)
2d8c7b7b-5242-51ec-bc74-810eb899b011 | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
2e55e64a-0592-58f2-90ef-d880e3357df7 | note | Method - Visual inspection
ba3acae5-437e-5c7a-823d-bf7fe454fca4 | note | Frequency - Each lot
e805fba9-b73c-5889-93dc-7873391449ef | note | Category - HP
a93032c6-432f-5120-9c4d-bd14ee36fead | note | Responsibility - SE/Nominated Authority
7847bd56-52d8-5851-8856-1e86bf5ae369 | note | Verifying Documents - This ITP
867ba0a7-b5dd-5983-9ce9-638ef9fd7653 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Groundwater
cbd39376-812f-5ad9-88ab-cf40dd2e2f80 | note | Reference - Section 204.06 h)
16826619-2e9e-5a6b-94e2-2ca05cb27231 | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
c313b280-406a-503c-a5ca-aa6c1d9d5e2f | note | The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
fecb422e-a636-55b9-b651-7bbf22db4632 | note | Method - Visual inspection
ecc65a18-98c4-5a57-87f3-f39c1cb0dcae | note | Frequency - Each lot
03637807-2b0f-5112-b385-7a6901407618 | note | Category - HP
732134d2-8b75-516d-9042-69013f68a0d4 | note | Responsibility - SE/Nominated Authority
75cc0c13-1248-5a6f-8d2f-86ea12b1c56f | note | Verifying Documents - This ITP
87ed565d-5667-5fc8-82e6-ab7d02efaad6 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Cut to Fill Zones
bf6b3ac1-5281-5ac0-9228-b30e7bf5c304 | note | Reference - Section 204.06 g)
cfe6cad4-7059-5ac7-b604-54d8e36e2b40 | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
e202154c-b981-54b6-82de-9c3127b9d306 | note | Method - Site Inspection
d7e538e8-3e4d-540a-9e2c-b2312586febd | note | Frequency - Each lot
a869b10c-6b40-53f9-a38e-ea74afe250ee | note | Category - IP
2fcddaa5-9edd-50a9-8d49-66c0d8e6db66 | note | Responsibility - SE/Site Supervisor
edebc9fb-77dd-56d6-9f4e-fd14a0ab6555 | note | Verifying Documents - Sign ITP
da315dfc-0586-5ba8-8d2a-88d31f806972 | date | Date Completed:
| checkpoint | 5.7 - Proof Roll
abf33bb9-5fdb-52cd-a325-38f69546d39a | note | Reference - Section 173
edcf178a-e26a-505e-bdb6-04d483689d17 | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
bb3f8019-1054-5077-9023-b6bea4ca4eda | note | Method - Visual inspection
ab015910-2658-5966-9f78-9430a0c9002a | note | Frequency - Each lot
9197be12-d19f-5ca4-8c0b-2793d62b017a | note | Category - HP
721ce0dd-a573-58ba-b3a7-0bed70e49167 | note | Responsibility - Site Engineer/Superintendent
858d2eaf-723f-58f9-88bd-a8e7d31c6607 | note | Verifying Documents - This ITP
15334f87-3bba-57ce-9354-d62f7906da93 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.8 - Compaction Testing
c4ad0127-7c06-58ed-9b14-e0966936395a | note | Reference - Table 204.131
7817aa3c-2b86-53af-ac52-86202633a9fb | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
486ff726-b40e-50bf-8c26-d3f03704efdc | note | Scale A: Characteristic Density Ratio 99%.
bed677cd-45bc-5d6e-8fea-9e8a4c22eea9 | note | Scale B: Characteristic Density Ratio 98%.
0a20e21f-53bf-50fc-99c8-1b6e1e4daced | note | Scale C: Mean Value of Density Ratio: 100%
7d019dd5-e702-55dd-b40d-7e17bffd6b51 | note | Attach: Compaction Test Result:
2e93ad84-53e8-5395-8579-329be8a6989f | note | Method - Document Review
bb4d8816-26e3-5ece-92dd-da1fc2d82908 | note | Frequency - Each lot
5cb56ada-7525-5db0-86d6-7347774ae057 | note | Category - IP
5981f34e-1749-5d76-87e7-cc4a156c0b3a | note | Responsibility - PE/SE
1069cd4b-e880-5d80-b897-b497b1058913 | note | Verifying Documents - Test Records
5d4c9c17-7ed4-5b58-863c-a36b0fe3280f | note | Lot Register
abfb48e2-30ee-5ce5-8a15-4643e493bc4d | date | Date Completed:
| checkpoint | 5.9 - Post Compaction Material Property Testing
b45cb912-a745-50f0-99f9-419966923399 | note | Reference - Table 204,041
7efff24c-2cbb-5003-a4d4-00ec772d2ddb | note | Table 204.141
c6e90238-95e2-52c1-8e53-3332287cc525 | note | Section 204.14 a) or b)
4a5626d9-7a29-5a06-822a-9b047b44bb93 | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
59d8ebfe-d528-58fe-9ba1-ff374ef887b1 | note | CBR ≥ 3% and Swell ≤ 1.5%
4a121581-1950-5778-963c-7afc9c8aa41e | note | Max Permeability = 5X10-9 m/s
16e87b2a-5606-59fc-9f9e-0bc80ee6742c | note | Grading: 75.0mm 100%
2a79fc1b-91bc-51e9-b37b-8e7654657f75 | note | 4.75mm 40-80%
5c5e41ac-ab43-50ce-a834-098fba7aec4d | note | 0.075mm 10-40%
e0e04acd-d21b-5da0-8422-001f1bcfb05a | note | Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
54f43dc4-d61e-5deb-b7a1-2c88a6da3da7 | note | Scale A:
bb54881f-31a6-560a-b137-e07ee16258a9 | note | CBR & Swell
2bbef769-31e0-5dbe-841b-2e5c100e1105 | note | Initial - 1 Lot Test to determine Assigned CBR and swell
220cf4e9-6b0c-5f86-b531-aaba0e96a20c | note | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
43c95da2-2ab1-5629-96b4-7e150a56f278 | note | Max Permeability
b54215d6-d076-5363-bf89-bf15189da42a | note | Initial - 1 test per 2 lots
da86e7a7-8756-592f-8491-b2c2c39ecf7f | note | Reduced - 1 test per 4 lots
e90f33ae-e6e8-57f9-95f9-392dd261aeb3 | note | Grading:
2794d8c7-c096-5fbf-b622-2b7f263e3583 | note | Initial - 1 test for each lot tested for compaction
2a49c024-6491-505b-8902-d67ee2ae748f | note | Reduced - 1 test for every second lot tested for compaction
aac3a73a-8baa-54c4-ab24-985caf32c94c | note | Max. PI x%Passing 0.425mm & PI
c75076a8-2a1b-5088-9607-58ef54990484 | note | Initial - 1 test per 2 lots
9d3065a2-ce4c-520e-87dd-e7b82cee1119 | note | Reduced - 1 test per 4 lots
909b5e97-a84c-5b1e-b54d-b7eaa1019676 | note | Scale B:
f866ab87-ba8a-5b2e-bedd-531a910c9e04 | note | 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
97a335c2-6d17-51d2-81c4-9e8ef2384e54 | note | Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
0b3bc9b4-2ca1-56c3-8eac-f13a5829ef26 | note | Attach: Post compaction test results
f9aaf5f2-5dba-5f0e-85d9-3486c0edce20 | note | Method - Review Document
678fc9c9-eab9-5093-8bae-f6c8b14e7b62 | note | Frequency - Refer to Section 204
848d26ab-608d-5759-994b-4dae07155655 | note | Category - IP
82e17378-040f-592b-96df-64c2d608cc51 | note | Responsibility - PE/SE
e0408a22-efe3-572c-a576-03e026050efb | note | Verifying Documents - Sign ITP
57a1a3a5-c322-5ff0-9fd0-90b260e39b68 | note | Attach Material Property Test Report
abb08515-506d-5c6e-8edd-ac2c7b5b5c9e | date | Date Completed:
| section | 6 - Post Construction Activities
| checkpoint | 6.1 - Survey Conformance
464c3684-c41d-5314-a509-a757a3761280 | note | Reference - VicRoads 204.03f,g and h
0f2f5917-a610-5d09-b8e6-652c2d1ada58 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
e8c67308-c717-5ae7-81dd-0d5688013dc1 | note | Level tolerances (Scale A):
d4d13d9c-0b54-5d2d-bf9a-7e684c277185 | note | Range x = +5, -15mm
2908c60a-5f2a-524a-962e-c5cceb4e5f73 | note | Max S = 12 mm
390b3bde-dde7-5445-8bdd-fff98e2f3a7f | note | 80 measurements per lot
f1dc11f8-6efc-50d4-b559-1f2dfb7d1489 | note | Level tolerances (Scale B):
d0460f13-2049-55ef-a39a-2ffaa261f1ba | note | Range x = +5, -25mm
1209f24a-70be-539e-b723-5dae8eeb6c76 | note | Max S = 15 mm
198a14e2-b0de-5204-8733-cb99dc3cf5d1 | note | 40 measurements per lot
a4b6d4ba-ffc1-509e-b0c2-dd6cfa2c1c5e | note | Level tolerances (Scale C):
d7ca8de2-9be4-53d4-90df-4ad3cecba1bc | note | Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
a1d616de-d64a-50b2-9875-8dc0bd2caa9e | note | Method - Review Document
c1da78a0-f4e4-56ad-8dd3-c72b1f7eec71 | note | Frequency - Each lot
2e8ad31e-a545-5118-8035-b6f4f41f050d | note | Category - SCP
870df477-1571-52a4-af26-deb4d2c3421e | note | Responsibility - SE/Surveyor
60635c4a-7dc2-5a58-bc8d-8a3d0ad7f781 | note | Verifying Documents - Sign ITP
5852b3d7-7d40-5f69-a650-fcb00a90e866 | note | Attach Survey Report
5d76aa78-6e65-5d90-9109-175b99668729 | date | Date Completed:
| checkpoint | Final Inspection
e398a81e-d8ce-5518-90b1-dfa0ba52d31d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
86040a30-b8ac-5ca2-8179-61fe3a18a4a2 | textbox | Print Name:
e359971c-b909-5749-88fe-75b132d667e1 | textbox | Position:
552a64ae-cf55-5aa0-ac73-f1082b1c619d | date | Date:
| checklist | ITP-CIV-CAMMS-Type A Fill - Road Rev 0 | itp | ITP-CIV-CAMMS-Type A Fill - Road Rev 0 |  | edb8489a-90f8-492d-ad04-69bd2b474d92
| section | 1 - Referenced Documentation
| checkpoint | Referenced Documentation
fa515f9e-725f-50f4-be1f-a6b2bc0541c0 | note | Document Title: ITP-CIV-CAMMS-Type A Fill - Road (Supply and Install)
97300609-12a7-5628-bdc9-4acf6f82efef | note | ITP Description: CAMMS-Type A Fill - Road (Supply and Install)
8734d226-5cc2-54e7-842c-e6bd4aa94f1b | note | Discipline (e.g. CIV/STR/RAIL: CIV-CAMMS-
88c0230b-74ba-53fb-a74f-612a6c03abe6 | note | Revision Number: 0
42ec91ab-4274-588a-852a-d85e0c89c4a4 | note | Revision Date: 18/08/22
9ad2ab18-80fe-5bc2-9a88-69329621b123 | note | ITP created by: Victor Mira
3bbb779b-ced0-53b0-a080-606bd8a2c886 | note | ITP approved for use by: Aldrin Guinchoma
| checkpoint | 1.1 - Non Dependent
018bec5b-629f-5969-8100-1e4c5529b396 | note | Reference - IFC Drawings
8cbdf062-1778-5cd1-a8ab-1bdc122a39ff | note | VicRoads Standard Section 176 (Sept 2008)
0c735927-5aa1-56df-931d-d58294b87d74 | note | VicRoads Section 204 (Dec 2015)
e438ad5b-24c0-53c6-bb70-2929e7257ec4 | note | Code of Practice RC500.20
674407cd-00b1-590c-962b-d62a428b746b | note | Code of Practice RC500.5
| section | 2 - Preliminaries-Materials
| checkpoint | 2.1 - Material Conformance
52961df4-f35e-5d8d-82bf-34d730d52a16 | note | Reference - Section 204.04 b)
2b84e997-c714-5362-9f95-282d970aae03 | note | Table 204.041
f17b8615-076f-554f-8675-ff64038d2b4c | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
608a3896-a8d7-596c-8ca9-4da4672c6af7 | note | • Assigned CBR≥%8%
e464fc1f-72d2-5a65-b593-44ed4d1dbca9 | note | • Swell ≤ 1.5%
2d679f7b-5d52-5854-8eda-0aafbbb2da10 | note | • Permeability ≤ 5X10-9 m/s
0a5eb090-42c7-5d1c-bc0f-e31a073c22f7 | note | Grading:
5f88c050-5e87-5579-857d-b9d1b035bdd5 | note | • 75.0mm 100%
3ae4cdd7-51ca-5616-9415-d04690a9e3fe | note | • 4.75mm 40-80%
6d63dda9-dba8-543d-a9e0-f0985b64a6c6 | note | • 0.075mm 10-40%
eeac30c5-2700-5c75-acc5-6ba749e43852 | note | Reference: Material approval in Teambinder:
cda2de01-6a7d-5f28-8d63-0f36fc87acc9 | note | Method - Document Review
d6121d7e-6b4b-5ca9-a452-1c50748a0e11 | note | Frequency - Once, for each material type
36ba39b7-95e1-5196-8164-087c2589eb83 | note | Category - HP
42edf10c-17f6-57f4-9c84-f7aac02872dc | note | Responsibility - SE/Nominated Authority
91575386-20e0-54b4-b069-1a864be914dc | note | Verifying Documents - Supplier Material Conformance Certificate
65b4a28f-3523-5468-990f-692107621028 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | 3 - Preliminaries-Documentations
| checkpoint | 3.1 - Pre-Commencement of Fill Works
fb7772ea-2928-5d64-abab-0ee9b87e1cff | note | Reference - Section 204.10 (b)
ec3730a7-01bf-5755-960f-3f4e1b23bcd2 | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
9cce999f-8537-54a9-abae-acf605fbd48f | note | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
81c14dc5-6a68-5f22-ade4-cbc5723ca03f | note | No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
24ce2e68-0372-52f6-add6-ee4eb9d97e6c | note | Reference: Subgrade Preparation Lot Number:
72e592d4-a744-5a52-b960-ce3f7dbd89ba | note | Method - Visual Inspection
b2f64a05-cffb-5566-aa65-28e05d141005 | note | Frequency - Prior to commencement of fill works
66dcfc49-21e5-5b0b-9a45-8c84d9cdfe58 | note | Category - HP
13565228-a81e-5942-8c99-5229585c694d | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | 4 - Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set Out
30c10061-aff5-5bc9-aa94-796e7d07b33f | note | Reference - Design Drawings
d7969291-daf8-5361-8143-e74dd381be04 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
3d48b9e5-abde-5723-941a-f5e4c9059610 | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
5258f66f-c674-5ad9-9712-5886318e988e | note | Method - Visual Inspection
fde88d89-17aa-5f75-a538-1e641c33e93f | note | Frequency - Each lot prior to commencement
38ebe156-645a-5099-9e5c-f3ae8675baac | note | Category - HP*
e2c3ab2d-6b12-5b78-b5ff-8d02acdef3d9 | note | Responsibility - PE
1334341a-5529-5ccd-9c25-b9a7fbfaf32f | note | Verifying Documents - Signed ITP, Lot Map
816184eb-104c-568e-a94d-de06a313982e | date | Date Completed:
| section | 5 - Type A Fill/Verge Activities
| checkpoint | 5.1 - Placing of Fill
10a30941-797a-5736-b71f-1d174ef825e3 | note | Reference - Section 204.10
46a51074-c20d-517d-a240-16d0b558d981 | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
24482d9d-703f-54e2-a8b8-6ae7925ac326 | note | Method - Visual
9c54fdcc-ea3d-55ba-b52f-4835b17783d5 | note | Frequency - Each Lot
7f36413a-813c-521b-b651-2c103157bf9e | note | Category - WP
ddf80980-2c39-5800-9501-c8dd434433d3 | note | Responsibility - SE/Site Supervisor
4f873408-d309-5ff5-998c-542e364fd02b | note | Verifying Documents - Sign ITP
8c36b90c-0958-598d-a959-7e727f65e2be | date | Date Completed:
| checkpoint | 5.2 - Test Roll
f4a061de-a12b-5084-8de9-640029279965 | note | Reference - Section 173.03
6eccbb57-8df9-5a8e-8c4a-555d3e5987c8 | note | Section 204.12
fbe291ce-3e8c-5377-b11f-08143e04a3a5 | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
3599d283-f2fa-5c96-b4e5-c23465d3e320 | note | Method - Test Roll as per 173.03
6c992841-fee6-51b2-a3a1-32051004a40f | note | Frequency - Each Lot/Layer
4edbbf9b-4847-569d-81a9-d9abebd8b03d | note | Category - HP
400b3a64-12e9-5cbe-97ac-db2f2b596b27 | note | Responsibility - SE/Nominated Authority
34e5ad96-641b-55d8-a8a2-24376cc9bb90 | note | Verifying Documents - Sign ITP
5cbd3f60-fad9-5892-b980-c82082334a76 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Compaction Testing
b8b3c8d7-33a3-58d3-a561-3e1930458ead | note | Reference - Table 204.131
a1dbf03b-67cd-5e63-882c-6939e036cee2 | note | Section 204.14 c)
ef6c5d7e-8572-5283-a992-28f525bcefc8 | note | Table 204.142
e34d5ef2-1a8c-53e4-9578-d8ed9e73838a | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
e295bf20-dffe-5b11-87eb-278ad1f8b7ed | note | • Standard Compactive Effort
b12f097d-95e1-5bf8-a832-916d5ca5c44c | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
425d90db-9612-5760-b6bd-f7b2abe0aeec | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
2389cf5d-6466-526b-a6fd-0ec28abd17ea | note | • Compaction and Moisture content
ca29e7d1-606e-5b6e-a706-34843002790f | note | – Scale A: Characteristic Density Ratio 99%.
63acc9df-b7b7-53ce-ae4b-0950afec8641 | note | – Scale B: Characteristic Density Ratio 98%.
777c8f29-d538-5aff-94f4-75a846a360e0 | note | – Scale C: Mean Value of Density Ratio: 100%
caf2e321-d739-5cf9-a38f-59305f497b8b | note | • Lot size - the leser of one day's production or 5,000sqm
34ef067b-3014-5764-a326-41fb4eae33a0 | note | ATTACH: COMPACTION TEST RESULTS
a720b536-e8fb-58ff-af18-e2db5f08069f | note | Method - Review Document
2fb8878a-b625-5104-b78d-2b0da93eb7c3 | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
2d8e7252-3e96-5b79-a7c9-cecffb02c606 | note | Category - IP
dce3259c-fb0b-5538-bf83-c4df9ac3673f | note | Responsibility - SE/Site Supervisor
553ac4b0-36df-50e9-82c7-104e7128387d | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
a1d675cc-fc87-505f-aae6-a37cc84b600d | date | Date Completed:
| checkpoint | 5.4 - Preparation of final surface
6d01447b-a809-5b49-9af2-7f6e86402e30 | note | Reference - Section 204.15, 204.03 (g)
e767c8a5-0078-5476-bb7b-7926409953e6 | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
41f83b44-5488-5334-8481-d901ed8e7365 | note | Method - Measure
69367945-9730-5217-96a0-204370fffeb4 | note | Frequency - Top layer
db8a951c-0e5e-5c3d-a387-76451ab7a69e | note | Category - IP
d8b8e5e6-d4fc-5027-a81b-ea5961c07630 | note | Verifying Documents - Signed ITP
edee2230-6168-54e2-be86-64039f426ab2 | date | Date Completed:
| section | 6 - Post Construction Activities
| checkpoint | 6.1 - Post Compaction Material Property Testing
bb0d89d1-f72f-56fa-bb92-16a96eac3fab | note | Reference - Table 204,041
4ba0990d-0700-5429-9530-e31d7f1c83b4 | note | Table 204.141
3d09453b-17b7-5880-9aea-b7ead27cdeb6 | note | Section 204.14 a) or b)
3495ea21-f51b-5520-8229-c695eb0982fc | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
8b9c3047-19e0-5b46-8ad6-2e964479af81 | note | ○ CBR ≥ 3% and Swell ≤ 1.5%
96daf3d7-a326-5738-8f56-e418b3ce3827 | note | ○ Max Permeability = 5X10-9 m/s
feb7e7a9-1c92-55d0-8223-39ca9ba5898c | note | ○ Grading:
5fa340e4-ff15-5779-bf7f-383eee7cdac8 | note | – 75.0mm 100%
9ab3deef-722e-5a2e-b455-8dcce7e3df30 | note | – 4.75mm 40-80%
829356d0-435b-5216-b154-d6d62db69c1a | note | – 0.075mm 10-40%
f7ee26ef-22c3-535d-8a5d-7804c59aeab6 | note | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
9f738045-ba9a-5e24-b806-69cedc1a0f19 | note
25504062-fe8a-5690-a0eb-38547679aea4 | note | • Scale A:
2a177682-bfe9-5906-aa46-ccc53e5a4f9c | note | ○ CBR & Swell
b4c410a0-a85e-5091-8bac-6d98f55272b5 | note | – Initial - 1 Lot Test to determine Assigned CBR and swell
a1173ecc-851a-57da-9381-0effdde57a1d | note | – Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
8c3d11e2-6b56-528d-b00c-fc2e871d9f72 | note | ○ Max Permeability
74c505de-bbc7-5273-b506-62746af86cec | note | – Initial - 1 test per 2 lots
d6c83e8a-ac42-54c0-80c1-2b7b81a2fcba | note | – Reduced - 1 test per 4 lots
6d9cd051-887d-5067-bbc0-fd96db1ce0e4 | note | ○ Grading:
46f33495-9e1a-5fac-9f82-073e283b5521 | note | – Initial - 1 test for each lot tested for compaction
79608768-053c-5bfd-8049-cde5900b9910 | note | – Reduced - 1 test for every second lot tested for compaction
5f3929d6-dad3-57d1-95d2-95f1894678c7 | note | ○ Max. PI x%Passing 0.425mm & PI
1ab1c814-37fb-5d08-9f92-33705982d8a5 | note | – Initial - 1 test per 2 lots
193ee824-1799-5758-b303-4f7723f48ed7 | note | – Reduced - 1 test per 4 lots
098bac24-c5cd-5bc1-bf48-e1d25ee4703b | note
d7279bfc-b393-5cfa-ab42-7160757a8942 | note | • Scale B:
86a07eef-1877-51e5-ab87-608df36ad50e | note | ○ 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
28b3d773-0acf-5f5e-92ba-1178e00303ea | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
30484dac-ef41-54df-be37-b2d52f2989ab | note | Attach: Post compaction test results:
af3528b8-d553-5b59-a0ed-04d6698192db | note | Method - Review Document
5bc2f759-b240-56f4-9729-ffdcaf912423 | note | Frequency - Refer to Section 204
e8c7de5d-064f-53b5-9497-c5bd5514f29e | note | Category - IP
17d676e5-45e6-5a7b-9ada-7246e5724141 | note | Responsibility - SE/Site Supervisor
4f155af7-dd4b-5401-a95e-7421be4560a8 | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
6743d660-3b85-5d91-af3e-205f6367606e | date | Date Completed:
| checkpoint | 6.2 - Survey Conformance
bf50e102-c79b-5e43-9ead-a105c4c57979 | note | Reference - VicRoads 204.03f,g and h
9dce3e4e-1270-54de-96fb-348b5c43dd79 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
ae38df25-897c-5211-84ed-8f3f20faff9e | note | • Level tolerances Scale A:
cf950a01-4114-522d-b232-659392494930 | note | ○ Range x = +5, -15mm
ec92f603-63c1-5ad7-9c6b-aa1cce517b56 | note | ○ Max S = 12 mm
6fb0b1b3-94df-56de-a37d-d50af6c924a7 | note | ○ 80 measurements per lot
4ca8d217-17f9-5e23-b2ea-567ab48749ad | note
58863008-f389-5761-b88c-f2aec5e8f9e5 | note | • Level tolerances Scale B:
da1a054e-c73a-5ca2-8952-d14a9f08a5fc | note | ○ Range x = +5, -25mm
4a7fe63b-8db2-5fc8-835f-f7176415f404 | note | ○ Max S = 15 mm
82f1e0b9-2d72-58b6-a143-c6cd3a2671d1 | note | ○ 40 measurements per lot
d8d3dcc7-5eab-52f7-8ccb-bc4fa9f60eb3 | note
836d5878-3366-5c1c-ae12-9e6aa995e2d5 | note | • Level tolerances Scale C:
eeb0db66-f235-5c61-a58f-01840c674f38 | note | ○ Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
f2420367-fc5d-5b83-8e4f-2025c87d0a56 | note | Method - Document Review
1f514e32-32b8-5d3d-8186-64697b9ac3cd | note | Frequency - Top of Type A/Verge
6a070776-b4e1-5a61-aa58-a915991d99ab | note | Category - IP
bb4f1859-acdd-56c6-be07-92c49dae9332 | note | Responsibility - Surveyor, SE/PE/SPE
2ea5f4a4-9b1c-5598-9135-f0ba09b51584 | note | Verifying Documents - This ITP, Survey Conformance Report
efa91caf-46e3-52e4-814a-eb557dff8193 | date | Date Completed:
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
c799b033-002b-5446-8331-dbdd44ff462c | note | Reference - MRPA Quality Management Plan
214394a3-4310-5345-904f-e4b3d5355fae | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
39144b33-71e6-5f50-bd53-1ac47fd79396 | note | Method - Document Review
17aa7abb-f4ef-58d5-aba4-81c2f9e26f39 | note | Frequency - Once, prior to closure of this lot / element / Work area
fa4f174e-e0a2-5337-8ed1-0fbe8c28359c | note | Category - HP*
94fc5723-8787-5651-b0c4-0276d3d06a31 | note | Responsibility - SE/PE/SPE
6f4190b7-97fc-592c-a29d-84b3c3218bf0 | note | Verifying Documents - This ITP
54372667-9ea5-58d7-9f6e-46de2b7e2a23 | date | Date Completed:
| checkpoint | Final Inspection
feaf9877-5850-5df2-9d17-a0caf19f37e9 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
e930627d-27ef-5029-8a23-ede9b15893fe | textbox | Print Name:
eb09d6b2-026f-5443-8fb6-736bd2eff34e | textbox | Position:
6e09ce7e-6aae-50ec-adbf-8cd2313eb441 | date | Date:
| checklist | ITP-CIV-CAMMS-Unbound Flexible Pavement Construction Rev 0 | itp | ITP-CIV-CAMMS-Unbound Flexible Pavement Construction Rev 0 |  | f744d3ee-8c8f-4d67-a40d-fdb4ba43a3d4
| section | 1 - Referenced Documentation
| checkpoint | Referenced Documentation
b55c62ca-d792-5c30-b0a4-165e6a9296ea | note | Document Title: ITP-CIV-CAMMS-Unbound Flexible Pavement
13f61ea6-3ac9-54c7-8d07-91a9066e6cbe | note | ITP Description: Unbound Flexible Pavement
91b15e8d-0d0b-5667-8294-4f4e79cfb9b1 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
793cf508-63f8-5dfa-9f91-19bbdbe8d3cc | note | Discipline (e.g. CIV/STR/RAIL): CIV-CAMMS-
c3cea942-d328-5d3d-9301-a38552e4b570 | note | Revision Number: 0
e02035c2-00ad-5a12-bc04-0339495ab972 | note | Revision Date: 06/09/2022
abe33643-1e73-5566-bd3a-285677a8a75e | note | ITP created by: Victor Mira
4f1461ef-2092-5ac4-a88b-9338ac36061c | note | ITP approved for use by: Aldrin Guinchoma
227fb451-4571-57fc-95ce-599f2b621019 | note | 1.1 - Non Dependent
36666f14-99f3-509b-8ce3-015e4a2b269e | note | Reference Documents: IFC Drawings
559a7b5a-6740-54f3-869d-fd62c4fae118 | note | 1.2 - VicRoads Section 173 (10/9/2008)
4fba219a-4678-5882-b5cd-987e808a70d5 | note | 1.3 - VicRoads Section 304 (13/8/13)
da660cb4-376d-519e-97f7-dcdc526ca729 | note | 1.4 - VicRoads Section 801 (19/07/18)
7130887a-d95c-5e6f-9d3a-dc7cb4e4656c | note | 1.5 - VicRoads Section 812 (13/07/16)
| section | 2 - Preliminaries-Materials
| checkpoint | 2.1 Crushed Rock Mix Design
68a902b3-c1e6-58de-8a46-20956b389639 | note | REFERENCE:
4751b681-53e9-50fb-9db1-f83c07a8cc8f | note | Section 304.03
8366ef5e-cc0e-5be9-8149-d293b9b30d27 | note | Section 304.05
ef8fd89a-7800-54f7-b587-5a28a61016f8 | note | Section 812.04
67800bb9-7a78-5310-a90c-6c024e688be7 | note | Table 812.121
ac927852-f881-5e43-a56c-1ca11bb27a13 | note | IFC Drawings
56367f0e-c33c-52c9-9d34-40e4e1747f63 | note | ---------------------------------
1fc216b2-a2c7-5b37-89b6-c99990ceb593 | note | ACCEPTANCE CRITERIA:
da489b47-34b2-5c45-b1fe-90c26f52f2e1 | note | All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
acbada30-6bf8-5bf5-ba43-018dbe1d3068 | textbox | Enter: Teambinder Material Approval number
099915b6-b0d9-561c-9bb7-92e54a1116d7 | note | ---------------------------------
3900d7b9-c07e-52fa-8f1d-86ae4e9fd37a | note | METHOD: Document Review
2101cb7a-99ef-5ec2-bfd1-cea79804647b | note | ---------------------------------
85b19f5a-03b1-510c-8558-23c4737fb7ad | note | FREQUENCY: Material conformance as per Table 812.121
b4a9dc93-de53-57c7-9561-921f67ffc044 | note | ---------------------------------
555fbab6-8e5d-57a1-91cb-1d352fa09110 | note | CATEGORY: HP
d9a34524-0503-5175-892a-1c2d2e3e6c1e | note | ---------------------------------
2d43b345-40cf-5d30-a968-821a51fa5092 | note | RESPONSIBILITY: NA
8d4cecf1-e86b-5dc8-be7c-63e2fa39f2f9 | note | ---------------------------------
b63fcff2-a5d2-500a-a79c-0d274b0342b4 | note | VERIFYING DOCUMENTS: TeamBinder Material Approval Number
d30a2296-79f3-5e6a-8161-e8b8d8bcf821 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | 3 - Preliminaries-Documentations
| checkpoint | 3.1 Subgrade Preparation
0a77fc9a-cd97-5345-8cff-4a6fc6d3d8f6 | note | REFERENCE: 304.04
9dcd28bd-0e21-52f5-a571-296f0ca43c53 | note | ---------------------------------
cb8fe355-79ec-5e91-95de-540868fc6533 | note | ACCEPTANCE CRITERIA:
94a030a0-8ac3-5b26-8c0a-981d645bfe6b | note | Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
ba45e699-1062-50d6-a60d-f2384b1e070e | note | Reference: Subgrade Preparation/Type fill Lot Number:
e65e0f0e-ac83-5c56-80fd-3e58620f803a | note | ---------------------------------
d76d8c23-44e0-5753-abed-0a5bd24e52a5 | note | METHOD: Document Review
d3d08d4b-4d83-5a85-9834-704cb4f24441 | note | ---------------------------------
72110011-8105-5b79-83ab-918691611c35 | note | FREQUENCY: Each Lot
8b0cfad9-5cc9-5e43-9116-cd31f46e6e47 | note | ---------------------------------
3355057c-9191-58fb-82c2-0e2e4c78d8ff | note | CATEGORY: HP*
ac4c4c19-812f-5c8f-b649-796ca7403866 | note | ---------------------------------
a041c668-9c95-5dbe-8ac9-a28267432740 | note | RESPONSIBILITY: PE
d52543bb-4727-57f2-8082-5dc5c53b9a26 | note | ---------------------------------
f454bbb4-6c59-54cc-9591-49abecd42a2f | note | VERIFYING DOCUMENTS: Underlying layer Lot number
778513dc-057c-5981-bec9-8982df6bb7d9 | date | Date Completed:
| checkpoint | 3.2 Select Scale
6d7cc770-950a-5318-ba93-7526a788e108 | note | REFERENCE:
9e0feb14-2d60-5d3d-9a30-684020a484ae | note | Project Requirement Specifications
345e0b14-ff5b-501d-95f0-bab4580add89 | note | IFC Drawings
c9ea8d1a-b337-558b-8992-b7b8af7bf17e | note | ---------------------------------
68266dd1-c597-515f-a440-08efd011da97 | note | ACCEPTANCE CRITERIA:
169bbf9e-dcf6-557a-bbb0-2ae098ea66ea | note | Specify site specific scale:
2ee37d7a-3f91-5504-8744-be908d03fb74 | textbox | Enter: Site Specific Scale (A, B or C)
27c5eb12-913d-5cef-a7e7-e6164acbdaf5 | note | ---------------------------------
6ccad292-f733-5c7f-ae80-818943703a86 | note | METHOD: Document Review
412ccf13-5431-5267-9990-7fa814d45626 | note | ---------------------------------
425894c3-d09f-5482-8cc3-3347d2a2b0f6 | note | FREQUENCY:
f26abbaf-eb6d-57ef-89d8-22b799a6dd2b | note | Prior to Commencement
d3083ceb-b2d9-5a35-868f-1f4e26ad6ff5 | note | Each lot
5c59ba97-8280-55a9-bc8a-66f0e3f262cd | note | ---------------------------------
4052575c-0a81-5592-b760-0dd21175a9cd | note | CATEGORY: HP*
96230fa2-a7d4-5cec-8deb-18f5a366fc1a | note | ---------------------------------
51aea4e4-e81c-58da-ac21-c24d8ed4e072 | note | RESPONSIBILITY: PE
07cc8e69-c803-5efa-9d6f-6b48a3c6d09b | note | ---------------------------------
1033ea59-d351-56e5-a79c-12094146064b | note | VERIFYING DOCUMENTS: Sign ITP
e1f4ea25-c5b1-55fe-a09b-c4843baac350 | date | Date Completed:
| section | 4 - Pre-construction / Pre-installation Activities
| checkpoint | 4.1 Survey Set-out and Lot size
5409ac50-a78f-5950-8b06-bcf37ce72cbc | note | REFERENCE:
4c19df48-11f4-531f-bc86-f6865ceb1c11 | note | IFC Drawings
cceac362-32e6-507a-ad53-4c37ca164790 | note | Section 304.06
170aa09d-0885-5d35-a47e-0c925a63c77b | note | ---------------------------------
f2536fbe-317f-5649-a038-213dd81753c3 | note | ACCEPTANCE CRITERIA:
b7a59640-6cd5-5d6b-8df2-cb035a3e1e2b | note | Lot size shall be the lesser of 4000sqm or a days production.
223d9cf2-cd4d-51dc-89cd-83caf06ecf51 | note | Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
77993d6a-47a9-5e11-9b74-2a0344b9ad6c | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
78862ad8-2c08-597d-b451-6f6913661239 | note | ---------------------------------
1b0127dd-e441-5bf3-9f28-d8afce054975 | note | METHOD:
03bbaece-49ba-51ee-a8b6-85409b1e8678 | note | Survey
5e8c7bc6-8b59-5370-8374-26540f992247 | note | Document Review
a7b4571e-e366-5365-95ca-a222693655f4 | note | Measure
d6fdc7cf-b8b2-5439-834b-ae4d475f04db | note | ---------------------------------
9d2cdf13-c855-5900-b6cc-a515aa229f1c | note | FREQUENCY: Each lot
4f354337-be00-58e9-accd-40b8cdfeee2a | note | ---------------------------------
1dc9dd2c-bb17-5487-9dd0-4c1d60bd872f | note | CATEGORY: IP
c79e69dc-90c8-539d-ae83-9e860a75283b | note | ---------------------------------
3612b60d-3a6b-5de9-bbb3-a9603110d6d1 | note | RESPONSIBILITY: Surveyor/SE
baad0808-19d1-5990-906a-37a6846bc62a | note | ---------------------------------
74f337a1-f617-587d-830b-44ef45fff1c2 | note | VERIFYING DOCUMENTS: Sign ITP
6b29f2dc-d36c-5639-ace0-7e28e720bacf | date | Date Completed:
| section | 5 - Construction / Installation Activities
| checkpoint | 5.1 Crushed Rock Delivery Dockets
e888277f-1119-5abc-bde0-3647bfbd6740 | note | REFERENCE: 304.04
9b32beba-3398-529a-9eb3-a4d19e57e47b | note | ---------------------------------
e1ecc8d3-5d85-5c23-8886-5cda59fe8a62 | note | ACCEPTANCE CRITERIA:
a6b49288-492f-5abd-b2ac-1ae5a31074a1 | note | A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
88c936af-18b0-51fc-b2d8-747430a81813 | note | ATTACH: Delivery Docket(s)
011452d6-a4f6-57df-ad3f-db8feb166519 | note | ---------------------------------
68a06e94-9efa-55c7-b92e-1f7c046c5eb8 | note | METHOD: Document Review
f7d2b292-9a4a-507c-ba5a-ef93de679049 | note | ---------------------------------
6b907202-b678-520b-8506-116d64178633 | note | FREQUENCY: Each Lot
267477f9-cf95-584a-8363-024cec832c52 | note | ---------------------------------
947f035d-6efb-58b5-b824-092854a9f7d6 | note | CATEGORY: IP
d1f46f3b-a35b-54ea-a419-c01e1fcf9db4 | note | ---------------------------------
3caab89e-bfc9-554b-a065-4dcfcb211cff | note | RESPONSIBILITY: SE
c3329b50-052c-54c4-bcea-3c0986b403e2 | note | ---------------------------------
b198e82a-183c-563b-904a-eda4658982cf | note | VERIFYING DOCUMENTS:
6132c422-e79a-5df2-be45-21d3b0f64041 | note | Attached Docket
6436ad19-a2ae-5872-a193-35ce744e89b8 | note | Sign ITP
24cd4e46-6e38-5838-88f9-72d86df445aa | date | Date Completed:
| checkpoint | 5.2 Placement of Material
8021135a-1436-5029-b0cb-96a8fd49333c | note | REFERENCE:
3f4067c4-d870-585d-b660-4e16952a2c43 | note | Section 304.03
ee1f82d7-82ae-5a24-968e-3ad41d06f65d | note | Section 304.06
63a05123-8bc2-598a-9401-7d03f626a506 | note | Section 304.08
3de5777d-3ca0-5c9c-b26a-c6ead229f516 | note | ---------------------------------
49e70309-4983-5e6e-b417-dd3386e990a4 | note | ACCEPTANCE CRITERIA:
c85841d3-dd1d-5850-82d6-e1dc626e568b | note | Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
4e8d0fe1-8fa0-5ec3-9773-d5bd30221c4c | note | Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
d1dfcd97-121a-50f5-892f-fd78991c19b6 | note | Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
c75e935f-40e5-5057-ac3d-a32f38ef2c4a | note | At no location shall water pond on the surface of any pavement layer.
fbd5db62-ba6b-536b-b6a0-b6b97e7848cc | note | ---------------------------------
1d406a74-ac29-573b-b35a-568538547b59 | note | METHOD: Visual and Measure
d020afee-fac8-5ba2-a7d6-709a59be7493 | note | ---------------------------------
7cfdcb63-aaeb-545c-b9ea-e7a9ddf586c0 | note | FREQUENCY: Each lot
27c4e985-587b-51c8-9e83-b01c5e30e895 | note | ---------------------------------
a1dbe192-093e-5485-af8d-3a78bab7e384 | note | CATEGORY: IP
3e8b5874-dd25-58af-a441-239088a5dd32 | note | ---------------------------------
4ba77cfe-fe4f-550b-8f1e-55dc230895d4 | note | RESPONSIBILITY: SE/Site Supervisor
fc53907c-6bcd-576a-9f2d-2e5d6334e699 | note | ---------------------------------
e53d2792-cbb5-5125-8bad-117e2f924f53 | note | VERIFYING DOCUMENTS: Sign ITP
03c5fa2f-caa1-530d-aaca-4125f1c757d4 | date | Date Completed:
| checkpoint | 5.3 Construction - Jointing
64123a85-1d02-5f19-9453-4844d573de1d | note | REFERENCE: Section 304.07
ba4668de-6477-5670-8461-6a5ae415f54d | note | ---------------------------------
539f24af-9fba-5ec9-aee8-ba60a8a5f3fc | note | ACCEPTANCE CRITERIA:
864dd519-79f4-50e0-92c6-ab97ff7c9c4a | note | The layout of joints shall conform to the following requirements:
0af072d6-394f-5d3d-ab66-66ba9ebd508f | note | (a)material shall be spread in such a manner as to minimize the number of joints;
4bd06322-9544-5c96-8c06-de20a3497113 | note | (b)for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
293aa40a-5624-5c73-8d3f-548e0a2b5868 | note | (c)transverse joints shall be offset from one layer to the next by not less than 2 m;
5851416f-b2d0-5856-bfe2-cd580837e20b | note | (d)longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
4f1feef5-2283-5963-851e-6ecfa3f790e0 | note | (e)longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
5ba5b430-c84f-5350-a141-b00bfb8907e0 | note | ---------------------------------
a008ea52-f60c-5d98-ae21-349d8aa97603 | note | METHOD: Visual and Measure
d3aef334-c0d8-5fed-87e5-78bb78ea1c92 | note | ---------------------------------
d3001caf-47ae-5d67-935e-4d884711ac6e | note | FREQUENCY: Each lot
cdbc1da8-6ff2-5ecf-ae52-a4a4a529149d | note | ---------------------------------
4f2c5ec1-2d52-56da-94f7-e43c8608f8da | note | CATEGORY: IP
733883d5-a871-5443-a545-980606eff550 | note | ---------------------------------
b5133e64-d470-5d51-9f01-874f3b929876 | note | RESPONSIBILITY: SE/Site Supervisor
bf948f03-ceb3-52b7-ae63-0a571afdc19b | note | ---------------------------------
41bdf602-39cc-523b-b28a-4f6429b5ecb2 | note | VERIFYING DOCUMENTS: Sign ITP
76dacd57-462d-5753-99e4-c913c373f31d | date | Date Completed:
| checkpoint | 5.4 Compaction test (Frequency)
8eecee5b-2b46-57ab-91d1-5362ecc28d53 | note | REFERENCE: 304 .11 (b)
3a573e89-60c3-5c2d-b255-c62a548d3bf7 | note | ---------------------------------
1dca3086-5fa6-59a5-ba35-15162f7ffdce | note | ACCEPTANCE CRITERIA:
e980943f-1537-5888-950e-2e8dfd9cbd62 | note | The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
1ba1c076-c564-5b1c-8f94-755249eba709 | note | The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
15d9c8df-722e-5604-abb0-2b0f830e128b | note | Scales A and B: 6 samples
b7cdb2eb-cd50-5a38-a86f-017578def4c3 | note | Scale C: 3 Samples
2a8363d9-5a75-5d22-8637-18f5f0b04d61 | note | Pass: Tested
532b0cb4-2d40-50f4-a32e-db77e21c3973 | note | NA: Not Tested
860d4b10-a8aa-58ff-b905-fc12cecb4fc3 | note | ---------------------------------
e003a94e-eef6-5287-b134-01eb5bc6783c | note | METHOD: Visual
9ee6a47a-f402-5008-93b5-54ee050f6093 | note | ---------------------------------
3a7488f0-38b7-5766-a23f-96e8038e63da | note | FREQUENCY: Each Lot Where applicable
782c5fba-caef-5c66-95fd-0167f90cbcd3 | note | ---------------------------------
1021c69c-3d0f-56ed-900d-584499651654 | note | CATEGORY: IP
d3e9ae6e-a945-5e6e-942b-b4abd51ad972 | note | ---------------------------------
37e92ba0-65a0-58c7-8626-5a6055929544 | note | RESPONSIBILITY: SE
1041ba27-50b1-575a-a56d-7733d3f838fc | note | ---------------------------------
600a8c1f-4e05-587b-9ba7-6f24a9f1ce90 | note | VERIFYING DOCUMENTS: Sign ITP
b0b5ee3c-8310-5622-9e6c-6a8162bf8bad | date | Date Completed:
| checkpoint | 5.5 Post Compaction Materials Testing (Frequency)
b507b699-4342-5a28-aea5-ac48c6cac71f | note | REFERENCE: 304.11 (c)
a5d5af23-a01a-53e9-bf88-70a69fd1f3e5 | note | ---------------------------------
9e0638ae-1a18-5088-ac74-cdb9cb682e69 | note | ACCEPTANCE CRITERIA:
da2ff6e4-cc41-509e-914f-728ec3f5ee68 | note | ○ SCALE A: The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
0f9d2dc2-3598-5c28-b3e9-7712afcdbb58 | note | Compaction:
81a2653b-8fda-5543-9096-e40701a996ce | note | Lower Subbase: none
0fd9fe5d-f6cf-534b-9164-ac7353d6ddc0 | note | Upper Subbase: 1 in 4
0ac3d048-5861-53f1-a1e1-51b8913fbc15 | note | Base: 1 in 2
2069c7c6-0080-58f7-9443-a94aafb579f2 | note | PI:
858ba2ca-eeca-5b4e-9ca0-543366de3fdc | note | Upper Subbase and Lower Base: 1 (two samples) in 8
37d0a479-e77c-5e75-a2af-65c687781b18 | note | Upper Base: 1 (two samples) in 4
485cec2a-0513-5c16-b762-0e7d66310019 | note | ○ SCALE B: the first lot of each pavement course shall be tested for post-compaction grading and PI.
316b2364-ac93-59f1-819a-850f1ea59e6c | note | ○ SCALE C: Post compaction grading and PI testing is not required (CHOOSE NA)
579f35ea-5b48-5542-8564-8fd388ae9091 | note | ---------------------------------
16549729-6931-5d7f-87f5-5036437aff82 | note | METHOD: Visual
80e04843-a658-58f7-bf22-98a3e8d8522f | note | ---------------------------------
56ef0c12-cea3-5771-b7b2-a19ab8154b88 | note | FREQUENCY: Each Lot Where applicxable
d75f02ab-81c8-57c2-b40e-76e6e5a512aa | note | ---------------------------------
84931af5-1c11-5fdb-8657-23047830793a | note | CATEGORY: IP
2e9c2c8d-3328-52fc-8c0e-191de90ac8b2 | note | ---------------------------------
32af05aa-d46d-5418-9b8f-fec60d590ab5 | note | RESPONSIBILITY: SE
4d6afa15-f53d-58c7-bdad-f3650682e000 | note | ---------------------------------
86acb60a-93cd-5887-be3a-63c9d0d8f896 | note | VERIFYING DOCUMENTS: Sign ITP
81129061-42f6-5fbb-aa43-6b3072cd91db | date | Date Completed:
| checkpoint | 5.6 Proof Roll
436c3a55-c9f4-542c-9ff8-38c32884b96b | note | REFERENCE: Section 304.08
e3ef5946-659f-5ae2-8758-a4f417086f89 | note | ---------------------------------
d29ace57-b6cf-5013-8212-86cc74662812 | note | ACCEPTANCE CRITERIA: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
ee2920f8-bb61-52ba-ae01-fe5e45f9a058 | note | ---------------------------------
d2e78016-9b70-5b72-9eff-2417fc32f749 | note | METHOD: Visual
7bad6757-d77d-5a7d-ae8d-dfabb95b4f33 | note | ---------------------------------
4bd6b641-949d-5c8a-b39a-8144c277812a | note | FREQUENCY: Each lot
da7df698-a768-5127-92cf-65a242eb470d | note | ---------------------------------
fddf0efe-1dfa-5cff-b778-6bdb74967567 | note | CATEGORY: HP
163788a4-d81f-594d-b9f3-f40c200138f0 | note | ---------------------------------
8106c381-8e83-5474-b61d-104057cf7a6c | note | RESPONSIBILITY: Nominated Authority
df37c5f6-1b1f-5beb-af87-3e046c24022e | note | ---------------------------------
413a0a31-4a84-53f2-98cb-52cc7cd052b7 | note | VERIFYING DOCUMENTS: Sign ITP
dff9c164-91a3-5d47-a3c0-351e611a0fd7 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.7 Protection of compacted layer
05eec8b2-a56e-5c65-b425-426229b33c74 | note | REFERENCE: Section 304.09
764dc145-4b8c-5cc8-a696-831bb6cbda36 | note | ---------------------------------
24319235-d618-565d-9f28-6a9da47ea55e | note | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
2567b0c4-945d-5d4b-9a04-c005587560a2 | note | ---------------------------------
4a86fc96-c807-5f5e-b561-fe23a476c4ba | note | METHOD: Visual
03b437f3-48d3-5f77-a43b-8c5f98f660a6 | note | ---------------------------------
909a33c3-42f3-5d76-8c3e-07fcd4208e1d | note | FREQUENCY: Each lot
e73be73e-2caa-5a8b-9435-334d5033636e | note | ---------------------------------
d342a9a3-22ba-5ec9-b19d-32d731b56139 | note | CATEGORY: IP
d28b7024-d37d-5642-8fb2-4cd767fa3a1e | note | ---------------------------------
e01790d6-026d-5b3c-89b0-7a8cd5653259 | note | RESPONSIBILITY: SE/Site Supervisor
8ed8244f-1839-5523-9f32-ad25e98233bd | note | ---------------------------------
42bcd6ad-c661-55a5-ae72-f016fa54264f | note | VERIFYING DOCUMENTS: Sign ITP
062dd11f-9616-58f3-9788-e2ac28490f0f | date | Date Completed:
| section | 6 - Post Construction Activities
| checkpoint | 6.1 Compaction Testing (results)
85d432d4-6c9a-570f-91e6-629a343c9981 | note | REFERENCE:
f4e32e1a-b6fe-5466-bea1-0b88e395cfb7 | note | Section 173
8f712bb4-defe-59ea-a933-37c1a597055c | note | Section 304.08
7079092d-bd25-59a0-9e2b-652cb4b97b15 | note | Table 304.081
e411fe84-d11e-5fa9-9496-de630c30d1c6 | note | ---------------------------------
589abf5d-285a-5439-8d17-a24df0e85fa5 | note | ACCEPTANCE CRITERIA:
01108911-6712-5751-be85-f7a08494f74c | note | During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
aca9c562-4300-5293-a22f-9e8d17f5c30f | note | Density Ratio to be based on tests performed with Modified Comp active Effort.
221a2a46-7bd3-5c22-9500-ffdf0fc25280 | note | ○ Scale A:
e5e6adab-18c0-54ae-938f-671bbeec1a67 | note | – Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
2f1515bb-165e-5c04-9da2-baac231cb577 | note | – Base Layer CDR ≥ 100%
b76766b4-8cf6-5e3d-8502-8034a2f9f476 | note | ○ Scale B:
c0a9ca9d-fa0a-5fb0-9d86-9e61efffb97e | note | – Subbase Layer CDR ≥ 97%–
577cc1b3-3a37-5144-b05c-bfaab5492732 | note | – Base Layer CDR ≥ 98%
3528040c-2567-5199-9e7d-1f92e09049fe | note | – 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
63058b58-127d-5b52-81b8-875a483ff8aa | note | ○ Scale C:
6d11b966-004a-5908-b849-887bdc59a05b | note | – Mean Value of Density Ratio (3 tests):
1de1e6ea-80d6-5bd3-bcb3-42bfbdb299cb | note | – Subbase Layers >98%
9b52a5dc-252f-5720-b504-cecea3810693 | note | – Base Layers >100%
6249b548-bf8b-53f7-b900-0f20a5fd0278 | note | ATTACH: Compaction Test Results
25f6798e-eeb5-5185-8c96-3ec18b63f1d8 | note | ---------------------------------
359cf896-8ca6-5695-9994-89b460f3bbba | note | METHOD: Document Review
2e2cbf31-0f2d-5aca-af6c-9115b48aa7f1 | note | ---------------------------------
52704361-bdc8-5d5f-86de-678065c24165 | note | FREQUENCY: Each Lot Where applicxable
71d1806e-12dc-559e-b11d-0358f10670ac | note | ---------------------------------
7fbb39ac-ad51-50e6-9a87-a30597f37e90 | note | CATEGORY: IP
9c945e17-5e38-5ea2-bc2b-6fcd7fae42c2 | note | ---------------------------------
a202f23b-623c-5509-b1b5-b2dde76c7342 | note | RESPONSIBILITY: PE
70a41860-71b7-56a3-a0dc-e62479cd30cd | note | ---------------------------------
5f261207-de99-5126-a8ef-b57aee0c62e2 | note | VERIFYING DOCUMENTS: Compaction Test Rersults
83433fe2-b080-51b3-9c8d-15ade7ca7b6e | date | Date Completed:
| checkpoint | 6.2 Post Compaction Materials Testing (Results)
513b8e86-e315-5db1-a856-2df69fbe9e79 | note | REFERENCE:
31fff90d-b7f1-5bd5-afbc-11eced2ed0e0 | note | Section 304.10
781cae46-8135-5359-874e-fc57594960c4 | note | Section 304.11
f65daeeb-d048-59ce-a7c6-9a1f84f236c9 | note | RC 500.02
05788357-72d5-5995-b60b-e797d68ee422 | note | ---------------------------------
21743c15-4db3-5604-9c79-cf9db691c0ec | note | ACCEPTANCE CRITERIA:
c04d89d7-a8ac-5d11-87c1-25e88bbb0466 | note | Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
75b5c973-7435-5508-aef9-6b75b005d04b | note | ○ 20mm Class 3:
45f592d6-1945-5fc6-ac95-18c8e577d3db | note | – Grading
3ddea421-fe35-578c-8bf4-47ae3953b58d | note | 26.5mm 100%
b4750c40-241d-5222-8a56-760755eee81e | note | 19.0mm 95-100%
f2401ea0-0eca-54ca-b36f-f4fb49c6fbeb | note | 13.2mm 75-95%
b70c938d-987f-552c-ae7c-6c42c6a52fa3 | note | 9.5mm 60-90%
e1a3c8a5-4eb6-52a2-9606-d2204f20833c | note | 4.75mm 42-76%
078676b2-5201-53fc-a7ff-a8058b2cb81b | note | 2.36mm 28-61%
86c7bb21-ec27-57eb-b64c-193db13ed4ec | note | 0.425mm 14-29%
3124e430-4cf6-532c-a6b2-3b66e59db80f | note | 0.075mm 6-14%
de401da6-9ab2-5da4-956f-dc5c0f22cccd | note | PI between 0 to 10
461e843d-b478-5ff7-a68b-6c64b7cd0fe0 | note | ○ 20mm Class 4:
4dcd3bb4-7eca-58b6-a1cc-204255b8706f | note | – Grading
d8369a0d-92cc-501a-9bce-863178479d5d | note | 26.5mm 100%
43c19236-42ba-5332-8623-d2e568828df8 | note | 4.75mm 42-76%
5f6c1716-785b-527b-a24a-ed7c70e976e2 | note | 0.425mm 10-28%
5ee8ec8d-86b9-524e-8df7-772609a9dee3 | note | 0.075mm 2-14%
deeef6e8-8c43-5000-841d-46cd6f0a24f2 | note | PI between 0 to 20
45672309-51fd-50b2-9f3d-ffe2b83e6112 | note | PI x % passing 0.425 mm sieve (max) 450
cb06c1ef-8283-5132-b42d-b705c223ddd6 | note | ○ Scale C: Post compaction material te
6c89b3fc-8d22-55d3-8c72-c3682f3d63c3 | note | ---------------------------------
484e37b2-afdc-5b38-9627-fb4c23b5f342 | note | METHOD: Document Review
875a1b92-887d-5778-9ae3-ca9d69fbe79e | note | ---------------------------------
29fd9910-1802-5016-966a-cdae2f93fe57 | note | FREQUENCY: Each Lot Where applicable
39cd36af-4b92-5781-bba1-4dcb8affec4e | note | ---------------------------------
6002bb76-8930-556d-a914-31c56e22c18f | note | CATEGORY: IP
c3fa00cd-28f4-5bbf-bd85-1d5b5642bf1d | note | ---------------------------------
e3eca85f-abc7-5f41-b835-2ae0b5f4557f | note | RESPONSIBILITY: PE
652ce04c-220c-579d-8fd9-8aca4552514d | note | ---------------------------------
c361a182-ac46-5253-b266-4119a9fc975c | note | VERIFYING DOCUMENTS: Compaction Test Rersults
c1e5dbc3-1643-5ed6-b90c-40416a02ee28 | date | Date Completed:
| checkpoint | 6.3 Survey As-Built - Surface Level
09a18864-81ae-526a-9689-e749deda7e62 | note | REFERENCE:
f1f1e660-e4dd-5292-9f1c-abb723e0a4dc | note | IFC Drawings
f0262e6a-0e62-506f-836a-f6bc2a022a8c | note | Section 304.06
8dc87aac-7c92-5426-9621-70a7d0cc4cc3 | note | Table 304.061
7065bbff-a65b-5462-b501-a4782e82fecf | note | Table 304.062
4a100fce-5675-5309-85b2-deca0551efae | note | ---------------------------------
00037401-05f9-5321-b6a6-90d2a9633e89 | note | ACCEPTANCE CRITERIA:
cec57e67-6746-5957-90ab-e12c7e38489f | note | No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
cee12b34-33fc-5b2e-ab1a-2cbcad30ef1d | note | Subbase course shall be not < the specified thickness by more than 15 mm.
95f9d542-8e6f-5924-a3ae-0506dbcbafee | note | Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
d771d4af-b012-5c5c-9c89-6e2e990563af | note | The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
a0c46964-1526-5a07-b1a6-45e194764894 | note | ○ Scale A: A minimum of 80 measurements per lot
e900a0e5-0215-5b94-8284-48c02e7bdbe9 | note | Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
e95b82a6-c5a0-5523-a85f-da0d2a48950c | note | Base: mean range ±5mm, maximum Standard Deviation of 8mm
377ba864-1658-57cf-b1d9-dc54734452a8 | note | ○ Scale B: A minimum of 40 measurements per lot
59242fc7-7163-5d4b-8611-55ef6076c227 | note | Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
28d868ec-0a0c-5bd3-a476-b7f53e3488cf | note | Base: mean range ±8mm, maximum Standard Deviation of 10mm
a6a6221d-3bb5-5c58-9f24-e6ff08cf2f78 | note | ○ Scale C:
268559e6-f051-5554-9718-4217592c3e58 | note | Lower Subbase (mm) +15/ -25
bab41298-b6be-585f-8641-4662942476c9 | note | Upper Subbase (mm) +10/ -25
1593b53b-202b-5541-8b75-9eb657a30b70 | note | Base (mm) +/-15
8323ed6f-f6bc-59c0-afdd-5ab4a0c3c61f | note | ---------------------------------
b36345d6-71dd-51fd-afd5-1bf4f9429b64 | note | METHOD: Document Review
f0f90a9b-4ed2-55d4-8210-19273fe72597 | note | ---------------------------------
508dce27-1df2-5661-a131-772f88f75134 | note | FREQUENCY: Each lot
404fe49d-18b4-55e1-8e7a-8fb49df33373 | note | ---------------------------------
4c74e684-d08c-54e9-8cf9-f226ef378843 | note | CATEGORY: IP
82285ee8-50dc-5f94-991f-6612bdb35eda | note | ---------------------------------
ba98b8dc-2aa2-5cce-a494-4418b282a37c | note | RESPONSIBILITY: PE/Surveyor
a9c04c23-4a3a-5b6f-94e4-4fc54437bf76 | note | ---------------------------------
3b910d95-599b-5354-95d7-ff2d038a7baa | note | VERIFYING DOCUMENTS: Survey Conformance Report
a5e3ef50-8e92-5128-9dab-248deabb16fd | date | Date Completed:
| checkpoint | Metropolitan Roads Program Alliance Final Inspection
466a1ce8-e38e-5edb-9ae0-330f1362419a | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3f9dca37-9bf9-58ab-82ae-87009338a9d8 | textbox | Name:
217c0efb-6411-59ce-b868-f024c44b8d48 | textbox | Position:
2fad6147-33e2-5546-a328-edf245079e42 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-RAIL-CAMMS-MTM-Conduit and Pit-Temporary Rev 0 | itp | ITP-RAIL-CAMMS-MTM-Conduit and Pit-Temporary Rev 0 |  | e26fd899-d5df-4826-b4bb-9b9e8026dd3a
| section | Referenced Documentation
| checkpoint | Referenced Documentation
bf90ed8b-6c22-519d-98d8-06d4df0cfe66 | note | Document Title: ITP-RAIL-CAMMS-MTM-Conduit and Pit-Temporary
e3efe4a6-a8b7-5484-9057-58bf1a511256 | note | ITP Description: Conduit and Pits-Temporary
9686f80d-a5e2-5138-8a00-3ab5dd783b0d | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
6c8425a7-21f0-561d-9158-afc2f2989546 | note | Discipline (e.g. CIV/STR/RAIL): RAIL
7eab6f97-9dad-50c8-9632-1071756b7ca0 | note | Revision Number: 0
fe3bb6eb-4410-54c3-9394-d28273527773 | note | Revision Date: 30/08/2020
3249d04b-26cd-5581-8099-8f4c10be896f | note | ITP created by: Isaac El Zayat
81da3fe3-0c6c-5be1-9106-1549665c1658 | note | ITP approved for use by: Victor Mira
37fd94cf-db1d-5775-a897-842b57534db7 | note | 1.1 - Non Dependent
9189eda9-272b-52f3-b609-fe0a91081196 | note | Reference Documents:
0e598221-7b94-5b4c-8740-58f974e03f18 | note | IFC Drawings
8ed73d3c-20d4-5533-a29c-5177f63830be | note | L1-CHE-STD-043 (VRIOGS 012.2.1)
985b610d-0718-5160-b307-2efd6ad9cfeb | note | Australian Standards
| section | Preliminaries-Materials
| checkpoint | 2.1 Conduits
1f566cf8-66d2-5744-8945-097202548107 | note | REFERENCE:
282c901d-82ba-54c5-b505-094c4790234b | note | Comms Conduit: AS/ACIF S008:2006
abe96299-4472-5374-b1b8-7615d62d8fdb | note | LV Conduit: AS/NZS 3000 - 2000.
10c3dfbc-4d42-59fd-8026-7676d8b33d17 | note | L1-CHE-STD-043
f1548a03-bc0e-5c54-b6ad-c707827be01d | note | ---------------------------------
4e945a6d-57bf-5d36-baae-63498a59ca54 | note | ACCEPTANCE CRITERIA:
f94a93fa-ee2f-5b71-8a07-1a645b80cf38 | note | Comms Conduits: 100Ø (114mm OD), PVC White comms conduit 4.6mm wall thickness
86667eb5-a06b-563d-aff8-c0e8d5a6648a | note | LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
a2c16ffd-39a1-5a13-b155-3b85b5e7691d | note | Inspect materials upon delivery and attached delivery dockets.
32ac31d5-d38d-5171-a784-90a1039dca7e | note | ---------------------------------
a6bb60ac-bb24-5634-bf00-c145d8fadd49 | note | METHOD: Document Review
3408d780-0cc4-528f-b921-188f279bec93 | note | ---------------------------------
83524a85-5cdf-58c6-a0ae-d708788496cb | note | FREQUENCY: Each Material Type, Each Delivery
c708a368-4c2c-585c-b115-6ff70f20037e | note | ---------------------------------
a67b8cee-6be4-5715-b82f-363c69c23bbb | note | CATEGORY: IP
83b42dec-5bd9-569e-a56e-a5600b021000 | note | ---------------------------------
290ddaac-b44d-5343-8c16-24e54a88fce3 | note | RESPONSIBILITY: SE/PE
eae9e3da-6a95-5ae5-8ce3-517c8825c2cd | note | ---------------------------------
cd8af18e-5501-538a-a330-0043d79c0a95 | note | VERIFYING DOCUMENTS:
4687bd63-6601-523f-b498-106e471de7bc | note | Attach Material Conformnace Certs, include TB Approval No.
28827953-f9e5-573c-bdca-f8596c754335 | note | Attach delivery dockets
be89af8b-ed39-5fc2-8378-136f21032f66 | date | Date Completed:
| checkpoint | 2.2 Pits and Pit Lids
6d506818-b57a-5bb3-b548-2116ce2d3926 | note | REFERENCE:
3235a2fe-c980-5ab4-ba37-5405e5663256 | note | IFC Drawings
d03300ee-348b-5310-8a35-7b9141bb86a6 | note | L1-CHE-STD-043
00e0f5eb-ccad-54a3-88f1-c0f12e287045 | note | ---------------------------------
1e27fb79-1634-51a8-a53a-49ef2ce02832 | note | ACCEPTANCE CRITERIA:
0b76269e-13f6-56d5-bc7d-fe1658e49bde | note | • Pits: Concrete Pits to be made as per AS 3600
b3b28c53-38d6-56e3-9903-5649947518c2 | note | • Pit Lids: Pit Covers shall comply with AS3996-2006
7a9ad78b-9283-557f-982a-21e3fe5ff662 | note | Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
7b92b1e1-d438-524a-bbec-a2a2b15aba7b | note | LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
068d700f-8048-58fb-b7d7-f612d8a75da0 | note | Inspect materials upon delivery and attached delivery dockets.
182797c4-8ed7-5b01-8a0e-ecd6cb77f3e2 | note | ---------------------------------
60fc863d-0931-5c85-af09-85cc1d34d025 | note | METHOD: Document Review
86f14eb0-ab1f-58e3-8061-d2831001d0cd | note | ---------------------------------
af73d79d-4717-5dac-a8e6-4183eadeb155 | note | FREQUENCY: Each Material Type, Each Delivery
47e3cbba-3db0-5389-a34e-b277a1a8e7cd | note | ---------------------------------
cf60397e-6755-5484-9997-432723e9a66e | note | CATEGORY: IP
ab79d8cc-260b-58ae-8d4d-9b6cce91bc38 | note | ---------------------------------
d61f3992-2d52-566e-92ab-22e02ab16b16 | note | RESPONSIBILITY: SE/PE
c28b82e3-cf53-5ebe-9660-8e00dcafe351 | note | ---------------------------------
ca609459-7050-50eb-94ca-6a4116066f4e | note | VERIFYING DOCUMENTS:
a7d8627c-fbee-5c90-8ea7-88ea1afe0ec1 | note | Attach Material Conformnace Certs, include TB Approval No.
a701adbb-9f0c-5634-a171-f957317ddd9e | note | Attach delivery dockets
e7dd3031-e21a-5a79-a196-3e65bf00d58e | note | Attach Precast Birth Cert
572096ac-5605-5c68-b5d2-ea29d7c8d8f3 | date | Date Completed:
| checkpoint | 2.3 Warning/Marker Tape
ef80df02-bb70-5ce4-b2e1-48046e974050 | note | REFERENCE:
a558872b-0457-5402-941a-237de154f372 | note | IFC Drawings
9d15a2f1-e17d-5c10-b4ec-8536003986c6 | note | L1-CHE-STD-043 6.4
16abf6ed-ec92-56aa-9bba-0b2d3407c14d | note | ---------------------------------
beba12a2-a3f2-50a8-87d6-082df0d52645 | note | ACCEPTANCE CRITERIA:
5d9674b3-844d-5104-9988-e7eadb4f2318 | note | • Warning/Marker Tape:
7ad77e8d-dc13-5d9b-8abf-d3987edc894e | note | • Above LV:
9122fcfc-5c60-5356-92c7-03c8573a0bcf | note | 150mm minimum wide orange coloured PVC
82f14355-0f0c-5582-978a-b06ff970a0a9 | note | ‘DANGER RAILWAY SIGNALLING CONDUITS’
1e1ff94c-76d9-5a39-bcf7-bf4512db72bf | note | • Above Comms:
ae642106-478d-55d8-a443-abeb26f32317 | note | 75mm minimum wide white coloured PVC
11bb940e-c8bc-5c73-93ac-04d20c93a7b3 | note | ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire
2c07dbc7-ae07-54e5-a2f4-d61959f6dbf2 | note | Inspect materials upon delivery and attached delivery dockets.
049fddd8-d588-5f29-850e-13dfa7712cb8 | note | ---------------------------------
a7e6e58a-fb40-5063-8e1b-5d8916d9e34e | note | METHOD: Document Review
d8441dd9-e4fc-513d-bc50-c3a0627eec46 | note | ---------------------------------
784215b3-63ea-50a1-b30e-ca0caf4322a4 | note | FREQUENCY: Each Material Type, Each Delivery
f1c19371-0429-54eb-b25f-b164a6194878 | note | ---------------------------------
1907ae65-a1ea-50d9-b939-022f9d6c2d7f | note | CATEGORY: IP
89ad9da6-1ed3-5e89-ad47-a8b776453c70 | note | ---------------------------------
8b54635c-e91b-5adb-a720-23a50c6a77be | note | RESPONSIBILITY: SE/PE
97e4a208-9f01-5fdf-b835-974c12b4d71b | note | ---------------------------------
66335cde-18b2-51d0-b536-679628d3cd90 | note | VERIFYING DOCUMENTS:
8547a0f4-7c1a-5096-b508-1b4f09fa9ccf | note | Attach Material Conformnace Certs, include TB Approval No.
92767350-2ec3-5157-9df7-70b234f3bd4b | note | Attach delivery dockets
ce026a42-24bb-52f7-94e0-e6aefe9fe6b0 | date | Date Completed:
| checkpoint | 2.4 Protection Barriers
b042269e-e45b-50fc-b8b6-20f65c79cafb | note | REFERENCE:
1dfd535c-2e07-5259-817c-48321860f8cf | note | IFC Drawings
449631db-a1c3-547f-ab65-16a1ce1f6372 | note | L1-CHE-STD-070
059a40c5-88ec-5b8b-9dfe-bde3a632c876 | note | ---------------------------------
0a34e599-0b22-5877-824b-6eb488830854 | note | ACCEPTANCE CRITERIA:
f989f733-a357-5557-bc30-86c68ac56296 | note | Approved plastic protective orange strip (Vinidex or type approved equivalent)
8d94fd48-c6c6-5b6c-a823-b8be72cd9c79 | note | Inspect materials upon delivery and attached delivery dockets.
cb59e849-3839-55eb-a626-aee09676f8e4 | note | ---------------------------------
717a769a-1d87-50fb-b360-0a73b132c901 | note | METHOD: Document Review
c2dd9435-54d0-5945-8fc7-e73a6c307961 | note | ---------------------------------
2b81e876-dee1-574b-a336-4ecf8e1a497d | note | FREQUENCY: Each Material Type, Each Delivery
f9a18784-9607-5401-9038-bd671ad71655 | note | ---------------------------------
cc1d6462-2b04-5d15-903d-35eecf86599f | note | CATEGORY: IP
7a09221c-dd4e-59bd-abc5-90029e0aa7c6 | note | ---------------------------------
d3c0ed0c-a95d-58d8-98e7-547708c2d16a | note | RESPONSIBILITY: SE/PE
cb752997-6860-51e5-8416-d53563f024a7 | note | ---------------------------------
0cc4748e-d2e2-5752-9f6f-d3ebd6a3da96 | note | VERIFYING DOCUMENTS:
2f2cc158-06b2-55b2-bd94-4c67ebf3e9e9 | note | Attach Material Conformnace Certs, include TB Approval No.
e8900088-dc30-5df7-a895-0ae044188b34 | note | Attach delivery dockets
df81d17d-cad3-58d8-b553-ec4e99c5a97a | date | Date Completed:
| checkpoint | 2.5 Backfill Material
03eb518f-ace3-55f4-bc20-e8b810177cec | note | REFERENCE:
838df13f-e840-5bc5-bb05-faadffa5f714 | note | IFC Drawings
15f91c3a-0175-5294-97ff-7427f2952281 | note | L1-CHE-STD-043 Section 2 Table 1
6308ac7c-1685-58b0-acda-d0e81b82e6b8 | note | ---------------------------------
b025d7eb-4640-5dbe-9a53-66d2397081a1 | note | ACCEPTANCE CRITERIA:
ea95a501-1842-5cfd-9f41-34667839c1ac | note | Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could dmanage the conduits.
31b6cb02-023e-5a79-9019-5839320eb9d3 | note | Inspect backfill material.
8a8b0042-2c7e-5b84-a6df-b012b678c55f | note | Attached delivery dockets (if applicable).
c3af4524-c51b-5921-b28a-93b1fd70d4b1 | note | ---------------------------------
14dd357d-5503-5292-83fa-bcddcf4e64ea | note | METHOD: Document Review
e7928602-2739-5e84-946b-fcada7bc34ca | note | ---------------------------------
8d88bf2b-5fb2-5b45-983f-3ef9ec0f1195 | note | FREQUENCY: Each Material Type, Each Delivery
630c937d-5108-53a9-a43a-dd68eeb1e00e | note | ---------------------------------
c6b6f3cc-6567-5a93-bb79-d68315d2637e | note | CATEGORY: IP
75b76b75-3a0e-5efd-9afb-b71d8d0d6b1d | note | ---------------------------------
9592a3d1-7ca6-5dd6-98ef-f8bc469a0ec0 | note | RESPONSIBILITY: SE/PE
3c25ed44-dcd0-5b49-91d5-b649d8939368 | note | ---------------------------------
ee551379-aab1-55a9-bb57-b35da3aa72ce | note | VERIFYING DOCUMENTS:
27b21db6-3fc6-5ee0-adb4-fb7a68206a1b | note | Attach Material Conformnace Certs, include TB Approval No.
7e433f6e-525b-5b6a-92a2-9e625392a5c6 | note | Attach delivery dockets (if applicable)
0da65980-8b39-5cd1-ac59-6d480c0565e3 | date | Date Completed:
| checkpoint | 2.6 Bedding Sand
7da71428-837b-5761-bd45-269b5bab3529 | note | REFERENCE:
d67a3be5-04f7-5c12-bd4f-8527d703d753 | note | IFC Drawings
4e787d3a-aff5-5933-a2f3-611a7140a188 | note | L1-CHE-SPE-313
1dd76df1-9c0f-5423-bd86-c6614a9c5cf5 | note | ---------------------------------
a5841c79-993d-5a25-8163-8748818db088 | note | ACCEPTANCE CRITERIA:
8fb67725-85ab-5828-ab24-9e997bd961dd | note | • Recycled Glass Sand shall be free of any perishable matter
bfbb350d-6de4-5085-9000-b1676ca896d2 | note | • Bedding material and embedment material shall comply with the following grading requirements:
3b148c46-0553-5628-bc14-eec0924065d2 | note | 4.75mm passing 100%
5a3f4c5b-7e30-571a-b0a1-b42c5ad42451 | note | 2.36mm passing 75-100%
0133516b-237d-5149-b379-4f12a5bc9c6b | note | 0.075mm passing 0-5%
67ba5836-cdbb-5d64-90ad-f1b8b66fd21d | note | ---------------------------------
c84fc911-e01a-5ac0-8a0a-1e261ac460f0 | note | METHOD: Document Review
d6982ad0-4a0f-5af9-b5da-3f733e2bb82e | note | ---------------------------------
d3f6e490-5e29-5a55-a79f-228fd4d848e4 | note | FREQUENCY: Each Material Type, Each Delivery
d989b824-47fb-5e45-9ad4-c871f45b43a8 | note | ---------------------------------
0ab1f44b-624e-57f0-b477-cfaef3f8b5ea | note | CATEGORY: IP
b04e0233-465c-5333-9dd7-a727030bd051 | note | ---------------------------------
a6a2349f-f907-5257-9efb-0bc0adaa6006 | note | RESPONSIBILITY: SE/PE
d79ecb9f-ea0c-5ee3-b481-165f3f00495c | note | ---------------------------------
ec226a2d-6d4e-53c4-bb1f-b569b0ae4887 | note | VERIFYING DOCUMENTS:
68d56421-39ea-522a-bd4b-7c67110cbe75 | note | Attach Material Conformnace Certs, include TB Approval No.
c4500129-608b-5f03-a212-5891d92df0c8 | note | Attach delivery dockets
8a2545b8-d09b-5c5e-8938-8fb7aec74f5e | date | Date Completed:
| checkpoint | 2.7 Draw String
62316771-d111-517d-a239-8100ae90e581 | note | REFERENCE:
62195fa0-f41d-5d02-b396-6013661914ef | note | IFC Drawings
4c557bc7-d6e9-52eb-8170-86148dc41832 | note | L1-CHE-STD-043
0eb575cb-c5ba-5300-9722-a0e79a9f9514 | note | ---------------------------------
3ac33559-cc2e-542a-aa7d-b8511dcb3386 | note | ACCEPTANCE CRITERIA: 6 mm diameter polypropylene blue/yellow
d0884ccb-f866-5520-933d-a20debd8ef32 | note | ---------------------------------
b4528542-249a-59fb-8ca6-b78b61278a87 | note | METHOD: Document Review
3a7563ab-c157-57b0-b3f2-1faf79167672 | note | ---------------------------------
848e59a1-0bc6-5986-8852-9a549fcb09c6 | note | FREQUENCY: Each Material Type, Each Delivery
93b503e3-5807-51db-91d0-d466af4cb78e | note | ---------------------------------
2c0700bd-f442-51ce-93c8-c1ac9a99285e | note | CATEGORY: IP
467a4688-1cba-5bb6-98c6-447fdbcf3675 | note | ---------------------------------
3d8ee86e-473e-522a-bf64-5ccaeb1e1566 | note | RESPONSIBILITY: SE/PE
52761bb0-692b-53b3-983a-055dc0368311 | note | ---------------------------------
95ce23d8-602f-5482-af0f-36febbc649ba | note | VERIFYING DOCUMENTS:
0a1c78d7-ef25-5dfd-adc7-eb30db1ee5d3 | note | Attach Material Conformnace Certs, include TB Approval No.
e9a7cb62-1225-5ee9-88b9-0958f64322b4 | note | Attach delivery dockets
68ba1ec1-f067-5aab-b569-2fdcfecbb8e4 | date | Date Completed:
| checkpoint | 2.8 Markers and Marker Posts
e605ce09-81e4-52d0-a204-d6c8a8a44ffd | note | REFERENCE:
711c6409-3ae3-5c29-9aa2-b19e19e87ee0 | note | L1-CHE-STD-043 13.2
b9329ba1-2096-51ca-854d-f7a50f7c1d0c | note | AS 4799
238fd729-2340-5742-9718-fc34e304cefa | note | ---------------------------------
eb65e49e-a034-504f-ba31-0f3b12a06774 | note | ACCEPTANCE CRITERIA: Markers and Marker Posts are to be manufactured in accordance with AS4799.
2bd4db00-64c6-5102-b8e3-08ca9a15b43b | note | ---------------------------------
e1f31c35-a5b8-53d9-b0c9-b06389055b72 | note | METHOD: Document Review
fe32ec1e-a3bd-515f-995f-162d847e643f | note | ---------------------------------
ec0a976f-e6eb-5f40-a685-b3b236fc7af5 | note | FREQUENCY: Each Material Type, Each Delivery
68d1a97b-c9a6-514a-9cf4-8f0f42b881de | note | ---------------------------------
7995bc0b-dbd9-5e56-b684-3e1446187c2a | note | CATEGORY: IP
4b8bd95f-1cd1-526c-be21-0cab09654bc5 | note | ---------------------------------
83373d6a-8f40-5859-8786-7e0c9c31ee5f | note | RESPONSIBILITY: SE/PE
445d8569-a71c-50ed-9365-5690e3aeccd3 | note | ---------------------------------
0ef611c4-7935-5107-8f81-4dd25c181c66 | note | VERIFYING DOCUMENTS:
0f9d709a-141b-5157-8641-73c5695ca12f | note | Attach Material Conformnace Certs, include TB Approval No.
73229cdf-0a05-5a0a-8e64-9d4dddd912c0 | note | Attach delivery dockets
a849f194-a044-5df0-892d-d6f6de1616d5 | date | Date Completed:
| section | Preliminaries-Procedures
| section | Pre-construction
| checkpoint | 4.1 Survey Set-out
06f68b60-3771-5bc4-af5b-937b2c71f861 | note | REFERENCE: IFC Drawings
e0aeb3fc-390d-5319-bc26-eb702f28fe79 | note | ---------------------------------
a52e8b70-167a-5ecb-bc4c-95896c8b2c2f | note | ACCEPTANCE CRITERIA: Survey to set out trench alignment and pits, and establish construction control (alignment and level).
ff9bc54a-afaa-533a-afa9-cd41b31f936f | note | ---------------------------------
7484a3c0-2d02-5504-976e-c84099794196 | note | METHOD: Measure, Visual
116c97c4-1d48-50f2-a01f-9a9b57a8f8d3 | note | ---------------------------------
e0197d6f-6d3f-505f-b871-5499b2157419 | note | FREQUENCY: Each element
c23c9a0f-05fb-5f4a-ab7a-e957379d37ce | note | ---------------------------------
9d9b8f00-5abd-538c-9a64-9ca3a5b3501e | note | CATEGORY: IP
cf34b04d-b6b1-5a45-8707-66ba90c175c1 | note | ---------------------------------
4969e812-3ce0-548a-8d37-4062bbaedfa5 | note | RESPONSIBILITY: Surveyor, SE/Site Supervisor
bce4d969-e8ea-527a-9166-8f71c40bb421 | note | ---------------------------------
85954051-6ee0-5ac5-9920-de16c2220a84 | note | VERIFYING DOCUMENTS: This ITP
5b16e36a-3145-5fce-a8a5-0f6e82b8f91e | date | Date Completed:
| section | Construction
| checkpoint | 5.1 Trench Excavation
abf0684a-a6ae-5de0-9650-5db6da13934d | note | REFERENCE:
5f704c55-69fb-59c4-b946-ba73613568d0 | note | IFC Drawings
f7161ea1-cd2d-55aa-9fbc-8215f1cdafb2 | note | L1-CHE-STD-043
4f69e87d-61a3-570e-bd0a-63525e979bda | note | ---------------------------------
ffa29e0d-f66a-5070-8519-23c9bef6f3b8 | note | ACCEPTANCE CRITERIA:
7d563da8-6a23-5a00-9b56-99448b787f10 | note | Trench profile and depth as per IFC drawings.
692616c9-2dfa-5c99-8afb-f8737472dc99 | note | The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
92330e20-d6cd-5822-80b5-f3de7b3b3d4e | note | The floor of the trench shall be level and free from all loose sharp objects; such as stones or rock of any type, or size, or rail ballast.
c0e6f3b5-0070-51fd-8eb9-1c68623bbccb | note | ---------------------------------
a4847ad8-a464-5523-a088-218df4067a1b | note | METHOD: Measure, Visual
6c6c635d-50d7-5389-8554-552f96124ab8 | note | ---------------------------------
d8a06271-513d-5321-ab28-6bc369098aa7 | note | FREQUENCY: Each lot
e848d48a-4d07-5936-8e9f-09313c753d91 | note | ---------------------------------
65188492-cd61-5d53-91c7-c059feb371cb | note | RESPONSIBILITY: SE/Site Supervisor
95e703a0-e9fc-5ffa-844b-04ea252a080d | note | ---------------------------------
60e3b842-42da-5cb7-971b-07d0f23721bc | note | VERIFYING DOCUMENTS: Sign ITP
226772e8-30bf-54a6-bc9b-a8d8c40c4ced | date | Date Completed:
| checkpoint | 5.2 Trench Stability
d7a00b18-a3c0-5e83-be8f-16300ec12764 | note | REFERENCE:
688aa16e-4f27-56c4-95bf-c2ad48695967 | note | L1-CHE-SPE-070
8480fa36-e475-50ac-ba54-0fd6a47c1cea | note | L1-CHE-STD-043
76030813-cbdb-5fe0-9910-b74ea55076e8 | note | L1-CHE-STD-070
e8269ead-d349-5491-ae6d-7401bb05d3d6 | note | IFC Drawings
8da17f0f-5d46-577b-8ad2-c7c8c7b87ba9 | note | MRPA standards
d603c5d9-72ef-5ca4-a1b5-fef736485928 | note | ---------------------------------
5e3146ac-52de-5094-967e-79b0b5925208 | note | ACCEPTANCE CRITERIA:
aff49d7d-69e1-55fe-88c9-61ff3663e3d6 | note | Trench stability check:
1a346432-87fe-5e4e-9f26-be525cdc1362 | note | – Shoring,
8715a2f4-3885-598a-8437-b76d7ec48859 | note | – benching
300eec64-38c0-5b27-8403-a46d2589af61 | note | – geotech signoff
b8c441cc-b004-5fb0-8801-6f5d4f1709d6 | note | ---------------------------------
0d29295e-e21e-5d64-bc3f-2c8e235b7446 | note | METHOD: Visual, Document Review
5422e6e9-fc9c-5128-b033-6ec827a9c7a2 | note | ---------------------------------
e7964096-a528-5833-a9ca-5f9e842ec8d9 | note | FREQUENCY: Each lot
759e1232-ae97-56a4-914b-3493dfd1ab64 | note | ---------------------------------
8f348d03-a637-5d64-8fe5-8c2f65e7c88c | note | CATEGORY: IP
1a39db78-83a0-5915-bb33-5adc6cafad30 | note | ---------------------------------
93da1aa2-8248-5be3-810c-ea83b04e710e | note | RESPONSIBILITY: SE/Site Supervisor
ae7bca71-465c-55cd-b03b-1269a2373f01 | note | ---------------------------------
d147143c-0b28-5152-8be2-81bc8bdac88b | note | VERIFYING DOCUMENTS: Sign ITP
b6dcb368-7230-5831-a849-e62c986472ae | date | Date Completed:
| checkpoint | 5.3 Conduit-Bedding Sand
cf2b6b15-f6bd-5d2a-b3de-058134edf203 | note | REFERENCE:
b634d083-9662-5a0f-b78b-48dc838b5cd5 | note | IFC Drawings
1ff8437d-9064-504d-a7d8-fb75813c6e3d | note | L1-CHE-STD-043
eddf0766-01f0-57c9-bc30-2b70409c9077 | note | ---------------------------------
9fd422a9-c208-571c-a697-96ae08c821dc | note | ACCEPTANCE CRITERIA:
11469c94-07ce-57d5-bef7-f5c2c99cc385 | note | 50mm bedding sand to be placed at base of trench in accordance with IFC drawings
0620345a-1c6b-5d95-9e4b-397280b08f11 | note | In areas where rock is encountered, the cables shall be laid on a clean bed of sand 100 mm thick
04fe0384-1557-5aa5-b4d2-71dc1452a60b | note | ---------------------------------
3da0d8d3-8302-5e9c-9fd9-961f566932c8 | note | METHOD: Measure, Visual
727d51c6-7108-5254-85e1-bed19eedcac9 | note | ---------------------------------
3c692a17-929f-54f3-ac65-077567bb390b | note | FREQUENCY: Each lot
08286d5f-05a5-56d9-bfa0-97e550f1664c | note | ---------------------------------
9825b245-9776-5a3f-9a2b-16b344b69e07 | note | CATEGORY: IP
d464aa5d-2c6c-5035-afe1-9904803265ca | note | ---------------------------------
37933f8b-4c8d-5684-841a-245ae5c818e2 | note | RESPONSIBILITY: SE/Site Supervisor
246d259d-f75f-53d6-a806-20faa06aee0c | note | ---------------------------------
d47c0cbb-c854-51db-9bc5-cce94d9c65a2 | note | VERIFYING DOCUMENTS: Sign ITP
ff45ae51-2360-51e2-9a72-723857307539 | date | Date Completed:
| checkpoint | 5.4 Conduit-Configuration
b4cd4b47-e276-5edb-85fc-ecb76075ace8 | note | REFERENCE:
1e9f751f-ac13-5d14-afad-40e65cfa4b19 | note | IFC Drawings
12050097-ee97-5276-abae-b638f0a287c2 | note | L1-CHE-STD-043
4975c10b-07a5-5c25-b8eb-6bf3a291c6a5 | note | ---------------------------------
281ca41a-ae20-51f3-bda2-def1b9d494f4 | note | ACCEPTANCE CRITERIA:
78df08b1-6ad2-53b2-aef1-7645321e8f7e | note | Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
ecfdfdf2-1477-5735-b492-02fc02cd4b86 | note | Min Cover
ec0b3e71-dab2-530b-88f4-747831df89ae | note | – Natural Ground: 800mm
e8a42497-84f9-5c77-bf23-314d31aa1e0f | note | – Under Road: 1200mm
87b1b8a4-58dd-591b-8256-23e2782a53d2 | note | ---------------------------------
c96cc1d2-5761-5e4a-99a6-0ae1056c1f52 | note | METHOD: Measure, Visual
b4c0195e-3bc9-5587-8033-bbc8bdc61f94 | note | ---------------------------------
8aca18a1-3eee-5dc1-bf32-391f42d348de | note | FREQUENCY: Each lot
49c88edf-0cb2-5d72-ba1c-fb9634f04e2a | note | ---------------------------------
b4335057-e6c6-5160-98e3-3f3d78371aa8 | note | CATEGORY: IP
e8bd8dce-f9ee-5a04-b156-ee8f085ac23a | note | ---------------------------------
22f2088f-5440-5063-b8f5-3a8f459dcf25 | note | RESPONSIBILITY: SE/Site Supervisor
4a1e6c9e-5453-5d3e-8aa4-8d9fb590d88a | note | ---------------------------------
64622c39-a841-5731-b192-dddb25c67e4e | note | VERIFYING DOCUMENTS: Sign ITP
93f02c49-934f-5813-9933-2067599ab70e | date | Date Completed:
| checkpoint | 5.5 Conduit-Separation of Services
ea206090-e14d-5745-9b90-856c85cc0a7a | note | REFERENCE:
261afc55-cbcc-5635-a372-ae82d42de17e | note | IFC Drawings
57c41735-5ea2-5940-bb53-7b9c91bbbb3b | note | TS-SP-013
179b690f-157b-5ea4-bead-a7e5644c1c59 | note | L1-CHE-STD-043
aad012e0-8b28-50ac-a2f4-0b0ef4bbb92a | note | ---------------------------------
1a590a8b-0156-5594-b517-18eb8e106632 | note | ACCEPTANCE CRITERIA:
ff4f208d-8e57-5149-adaa-4ef11bc8f3a9 | note | Separation of services
33dfd4a9-601a-5421-b067-f81befd7e1ca | note | – HV: Min. seperation distance between HV conduits at least 50mm
f238ca11-4457-57b8-9854-87e9a40aa6eb | note | – VicTrack: 100mm from HV
6a9ad61b-56db-5e70-9518-8035fbf29543 | note | – Utility: 300mm to utilities
a07e4341-2844-5c69-a88a-6d6550dd5afd | note | ---------------------------------
c1743fa5-6eb5-564c-90dc-81bb3f54b011 | note | METHOD: Measure, Visual
f7764138-ca03-5741-a4ec-81d837d01292 | note | ---------------------------------
a16b683f-114e-5c45-b935-f078df941f40 | note | FREQUENCY: Each lot
add440a5-93e7-5822-8f44-8304ca8814da | note | ---------------------------------
2a9290b8-ff55-53b8-9522-03077780d23e | note | CATEGORY: IP
531af432-2b39-5ac7-9092-ea5731a80a7d | note | ---------------------------------
464c931b-0392-5302-a0fd-a33a307fe07f | note | RESPONSIBILITY: SE/Site Supervisor
43b603ba-930c-565e-a35b-80af0ec5d1c8 | note | ---------------------------------
b8b35e5b-d976-5141-900f-4916300a6301 | note | VERIFYING DOCUMENTS: Sign ITP
fc037328-b131-5937-b322-5a2f8443a4ad | date | Date Completed:
| checkpoint | 5.6 Conduit-Joints
18ab26f9-1948-5509-bb71-2ab41064de1e | note | REFERENCE:
d32d4fd6-05eb-55c9-b25c-5d2a83907488 | note | L1-CHE-SPE-070
54eeb862-131a-543d-922f-b4cfa0b1b5c8 | note | L1-CHE-STD-043
bdde8f06-57f5-53e8-9490-b83321b98c53 | note | L1-CHE-STD-070
4560bd08-d7bf-5a9c-8111-8ef590f33da1 | note | IFC Drawings
e878650f-bdab-51e7-b4f7-4faf6b66a8b6 | note | ---------------------------------
efcaa11f-9cc1-5a45-a4ee-4a97f0c959fc | note | ACCEPTANCE CRITERIA:
47327ba9-abc1-5523-9ea7-37b243ac7af1 | note | All conduit joints shall be made by utilising the spigot and socket ends.
91dd5dcc-a228-525d-98c6-a500aeb7a5d5 | note | Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer.
75e8db83-b4cd-5145-83f6-34a5be7e5b2f | note | The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer.
c903aa47-a824-5007-808a-9cc3909f8629 | note | Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
eeb8beb1-5ffa-5a2d-9c2f-97cde8a28a37 | note | ---------------------------------
670ea1b3-ebe7-5d6f-883a-2393ff554f53 | note | METHOD: Visual
d299352b-b97d-5e22-8f28-7aeda4ef2226 | note | ---------------------------------
c8dad3cc-e76d-556f-ba8d-3afb07812bc0 | note | FREQUENCY: Each Joint in each trench
90c9334b-4719-5d32-8ba9-fdfbe981e355 | note | ---------------------------------
0c25b74f-2bf5-533a-94b3-09146697115d | note | CATEGORY: IP
2ccc600f-7a55-5836-903b-61070d0c7f1f | note | ---------------------------------
dae017fe-ee80-5e55-bc4d-6d341aadefab | note | RESPONSIBILITY: SE/Site Supervisor
e1d23bd6-e7bc-5988-bb50-a8d70e2e8823 | note | ---------------------------------
1b8456c2-7510-5787-8f6f-705d66014256 | note | VERIFYING DOCUMENTS: Sign ITP
d9142768-86b5-5dce-ab2a-62317c4add93 | date | Date Completed:
| checkpoint | 5.7 Conduit-As Built Pick Up
41b024ba-3db1-5b38-a0a1-58e7b23a6f91 | note | REFERENCE:
d52aa1a7-11e1-5fe4-acd8-4527a7679d4c | note | IFC Drawings
05d7e3fc-ce18-5017-85b8-cfc02e60fcfd | note | L1-CHE-STD-043
b35d9a0d-dbc6-5a3f-a8b2-3e4cde281e7d | note | ---------------------------------
b8186c16-440e-5a29-9026-aff17afd8ca2 | note | ACCEPTANCE CRITERIA:
de66e833-8abb-5415-8423-8a49e59d16a2 | note | GPS co-ordinates to an accuracy of ± 0.5 m shall be recorded every ten metres for the entire length of the cable route / trench, and at all changes of direction.
d6c4444a-1ede-5131-a7d6-dcb52789f451 | note | This method shall also be utilised to capture all;
73aeb6b9-e528-54ec-be2b-0abf90546f73 | note | i. Cable joint locations.
db31078f-2120-58d3-84a5-04a213cb21a8 | note | ii. Cable pit locations.
746ba369-f704-5ce4-a9b0-d513d04415e6 | note | iii. Under line crossings
cfd072e8-a967-55fd-b87b-c7ab2836547f | note | iv. Under road crossings
4a782ea7-7d66-5abb-afc8-4a8ebea3acf9 | note | v. Other significant points of the cable route
0d2ee097-ef27-5ba9-a663-d24b42584402 | note | ---------------------------------
0e46f47b-25de-5f3c-af82-ba0aceaaf23b | note | METHOD: Measure
97db20ae-bf19-5b6c-a2a9-232784c59c69 | note | ---------------------------------
c4113f93-e06f-54a4-80a3-f582d4c9b166 | note | FREQUENCY: Every 10m
83b9bc32-301e-51d7-991c-38bda7f24b3a | note | ---------------------------------
e17584ef-9030-535f-a2d3-ca747d41eda9 | note | CATEGORY: WP
c18a924a-a58f-5139-a9c5-3dfa7d6775d1 | note | ---------------------------------
a222d086-36a9-5580-b240-0ff7f11a3dcd | note | RESPONSIBILITY: SE/Site Supervisor
0a122641-408a-51ac-a6fa-0a42fe8d2076 | note | ---------------------------------
712cb3c1-4142-5f56-99fd-73bcb6e55fb4 | note | VERIFYING DOCUMENTS: Sign ITP
479f6f26-2525-5937-8685-27579cef359b | date | Date Completed:
| checkpoint | 5.8 Conduit-Bedding Sand Installation
a5ecba00-6076-54e7-a966-d53e2745512f | note | REFERENCE:
5a860324-69f1-516e-9689-933c07cfb88e | note | IFC Drawings
feac06ca-d86a-507f-8e5d-79334f1a8540 | note | L1-CHE-STD-043
3e7b36a9-21e0-542e-80c6-1756c5415d1c | note | ---------------------------------
badc9c44-2a6d-52ee-a7e7-ed52da07671d | note | ACCEPTANCE CRITERIA:
91af2717-813b-5835-a890-dfd758802a6b | note | Bedding sand extends 50mm past edge of conduits.
1cb2a618-c2bc-5c5d-8b38-336e8d741d69 | note | Bedding sand extends 100mm above conduits.
03b0b93f-8b13-5f85-b7b1-185c16ddb5bd | note | ---------------------------------
d07b6f02-af0e-563b-b9d8-01dd0323752d | note | METHOD: Visual
7112f32d-e385-5d5f-9fd1-b93f1d2c033e | note | ---------------------------------
f36c44fc-758b-556e-b86c-326c2fcfd1ce | note | FREQUENCY: Each lot
d3156323-4283-5abe-a2c3-b5aef3842eff | note | ---------------------------------
342a9b99-9471-5118-847d-27c698ff0dd7 | note | CATEGORY: IP
b389f3a0-2e6c-5c90-92c0-7c9bcc08727e | note | ---------------------------------
ee910d60-3f45-522f-bac4-7acd7054b6fc | note | RESPONSIBILITY: SE/Site Supervisor
3bed6293-3378-5b58-bd07-6a9ef37dafe4 | note | ---------------------------------
484d3571-26a7-54b7-8066-2d7410d8f416 | note | VERIFYING DOCUMENTS:
edc1e544-033b-5dd0-bb57-62f2920f3ebf | note | Sign ITP
4cc9b037-8c25-5941-93b2-064c3e841faa | note | Attach Delivery Dockets
fe0ef891-b01d-5cd5-92cf-2b5a0871e23c | date | Date Completed:
| checkpoint | 5.9 Conduit-Protective Cover
73311859-1540-5bc8-a7c9-d6692521e149 | note | REFERENCE:
d21c26e9-74ba-51ca-967d-fdec85fd8389 | note | IFC Drawings
30b862d7-fd1b-5df6-8364-0e05ecad348b | note | L1-CHE-STD-043
7edc8764-c30d-583f-a150-028c35b39c7c | note | ---------------------------------
bcdace18-0d59-5fad-86d1-5b01816d5dba | note | ACCEPTANCE CRITERIA:
16bc11a9-4ce6-5246-aa75-ebc7662b3a3e | note | The cover strip shall be placed on top of the cables and overlap the cables by not less than 50 mm on each side
9f069712-ca4e-5116-be2a-b25bd91b5bd8 | note | The protective cover shall be no closer than 75 mm above the cable/s
a6db99d9-4669-5af6-846b-fbe32800ac2d | note | ---------------------------------
c35ef9e2-6e7f-56f4-b1eb-c5a196c78141 | note | METHOD: Visual
78292c70-90d0-59c7-8f65-fd55c23df731 | note | ---------------------------------
1dffe008-9c4b-5c00-a14f-bc996f3d255b | note | FREQUENCY: Each lot
be72ca41-8387-544f-ade1-d7d2909265d5 | note | ---------------------------------
27f04208-1318-539a-800e-53fbe047c6f8 | note | CATEGORY: IP
8f4316fc-37dc-5a4d-bc9b-4794ea2deb7a | note | ---------------------------------
95fdb6dd-8b3d-58a7-93cb-45b19c7a647f | note | RESPONSIBILITY: SE/Site Supervisor
1391ee5f-0155-5cae-a61b-69cea58de81e | note | ---------------------------------
3bfda7e2-287f-5822-b6e3-cb830ba280a4 | note | VERIFYING DOCUMENTS: Sign ITP
bc60f98e-284b-5f37-8bc1-ac727c9cb3ce | date | Date Completed:
| checkpoint | 5.10 Conduit-Marker Tape
7381eb02-49e4-520c-8fd0-b26db9055f7f | note | REFERENCE:
c2bf3ac7-ab7c-594f-96f5-f109e7932e91 | note | IFC Drawings
7e02cdd9-0398-5944-afa0-5db623058789 | note | L1-CHE-STD-043
b94ff2ec-1aac-59f5-8fe5-4248f960c653 | note | ---------------------------------
81412166-ba8a-55ca-9b59-235f2c899d0c | note | ACCEPTANCE CRITERIA: 150mm wide orange coloured PVC "DANGER RAILWAY SIGNALLING CABLES" marker tape shall be installed in all trenches 300 mm below ground level
c690abbf-ab12-5914-829b-d95faa19c75c | note | ---------------------------------
f41986e5-7413-52f1-9ddc-036817609578 | note | METHOD: Visual
11d88636-d172-5400-a2b0-bb5c3c8231ae | note | ---------------------------------
ad0905a6-39ef-5193-97e1-3cfd5391896d | note | FREQUENCY: Each lot
aec97f61-5918-5dcb-a233-984c580cfbfd | note | ---------------------------------
aa25033c-e722-5350-9274-5763df478834 | note | CATEGORY: IP
deff2ded-2a89-5d98-92c2-fe2384bf8112 | note | ---------------------------------
fabd5efa-1213-5406-8692-5dab1d3b5cd4 | note | RESPONSIBILITY: SE/Site Supervisor
bfc755c7-c67f-5268-bd1a-492a48e0a829 | note | ---------------------------------
07b3a91c-6157-53cc-9256-2c9ba6fbbb46 | note | VERIFYING DOCUMENTS: Sign ITP
52987845-b45d-58de-9e63-87090cc0132f | date | Date Completed:
| checkpoint | 5.11 Conduit-Backfill Installation
bb0b0cbb-e0e0-5228-8503-1937362ade6d | note | REFERENCE:
a45d370c-5d7b-5f4b-810a-b4e889495e97 | note | IFC Drawings
4371c914-c424-5f9d-a66f-e653b1b7141b | note | L1-CHE-STD-043 clauses 6.15 and 6.16
ce02c79d-b3f5-54ea-b854-d66036e1796c | note | ---------------------------------
64f9c4c9-b1fd-5183-bb16-59cc6ba2f215 | note | ACCEPTANCE CRITERIA:
6b02e706-8e7d-5b7d-b4ab-b706dc83081a | note | Backfill per trench profile
2e68b62d-a7b9-5d8f-ae91-a9100462c4b2 | note | – 150mm layers
686426f4-3da9-59f8-80ce-b3436a5a7464 | note | Backfill material to pass through 30mm sieve and be free of material that could damage conduit.
0c5d10e3-6418-5d33-9d62-c33458b26d28 | note | The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
04750a70-15ff-56d3-acc0-a8e145a4efc1 | note | Trenches under road pavement - backfill to be same material as the road formation material.
2cee32b8-c702-5c9e-bcf8-6d49a900e17b | note | ---------------------------------
9fe470cc-fd6f-51d5-82cf-5ff37a00f2c9 | note | METHOD: Visual
9500e0c5-9760-5b89-a5a0-577d8acc179d | note | ---------------------------------
67282431-1eec-509b-8ed6-2d23a0b8c588 | note | FREQUENCY: Each lot
e82ad2e6-e119-512c-99c4-6513914e6098 | note | ---------------------------------
1b653c0e-4073-564e-8aa3-6ae2355ea1a6 | note | CATEGORY: IP
ad8574c9-dc5e-595f-8133-747f48a05341 | note | ---------------------------------
c9174c2e-aa58-5563-929a-b071b1074b38 | note | RESPONSIBILITY: SE/Site Supervisor/NA/VicTrack Rep
4a48148a-e07e-5e05-8eff-5cab4175a927 | note | ---------------------------------
fe7454c1-c64b-5192-ae65-34727c333cc2 | note | VERIFYING DOCUMENTS:
24e0f884-b8f5-5e5b-9978-17918b3407ab | note | Sign ITP
d4e86ac3-6611-5a12-97f3-c4cc4af698ca | note | Attached Delivery Dockets
c5df2e16-1f19-5c30-8048-fc405d204f13 | date | Date Completed:
| checkpoint | 5.12 Conduit-Compaction Testing
a8cb80bc-03d2-58c7-9d2b-da778a2f87af | note | REFERENCE: L1-CHE-STD-043 clauses 6.16
e8d88c48-beb7-5f33-88b9-1a2036bf092c | note | ---------------------------------
e7efeca5-f167-544a-a835-7b2506cb86f2 | note | ACCEPTANCE CRITERIA:
89d90074-5c4a-5f4b-9e42-882e59455b34 | note | Compaction to achieve 95% Standard Compaction.
f10db769-dd26-5456-88bf-3ea243afed41 | note | The tests shall be taken on a frequency of one (1) test per 200 linear metres per layer or one (1) test per area per layer where any area of excavation is less than 200 metres long.
ba1e272f-1875-5d13-a4b7-a04c7e747379 | note | ---------------------------------
f56ecb4e-27cf-5e5d-acc8-dfd9812e718a | note | METHOD: Document Review, Visual
f7f83ba4-178a-51a6-a41b-7163abb95a0c | note | ---------------------------------
56aaf35d-83ff-5841-9346-869dd335e1fa | note | FREQUENCY: Each Layer & Every 200m OR Per Area
472e3681-cbe3-5a23-a8ff-8f92306f1737 | note | ---------------------------------
b5e1371d-3e00-57ff-a615-8ec6b76d43e5 | note | CATEGORY: IP
42877131-f3a9-5ab6-9bca-781f9d26edf9 | note | ---------------------------------
0d753054-d7c3-58e9-b9eb-408b36f268e4 | note | RESPONSIBILITY: SE/PE
cf202e91-8eb3-5e12-bd49-d98d29a38e2a | note | ---------------------------------
0a25dde7-3e36-5ad2-8e91-5f6300e48db3 | note | VERIFYING DOCUMENTS:
122d4f54-e4af-59b7-bbb3-bdc581d50ab9 | note | Sign ITP
20cb7c81-f0cf-5363-a038-f8fc66cd4ee3 | note | Attached Test Report
8e49f7fc-2999-5639-a3e6-b8b7681c66db | date | Date Completed:
| checkpoint | 5.13 Pit-Bedding
6e929e59-d5f8-57fd-8009-96f265cc78bc | note | REFERENCE:
9658d7d2-9abe-5cd7-8956-24c7785d3124 | note | IFC Drawings
6c5f6177-0ffd-5707-b0e9-f9f522e60030 | note | L1-CHE-STD-043
b7ec8bb4-dc86-56dd-8bfa-644f239615a4 | note | ---------------------------------
a247260d-f501-5fd7-9b53-f413a0735320 | note | ACCEPTANCE CRITERIA:
a0984011-0f42-5a55-a1d9-fb15161d0e99 | note | All pits and chambers shall have a prepared foundation of “A” grade 20 mm crushed rock not less than 150 mm thick
c1d09a7c-d3ed-5f54-a9fd-edec88829dda | note | Gravel drainage sumps shall consist of 20 mm aggregate with a minimum depth of 300 mm
50f1e8a2-a827-53f8-b2ff-ccb78b663626 | note | ---------------------------------
c5d90adc-01b6-54e0-9a3c-55ffe05dd8c5 | note | METHOD: Visual
f830c23a-a70f-5cf3-8595-6d5e26053574 | note | ---------------------------------
eed296fd-7fb8-5bc1-937b-bc54bd0f8be4 | note | FREQUENCY: Each Pit
f7ab3cb6-04e8-55ab-bffb-86b04478febe | note | ---------------------------------
90daa935-7e09-5a43-bfcb-dbab224741e2 | note | CATEGORY: IP
3f497314-bf57-5bee-b9f8-b9ccd7d05ac4 | note | ---------------------------------
ab8dcad5-16fc-5308-932b-22fded47d566 | note | RESPONSIBILITY: SE/Site Supervisor
f9156e77-bc1f-586c-9a23-91e2c8684b0f | note | ---------------------------------
461ba30b-ce93-5089-b3e3-ab5fda6214b7 | note | VERIFYING DOCUMENTS:
f5026022-dc64-5d34-ae2d-00f52690fcee | note | Sign ITP
a2878826-dd88-56e2-995a-cb8750162fe0 | note | Attach Delivery Dockets
5342bf1c-f0df-5dc2-a343-b2d8909b26fb | date | Date Completed:
| checkpoint | 5.14 Pit-Orientation
ce9064b5-109b-526a-971d-c19cc2681482 | note | REFERENCE: IFC Drawings
0280642f-737a-5590-9f72-9112da6e206c | note | ---------------------------------
edded9a4-e520-59f0-9c57-98a14063934b | note | ACCEPTANCE CRITERIA: Pit to be parallel to track and parallel to conduit route.
b4a077ab-795c-5a26-9eae-bf4fbfb3f34d | note | ---------------------------------
af57b689-c0d5-58bf-be95-36d643d7bfe9 | note | METHOD: Visual
e7ca725c-ad30-5223-8996-6314780bb38c | note | ---------------------------------
376d7ae2-aada-5425-9e49-d51fbf3e684d | note | FREQUENCY: Each Pit
5c1f5e69-cd27-5e3b-9fdf-2f1431886aea | note | ---------------------------------
d99272a3-3c8e-5447-b8ba-29dbe918d497 | note | CATEGORY: IP
b747a786-f899-50f1-9377-95eb6c73928f | note | ---------------------------------
92647f0f-176c-5b53-882c-599d8d4c11a6 | note | RESPONSIBILITY: SE/Site Supervisor
72c54259-ba01-5073-b551-ed1e26075f51 | note | ---------------------------------
322c88be-4b7f-5c17-8c3b-ad076bc71b2d | note | VERIFYING DOCUMENTS: Sign ITP
51ac27ec-0dcf-565a-95e1-12a1236bd01a | date | Date Completed:
| checkpoint | 5.15 Fit off-Conduit Entry
8bbbc45b-ee01-51b5-bdaf-403ad7851ccb | note | REFERENCE:
be03c965-cd2e-5ee0-a058-1831f1c46b4e | note | IFC Drawings
01876e0c-f2bb-5e77-908a-1c48a8cfd794 | note | L1-CHE-STD-043
7fd62aaa-b2c0-5a48-9819-d5c9a80a25f1 | note | ---------------------------------
e0e4e69a-06ef-5b38-a7e3-0d4c1cea1312 | note | ACCEPTANCE CRITERIA:
ed7951ea-c24e-527e-8fe0-cb663b006187 | note | Entry holes shall be 100 mm minimum from the base of the pit or chamber.
13b525b1-d879-5f54-a996-ce861ec029d8 | note | The end of conduits shall not protrude more than 50 mm into the pit space
f6a32e28-d01f-54a9-ba15-8b56c63eed06 | note | ---------------------------------
5d75bd9b-de96-5191-8eb5-9dfd648a9aaf | note | METHOD: Visual
b4d9b324-be1d-5093-9ec8-059adc623451 | note | ---------------------------------
b3baead0-eb73-5c9f-97b1-98a96aadd1d1 | note | FREQUENCY: Each Pit
498abb0c-19bf-5e2f-bbf1-49ef0c667e89 | note | ---------------------------------
c9bc3126-70db-54b1-9366-8c134c772ec7 | note | CATEGORY: IP
30133cde-9dd6-5562-8ca7-6857e6b19159 | note | ---------------------------------
e48114f6-f5c7-5729-a035-8b8aa8adcb2e | note | RESPONSIBILITY: SE/Site Supervisor
7edcbd9c-7e01-5b08-95f6-24f9d2cc1fa8 | note | ---------------------------------
92912a63-8eac-57e9-bc1a-bb0883798201 | note | VERIFYING DOCUMENTS: Sign ITP
c691f231-2c82-5b90-bc0e-ab3ad14a1a75 | date | Date Completed:
| checkpoint | 5.16 Fit off-Spigots
7255ceae-58bc-510f-863b-6a33fd42ebe6 | note | REFERENCE:
7ca5bb9c-a102-5c6d-b8c6-941ec52a7d72 | note | IFC Drawings
de9d0d13-4c66-5231-b0b5-a02972ce97e7 | note | L1-CHE-STD-043
18061692-2349-51e7-9095-2a4fb6e4ae5b | note | ---------------------------------
7465b800-cb64-516b-bdb7-ebe6a452ba9d | note | ACCEPTANCE CRITERIA: Spigot bush to be installed on conduits being cabled
4ae8467f-8654-5d38-95de-4d5adf754b0f | note | ---------------------------------
0b69cf1c-a46e-599d-8c18-82d0a639f7e2 | note | METHOD: Visual
6c5e3a4d-6db9-56fe-bc2c-3b7b51fe2496 | note | ---------------------------------
d0895e1f-9d08-5959-9e1a-a3eebd5505b7 | note | FREQUENCY: Each Pit
78ed9aa3-dc10-51c6-bf47-88fbe802a22e | note | ---------------------------------
219ebfbd-cdcc-5c84-9e45-5867411bb75e | note | CATEGORY: IP
9dca2379-59dc-5b58-91ec-10b908e37ba4 | note | ---------------------------------
1c0ebab7-24a7-51bd-a32a-50635882420e | note | RESPONSIBILITY: SE/Site Supervisor
169b2ebf-6f6e-5a52-bcb2-35d015b123b1 | note | ---------------------------------
9d81f594-c5a7-5c98-8bed-d1df32f5d1b9 | note | VERIFYING DOCUMENTS: Sign ITP
0979e033-dd93-5f29-b3a8-313b09a94eb2 | date | Date Completed:
| checkpoint | 5.17 Fit off-Draw Ropes
4074d254-e689-5c9c-9f97-b269db15761e | note | REFERENCE:
a267b033-a555-5d53-b4dd-1fe2b9897fcf | note | IFC Drawings
ffe70d7b-b6a1-5622-988a-405e7bf888ed | note | L1-CHE-STD-043
3e5eef90-bf7f-505f-9a06-3842c33577a6 | note | ---------------------------------
65bcfe82-503c-5768-8870-88d59a4bbd3a | note | ACCEPTANCE CRITERIA:
acce1bb7-df37-5294-82fb-b87c50735d48 | note | The draw wire shall be continuous for the complete length of the conduit run.
313bc700-150a-534b-beb0-442d5e5b860a | note | The draw wire shall have a minim of 2 metres of slack within each and every pit along the conduit run, and shall be suitably anchored at each end of the conduit run and then sealed with proprietary end caps
ffde1b6f-e94c-5299-bf90-8c4c5500fed4 | note | ---------------------------------
ee0b0ff6-9dad-5764-9326-ba89586743e1 | note | METHOD: Visual
874e57a5-0e14-5e7a-9da3-69e524fcb269 | note | ---------------------------------
96367e10-6c83-5a08-9837-1aa5f429152c | note | FREQUENCY: Each Pit
00190f78-a539-548a-bbf6-5c69803e65b6 | note | ---------------------------------
883e55ea-7e8b-54f5-a219-da0b592abf84 | note | CATEGORY: IP
99e71e22-eecc-546a-8dc5-c7d4b4b805bc | note | ---------------------------------
44c930a8-3509-5152-b8ca-7c2b2cbe76f0 | note | RESPONSIBILITY: SE/Site Supervisor
edcdb8cf-b135-5030-bbd7-72e0203ae5c9 | note | ---------------------------------
883174bd-24a3-5be2-8dac-cedb0445ad96 | note | VERIFYING DOCUMENTS: Sign ITP
a5cccea6-8f14-5a49-8402-41193885d3a6 | date | Date Completed:
| checkpoint | 5.18 Fit off-Step Irons
71ba9b5f-fbe9-5728-9d92-d494ec994b43 | note | REFERENCE:
59e86a22-60b7-5081-b4ac-a5b1f6e8582d | note | IFC Drawings
0502276a-32b0-5767-8d91-0074cfd8e74f | note | L1-CHE-STD-043
914b795a-58b9-5df8-b2b7-e11841d72fd0 | note | ---------------------------------
cec29dd4-e699-5327-b5bf-eecdb2dd3c65 | note | ACCEPTANCE CRITERIA:
e93bc8d7-cda1-5506-81d4-89a7d6e99ff9 | note | Unless otherwise noted on IFC drawings, the below is required:
7733028a-e8bd-57b7-8247-4e0eb7fded38 | note | All other Pits: Step irons/rungs to be installed if pit is greater than 1.2m in depth (including lid thickness)
24fe9aab-adb7-5973-b61d-8be74326db01 | note | ---------------------------------
1f6219f9-7cc6-5208-a98e-80333a0d7477 | note | METHOD: Visual
25c3c192-1f64-54f3-aa91-452f0c582486 | note | ---------------------------------
346e6e51-4035-5a5c-bcf7-bff81f58b88b | note | FREQUENCY: Each Pit
e528e64e-f057-591b-b636-cfee0a0bafd0 | note | ---------------------------------
2e074583-571f-584d-bc09-bd925efef47f | note | CATEGORY: IP
6706d7b3-dbd1-5caa-88c1-2b5fc89c2bd7 | note | ---------------------------------
f0e39ad9-e689-5ec3-9fbe-a8c05631193a | note | RESPONSIBILITY: SE/Site Supervisor
3aa3d424-1548-56e6-85a9-19b0ec7d4675 | note | ---------------------------------
896b5897-2e7d-5693-90c0-c5c9c3d5a447 | note | VERIFYING DOCUMENTS: Sign ITP
e08f2208-5716-52cc-a783-ee811cbaf668 | date | Date Completed:
| checkpoint | 5.19 Fit off-Spare Conduits
078867e8-e406-58df-9958-76fc1b922c48 | note | REFERENCE:
ca2d57c6-302e-5a42-aed2-4172bff4ff8a | note | IFC Drawings
36351984-fc87-5e38-a1b7-0e2e6649c603 | note | L1-CHE-STD-043
3012111c-4847-5725-99fa-bdfd25ff60da | note | ---------------------------------
cf4a0196-40fa-59df-8d7f-3539f285fbf6 | note | ACCEPTANCE CRITERIA: Spare conduits to be capped and to be included on survey report.
ccd0a270-bf9e-55ce-9549-071d72836b68 | note | ---------------------------------
0cb07a3d-a54a-59ef-80cc-77b669db7808 | note | METHOD: Visual
f2200096-b4c8-5d5f-8a72-19abbd6f0dec | note | ---------------------------------
beba62ec-0a4b-5883-8f9c-3a139a67a528 | note | FREQUENCY: Each Pit
6ede2914-d6cf-5ba0-a129-0682f334d118 | note | ---------------------------------
dafd858f-3a7a-554a-bd4f-d7e6c9fd764f | note | CATEGORY: IP
b02df474-2e99-53da-89f6-7838cb5b79c2 | note | ---------------------------------
a6a20aee-5690-5bdc-a56d-e6294174c92a | note | RESPONSIBILITY: SE/Site Supervisor
cafef71a-cf2d-5d2a-aab0-fcb8f5a5634b | note | ---------------------------------
54fe0f62-cf52-5942-bf4a-649567794564 | note | VERIFYING DOCUMENTS: Sign ITP
4676cacf-b9b8-56b5-b1e1-4bea550a75dd | date | Date Completed:
| checkpoint | 5.20 Fit off-Pit Lables
bc774510-1e67-54f3-b0d8-6ed72694a0c0 | note | REFERENCE:
43d45625-90e5-558b-8045-585aa41a0d64 | note | IFC Drawings
0fde9cc3-a34c-5cbf-b986-ce3ea4800701 | note | L1-CHE-STD-043
f333f995-75c3-5fce-8b68-4a848ef6aa9a | note | ---------------------------------
e6c08311-c982-5f2d-8540-ec612694923d | note | ACCEPTANCE CRITERIA:
acac89bf-5341-5775-a85c-d4fdfd21d5b3 | note | Pit labels Brass Label (30mm x 150mm)
5b925bb5-848f-5e3d-90f4-63cf6837146f | note | – Signalling: Railway Signals & Comms
0f6a2a96-70fa-58b2-89be-1b470d8745c4 | note | ---------------------------------
29c95b21-ecdb-572f-85fe-68ed656dc03d | note | METHOD: Visual
74bc9ef6-3716-5590-89c8-2ea741a836fa | note | ---------------------------------
147fc2b8-86be-543d-b95c-aff0c5ede740 | note | FREQUENCY: Each Pit Lid
3d4de1a2-7265-5454-9d07-4346fe6be89a | note | ---------------------------------
72956e06-dbf0-5da9-9191-1acb57adb6b6 | note | CATEGORY: IP
7e7665bb-ed2a-5f40-91de-aab10d68f173 | note | ---------------------------------
254a1fd4-4279-5046-8891-2d8807393326 | note | RESPONSIBILITY: SE/Site Supervisor
47d1416b-47cc-59cf-bbe7-665d709a1f5f | note | ---------------------------------
b6e74064-69d9-528b-b4b5-34eaa31e81e7 | note | VERIFYING DOCUMENTS: Sign ITP
3572ee51-69e6-5473-991e-15410fe046e9 | date | Date Completed:
| checkpoint | 5.21 Protection and Labeling-Non Trafficable Pits
74537bfe-bd02-5bba-914c-7cfe29834105 | note | REFERENCE:
62993115-efe1-52b4-884b-208ff14853cc | note | L1-CHE-SPE-070
2a9b9f59-b72f-5933-afba-6d5df565d237 | note | L1-CHE-STD-043
5af97cbe-e89b-504e-9741-a03758e4e817 | note | L1-CHE-STD-070
8f45259f-a956-5688-910b-5fa255b21517 | note | IFC Drawings
80d97669-bbc3-59b4-8a76-78cca8d8316d | note | ---------------------------------
80ca2703-6fe0-50d8-ac84-61f6f3fddea4 | note | ACCEPTANCE CRITERIA: Non trafficable pit lids to be 50mm above FSL and to have 2 x white bollardes installed at the corners of the pit.
9be96390-54e6-5ada-af24-845c3b616ff5 | note | ---------------------------------
60d0b6e3-52b8-53c8-8856-58b34fe67520 | note | METHOD: Visual
30957d99-bfb8-586b-83d5-5f75de10d8db | note | ---------------------------------
8069d1ad-5c98-5b2b-8c22-88fb3a42aac1 | note | FREQUENCY: Each Pit
faa20b86-4678-59cb-970a-f3f18672dfbe | note | ---------------------------------
41622397-f593-5531-a5e4-5e9c6f20d3a8 | note | CATEGORY: IP
c007c3c0-a2dc-5720-beaa-3079c8240c6d | note | ---------------------------------
bc24713f-81f0-5a8b-ac6d-3ab41f8fe19d | note | RESPONSIBILITY: SE/Site Supervisor
0cc72b46-e253-5361-9030-a5a2b77a93b9 | note | ---------------------------------
4b4ed166-f883-5107-8165-adc02a622cec | note | VERIFYING DOCUMENTS: Sign ITP
668f537a-d632-5571-99fa-17ee060b9eec | date | Date Completed:
| checkpoint | 5.22 Protectipon and Labeling-Cable Route Markers
308e2b03-accf-5b8b-99fe-795ee5b8f94b | note | REFERENCE:
71ddb68d-0bbf-507a-9372-31e8e6e10421 | note | IFC Drawings
263dc0c4-3340-5102-b4b7-03feda6be638 | note | L1-CHE-STD-043
5125832e-671f-52b8-9944-1a59ee3a024f | note | ---------------------------------
d2671f01-a9c3-543a-8cb3-275d72a32c22 | note | ACCEPTANCE CRITERIA:
93e0618f-1dcc-5318-b825-d5cb96309d37 | note | Cable Route Markers
853b8425-02f4-5ace-82ec-587108155c15 | note | – points entering & leaving the rail corridor
f0cefdb1-d911-5ec2-8187-9552e0e10cbd | note | – no greater than 100m spacing
e649b8ac-32f1-5444-8b00-537df1320ddd | note | – Change of direction (more than 5 degrees)
1ed495c9-9aef-5e93-8678-70e05391a4e5 | note | – White posts with marker plates for conduit runs
e395cb99-6144-5cb0-ad96-650b76ddbd25 | note | ---------------------------------
81b77381-6629-53a2-a893-247fe79b5664 | note | METHOD: Visual
0985cebe-1def-512f-92ae-bc730a988dce | note | ---------------------------------
ea701261-9498-5bcb-93f9-b8ec2b725d7c | note | FREQUENCY: Per Cable Route
65386ae2-883d-5221-94ed-26a22132499a | note | ---------------------------------
b63d58ed-e8f9-5671-8046-e9bbe93cce42 | note | CATEGORY: IP
b8bb3e47-c43b-549f-95cd-60e092049be6 | note | ---------------------------------
d5196054-fc1f-509b-aec6-f643489da1e4 | note | RESPONSIBILITY: SE/Site Supervisor
4afeefd4-9674-5fe1-bb0c-049d2fdcda6f | note | ---------------------------------
ce5bead0-63ef-5a2e-b157-2b592800aea3 | note | VERIFYING DOCUMENTS: Sign ITP
47978279-2b2f-5cf0-9978-383fda0bf60c | date | Date Completed:
| section | Post Construction
| checkpoint | 6.1 As-built Survey file
be9a9767-598f-55d9-b62e-6fe4bc49af73 | note | REFERENCE: L1-CHE-SPE-070 Section 13.1
4c3cb599-54f9-536c-810b-04b59256021f | note | ---------------------------------
0634eec1-8e0f-5718-818d-c6194eddf328 | note | ACCEPTANCE CRITERIA:
fa412b32-6ae3-56b9-8672-a431c7966709 | note | Survey report to include but not limited to:
c6d93540-80df-5318-87c4-1dc0575d9b7a | note | – Cable joint locations.
22a94382-c2bf-57c5-ab67-7f8e174a0a82 | note | – Cable pit locations (Corners)
51555784-b70a-504c-b4f3-31ca27971cad | note | – Pit dimensions & pit lid type
9b139d67-d045-5d21-b3fe-b68903028092 | note | – Under line crossings
fcc9aa93-72bc-5a56-bcf0-900290fc1301 | note | – Under road crossings
4b7fbdf4-329d-5c02-87d3-52619c849d85 | note | – Changes of direction
a3bad155-2a72-534a-b18c-0d3fa88cebdc | note | – Spare Conduits
1152deeb-150c-5e5c-8b8f-9b2268ba5ce8 | note | – Conduits labelled as per trench profile
64122a68-b1ab-5368-8574-bc8936dae21d | note | – every 10m
84ead3a6-4aba-52c1-9bdc-1e7c25b039cc | note | – Other significant points of the cable route
2780a2b3-e530-5280-94ad-911919a1acf1 | note | ---------------------------------
bc507128-316e-5aa5-bfb2-32b52cc45927 | note | METHOD: Document Review
36cd25a4-0407-5016-9866-c1318046e926 | note | ---------------------------------
9be53b44-5938-5aab-bade-3935dce84b37 | note | FREQUENCY: Each Design Pack
392a4c1d-e173-5d3f-a1f9-4886fc476b6d | note | ---------------------------------
767d69b5-3bc4-546f-ac43-e656d10d6f52 | note | CATEGORY: IP
085c3445-3fbc-58d6-9298-e04b24cf2bae | note | ---------------------------------
17a465e6-40d2-5452-83a8-4b71d1e2dc16 | note | RESPONSIBILITY: SE/PE
f73a314d-2b88-581a-8158-45652fcc659b | note | ---------------------------------
94e495fa-034e-5cfa-ac91-f8d311a3c2b8 | note | VERIFYING DOCUMENTS:
c99b6b47-0d0a-5b74-96d8-449bd06092eb | note | Sign ITP
673290c6-8e14-5da2-9d73-2be4cc96f757 | note | Attached Survey Report
d54036ab-a595-53f7-be54-fd9296cb7114 | date | Date Completed:
| checkpoint | 6.2 Engineering Redline mark-up
b79d37da-091a-584a-a128-6e49f2c91217 | note | REFERENCE: IFC Drawings
512fb310-5067-5523-afd0-0ac0fcfbca38 | note | ---------------------------------
a0d1852f-3170-5af7-adc9-59d98c119b64 | note | ACCEPTANCE CRITERIA: As constructed cable plans shall be provided for the entire cable installation and in accordance with AS 4799 and the PTV Infrastructure Drafting Standard.
c53c31a8-c877-582d-aa93-0f840a6b3381 | note | ---------------------------------
9ea9210d-c8aa-5c37-b580-61cbf07995e9 | note | METHOD: Document Review
b46c4cad-47c5-513b-8c1d-8dad62bdd0d2 | note | ---------------------------------
c198fee0-003a-54df-bfa9-99c78deccb7e | note | FREQUENCY: Each Design Pack
48ebbd47-f19b-5dbe-b88d-b12b323a208d | note | ---------------------------------
a508def2-7c12-5093-98b1-4a7f2ca2bb7b | note | CATEGORY: IP
7dfc6101-7172-5b36-96c0-b348b6a2ef37 | note | ---------------------------------
8510736f-fe54-54d2-9bbb-60712a5faee3 | note | RESPONSIBILITY: SE/PE
32f80c9d-4aa0-5aec-a1d0-5a9fec01cfd9 | note | ---------------------------------
9ea2d452-7d7b-5002-b08b-0f67dab9df82 | note | VERIFYING DOCUMENTS:
80e0023f-7fce-5a6d-bfe4-3806dfa8c5ab | note | Sign ITP
0d8cf878-4f95-583d-9084-f15adac248e1 | note | Attached RLMU
08864fe6-0201-5aea-bda0-1e94a4e5767f | date | Date Completed:
| checkpoint | Metropolitan Roads Program Alliance Final Inspection
9cf75333-a764-5237-854c-936b0df0b862 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
dade164b-c80b-555b-a6e4-ea3fee3d10f5 | textbox | Name:
be2b6a30-c9b1-5bad-b529-d52f43218a9b | textbox | Position:
eeb4cecb-fb9d-5ee6-8835-3afa32185565 | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-RAIL-CAMMS-MTM-Stormwater Drainage Rev 0 | itp | ITP-RAIL-CAMMS-MTM-Stormwater Drainage Rev 0 |  | 858657f8-8819-4b23-8bb8-ae41a661d944
| section | Referenced Documentation
| checkpoint | Referenced Documentation
ee0f1665-f439-5778-8996-b6b588da05c3 | note | Document Title: ITP-RAIL-CAMMS-MTM-Stormwater Drainage
ca9d17f2-29ba-56a6-a100-99b7c3187e72 | note | ITP Description: Stormwater Drainage
c5036338-012b-5962-8959-6240580c8e7c | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
c12a1f08-325d-5c32-acf2-8dc238f4ab10 | note | Discipline (e.g. CIV/STR/RAIL): RAIL
48cf106b-6259-51fe-8fec-09db1dc83b3a | note | Revision Number: 0
43da4b3d-8fbc-5482-b586-7fdb3f1f0b43 | note | Revision Date: 12/08/2022
125a0c32-8fd8-56e0-b84e-de1a002abd97 | note | ITP created by: Justin Kreinberg
e7f9fa0f-e51e-5b46-a0a1-6b9a6c6236aa | note | ITP approved for use by: Victor Mira
f873287d-6fc9-5473-9110-18a97e28102b | note | 1.1 - Non Dependent
57c32a93-f63f-5b4d-a0cc-15b9afb69fb6 | note | Reference Documents: VicRoads Section 701 (May 2020)
181c8fbc-13f1-5609-9e3b-0db7f720adde | note | 1.2 -
f0a42740-6b31-5210-aebe-63d601c37320 | note | Reference Documents: VicRoads Section 705 (June 2021)
617ebc07-b510-5c91-8547-37f7078a7d94 | note | 1.3 -
f075b407-a6ec-589d-b9f1-9f66f76e49f6 | note | Reference Documents: MTM Track Drainage L1-CHE-STD-030 (July 2018)
| section | Preliminaries-Materials
| checkpoint | 2.1 Drainage Pit - Supply
d35fb691-3fff-53db-bea9-7884543395ba | note | REFERENCE: Section 705.07
0d0b8b81-2930-578b-b868-619f2eba9ee2 | note | ---------------------------------
176605a4-5f4b-5859-9a35-d8e6e0ed4581 | note | ACCEPTANCE CRITERIA:
93903a24-2529-53a1-bd19-468e350abb02 | note | Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with 705.07.
a1e4191c-14c8-5dce-aea0-2fbad92fe53a | textbox | Enter: Teambinder Material Approval number
82f90c8e-c567-5de1-ba48-4262e22fa9df | note | ---------------------------------
eb02dd27-63d7-5270-a7b6-f5ee8f7b19ce | note | METHOD: Document Review
2467cf1c-b48f-5939-9b2f-b2a6394163a6 | note | ---------------------------------
4e22e45d-48b0-5f66-acc2-818538980ba3 | note | FREQUENCY: Each lot
8f21f7a0-2955-5c26-b397-a13c1b32fd73 | note | ---------------------------------
95b4b310-4a1f-5600-ba35-a3c69b7ab9cc | note | CATEGORY: HP
53d0674a-f8e0-5f54-a473-cbaaf411c3dd | note | ---------------------------------
45241d70-f4c6-513a-944c-4f344a98db8a | note | RESPONSIBILITY: SE
83d6435d-017d-5d4a-b7d9-2d4a96b60086 | note | ---------------------------------
117db91e-b88f-5232-8a54-6c7ec96ad22b | note | VERIFYING DOCUMENTS: Teambinder Material Approval
61929c14-d409-58f7-9a6b-737fc273c74f | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.2 Drainage Pit - Step Irons
249617d1-8ef7-5e60-9cb8-786b6e630206 | note | REFERENCE: Section 705.04
50de1a42-c0a7-544a-988b-47e155dd8a5c | note | ---------------------------------
58f05bb9-1346-598c-b5f0-a9a271765eca | note | ACCEPTANCE CRITERIA:
fb82c56e-b483-54f9-95b1-aa0c3c207379 | note | Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
ee380b23-2ffd-56ff-b927-3f5a5ceb6b5e | textbox | Enter: Teambinder Material Approval number
6f39f51a-2563-5c52-8e0b-80b6c3fdf3cf | note | ---------------------------------
4cf0af88-3aec-52c1-b44a-dabb111e76aa | note | METHOD: Document Review
b6b5dbc6-ad1c-572b-9ea8-601dedd3c4ff | note | ---------------------------------
15e8221b-1426-552b-8499-1aa47a1a10cc | note | FREQUENCY: Each lot
fd0f4f98-4cb3-53ac-9e46-6dfdeec68874 | note | ---------------------------------
f5e6a3f1-c94b-5f3e-a29e-7395861221c2 | note | CATEGORY: HP
1750a881-a46c-5f65-a02f-381ab14f87dc | note | ---------------------------------
236066b6-fe84-5df8-9a9a-77f69e3afeb7 | note | RESPONSIBILITY: SE
4aa57b68-c1c0-5bef-9f86-05416b63f0a0 | note | ---------------------------------
ad922f16-3afb-51f0-9abd-10cf7c77830c | note | VERIFYING DOCUMENTS: Teambinder Material Approval
aceccb1a-01ce-576b-89c4-934f5b503190 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.3 Drainage RCP Pipes - Supply
02b426b2-6280-5138-9d31-1d974aa874b2 | note | REFERENCE: Section 701.05
6ae553c2-ca7d-510e-b4ef-086d45bae2f6 | note | ---------------------------------
f1562463-519f-5771-a3b9-65cb871d0347 | note | ACCEPTANCE CRITERIA:
92522e6a-6e3d-5093-908b-743a712a1467 | note | Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with 701.05.
a39ffbe1-ed9d-5949-814b-5da898b8f444 | textbox | Enter: Teambinder Material Approval number
df99abc4-b95d-5c54-906c-92750fdd3741 | note | ---------------------------------
6207baf8-56e7-58e4-8184-cf14f9f86f08 | note | METHOD: Document Review
2165d4de-eb5e-504f-83f9-ba1c14d7025b | note | ---------------------------------
7e4aecaf-0a5c-54d6-b596-2c88a5dcacb6 | note | FREQUENCY: Each lot
75aace53-45e7-527a-8583-a84a87ce555a | note | ---------------------------------
990262ed-a1a5-55b4-b27a-63b5abdb9756 | note | CATEGORY: HP
8b365e65-5dc1-541f-982f-5b9d4a4913d5 | note | ---------------------------------
ccaedc50-6ca6-53c2-9f35-a3b9a5a6cd5f | note | RESPONSIBILITY: SE
1c412879-2448-52f8-baeb-1773e5bf0897 | note | ---------------------------------
6c6d4f30-73be-574d-a8ca-59d8c2ac4a9f | note | VERIFYING DOCUMENTS: Teambinder Material Approval
ee1235ea-b652-558c-8f48-0b46ef5a2a1b | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.4 Drainage Flexible Pipes - Supply
4b42108b-bf31-592b-8e17-97652c40353c | note | REFERENCE: Section 701.07
4da5202c-e8ec-5532-bf70-65815c18aeac | note | ---------------------------------
fe25e9ab-1d57-5212-bad0-2f29a8538d68 | note | ACCEPTANCE CRITERIA:
f6a4e174-3ea4-53fa-8135-eab9b55f0220 | note | Flexible pipes shall be supplied in accordance with 701.07
27aea3b7-46f8-527e-bcd3-f6c068614576 | textbox | Enter: Teambinder Material Approval number
7569500f-bb36-507c-b721-b8f65c4cc06a | note | ---------------------------------
38d7e840-2db4-542b-a60f-5ac5e9515f38 | note | METHOD: Document Review
4661889e-d64c-5a1c-aa94-618eb16db1f1 | note | ---------------------------------
ea901287-1084-50a0-90a8-c8d234a1e1de | note | FREQUENCY: Each lot
a3b64976-3d0a-5777-8550-0dc9fd722961 | note | ---------------------------------
b898c484-87e5-5b6b-a547-2c638f7bf07c | note | CATEGORY: HP
85f80947-c023-5afd-8ae8-d8df5e9cbc4b | note | ---------------------------------
68fa8178-43a0-5486-91a8-27106d4d7277 | note | RESPONSIBILITY: SE
7493a83d-224c-5e31-a842-6993245af300 | note | ---------------------------------
c3b6b87e-c570-5c8d-9a4a-861adf35a5dd | note | VERIFYING DOCUMENTS: Teambinder Material Approval
d9743002-2d19-5f48-b8f9-673ad851342f | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.5 Drainage Slotted Pipes - Supply
33f95161-186c-5789-945f-6a336aa441cd | note | REFERENCE: Section 701.07
a3d00c9c-932a-5ecf-89cf-cc6de5e9d23f | note | ---------------------------------
cbe915e1-e354-5f93-9600-51573dc520af | note | ACCEPTANCE CRITERIA:
6ac404e0-569a-5b26-9eff-af9938e8ba1c | note | Subsurface drainage shall be supplied in accordance with 702.04
68f97cd9-cf0f-5f2e-90dd-9e22805cf0df | textbox | Enter: Teambinder Material Approval number
1e40e83a-21c3-5125-932a-80e84b28a7c6 | note | ---------------------------------
7aab155d-dcf6-590c-89e1-05ff82809c62 | note | METHOD: Document Review
e5bbb8ee-9fb1-55ae-8a2f-f16bb71dbddc | note | ---------------------------------
2215b88b-a7b2-5ff4-987c-04e43d33ae87 | note | FREQUENCY: Each lot
c31a3c15-1553-51f0-ac9a-9c9a433a48d0 | note | ---------------------------------
35808bbf-8f0d-5fcc-96b7-991a9b51cfa9 | note | CATEGORY: HP
faa83399-21e5-5737-a783-11282fbf7d17 | note | ---------------------------------
f86e29e1-66df-5dcb-93ac-16dd13751864 | note | RESPONSIBILITY: SE
c88050b2-66f1-5bde-8be6-763aa2ecb0b4 | note | ---------------------------------
4d812e67-d6e2-571d-b67e-d80ff80df937 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
b7b02ae6-ac82-5c96-83dc-9c8c2b7cdbd6 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.6 Drainage Bedding Material - Supply
ace21155-794b-5bf1-893e-a81c478fe97b | note | REFERENCE: Section 701.09
a2527941-f1e5-5843-bfa3-3ab3baab3108 | note | ---------------------------------
d6275d7a-a541-5cc7-b70b-b21401af8d20 | note | ACCEPTANCE CRITERIA:
2fbe0a1f-37c4-51ff-b0ad-a6be070f56fd | note | Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
8ee0743c-1bc0-55c2-82dc-fb6f444ee84a | textbox | Enter: Teambinder Material Approval number
086bc06d-0161-59ee-baaa-21c60b9ada33 | note | ---------------------------------
3916bbf4-dcc8-529e-8c57-dba79f5145d0 | note | METHOD: Document Review
66613016-5666-5f13-9f1a-d2b8ae07d07a | note | ---------------------------------
5b49b9f8-8222-54e8-9f6d-5252fad10de7 | note | FREQUENCY: Each lot
25680218-bc2a-5253-956f-4ecaa0300424 | note | ---------------------------------
b17266fb-2460-5520-abe9-87facb2125d0 | note | CATEGORY: HP
d51816a2-a478-5edf-985e-e709e8a26bff | note | ---------------------------------
0508c454-3218-58b3-9042-e32078a99195 | note | RESPONSIBILITY: SE
3aeb1c7c-d631-5d97-8819-d0c6223faff8 | note | ---------------------------------
86c7f31c-68a8-5d1f-b194-15e3c47ebda0 | note | VERIFYING DOCUMENTS: Teambinder Material Approval
ff4507ed-bd7e-5e9c-90b6-3585d81b8ff1 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 2.7 Drainage Backfill Material - Supply
9bc5fe82-03f3-509a-940e-59dd44fb6f1d | note | REFERENCE: Section 701.09
0b1eacdd-5010-5ebc-b453-47775a5d26e0 | note | ---------------------------------
3f280de6-d595-5b24-a8ad-3f4c06f73281 | note | ACCEPTANCE CRITERIA:
d7a64c0d-1737-5fd9-89f3-966cf49b7dae | note | Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
0e0561bd-9ab2-5ea3-8c19-8d7d646d9f69 | textbox | Enter: Teambinder Material Approval number
8372510e-f2c9-5039-8238-bee6df3270df | note | ---------------------------------
d5c9d286-69a6-5f1d-b649-ffa0c693d0b3 | note | METHOD: Document Review
482b3714-4726-590a-99e9-4a357291a726 | note | ---------------------------------
f8a29500-fb49-5d1a-873e-bf098b0898fc | note | FREQUENCY: Each lot
2b82f3f7-f1c5-594e-9f3b-9a11e86b4b39 | note | ---------------------------------
9a6dcc54-9a09-5393-bf9d-456e6677edf4 | note | CATEGORY: HP
f7adff96-2203-5711-8ff5-0d8e2d374777 | note | ---------------------------------
f8fed124-ec9e-5a67-8eb6-dc99bbe46ce0 | note | RESPONSIBILITY: SE
eb8d0b49-4a13-58be-a048-40893a213697 | note | ---------------------------------
b3131080-e373-526a-bcf0-4a7d84758d6a | note | VERIFYING DOCUMENTS: Teambinder Material Approval
25716d88-2f9d-54ae-85ff-d1b3c0c735af | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Preliminaries-Procedures
| section | Pre Construction
| checkpoint | 4.1 Survey Set Out-Pits
24c3045e-d0ac-57b8-a766-93517d9a185c | note | REFERENCE:
65d723e9-0a55-590f-8403-ec2bef2392fa | note | IFC Drawings
1a1702aa-0e12-5527-969e-cbb197217b4f | note | Section 701.10
972eb1d6-5ba6-5344-b116-31fc8701d517 | note | ---------------------------------
b3497c5e-d2d4-539c-b2cf-9cbdcc2fe8e3 | note | ACCEPTANCE CRITERIA:
86b592cf-7026-5649-93e7-a109bb02d17c | note | Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
26739f1c-d4c3-542f-8c6b-826eac4aba81 | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
3a8068e6-602d-5de7-a37b-2002ed28a5da | note | ---------------------------------
de790a75-201c-5785-b08a-61cb339dc1b8 | note | METHOD: Visual inspection
1c0e42e0-a1de-5b89-bbd6-7e38d9244bb2 | note | ---------------------------------
e7cde081-9fec-5d90-a631-f15c57a2a455 | note | FREQUENCY: Each Lot
fb5c90ef-eda4-50a1-8718-701b43112cfe | note | ---------------------------------
3c601cb1-ffcd-5fd6-8864-dc8c0f262ce4 | note | CATEGORY: IP
b04c4f49-4a19-5339-9327-7e74a4a5a892 | note | ---------------------------------
c5eb69db-c61c-557b-9fb3-65272332d919 | note | RESPONSIBILITY: SE
e32fb930-0599-5bb6-bf4a-89eeba3aaf47 | note | ---------------------------------
cb6a4a70-c046-511f-866c-d58b7e2a288a | note | VERIFYING DOCUMENTS: This ITP
bd7c1d2e-4cab-5814-9769-e86786a0bedc | date | Date Completed:
| section | Construction - Pit Installation
| checkpoint | 5.1 Pits-Pit Excavation
ed6be0ec-1c62-5653-bbcc-1662170f51af | note | REFERENCE:
0cbfd44d-6c41-5300-b71a-96023c18dfc7 | note | IFC Drawings
6f91ef1f-02a9-57b7-b581-0d95886f6416 | note | Section 705.05
7d59e0c7-9b46-54a6-ac3d-9dc92a483be2 | note | ---------------------------------
e70ee95c-cb83-5058-b40a-6a3b8819985f | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
42e95654-e866-5d86-a256-b9f74968f0d4 | note | ---------------------------------
b870fb0e-5e69-53da-9f32-451622b18cdd | note | METHOD: Visual inspection
1bca50be-53d2-515c-9341-618d0522dff2 | note | ---------------------------------
c3b3cee9-6dcc-5db6-86e8-501ec35f8b5b | note | FREQUENCY: Each Lot
d4e2409f-58b1-5728-81de-b04cf8c4e791 | note | ---------------------------------
457a7cfe-1e7a-5bbb-a987-5b90b0f9edec | note | CATEGORY: IP
ea2f9a3b-1671-5a11-928e-3679e3b749de | note | ---------------------------------
ebf56e51-8b16-5aeb-9c59-9125185090d6 | note | RESPONSIBILITY: SE
4396d11b-1fa4-51dd-bf52-4435d138f09a | note | ---------------------------------
72dfbe1c-c464-5ab7-9e02-90cf517933dc | note | VERIFYING DOCUMENTS: This ITP
878ddb73-2b4b-5b25-8136-39ac23718970 | date | Date Completed:
| checkpoint | 5.2 Pits-Excavation Foundation
85a96a73-ff5e-51e5-8c04-498f12d75018 | note | REFERENCE:
712033fb-a9b7-510d-9ba0-75a0e52eda74 | note | IFC Drawings
e6765f0a-69f6-584d-a891-c7b32d8a7835 | note | Section 705.05
2b69a6b9-5616-54d2-ab00-43c5f4e5d281 | note | ---------------------------------
dea16ed0-fab9-5a25-bb8a-7e40653cea9d | note | ACCEPTANCE CRITERIA:
c99e3955-7a04-57af-9ab9-cdf9cf4a88c2 | note | Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
51b30dbd-0035-5670-bc46-0c9616282dd0 | note | > 80mm for clay foundations
719e2db2-7a1a-5398-ad81-3b41cb511144 | note | > 150mm for rock foundations
2ad43ef5-6811-59e4-a206-00826d7ca5cc | note | ---------------------------------
89a9f105-91c2-5b76-8323-6684834864ab | note | METHOD: Visual inspection
7cbe07a9-35e0-5895-9ae3-68a79e444fea | note | ---------------------------------
bdb00c1e-53ad-5f91-b651-a54eb35e4a0d | note | FREQUENCY: Each Lot
2cdd8b35-d087-5a06-b886-dbb32e26a1ce | note | ---------------------------------
3785669a-ca78-5783-8fb8-442984a0560c | note | CATEGORY: IP
39eca24b-03c2-55a6-a77e-5150b245fcc1 | note | ---------------------------------
331db0ad-de57-5f25-b239-ca91df89bb31 | note | RESPONSIBILITY: SE
67471aef-aea3-5b9b-88a8-4b42a8411f7c | note | ---------------------------------
355aa3c4-e68c-539b-9811-c66713209352 | note | VERIFYING DOCUMENTS: This ITP
b1505cc4-d68f-55a6-a09e-3092e2a737f5 | date | Date Completed:
| checkpoint | 5.3 Pits-Placement of Pit
85cd7ea1-f306-5598-baac-98e19da6f39a | note | REFERENCE:
8aa840b6-632f-593e-8217-138ba93d99cc | note | IFC Drawings
15f8f898-e5b4-5f0f-8798-27c8f6596079 | note | Section 701.10
c9979c2c-a4e0-5335-a8da-0af05f98f9fe | note | ---------------------------------
af86d084-4940-5c57-8623-80fe428b100d | note | ACCEPTANCE CRITERIA: Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
1e58d8a6-83d4-5a2b-b4e3-dffdb3d9898d | note | ---------------------------------
2ab17e29-3d9c-5b41-9d58-f28634d9964c | note | METHOD: Visual inspection
6d05f5c1-cd99-5369-b491-e03f61afd2ac | note | ---------------------------------
08dedde9-ec63-5ab7-b1d4-fc819660bb7c | note | FREQUENCY: Each Lot
da02ae8d-1a26-54ea-9ff9-e097cf8bbb47 | note | ---------------------------------
190d5bee-c547-52a3-bc31-885d27c1879a | note | CATEGORY: IP
011e21d4-2545-5df7-9300-2c1705557a55 | note | ---------------------------------
8c8d14e0-9dfb-5f68-b0fd-61f51a4c514c | note | RESPONSIBILITY: SE
af6f3432-07ec-5cce-abab-6f6cf54b4e49 | note | ---------------------------------
e713689d-4c80-5de9-ab9f-fb2c8965a9f3 | note | VERIFYING DOCUMENTS: This ITP
ea4acdd0-36ab-519d-a1e9-f31c9c7dac40 | date | Date Completed:
| checkpoint | 5.4 Pits-Jointing
ee2d2e28-80eb-5773-b7ba-09baeb128dc1 | note | REFERENCE: Section 705.11
45c67af3-d133-5e14-abfe-811500e85c84 | note | ---------------------------------
cab47e0d-ff4e-5bbb-b310-376ae61954f3 | note | ACCEPTANCE CRITERIA:
fc409264-d5e3-51d8-997c-d94ef0504e98 | note | All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
fc010168-a5d9-5b8b-bff5-45dce5f5b295 | note | Exposed reinforcement shall be coated with an approved epoxy treatment
ccac88dc-f7bc-540e-a702-01088c2b185f | note | ---------------------------------
3405c58c-815c-5bab-bb1f-17b6565469e7 | note | METHOD: Visual inspection
cb4eeede-9b00-5493-8aa9-7d43160ef0f7 | note | ---------------------------------
7f2b43c5-e363-589a-abf8-de0cfd7da6b1 | note | FREQUENCY: Each Lot
36b96de6-5865-5abb-a344-73de24356c3a | note | ---------------------------------
eff48ed6-2fde-594d-ad41-beae05169333 | note | CATEGORY: IP
dfeeb822-af59-5341-ba42-82686d48fe10 | note | ---------------------------------
c17f67c3-a359-5294-ab6e-65228d6bd126 | note | RESPONSIBILITY: SE
2939739c-59ea-56f6-9bba-3db4f00c14c1 | note | ---------------------------------
0b681a28-75a2-567a-8dcb-ebbece4ad935 | note | VERIFYING DOCUMENTS: This ITP
c4624971-1b90-5473-9471-38530abe8fb2 | date | Date Completed:
| checkpoint | 5.5 Pits-Shaping of Floor
f10c35d8-65d7-5b92-b88f-2b0b8a889794 | note | REFERENCE: Section 705.13
358daee2-973e-562b-b05c-9f7b337dc660 | note | ---------------------------------
954953d3-5ae9-5175-a49a-3f037772fda4 | note | ACCEPTANCE CRITERIA: Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
6e0ff7b7-fa57-5e66-91b6-a7f54abac9eb | note | ---------------------------------
2a2a9c4c-adb1-53c9-b956-fda8fc13d969 | note | METHOD: Visual inspection
35f00cd6-2c35-54b0-8434-ba50d0b89b85 | note | ---------------------------------
70f73234-7ee9-548e-b13a-3467d0a96f30 | note | FREQUENCY: Each Lot
f2776a16-304d-5cb5-8010-fcb8eb989cc2 | note | ---------------------------------
a0f88a33-6483-5989-8d00-9cf80aab2300 | note | CATEGORY: IP
1e636efb-65f9-5a77-8a9f-6ac9eb8549f1 | note | ---------------------------------
898d930f-4604-51a4-aa55-f1e249e12137 | note | RESPONSIBILITY: SE
1436ae27-0d2a-5a7b-9331-c8d89e8aefa5 | note | ---------------------------------
df0b565a-c79a-5307-a078-e700c99d52a5 | note | VERIFYING DOCUMENTS: This ITP
f07c80ba-e492-54f0-9464-83e2043a7f85 | date | Date Completed:
| checkpoint | 5.6 Pits-Step Irons
34ba0edb-b7fb-56f8-a7ef-92fccffc9f3e | note | REFERENCE:
41cf660d-15e7-5d17-8e60-1df09ee8b895 | note | IFC Drawings
75e0407d-f21c-57ad-bf13-1bbe6cf3ec81 | note | Section 705.12
702f758b-25a9-58f8-b63f-ad7c542980f7 | note | L1-CHE-STD-030
42e56a8d-e91d-5f9b-8948-5da4beccdd6f | note | ---------------------------------
eee614f4-ef23-5f0a-a8cc-d8197af6e1dc | note | ACCEPTANCE CRITERIA:
12ccab27-0ecb-5273-8ed0-d8179133e26f | note | Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them.
30bfe0b2-e752-51bc-b2ee-cf9444c83ab8 | note | Step rungs do not come within 50mm of the top of the riser
85ee49ac-02a5-51fe-a1bb-ca12919d295d | note | ---------------------------------
5aede39f-1bbb-5981-86c8-3a804a1193d2 | note | METHOD: Visual inspection
28b12efd-242c-5c15-aab8-41dc5fd30cdc | note | ---------------------------------
eb92abd3-89cd-5b48-a02e-931929e290eb | note | FREQUENCY: Each Lot
57ec8156-e8f3-515b-927f-684bc8bbc126 | note | ---------------------------------
e522f67c-fe93-5c71-9b6c-1c5a4749530e | note | CATEGORY: IP
1f7f9f75-928d-5b58-8db6-9047f72f8d90 | note | ---------------------------------
ba6c9f5b-1945-56cc-afa1-66df031fb173 | note | RESPONSIBILITY: SE
31584d5a-ad2b-5bc3-9e19-761b08481d97 | note | ---------------------------------
8bc7e1eb-9f1e-546e-8d12-2fe9f503ddfd | note | VERIFYING DOCUMENTS: This ITP
f6913d58-b792-546f-af64-f18f2230fa76 | date | Date Completed:
| checkpoint | 5.7 Pits-Fitting of Covers
4532c040-f590-5f96-af12-5b540a605a9d | note | REFERENCE:
366c940a-d048-5408-bbc6-837fc95f0c06 | note | IFC Drawings
d94ee30b-c1b1-5c77-9dda-34bb847252d4 | note | Section 705.17
7f92d463-5be4-5480-b2ad-bb74df9650c6 | note | ---------------------------------
47fab317-27c7-5275-ad0f-498e03c331f7 | note | ACCEPTANCE CRITERIA:
836d9c66-059c-5abd-bbda-3f0e3c925036 | note | Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
89b65fa6-f352-57a8-9245-9eda18f45109 | note | Height shall be within 10mm of the design level
34425cb7-da15-58d5-8f7d-752c8d051cac | note | ---------------------------------
0c3fb92c-39cd-5705-a401-12a03faf0a5f | note | METHOD: Visual inspection
bba49c76-c8b2-5080-bb06-1ba7274dc845 | note | ---------------------------------
486668c4-a7ce-5cc0-93d4-6bf7f24a6b39 | note | FREQUENCY: Each Lot
603c3a49-7425-522e-a769-21a0d5355fa6 | note | ---------------------------------
0dc9b661-5484-5700-9448-3ce8129872b9 | note | CATEGORY: IP
0fd4bc91-5731-59da-bc9d-e26c5517b637 | note | ---------------------------------
1755cce9-0031-5ec6-b6d4-b69a8f8900e9 | note | RESPONSIBILITY: SE
2ba28105-3498-5d96-9761-6c1306fa07e4 | note | ---------------------------------
b557e12e-f2c3-56ab-848b-c325265dcbb2 | note | VERIFYING DOCUMENTS: This ITP
7bb8eef7-adcc-5cf5-95f5-b18967eba967 | date | Date Completed:
| checkpoint | 5.8 Pits-Pit Lids
bd1098e3-8d44-5559-82a0-3ea0df6e5e4f | note | REFERENCE:
34e7359d-b39e-5e61-bf4d-a6e84d0a2ade | note | IFC Drawings
3d45db80-cc4a-5f63-b168-bf574e032831 | note | L1-CHE-STD-030
b6f9e720-43e9-5f27-a46d-3f7489714922 | note | ---------------------------------
c0e13d23-1d07-5c68-a38b-219d2bdcbc65 | note | ACCEPTANCE CRITERIA: All stormwater pits shall be provided with a locakable minimum Class D piit lid, grate or ballast cage in accordance with MTM L1-CHE-STD-030
63d8f780-100b-557c-b451-1bfbf517a8fc | note | ---------------------------------
2ffea3f0-1976-5939-82f0-363b23084255 | note | METHOD: Visual inspection
142000b6-0432-59f7-b6cd-1e23f6216688 | note | ---------------------------------
862c5908-7066-5c0d-b26b-7f7e839a3cc3 | note | FREQUENCY: Each Lot
0b97a811-e93a-5668-a4cb-006c0a1eee67 | note | ---------------------------------
808d5a99-9137-5304-9622-7fc18112d8a1 | note | CATEGORY: IP
5e3aaac2-ca5f-55cc-be6c-e04d04eb59c0 | note | ---------------------------------
d0478c26-032e-5d2f-bc7d-3af33fe815f2 | note | RESPONSIBILITY: SE
f06db88f-84e8-59ea-9ac8-fb1f1bcc2c93 | note | ---------------------------------
4c902db5-4669-5f40-97a3-6943b1e2dbf5 | note | VERIFYING DOCUMENTS: This ITP
2e61b87a-c2e7-5d5b-8d29-d3615917283b | date | Date Completed:
| checkpoint | 5.9 Pits-Backfilling Around Drainage Pits
b06e7bd1-dede-5309-b6ee-6a1859ac5bf2 | note | REFERENCE: Section 705.18
3a15db24-964f-57cf-b272-2571688601d9 | note | ---------------------------------
699361dd-85cf-50e1-bc7e-fb2112dc57c9 | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
86dcc65d-e469-5709-aef6-5f911079aa12 | note | ---------------------------------
eab1bfab-d8bf-5097-a482-588e7e1242fb | note | METHOD: Visual inspection
f7e471e8-eba0-5880-a3b7-45b8f10519d4 | note | ---------------------------------
fab3b738-ce7d-558d-80d5-aeac12f7ea36 | note | FREQUENCY: Each Lot
326eb8ce-3168-58ff-8610-2bf2b173abca | note | ---------------------------------
dd63fe2f-f2a9-524d-8286-52d7894eb559 | note | CATEGORY: IP
1869fd24-4964-5d0a-9e6d-f6028f91134d | note | ---------------------------------
ebd3f927-0fdc-594a-9c9c-56640fe49fea | note | RESPONSIBILITY: SE
0f5dcba4-64be-5110-9284-b27ed2abe28f | note | ---------------------------------
6321e96b-e970-5db7-8ec2-77404b531ef5 | note | VERIFYING DOCUMENTS: This ITP
bfe23dd3-021f-553f-8304-b4f985c23e3c | date | Date Completed:
| checkpoint | 5.10 Pipes-Trench Excavation
4d14f358-afa0-51c6-ac56-3ab0905bce8b | note | REFERENCE:
5fd7bf4f-2ea0-53b4-bfe4-16091c76165e | note | IFC Drawings
84365ac4-e233-573e-8080-3e5bd9fb58ac | note | Section 701.15
949e2451-0807-555e-ae73-104ec26499fb | note | ---------------------------------
37b6640e-54fa-507d-afdd-9cc6b18b13ab | note | ACCEPTANCE CRITERIA:
abd7a860-0881-524f-b8b9-f3c1ba0e51a6 | note | Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
56256ba5-a5a1-5e50-81d3-47b8a2e78e65 | note | > 300mm, < 600mm for RCP
c546965e-3e80-5d1f-967f-ac998f4dd9e5 | note | > 150mm for Flexible Pipe
f9e0d5ea-ad14-5832-90f3-aff6f02a6244 | note | The base of the trench shall be compacted to refusal using mechanical plant.
c1bf97ab-121a-5a78-bef7-a03183fb6ff4 | note | ---------------------------------
8dd74a29-f481-5ce3-b6ba-96237fa35cfa | note | METHOD: Visual inspection
82a0d95a-553a-5761-a6e5-59f0ad44375d | note | ---------------------------------
ee5aec51-0f4c-517d-84ef-ef67b4ccf78d | note | FREQUENCY: Each Lot
bb052810-abda-5583-b528-84c166b2818d | note | ---------------------------------
e249fb66-6291-5961-b80b-6836d48035a4 | note | CATEGORY: IP
2d017219-2582-5d0e-8edc-3c9f44fe6e82 | note | ---------------------------------
f5a3d236-3c4c-5420-b1c7-c9966d87c7f9 | note | RESPONSIBILITY: SE
5b9a58f2-e2be-51a4-a7ce-9c633db9f004 | note | ---------------------------------
2e68f86a-1561-5d5b-b7ed-8a687cdeca7e | note | VERIFYING DOCUMENTS: This ITP
479691f4-0a47-55b6-9e35-e3ae7e0cfa89 | date | Date Completed:
| checkpoint | 5.11 Pipes-Bedding Placement
b4e3f79d-f3d8-51d0-a352-f3a25736235a | note | REFERENCE:
1f271d1e-9b55-532c-b7a8-4ac68366e507 | note | IFC Drawings
08948b4d-71a5-5d7a-8d51-6cec79015c7b | note | Section 701.16
293a7ef2-cb0a-51d2-8779-18da5a6f771f | note | ---------------------------------
744abee5-8722-53c7-9751-32fa4d5be873 | note | ACCEPTANCE CRITERIA:
06893c25-64c7-56f3-b8d4-02caec541940 | note | Bedding material shall be provided and placed in the full width of the trench to the below minimum:
a04833af-65d1-5772-8c0c-ffb40d41a80e | note | > 100mm where D<1500mm
5f1d119f-42e0-5f45-a559-2d170dd2fa7b | note | > 200mmwhwere D≥1500mm
00522a45-06d2-5053-a3ac-bae07e8398f3 | note | Bedding material shall be placed and compacted in layers <150mm loose thickness
e54a318c-cfd3-5a72-90e2-5ca0704b28eb | note | ---------------------------------
0bd577d0-595f-5cfc-a9ec-44bfa92a6925 | note | METHOD: Visual inspection
8660f428-3cd5-5e96-94b2-465452d8d5d5 | note | ---------------------------------
2a0f0780-9f96-5589-b966-c29bd72f4e21 | note | FREQUENCY: Each Lot
d024a489-4f9e-51be-a76b-8056a91992fa | note | ---------------------------------
4b17f5fb-4c37-5e7d-b702-345208d43042 | note | CATEGORY: IP
2a3001f6-db6f-520a-96bb-88d22c1f1c16 | note | ---------------------------------
32545f4b-a18e-5a92-9aab-913d6f8ba3ef | note | RESPONSIBILITY: SE
f2649f91-0bc4-5676-8240-f970d2f3c213 | note | ---------------------------------
50d4adc4-dccf-5df1-8788-4c449f2aab26 | note | VERIFYING DOCUMENTS: This ITP
03c6db59-6e3c-5036-890f-ad8c5710bb49 | date | Date Completed:
| checkpoint | 5.12 Pipes-Placement of Pipe - RCP
06e15bf1-5e65-5e63-af80-b67d4271856d | note | REFERENCE:
9f159d52-ee9d-5fbb-bbdc-4a54e1a9de36 | note | IFC Drawings
f44ba8d0-a385-56aa-8c85-de23bc159514 | note | Section 701.17
8cf575bb-c238-56f0-908f-8a8c6994c51a | note | Section 701.20
44662b7d-def0-5dfb-a7a9-ee492f6dd3b3 | note | ---------------------------------
a99ae201-8a98-5d54-addc-ead713eb9813 | note | ACCEPTANCE CRITERIA:
f4fd9ed9-024a-5a61-b0da-9543402805df | note | Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
8654a0c8-b700-54c2-8edb-a8d2c66b3407 | note | Gaps between spigot and socket are in accordance with the manufacturers specifications
aee5635f-d0bf-59d2-83e9-ec4db47117eb | note | The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
480de007-bfcd-503b-9b7d-082368669b21 | note | ---------------------------------
507f39b5-8b6c-5a78-bfd6-99116e59a4e0 | note | METHOD: Visual inspection
9cb8386c-8df3-5a25-a701-9913139c7989 | note | ---------------------------------
35149eb1-d841-5eea-85ec-c4b8892f168f | note | FREQUENCY: Each Lot
536daa6b-9674-557c-a9ff-9269503e2375 | note | ---------------------------------
3eb4e9b8-e95e-55ee-9d66-7f0b19ded748 | note | CATEGORY: IP
33ba882c-5051-5202-95e8-c1bc814ba019 | note | ---------------------------------
42178f99-3aa6-515e-b50d-a6be12f96044 | note | RESPONSIBILITY: SE
ed2fbf33-ebba-5c2c-b193-20212630fdc2 | note | ---------------------------------
cfe287d8-471f-53dd-8ef4-528b8197a0e4 | note | VERIFYING DOCUMENTS: This ITP
da98a8df-aba4-5824-8f36-5e3a62e3dead | date | Date Completed:
| checkpoint | 5.13 Pipes-Placement of Pipe - Flexible Pipe
49ebfbdf-ea86-5e48-97a9-7aa8e060cf8e | note | REFERENCE:
0e7a30f9-403c-51fd-ae6a-20c2bed782cc | note | IFC Drawings
1aee6f40-17f7-5e18-aec9-4cd3f532cc92 | note | Section 701.17
5ff76d14-24aa-5a63-9055-57ec70219988 | note | Section 701.22
8e1d5d5a-ed66-5524-9ea8-3433af1c11f0 | note | ---------------------------------
6d6ef945-6f31-577e-83bb-7b39aa103c90 | note | ACCEPTANCE CRITERIA: All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications
37295e20-5c6f-5405-ac4f-a5355063dd7e | note | ---------------------------------
0dcc0960-808e-5429-9466-a4731d1fc196 | note | METHOD: Visual inspection
3328b9fd-3ec6-555f-b8c4-ae4d31393d18 | note | ---------------------------------
75794902-c9cc-5dab-9027-0c8a077e46a5 | note | FREQUENCY: Each Lot
66bd8ac2-2ccf-51d4-b6a3-80c3fc63d5d4 | note | ---------------------------------
9a783f71-6ce5-5691-9119-639849057cfa | note | CATEGORY: IP
318349bb-5ef0-5d7e-9c26-30ffaa446205 | note | ---------------------------------
2b827bf6-0e65-5c73-abbd-a052d0bc6515 | note | RESPONSIBILITY: SE
77e31f6b-35ff-59ef-9cbf-56e81a05b03c | note | ---------------------------------
551188a0-ade0-541d-ba11-652b68c90708 | note | VERIFYING DOCUMENTS: This ITP
2f6c5883-845b-51bf-8a12-104979a91f0b | date | Date Completed:
| checkpoint | 5.14 Pipes-Lifting Holes
2220f9af-ff2f-52ed-aac9-d03bf5ec5de4 | note | REFERENCE: Section 701.18
a7b56b7a-123e-51af-8618-145a8c5003af | note | ---------------------------------
252e31c8-5dad-5401-be4f-3878c055a07c | note | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
3de0cf93-4362-593b-b593-93641fae2513 | note | ---------------------------------
ccc02da8-a08e-57c8-a380-56e37b105906 | note | METHOD: Visual inspection
4a2ccdfd-6139-58a2-9999-485c8d456c07 | note | ---------------------------------
c14dadc0-c35a-5bcf-9759-eb06022489b0 | note | FREQUENCY: Each Lot
de0d2bf9-a228-5ac5-a8f2-d91cac94626d | note | ---------------------------------
ecbeb7b4-5103-5396-87c9-70597a14225e | note | CATEGORY: IP
5432f01f-9e75-5a23-871a-a73fdf979b39 | note | ---------------------------------
bdec262d-f7e1-5339-9689-2f541b3202a3 | note | RESPONSIBILITY: SE
2a8401d1-31fd-5ae0-9d26-640b92735419 | note | ---------------------------------
1c6583f1-afdc-546b-a3fe-9aa045d97df5 | note | VERIFYING DOCUMENTS: This ITP
ccaff243-1589-576e-9b5b-c8026af8157b | date | Date Completed:
| checkpoint | 5.15 Pipes-Survey Conformance
4e3e046b-9436-548c-b924-18289542a040 | note | REFERENCE: Section 710.10
66e43c9a-ccbe-50db-b93c-5bce25bea3f1 | note | ---------------------------------
6efd62c1-a4a9-56c4-928e-aafe8e7826fc | note | ACCEPTANCE CRITERIA: Location of drainage shall be verified by a surveyor prior to backfilling
f03dd153-9848-5d65-914a-12f511503aba | note | ---------------------------------
639ba107-f120-5a6e-b6ca-c4901be5343f | note | METHOD: Visual inspection
113d97b7-2825-5408-baa4-aad946bbcdb5 | note | ---------------------------------
27078ed7-3f69-5a5d-83f2-d33c83ceb0bc | note | FREQUENCY: Each Lot
b2d2ddd4-5524-54fa-9869-98e26432ebed | note | ---------------------------------
23f4a3f7-ec1d-5e42-bc7a-f2852cdff7b9 | note | CATEGORY: IP
c7239f3a-7f1d-5f96-9ccc-563e86980d37 | note | ---------------------------------
464423d7-c7c9-5c3c-8123-87285b55b87f | note | RESPONSIBILITY: SE
7421cbae-8301-5726-a2aa-11518a8e3d5d | note | ---------------------------------
d9d24082-7013-5142-95f6-ee729c78e1b0 | note | VERIFYING DOCUMENTS: This ITP
74f8c082-903e-5b1a-934c-b3a374e4df6f | date | Date Completed:
| checkpoint | 5.16 Pipes-Backfill Placement
b42df311-ea17-527f-b087-0d83dacdab2d | note | REFERENCE:
a417b9ab-ba11-512c-8f07-b8698f65b36e | note | IFC Drawings
b6f41a02-56ef-5f18-a78c-90032e2cb2ce | note | Section 701.16
5ea19ec1-2b5d-5e18-b1ab-d891f0b64fa7 | note | ---------------------------------
78dadb77-571e-5445-bf05-ce68e99dbdfb | note | ACCEPTANCE CRITERIA:
b3969438-529e-55d4-9872-f0f309c4dd9e | note | Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
7484e7e9-2e5a-5648-a6d9-5f8a2ac5b138 | note | Filling shall not be placed within 2.0m of the open end of the pipe.
8b8831d1-3c7e-5642-8bd7-be573629f0f8 | note | ---------------------------------
4bb396d3-abdd-5658-9469-79c799c859de | note | METHOD: Visual inspection
f9e52bcf-5c66-56db-a804-c6c3260e2faa | note | ---------------------------------
b09237b9-9ffd-527b-9055-065485aa1c14 | note | FREQUENCY: Each Lot
01e7a8fa-d452-5f31-a726-a7a0cf827946 | note | ---------------------------------
444c49b4-ab69-56ce-a048-ce28628d2e59 | note | CATEGORY: IP
e7eb91c9-a28b-53b9-b6e8-84d92d0c4f6c | note | ---------------------------------
6e252302-43b3-54ed-bd18-a89a96c204ce | note | RESPONSIBILITY: SE
3983c04c-edd6-5ca4-9757-8992ac6a5dd1 | note | ---------------------------------
f6c8524f-d310-5322-8cd9-cb22fa72eda9 | note | VERIFYING DOCUMENTS: This ITP
8517bf81-afe8-53d9-82c9-c0607b82626f | date | Date Completed:
| checkpoint | 5.17 Pipes-Backfill Testing
820058d3-598a-5434-9968-d4b1f215cdf3 | note | REFERENCE:
97677478-e79b-5693-8f53-be7efd687af8 | note | IFC Drawings
42458fb1-8e5a-5c1e-8e51-a220620d46ac | note | Section 701.20
d0a75b39-c421-5666-88a2-1fa0ead6f58d | note | Section 701.29
87b5e65d-95c0-5548-bdc0-1f77a9ad0de7 | note | ---------------------------------
5569456e-310e-52db-a278-9d5a6e4466c2 | note | ACCEPTANCE CRITERIA:
637dd737-3b4a-5793-9646-695f771a8954 | note | Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
d9d2d235-8a02-51cd-9f31-5d84aa57d169 | note | Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
8d08768b-539d-51fa-a131-be2738015d1e | note | ---------------------------------
62af36e5-d2a0-5361-b3a1-cbdb9449c428 | note | METHOD: Visual inspection
2328ac16-5c30-5008-ba9e-9d8daaa8a648 | note | ---------------------------------
b506f5c2-df8a-5dc8-80c0-319a8c84eede | note | FREQUENCY: Each Lot
0e0c2357-2bfd-543d-9023-e5e4bf97761f | note | ---------------------------------
0c33bf99-cb2d-52ee-97b8-a1a8c1881168 | note | CATEGORY: HP*
67ed0c34-517d-5ec5-a0d6-916fd1f3f499 | note | ---------------------------------
3c8ae780-9e2c-55c3-a312-5b06b73e0638 | note | RESPONSIBILITY: Nominated Authority
f2ca7ecd-4d04-5125-a1aa-73f817a5fc55 | note | ---------------------------------
6865ca43-0d59-516a-8ca4-27359b23bca1 | note | VERIFYING DOCUMENTS:
2819332c-48d9-54c7-8b09-276e9dc4292a | note | This ITP
7bd7c424-7165-5a55-be1a-337e02d2c2f3 | note | Attach record of test report
dd3786f4-0147-56bd-a8d5-d35a095fd7eb | note | Attach material delivery docket
b7040397-4b83-56c2-839a-a7ab5173d048 | date | Date Completed:
| checkpoint | 5.18 Slotted Pipes-Trench Excavation
b5b245ef-a343-5534-b357-d5751cb70886 | note | REFERENCE:
fd9c6005-9307-5731-bee3-cbcaf2424f03 | note | IFC Drawings
00f15a06-c160-5044-80ec-793490fb78c6 | note | Section 702.08
7849dc5e-af99-5882-8e28-fb7cc3e2d3a3 | note | ---------------------------------
46eca9e7-2dfd-59f4-8eac-f80d30592d4f | note | ACCEPTANCE CRITERIA:
78dd904f-e15c-5237-a785-a6682f9d34f8 | note | Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of > 150mm for Flexible Pipe
5cceb90b-6782-58c1-8c13-f6c38d7a8a3f | note | The base of the trench shall be compacted to refusal using mechanical plant and be <50mm below the specified level of the invert
53574fcd-13a1-500f-b6cb-87955612b7e6 | note | ---------------------------------
d60d3d4c-f27e-5e4c-a57c-a77b58eb762f | note | METHOD: Visual inspection
9eb1f72a-8b8a-5dbe-8ea2-23f9a13dd834 | note | ---------------------------------
61a6f493-76e7-5758-b8f4-cc46820d6bfa | note | FREQUENCY: Each Lot
6c8e0eb8-6fa8-5733-9f41-0f755974c27a | note | ---------------------------------
f2cc37ab-1376-5aff-9293-f31b6ad809b7 | note | CATEGORY: HP
c6884d8b-2da2-5951-b92d-662f96a4dba2 | note | ---------------------------------
c6ccdf9a-cd1f-5b08-8a2b-f32728e81ef6 | note | RESPONSIBILITY: SE
c7b18488-e8f2-5863-b340-30c60a8472c2 | note | ---------------------------------
4203bdbb-7783-579a-90c7-093dd285340d | note | VERIFYING DOCUMENTS: This ITP
38c7ce53-c0c4-5860-b190-eedfc9b24c89 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.19 Slotted Pipes-Geotextile placement
05c5ab3a-2513-5cc5-890d-0a6ab7a5057a | note | REFERENCE: IFC Drawings
dd2eced2-721d-5ac9-b794-d486f193e8e0 | note | ---------------------------------
33ad62bd-d418-5d95-b9a5-4b5cbae0655b | note | ACCEPTANCE CRITERIA:
84be3a73-e262-50ed-a59d-098fb71ab197 | note | Trench to be wrapped with geotextile in accordance with the manufacturers specifications.
e90bcdda-7b4d-50f6-98ec-823a0e01bbf2 | note | All laps are to have 150mm lapped at the top of the trench
68796600-c8b9-5a1b-abb6-f95efb7e6f17 | note | ---------------------------------
f4b72f64-aa07-5175-83da-1d97b970feb7 | note | METHOD: Visual inspection
c1609c5e-f9a8-576d-a45d-e754cb049829 | note | ---------------------------------
eb35193d-0047-5825-b6ca-427df50a6b63 | note | FREQUENCY: Each Lot
a6c68a3b-952f-58dc-9774-c97958253321 | note | ---------------------------------
37a2a97a-3c03-5cd4-9dba-0e4ed8a731f7 | note | CATEGORY: IP
ae432d08-f7e7-5787-ac6b-4879877a5213 | note | ---------------------------------
bc84a794-f8b8-5370-8112-fe4c0f8c5147 | note | RESPONSIBILITY: SE
997a0894-e01c-50e9-ba90-0f12d6cd874d | note | ---------------------------------
757b103a-4a58-58bd-a299-039a4e8a0fe1 | note | VERIFYING DOCUMENTS: This ITP
b6d580f2-adcb-5e0f-8253-379690996400 | date | Date Completed:
| checkpoint | 5.20 Slotted Pipes-Bedding Placement
eb16a4d1-0372-5539-8fd3-6ad01a7534a5 | note | REFERENCE:
ece36646-006a-597a-8478-ed4385431db2 | note | IFC Drawings
6a3f3ccb-54b4-5749-857e-7875d0c15018 | note | Section 702.09
32561caa-4556-5965-a497-6bac3b254dca | note | ---------------------------------
0f09302e-7ca9-5d2e-a52d-b1bf7807ffc3 | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
aa71f248-538f-5d28-b394-9d2310b0c95b | note | ---------------------------------
046e77e6-5b32-52de-9f5e-b45cd8a9aefe | note | METHOD: Visual inspection
d02a8581-bf3e-5a0b-aeea-1036deb8a464 | note | ---------------------------------
0acd30a6-ed9a-516e-9290-df75fe125c05 | note | FREQUENCY: Each Lot
a0412db0-c9a3-517b-8881-d3a975d16584 | note | ---------------------------------
e5ac17ec-613e-5265-8e6e-03cf9a0b2e40 | note | CATEGORY: IP
71a615d4-c89a-5fc5-8970-170e20e73ebb | note | ---------------------------------
1c4cc3d2-78b1-554c-88b8-6c706f11e7f2 | note | RESPONSIBILITY: SE
e6dbfb76-1f8d-58b7-86e2-62848202eb70 | note | ---------------------------------
0a363582-3953-5b1d-b756-362161b53dcb | note | VERIFYING DOCUMENTS: This ITP
e843858f-db7b-5e7b-a95a-6c8c6aa05377 | date | Date Completed:
| checkpoint | 5.21 Slotted Pipes- Placement
cdd94068-ed09-5ee3-bc60-0c686f48ad0a | note | REFERENCE:
d9876986-0981-5c73-a942-0c1097f3b275 | note | Section 702.03
66891bda-c8cd-569e-b93b-a5a2b2d98338 | note | Section 702.09
608b563c-e99f-58cf-ac03-c89085233dda | note | ---------------------------------
fcd85316-eb06-5036-ab23-ac1bb154d9ae | note | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the opening in the lower half of the pipe.
d3e68be9-5e20-5774-81d8-4eadab521d5b | note | ---------------------------------
a9ebddb6-64a7-5337-bc82-9ad595313389 | note | METHOD: Visual inspection
1eb6e129-a718-5c29-9169-52d7972bc473 | note | ---------------------------------
98ee3056-7438-5ad5-95b7-e9b9134a51a7 | note | FREQUENCY: Each lot
0601b374-12a9-5961-8a0d-004e0843e1a6 | note | ---------------------------------
e1aaba7a-b7b6-5c2a-b590-f958ff0a61fc | note | CATEGORY: IP
3ab7e929-cce3-5e20-a89f-c8b07616abfd | note | ---------------------------------
2bc8aa86-d197-59f6-a1e8-c6adf92bb499 | note | RESPONSIBILITY: SE/Site Supervisor
58fc6651-3614-58e6-922a-a70bc3a2253c | note | ---------------------------------
4addd832-5db7-57da-aa7c-e1224cb0aaac | note | VERIFYING DOCUMENTS: Sign ITP
a73b1f53-027f-564e-ada9-cdadb0bd57f9 | date | Date Completed:
| checkpoint | 5.22 Slotted Pipes-Backfill Installation (Granular Filter Material)
044baaac-a67b-5053-a032-56198d64febb | note | REFERENCE: Section 702.09
238f0ae0-adff-566b-8172-0a2435c65c39 | note | ---------------------------------
2fb73e0f-b078-55ec-b25d-d7f7044a1f38 | note | ACCEPTANCE CRITERIA:
efb7ee9f-8379-5ed9-b495-8cbb21ad66a6 | note | Material shall be placed moist and compacted in layers not exceeding 300mm.
f19bae9b-57a4-5d1c-aeab-30aeff2e650a | note | The method of compaction shall be in accordance with the procedures and reviewed by the NA.
3829893a-134e-5fed-b37a-4b7185ab8440 | note | ---------------------------------
b746ee56-d877-5035-a2e6-b6fb2054c643 | note | METHOD: Visual, Doc. Review
b830b5d3-68ef-5c1b-960f-59946746042b | note | ---------------------------------
198de62d-2057-5272-97ea-d5910c89f6a5 | note | FREQUENCY: Each lot
3ba3f732-fd4a-5b4d-afbc-8f7ec22206fc | note | ---------------------------------
d13d54dc-28ce-58b8-ac47-c70104268209 | note | CATEGORY: HP
1c5331c0-4470-584a-9539-4552b03267b1 | note | ---------------------------------
94bc40c1-5bf0-56d4-a5aa-3f08a275debe | note | RESPONSIBILITY: SE, NA
676a91d2-4a40-5786-9e7e-17f1aaf61242 | note | ---------------------------------
939c8c1d-47e7-5668-92ec-a1001062189b | note | VERIFYING DOCUMENTS:
42892726-ebc9-582c-b412-95ef849188f4 | note | Sign ITP
f4fd2f82-6ff9-5cef-9a23-81cc94471173 | note | Attach Backfill Delivery Dockets
7a22b10a-6610-5d63-8233-605a8a6ca72d | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| checkpoint | 5.23 Slotted Pipes-Backfill Installation (No Fines)
974522fc-aa36-5435-a088-ecf04e9e91ac | note | REFERENCE: Section 702.09
5e5fce74-fb8b-527f-8335-ac8db46896d1 | note | ---------------------------------
e7186fd4-c6dd-5211-9416-c889bbe23286 | note | ACCEPTANCE CRITERIA: All subsurface drainage shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
ae0dd1e7-3c62-596c-baf7-f8389fe2c0db | note | ---------------------------------
fda5e73b-5f11-5966-a540-fa5ce7b2dc08 | note | METHOD: Visual
a34c7f77-4614-5161-981d-804a502e7544 | note | ---------------------------------
4eff83fc-9bb8-5066-8ce3-0821e1ccddb9 | note | FREQUENCY: Each lot
a97903e2-6362-591b-bf96-6d75e9ea9101 | note | ---------------------------------
9cf93d9c-579c-56c7-8aa4-e624d5f230ed | note | CATEGORY: HP
b11b403b-e023-5d8e-aff7-00a60fe71cff | note | ---------------------------------
304c56c3-f9cd-52bc-8f42-c73d22f08315 | note | RESPONSIBILITY: SE, NA
f7bc0362-c179-5e7c-9c7c-dce7873bb7fb | note | ---------------------------------
20145e76-99ff-5337-906c-6e5a38042ed6 | note | VERIFYING DOCUMENTS:
1900f08c-ba76-5f98-b5dc-384faed8a9f2 | note | Sign ITP
ad9d87d0-1611-58a7-bb3d-fb47f156b079 | note | Attach Backfill Delivery Dockets
33adaa53-2897-5bb4-8338-fd1757b6eba6 | date | Date Completed:
| signoff | NOMINATED AUTHORITY HOLDPOINT
| section | Post-construction / Post-installation Activities
| checkpoint | 6.1 Flushing & CCTV
dc85a34b-ce40-57f4-bb58-ea98e113d82e | note | REFERENCE:
e702f4e6-55c7-5f80-aec2-51319c6a0ebe | note | Section 701.28
c6a499fb-665b-5a03-b480-1ad8a7e8278f | note | Section 701.30
c5217ef7-9f45-53c8-9a88-08d0db5345a1 | note | ---------------------------------
e43a0c02-be3c-5e1e-bd59-90b00d6ea889 | note | ACCEPTANCE CRITERIA:
b0a45514-25a0-5c0f-adca-0f449a05deb6 | note | All pipes shall be flushed clean from end to end on completion
72ec1625-98ba-545b-9717-2be8a5c37679 | note | All drainage lines shall be inspected after completion of earthworks to subgrade level and prior to construction of the pavement layer by an independent testing organisation using CCTV
e4a53ddc-8a69-5e84-b2a2-4684abfa30ab | note | ---------------------------------
5e895991-d071-5988-b5be-69fb39ec04ec | note | METHOD: Record Review
d1903101-56a4-5b73-a0e2-fe65df214dee | note | ---------------------------------
90686740-0360-5e95-86a3-95d728fb5b7b | note | FREQUENCY: Each lot
ecd1f3bb-6f66-5caa-97cb-a63f63d6952f | note | ---------------------------------
935734cb-3dfd-5130-be07-3b53c19c6589 | note | CATEGORY: HP*
46ef9af9-cc1f-593b-a252-930f1d5f95a6 | note | ---------------------------------
c430aab2-af78-51d2-9a07-167000ee2e39 | note | RESPONSIBILITY: Nominated Authority
249354c1-6db3-5e14-aff6-d033594a6a1f | note | ---------------------------------
20e2c0c6-fec4-5643-9a2a-2d07330bbaec | note | VERIFYING DOCUMENTS:
a429cdb7-91ac-5952-bf05-eee6a2bac67d | note | This ITP
3fcb9b40-a31b-56bc-adb5-036189305105 | note | Attach Inspection record
2f98c48e-6edc-59d2-a7ba-87898266fe4f | date | Date Completed:
| checkpoint | 6.2 As Built Information
48796809-da90-5ef8-b819-d095dab9c113 | note | REFERENCE: Section 701.10
081ba7f1-0a9a-50e5-8e1b-cf589fbf98fc | note | ---------------------------------
00141b82-678e-523e-8877-c7cc3efe2597 | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage is within the tolerances specified in 701.10
bd8d4df5-e55d-5a75-b525-8a4aecfba789 | note | ---------------------------------
7cc3b521-5216-5d8a-b287-597d3ad9e499 | note | METHOD: Document Review
1ce55bc9-0394-538d-871a-83ca85a6d174 | note | ---------------------------------
22c7c124-c0d8-565b-b961-a7b01e77d2ad | note | FREQUENCY: Each lot
05da4a4e-c905-58e1-9ec4-6d182e89e495 | note | ---------------------------------
a61c2355-dd35-57eb-b4b6-c747d2e38e58 | note | CATEGORY: IP
b8965b1c-d73c-5990-ac40-858c00230bfb | note | ---------------------------------
47950599-6932-53d6-920f-0b306013bbc6 | note | RESPONSIBILITY: SE
4494bc3d-d4c6-5769-99ed-dcdb10c19075 | note | ---------------------------------
dd0c8171-f023-5c45-aefe-8cafbdb8b81e | note | VERIFYING DOCUMENTS: Attach Survey Conformance Report
8193a011-7cf0-54bc-a7d8-54084df7c2a7 | date | Date Completed:
| checkpoint | 6.3 Non-conformance Report (NCR) Closure
7282d987-74e1-598c-b48a-ac8e0d0d9fa7 | note | REFERENCE: MRPA Quality Management Plan
a0aa31ed-567e-549b-b6a9-6c9db4f99509 | note | ---------------------------------
58939b71-f09f-5147-9df1-c2b6fa7aae66 | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder
bd757316-40c7-520f-b8b2-b538e23b49b3 | note | ---------------------------------
faeac183-b317-53b4-93ce-10fa785b2b8f | note | METHOD: Document Review
5725ff7b-27f6-5efb-8770-958fc629bf06 | note | ---------------------------------
5d2e5fed-b16d-5b89-8561-7957647bf728 | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
62d298c7-3a73-5a4d-8add-e422b03b5af9 | note | ---------------------------------
08cc5676-d90d-55f0-ac31-4bdafac9b211 | note | CATEGORY: HP*
7bc906e3-8b2d-5ba3-9575-90f35cbbe589 | note | ---------------------------------
48846afc-24e4-56a9-8f11-99aae2179fd1 | note | RESPONSIBILITY: SE/PE/SPE
e8b09220-5dbf-53b0-a2ac-0a84d2cf6e69 | note | ---------------------------------
7ff47de5-2b43-55ba-be2d-4a6c98c34d73 | note | VERIFYING DOCUMENTS: This ITP
d80159cb-e873-59e7-a5c6-d5c44bc799b7 | date | Date Completed:
| checkpoint | Metropolitan Roads Program Alliance Final Inspection
aaa886a7-9224-551b-83ed-a507a443a674 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
b6b1953f-c577-592c-95d2-7f1f15ea7bdf | textbox | Name:
805d8c22-d1f8-5270-ac6a-526bd44ba46a | textbox | Position:
1704ad4a-c42a-59f0-85a2-e5925c9d132c | date | Date Completed:
| signoff | Sign ITP
| checklist | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 | itp | ITP-STR-Concrete Coatings (Protective &/or Decorative) Rev 2 |  | d5963e0e-ff74-4ae6-a8f1-89193596998a
| section | 1 - Referenced Documentation
| checkpoint | Reference Documentation
ebf62cfd-6169-55bb-b642-47cde6574b8b | note | Document Title: ITP-STR-Concrete Coatings (Protective &/or Decorative)
0d6f147a-6889-5476-90f5-b7b2375f4e24 | note | ITP Description:Concrete Coatings (Protective &/or Decorative)
08d94395-4086-5c1a-ad4f-268718a4d92f | note | Discipline (e.g. CIV/STR/RAIL): STR
21c9acf4-cb51-5929-8c11-06abd7bdd3b7 | note | Revision Number: 2
dbef52d2-5964-5a24-9fc1-9b1f5ba0bd2c | note | Revision Date: 11/12/23
ed27cd5d-0871-50db-88e1-325bbee9162e | note | ITP created by: Mike Freeman
5e4f72f9-0335-5833-b6e7-1a7bdd412fa6 | note | ITP approved for use by: Mike Freeman
651479ce-4ae6-506b-9713-362bfb5dc4ed | note | 1.1 VicRoads Section 685 November 2018
628cb3da-fa4d-5290-a4ef-de7dc7a3f9b2 | note | 1.2 VicRoads Section 686 November 2018
| section | 2 - Preliminaries
| checkpoint | 2.1 - Anti-graffiti System Selection
e3356397-e9ae-5fdf-a29a-094b4664308e | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (e)
1013ee35-52fc-50a7-b685-40932484d08b | note | – – – – – – – – – – – – – – – – –
22f215bd-1368-5ac4-a0eb-c9c1a74ad7b0 | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
d037cfec-e65f-580a-8641-14f0de76aa8b | note | i. be either a film-forming or a penetrant system ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification) iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses (film-forming): WFT total = 175µm min. OR WTF per coat = 88µm min. DFT total = 100µm min. vii. adhesion to substrate (film-forming): 0.75MPa min. viii. application rate (penetrants) as per the minimum thickness on the manufacturer's TDS
64356883-472a-5cf4-84e7-aeccec806c3a | textbox | Enter: Teambinder Material Approval number
0a8baa96-f4b6-50e0-a239-7432af5d2902 | note | – – – – – – – – – – – – – – – – –
917c101a-6ac0-59b2-818c-ed539f7f0f7c | note | METHOD - Document Review
06b5efa7-1fe9-5f35-93ec-cffbee415eb8 | note | – – – – – – – – – – – – – – – – –
ca88bda9-2bd0-5457-b8b5-53d5447abef3 | note | FREQUENCY - Once, for each coating system, 14 days prior to application
bff12959-c556-578a-b022-6d88b260a2a8 | note | – – – – – – – – – – – – – – – – –
608d0b73-551e-5f3a-bb9a-62429b1f00a5 | note | CATEGORY - HP
27d26cea-13cc-50ff-866a-812c94dad374 | note | – – – – – – – – – – – – – – – – –
f11df0d6-cf94-55d3-82af-cb5e278d28f4 | note | RESPONSIBILITY - Nominated Authority
d9ef5ea7-c0c1-5273-984e-aa493e4b6950 | note | – – – – – – – – – – – – – – – – –
426d507a-7999-525d-9f76-7bed362e410e | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
326b82a6-9a1f-5f76-a7da-0c710d513d70 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Decorative & Anti-carbonation System Selection
9ba097e3-c0b0-5a0a-8594-0e29776d14e0 | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 686.04 686.05 (a) & (b) Table 686.051
ec62a386-26cb-54eb-9d92-5583d2373c0b | note | – – – – – – – – – – – – – – – – –
b08bef56-299e-591e-9918-e1b2d2ba303a | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
99ff4637-77c9-5605-a46f-c101120dee52 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
00eca1c6-321d-5e65-b4af-a4341cd72905 | textbox | Enter: Teambinder Material Approval number
0b2a1fb2-eaae-5f46-80ba-97a4af8bae4e | note | – – – – – – – – – – – – – – – – –
5f3aae9d-b414-5436-a3d8-62e16043dbde | note | METHOD - Document Review
9200d8a4-5584-5b8c-91c5-ebf4ed962768 | note | – – – – – – – – – – – – – – – – –
f70d6eea-7569-512f-9110-2e02298478fe | note | FREQUENCY - Once, for each coating system, 21 days prior to application
1c684f1f-75d2-5af5-8bf4-7d9835f96a31 | note | – – – – – – – – – – – – – – – – –
665acc0c-9c65-56f2-b803-25e2a45a6436 | note | CATEGORY - HP
474b5895-860b-59d7-b23f-6832ed5e8b00 | note | – – – – – – – – – – – – – – – – –
0248b879-d0c2-5445-be97-1a8bb729f908 | note | RESPONSIBILITY - Nominated Authority
ccd657d7-a608-5160-ba92-07948cb5eecc | note | – – – – – – – – – – – – – – – – –
d5ae6aa4-49df-5327-9776-5f5e1f36c00c | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
ea5c3d04-e594-53a7-aa30-f980313d7e62 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
6ed310b0-84ca-5f25-8a29-3194df5fe308 | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051
cb3ca86f-cebe-593f-89ce-483165f1be23 | note | – – – – – – – – – – – – – – – – –
3f377b2c-8281-5c45-a205-93991e02ab91 | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
5f3bbb48-bdca-5a3f-aa6e-72f2f72d93ea | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system ii. be water or acrylic based, solvent-free with all coats compatible with each other iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system iv. be non-yellowing, colour-fast and not subject to fading v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure vi. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 150µm min. vii. adhesion to substrate: 0.75MPa min. viii. able to bridge cracks up to 0.3mm wide ix. able to be re-coated within 24 hours x. have a minimum pot life of 1 hour xi. compatibility to an alkaline surface xii. equivalent air thickness >150m xiii. equivalent concrete thickness >450mm xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s xv. Water vapour equivalent air layer <4m
a527c540-8ff4-5f71-a90b-dd049d78c9dc | textbox | Enter: Teambinder Material Approval number
984b6d5d-7f48-5653-b456-511a327b133b | note | – – – – – – – – – – – – – – – – –
cc588d9d-71b3-5ec7-badc-1ec4295a4a37 | note | METHOD - Document Review
de693d16-872f-5e85-bbe5-384f32c08957 | note | – – – – – – – – – – – – – – – – –
b3bfd4b4-58ad-5fcb-becd-0cda4f0e7145 | note | FREQUENCY - Once, for each coating system, 21 days prior to application
5e3c65c1-cf5a-5a8d-a2cf-923e15d1d166 | note | – – – – – – – – – – – – – – – – –
94b5a294-0d04-5bee-9d01-9d7f3982f0e2 | note | CATEGORY - HP
5551e8c1-b6e1-5eab-aa78-502568be24bc | note | – – – – – – – – – – – – – – – – –
022cbee2-6857-589a-8690-bf9f37e12d26 | note | RESPONSIBILITY - Nominated Authority
d39cc64e-c258-5971-8691-939f50aacc64 | note | – – – – – – – – – – – – – – – – –
53046865-466c-5a5f-aba1-4e41cab5a4eb | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
f8d790b4-0c2f-57a6-aada-9adec6f440fe | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
4f4ad9e0-62ae-541f-a677-80b09bd14782 | note | REFERENCE - IFC Drawings Coating System TDS Surface Cleaner TDS 685.04 685.06 (a) & (b) 686.04 686.05 (a) & (b) Table 686.051 686.05 (c) (i) & (iii)
3ae5ea70-fc1c-5d82-bd4a-ca7e5bd288f1 | note | – – – – – – – – – – – – – – – – –
9ef16377-105e-59c5-80cc-3a54e01577ef | note | ACCEPTANCE CRITERIA - The system shall be selected based on the following criteria:
2ca7603e-f1b0-5187-9edb-09e5879ca409 | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat ii. all coats to be compatible with each other Penetrants: iii. active ingredients: Silane = at least 95% Solid silane & silane cream = at least 80% Silane-siloxane & siloxane = not specified iv. application rates: Silane = 2 applications of 0.3L/m² min. Solid silane & silane cream = 1 application of 0.4L/m² min. Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS Film-forming coat: v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) vi. to be water or acrylic based, solvent-free vii. to be non-yellowing, colour-fast and not subject to fading viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure ix. application thicknesses: WFT per coat = enough to achieve the total DFT DFT total = 200µm min. x. adhesion to substrate: 0.75MPa min. xi. able to bridge cracks up to 0.3mm wide xii. able to be re-coated within 24 hours xiii. have a minimum pot life of 1 hour xiv. compatibility to an alkaline surface xv. equivalent air thickness >150m xvi. equivalent concrete thickness >450mm xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s xviii. Water vapour equivalent air layer <4m xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
23178a56-041a-5b91-81e8-928ab8948818 | textbox | Enter: Teambinder Material Approval number:
635386c1-93db-5483-bd0d-f580b51758b8 | note | – – – – – – – – – – – – – – – – –
7dba8bc9-8271-5250-835c-1e12ea8b84d3 | note | METHOD - Document Review
133b289d-060d-58e2-a83c-3fcb99babfb1 | note | – – – – – – – – – – – – – – – – –
cc97afc4-2b39-5df9-b205-6fe40abf7cce | note | FREQUENCY - Once, for each coating system, 21 days prior to application
30ac2cee-24d0-50df-b85a-0cf35a67ef8f | note | – – – – – – – – – – – – – – – – –
bbb59dd1-10df-5d31-8970-6140bc46fb5f | note | CATEGORY - HP
f2bf8a94-7986-59bb-9885-a236ab30d332 | note | – – – – – – – – – – – – – – – – –
cbc1bcad-959c-5c7b-a13d-4de8518ed94d | note | RESPONSIBILITY - Nominated Authority
84b3dacd-f7e0-5371-98ee-71a6af21d0c3 | note | – – – – – – – – – – – – – – – – –
e1da6992-0193-5bbf-890d-3b7baeb3e094 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
92e4bbb4-97c8-5ad3-a317-84c600f34c33 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Quality Documentation
eae5d80b-c016-599f-ab51-78cc9f346ea8 | note | REFERENCE - 685.05 686.04
fdf409f7-735a-5710-906a-ad912b494477 | note | – – – – – – – – – – – – – – – – –
79a87b4f-46ad-5236-9208-a1353bde9942 | note | ACCEPTANCE CRITERIA - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
763949da-25a0-5ac1-8262-9daf23903dd3 | textbox | Enter: Teambinder Hold Point number
cde6674f-c008-5a9f-9ce0-9b648f14b724 | note | – – – – – – – – – – – – – – – – –
f0925e50-f1ec-5299-a070-523a7dda4335 | note | METHOD - Document Review
8fdf4e23-3b3c-5df6-a6e5-35cb68377cbd | note | – – – – – – – – – – – – – – – – –
6931745a-41ef-500c-8315-036afb590d55 | note | FREQUENCY - Once, for each coating system, 21 days prior to application
75f359a2-5648-59cb-9f82-3f8e40885f00 | note | – – – – – – – – – – – – – – – – –
fb476e5c-2283-50d4-a977-24cd548e2997 | note | CATEGORY - HP
8ec4e513-1c7a-5e3d-bef5-30d1733d1174 | note | – – – – – – – – – – – – – – – – –
bc7da4b3-2e81-5b96-9f95-3f8af8ecf8d3 | note | RESPONSIBILITY - Nominated Authority
d98573ec-7e23-5c81-8a0b-e18df476deb6 | note | – – – – – – – – – – – – – – – – –
abd3847c-ba4e-5fd8-bed4-2a4b1d3dd52c | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
30a2d5a5-5749-5728-9045-67e54593b853 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Coating Personnel & Equipment
da9ee805-125f-581a-87e6-effdd85085ed | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.16 686.19
ff494f7e-2345-5244-8e34-cb08b5e2a66d | note | – – – – – – – – – – – – – – – – –
746621e0-0e2c-5612-9b2f-b3e55810a06e | note | ACCEPTANCE CRITERIA - The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques. Application personnel require 2 years minimum experience. The supervisor shall remain present at all times. Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
f274aec6-2b08-5445-b4fd-3005a5b2c970 | note | – – – – – – – – – – – – – – – – –
acf2a470-0c74-53ab-b093-80472a93990f | note | METHOD - Document Review
9a5da869-c48c-5264-9ee2-195a1b9ab3bd | note | – – – – – – – – – – – – – – – – –
2586c726-1433-514d-be39-c525a6d6d64f | note | FREQUENCY - Once, prior to application.
5e9fa58b-11e4-5b56-a160-02b3e76709d1 | note | – – – – – – – – – – – – – – – – –
02ecbe53-e72d-57fa-99d2-81ba73e41ff4 | note | CATEGORY - IP
bafa73c1-1104-5612-90e6-29d97fa45e8e | note | – – – – – – – – – – – – – – – – –
59376cc0-9ba1-5c6f-b66a-2521eb38a572 | note | RESPONSIBILITY - SE/PE/SPE
4c49042b-e27c-5b92-8b06-1f4312593e6f | note | – – – – – – – – – – – – – – – – –
ea197588-2222-57ff-9026-643e12d2f976 | note | VERIFYING DOCUMENTS - This ITP
5d6fe0bf-9bf4-54f5-b741-a1d553a6cd2b | textbox | Date Completed:
| checkpoint | 2.7 - Protection of Adjacent Works & Property
0ceaccd8-9400-574e-a6a9-9c042388e22b | note | REFERENCE - 685.17 686.10
79de4c34-49e0-5d71-84b5-86da45e6b898 | note | – – – – – – – – – – – – – – – – –
044182c5-4bd4-57c6-bdfd-48ac6aeb7771 | note | ACCEPTANCE CRITERIA - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes. No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
941f732c-dce5-5dd0-95e2-31bb19efecf8 | note | – – – – – – – – – – – – – – – – –
3fbed370-8cdd-515b-b92c-19abf892b7b1 | note | METHOD - Visual Document Review
0ee11e8b-bde3-5286-915e-9259df20de95 | note | – – – – – – – – – – – – – – – – –
27e8a024-dc73-5e20-b30d-aa2df7d387af | note | FREQUENCY - Where applicable, 2 days prior to application.
c25e0d71-1a52-59fb-8418-59fcb053bf4f | note | – – – – – – – – – – – – – – – – –
767449d0-bcb7-5450-87a6-cfcc82eec914 | note | CATEGORY - HP
5157a25b-b894-583f-8d59-cd702dafb84a | note | – – – – – – – – – – – – – – – – –
93ea71ad-c38e-5bba-b351-791bcfbd3e7f | note | RESPONSIBILITY - Nominated Authority
0dd3069d-504b-5025-bd58-e11354951403 | note | – – – – – – – – – – – – – – – – –
ab4c458c-33e4-5623-817f-8ba794b27850 | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
5aedbd96-2f32-5d39-83d9-a540bd7b612c | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Minimum Concrete Curing Period
60811e2c-403e-5fde-b078-4144c18e67c6 | note | REFERENCE - 685.08 686.16
77e16cc1-e830-5e9d-a548-0c0347ccb22a | note | – – – – – – – – – – – – – – – – –
9c014dfd-4244-53d4-9274-32902f674198 | note | ACCEPTANCE CRITERIA - Concrete shall not be coated until the minimum concrete curing times have elapsed: Standard cured concrete = 28 days Accelerated cured concrete = 14 days Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
e32e7401-21ad-5025-b50e-8d9077fe4aae | note | Note: All durations may be reduced by 50% if the moisture content is less than 10% when measured with a moisture meter.
d3e11755-02b0-5df9-b04f-35df9a29a774 | note | – – – – – – – – – – – – – – – – –
de2c25a3-5ecf-5283-adb7-bb9a197a6f49 | note | METHOD - Visual Document Review
7c3330e7-75ac-5de5-ae51-802a2712a593 | note | – – – – – – – – – – – – – – – – –
518f294a-00bd-5846-a481-3978d227aa9a | note | FREQUENCY - Once, prior to application.
3da45566-95a5-53ab-bdcc-1c43424e236e | note | – – – – – – – – – – – – – – – – –
57dfd387-7151-59bb-bbc9-8dbb0329a7fa | note | CATEGORY - IP
b577f13a-d0cd-59b4-8a9c-76d878cbe201 | note | – – – – – – – – – – – – – – – – –
60783966-fa20-5a69-abda-504bc465716b | note | RESPONSIBILITY - SE/PE/SPE
295b4fc9-5de6-5d83-8d0c-e12bb223feaf | note | – – – – – – – – – – – – – – – – –
4710e1a3-f9c3-55cc-84df-a953b929b1b5 | note | VERIFYING DOCUMENTS - This ITP
42a8e490-ac6e-53d0-9a65-f51363c90024 | textbox | Date Completed:
| checkpoint | 2.9 - Trial Application (or Past Performance) Inspection
b181a02b-c5dd-57ab-99dc-631841ea09ec | note | REFERENCE - 685.11 686.13
58d31442-4380-5e4a-80c0-54de8735ed3d | note | – – – – – – – – – – – – – – – – –
bf4ffda2-3251-5a5f-8208-fbbe84ff3a4f | note | ACCEPTANCE CRITERIA - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate. Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
5a19ec67-7fe3-5b6b-a540-0fd8f91684f2 | note | Attach: Inspection Photographs OR
ee39c334-0cb0-53c7-b1b2-872b41ba5967 | textbox | Enter: Teambinder Hold Point number
a819c9c7-3b1d-5e48-8297-b28350a4e7aa | note | – – – – – – – – – – – – – – – – –
5ac32b70-75c6-540b-8108-3ae65d1431b2 | note | METHOD - Document Review
3effc6f8-f925-569f-9001-261403b91032 | note | – – – – – – – – – – – – – – – – –
eb9d364d-3185-5a6e-bfd5-9dc4352e67f1 | note | FREQUENCY - Once, for each coating system, 7 days prior to full coating application
c4160185-ed20-5843-8826-66a805cfb2a8 | note | – – – – – – – – – – – – – – – – –
4cef1ff7-ed16-58bb-bad0-16e642d46fac | note | CATEGORY - HP
1ad865ec-66c4-5435-b9e3-652162153887 | note | – – – – – – – – – – – – – – – – –
971eedca-4b32-58a0-a9ee-e8ecee3acddd | note | RESPONSIBILITY - Nominated Authority
764f1439-0a02-5908-9b51-50e77acab72f | note | – – – – – – – – – – – – – – – – –
ffc9108f-8904-56e1-8efe-6e68f883f75a | note | VERIFYING DOCUMENTS - ConQA Hold Point Release
2a8a08db-3d71-51c5-89ef-6f89188c37d8 | textbox | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Pre-application Activities
| checkpoint | 3.1 - Material Records
dbb45701-19bd-5b30-8137-74ff002e12d8 | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.10 686.12
469e2e3c-3ef8-59e0-850f-eeb5fa0be05e | note | – – – – – – – – – – – – – – – – –
3256b853-35cf-5152-b4fe-7fe4c9c38524 | note | ACCEPTANCE CRITERIA - Materials shall be brought to site in unopened, sealed containers, clearly marked with: the manufacturer's name & address product reference batch number quantity manufactured in the batch date of manufacture
9fc3bfb9-9756-568b-b412-ca31a4241d21 | note | Product beyond the manufacturer's shelf life shall not be used. Each product shall be traced to final location.
477ed76f-f724-566c-9eb4-675b542bddc8 | note | – – – – – – – – – – – – – – – – –
7f60e6b2-96d7-5575-85d2-24f15ad847cf | note | METHOD - Visual
c2d1f819-c67d-5f04-8e4b-904186bcda83 | note | – – – – – – – – – – – – – – – – –
3657c5f7-0a3e-568c-a4a0-20b8613cb352 | note | FREQUENCY - Prior to application
1662024e-67f5-5576-99ec-c4809b60d7d4 | note | – – – – – – – – – – – – – – – – –
512fa0fb-29fd-5aa1-8f6e-356a8b5d6809 | note | CATEGORY - IP
1912f92a-78a4-5d9c-8029-2529d3cc2d7a | note | – – – – – – – – – – – – – – – – –
9f3e0404-629e-5518-895d-6fd61089d6a4 | note | RESPONSIBILITY - SE/PE/SPE
3ca75a3e-d842-5106-a23b-5e52d6e99a71 | note | – – – – – – – – – – – – – – – – –
1c195274-2b83-5e11-a804-b2b68115901f | note | VERIFYING DOCUMENTS - This ITP
e2e18451-4933-5b3d-9be3-661c9ea534c8 | textbox | Date Completed:
| checkpoint | 3.2 - Weather Conditions
91cf58f1-fe83-5a4f-937b-e1406a3dbfc7 | note | REFERENCE - Coating System TDS Surface Cleaner TDS 685.09 685.12 (a) 686.11 686.14 (a) (iii)
17ef4f56-d449-53bd-b3d6-93badb06cb3e | note | – – – – – – – – – – – – – – – – –
17a31810-9c02-5073-9cd7-9d8bc245209d | note | ACCEPTANCE CRITERIA - Coating systems shall not be applied under any of the following conditions:
8792d8f9-24bf-563f-8431-6f06812d2b7e | note | i. windy conditions where spray/splatter may be generated ii. when wind-borne debris is likely to contaminate the uncured surface iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate vii. when the substrate surface is wet or damp (unless it is required for the coating system)
2c07e0c4-8eb1-5c28-88d8-eafad960667e | note | Weather conditions are to be recorded.
8395e254-842e-5249-92bd-ebeaf0aa2346 | note | – – – – – – – – – – – – – – – – –
965ab86e-8a85-5d3e-933a-05b40fd690c5 | note | METHOD - Visual Measure
ba36040b-db19-5f4d-b72c-bd8ace72bc01 | note | – – – – – – – – – – – – – – – – –
03f089f8-29aa-52da-b45c-580badd91e61 | note | FREQUENCY - Prior to application and every 4 hours per shift
eb9e92e0-19c7-57d2-bddf-0952accc7980 | note | – – – – – – – – – – – – – – – – –
d89789d8-a331-5f7e-aa78-d456a7f2739e | note | CATEGORY - IP
56dba6e8-b928-56ce-a88c-784849e5f124 | note | – – – – – – – – – – – – – – – – –
9e7702ef-e28e-59c4-b582-c9f0eea222d2 | note | RESPONSIBILITY - SE/PE/SPE
1bcd2c80-9f0f-5edd-8545-ce84d973dd2c | note | – – – – – – – – – – – – – – – – –
acc01882-972e-5efa-a02f-17ef37715fe5 | note | VERIFYING DOCUMENTS - This ITP
9a222357-4454-50b4-b8c5-e86af8c7cce2 | textbox | Date Completed:
| checkpoint | 3.3 - Surface Preparation
a0861294-29e0-573a-9117-90d432b7c5f9 | note | REFERENCE - Surface Cleaner TDS Coating System TDS 685.05 686.06
11aa7912-d515-5eec-892a-d789c82bb49d | note | – – – – – – – – – – – – – – – – –
c51cdf6f-b661-5293-96a6-f8cccc909676 | note | ACCEPTANCE CRITERIA - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means. The surface shall then be flushed with water. Any concrete defects exposed during the surface preparation shall be repaired accordingly.
67ea195f-1ece-5920-8c4e-47516cc5db66 | note | – – – – – – – – – – – – – – – – –
728d02a3-5b21-5ed0-b994-8eaa4d21562f | note | METHOD - Visual
eb2e5ffd-3b75-5a6e-8d84-47a934ea0718 | note | – – – – – – – – – – – – – – – – –
43f0c3b6-0fba-5cda-84e0-d4e9a5b5da95 | note | FREQUENCY - Once, prior to application.
56522e0a-b2e8-5a7f-8700-7373ff40817f | note | – – – – – – – – – – – – – – – – –
b119e8a4-ea63-5018-b6ea-6d227d37843d | note | CATEGORY - IP
d9e32f01-c4b0-5619-94bb-24d890037a9a | note | – – – – – – – – – – – – – – – – –
ec88d075-1e14-5e87-b0f5-7cb14b7b360d | note | RESPONSIBILITY - SE/PE/SPE
ef9616cc-b4f6-5a4e-90e6-269628e52771 | note | – – – – – – – – – – – – – – – – –
0d23c258-8c4f-5d2b-b693-e63d716ee12b | note | VERIFYING DOCUMENTS - This ITP
756f9760-aa36-52ef-8d9e-8cecfd6d1389 | textbox | Date Completed:
| checkpoint | 3.4 - Surface Moisture Testing
9e6e8517-c0b6-5c0e-8d02-b55925476163 | note | REFERENCE - 685.12 (a) 686.14 (a) (iii)
b2fb9fa7-ef51-5f0f-a376-fe327deeba02 | note | – – – – – – – – – – – – – – – – –
4a804b47-75a1-59dd-8635-77f0e094ea1f | note | ACCEPTANCE CRITERIA - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS. Surface moisture conditions are to be recorded.
16bc95a2-fe14-506e-bf01-683e13af7913 | note | – – – – – – – – – – – – – – – – –
44b2591f-386d-552e-bf8c-2abd74c2b545 | note | METHOD - Test
0ce87e8e-585c-5007-9898-33412f677051 | note | – – – – – – – – – – – – – – – – –
0c7120f8-b073-5f1d-b2e7-6e86b67fc4e1 | note | FREQUENCY - Immediately prior to application, test 1m²
65651eaa-a477-5618-8686-584c3891ef9e | note | – – – – – – – – – – – – – – – – –
5849f456-0d1a-5301-bf33-4378edcd7e1c | note | CATEGORY - IP
a1cbb57e-cc10-5d48-9369-7b3e78e29953 | note | – – – – – – – – – – – – – – – – –
b68ce990-0675-5029-b8ee-31444ea4efee | note | RESPONSIBILITY - SE/PE/SPE
f96eea1c-6d0b-5070-8e84-aed237763259 | note | – – – – – – – – – – – – – – – – –
fb64a259-316b-5f66-871e-39da593a0b4a | note | VERIFYING DOCUMENTS - This ITP
1ec699d9-3dff-5c86-9afb-c9cc8233e7a5 | textbox | Date Completed:
| section | 4 - Application Activities
| checkpoint | 4.1 - Method of Application
493c5481-3454-5270-b99a-4923ce213f83 | note | REFERENCE - Coating System TDS 685.07 686.07 686.09
92b4489c-2b77-55fe-b4c9-ecbbf9eb2eb3 | note | – – – – – – – – – – – – – – – – –
aca9fd02-980a-595e-86b8-07cc8781b645 | note | ACCEPTANCE CRITERIA - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved. Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified. For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application. Times of coating(s), material names, locations coated and volumes used shall be recorded.
e3bf83ef-cc01-59e3-bda8-cd38ddb1911d | note | Attach: Coating Application Record
966c27c4-5a2f-50e5-8170-19297308b7d0 | note | – – – – – – – – – – – – – – – – –
c387fa8c-6601-514d-a181-e9afdce3b81a | note | METHOD - Visual Measure
37e2892d-e71d-5951-88d2-321dbe3935ab | note | – – – – – – – – – – – – – – – – –
abe8ecad-6a2b-57d2-98e8-b4cccb47d65e | note | FREQUENCY - Each coat
33413501-fde7-5e10-964e-aec2dca9ca25 | note | – – – – – – – – – – – – – – – – –
ac334a34-2bd7-5bca-bd30-30bf3d95829c | note | CATEGORY - IP
46c2a7b6-e84f-563a-a538-e23023059039 | note | – – – – – – – – – – – – – – – – –
1634f20b-ea3b-56c2-8cb1-c30d6789a9b0 | note | RESPONSIBILITY - SE/PE/SPE
5855c5a4-e45b-5c27-8c44-dc846ac4c98f | note | – – – – – – – – – – – – – – – – –
6bd3e9ed-68a6-548a-b7de-ff2d626f6326 | note | VERIFYING DOCUMENTS - This ITP
4622d820-5305-5d2c-a8dc-9fcb5709f34d | textbox | Date Completed:
| checkpoint | 4.2 - Wet Film Thickness (WFT) Testing
c2484e73-74ff-5c0a-8c27-af55def2a297 | note | REFERENCE - Coating System TDS 685.12 (b) (ii) 686.14 (b) (ii)
61217586-d406-54da-ab95-c0f2fabe9dc6 | note | – – – – – – – – – – – – – – – – –
aafe61df-e962-56a8-979b-fcfe275a9dda | note | ACCEPTANCE CRITERIA - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
dbcdcd73-48bc-5bcf-bc61-de4ea8c938a4 | note | Attach: WFT Test Results
61a37b79-1b46-5729-a89c-4a71d51925c7 | note | – – – – – – – – – – – – – – – – –
1b84cf64-320f-56b4-8e40-1719b1f0a5db | note | METHOD - Test
d20d2c2e-f88a-594c-ba23-51dbf5c7fe12 | note | – – – – – – – – – – – – – – – – –
d33d033e-7233-5e0a-a2a8-ef68bd1101b6 | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
9db04385-207b-570c-880b-aa0e5e4dbbc9 | note | – – – – – – – – – – – – – – – – –
54679a0e-d241-5009-a12c-4d9e153fb2d9 | note | CATEGORY - IP
8364df07-d2bf-536c-9346-f640d7c1d20b | note | – – – – – – – – – – – – – – – – –
fda03b6e-fc33-5151-8e01-abbcc7b22ff0 | note | RESPONSIBILITY - SE/PE/SPE
ac1d1725-bdbf-5de0-bafd-a7c06731f96b | note | – – – – – – – – – – – – – – – – –
d97e53d6-9dda-5ddd-9cb2-a6554fde0e8c | note | VERIFYING DOCUMENTS - This ITP
59ef425c-975c-55c1-ae27-b7d18277948f | textbox | Date Completed:
| checkpoint | 4.3 - Inspection & Defect Identification
045fc696-ec66-56fd-9dcf-527c9555e151 | note | REFERENCE - 685.07 685.13 (d) 686.07 686.15
e6def57b-7769-5397-ba19-18dcd17fa0ca | note | – – – – – – – – – – – – – – – – –
2683f890-8126-50b5-836d-a37dbeafb2e8 | note | ACCEPTANCE CRITERIA - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats. Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
b32a8a74-b0e9-5c30-a0b4-56f3259f8720 | note | – – – – – – – – – – – – – – – – –
c93ffceb-6f3b-5c95-8471-42520d3ab61e | note | METHOD - Visual
40b268f2-7dff-56fe-94ac-0b78706f2c60 | note | – – – – – – – – – – – – – – – – –
60cc7c0c-9958-5f3e-b626-bc5c6db878bd | note | FREQUENCY - After each coat
8f533a4a-6d1a-5781-806e-3cffd2028872 | note | – – – – – – – – – – – – – – – – –
e8b5a3e3-55ba-5e8f-b384-f63d0498b85c | note | CATEGORY - IP
672032f5-7e77-5e6d-b2d9-337bc2bd5a55 | note | – – – – – – – – – – – – – – – – –
57f69bab-6ee5-5b22-aedd-8e15a8d18cdc | note | RESPONSIBILITY - SE/PE/SPE
5b99632a-c850-502a-abd3-18b42fdb98d9 | note | – – – – – – – – – – – – – – – – –
1a543f16-eb46-5422-bc59-890a5ea52535 | note | VERIFYING DOCUMENTS - This ITP
84789195-df65-5cba-ba37-802f1aa02141 | textbox | Date Completed:
| checkpoint | 4.4 - Drying and Curing
3b60a252-24bd-518b-b316-c75cd11e2f85 | note | REFERENCE - Coating System TDS 685.17 686.09
f10fd9ae-e36d-5290-9598-997cb34fbb8c | note | – – – – – – – – – – – – – – – – –
01ec810c-8fdf-5eef-8c38-eaa1fd9c20f3 | note | ACCEPTANCE CRITERIA - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
ea086422-f0f1-5f88-b84c-5fff82246828 | note | – – – – – – – – – – – – – – – – –
aae7cf4a-bf08-525b-8e35-6522fbe1744d | note | METHOD - Visual
fc26c1b8-7e53-587e-814d-8531dba0d210 | note | – – – – – – – – – – – – – – – – –
a9aa629f-b760-51b8-b886-71ca57fa1c80 | note | FREQUENCY - After each coat
276d476c-3d9d-5b3f-8437-0ae4ed4b0ea1 | note | – – – – – – – – – – – – – – – – –
9b9023ef-1272-5811-8006-37ba5087be21 | note | CATEGORY - IP
4426b201-95ea-5a7b-9f88-6abd0bcad051 | note | – – – – – – – – – – – – – – – – –
10fd4f1e-9e64-5a74-a704-9b6b28a130c5 | note | RESPONSIBILITY - SE/PE/SPE
254c2ba1-456e-5511-8cb4-781148309966 | note | – – – – – – – – – – – – – – – – –
d9914f22-1a8c-592f-b632-1da2ed8271e8 | note | VERIFYING DOCUMENTS - This ITP
73975a62-6aec-5b39-8da3-be50684692cd | textbox | Date Completed:
| section | 5 - Post-application Activities
| checkpoint | 5.1 - Clean-up & Waste Disposal
473e405a-20eb-5c4b-ac82-2a290e85cec9 | note | REFERENCE - 685.09 (c) 686.10
4734833d-9c14-592f-b526-d3b8dea8fe14 | note | – – – – – – – – – – – – – – – – –
15c157f6-58eb-52a9-b5cf-4f3034537b97 | note | ACCEPTANCE CRITERIA - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
0c45d18d-5bf6-521a-b7e7-702afa286aba | note | – – – – – – – – – – – – – – – – –
43c74474-91b0-5c4f-83df-89add1f6b013 | note | METHOD - Visual
75fa2b6f-96a9-5319-850f-0d93f5a3bc74 | note | – – – – – – – – – – – – – – – – –
1bb7079f-8edb-5927-b18d-2ddf49cf55b2 | note | FREQUENCY - At completion of Works
af871e42-bf54-5a24-92ae-bca103009850 | note | – – – – – – – – – – – – – – – – –
6cd2f5f1-7fcf-5ec9-812a-21d6c5340fa6 | note | CATEGORY - IP
3141fe15-a1f1-5e89-bcc6-ef2d73129934 | note | – – – – – – – – – – – – – – – – –
80fa7851-d227-5a4e-be0c-07384a652261 | note | RESPONSIBILITY - SE/PE/SPE
e241ba86-a026-523f-96de-5eedb8cad2b8 | note | – – – – – – – – – – – – – – – – –
7e50fc2d-42cf-53b6-8eeb-f254ca3b77fc | note | VERIFYING DOCUMENTS - This ITP
35f49e62-9c4a-53ed-8682-cdb3500c6300 | textbox | Date Completed:
| checkpoint | 5.2 - Dry Film Thickness (DFT) Testing
b4d95241-ab1d-58dc-bd02-dc92da8a60f4 | note | REFERENCE - 685.12 (b) (iii) 686.14 (b) (iii)
c9aa2334-90f1-5053-beab-299312a1289d | note | – – – – – – – – – – – – – – – – –
578867eb-714e-5951-b2f6-c37a41d2a604 | note | ACCEPTANCE CRITERIA - The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses: i. Anti-graffiti system = 100µm Ii. Decorative & anti-carbonation = 150µm iii. Decorative, anti-carbonation & anti-graffiti = 150µm iv. Atmospheric & splash zone (dual protective) = 200µm
e5f03341-acca-5e69-9415-a4e81262b4f4 | note | No more than 15% of the readings shall be less than 90% of the required thickness.
0e25e303-d7ac-5b95-9047-863aad871dc8 | note | Attach: DFT Test Results
301155d6-6e39-58cf-b4c3-ec8d006bf330 | note | – – – – – – – – – – – – – – – – –
4b6340d6-1114-570b-816f-24879f664d2e | note | METHOD - Test
b9666331-f0b1-5b48-8cd0-ac3e17145b35 | note | – – – – – – – – – – – – – – – – –
1d4b4d06-e09a-5ba7-b14e-ed8a0ab2b041 | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
fd4a64c5-46de-5338-a441-644aea8ed24c | note | – – – – – – – – – – – – – – – – –
410a50a9-c2f1-522f-9f52-91867ded2558 | note | CATEGORY - IP
c033cf2f-ad9c-5ccd-b2c6-dae20a1dcd46 | note | – – – – – – – – – – – – – – – – –
1f1f16d2-3dd8-5f91-b421-19359d19af2c | note | RESPONSIBILITY - SE/PE/SPE
3f15e846-b49e-5198-b69a-f7b4d49491e6 | note | – – – – – – – – – – – – – – – – –
b1521897-8449-51c3-b349-eabf49469f27 | note | VERIFYING DOCUMENTS - This ITP
a5752485-592e-560e-b4e4-440c7a03ae93 | textbox | Date Completed:
| checkpoint | 5.3 - Adhesion Bond Strength Testing
1cc8a1cc-d9e4-58b4-aeae-35e6192166d8 | note | REFERENCE - 685.12 (b) (i) 686.14 (b) (i)
15a7621e-5b73-5eb9-ac86-58e43c9a254a | note | – – – – – – – – – – – – – – – – –
30ce2657-d516-50d2-8eb2-cd9b5bb701cc | note | ACCEPTANCE CRITERIA - A minimum of 14 days after application, the bond-strengths between: i. the coating system to the substrate, and ii. Separate coating layers shall be tested using 50mmØ aluminium dollies. The subsequent results shall be greater than 0.75MPa.
ce65e6ff-a59b-5e82-8a27-f2bcee847253 | note | Attach: Adhesive Bond Strength Testing Results
c72a6af2-eab1-5382-b403-d198f07a6bc8 | note | – – – – – – – – – – – – – – – – –
78737d27-a026-529b-93a9-a423bcddc735 | note | METHOD - Test
21d4d6ae-51ea-55cb-b261-e35826482503 | note | – – – – – – – – – – – – – – – – –
b01ba31d-abce-50e0-bd87-96401dab7481 | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
b004a044-fcd8-55fd-9276-f281b959f88f | note | – – – – – – – – – – – – – – – – –
362b7693-bfaf-5769-a4a0-962726d6585b | note | CATEGORY - IP
1f68e5e7-a671-5f34-8b67-39fd0a655672 | note | – – – – – – – – – – – – – – – – –
c4788c27-f31d-56e8-af07-25eec8d6fc88 | note | RESPONSIBILITY - SE/PE/SPE
3eb96a4e-a6f3-5c63-a02f-4c4ebcda3b95 | note | – – – – – – – – – – – – – – – – –
1a01eff8-3327-514b-a952-233a094308c1 | note | VERIFYING DOCUMENTS - This ITP
2e2e4312-cd8b-5e7d-891e-d2090f4a7dff | textbox | Date Completed:
| checkpoint | 5.4 - Penetration Depth Testing
4fe028dd-88ee-5cca-979c-3f68dce44181 | note | REFERENCE - 685.12 (b) (v) 686.14 (b) (v)
d4042058-032b-5646-b0c3-393b347f057f | note | – – – – – – – – – – – – – – – – –
267f2b83-7fd0-53fa-a809-362270042a2e | note | ACCEPTANCE CRITERIA - Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration. The subsequent results shall be: i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible) ii. Silane, Solid Silane or Silane Cream = 5mm min. iii. Silane-Siloxane or Siloxane = 3mm min.
8199a1bf-d5f2-5bed-8ece-c757d5221f3e | note | Attach: Penetration Depth Testing Results
c39d3396-4a56-57c1-a567-9cacaf224e4f | note | – – – – – – – – – – – – – – – – –
b159afae-0b45-546d-a847-a891789cb79b | note | METHOD - Test
484b122f-fbad-580d-ba1b-ca410595d24e | note | – – – – – – – – – – – – – – – – –
c1c3a16a-1e2e-533d-87f8-1554b0c1ccfc | note | FREQUENCY - Where applicable, 3 no. tests every 50m² or part thereof
958e048a-0c53-5663-940b-b4189dcffb8a | note | – – – – – – – – – – – – – – – – –
02a5938b-ce9d-5250-bf5e-175939293c1b | note | CATEGORY - IP
df99a23b-0ce8-5ba1-83e3-62491b8ba81c | note | – – – – – – – – – – – – – – – – –
68e34a94-8fb1-572c-90ba-6a739000f30a | note | RESPONSIBILITY - SE/PE/SPE
fe4f6064-41a4-5bff-9fb4-e9daadcf1931 | note | – – – – – – – – – – – – – – – – –
12f4b5bf-1a9f-50e0-b282-108afc2478b0 | note | VERIFYING DOCUMENTS - This ITP
7c4b9238-4cc0-58ad-be93-70db1f246fbc | textbox | Date Completed:
| checkpoint | 5.5 - Non-conforming Coatings
6aa7b1d8-9ce9-570f-b7b8-6370e2a68587 | note | REFERENCE - 685.14 686.17
63bea1c1-2dae-5261-887a-a76c5e68dcd2 | note | – – – – – – – – – – – – – – – – –
50105fd3-1cf5-5a61-bdef-e024e1d2012f | note | ACCEPTANCE CRITERIA - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
141fbbea-51dc-509e-a03e-922b8fe38b01 | note | – – – – – – – – – – – – – – – – –
34885b3e-ec35-5c8e-9d30-c49bf89888f5 | note | METHOD - Visual
46ff7232-98c1-56dc-845e-40c5bc695a7f | note | – – – – – – – – – – – – – – – – –
4c8872b2-06c2-5e95-a727-861fd62e0355 | note | FREQUENCY - Where required
c9f1d184-9b61-5632-a346-cc8de0f54afb | note | – – – – – – – – – – – – – – – – –
9c25a048-b0c7-566f-ad9d-9a09d466e096 | note | CATEGORY - IP
a4e6f890-9cc9-5f4d-9ec3-af3af64b29bb | note | – – – – – – – – – – – – – – – – –
e3840cbb-d3f2-503a-ac5d-c691180d0ddb | note | RESPONSIBILITY - SE/PE/SPE
c4350e51-8160-51f0-9ea3-d0f30caca280 | note | – – – – – – – – – – – – – – – – –
3c2d33c7-e313-5525-ac95-7fe1232cd588 | note | VERIFYING DOCUMENTS - This ITP
c57155cf-395c-5602-ae23-ae13e7a698cd | textbox | Date Completed:
| checkpoint | 5.6 - Coating Application Guarantee
c740d635-aedb-5da5-8d35-8b8e60036957 | note | REFERENCE - 685.06 (b) 686.05 (a)
a2627019-e402-5db2-a271-648674d9ce20 | note | – – – – – – – – – – – – – – – – –
ee567e39-f047-503b-acae-c0006682546f | note | ACCEPTANCE CRITERIA - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
8cd1d607-848f-54ef-a3eb-02f1121437c2 | note | Attach: Coating Application Guarantee
aca2d8cb-95fa-5470-a923-45485d3ea1f2 | note | – – – – – – – – – – – – – – – – –
9d5acca7-425e-5cc6-9bc5-9e7a1c13c584 | note | METHOD - Document Review
c4451e71-e74c-505b-b16a-264d3e5d31f0 | note | – – – – – – – – – – – – – – – – –
0eed5967-f08b-56c6-9476-908c24ec22c5 | note | FREQUENCY - At completion of Works
c295bd02-188d-597a-8f1b-6446ef498c08 | note | – – – – – – – – – – – – – – – – –
7fdd6492-2329-51ec-88ba-cf48222ecd6a | note | CATEGORY - SP
4d6b1565-bffc-5954-ad1a-504cfe44f0bc | note | – – – – – – – – – – – – – – – – –
3b7f020f-bf99-596d-a796-9a8785be0b5c | note | RESPONSIBILITY - SE/PE/SPE
e6439bd8-c4cb-57b3-a802-3c0f2491264a | note | – – – – – – – – – – – – – – – – –
4e35a047-41f5-5929-bf44-0576752c407f | note | VERIFYING DOCUMENTS - This ITP
b0e2b2cd-fa8c-548b-a325-7b01887ca1ae | textbox | Date Completed:
| checkpoint | 5.7 - Repair to Damaged Coating
104fbacc-83aa-57c8-b160-765656b81e7a | note | REFERENCE - 686.17
57e3c17e-af64-5b63-885f-76007668cbd1 | note | – – – – – – – – – – – – – – – – –
658cb35d-d8d9-5a59-8021-f7a017995127 | note | ACCEPTANCE CRITERIA - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
beb7446e-5eef-5df0-ad55-103ab2e0e5d1 | note | – – – – – – – – – – – – – – – – –
c03ca874-609c-576f-b502-e7a3b8e760b6 | note | METHOD - Visual
4bb9af53-8dd3-5ee8-9c38-ad0e5822a748 | note | – – – – – – – – – – – – – – – – –
acddf7e2-624c-527a-83ee-13c9905c405c | note | FREQUENCY - Where required
d04d5b3c-1615-51a6-a18f-dfcc7e5b2312 | note | – – – – – – – – – – – – – – – – –
8a14dfd4-2296-5d2f-89fb-33615b8535b4 | note | CATEGORY - IP
4651b042-8214-5adc-8e43-2bb78571c025 | note | – – – – – – – – – – – – – – – – –
8ae865ca-9967-516f-ab30-ada1b05b618e | note | RESPONSIBILITY - SE/PE/SPE
bae5b287-f0f5-588a-bcc0-d9a2a6d33903 | note | – – – – – – – – – – – – – – – – –
c87d1edb-6cff-5d14-9bca-b03ac162c0c5 | note | VERIFYING DOCUMENTS - This ITP
f89feb87-c616-5054-8442-368c903192d0 | textbox | Date Completed:
| checkpoint | 5.8 - Non-conformance Report (NCR) Closure
c19fad57-1657-5898-a510-3c9223c64d57 | note | REFERENCE - MRPA Quality Management Plan
8771e612-84d8-59f7-bffa-528dc4f9ac3f | note | – – – – – – – – – – – – – – – – –
a5fc614e-8566-569a-af0c-d0d845a97e76 | note | ACCEPTANCE CRITERIA - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
5e95408c-7f7d-5373-b862-1522c53f50ce | note | – – – – – – – – – – – – – – – – –
73140741-d967-5042-8f12-03c31bb5004e | note | METHOD - Document Review
0a313b75-158a-5cd4-b1fd-5ba2a92dd95d | note | – – – – – – – – – – – – – – – – –
45477ddc-125a-5e7c-9260-540cc7643539 | note | FREQUENCY - Once, prior to closure of this lot / element / Work area
c806393b-a76a-5f94-a312-6a44790df7db | note | – – – – – – – – – – – – – – – – –
de1f2f89-bf03-5247-a58e-d8d1a9913496 | note | CATEGORY - HP*
0b1ff173-4e90-5c10-936f-599a41934a91 | note | – – – – – – – – – – – – – – – – –
b5ac22ad-6e4b-518d-a70c-6164d8ac1fb1 | note | RESPONSIBILITY - SE/PE/SPE
85639dc2-b2b6-5543-806c-752600e4a63e | note | – – – – – – – – – – – – – – – – –
380c109a-8e34-5b01-8acd-807fec48b1da | note | VERIFYING DOCUMENTS - This ITP
ac4f66b6-35c2-5f57-a13c-e4c192f76a29 | textbox | Date Completed:
| checkpoint | Final Inspection
7787f32a-6c07-524b-949c-994e033d0e07 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
930e4186-d63a-5b6e-a291-2670cee01321 | textbox | Name:
94a27d18-b517-52c4-8376-9087814d945e | textbox | Position:
c2ddc0bb-7bbb-5e09-95b7-ce714c7a28ce | date | Date Completed:
| signoff | Sign ITP