## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-185-CIV-Camms - Furniture Installation-Wamarra | itp |  |  |  |  | ITP-185-CIV-Camms - Furniture Installation-Wamarra Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-185-CIV-Camms - Furniture Installation-Wamarra
label | ITP Description: Camms - Furniture Installation-Wamarra
label | Discipline (e.g. CIV/STR/RAIL): 185-CIV
label | Revision Number: 0
label | Revision Date: 17/07/2024
label | ITP created by: Chloe Mitchell
label | ITP approved for use by: VM
label | 1.1 Non Dependent
label | Reference: AS1428.2
label | 1.2 Non Dependent
label | Reference: AS2890.1
label | 1.3 Non Dependent
label | Reference: AS/NZS1428.4.1
label | 1.4 Non Dependent
label | Reference: AS4422 - 1996
label | 1.5 Non Dependent
label | Reference: AS4685.1:2014
section | Preliminaries - Materials
checkpoint | 2.1 Preliminary Activities Completed
label | ACCEPTANCE CRITERIA: All ‘pre-construction’ authorisations and checks completed and approved.
label | Ensure that the following items have been actioned:
label | – SWMS reviewed and approved
label | – Plant Pre-start Inspection
label | – Service locations identified
label | – Permits issued
label | – Traffic Management Plans
label | ○ All staff inducted
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to works start
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 2.2 Work Lot Map
label | REFERENCE: Work Lot Map
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Work lot map attached to work lot.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to works start
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 2.3 Survey Set out
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Location and heights of drainage components to be setout prior to commencing works as per the alignment and position as dictated by the approved drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to works start
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Material Compliance
checkpoint | 3.1 EPDM Softfall Rubber
label | REFERENCE:
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Rubber to be 3-part mix for EPDM containing:
label | ○ E011 Light Brown
label | ○ E090 Brown
label | ○ E080 Orange
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material Approval, This signed off ITP
date | Date Completed:
checkpoint | 3.2 FU1A Platform Seat
label | REFERENCE: CSA Drawing #CS9576, AS1428.2
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Platform Benches manufactured as per approved shop drawings and in accordance with AS1428.2.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material Approval, This signed off ITP
date | Date Completed:
checkpoint | 3.3 FU1B – Seat
label | REFERENCE: CSA Drawing #CS9654, AS1428.2
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Platform Benches manufactured as per approved shop drawings and in accordance with AS1428.2.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material Approval, This signed off ITP
date | Date Completed:
checkpoint | 3.4 FU3A – Boulder Small
label | REFERENCE: MRP-052-C-SME-DRG-82-CBE-AUD-1003
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Boulder to be bronze to yellow colour granite ranging from 0.5 – 0.8m.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material Approval, This signed off ITP
date | Date Completed:
checkpoint | 3.5 FU3B – Boulder Medium
label | REFERENCE: MRP-052-C-SME-DRG-82-CBE-AUD-1003
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Boulder to be bronze to yellow colour granite ranging from 0.8 – 1.2m.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material Approval, This signed off ITP
date | Date Completed:
checkpoint | 3.6 FU3C – Boulder Larger
label | REFERENCE: MRP-052-C-SME-DRG-82-CBE-AUD-1003
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Boulder to be bronze to yellow colour granite ranging from 1.2 – 1.8m.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material Approval, This signed off ITP
date | Date Completed:
checkpoint | 3.7 Cyclist Fencing
label | REFERENCE: Moddex Drawing # 17380 Sheet 1
label | ○ Moddex Drawing # 17380 Sheet 3
label | ○ MRP-052-C-SME-DRG-80-CBE-CRG-2102
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Cyclist fencing to be manufactured as per the approved shop drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material Approval, This signed off ITP
date | Date Completed:
checkpoint | 3.8 Bollards
label | REFERENCE: Safety Xpress BOLSM140
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bollards to be manufactured as per the approved shop drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material Approval, This signed off ITP
date | Date Completed:
checkpoint | 3.9 Speed Humps
label | REFERENCE: AS2890.1
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Speed Humps to be manufactured as per the approved shop drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material Approval, This signed off ITP
date | Date Completed:
checkpoint | 3.10 Wheel Stops
label | REFERENCE: MRP-052-C-SME-DRG-80-CBE-CRG-1401
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Wheel Stops to be manufactured as per the approved shop drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencing any activity
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material Approval, This signed off ITP
date | Date Completed:
section | Pre-construction Activities
checkpoint | 4.1 Setting Out - Position of Posts and Signs
label | REFERENCE: Section 714.06, IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Set out work in accordance with IFC Drawings.
label | ○ The required positions of all posts and signs shall be checked and confirmed by the Supervisor before the erection of posts
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to start
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 EPDM Rubber Granules
label | REFERENCE: MRP-052-C-SME-DRG-80-CBE-CRG-5201
label | ○ Impact attenuation and fall zone dimensions as per AS4685.1:2014 and AS4422 - 1996
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Top wearing course shall typically comprise EPDM rubber granules with pigmentation of granules continuous for their entire cross section.
label | ○ Minimum 40mm depth shall be maintained or as specified by Playground manufacturer for impact attenuation.
label | ○ All wet pour to have rolled edges.
label | ○ Material to consist of two-layer profile (wet pour application)
label | ○ Apply primer or polyurethane coat to the concrete to ensure adequate bonding of the rubber material
label | ○ Do not install rubber in temperature greater than 30degrees
label | ○ Softfall rubber shall be installed in a single pour to prevent joins and edges
label | ○ Finished surface shall have an even appearance, be free from localised depressions, be flush with adjacent edges and true to line & level
label | Thicknesses of single density and double density rubber surfacing shall be as per the below table depending on fall heights.
label | 600mm fall height ¦¦ 15mm single density rubber
label | 1100mm fall height ¦¦ 15mm granule + 20mm base under surfacing
label | 1600mm fall height ¦¦ 15mm granule + 35mm base under surfacing
label | 1800mm fall height ¦¦ 15mm granule + 45mm base under surfacing
label | 2200mm fall height ¦¦ 15mm granule + 65mm base under surfacing
label | 2600mm fall height ¦¦ 15mm granule + 75mm base under surfacing
label | 3000mm fall height ¦¦ 15mm granule + 85mm base under surfacing
label | Beached Edging ¦¦ 420mm
label | – – – – – – – – – – – – – – – – –
label | METHOD: Verify
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Rubber Surfacing TDS/Manufacturer’s Manual
label | ○ Delivery Dockets
label | ○ Rubber Attenuation
label | ○ Certification
label | ○ Supplier Warranty
label | ○ Slip Resistance Test (if applicable)
label | ○ Manufacturer’s Warranty
date | Date Completed:
checkpoint | 5.2 Installation of Furniture - FU1A-Platform Bench
label | REFERENCE: CSA Drawing #CS9576, AS1428.2
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Fixing method to be bolt down as per manufacturer’s recommended installation requirements.
label | Footing details to comply with the below:
label | ○ 300x300x300mm deep for isolated pad footings
label | ○ 125mm deep for slab footings
label | ○ 25MPa concrete
label | ○ Bolt down to footings with 4 x M12 x 75mm Dynabolts or similar
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.3 Installation of Furniture - FU1B - Seat
label | REFERENCE: MRP-052-C-SME-DRG-82-CBE-AUD-1003
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Fixing method to be bolt down as per manufacturer’s recommended installation requirements.
label | Footing details to comply with the below:
label | ○ 300x300x300mm deep for isolated pad footings
label | ○ 125mm deep for slab footings
label | ○ 25MPa concrete
label | ○ Bolt down to footings with 4 x M12 x 75mm Dynabolts or similar
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.4 FU1C – Station Seating
label | REFERENCE: CSA Drawing #CS6506, AS1428.2
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Fixing method to be bolt down as per manufacturer’s recommended installation requirements.
label | Footing details to comply with the below:
label | ○ 300x300x300mm deep for isolated pad footings
label | ○ 125mm deep for slab footings
label | ○ 25MPa concrete
label | ○ Bolt down to footings with 4 x M12 x 75mm Dynabolts or similar
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.5 FU3A, FU3B & FU3C - Boulders
label | REFERENCE: MRP-052-C-SME-DRG-82-CBE-AUD-1003
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Boulders on Slope:
label | ○ To be installed in various sizes with minimum diameter of 500mm in any direction.
label | ○ Minimum 50% of boulder surface to be compacted into subgrade.
label | Boulders on Flat Planting Bed/Adjacent to Tree Planting:
label | ○ To be installed in various sizes with minimum diameter of 500mm in any direction.
label | ○ Stabilised embedment to concrete base of boulder to finish 50mm below adjoining finished surface.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.6 Cyclist Fencing
label | REFERENCE: Moddex Drawing # 17380 Sheet 1
label | ○ Moddex Drawing # 17380 Sheet 3
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Cyclist fencing to be installed as per the approved shop drawings and as per the manufacturers specifications
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.7 Bollards
label | REFERENCE: Safety Xpress BOLSM140
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bollards to be installed as per the approved shop drawings and as per the manufacturers specifications.
label | ○ Fixing method to be bolt down as per manufacturer’s recommended installation requirements.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.8 Speed Humps
label | REFERENCE: MRP-052-C-SME-DRG-80-CBE-CRG-2102, AS2890.1
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Speed humps to be installed as per the approved shop drawings and as per the manufacturers specifications.
label | ○ Fixing method to be bolt down as per manufacturer’s recommended installation requirements.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 5.9 Wheel Stops
label | REFERENCE: MRP-052-C-SME-DRG-80-CBE-CRG-7101
label | ○ MRP-052-C-SME-DRG-80-CBE-CRG-7102
label | ○ AS2890.1
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Wheel stops to be installed as per the approved shop drawings and as per the manufacturers specifications.
label | ○ Fixing method to be bolt down as per manufacturer’s recommended installation requirements.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
section | Conformance
checkpoint | 6.1 Redline Markup Drawings
label | ACCEPTANCE CRITERIA: Redline drawing to be produced and maintained by engineers to include all changes during construction
label | ○ Redline to use attest IFC version of the design drawings to identify any variations
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | 6.2 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that This ITP Signed-off covers, have been closed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed-off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP