## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
a6275bb8-c16c-4309-840c-4dfef0de0dae | checklist | Equus Matacryl System Sequence |  | Equus Matacryl System Sequence | 6143ad16-bc98-431b-8b05-be427acf2fbc
fd27c8af-4334-40f9-b339-b9723020badd | section | Details
de5a2be6-87df-4d95-80a1-7177bf939f3b | checkpoint | Preparation of area completed
b166920e-0cb8-46b6-aa92-4fbe270d7014 | checkpoint | All outlets and penetrations installed
ea2f6d51-0295-43d2-8caf-94d6326d1f12 | checkpoint | 108 Duracon primer applied
34c50ffb-8017-4074-af31-c42e018481f2 | checkpoint | 107 Duracon primer applied (steel only)
ab6e61ab-3108-4c40-a2fc-350b737601ed | checkpoint | Matacryl Manual 1st layer
b3f64f47-75a3-4abc-9ea8-d6e84fb0f5ef | checkpoint | Quartz sand applied
0e84b5dd-c446-446d-a0b9-88038e76d42c | checkpoint | Matacryl STC 1st coat applied
4d06e0ee-0f21-41dd-a26e-28e8312c6e20 | checkpoint | Matacryl STC top coat applied
881a5653-19e2-46de-9682-c36a541b7245 | checkpoint | Area left clean and clear
246700a1-6b98-4430-9e5c-eae31c621b27 | checklist | Equus Two Layer System on Concrete Sequence |  | Equus Two Layer System on Concrete Sequence | 6d62e4a5-9a28-4b95-aabc-04de3de43204
77d4da38-18d3-43ca-8f6a-a47af9edfa9f | section | Details
28cef2d7-baa6-4989-bbcc-0ac259e2cd6f | checkpoint | Area Preparation works completed
2df93f58-4276-40a0-965f-6de98b32ba68 | checkpoint | Substrate Checked & Aceptable
e184b349-e160-44ff-b525-169bdc242ce5 | checkpoint | Outlets / Overflows installed
48cc3441-1d0e-4d2d-8bf3-2a61eb26b1a1 | checkpoint | Membrane primer applied
318a26de-20d6-4b2e-a10d-8fad0a33f1ed | checkpoint | Anele fillet installed
9bba30f5-6b0a-4e53-8737-8a0b0b48cc8d | checkpoint | Base sheet installed
4550eee1-3f6b-469a-b6bd-b19e2c26f97b | checkpoint | Cap sheet installed
741698f1-9c99-4d56-9d17-c5f125642c32 | checkpoint | Membrane details checked
d167cce0-f757-4a17-a123-d2415f60ffee | checkpoint | Terminations / flashings completed
3a862352-3b8e-4b56-8cdf-79759983c012 | checkpoint | Area left clear of materials / Rubbish
4740d397-aee6-45d2-a0c0-e94e5f840641 | checkpoint | ILD Test Completed
f10d9101-65e4-4da2-9ccb-0199d3c029cb | checklist | Equus Two Layer System on Plywood Sequence |  | Equus Two Layer System on Plywood Sequence | 5a16be1b-e739-426f-b5c4-802a7694f297
330f65b8-ef65-41d5-83bf-145af547b7b0 | section | Details
b0d01023-3e76-41be-ba3f-227f62e742be | checkpoint | Substrate Clean and Dry
f111dfd6-cb34-409c-bcce-236f7051f9d0 | checkpoint | Outlets / penetrations installed
c1ee4da0-155e-466d-bdca-35e612e8b459 | checkpoint | Nuralite Bitumen primer Applied
319ca4a1-cb9f-46cc-8e49-519b0c73d871 | checkpoint | Angle fillet installed
c5ac6477-fe04-42fb-8ee2-b0bf41a19c6e | checkpoint | Nuralite Base sheet installed
301eb874-5c6d-40f7-8210-1522c41db209 | checkpoint | Nuralite 3PM Cap sheet installed
da330ea3-d855-497c-88cf-8ad0425b5cc5 | checkpoint | Terminations / Details completed
115f543e-bc63-4665-b3c9-75b832462502 | checkpoint | Membrane details checked
b23c4cc3-8498-4be3-9cf6-50ed602c2585 | checkpoint | Area left clear of materials / Rubbish
4e73fa17-63dc-41e6-801c-b98f916bd1c7 | checkpoint | ILD Testing Completed
0bc8b793-8cab-40a0-bb4c-120679628f4a | checklist | QA - Torch On Membrane |  | Torch On Membrane | a8e8e5df-fa1b-4164-9eb5-3bcaaed63e0c
c6d14088-b8e8-48b6-a77c-5a1cff9ac4f8 | section | Details
a104a6dc-b248-42e8-ab3c-6fdb9b407c5b | checkpoint | Substrate, inspect/clean
443ef495-df31-41e7-beff-5cf8f2dfe649 | checkpoint | Membrane primer
a52f7036-6036-4f1c-89ae-7daa779f90dc | checkpoint | IlD mesh/plates
3e27f11f-20cb-43da-a6a4-1bc38441fd86 | checkpoint | Base sheet fully torched/Self adhesive
a4220fff-56b5-4cec-b620-05dfc23bec25 | checkpoint | Cap sheet
e95b6012-4283-4f49-9f8c-ac7f61c7b3e6 | checkpoint | Penetration detailing
0648b885-f654-4aee-8894-46f67162177f | checkpoint | Termination bar/sealant if required
c3a81ebe-0a77-4645-a3b1-0524b8ec9c98 | checkpoint | Completion photos
cd9c345c-3cf8-4e5c-b4ed-9939958760d0 | checkpoint | ILD test completed