## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP 401 - Drencher Hydrostatic Pressure Test |  |  |  |  | Yes | ITP 401 - Drencher Hydrostatic Pressure Test | 06b9a35f-c8b8-4d24-ac0e-49cdbd5fa3c3
checkpoint-group |  |  | section | Guidelines
checkpoint-status |  |  | checkpoint | Guidelines acknowledged
label | ee0ba703-b247-5225-aa1c-5bbc8054f770 |  | note | Air - 50Kpa for 30mins.
label | 1826d610-de9e-592b-ab63-7c3c48b60cae |  | note | Water - “1400 kPa for 2 hours” with no pressure loss.
label | 9857bfb6-3695-5709-b712-8ca2f2b63d9c |  | note | Note - 1400 kPa will be the maximum tested pressure
checkpoint-group |  |  | section | Air Test
checkpoint-status |  |  | checkpoint | First Sighting
date | 3a271804-458d-512c-9101-b26b4fd9e427 |  | date | Date:
text | 6edc5c15-c9d9-50f0-b3b4-ab7f0885e46d |  | textbox | Time:
text | 3e0be601-e6c6-5619-aceb-a1b66066f441 |  | textbox | Pressure:
text | 6a25e68e-ad70-5413-8e55-34d488442b28 |  | textbox | Witness (CF:)
checkpoint-status |  |  | checkpoint | Second Sighting
date | bd09d93c-95a8-5f16-b84f-3b2ce2ad6d6b |  | date | Date:
text | 2d0b1b2f-0b91-5907-8741-50601211f98e |  | textbox | Time:
text | bd332f5e-c42e-5ddb-b41b-4ce46fccb498 |  | textbox | Pressure:
text | 8a4fb502-a0cb-5e0a-8bd5-fa6df8457f31 |  | textbox | Witness (CF:)
checkpoint-group |  |  | section | Water Test Rough-In
checkpoint-status |  |  | checkpoint | First Sighting
date | 808693ba-8e50-538b-aee9-fda8fecf146c |  | date | Date:
text | 2282d448-0fcf-507b-9efb-6c473d1ec2c2 |  | textbox | Time:
text | 18bc6f91-0e4f-5f57-8fc9-66aeb6a06c1b |  | textbox | Pressure:
text | eb509d4b-7e35-5213-be42-7d497f7261a7 |  | textbox | Witness (CF:)
checkpoint-status |  |  | checkpoint | Second Sighting
date | 82360183-4bac-5bf1-aba4-7797187a2f67 |  | date | Date:
text | 04d208c8-3dcf-5d72-88f5-6eac98b8c77d |  | textbox | Time:
text | 9da9c4f3-23cc-5730-8747-f53eaf5d741f |  | textbox | Pressure:
text | 3041464b-d172-5acd-917d-b5271ca22916 |  | textbox | Witness (CF:)
checkpoint-group |  |  | section | Water Test Fit Off
checkpoint-status |  |  | checkpoint | First Sighting
date | 4949096a-223f-5b91-aa96-f20660b769a5 |  | date | Date:
text | 87bd7e89-011f-5cf4-b433-5a683d777728 |  | textbox | Time:
text | b527578a-64c7-59d1-b036-6370f5b64c47 |  | textbox | Pressure:
text | 6397474b-04c4-5430-b428-c8e916062d70 |  | textbox | Witness (CF:)
text | d537d329-3c84-577e-8602-14e1e7cd8b79 |  | textbox | Witness (MPX:)
checkpoint-status |  |  | checkpoint | Second Sighting
date | 887510be-fa30-5a76-8f3f-b171e2e19eb1 |  | date | Date:
text | fab9bbac-820f-5e71-99f9-5ac7076248a2 |  | textbox | Time:
text | 8afc5d17-ea56-5d73-8414-ee728a2ddc08 |  | textbox | Pressure:
text | 9f862b92-3959-5f70-84b6-acca3a2bf3eb |  | textbox | Witness (CF:)
text | c2980211-099a-5129-a21d-7395a66ee655 |  | textbox | Witness (MPX:)
checkpoint-group |  |  | section | Subsequent Sightings if Required
checkpoint-status |  |  | checkpoint | First Sighting
date | b7063709-7a81-542b-aee8-84c6998c9209 |  | date | Date:
text | 06d7800e-b643-5f8e-8ca9-7fa9a847285c |  | textbox | Time:
text | 75ea6edd-baa0-599c-acd5-05e9daa21c9a |  | textbox | Pressure:
text | b89a60c4-b566-5f73-abaf-02d875ae4568 |  | textbox | Witness (CF:)
text | 422c6552-17db-5a68-9213-ea78978a2521 |  | textbox | Witness (MPX:)
checkpoint-status |  |  | checkpoint | Second Sighting
date | c2f511bd-8574-5e0d-8ea2-964c711fd21e |  | date | Date:
text | 12fbd32b-f230-5654-be89-7640ab77e85e |  | textbox | Time:
text | 8f71bc1f-bca8-5150-a4b8-fafe032ec32f |  | textbox | Pressure:
text | e646d6f6-f360-5953-ab79-de35e07dc9a3 |  | textbox | Witness (CF:)
text | c9fda684-2c41-5221-877f-ded22f71b1b8 |  | textbox | Witness (MPX:)
checklist-flat |  |  | checklist | ITP 601 - Electric Pump Installation / Commissioning |  |  |  |  | Yes | ITP 601 - Electric Pump Installation / Commissioning | 0ac57a13-3cde-4185-9143-18c6dec74acf
checkpoint-status |  |  | checkpoint | 1. Pump room drawing revision
text | 4637aace-2eae-5992-861a-3c469ce7aee5 |  | textbox | Drawing No.
text | ef0f72a5-751a-5cab-ba34-e83431a7ed6e |  | textbox | Revision No.
checkpoint-status |  |  | checkpoint | 2. Piping as per installation
checkpoint-status |  |  | checkpoint | 3. Power available from electrical contractor & approved for use
checkpoint-status |  |  | checkpoint | 4. Pump performance site test results Elec S1
checkpoint-status |  |  | checkpoint | 5. Pump performance site test results Elec S2
checkpoint-status |  |  | checkpoint | 8. Panel function test for Diesel Controllers
checkpoint-status |  |  | checkpoint | 9. Panel function test for Electrical Controllers
checkpoint-status |  |  | checkpoint | 10. 15 minute pump run test
checkpoint-status |  |  | checkpoint | 11. 90 Minute pump run test
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | 138f3bf9-cc63-5f6d-ad1a-2864877023f4 |  | textbox | Checked By:
text | e0ac383f-a926-5a51-b0ad-fbdf629a625f |  | textbox | Date:
checklist-flat |  |  | checklist | ITP 301 - Sprinkler Installation - Install RI, High level |  |  |  |  | Yes | ITP 301 - Sprinkler Installation - Install RI, High level | 0e62e49a-61f8-4982-a054-6876c6c89b01
checkpoint-status |  |  | checkpoint | 1. Dr’g No: / Revision Correct.
text | 96062feb-c0ce-5a93-a143-8e39694bcd99 |  | textbox | Drawing No.
text | cee132e5-343d-5940-9f7c-6fb5534f8592 |  | textbox | Revision No.
checkpoint-status |  |  | checkpoint | 2. Supports spacing & fixing as per code AS2118 Part 9.
checkpoint-status |  |  | checkpoint | 3. Pipework installed as per Dr’g.
checkpoint-status |  |  | checkpoint | 4. Concealed space sprinklers installed.
checkpoint-status |  |  | checkpoint | 6. Pipes left out as noted below.
checkpoint-status |  |  | checkpoint | 7. Flexibles installed.
checkpoint-status |  |  | checkpoint | 8. Charge hand inspection.
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | 14369ae3-01ec-5f09-82a0-fbdb694cc0cb |  | textbox | Checked By:
text | 467a06b0-0e2b-58da-b83d-91b69a822fdd |  | textbox | Date:
checklist-flat |  |  | checklist | ITP 501 - Fire Extinguisher Installation |  |  |  |  | Yes | ITP 501 - Fire Extinguisher Installation | 214f7a13-aa26-49c8-9afa-c5407b7ed2d3
checkpoint-status |  |  | checkpoint | 1. Location confirmed with MFB stamped drawing or building surveyor descriptions
checkpoint-status |  |  | checkpoint | 2. Correct unit height & clearances
checkpoint-status |  |  | checkpoint | 3. Extinguishers tagged
checkpoint-status |  |  | checkpoint | 4. Extinguishers in new condition
checkpoint-status |  |  | checkpoint | 5. Instruction signage plate installed
checkpoint-status |  |  | checkpoint | 6. Location signage installed to code
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | 62e35d84-8191-528c-98d3-69830423d07c |  | textbox | Checked By:
text | 72ddde03-97f6-505c-9d3e-30d858ec468e |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 401 - Sprinkler Hydrostatic Pressure Test |  |  |  |  | Yes | ITP 401 - Sprinkler Hydrostatic Pressure Test | 3c8ed136-5f3c-4193-bcd6-0f01707d2f94
checkpoint-group |  |  | section | Guidelines
checkpoint-status |  |  | checkpoint | Guidelines acknowledged
label | 88861ada-18ae-551e-9d0b-54820edfebc4 |  | note | Air - 50Kpa for 30mins.
label | 37a3173f-5fc4-52a2-8afe-4c02c1711f79 |  | note | Water - “1400 kPa for 2 hours” with no pressure loss.
label | 74d61ad3-ccdd-578c-98aa-c3044b362565 |  | note | Note - 1400 kPa will be the maximum tested pressure
checkpoint-group |  |  | section | Air Test
checkpoint-status |  |  | checkpoint | First Sighting
date | 0bd4388c-466b-56b2-b2e4-5ad21112ba88 |  | date | Date:
text | ad690c6f-448d-5d58-8ad5-7dd67c41cefd |  | textbox | Time:
text | f2a0d516-7b1d-5239-8943-f5f865bc3004 |  | textbox | Pressure:
text | 477dc767-c867-58ba-a9b9-27958fb21307 |  | textbox | Witness (CF:)
checkpoint-status |  |  | checkpoint | Second Sighting
date | 337293da-c499-5388-bcf6-bfb83486400f |  | date | Date:
text | 942407d9-cb19-51fe-a419-39e2a846f84f |  | textbox | Time:
text | 1da65a8e-e510-5ab0-a078-93719d390da8 |  | textbox | Pressure:
text | 2351ce54-6285-5194-856c-391a62e0c03d |  | textbox | Witness (CF:)
checkpoint-group |  |  | section | Water Test Rough-In
checkpoint-status |  |  | checkpoint | First Sighting
date | da5ce067-6171-5b64-8c76-288875ae386d |  | date | Date:
text | fd5c74c2-a851-5da5-a26a-e8f1dd4d49e2 |  | textbox | Time:
text | 2a30b698-65d8-5db1-93c2-ea0e0e0e4d4d |  | textbox | Pressure:
text | 882bfe5c-d9a9-576c-a231-6af570bc5bea |  | textbox | Witness (CF:)
checkpoint-status |  |  | checkpoint | Second Sighting
date | 0844767d-132d-5dd1-938b-13d2bc22868b |  | date | Date:
text | ce7a533a-3a40-5be8-ba93-2b94a7f1f4f5 |  | textbox | Time:
text | 6034b5f3-91ea-5a22-a392-94e8831fbd5b |  | textbox | Pressure:
text | 716a5807-1f79-593a-9c60-340dece8ff5d |  | textbox | Witness (CF:)
checkpoint-group |  |  | section | Water Test Fit Off
checkpoint-status |  |  | checkpoint | First Sighting
date | e3c11c06-8533-54a1-b15c-829cd1878b80 |  | date | Date:
text | b3c5c686-57a8-5485-8454-e2a802b900ac |  | textbox | Time:
text | dde8b75f-5ac3-5c33-9c4e-dff39f512694 |  | textbox | Pressure:
text | a5b3fd6c-483d-5252-9a9f-c07c4b062c55 |  | textbox | Witness (CF:)
text | 56e5ea41-d99e-5dbb-9116-1ab42a8ebcbc |  | textbox | Witness (MPX:)
checkpoint-status |  |  | checkpoint | Second Sighting
date | 1d3b1989-73de-5b3b-9d48-ed638d2f53c9 |  | date | Date:
text | a0730be2-6b82-5f61-9fc6-eddf1266cd76 |  | textbox | Time:
text | 19e6fe4e-f3a8-5c2e-b328-4f6ca5d29e42 |  | textbox | Pressure:
text | 3e94f98b-aa74-5c31-9ec0-dbe6614716b6 |  | textbox | Witness (CF:)
text | 5630e50b-74be-56b3-9236-472e79101f18 |  | textbox | Witness (MPX:)
checkpoint-group |  |  | section | Subsequent Sightings if Required
checkpoint-status |  |  | checkpoint | First Sighting
date | c2132ac4-cd29-57f2-baee-f09d5ed6ba8e |  | date | Date:
text | 9d722fa7-4add-5ec7-8e24-9579a15b4f1b |  | textbox | Time:
text | 08f8b2d9-8269-5ec3-a1d1-9dad5b2b5804 |  | textbox | Pressure:
text | 2f5fef7a-0348-50e9-86fd-36475884acf6 |  | textbox | Witness (CF:)
text | 350c69f9-1ac0-5660-a879-a645eaddb6ea |  | textbox | Witness (MPX:)
checkpoint-status |  |  | checkpoint | Second Sighting
date | 67472862-8257-5e91-aee5-1a178e8082d4 |  | date | Date:
text | 765eb6b2-75e1-5a2c-8593-dcb8f1ec271b |  | textbox | Time:
text | 1bccc56e-12f7-5d5a-96b3-211d5e798b80 |  | textbox | Pressure:
text | 0b668d4b-77d1-5361-a0af-ba73e74e9cee |  | textbox | Witness (CF:)
text | bbcd5f83-618d-5d6b-9b2b-9442cc49a4ab |  | textbox | Witness (MPX:)
checklist-flat |  |  | checklist | ITP 701 - Booster Installation |  |  |  |  | Yes | ITP 701 - Booster Installation | 45ae6b00-c467-49c6-81e9-cdd1de65edcb
checkpoint-status |  |  | checkpoint | 1. Installed as per drawing
checkpoint-status |  |  | checkpoint | 2. Drawing revision
checkpoint-status |  |  | checkpoint | 3. MFB required clearance confirmed
checkpoint-status |  |  | checkpoint | 4. Labelling per stage & level provided
checkpoint-status |  |  | checkpoint | 5. Isolations valves closed & locked
checkpoint-status |  |  | checkpoint | 6. Pressure gauges at T.M pressure
checkpoint-status |  |  | checkpoint | 7. Storz couplings installed to suction points
checkpoint-status |  |  | checkpoint | 8. Hydrostatic Test Completed (1700 kpa)
checkpoint-status |  |  | checkpoint | 9. Independent Certification
checkpoint-status |  |  | checkpoint | 10. Contractfire Completion Statement
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | e94eb9af-2b1d-58d9-9196-e48bb242f18b |  | textbox | Checked By:
text | 353739b7-85a8-5b45-b153-f208d743c074 |  | textbox | Date:
checklist-flat |  |  | checklist | Drawing - Fire Extinguisher Installation |  |  |  |  | Yes | Drawing - Fire Extinguisher Installation | a5e14613-0d34-4b01-9d08-1ce3183d2389
checkpoint-status |  |  | checkpoint | Installation locations as per drawing
checkpoint-status |  |  | checkpoint | Drg No / Revision
text | f2dec735-287a-55e2-89ef-85abd1b303e1 |  | textbox | Drawing No.
text | 590bfa3b-dec8-5904-a117-1b538e47f790 |  | textbox | Revision No.
checklist-flat |  |  | checklist | ITP 801 - Project Completion/Certification Checklist |  |  |  |  | Yes | ITP 801 - Project Completion/Certification Checklist | b8491d36-c359-4d4d-b496-eaebca46ca7d
checkpoint-status |  |  | checkpoint | 1. Hydrostatic Test Completed (ITR401)
checkpoint-status |  |  | checkpoint | 2. Independent Certification
checkpoint-status |  |  | checkpoint | 3. Contractfire Completion Statement
checkpoint-status |  |  | checkpoint | 4. Contractfire Warranty Statement
checkpoint-status |  |  | checkpoint | 5. Operation & Maintenance Manuals
checkpoint-status |  |  | checkpoint | 6. Quality Assurance Documentation
checkpoint-status |  |  | checkpoint | 7. As Installed Documentation
checkpoint-status |  |  | checkpoint | 8. Testing & Maintenance Commences
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | 097ccc81-503b-57f5-9c91-b1941e7cd295 |  | textbox | Checked By:
text | 46eeb947-e3d1-5cff-8ecf-7610de524125 |  | textbox | Date:
checklist-flat |  |  | checklist | ITP 304 - Sprinkler Control Valve Installation |  |  |  |  | Yes | ITP 304 - Sprinkler Control Valve Installation | b8bf265b-6b75-4287-b6cd-c7709e0ed9f7
checkpoint-status |  |  | checkpoint | Sprinkler Rough-In completed
checkpoint-status |  |  | checkpoint | 1. Monitored Alarm Valve Operated
checkpoint-status |  |  | checkpoint | 2. Solenoid Valve Operated
checkpoint-status |  |  | checkpoint | 3. Flow Switch Operated
checkpoint-status |  |  | checkpoint | 4. Run Remote Test Drain
checkpoint-status |  |  | checkpoint | 5. Installation Pressure Switch Operated
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | 53adad9f-a619-5eec-b4d6-6f6433df07c8 |  | textbox | Checked By:
text | 8d6b3b12-b7fe-5803-ab67-84ff51d1d4c9 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP 402 - Hydrant Hydrostatic Pressure Test |  |  |  |  | Yes | ITP 402 - Hydrant Hydrostatic Pressure Test | bfa67915-2638-4813-8bd6-d214524ca247
checkpoint-group |  |  | section | Guidelines
checkpoint-status |  |  | checkpoint | Guidelines acknowledged
label | ba543ebd-2a49-5108-b42d-f31ad44f7e87 |  | note | Air - 50Kpa for 30mins.
label | 1d0b5668-f3a4-56cb-a0e5-919375265be6 |  | note | Water - “1700 kPa for 2 hours” with no pressure loss.
label | caa274d1-0654-5aee-b801-6e042793742f |  | note | Note - Or 1.5 times the highest hydrant if greater – i.e 700kPA + 350kPA = 1050kPA + RL difference greater than 65m (650kPA) = <1700kPA
checkpoint-group |  |  | section | Air Test
checkpoint-status |  |  | checkpoint | First Sighting
date | 8e62f809-69fd-5537-88ef-8305cea40152 |  | date | Date:
text | b434f68a-cb7f-5f6a-af45-65adbd4d449e |  | textbox | Time:
text | b1a875ed-f3ed-556c-9e25-82e61c6574f4 |  | textbox | Pressure:
text | d2628753-62b1-55dd-b324-d6f2760b15b1 |  | textbox | Witness (CF:)
checkpoint-status |  |  | checkpoint | Second Sighting
date | 03478f6e-8541-5236-95fa-0f64a5297aca |  | date | Date:
text | 96dfcd9f-58b0-5be8-b9d7-cf1292b71526 |  | textbox | Time:
text | 18281985-dd1e-59d8-b289-5bfe2606819b |  | textbox | Pressure:
text | 4eefdfa9-b7ef-53e3-8b62-02f83ca1f4d8 |  | textbox | Witness (CF:)
checkpoint-group |  |  | section | Water Test
checkpoint-status |  |  | checkpoint | First Sighting
date | c039b0c8-9eae-52fb-b41e-d1b3be530cf4 |  | date | Date:
text | 29c5095d-f488-5c8f-a1fd-bdbe9064aef1 |  | textbox | Time:
text | 4bddff98-d34b-5407-aac6-461bcab729c7 |  | textbox | Pressure:
text | b8ffc0cd-9c00-5a71-b317-99e466125527 |  | textbox | Witness (CF:)
text | 86845bb0-b789-5273-b597-6d876d55a21f |  | textbox | Witness (MPX:)
checkpoint-status |  |  | checkpoint | Second Sighting
date | 71b3c32f-b73f-57f8-bef1-1231b5abe0c5 |  | date | Date:
text | ae87c10d-85cd-5d29-9e33-6d34031cfe82 |  | textbox | Time:
text | 42bed76f-56a3-5e89-9aa6-9a5041f60878 |  | textbox | Pressure:
text | 51b0bed2-72d9-5703-88f9-301a0f0e4042 |  | textbox | Witness (CF:)
text | e96f020b-fcd5-5571-9a7d-3a3e00cfe4c2 |  | textbox | Witness (MPX:)
checkpoint-group |  |  | section | Subsequent Sightings if Required
checkpoint-status |  |  | checkpoint | First Sighting
date | a08c8185-04cb-57ff-bf94-6532398c6c24 |  | date | Date:
text | a1d26c54-6844-58cb-88ac-56be1a837270 |  | textbox | Time:
text | 67da95cf-04fb-5c09-9dc8-0b76d57d92ce |  | textbox | Pressure:
text | 2c75acb7-4ac2-59f8-9c35-688a17cc7785 |  | textbox | Witness (CF:)
text | 521dc845-cb05-527b-a5c2-6fb217024680 |  | textbox | Witness (MPX:)
checkpoint-status |  |  | checkpoint | Second Sighting
date | 362f4cf3-4ec5-5b30-941c-edefb47165e7 |  | date | Date:
text | 47ba05f5-40b4-59a6-bfd1-cbabb53a8a83 |  | textbox | Time:
text | 3a4e8f54-eba9-5a5e-9f41-ac465b426b54 |  | textbox | Pressure:
text | cc02344e-742c-53e0-ab46-f8c033b04749 |  | textbox | Witness (CF:)
text | 6d51c84c-d9c3-5827-9a48-6f323b5a8ea4 |  | textbox | Witness (MPX:)
checklist-flat |  |  | checklist | ITP 601 - Diesel Pump Installation / Commissioning |  |  |  |  | Yes | ITP 601 - Diesel Pump Installation / Commissioning | d183e044-4b3a-48c7-b4fb-77aaa64f432d
checkpoint-status |  |  | checkpoint | 1. Pump room drawing revision
text | 97117255-4315-5051-ac90-3c4251c81673 |  | textbox | Drawing No.
text | c0eb5ac4-29eb-5819-8152-ecca2de7d355 |  | textbox | Revision No.
checkpoint-status |  |  | checkpoint | 2. Piping as per installation
checkpoint-status |  |  | checkpoint | 3. Power available from electrical contractor & approved for use
checkpoint-status |  |  | checkpoint | 6. Pump performance site test results Diesel S1
checkpoint-status |  |  | checkpoint | 7. Pump performance site test results Diesel S2
checkpoint-status |  |  | checkpoint | 8. Panel function test for Diesel Controllers
checkpoint-status |  |  | checkpoint | 9. Panel function test for Electrical Controllers
checkpoint-status |  |  | checkpoint | 10. 15 minute pump run test
checkpoint-status |  |  | checkpoint | 11. 90 Minute pump run test
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | 36711e4b-1042-5738-8359-dcffe2ab65ea |  | textbox | Checked By:
text | 6d95b3b8-6ee3-569d-8066-b0d939032330 |  | textbox | Date:
checklist-flat |  |  | checklist | ITP 302 - Sprinkler Installation - Below Ceiling Fit-off |  |  |  |  | Yes | ITP 302 - Sprinkler Installation - Below Ceiling Fit-off | db3a59ea-8cf5-4245-ae83-72e054d4ce75
checkpoint-status |  |  | checkpoint | 1. Drg No / Revision
text | c6dd2c2c-e797-5131-ae1c-a473260d1d7c |  | textbox | Drawing No.
text | 2e51d71a-bf1b-5435-898f-b3f24e449821 |  | textbox | Revision No.
checkpoint-status |  |  | checkpoint | 2. Ceiling grid levelled
checkpoint-status |  |  | checkpoint | 3. Sprinklers installed as per drg
checkpoint-status |  |  | checkpoint | 4. All escutcheon plates installed
checkpoint-status |  |  | checkpoint | 5. Areas not fitted-off as noted below
checkpoint-status |  |  | checkpoint | 6. Pressure Tested (refer I&TR 401)
checkpoint-status |  |  | checkpoint | 7. Charge hand inspection
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | 53f51c48-a9dd-5f03-aed7-eef14269e09d |  | textbox | Checked By:
text | b1b53409-7d3c-53e5-9c3d-ebe8b79c6b98 |  | textbox | Date:
checklist-flat |  |  | checklist | ITP 303 - Hydrant Installation - Hydrant / Hose Reel Install & Fit Off |  |  |  |  | Yes | ITP 303 - Hydrant Installation - Hydrant / Hose Reel Install & Fit Off | e96bc3e6-e09a-48e9-a7a9-8d46277f54d6
checkpoint-status |  |  | checkpoint | 1. Drg No / Revision
text | 2dab96c9-173f-54b0-9173-a81c34c25c5c |  | textbox | Drawing No.
text | 44be61df-bf6e-52a5-bf61-3b9466f17e5e |  | textbox | Revision No.
checkpoint-status |  |  | checkpoint | 2. Supports spacing & fixing as per code. AS:2419
checkpoint-status |  |  | checkpoint | 3. Pipework installed as per drg
checkpoint-status |  |  | checkpoint | 4. Pipes left out as notes & reason
checkpoint-status |  |  | checkpoint | 5. Hyd valve installed at correct height
checkpoint-status |  |  | checkpoint | 6. Hosereel installed at correct height
checkpoint-status |  |  | checkpoint | 7. Signage & labelling installed
checkpoint-status |  |  | checkpoint | 8. Hydrant valves locked open
checkpoint-status |  |  | checkpoint | 9. Valve Numbers and Labelling installed
checkpoint-status |  |  | checkpoint | Contractfire Sign Off
text | cdd45db1-2603-5f41-a0c1-622b51af4d5e |  | textbox | Checked By:
text | d4d1b57a-bb33-5732-a7cf-705829bdc8a5 |  | textbox | Date: