## ACUTE
FRANKSTON HOSPITAL REDEVELOPMENT ACUTE BUILDING Date: 5/3/24
LEVEL | Sprinkler Rough In 301 S | Drencher Rough In 301 D | Sprinkler Fit Off 302 S | Drencher Fit Off 302 D | Hydrant Install 303 | Sprinkler Control Valve Install & Operation 304 S | Drencher Control Valve Install & Operation 304 D | Gas System Install & Operation 305 | Sprinkler Hydrostatic Test 401 S | Drencher Hydrostatic Test 401 D | Hydrant Hydrostatic Test 402 | Extinguisher Install 501 | Pump Install & Operation 601 | Booster Install 701 | Final Documentation and Signage 801
B1 | YES X 2 |  | YES X 2 |  | YES | YES X 2 |  |  | YES X 2 |  | YES, System tested for the whole of Stage 1 | YES |  |  | YES, 1 X Doc required for whole building.
L1 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L2 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L3 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L4 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L5 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L6 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L7 | YES |  | YES |  | YES | YES |  |  | YES |  | YES, System tested for the whole of Stage 2 | YES
L8 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L9 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L10 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L11 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L12 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L13 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L14
L15 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L16 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES

## MDCP
FRANKSTON HOSPITAL REDEVELOPMENT M.D.C.P Date: 5/3/24
LEVEL | Sprinkler Rough In 301 S | Drencher Rough In 301 D | Sprinkler Fit Off 302 S | Drencher Fit Off 302 D | Hydrant Install 303 | Sprinkler Control Valve Install & Operation 304 S | Drencher Control Valve Install & Operation 304 D | Gas System Install & Operation 305 | Sprinkler Hydrostatic Test 401 S | Drencher Hydrostatic Test 401 D | Hydrant Hydrostatic Test 402 | Extinguisher Install 501 | Pump Install & Operation 601 | Tank Install & Commissioning 602 | Booster Install 701 | Final Documentation and Signage 801
L1 | YES |  | YES |  | YES | YES |  |  | YES |  | YES, 1 X Doc required for whole stage. | YES |  |  |  | YES, 1 X Doc required for whole building.
L2 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES | YES E&D | YES | YES
L3 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L4 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L5 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L6 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L7 | YES |  | YES |  | YES | YES |  |  | YES |  |  | YES
L8 |  |  |  |  | YES