## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-008 - Line Marking | itp |  |  |  | Yes | ITP-008 - Line Marking | 1de5882a-7dde-4618-bf1c-3daf1cf0a34e
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Line marking Conformance
label | 6decc52f-f238-5406-ab45-b16481be0a0b |  | note | FREQUENCY: Prior to commencing any activity
label | 7c288dfd-04f6-552e-b391-cad67fc8e389 |  | note | SPECIFICATION REFERENCE: 721.A05
label | 0eed24db-71c4-56d9-8c7a-215ae2ec8619 |  | note | ACCEPTANCE CRITERIA: Materials to be used conform with speciﬁcation
label | fa4c2060-243b-501c-8e2f-27a76b3071ef |  | note | METHOD: Record Review
label | 6433e9d9-b4ff-5fb3-90fa-e39d594a5687 |  | note | RECORDS: Material sheet
label | abe5d130-c2eb-59cf-932e-10707b24b6f6 |  | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
date | a6bb2cbf-0d23-52b0-b090-753f9c10c343 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Site preparation
label | d18fc51f-9df8-57ee-b89e-384f6558a56e |  | note | FREQUENCY: Prior to commencing any activity
label | d66cd9af-99fe-503e-b88f-bec56f029177 |  | note | SPECIFICATION REFERENCE: 721.A06
label | c4e4e470-6b2e-5cbb-b3a3-fb2a6752d2b4 |  | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings. Removal of any foreign material or debris.
label | 94a82f71-9f08-575c-9f6c-bdbbbe4ed1bd |  | note | METHOD: Visual and photos
label | b39132fc-055b-52d3-8708-1e0fd0fa57a5 |  | note | RECORDS: Photos
label | c9307376-374c-5ff1-b4c2-6f24de01fc24 |  | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
date | 14672bcf-16ca-5aa0-a5d7-8cfe11bb7f1c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Set-out of Pavement Markings
label | 7bde258e-74c2-5c81-bf6b-35ad7ddc6081 |  | note | FREQUENCY: Prior to commencing any activity
label | de495b17-2a23-56c0-ad33-f7afc9581f62 |  | note | SPECIFICATION REFERENCE: 721.A09
label | 6e1c40b2-5fcd-51d6-b2b3-7fb4bff75f4c |  | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
label | 29c9a0d7-fe06-53d9-a7d2-a1303ed045e4 |  | note | METHOD: Visual and photos
label | c558960a-0248-57f7-90b1-384e21ba49ad |  | note | RECORDS: Photos
label | f1b399a1-dea7-51e6-87f2-19eb06a93111 |  | note | RESPONSIBILITY: IP - Contractor Representative, HP - SWA Representative
date | 08893043-6dba-527a-9b46-af7ef49a05f5 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Installation
checkpoint-status |  |  | checkpoint | 2.1 - Line marking Installation
label | c216f09e-e64f-5289-90ff-ea17db6088ce |  | note | FREQUENCY: During Construction
label | 7b41ef96-e45e-5b58-8eba-c45bf7e440a0 |  | note | SPECIFICATION REFERENCE: 721.E01
label | 1fbb8408-bf5f-5a16-a62c-f142b6eaf5bb |  | note | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
label | c7f74a36-d531-5906-8184-1de2656be786 |  | note | METHOD: Visual and photos
label | 2de447ee-5a6f-56df-822b-09690da6d889 |  | note | RECORDS: Photos
label | 83888801-2031-57f3-9d6e-cf2df5ddddfa |  | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
date | ecf7e8c7-cd15-594e-b258-61d9a4262581 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Glass bead Install
label | 5455461d-d578-5fef-9098-a807025a435f |  | note | FREQUENCY: During line marking works
label | 129c5718-be6b-5fc0-91c6-c9e6c29be098 |  | note | SPECIFICATION REFERENCE: 721.E01
label | ce56130a-5110-595a-aec7-42c6ca9abcef |  | note | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a ﬂuid state to ensure embedment. Glass beads to have uniform distribution.
label | 351b2f21-f74a-5d7f-b7a2-9715036c0f93 |  | note | METHOD: Visual and photos
label | e9e028e9-191f-54b7-80e9-a5bf175842e5 |  | note | RECORDS: Photos
label | 6d897b20-0225-53cb-9378-5dd5cfdc8b15 |  | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
date | 66e6e253-8acf-59ac-ae0d-5e39d27d0b8f |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Compliance
checkpoint-status |  |  | checkpoint | 3.1 - Completion Inspection
label | a78cba1d-391d-5576-b565-d7c818c9ae63 |  | note | FREQUENCY: Upon Construction
label | eca57be0-f036-5a9c-bdf8-e25656d8747b |  | note | SPECIFICATION REFERENCE: 721.E01
label | c016ebed-7ed6-50d5-901b-0940617d2880 |  | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects.
label | d3cc0d09-3bbe-5fda-a526-1c56c0b925f3 |  | note | ○ Edges and cuts-oﬀs shall be neat and sharp, and there shall be no visible run-oﬀ, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles
label | 89a29f29-226a-5cf8-a981-41a43db99235 |  | note | METHOD: Visual and photos
label | e7353a58-a06a-51aa-8a5e-2b88791f02b0 |  | note | RECORDS: Photos
label | 2139db14-7aa0-5b72-8de0-a3783d940be8 |  | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
date | 453e1ff4-6428-5952-a42b-9d525c515a66 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 5d9c743b-b1d0-566a-9dda-72569b99b130 |  | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
text | 2275156b-b27e-564c-83c7-e53642e4cd9e |  | textbox | Print Name:
text | 6b1dd9bd-aca6-522f-9252-6caa596d6f13 |  | textbox | Position:
date | 3320fbd0-ce9f-544f-b805-702c0f697824 |  | date | Date:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-045 - General Concrete Paving | itp |  |  |  | Yes | ITP-045 - General Concrete Paving | 31e44898-df83-4487-b1cc-5d63c9e2acd3
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | eee305db-0ad2-5699-b288-4788c2b43125 |  | note | FREQUENCY: Prior to commencing any activity
label | c8d7bea0-57cc-583c-9fd9-b621043824cf |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 6b9c67dd-4cb9-5f4b-9744-4e7527ee10ca |  | note | – using the correct and complete set of drawings
label | 3efe8d84-93fb-583e-bc2b-451f4118c0b7 |  | note | – all drawings are the latest revision
label | 31b372e6-c70b-5e8e-b17b-8f237045cce6 |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | 38ee64f2-e227-5668-bfab-9ec0daf653ba |  | note | METHOD: Visual Inspection
label | 7f692d85-cf72-5493-8c74-aaef275660b4 |  | note | RECORD: Signed ITP
label | 45436503-1205-5db6-96ee-9a9e0dfc19a0 |  | note | IHP
label | fdd44d80-f5cd-5032-bfb5-8f806677d98e |  | note | RESPONSIBILITY: SWA Project Manager
date | 8f7436cd-24d0-54e5-af47-eaeee43eef71 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 9f91c3b5-48be-5d37-85a0-8256be9ca02d |  | note | FREQUENCY: Prior to commencing any activity
label | 93c0e39a-a5f8-5024-8170-a9a032969438 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
label | 0d4b03c9-0adb-53ab-befb-105153d6be76 |  | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
label | 03b7fbd0-c5c4-5500-a36e-404816c634db |  | note | METHOD: Visual Inspection
label | 0e717617-a77c-522a-8569-c6d075d69eab |  | note | RECORD: Signed ITP
label | 88dddc8f-70a7-5945-a81b-4cb883b91b85 |  | note | IHP
label | 2dab62d2-2af2-541a-baa5-45ecddeaafad |  | note | RESPONSIBILITY: SWA Project Manager
date | 0c45d27c-a007-5bf8-8f0c-28f42159517f |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - Survey Set-Out
label | abae3e05-7160-545e-a830-bc34f458e2b8 |  | note | FREQUENCY: Prior to commencement of excavation.
label | b4301f2d-b7b3-5195-ad81-984de74540b5 |  | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | 02d60dce-893c-51bf-a329-de97b920bb44 |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 97460939-0a43-504b-87a3-7e7a2c0a03e2 |  | note | METHOD: Verify
label | f09ee51f-e536-52c2-9ac9-de3e2305bacb |  | note | RECORD: Signed ITP
label | 12b8d6be-108e-5097-a66e-99ebd8a9eca4 |  | note | IP
label | d8157272-ebae-54db-a99c-80b3065efb5e |  | note | RESPONSIBILITY: SWA Project Manager
date | 02b04572-69a8-53d1-818b-757e80e6a654 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Excavation Permit
label | 03252232-fe2e-5a4d-b036-738dad4895a7 |  | note | FREQUENCY: Each Lot
label | 8af09b81-6abb-5249-a7bb-ab137bc4f8cb |  | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
label | c07e38af-35e2-5e79-b28e-0fc068c3c13e |  | note | REFERENCE DOCUMENTS: Excavation Permit
label | 4a361387-65a4-5272-b5ec-4388fde85aaf |  | note | METHOD: Verify
label | 856122d7-7ff0-5172-91bd-85e294e46ccd |  | note | RECORD: Signed ITP
label | 97cbc96f-7798-5c85-a32b-0160f8864d66 |  | note | IHP/IP
label | 45a8e1bc-177e-530b-8779-e42edbb64f42 |  | note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
date | ab6dfcee-9cc6-5b21-bec3-6a58e2b39ce4 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Formwork
label | b3b985c0-28db-545c-8d82-3d36a4cfa80e |  | note | FREQUENCY: Each Lot
label | 9ee77081-b54e-5159-bcb7-ea45c4ac6a7d |  | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
label | b760cfe0-e69e-511f-8e5e-33a77b7c533f |  | note | REFERENCE DOCUMENTS: AS 3610
label | 89f51154-a6d6-5e74-8575-0ab43c80eb8e |  | note | METHOD: Site Inspection
label | 84f7f7fe-b106-520f-8f37-4718d9860513 |  | note | RECORD: Signed ITP
label | e7d3d7a3-84e2-57cf-8274-2b32d9c52d50 |  | note | IP
label | ba5a65f5-ec86-5068-a12f-628344a3522f |  | note | RESPONSIBILITY: SWA Project Manager
date | 43b7d9d1-2223-565c-8c60-93cfb407a4c2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Reinforcement
label | d977ed63-365a-5784-8115-9cb77129d6b8 |  | note | FREQUENCY: Each Lot
label | 9fbdaaf1-a7a8-5a80-a574-d0f94a16fe47 |  | note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671. Minimum cover of 50mm.
label | deed33a2-cf34-5341-b812-33d94defdda1 |  | note | REFERENCE DOCUMENTS: AS/NZS 4671
label | bb66d9c4-36e8-5292-a3fb-894b1e131ce7 |  | note | METHOD: Visual Inspection
label | ab682694-8311-5184-8de8-d53d35473aa8 |  | note | RECORD: Signed ITP
label | b7836cc6-a210-5599-aefc-3a2b6b85f24e |  | note | IP
label | 50cb1299-6081-5559-93fd-20d8e6674e5a |  | note | RESPONSIBILITY: SWA Project Manager
date | 923e47b5-5730-54a5-aef7-ac426c05fb6c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Temporary Drainage Provisions
label | 24f4c914-4947-5a8f-8ec7-2ecca6acae77 |  | note | FREQUENCY: Prior to commencing
label | 3169cfbd-1019-5fc7-a713-0752a938f562 |  | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. Obtain written approval from relevant waterway authority.
label | a5994913-35dc-5e73-8d0d-3af76faf0e42 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
label | fa7ae607-c8e0-51db-8357-442afacae9ea |  | note | METHOD: Visual Inspection
label | 3952a518-6b38-5987-9d53-9f2618de5399 |  | note | RECORD: Signed ITP
label | 6a994837-f953-506c-b73a-23444f4627ea |  | note | IHP
label | b295128c-a848-5bda-828d-6927061ea0f0 |  | note | RESPONSIBILITY: SWA Project Manager
date | 247db84d-0562-5b5f-b1c7-aadaf6b5769d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Bedding
label | b86142db-7ed2-506c-8022-12f89d4cfec4 |  | note | FREQUENCY: Each lot as required
label | 19ccc43e-9e69-5614-8486-9250ae584e49 |  | note | ACCEPTANCE CRITERIA: Crushed rock bedding material as per drawings
label | f9b52c92-bf19-5eca-a988-d11736b9bb1c |  | note | ○ Bedding trimmed, moistened, and compacted as necessary
label | 4150a687-4a52-5cb5-9ddf-29e55bdcd3b6 |  | note | ○ Bedding compacted thickness: Footpaths and other surfacing ≥ 50mm
label | 58cfa338-2c0a-5856-9c01-9fa94cae0523 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.18 IFC Drawings
label | 8a81b5ba-6e5e-562a-b6e7-285e246fd04d |  | note | METHOD: Site Inspection/ Document Review
label | fc1ed9dd-34c1-5b3c-abb1-78b58b4fe61c |  | note | RECORD: Signed ITP
label | dbd7fe59-b8af-5708-bbd9-5d0d59c7e813 |  | note | IHP/AP
label | 9424fe40-9803-541f-a6a3-27aa14256388 |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | 874afa84-ec5a-54d4-8a36-ee27ac2b52a5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Concrete Placement
label | 4f7d565d-7f57-5453-b26a-93912bc3bd78 |  | note | FREQUENCY: Each lot as required
label | acc00d4e-8e07-599d-a0fd-1db87aff3296 |  | note | ACCEPTANCE CRITERIA: Concrete strength as per drawing speciﬁcation
label | a663f449-dcd3-5701-bddf-3ba323dabc69 |  | note | ○ Comply with requirements of AS1379
label | 665753b3-3f85-5bc6-9053-cd7aab90e78f |  | note | ○ Aggregates to comply with Table 703.051
label | 1d6965d9-4404-563d-822a-7be694dfb7ac |  | note | ○ Extrusion machines cement content ≥ 320kg/m3
label | fad3e71a-cc88-5f5f-acc7-f5b89e5181d0 |  | note | ○ Surface pitting < 5mm diameter
label | 9858029a-694f-585c-9191-dd273623ecd9 |  | note | ○ Concrete to be satisfactorily compacted. Proﬁle transitions between 10-20mm per metre.
label | 2d590dc3-87de-56f6-98c5-7ae19cd651e3 |  | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.04(b), VicRoads Std Specs 703.20, VicRoads Std Specs 703.21 IFC Drawings AS 1379
label | f6bee428-7f17-5475-aa09-5cfc7aad58e6 |  | note | METHOD: Visual Inspection
label | c09aa0fe-5e05-5d2e-9d3d-d1463ffac490 |  | note | RECORD: Signed ITP & Test Reports
label | d6565033-d887-5731-ad83-91bb7cb2a0b9 |  | note | IHP/AP/TP
label | cd559b5b-f877-5455-b216-12021ee4b89e |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
date | de0c3ad5-15ba-5d22-acab-0dc1ea949d0e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Finish Surfaces
label | 97d1d49e-0650-5d7a-a283-fe6beac811b7 |  | note | FREQUENCY: Each lot as required
label | 2458e28b-0d1d-55df-bf30-2fd7e5864265 |  | note | ACCEPTANCE CRITERIA: Footpaths and other Surfacing: Wooden ﬂoat ﬁnish
label | 01554e45-55e2-573e-8714-8a9355e842ad |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.22
label | e383673f-a8cf-5bbc-8153-de67e5b615ec |  | note | METHOD: Visual Inspection
label | a9b975bf-17ce-5878-b1d3-1130035dbc29 |  | note | RECORD: Signed ITP & Test Reports
label | d787be7c-1b20-5e06-b37a-a68c9f3e271a |  | note | IHP/AP
label | 9b3c965a-a117-5631-95d7-940e51cba2e9 |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | 0d0ba586-677c-5291-8567-6edcec752a21 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Tolerances
label | 7e1f213e-c927-5e3a-bb54-588ffee96534 |  | note | FREQUENCY: Each lot as required
label | 0039b4cc-3463-5e3d-9747-203a1732f40b |  | note | ACCEPTANCE CRITERIA: Match existing surfaces ± 5mm
label | c6d108b4-31ec-58dd-a1c9-0fdaf1cdb20e |  | note | Section dimensions:
label | 76921a82-71b7-50fa-87ca-eb95f7c7e047 |  | note | ○ Within 5mm and 15mm for width; and
label | 2f686c82-3021-5e91-86dc-383081391768 |  | note | ○ Within ±3mm for dimensions less than 25mm.
label | 823267a9-7e77-531f-b955-7c5996bd3df5 |  | note | Concrete footpath:
label | 423372ed-8a34-59a6-bb01-bacb34bc7c0a |  | note | ○ 150mm thick
label | 1ac7b9db-405b-5a4b-9c53-d41690d3f1d5 |  | note | ○ SL72 reinforcement
label | 2a0eae66-1f89-55b8-89cd-aca1468ee7b6 |  | note | Concrete Surfacing:
label | bd278de7-ae77-531c-8e6a-f98576d30908 |  | note | ○ Type 1 100mm
label | 6a9a005c-a671-5582-88bc-e979a7ad5656 |  | note | ○ Type 2 150mm
label | 59281743-6354-57b8-9065-4eb789c31dd4 |  | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.13 IFC Drawings
label | fce9109c-59a6-57b8-a526-a376140eb285 |  | note | METHOD: Visual Inspection
label | cfca9fed-4e1f-5b37-ac15-be65df065258 |  | note | RECORD: Signed ITP
label | 62a919a0-fbce-5427-bb9b-b5a2305a2328 |  | note | IHP
label | 4f5590ec-c453-5983-b09d-f0a68b59cc58 |  | note | RESPONSIBILITY: SWA Project Manager
date | 8b537dfe-da43-5a13-906f-d5e10c4d52d7 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.10 - Joints
label | c0eda2c0-4fdb-5684-a781-2574ebefbc25 |  | note | FREQUENCY: Each lot as required
label | a1d0afd5-e008-5fe7-9428-81a406c1d340 |  | note | ACCEPTANCE CRITERIA: Footpaths and other surfacing:
label | 00367f8a-f964-588f-ad0e-9aece009add2 |  | note | ○ Expansion joints at 12.5m regular intervals
label | c7bb1a40-deab-58bd-a61d-eaff096da0d4 |  | note | ○ Control joints at 2.5m regular intervals
label | 3b81d342-8743-502f-8d9b-d1fef036eafe |  | note | ○ 20mm deep and 5mm wide
label | 6890dbdb-92eb-5c26-9d1f-694580d3c34e |  | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
label | 28b948a1-deba-5b69-86f0-ce86f3b2389d |  | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.23
label | 9dc6f66e-636b-5095-8f59-286d7cd20127 |  | note | METHOD: Visual Inspection
label | 2c38b942-8492-52a6-861e-c17e97ea07ab |  | note | RECORD: Signed ITP
label | 242f470e-e1d3-5f64-9745-98a9bb169abc |  | note | IHP
label | a8a79afc-d754-595c-a364-ffc1cd16cfb3 |  | note | RESPONSIBILITY: SWA Project Manager
date | 398720d9-0b29-530a-9002-bd63a7e02063 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.11 - Backﬁlling
label | f2fea800-ab53-551b-8af7-686702f2bbeb |  | note | FREQUENCY: Each lot as required
label | a9e9f3e1-8090-57d3-89ab-f537973b7684 |  | note | ACCEPTANCE CRITERIA: Topsoil compacted in layers < 150mm
label | 7bff6008-e82e-5e36-923d-bb08df9da072 |  | note | ○ Width ≥ 300mm behind edging to top of edging
label | 00c16956-63fb-5a9f-95b5-38084361c3e7 |  | note | ○ Topsoil placed after 3 days of concrete placement
label | c4bb5253-c4e9-57f6-9cb7-12ababf9993d |  | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.26
label | cb708d60-148c-5c77-b55b-8c03917beea2 |  | note | METHOD: Visual Inspection
label | a52af329-6691-5041-b433-630a748bddb0 |  | note | RECORD: Signed ITP
label | c6d14f8b-b636-5e39-bd6c-45c1d8bcbb50 |  | note | IHP
label | eb384a0c-84cf-5b91-acb2-e9ce86be90b0 |  | note | RESPONSIBILITY: SWA Project Manager
date | 8d7ea636-fc0d-536a-8d62-d1c00989f915 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | b61cd3df-1245-58d3-98da-582d5d4fb73e |  | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
text | ca92968e-fd7d-596f-b881-5c495579f796 |  | textbox | Print Name:
text | 7536c187-d446-55b3-a24c-2c06c642217f |  | textbox | Position:
date | b45b5b7b-c0f3-5fb7-92e9-46c8c6e8a06c |  | date | Date:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | ITP-009 - Road Signage Checklist | itp |  |  |  | Yes | ITP-009 - Road Signage Checklist | 4a03a7de-8397-44e8-8eb7-36796f59925e
checkpoint-status |  |  | checkpoint | Inspection Checklist Items
text | dc9b7c6f-a3ed-5493-8998-dbc970ea3834 |  | textbox | Sign Code & Dimensions
text | a917188f-ab1a-5f77-b82e-144aef0167e9 |  | textbox | Chainage Location
text | c5198dd8-98c3-59ae-a1b4-113408481183 |  | textbox | Number & Post per Assembly
text | 2477ad5e-17d6-5890-b4ad-005a3ffec528 |  | textbox | Mounting Height (H) (mm) & Spacing b/w post(S) (mm)
text | 98565e99-e225-56ba-bf92-09385b9da396 |  | textbox | Post Hole Depth (D) (mm)
text | 64db3e30-c50c-5fe8-8663-c497b25407f1 |  | textbox | Fitting Type and Number of Fitting
date | dd0678d8-3635-54eb-bb12-b59c577f0e13 |  | date | Footing and Sign Installation Date
label | 9600558b-1bcf-560a-b940-10cd212b3d9d |  | note | Photos
checkpoint-status |  |  | checkpoint | Final Inspection
label | 4c619913-70b2-59b9-8e85-7aa07009facc |  | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
text | 7c9377e4-e5f8-5220-be1f-c2b39c3c57de |  | textbox | Print Name:
text | f6476e10-3a1a-5684-898c-a073d3a3fdf6 |  | textbox | Position:
date | bd7fa19e-daa1-5a8b-9ef3-03c4d76e0e2f |  | date | Date:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-004 - Underground Drainage | itp |  |  |  | Yes | ITP-004 - Underground Drainage | 555a15e2-c394-4195-b3b7-2def244e05c1
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to.
label | ff7f771d-f196-5e94-89c0-d98ee7bccdc5 |  | note | FREQUENCY: Prior to commencing works
label | f1e48edd-754f-5254-98e2-0d81f4bf1295 |  | note | ACCEPTANCE CRITERIA: Refer to the VicRoads Traﬃc Management speciﬁcation 166
label | 846dc3d1-3f0d-548b-88ce-ec81a4516cfc |  | note | REFERENCE DOCUMENTS: Traﬃc Mgmt. Plan
label | 3b32932d-65ad-5802-8d9b-f12f832e80a9 |  | note | METHOD: Visual Inspection
label | 9af47316-48b4-5e62-a789-d9cb5127c919 |  | note | RECORD: Signed ITP
label | 09237390-a739-5faf-b772-8dade004f4a6 |  | note | IHP
label | 7c013968-a164-5048-9bf4-0e39e513a1eb |  | note | RESPONSIBILITY: SWA Project Manager
date | 30b0e11b-b6b1-5617-ae1d-0998085e5877 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Purchase of pre-cast pits, pipes and end-walls
label | 195669b0-1473-5494-a15a-ad3ec8a39b49 |  | note | FREQUENCY: Approval prior to placement of order
label | 31a43218-3e13-5342-b183-b8ec49858bb2 |  | note | ACCEPTANCE CRITERIA: Refer to Construction Drawings
label | 5700c480-85eb-5218-93a3-706a1f664619 |  | note | REFERENCE DOCUMENTS: Vic roads Standard drawings
label | dd1103a1-592e-5fa2-a1df-403df97b4a5e |  | note | METHOD: Review and approval of documentation, Visual inspection
label | b1ea887b-e0bf-56d9-9b74-1e58a173bb73 |  | note | RECORD: Signed ITP
label | 87e90362-6a1a-532a-b98e-3458a3a56f01 |  | note | IHP
label | ef83053c-2695-53b4-b1cd-2a6e14967af3 |  | note | RESPONSIBILITY: SWA Project Manager
date | 4eee7202-5202-5afd-a007-1628a7ce0d0f |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - CONFORMITY WITH DRAWINGS - The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed.
label | 41bc5e39-ebc3-5862-ae41-6030e1febc70 |  | note | FREQUENCY: Each lot as required
label | 8048936d-695b-5cdd-937b-b38056a05933 |  | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent.
label | 44adf031-0957-5d70-9ecf-c9728a776289 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
label | 2af47ceb-97b3-5f1e-8621-68cb1577ea32 |  | note | METHOD: Construction Drawings
label | 4eb6ebae-de34-501e-b1c7-690696fc4379 |  | note | RECORD: Signed ITP
label | c1e9b9c5-bfe7-56fc-8315-e88f4513fc5d |  | note | IHP
label | 0314b7e7-da94-50cc-96a9-00fc9f06bed8 |  | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | b225dc7d-df7d-533f-8ab6-615287710640 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level
label | 2253bb94-74fd-544f-b1be-00da20521073 |  | note | FREQUENCY: Each Lot
label | d326f21e-5a8e-5f77-b41b-fd03ece16966 |  | note | ACCEPTANCE CRITERIA: Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be:
label | 91a11db4-0d59-5076-8514-b961491675e5 |  | note | (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm
label | 7af79b61-d7d4-592d-b239-f1ea814f9603 |  | note | (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm
label | 5ccb1813-f18a-572c-ad93-988c6e037d8b |  | note | (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | d89417c4-1dbd-54c6-a591-3542d3627404 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
label | 6e29027b-260e-5746-8b1e-04e31e593e2a |  | note | METHOD: Construction Drawings
label | f646c043-e403-532e-bf52-ac5c9d1595e4 |  | note | RECORD: Signed ITP
label | 5796186f-716a-5899-afe2-91ea32a06e83 |  | note | IHP
label | 08433fe9-66f6-596e-b684-be188dd7aa3d |  | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | f4968ee5-7261-587f-a4c3-61303e64aad8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - EXCAVATION
label | eb6a81b1-106b-5f34-acc5-de0ef1dc8f6b |  | note | FREQUENCY: Each Lot
label | d37c6318-756c-531a-b22b-17daa23f131a |  | note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm
label | 5f543bae-e0ac-5b82-80d5-ad5d368ef555 |  | note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.14
label | 239f74ed-19b8-5b33-a3e6-4f71c526e866 |  | note | METHOD: On-site Measurement
label | c5554e91-31f3-535b-a926-8a87cca0db04 |  | note | RECORD: Signed ITP & Drainage Checklist
label | a828992a-5878-5fea-a175-7d8ac53ec858 |  | note | WP
label | 33b10b9d-3efd-5adc-aff9-bbe3d9ff2872 |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | d8375f6f-ff33-5a15-b156-fb2952ca0d6e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - CULVERT BEDDING - Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert
label | 25edea32-d970-5686-9c14-edca3b9efbfc |  | note | FREQUENCY: Each Lot
label | eb66c574-bb8f-5179-b2c3-6a00493b25af |  | note | ACCEPTANCE CRITERIA: The compacted thickness of bedding material following any shaping necessary shall be not less than:
label | 3388aab4-97b7-511f-94a8-f344513ebbc7 |  | note | ○ 100 mm where D < 1500 mm
label | 7d4a4a5d-71ea-55d7-af83-c565b0b0ecd2 |  | note | ○ 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
label | 63c746b0-d9c2-53e3-82b2-3869e08c7f7f |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.15
label | 1efcf702-d6c4-5fc2-b96a-28f08dfcd303 |  | note | METHOD: Site Inspection
label | 18a937f2-a3e1-5bfd-80bd-dcaa997371f6 |  | note | RECORD: Signed ITP
label | cfb493f4-4784-5d48-844f-4e73bfc61023 |  | note | WP
label | bfa05788-6b45-5bad-ac25-11dc14849300 |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | 164537f7-8e27-51d7-84f9-89a18d28af18 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - PLACEMENT OF FILLING
label | c1c0360c-17a2-5ff3-bc82-281da7c28cc7 |  | note | FREQUENCY: Each lot as required
label | bd9a776e-abe2-546a-b401-bb87129b5561 |  | note | ACCEPTANCE CRITERIA: (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
label | 160d80d9-ff77-5f51-b798-2054f70cd708 |  | note | (I) Culvert Under Area not to be Paved
label | 0520f71c-d372-5b7a-915f-3b14a6e7c495 |  | note | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
label | 288ada38-b0ab-508b-a609-231cf2a5eb01 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.18
label | c11628d9-8c2f-547c-a3d4-bd3c29584dbd |  | note | METHOD: Site Inspection
label | 34d13068-7144-586d-9cb4-8dc1e9561164 |  | note | RECORD: Signed ITP
label | fa434381-2d8a-5b79-8a37-a56f27a08b6b |  | note | WP
label | 95987a52-448a-5ad6-ad46-d0a13403a993 |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | 96f4d2af-c83c-5fea-88d4-62590757ddd1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS
label | 138dc408-69fc-5f5a-8457-3469d3d95724 |  | note | FREQUENCY: Each lot as required
label | 9a2feca4-3283-5092-bfd0-a4678f117675 |  | note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV).
label | 4e9109f9-343f-5fbc-9da1-718231d95947 |  | note | ○ Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
label | 87e7f08a-f96f-5d07-b90d-aa12b5d88b49 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.28
label | 62e347ab-b426-508c-ae0c-1024c9cc5cfa |  | note | METHOD: Visual inspection
label | d7f8dc8d-3819-5d55-8f64-c2b409877f47 |  | note | RECORD: Signed ITP
label | 8089c255-87cb-5470-a96e-b2c801bafb1d |  | note | HP/AP
label | c3e603f4-4c5b-53b7-8f4f-ee08d4470d78 |  | note | RESPONSIBILITY: Project Engineer/Clients Superinten dent
date | d5bd297f-9113-5a39-b980-f5e0b8f88b12 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Where required installation of Geofabric or Jute matting and beaching material in swale drains
label | cd3f9388-74bb-5021-a6db-086733703b09 |  | note | FREQUENCY: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse
label | bf175921-e803-564c-8f3d-1bf7d662556d |  | note | ACCEPTANCE CRITERIA: Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows. Rock shall be placed with a geo-textile liner.
label | a88ccc67-6170-5043-a577-bb75f2d995aa |  | note | REFERENCE DOCUMENTS: NIL
label | c4b9166f-c4a8-5869-8242-4ff325f26b11 |  | note | METHOD: Visual inspection
label | 8d82beaf-77e0-5b9c-877d-eefb3b017b03 |  | note | RECORD: Signed ITP
label | bdadf9cc-a6a1-5f77-81ee-d96f0df941b1 |  | note | IHP
label | d4dafda0-0727-562c-994e-7c2f64c04999 |  | note | RESPONSIBILITY: Project Engineer/Si te Supervisor
date | aebf675d-db93-5925-94f6-6aaaedf55e39 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Testing Requirements
checkpoint-status |  |  | checkpoint | 3.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT - Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | 38f7f3fd-186b-5a94-9d3c-d46cfddc8722 |  | note | FREQUENCY: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls)
label | 39406688-46e7-5934-88dd-11172fada3d6 |  | note | ACCEPTANCE CRITERIA: (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | fc9b0346-7df2-5e7c-8e79-36472f115322 |  | note | (b) Backﬁll
label | 84515d71-0f2e-55eb-9c0a-e16782ff187a |  | note | (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | 73d39840-e6d7-5c0b-8fd4-8bafe562197f |  | note | (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | 396e2c2c-1b7b-578c-bd19-8bc8eb1b9057 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 701.19
label | b4b94626-f9df-5024-bf29-1e39dbd6c81e |  | note | METHOD: Lab Test
label | 74d128c5-1452-5f90-beee-94ceb44c230b |  | note | RECORD: Signed ITP
label | 3782413a-7cf5-5707-89ed-a514e9b0186e |  | note | IHP
label | 020dfa56-df5b-5eee-81e0-d26e3b402d1a |  | note | RESPONSIBILITY: SWA Project Manager
date | 1492241a-2e16-51e4-bc88-241b9eba531f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | bd0e6189-8169-5e75-838d-b3124d3c7a13 |  | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
text | 0db37f49-dd06-5ab4-9403-1ca4a21edb57 |  | textbox | Print Name:
text | f9cbb62d-571f-5bfd-bb23-97eeb63cd4a6 |  | textbox | Position:
date | 52ce646b-4fd7-5d88-bf27-a1d49b30da0a |  | date | Date:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-007 - Hot Mix Asphalt | itp |  |  |  | Yes | ITP-007 - Hot Mix Asphalt | 8a26ec7b-47e9-40ba-bcf0-db20d12d50e2
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Site Inspection and Base Conditions
label | d688b9be-5b87-57c4-9401-8e4ee3044ced |  | note | FREQUENCY: Prior to commencing paving.
label | 77fe2bc8-1442-5be1-96e4-22b2b5e30898 |  | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from surface water. All manhole and valve covers have been raised or lowered to the new surface level of the pavement.
label | 5db3395a-5a33-563d-af34-17c90380b207 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.1
label | 9f664117-1f46-5641-8a55-271a2941339d |  | note | METHOD: Visual Inspection
label | f6b9ce53-7b0e-55f5-bf58-2190378470f2 |  | note | RECORD: Signed ITP
label | 3149520a-eadf-5e65-84c7-25d8c44897df |  | note | WP
label | 62204960-fdca-5390-8706-6d46b6c16a02 |  | note | RESPONSIBILITY: Site supervisor
date | 7a542c34-35be-501d-bef9-f7c96b21f6bf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Ambient Conditions for Asphalt Placement
label | 0a2ecb52-16f0-520a-a241-548c9b5501b7 |  | note | FREQUENCY: Prior to commencing paving.
label | 58b668e8-a984-5f99-847e-f7f7849aa2ec |  | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed if the majority of the surface area is below:
label | 21a4db70-16bd-5874-b125-c5d207382d63 |  | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | e74390b4-ae7a-5952-85e9-f515b4722f5a |  | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs.
label | c975c47b-f504-5bc5-af6d-5fc2f3139d57 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 407.13
label | b5ace85e-d10c-5e83-8616-5240a88f8e00 |  | note | METHOD: Calibrated thermometer
label | 05794ef6-1210-5f5e-988c-9e216f5d1c6e |  | note | RECORD: Signed ITP
label | 1fa6e8b4-45b7-5c03-9bd0-ad631acac909 |  | note | IP
label | b320e086-223b-5c4d-a615-12e62920d7f4 |  | note | RESPONSIBILITY: Project Engineer/Site supervisor
date | cc06b2f3-d3c5-5b1b-8572-83b09a446a34 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Surface Preparation
label | 4e54f265-bace-5007-9924-59ff70e7ba9d |  | note | FREQUENCY: Prior to commencing paving.
label | 3ca451bd-60bc-5aa8-82ff-2fb8f95d4ae6 |  | note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material
label | d7bca43d-b98f-5a72-b645-801e4af922e9 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.3
label | b7150c70-7401-5f10-a71c-de2898c7e3a7 |  | note | METHOD: Sweep Clean and Inspect
label | 6deba588-d573-5826-8f7d-5cf57d2a7308 |  | note | RECORD: Signed ITP
label | 4f8547f4-8f39-585e-846f-eb93a72dee5f |  | note | WP
label | 97ac1dbb-d171-51cc-b773-9def1a760570 |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | 05dbeb64-1a43-5b0f-ab97-a2a9299cfea7 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - Application of Tack Coat
label | 2bc89cc0-05fd-5d39-8173-cf3ac73aea87 |  | note | FREQUENCY: Prior to commencing paving
label | 984a04d0-36e7-50cd-8190-d10f5be69ef0 |  | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform ﬁlm over the surface area at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
label | b126fdc9-f32a-5128-a548-41a431071e21 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 407.15, AS2150 11
label | a513f9de-8a20-5afb-8cdb-fe7b7bf868e4 |  | note | METHOD: Visual Inspection & photo evidence
label | 819b6f4c-677c-5939-bf3e-385c4c9c3ddf |  | note | RECORD: Signed ITP/Spray Record
label | 085a77d8-e12c-5d16-97d2-38661c7775e2 |  | note | WP
label | db648bc6-04a9-5f5c-ac17-0872310e84da |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | 9524c87e-3988-520f-8b62-836e7879ac95 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Planned Joints
label | ba46facf-a072-5cc6-93b1-8ddeca9a627d |  | note | FREQUENCY: Prior to commencing paving
label | 22cc8efb-d9e3-5cfa-9255-9ae523d70f8a |  | note | ACCEPTANCE CRITERIA: A site speciﬁc paving plan shall be generated by the contractor prior to asphalt commencement to adhere to the following: Transverse Joints: Oﬀset from layer to layer by at least 2m Longitudinal Joints: Oﬀset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an oﬀset from layer to layer of not less than 150mm.
label | ab9a16a0-8110-5e82-9f33-bbb12b923d13 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 407.17 (b) & (c)
label | 95996cce-9371-5937-9658-016a41201d7a |  | note | METHOD: Measure and mark out runs and submit Paving Plan to Client if requested
label | 3d58eaf1-61e9-5cc6-b381-2f3448a26604 |  | note | RECORD: Signed ITP/Job Sheet
label | 00d39b2f-424d-567f-bfa5-6a0decd08391 |  | note | WP
label | 9ec50226-d017-515d-846c-a3e479e4b999 |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | dbb35a21-e66d-5201-a4d2-1dff79c94fad |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Commencement of Placing
label | cca105be-6bd6-5600-ac6f-65bcc11a3079 |  | note | FREQUENCY: Prior to commencing Paving
label | 683db6f9-07e7-55cd-8bb3-bdaa06b97f49 |  | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub- base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Vicroads Superintendent.
label | 068e27e3-051d-572c-8924-d5b1ea8f3f4a |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.18
label | b511a1d6-2391-58b3-a195-d66345ed525d |  | note | METHOD: Visual Inspection
label | 53a5f474-6809-567f-bcda-a795f9214c82 |  | note | RECORD: Signed ITP
label | 63aeb9c7-da48-5ccd-8879-363cd0e982d5 |  | note | HP
label | a51be06b-60e3-5c7c-91e1-0b8ed01b9320 |  | note | RESPONSIBILITY: SWA Project Engineer
date | 2feae5b8-a61c-5937-9a35-e1a01f92a36d |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Delivery of Mix
label | 35c6435e-3596-510a-ab77-9fe4f8e7b182 |  | note | FREQUENCY: Each Load
label | 8dac07ce-4df2-5efe-83be-bf1ba1081dc2 |  | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | 9ef15b20-6680-5bdb-9cfb-9fa375011ac0 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.16, Table 407.081
label | ed145bdc-d3cd-59b4-a60d-32e90a0175ef |  | note | METHOD: Visual Inspection & Delivery Docket
label | 31350090-570c-5cb2-8a93-d05f68c8ecf7 |  | note | RECORD: Signed ITP & Production Dockets
label | 01d78e9e-b9b9-5b71-bbd4-212c346d7d27 |  | note | WP
label | bec095f5-a796-55ca-b444-42f5b4d59bea |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | 19cc829a-5c9e-5a21-8524-84978ad9bf59 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Traceability
label | 82c1addb-3683-5b4c-93c1-01ea48344802 |  | note | FREQUENCY: Each Load
label | e1f1bbfe-0d5f-5c7f-83bc-c2f11703b555 |  | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, oﬀset/lane and layer
label | 7b7f2e40-84a3-555e-8ae0-489a7049337d |  | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | ee9c3476-6420-55a6-9993-a2d1de3442f4 |  | note | METHOD: Project Engineer/Site Supervisor
label | 23c11b58-21bc-500e-a1c6-850486660080 |  | note | RECORD: Signed ITP & Traceability
label | e70ee5c4-d130-52b6-a5d5-7af94576eccc |  | note | IP
label | 9adf5571-8d0c-5fdf-b3ae-6535c2707fa5 |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | 44a30b4e-f09a-5f2b-bfae-62dff848ba35 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Layer Thickness and Level Control
label | ff96ea57-e6b4-5e2f-b266-c33d5fc970c0 |  | note | FREQUENCY: Regularly during paving
label | b8b4c9e2-2100-5327-a3a9-c2ab0e694095 |  | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or speciﬁcations
label | 5a70b30b-e11f-5018-bb87-4345416cb836 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20
label | 08d03c8b-a82b-5ccf-8737-a66353e78fcb |  | note | METHOD: Dips, string line, measurements oﬀ kerb
label | ad93486a-b761-59b7-8a32-3da121a65202 |  | note | RECORD: Signed ITP & Traceability
label | 73b78505-8b06-529d-b7e6-0c4856c4aca5 |  | note | WP
label | 34ac231a-8cb8-5f66-a3c2-d0bf25788dad |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | 33018af0-6960-5889-8c7c-7c828282672d |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Paver Stoppages
label | 002feb29-adaf-5658-ae69-f5df46cafaf1 |  | note | FREQUENCY: If paver stops
label | 3e721a1b-0f43-56cf-805a-523cb54c3fba |  | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
label | 942ba5fa-42f6-5275-9f04-0f4ea0d094da |  | note | Asphalt should be ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Max ramp grade:
label | a00ce693-9716-5d75-b53b-2000b9676a84 |  | note | ○ 40km/h – 20-1
label | d42553af-6974-50c2-90d8-9801971de2bf |  | note | ○ 60km/h – 30-1
label | cac18e2c-74bf-5902-8668-cfd79548b07f |  | note | ○ 80km/h – 40-1
label | b5595fd4-381d-5048-8c44-8b281365a04f |  | note | ○ >80km/h – 50-1
label | 81117fe2-cc8b-5f28-91ac-5bc494815aca |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20 (c)
label | b2bc6f2f-ff8b-514c-8300-32611bfa4ad0 |  | note | METHOD: Thermometer
label | e73f5314-0277-5e7e-b7d9-f0cf640711b4 |  | note | RECORD: Signed ITP & Traceability
label | 8a42da44-1238-560a-ad9a-d42ac4ae2cb9 |  | note | WP
label | 1e0101a2-201b-53fd-bb91-8a1a1ca37140 |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | 8ccf48ab-72e6-5fba-bf7d-c5a8ec70a402 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Surface Finish of Wearing Course
label | 4dfcca4d-6cd9-5059-96c5-7f49ee738a46 |  | note | FREQUENCY: During paving and after ﬁnal roll
label | 69febd5b-5b7e-5aaa-8709-463fd2426c24 |  | note | ACCEPTANCE CRITERIA: The ﬁnished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | 150e0736-0b04-54a4-8e7a-7931c1c79df7 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (i)
label | df87ffeb-c1aa-56b5-83c7-41217ac9ccdf |  | note | METHOD: Visual Inspection
label | 9fea420f-2c0a-5f15-ba5e-3302a9a34645 |  | note | RECORD: Signed ITP & Traceability
label | 984f1f0d-073b-5547-9c56-1bad2e6177d0 |  | note | WP
label | 29c20c6b-d274-509f-bafb-d926f20bdb16 |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | ad523783-fc01-5bf0-a6ee-655ee901c821 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Kerb and Channel
label | 07ca60f3-ee52-57e6-b0dd-5cb66e9cc014 |  | note | FREQUENCY: During paving and after ﬁnal roll
label | 8645ebc8-f881-5f69-8a08-46d7a3097f08 |  | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either ﬂush with or not more than 5 mm above the lip of the channel unless otherwise speciﬁed
label | 8dd06cfd-fb12-53a9-8ad4-f0e267ff66ff |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (ii)
label | 767fd6b1-2d01-5b59-84fe-65c38d519d41 |  | note | METHOD: Visual Inspection & Measurement
label | ccbd261d-642c-5fbb-887f-4c9d8bd42bbb |  | note | RECORD: Signed ITP & Traceability
label | d7fce216-ea7a-573d-b611-c9e33c6889d4 |  | note | WP
label | accfc560-ed8b-54d2-a681-96c53a9c120b |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | 8429c875-5a5e-5cce-ae99-b0f6f2a50ad8 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.10 - Alignment of layers not placed against concrete edge
label | 627dfba2-fac7-556e-9e93-8665eddfa9ab |  | note | FREQUENCY: During paving and at completion of work
label | 9f42c967-3d8b-50e2-b03a-b701b4fbb12b |  | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed oﬀset from centreline or design line. The rate of change of oﬀset of the edge of layer shall not be greater than 25mm in 10m
label | cb25d7fe-dae1-5e4a-946c-f9075c8adc68 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (iv)
label | 93f531db-bdf6-5972-91cb-a8bcc1019e4c |  | note | METHOD: Alignment as marked by Surveyor and measured
label | 263cd0dd-a3b4-55bc-b476-0f0d7811254b |  | note | RECORD: Survey Report
label | 7ad599ca-07d1-5ee5-9751-8cf7ecdc9b38 |  | note | SCP
label | 7db19754-8f98-5056-befa-eb8448c94030 |  | note | RESPONSIBILITY: Client Surveyor, Project Engineer, Site Supervisor
date | be21af9a-dbbb-5d73-923b-ce2e4ed1d78b |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.11 - Width of layers not placed against concrete edge
label | 4a9a14be-2086-57b2-9593-b9bf91e5b5b0 |  | note | FREQUENCY: During paving and at completion of work
label | b081645d-0eff-5ff6-94da-c8c81aba66a7 |  | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or speciﬁed width of layer by more than 50mm or greater than the design or speciﬁed width by more than 100mm.
label | 5682dcc8-6286-5be5-9903-fe928cd88306 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
label | e182e220-7601-562e-bf1d-b783541a2e5a |  | note | METHOD: Measurement
label | 576e1c36-cb82-5e07-add9-c30db9da78dd |  | note | RECORD: Survey Report
label | 7e12bf87-ce19-57c7-a3cd-c48f136371db |  | note | IP
label | 701fd94e-b617-5779-a62e-9088f361468c |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | e05f32b5-a38f-5191-b348-2b4e005ae60a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.12 - Traﬃcking of Asphalt & Paving of multiple layers
label | 297135e5-ed13-5bf2-b6b3-60822e7847e5 |  | note | FREQUENCY: During paving and at completion of work
label | 8d32ab87-f6d9-51a3-8e39-5ddb6e23cb82 |  | note | ACCEPTANCE CRITERIA: Traﬃcking of asphalt or placement of asphalt over freshly laid asphalt layer is not permitted unless the majority of the asphalt has a surface temperature lower than 50°C
label | d9f9b24e-9138-5594-8bf9-8d9afacda926 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
label | 08f0e70b-8783-508a-a289-8e3212659fc3 |  | note | METHOD: Measurement or suﬃcient time has lapsed
label | 68f2edb5-423d-58f6-880b-ffe22f7d8951 |  | note | RECORD: This ITP
label | 1a9d1188-0fef-5f2d-b2ce-39a176b42ce6 |  | note | IP
label | 7f4e2eb8-984e-5863-aa73-35bf680251cf |  | note | RESPONSIBILITY: Project Engineer/Site Supervisor
date | c0ea7700-500e-5ee0-81ff-63d8cd2a82fc |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Testing Requirements
checkpoint-status |  |  | checkpoint | 3.1 - Compaction
label | 3ea01a93-90b8-5aad-ab52-1f0ad5c4630d |  | note | FREQUENCY: Per Lot (6 shot test)
label | f36c22c2-771b-518e-9f9f-2e96e8204641 |  | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
label | df530418-75cf-5498-a9e5-98a12f1077d2 |  | note | ○ 95.0% or greater Accept lot
label | a885aa2a-d150-5ded-be97-e54e3a8180ee |  | note | ○ 94.9% to 93.0% Lot may be accepted at reduced rate
label | 8722fdb1-40ee-5b6c-abb6-5c54ceeb6058 |  | note | ○ 92.9% or less Remove and replace asphalt
label | 7b0a66d6-9185-5c93-ad10-be01dcf44c4b |  | note | For layers ≥50mm, if characteristic thickness is:
label | 4c3f1e16-ed84-5603-936e-2256cef26004 |  | note | ○ 96.0% or greater Accept lot
label | 960a15fd-97c4-5533-bd6b-de6cc1e8d086 |  | note | ○ 95.0% to 94.0% Lot may be accepted at reduced rate.
label | 1ba6fd39-3ae3-5145-8d5c-44343953e3dd |  | note | ○ 93.9% or less Remove and replace asphalt
label | e43ae737-0256-515e-8077-48ee79a67f65 |  | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.221
label | 85937a4b-7422-55a2-b459-567d8e37a27f |  | note | METHOD: Compaction Testing
label | 48296b9b-c05b-522a-8bdf-b1b3e3e1d468 |  | note | RECORD: Asphalt Field Compaction Report
label | c9314ccd-99a3-56e3-99d9-ad7ee2ee0c09 |  | note | TP
label | 2f032d04-b346-521b-a1d8-8762ffc48592 |  | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician Veriﬁed by Project Engineer
date | ed7eab13-91ea-5ca6-93e8-5c612059edcf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Surface Levels
label | a3b57793-0945-5ea8-9026-0401d2e010c9 |  | note | FREQUENCY: Each lot as required
label | c97caed1-4c69-5de5-813f-f2b9636177e1 |  | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
label | 56a92c5a-65bf-53fe-9336-974dfc6b8971 |  | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.222
label | d96e15c5-222a-5ebb-9cfc-9599336885ad |  | note | METHOD: Survey
label | b93cd5ab-2182-52e5-9651-43d28c3e9ba9 |  | note | RECORD: Signed ITP & Survey Reports
label | 14cf22b7-2397-5b6a-903e-3f50db452276 |  | note | SCP
label | fa364c43-4d29-58d2-9f4a-d9e17cc7dac5 |  | note | RESPONSIBILITY: External Surveyor Project Engineer to verify
date | d05db9ed-8783-5625-8556-9a307514c7ca |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 17776558-95c5-52a4-b43c-e734ad34c2d6 |  | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
text | 12075917-4f55-5e71-a2da-d7268412a15a |  | textbox | Print Name:
text | 59b83e06-98fd-57f0-a0b3-0202a69fc95c |  | textbox | Position:
date | 58008f9d-4619-5f03-a977-6d42d33a406f |  | date | Date:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-005 - Flexible Pavement Construction | itp |  |  |  | Yes | ITP-005 - Flexible Pavement Construction | 8e95ad02-824a-4de1-905c-ed068ecc0ebf
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - SET OUT OF WORKS
label | 21a438d3-f799-5869-9ca0-65c3b2e95d5d |  | note | FREQUENCY: Each lot as required
label | 1d06acbf-a00b-5e03-9db8-c71bc225cc9b |  | note | ACCEPTANCE CRITERIA: Ensure relevant construction drawing are being used to determine set-out of works.
label | e7ec4598-5998-59f4-a6da-3f7c62b4d1c4 |  | note | ○ Ensure all survey pegs are aligned max 40m apart and the oﬀset distances and heights are in accordance with relevant drawings
label | 472ba5b7-b2fb-5b14-afce-13d6e376b05d |  | note | ○ Refence checking to be conducted with string lines
label | 56cd3848-d046-5659-9cff-3b5220170d1e |  | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
label | 3c2d0e5c-ad3e-51fb-98da-f6b89fada6e6 |  | note | METHOD: Survey set-out
label | 46d63712-60bf-5ace-98dd-1bb84e6dab98 |  | note | RECORD: Signed ITP
label | 21f50034-22b9-5a3f-a7a2-09ceb5f4bd7e |  | note | SCP
label | 703fbd8e-ae1f-50f0-8dd9-fd0f1075f13b |  | note | RESPONSIBILITY: SWA Project Manager
date | 2c71cf9a-452c-5dba-96a4-f047f6c8fbae |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
label | e0c1e4c3-01ae-5a28-a97c-457c30e6c254 |  | note | FREQUENCY: Prior to commencing any activity
label | 83cee339-0a84-599d-96a0-5475fb179165 |  | note | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number speciﬁed in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
label | 77b93b7c-0603-5666-8f86-2d17e5e3bf3e |  | note | REFERENCE DOCUMENTS: Vicroads std sec 204.03
label | bb1ab119-fea3-5851-ae1a-f1ed4b3d8e0d |  | note | METHOD: Survey Report
label | f870a3d7-5a52-5e57-a3ad-fb8808c4ba5c |  | note | RECORD: Signed ITP
label | 9a11a0fc-62d5-5c21-baed-7d41c3cfb678 |  | note | IHP
label | d54a04d6-e5f9-5007-a6a1-5f5743055cd1 |  | note | RESPONSIBILITY: SWA Project Manager
date | 103858ec-6146-5004-8f4e-cc047cefe7fe |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (a) General
label | 4f049f58-666a-5046-a5a3-8c374b9a2092 |  | note | FREQUENCY: Each lot as required
label | 890cc7f0-2c5e-5912-a0df-e7880170454d |  | note | ACCEPTANCE CRITERIA: Material during compaction shall have a moisture content of not less than 85% of optimum. After completion of compaction of a layer, the moisture content of the material in the layer shall be maintained at a moisture content of not less than 85% of optimum until test rolling has been completed.
label | 33ba4406-6891-5a3e-be9b-aeb2dd202059 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
label | 45aafbde-c218-53c8-ba9f-ec8067913673 |  | note | METHOD: Visual & Laboratory Report
label | 21091960-9352-507b-9d8e-8277980a5e20 |  | note | RECORD: Signed ITP
label | 6b7d5eae-9cf2-575f-ad7d-b90f11fad58e |  | note | IHP/AP
label | 80f3b5fd-1d3f-5c4a-af15-dbc902752ec9 |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | 5b1c301b-eca4-5af8-918b-90a5383de1df |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (b) Material of Nominal Size 40 mm or Less
label | f0d761e5-1cf1-5154-9067-05b632345722 |  | note | FREQUENCY: Each Lot
label | 73f4bc54-68aa-56d1-8e9f-b58949ad10f5 |  | note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modiﬁed compactive eﬀort. The work shall be assessed for compliance with Scale B requirements being not less than 97%. See table 304.081.
label | 58ca41af-e55f-53c8-ac78-0969bd212cab |  | note | ○ For work to be tested for compliance with Scale B requirements, the number of tests per lot shall be six. See table 304.121.
label | 7298ed6a-a8d2-5300-ad8c-a877189c71ff |  | note | ○ The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm.
label | 673b97e8-f973-55cc-a012-7eff9d3dd982 |  | note | ○ The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
label | 2d522158-75e2-5ada-b75c-c6d64e3633b6 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
label | 5a2a1a0f-8eb3-5562-985f-a06d6a3bd2ca |  | note | METHOD: Laboratory Test Report
label | 38b38ded-4382-55a9-8321-91cce0bafc89 |  | note | RECORD: Signed ITP
label | fc050c64-6bbd-5fcc-a1d3-60db57ebc55a |  | note | IHP/IP/AP
label | aa41352b-a014-580f-a92f-f3367cc11c4d |  | note | RESPONSIBILITY: SWA Project Manager/SWA Site supervisor/RRV Superintendent
date | 091e976c-11b3-5010-bec3-26cdfc39bcbf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - TEST ROLL PAVEMENT LAYER
label | cf26d6d1-0a57-51a5-8998-6140e6be89af |  | note | FREQUENCY: Each Lot
label | 7021f6a6-d397-5d7a-891b-d587e34330a3 |  | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any ﬁll on the prepared areas until the area has been reviewed by the Superintendent. The Contractor shall provide for the Superintendent to be present during all test rolling.
label | b77690bb-91cb-57fc-89d4-7c8858b0d4ec |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 173.03 & 204.12
label | ddebae22-3f6e-5344-8a8a-847524cc851a |  | note | METHOD: Proof roll
label | 5502962f-5656-5b8c-b4cc-be0affcca612 |  | note | RECORD: Signed ITP & Test Report
label | 1d60d458-0615-5369-8e39-1fa82e4810bb |  | note | HP/AP
label | fb4f3192-b1fb-5ea8-99b9-42ab1d8acccb |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | 35502628-900b-5e3a-81f1-cd8fab79ff54 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
label | dd9451ef-7628-5777-b511-8406baf71479 |  | note | FREQUENCY: Each Lot
label | b5517203-2972-5415-a154-7513e172b6f0 |  | note | ACCEPTANCE CRITERIA: The surface level of the pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet either Scale B requirements as speciﬁed in Clause 304.12.
label | 93744061-4d1c-5633-81ff-e0fcad3646da |  | note | ○ Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
label | 7ca6e396-4048-5fbb-a817-d7b9b6aec8eb |  | note | ○ Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number speciﬁed in Table 304.061. Surface Level Tolerance as per Table 304.062
label | 8e8eaa68-3058-5d05-bab8-40a44dbc94ad |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 304.06
label | 1bb3836a-8681-55de-961b-4ea84c3730ab |  | note | METHOD: Survey report
label | c9b54e4d-138a-5902-a65d-40167a8a0199 |  | note | RECORD: Signed ITP
label | 17e955f5-a405-5b78-9b63-88db0449b409 |  | note | IHP/WP
label | 0ee07f49-db61-5573-aa0e-f85d91236efa |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | 0e76f698-81d7-554d-acc6-0a5da44178f2 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 7ac89bf9-222c-5771-bff6-eadc91bf12d7 |  | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations
text | 726d8fff-32d0-5a53-897e-89e54955aa0a |  | textbox | Print Name:
text | 9fd2b4b9-a3d2-5ac2-ae5f-5981ed4b8a07 |  | textbox | Position:
date | 2b92b7c0-85c8-53f5-8ecf-7a7cc9248cd9 |  | date | Date:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-010 - Guardrail | itp |  |  |  | Yes | ITP-010 - Guardrail | 959d7f0d-ee74-46fa-a68d-ba7171b95fc3
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 0ec57c45-86f2-5bdc-b58b-a216f96427bf |  | note | FREQUENCY: Prior to commencing any activity
label | 086cb6b8-35d8-503d-979c-02b0754ff62e |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | ab817a45-c92b-5e09-af6c-7c7e05ebd0bf |  | note | – using the correct and complete set of drawings
label | 0e87b665-1836-5f00-8bd9-0aff94e5fb43 |  | note | – all drawings are the latest revision..
label | aa50f204-8caf-51f3-b943-d67d410f8d74 |  | note | REFERENCE DOCUMENTS: Design Drawings
label | 4a0abe65-ea75-56fc-871d-5432bf3fb90c |  | note | METHOD: Visual Inspection
label | 251f8e93-1153-5553-8544-9e01118b4ab8 |  | note | RECORD: Signed ITP
label | 03256eb2-10f7-5eb2-acbc-768daed6ab0d |  | note | IP
label | 82c51713-01e0-5753-b05a-f8bc425c1a90 |  | note | RESPONSIBILITY: Project Manager/ Site Supervisor
date | 6dcf91aa-ca4f-5cd5-bded-9751eee20558 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 5afcc918-dc4a-558f-aa76-735dfd2c28bb |  | note | FREQUENCY: Prior to commencing any activity
label | 663cff31-6696-5aa8-af87-521b6453cf31 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS
label | 6a2336c7-2787-58be-84c1-3df28befa56c |  | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
label | c37a8318-8c2d-5a69-8c75-a83252fb4bc3 |  | note | METHOD: Visual Inspection
label | f341f913-15fa-54c4-97bd-e055ff085002 |  | note | RECORD: Signed ITP
label | 5742e225-b980-5fa7-b89e-fd6a8e25bfc2 |  | note | IP
label | 12c453ab-0f00-53a1-9a99-d7a762d45f9b |  | note | RESPONSIBILITY: Project Manager/ Site Supervisor
date | 179b0df0-6817-59e8-83a9-f173c1ad472a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Setting Out
label | 4c70ffe9-0fd7-59db-aade-198edbbb95fa |  | note | FREQUENCY: Prior to commencing any activity
label | 8dd0c908-2af4-5773-b10c-1cdd07379690 |  | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor.
label | caac9424-8219-5a49-be8c-0b27d7d96fdf |  | note | ○ Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
label | f0a37273-72f2-5e02-a92c-218a38f5abef |  | note | REFERENCE DOCUMENTS: Drawings 708.08
label | a0b2264e-1557-5811-a657-fa658781abaf |  | note | METHOD: Document Review
label | 25ba3632-56f1-5b5b-b635-2d5d334c04af |  | note | RECORD: Signed ITP
label | f9e669d5-a8fc-5868-88b2-85fd11d2861b |  | note | IP
label | 5f22be86-56b4-51c7-a4f6-77db6d3b4243 |  | note | RESPONSIBILITY: Project Manager/ Site Supervisor Superintendent
date | 540fad9a-8918-51a5-bfb3-689327283865 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - Supply of materials
label | 07311716-27c3-59bc-8c66-34ff2ec8f1e8 |  | note | FREQUENCY: Each Delivery
label | 41fd03e0-71a3-5cf0-8d71-d65231baead1 |  | note | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
label | 8e743b2d-c7ea-5d17-8f27-b941961e81bb |  | note | REFERENCE DOCUMENTS: 708.04, 708.05 Detailed design
label | 65b15744-9046-51d6-9b49-9c0cb11e31e5 |  | note | METHOD: Visual Inspection
label | 70bdaa8e-43b7-5dea-8b64-f89f86506728 |  | note | RECORD: Signed ITP
label | 1e7a1bf2-e8a9-5d1c-bb3b-ec9a92bfb1d2 |  | note | IP
label | d5b348f3-513f-539d-9466-d8c71722ef26 |  | note | RESPONSIBILITY: Project Manager/ Site Supervisor
date | 0c0c4c74-906d-528e-b904-8c78909e065c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Installation
label | 85a5de76-58b8-5d60-aee8-b55099377790 |  | note | FREQUENCY: Each lot as required
label | 8db5e8bf-9e53-5d1f-a2c4-2912b045a9c6 |  | note | ACCEPTANCE CRITERIA: The oﬀset, height and post spacing is to conform with VicRoads speciﬁcations and the detailed design
label | 88f58727-1259-5f70-9b1b-a724f725415a |  | note | ○ Where the face of guardrail is less that 1m behind back of kerb, the mounting height should be measured from lip of kerb. Otherwise measure from ground level Fasteners are to be snug tightened to AS4100
label | c5f6a30b-5ebc-515c-b4c2-7a399533416b |  | note | REFERENCE DOCUMENTS: Detailed design 708.08 SD3661 AS4100
label | 5f83d83c-6406-5083-9409-db6c8a43b72d |  | note | METHOD: Visual Inspection
label | fe660ed2-bef8-5c2e-9d8f-c860f088952e |  | note | RECORD: Signed ITP
label | b2c24674-080a-5153-8c78-959dfae3b2bb |  | note | IP
label | 01ba80f2-36ab-5720-b70e-1c3e7a2f224c |  | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
date | cd466e90-8a5b-5335-b067-d55ed355d4d9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - End Treatments
label | 51b415f8-bb9e-5625-823b-01f660682781 |  | note | FREQUENCY: Each lot as required
label | 57c5859d-5b20-5d54-8805-88afb2bad015 |  | note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads speciﬁcations
label | 0bbb2739-8a95-53a2-ace1-5e372d6aed4b |  | note | REFERENCE DOCUMENTS: Detailed design 708.08
label | 6ea32cbc-291c-531d-b0a3-17bcdbd44c54 |  | note | METHOD: Visual Inspection
label | 370fc108-8336-590c-b227-ef32a7bac163 |  | note | RECORD: Signed ITP
label | 623b922e-10a0-5aee-bbb3-be120111e4dd |  | note | IP
label | edfa7fad-f9b0-59fe-badc-78506f6adf76 |  | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
date | c070f63d-cad9-520d-a077-313ac75e4be6 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Motorcycle rub rail
label | 4d5697fd-9c4c-5f8f-a59d-ac37aa7b95a5 |  | note | FREQUENCY: Each lot as required
label | a748f548-eee9-5b61-873c-7ce62cbd9938 |  | note | ACCEPTANCE CRITERIA: Where speciﬁed, motorcycle rub rail is to be installed on the new length of guardrail
label | 237b6204-7728-5f89-802a-f6314a444077 |  | note | REFERENCE DOCUMENTS: Detailed design 708.09
label | 7509c32b-e1e2-562b-b3f5-6ad6425f2f4d |  | note | METHOD: Visual Inspection
label | e6c525e7-02f8-56aa-83bc-8a3ea15886d5 |  | note | RECORD: Signed ITP
label | 54c65d0e-d8a3-539d-a84c-45b0a1bc4744 |  | note | IP
label | 6ac946d1-567f-5d9d-8b3d-0ce869d45aaf |  | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
date | 29a00349-f5ee-5795-8f98-7a256ef90ccf |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 6ca108b5-1937-510e-89f1-beae553f2df9 |  | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
text | 68028ba3-22e7-5c2e-bfd6-3aaf14cc3eb5 |  | textbox | Print Name:
text | d1dbdee0-8b8e-5e3e-80e4-a67262f3bc1a |  | textbox | Position:
date | 59922202-9206-54e2-84fd-08300ad09ec6 |  | date | Date:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-002 - Earthworks | itp |  |  |  | Yes | ITP-002 - Earthworks | a1c13c96-9540-4df8-af90-a6a42142b510
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 63ef06e4-2920-5a35-b5b9-535fc9e300ba |  | note | FREQUENCY: Prior to commencing any activity
label | 975a3e51-9557-5498-a0e6-f409be88ad10 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | 613e7170-9728-5570-9c31-94beb88c7c44 |  | note | – using the correct and complete set of drawings
label | 8feb9044-c864-5b37-9c61-519e64230102 |  | note | – all drawings are the latest revision
label | 7ef1083c-e883-5714-9b92-dd73a27abd47 |  | note | REFERENCE DOCUMENTS: IFC Drawings
label | c62d4720-bd30-52d5-8674-bf431547ccff |  | note | METHOD: Visual Inspection
label | 661abbd6-eca8-532e-a3ff-1a64e77beb1b |  | note | RECORD: Signed ITP
label | 9a9af3b3-4708-566d-a616-369ced59562c |  | note | IHP
label | 72fb4da4-635e-5a66-ab2f-552827b9e2ba |  | note | RESPONSIBILITY: SWA Project Manager
date | 51e49a8c-5445-526e-984b-423795089fd5 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | 07d8c898-2208-523a-80f7-1387c0f63df8 |  | note | FREQUENCY: Prior to commencing any activity
label | 0751365c-1d20-5c53-b1bb-3b51d00d3665 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
label | a8f70dba-46e3-5a26-95d6-26e96fae383e |  | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
label | 1352caef-d602-554b-a7da-1423cabffbbb |  | note | METHOD: Visual Inspection
label | a0b75b41-f0dd-5860-96b6-6da3307d8ce6 |  | note | RECORD: Signed ITP
label | b53b50a3-f195-5159-859f-bc717daeffdb |  | note | IHP
label | 06ed450d-b079-5465-9db2-0846a76be876 |  | note | RESPONSIBILITY: SWA Project Manager
date | 7c543fa3-0593-5ec2-863a-f310fc8ca8f9 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - Survey Set-Out
label | 046dd51c-0175-5459-a6c5-f55a289e5f9f |  | note | FREQUENCY: Prior to commencement of excavation.
label | 59adf8ec-c302-58b0-9358-84cc178503e2 |  | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | f4ef093d-e2c1-520a-bcb4-4f73075c4346 |  | note | REFERENCE DOCUMENTS: Work Procedure
label | 6cb1adab-fa85-5394-b96a-55d7a6d14d84 |  | note | METHOD: Verify
label | f4f4540d-46e7-5141-aded-2d93b7455cf6 |  | note | RECORD: Signed ITP
label | 8ef72872-7802-5f59-bf65-b457024a33ac |  | note | IP
label | 4357050c-8bee-5b9c-851a-a546b7d3e05b |  | note | RESPONSIBILITY: SWA Project Manager
date | 4f7fa3db-aedc-5e1b-aadc-9eee1d7a7f47 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Excavation Permit
label | b66700e3-f3fb-5637-82da-e55576bdf4b2 |  | note | FREQUENCY: Each Lot
label | 19e84c8b-81ad-5fc9-9c1c-2cf7de12c162 |  | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
label | ce7a9b89-7a27-5c68-9149-9254a6ab0e3c |  | note | REFERENCE DOCUMENTS: Excavation Permit
label | 1fcaa11d-5c25-529c-bc7a-fb66f002513e |  | note | METHOD: Verify
label | b940a2cc-622a-5268-b6d5-4174d5bfe926 |  | note | RECORD: Signed ITP
label | 8d23f1bc-479e-5750-b0a8-4dc379f2e99d |  | note | IHP/IP
label | 19cde785-dfd3-5089-a243-0103582f7314 |  | note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
date | 329413a2-cceb-5639-8216-500c4af30ad1 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Sub grade Material Properties
label | 5fd83012-c466-593d-9c1a-748bded75184 |  | note | FREQUENCY: Each Lot
label | afe4b2e2-ed25-5b1b-9af5-d1e138adac8a |  | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut ﬂoor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
label | a1ffa119-4d34-5673-9c44-9dc6ea662460 |  | note | ○ If parameter met, rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
label | ad5e0754-0df5-5c5e-abad-2aae1ada4c77 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
label | 8ae13c3c-13ac-50c2-8189-e50b75a74f02 |  | note | METHOD: Site Inspection/Test Report
label | 6d2aaaa3-68de-5559-b12a-b31c9741aade |  | note | RECORD: Signed ITP & Test Report
label | 07fd6496-84d5-54b1-b081-eab94ff926ce |  | note | TP/AP
label | 10ab7e0c-4532-54d5-a31a-e33a6cd96b1d |  | note | RESPONSIBILITY: SWA Project Manager/External testing Company representative/RRV Superintendent
date | 3e8552c4-a105-5534-846a-e1af640e3f76 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Inspection of Subgrade Material
label | fc2ff622-f8b0-5225-9a20-3b3fb6fdc287 |  | note | FREQUENCY: Each Lot
label | 13024377-9a3c-5b23-84e9-ad46c0eb0d37 |  | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to veriﬁcation by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | d2cc98f5-f540-50ae-8a5e-e3e548ef5835 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
label | 0db4cef1-508a-5807-bef9-04f66542a0d3 |  | note | METHOD: Visual Inspection
label | 76a001cd-1c60-595d-81ea-30fe6d7c513e |  | note | RECORD: Signed ITP
label | 5b5cb03e-be09-5c3e-ae18-32be5d6e95ec |  | note | IHP/AP
label | c06704ae-32fe-5fa2-9cb1-3c0294866db3 |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | d3926330-b65c-5374-aab5-5164629eeec9 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Material Classiﬁed as Silt
label | 43018c9f-362c-57f1-a789-d614010c526d |  | note | FREQUENCY: Prior to commencing
label | 762a0a86-0d34-5b1d-abfa-fa16440eb526 |  | note | ACCEPTANCE CRITERIA: Material classiﬁed as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
label | 56b42410-7b7a-50f6-b7d5-89d80bb5a441 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (e)
label | 68b0c69e-dc73-5f91-a426-5d5e86656bb2 |  | note | METHOD: Visual Inspection
label | 5e98c672-e09a-5ac8-982a-016dbe24374d |  | note | RECORD: Signed ITP
label | cf5098b9-e705-5cac-a813-266e60de3dc5 |  | note | IHP/AP
label | b907f15a-9cc7-564b-8b66-da57e9316eb3 |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | a0191669-b753-5b5a-a7a3-8c73f82bad58 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
label | cb481af3-2357-5cbf-ad97-bc04aed2500c |  | note | FREQUENCY: Prior construction of the regulating layer.
label | 51f0b093-c186-5f27-a8c3-ccabdfbfd53c |  | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | 8ad4bf0a-5290-51af-a3e5-ee684a223608 |  | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | 61cb11b6-7c28-56b9-8dc8-cf645c711174 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (f)
label | 14a6497b-1d6f-5818-8481-9bf14cba7709 |  | note | METHOD: Site Inspection/ Document Review
label | d35e44fd-e587-5be6-a24f-718975f149ec |  | note | RECORD: Signed ITP
label | 49338d4e-2a96-5325-800c-ad111c64dd75 |  | note | IHP/AP
label | 12cb7c2b-36df-5553-ba6f-24e68e0207a8 |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | 2b1425cc-b454-5d77-98dd-96bd3b7aa072 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Unsuitable Material
label | db94795f-3834-5c1c-91f3-9fc4301600ab |  | note | FREQUENCY: Each lot as required
label | 702af76c-3a00-56f1-9fd7-7ccc840360ca |  | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review
label | 1b3e2ac5-48c1-5654-bd54-7761b3098b42 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (d)
label | 36c5022f-b720-5452-8061-86025516a283 |  | note | METHOD: Visual Inspection
label | 244ed7f3-e86b-5bac-9517-ea83524d8369 |  | note | RECORD: Signed ITP & Test Reports
label | f80bc235-fc80-596b-85fd-e33c182b9bd7 |  | note | IHP/AP/TP
label | f10559a8-06b7-5b31-8da5-5968ae7501a7 |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
date | 56094748-985f-5079-8f95-88fb28e47e3f |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 - Groundwater
label | 8e947778-8b84-5100-89f5-2f3fd0129bdf |  | note | FREQUENCY: Each lot as required
label | 7673e185-bc79-53b7-bcb2-29c2e8a77f19 |  | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | 516134ef-d6bb-59c1-8b17-ab08d4c1f88c |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (h)
label | d1271fbf-7904-518b-b1e7-07dbd73a020f |  | note | METHOD: Visual Inspection
label | 5ea962a4-e35d-5646-9f69-39256bf464cd |  | note | RECORD: Signed ITP & Test Reports
label | 3692b2d5-c7e4-55f3-90a5-cbebc233d986 |  | note | IHP/AP
label | cc609a62-4df2-51a4-b6b1-bc840724da7e |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | 9e689064-6953-575d-8309-6c093fb7d00c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.9 - Trimming and level conformity
label | 61509124-0ebf-5b78-8745-f05a38c4eab4 |  | note | FREQUENCY: Each lot as required
label | a17b198b-f0c1-55dd-8a4a-d54afc2b9c1c |  | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | 0d7a5745-75d9-57e4-9081-7b79048b2506 |  | note | ○ Level tolerances: Range x (Mean value of all measurements) (Scale A) x = +5, -25mm (Scale B )x = +5, -15mm
label | ad920ce8-f8b7-53b3-8743-60328344a9de |  | note | ○ Max S (Standard deviation of all readings) (Scale A) = 12 mm (Scale B) = 15 mm
label | 5e252ff1-5950-54c6-bf76-db5a1f002010 |  | note | ○ No. measurements (Scale A) 80 per lot (Scale B) 40 per lot
label | 87493cb0-d115-51c4-9d1f-759d71102d10 |  | note | REFERENCE DOCUMENTS: VcRoads Std 204.03 (f,g,h) Table 204.031
label | d04f4af3-fe8c-5e49-bcac-93f66a7ec19d |  | note | METHOD: Survey
label | 311b327e-4037-5495-95d9-fdd693c1be25 |  | note | RECORD: Signed ITP & Survey Report
label | 1018ec42-1b82-5abf-96e9-81d3440f82b4 |  | note | SCP
label | 92e60c36-bee9-5e0c-8f85-d4a9bc691cf3 |  | note | RESPONSIBILITY: SWA Project Manager/External Surveyor
date | 3b911a52-4913-54fd-8ba4-e6fcbb275574 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Testing Requirements
checkpoint-status |  |  | checkpoint | 3.1 - Test Rolling
label | d3a1bc80-faee-5112-bc75-bec68db18977 |  | note | FREQUENCY: Each lot as required
label | 4e918e84-6387-53fd-91c4-0ca52044fde4 |  | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep. ( Cl 173) Plant to comply with requirements of Cl 173.03.
label | 5aaa4854-fe7e-5cad-b4e1-74d41e8f3994 |  | note | ○ Pneumatic tyred plant nominated for test rolling procedures shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre.
label | 4277ddd7-f14f-588f-b3b9-ea39086bd6ec |  | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Section173.03 173.03 (ii)
label | 6ba8ef5c-35b4-5365-a45f-95d31a5cef58 |  | note | METHOD: Visual Inspection
label | 1a0d1f68-b539-5451-b907-0976dddbb2e2 |  | note | RECORD: Signed ITP
label | 9b6dc80f-3f74-52a8-8bd4-abfbdd979797 |  | note | IHP/WP
label | 9ead8112-2025-5ed7-be9d-429f573ab070 |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
date | b2ea547c-739f-5d7f-aa8f-212f732da151 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Compaction Testing
label | f6a27ea9-f413-5e1c-9775-326bd9c2ee19 |  | note | FREQUENCY: Each lot as required
label | cb715b59-c134-524b-89fc-b956d96a3462 |  | note | ACCEPTANCE CRITERIA: Ripped and re- compacted material below Cut Floor Level = minimum compaction 98%.
label | e62dc0ef-1dae-5206-971f-c837806fad71 |  | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 98%.
label | 5d92ffe2-2202-5931-b8a7-a03620b229c9 |  | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where ﬁll is to be constructed = minimum compaction 95%.
label | ce30c178-8296-5470-93d3-337682e65b40 |  | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Table 204.131
label | 8cc9c55b-be60-5c5c-a496-fe978d289bd0 |  | note | METHOD: Compaction Test
label | 1e3b7c0a-b2a1-539a-bacd-7cfd0f0697dc |  | note | RECORD: Signed ITP & Test Reports
label | 56699200-6334-5d20-84a4-70d33c6231aa |  | note | IHP/AP/TP
label | a0e93b15-f5af-5c9a-8e7c-cf39d73bfe28 |  | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representative
date | bfd3e807-29e4-5f56-ae7a-2ce38924e07a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | dcd25591-fde7-5bcd-a09b-d3e6d47d71ec |  | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
text | 16a05b1a-935d-5290-8681-c77a6eab76c0 |  | textbox | Print Name:
text | 64743c84-a5c9-5c74-99f1-e395de6b42c8 |  | textbox | Position:
date | 49bd4889-f620-5147-a465-3d6c08b91f49 |  | date | Date:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-006 - Kerb & Channel | itp |  |  |  | Yes | ITP-006 - Kerb & Channel | a4d29837-c0f6-4b8e-8931-9cd929c359d9
checkpoint-group |  |  | section | 1 - Preliminary Works
checkpoint-status |  |  | checkpoint | 1.1 - Check for correct documentation
label | 406918ce-3cdc-5bf1-b99b-1cc0ce3670a6 |  | note | FREQUENCY: Prior to commencing any activity
label | e011307f-87f3-5b57-afc6-849b34cae3d6 |  | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | be8c534a-b509-5771-ac62-7b511d66b998 |  | note | – using the correct and complete set of drawings
label | c69f4138-b3f7-51db-b97d-ccc326af37c6 |  | note | – all drawings are the latest revision
label | 822ffbea-10b5-5f82-8ab0-f8c159005040 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
label | 34936628-eb58-5204-b959-a44867dbf91e |  | note | METHOD: Drawing Register
label | 79444e64-5635-591e-91f8-b477547447c6 |  | note | RECORD: Signed ITP
label | d9bd5ac5-3489-5b71-9430-2ce1611cfa4d |  | note | IHP
label | add5cad4-344d-5ff9-9b01-f3492d8fa430 |  | note | RESPONSIBILITY: Site Supervisor
date | f8ea5604-b840-516b-b9b6-3986295a792a |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.2 - Implementation of all measures and controls
label | f1ed7616-4da5-594e-89ed-b752ad56207f |  | note | FREQUENCY: Prior to commencing any activity
label | 897e971e-0b58-53da-ba2b-45c29e989652 |  | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
label | a01e5185-92e6-5d8d-a6f3-c9eea4ec684c |  | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
label | c3a498a8-cfc9-5cf9-91bd-4bdad6bfba9d |  | note | METHOD: Visual Inspection
label | 47148980-a363-51fc-aec0-5235296d4922 |  | note | RECORD: Signed ITP
label | bc3fe039-08d6-5b5e-a8c2-555746084963 |  | note | IP
label | e13d9d0a-b15d-5f8b-bd51-dc48258f1cb3 |  | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | 2a2f6067-9e00-575e-b431-248df43cc440 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 1.3 - Setting Out
label | f103293e-2257-5261-bc5c-72da2d09ed65 |  | note | FREQUENCY: Prior to commencing any activity
label | 2fed43cc-312a-53e7-8a8e-f9ece4210455 |  | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor. Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
label | 31f53ffb-c188-501b-9f47-21af8c4b9fd6 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 703.13
label | 1688d011-d595-5d40-bfd1-813a57c0c5d8 |  | note | METHOD: Survey Setout
label | f132a59f-8e2b-5db4-ac00-1a50c25e51f6 |  | note | RECORD: Signed ITP
label | abe4a46c-5cab-59fd-919b-5f5eb81e9ca2 |  | note | IP
label | cf7c601a-6eea-58c4-92bf-cbcbc7a6625c |  | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | 941f7e22-16ae-5d20-ab1b-03abed20d5b2 |  | date | Date Completed:
checkpoint-group |  |  | section | 2 - Construction Works
checkpoint-status |  |  | checkpoint | 2.1 - Excavation
label | fc4b5e5e-7efc-5785-b195-266e3c5e4d0b |  | note | FREQUENCY: Check prior to placing material
label | 391c45c5-f8e1-5129-a718-7cde5ad901d0 |  | note | ACCEPTANCE CRITERIA: The base preparation for kerb and channel shall consist of a boxed out area to a depth of 355mm below FL and 1150mm wide. Excavation shall not extend more than 150mm from the edge of the adjacent face.
label | cd4e7867-48ed-52ef-8f01-7af0c0fe7913 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 703.20
label | 395c6ce3-2753-51a3-93ac-2c98f38853b7 |  | note | METHOD: Survey/Site Inspection
label | b6a9d6b7-6aa3-5b2d-9e12-f998914f0c63 |  | note | RECORD: Signed ITP
label | 3851b852-2945-58a2-b5e1-49e85c93b11c |  | note | IP
label | 2748247b-269e-5276-8976-c1df5a2cb9ee |  | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | 275a27df-78e2-54bb-beba-bccd1405ef56 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 - Subgrade Inspection
label | 7419fe17-5292-5f9b-af6e-6ab9f3ed0a53 |  | note | FREQUENCY: Check prior to placing material
label | b448cca9-b6ce-5da8-b0e3-7d05f86ef3be |  | note | ACCEPTANCE CRITERIA: Test roll subgrade to check for No visual deformation or springing. Where deformation is exhibited, the Engineer or Superintendent is to be notiﬁed immediately.
label | 0728161c-0c6a-5ff6-b941-64cfbc2b7da1 |  | note | REFERENCE DOCUMENTS: Vicroads std sec 173.03, 173.03 (ii)
label | f39ed3b9-079b-58c8-9755-6fb9aba9ef11 |  | note | METHOD: Visual Inspection
label | e468e85e-66dc-585b-991d-a6061a47cd52 |  | note | RECORD: Signed ITP
label | 68dbdd3b-1e7b-591b-9528-31a809df4c41 |  | note | IP
label | ba0308c4-4a24-5f91-9915-59aa7615f963 |  | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | 86650319-7ccf-5b27-a073-c105b613572c |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 - Bedding Preparation
label | e59e6c97-83db-5648-ac91-397818f406a7 |  | note | FREQUENCY: Each lot as required
label | 7ba6e700-5771-54d0-8877-7f24e9b6b106 |  | note | ACCEPTANCE CRITERIA: Bedding material to be used for base preparation shall consist of size 20mm Class 3 or Class 4 crushed rock at a minimum of 100mm compacted thickness. Preparation of ﬁnished base shall be 190mm below lip of kerb as per survey marks.
label | 3f13d882-6cd5-5b8c-977a-a1143ab675b9 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21
label | 41f35c2c-a05f-520f-a7ec-6ec733bf708f |  | note | METHOD: Site Inspection
label | fbe9548a-bbbd-542c-8d90-54fc5c63104e |  | note | RECORD: Signed ITP
label | ddd43e43-3217-5d2f-b08d-63fe96bf5a7a |  | note | IP
label | fdc53d79-8c28-5630-813c-dcc3012d51a1 |  | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | 55becea8-8fc6-5e8f-9292-936708566548 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 - Kerb Concrete Mixture/Strength
label | 1a135d14-44b7-59ab-abdf-e5d70cf31fbd |  | note | FREQUENCY: Each lot as required
label | 3f26fb6f-256e-598e-b9e6-32f4e8b8994e |  | note | ACCEPTANCE CRITERIA: Traﬃc routes a minimum of or equivalent to 320kg of cementitious binder material or geopolymer binder per m3 of concrete – VR 330/32
label | 7b5cdbee-30f5-5e93-891b-da9cfc6152a2 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.05, 703.11
label | 65ecbc29-e2f8-5f0c-9b01-3b2f4a5cf809 |  | note | METHOD: Delivery Dockets
label | 257a7f1c-f457-59cb-8c77-b6d58c927c89 |  | note | RECORD: Signed ITP
label | 87154659-50e1-5da3-a1fe-e622c69d60d0 |  | note | IP
label | 3593b420-23e2-5fba-aa66-ea5339877f43 |  | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | 0655ebfd-b77c-57fd-9155-b251f8b36dbe |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 - Tolerances on Line, Level & Shape
label | 8e4afeb6-97d5-5635-ad08-b6d52ddb3959 |  | note | FREQUENCY: Each lot as required
label | d8372740-cf9d-51c8-aef2-29373cca4e95 |  | note | ACCEPTANCE CRITERIA: All surfaces shall be ﬁnished in conformity with the lines, grades, thicknesses and cross sections shown on the drawings or as speciﬁed. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10mm. Except on curves or in shaped areas, the deviation of the ﬁnished work from a 3m straight edge shall not exceed 5mm at any point.
label | 9a5ffbb5-5164-51dd-b467-84c02f5bad84 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
label | 6158c054-13b7-53b6-8521-4c14420bbc7b |  | note | METHOD: Visual Inspection
label | ba02012e-f3de-5cee-947a-ccc94dab95a8 |  | note | RECORD: Signed ITP
label | 8bc8d6a9-f2df-5f9f-9f39-9ee3ee69107b |  | note | IHP
label | 7d102f00-ae1b-5335-bdd7-2293953dcd21 |  | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | fbf4435c-3c54-5df9-91a3-a82a670999a0 |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 - Kerb and Channel Finish
label | 152a4c81-2200-58c7-8846-475a98e97122 |  | note | FREQUENCY: Each lot as required
label | 710f7d21-3cbf-56cd-8d40-0e5b7b49ca9e |  | note | ACCEPTANCE CRITERIA: All edging shall consist of a smooth, uniformed and of a trowel ﬁnish. The mortar used shall consist of two parts of ﬁne aggregate, one part cement and suﬃcient water to produce a mix of suitable consistency. Thickness of the rendering shall not exceed 3mm.
label | efff80fd-0242-5e39-80b8-c9f8160181d1 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21 (a)
label | d850c6d3-a71c-5054-84ea-71aeafd4b346 |  | note | METHOD: Visual Inspection
label | 76ab2fe7-1bdf-5321-b5f0-3284d7615a29 |  | note | RECORD: Signed ITP
label | 53219070-0f0e-5f92-92bc-22136a46688c |  | note | IHP
label | 57dd1aee-e3f5-572b-a8dc-2d732d48fef2 |  | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | 394a1dec-5c62-5a2c-8294-8922811baf6e |  | date | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 - Kerb Backﬁll
label | c74426ba-4f22-5b05-9f10-30fcfc2e71d4 |  | note | FREQUENCY: Each lot as required
label | 7ca14e0d-b321-5913-b323-51a9714edbf0 |  | note | ACCEPTANCE CRITERIA: Once concrete has cured, topsoil which is free from perishable matter, shall be placed ﬁrmly compacted in layers less than 150mm thick and to a width of no less than 300mm behind the edging to the top of the edging.
label | 53f8edff-f0ea-5e80-bed1-59c7560088b6 |  | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.29
label | 7bc19819-ca2e-5e79-894d-e29bd539afa5 |  | note | METHOD: Visual Inspection
label | 080fb305-c66f-556d-a03a-33861058893c |  | note | RECORD: Signed ITP
label | 2d9a91b8-51ff-5edb-b545-a8456e4f6752 |  | note | IHP
label | df133037-dd9a-5711-96ad-bf48ac9a8097 |  | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
date | 6bb7c0a6-e316-5ac0-94bc-a436be1504c3 |  | date | Date Completed:
checkpoint-group |  |  | section | 3 - Testing Requirements
checkpoint-status |  |  | checkpoint | 3.1 - Compaction Testing
label | b307cbbb-e0f3-54c8-a277-335031719f5e |  | note | FREQUENCY: Each lot as required
label | 2f6160d1-c830-5bc1-b0c3-4f14ddd3bb97 |  | note | ACCEPTANCE CRITERIA: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six. A small lot is classed as an area equivalent to or less than 500m2 and requires only 3 individual tests. Compaction testing for crushed rock material shall be no less than 98%.
label | b9b69829-6d11-5e75-9067-7720b2b6557b |  | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08 (b) Table 304.081, 173.04 (d)
label | 6adc21e0-8da3-58ab-aefd-8685be89e42b |  | note | METHOD: Test Point
label | a92a55bc-a934-53b1-90dd-41b857704a5e |  | note | RECORD: Signed ITP
label | 55bcf49e-48ab-5bbe-9874-4ef19631138f |  | note | TP/HP/AP
label | c3d35af1-f2f2-529e-bd5e-850d1d7fa0be |  | note | RESPONSIBILITY: External Geo tester/SWA Project Manager/RRV Superintendent
date | ccbb13b1-06f1-5589-940d-1c78307f3d56 |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Conformance Testing for concrete strength & consistency.
label | 3f41a8b5-9b84-545e-a8f7-47afadee5d0b |  | note | FREQUENCY: Each lot as required
label | 64bce072-3844-521b-a3a0-5dd2b3a16ba7 |  | note | ACCEPTANCE CRITERIA: The minimum compression strength requirements for each strength grade shall be as shown in Table 703.111
label | e6dbae4c-ba22-505f-9712-e8ae967f620b |  | note | REFERENCE DOCUMENTS: Vicroads std sec Table 703.111
label | c07a8be1-b11d-51db-9679-f6b7058ac38c |  | note | METHOD: Survey Report
label | a73228ac-bee6-5e95-a53a-30015f0e35a9 |  | note | RECORD: Signed ITP & Test Reports
label | e0effab5-22c2-5331-abf3-391f5ddfa888 |  | note | TP/HP/AP
label | fb96dc8c-7e23-5fe2-9ae0-dfdbcf9b46db |  | note | RESPONSIBILITY: External Surveyor/SWA Project Manager/RRV Superintendent
date | bc9f3d1f-b1b4-541c-8f87-805c1d330bcc |  | date | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 8138864d-4a3b-5bda-986f-6aa83420317b |  | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
text | 873f6803-4544-5ef3-a4f4-c6a4310767ef |  | textbox | Print Name:
text | db859f22-cc9e-5287-af0c-cf55b244179c |  | textbox | Position:
date | 751dba85-2a55-5a4e-a2b7-ea4dee9eefbc |  | date | Date:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | SWA-013 - Pre - Construction | itp |  |  |  | Yes | SWA-013 - Pre - Construction | b8738fa3-7d57-47cf-b2b4-798567fc0026
checkpoint-group |  |  | section | 1.0 - Pre-Construction Checklist
checkpoint-status |  |  | checkpoint | 1.1 - Communication (1)
label | 6ac75fb9-74e2-5fb2-85a3-84c4b8008c39 |  | note | ACTIVITY / DESCRIPTION: Community and emergency services
date | c678d74b-a672-592b-b979-1c99b7f696d5 |  | date | Date:
checkpoint-status |  |  | checkpoint | 1.1 - Communication (2)
label | e55c5068-9fa4-5a1b-aa0a-6de36cbc5bf4 |  | note | ACTIVITY / DESCRIPTION: Emergency response plan
date | bda3f06a-3c3c-5018-af54-e0aff08de424 |  | date | Date:
checkpoint-status |  |  | checkpoint | 1.2 - Approved Construction Documentation (1)
label | 9628d657-61bb-5a84-9ad5-12752bc1064a |  | note | ACTIVITY / DESCRIPTION: IFC drawings (PDF, hardcopy)
date | 0d71f2f0-26f9-5995-bc5f-ccfbf607e17b |  | date | Date:
checkpoint-status |  |  | checkpoint | 1.2 - Approved Construction Documentation (2)
label | f343ec02-718c-59db-ab3a-25e80837e2df |  | note | ACTIVITY / DESCRIPTION: Digital (CAD) files (Surveyor)
date | 60cef747-332a-5e37-80d6-c09065e0a958 |  | date | Date:
checkpoint-status |  |  | checkpoint | 1.2 - Approved Construction Documentation (3)
label | 6486ac0a-36f4-5647-8cc9-8c58b9fc2796 |  | note | ACTIVITY / DESCRIPTION: Budget / Resource arrangement POs (incl. sub-contract agreements)
date | 0951336e-809c-5108-957b-34c50eb0e7de |  | date | Date:
checkpoint-status |  |  | checkpoint | 1.2 - Approved Construction Documentation (4)
label | a291999a-7702-54be-a784-596df5954215 |  | note | ACTIVITY / DESCRIPTION: Quantities / Specifications
date | aee31bd7-4cde-5a8f-a5ba-9514c271b1c7 |  | date | Date:
checkpoint-status |  |  | checkpoint | 1.3 - Dilapidation Report (records and photographs) (1)
label | 03636c61-da3d-5862-9ef7-a0e61d9ba316 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 79639933-4198-5797-be20-6f279137add8 |  | note | ACTIVITY / DESCRIPTION: Residential (ie: structures, access/gate, letterbox, fence)
date | 76df2442-44de-52f2-a7ee-9e1b2db476fd |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Dilapidation Report (records and photographs) (2)
label | 6e875f2f-1f6d-54b8-ad88-e8bac65328d1 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | ad5b0201-e292-57e1-b0be-3814d7cd5e6f |  | note | ACTIVITY / DESCRIPTION: Business (ie: structures, access/fence/gate, signs/letterbox)
date | 8118ed5e-26cf-5d2f-a5e1-25503267f92e |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Dilapidation Report (records and photographs) (3)
label | 1825af1f-9911-5784-b310-f67d99f16c75 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 34872f6b-7c88-59d7-8915-8ea569094049 |  | note | ACTIVITY / DESCRIPTION: Agricultural (ie: access, livestock, fence/gate)
date | b9ca6609-db0a-5eaa-9c75-18e375ab6eb3 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Heritage / Cultural listed areas: (1)
label | 67ed8b4e-48f9-57f8-a600-390c9bdd29c2 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | fa5dd48c-18b6-528b-a52f-0ec372b0b2c3 |  | note | ACTIVITY / DESCRIPTION: "No Go Zone"
date | 255ffa41-0fb6-50b0-be8a-005e04fba535 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Heritage / Cultural listed areas: (2)
label | aa5e5762-73d7-5990-869a-eae524283d11 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | c0716d5a-f08e-5685-94f9-d746f9de8103 |  | note | ACTIVITY / DESCRIPTION: Tourist attraction
date | fb3f411a-7165-5bd9-81c8-65d0947b8412 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Protected Environment (1)
label | c3537a7b-f353-5fa5-9655-321eb8f210b2 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | d36c54d2-7b0e-55a0-96df-a1570770f991 |  | note | ACTIVITY / DESCRIPTION: Flora
date | 63416b39-c036-5c4f-9cdd-9efbf878ddc8 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Protected Environment (2)
label | e374ec65-344d-5f55-9163-0363f1fc82c8 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 6874e82f-7eb2-55a8-a9e5-dca3b0fb7d8d |  | note | ACTIVITY / DESCRIPTION: Fauna
date | 5628aec3-4ec4-5365-a8b6-d9c417458b93 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Protected Environment (3)
label | ab221c3f-e8c1-5fcc-9705-0d3c8e189157 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | f016b3a2-6fac-5fc4-8857-7be2cfcc15e3 |  | note | ACTIVITY / DESCRIPTION: Water bodies
date | 07f39192-f364-5554-8b65-d980b885953a |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (1)
label | e0f4292e-52b6-5e42-a758-b0de3e089e54 |  | note | ACTIVITY / DESCRIPTION: Dial Before You Dig
date | 1e1eb03f-76ab-5ba0-855e-bcb622315ec9 |  | date | Date:
checkpoint-status |  |  | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (2)
label | 2e00c3ff-cbe8-5c74-af86-841465f410a7 |  | note | ACTIVITY / DESCRIPTION: Excavation Permit
date | 2aec04a3-0aad-5ac9-b793-83d1ef151c2b |  | date | Date:
checkpoint-status |  |  | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (3)
label | 7533acb9-6cc7-596c-a296-26e31d51c11a |  | note | ACTIVITY / DESCRIPTION: Assess and arrange for Service location
date | 13f705f3-bf35-53d8-8ca7-e84941343889 |  | date | Date:
checkpoint-group |  |  | section | 2.0 - Pre-Commencement Checklist
checkpoint-status |  |  | checkpoint | 2.1 - Traffic Items (1)
label | 55c62a7f-b4ab-5f3c-8def-280e4c917421 |  | note | ACTIVITY / DESCRIPTION: VMS boards
date | 6ac3d201-2c28-52a7-a8b2-90c414058ae2 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.1 - Traffic Items (2)
label | 5b9dd624-ae8f-581b-8874-6c737a56c425 |  | note | ACTIVITY / DESCRIPTION: TGS/TMP, MoA
date | ec18bf29-de58-576d-aabb-a088bed6a4ad |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.2 - Site marks / references (1)
label | 502435bf-bca4-55cb-b6da-3dd2a6dd1dcf |  | note | ACTIVITY / DESCRIPTION: Limit of Works
date | 1705a55f-e283-55eb-a225-cf0b20ff39c8 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.2 - Site marks / references (2)
label | ce62becc-d90c-520d-97b2-d9ebc15c1536 |  | note | ACTIVITY / DESCRIPTION: Survey control point
date | 1477e2f0-75ce-520a-97a9-db697eb6aa70 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.3 - Services, inspect/identify clash points: (1)
label | 1de60d9c-e7ab-5885-a3f6-0366865fff98 |  | note | ACTIVITY / DESCRIPTION: Sewer, Water
date | f335f453-2ac9-58b4-b6b4-18bc46f26df7 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.3 - Services, inspect/identify clash points: (2)
label | c6d0efd6-f8c1-556b-9d3d-ae7f2b631821 |  | note | ACTIVITY / DESCRIPTION: Gas, Electricity
date | 102be5f6-8768-518c-93a3-a2c773473a8f |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.3 - Services, inspect/identify clash points: (3)
label | 75076475-3b85-5121-ac0c-03db0e1eef54 |  | note | ACTIVITY / DESCRIPTION: Telecommunication
date | 14f8a3e3-f9ec-5544-b28d-605ec91d8327 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.3 - Services, inspect/identify clash points: (4)
label | 5f3060bb-3bb1-5591-b921-d4f59a6a92a6 |  | note | ACTIVITY / DESCRIPTION: Drainage (ie: council/shire, Other state authority)
date | de24c3b0-6b49-5f90-8428-2c576569d3e0 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.3 - Services, inspect/identify clash points: (5)
text | 5cd070f3-4bc2-5d15-82ac-70e37c344a84 |  | textbox | ACTIVITY / DESCRIPTION: Other specify:
date | 50d772c2-4165-5d56-8320-9c86a7d20b54 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (1)
text | 74683223-37ac-5f0b-9dc8-c59bbbb49457 |  | textbox | ACTIVITY / DESCRIPTION: O/H and U/G services flagged "No Go Zone"
date | 082b5cea-cbd9-5d32-b47a-12a91485a800 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (2)
text | 2d9b5ac8-2932-551d-afe9-cce406feb1b8 |  | textbox | ACTIVITY / DESCRIPTION: Trees(s) marked and approved for trimming or removal
date | 6ddf181a-e8b1-5fc9-ab3d-1f6b4ab98b3e |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.5 - SWMSs reviewed: (1)
text | 91edcc50-d584-52ff-9a80-5cf97676facd |  | textbox | ACTIVITY / DESCRIPTION: Site-specific
date | f484d58c-c0a0-5b74-9e0c-44d3b5f26fef |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.5 - SWMSs reviewed: (2)
text | b108d9a3-d755-5fe7-a3ce-9b4c144ed150 |  | textbox | ACTIVITY / DESCRIPTION: Spotter required / arranged
date | 241f3d92-8abd-5760-a197-07485a7903e6 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (1)
text | 000ad7b0-a0b3-5691-adc5-5fdb50559397 |  | textbox | ACTIVITY / DESCRIPTION: Sight and Clearance Distances:
date | 49c34f83-a82c-5d2d-99ae-76a827d686e7 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (2)
text | 845fa20d-5809-53bd-a769-4e8cf144dca5 |  | textbox | ACTIVITY / DESCRIPTION: Stop-slow areas, spotter, slips, confined space/work at height
date | 8d29808c-5f6e-5d17-ab5d-12701fcc7f8a |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (3)
text | da8e0f5e-1206-53be-ae77-1b48e2a2c06f |  | textbox | ACTIVITY / DESCRIPTION: Vehicle access to properties
date | 42516fb7-f459-51b6-a80b-3d181e45b9cf |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (4)
text | 5e983dd6-62b6-5c14-abdf-4a9d516d310a |  | textbox | ACTIVITY / DESCRIPTION: Proximity to Services: clearance requirements
date | 78bb6672-239a-5d14-9e90-b6fff32dfc28 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (5)
text | e5327478-ff3b-525b-9d22-e123465c38a6 |  | textbox | ACTIVITY / DESCRIPTION: Proximity to Water: supply point, watertable/dam/river/coast/port
date | 73da7c40-9c91-5b8e-8574-8dfb3ce76381 |  | date | Date:
checkpoint-status |  |  | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (6)
text | 9b5ae601-5c84-5742-862a-02d344119001 |  | textbox | ACTIVITY / DESCRIPTION: Site compound/Plant parking, material stockpile area, "dumpsite"
date | de3f3c7e-21fa-52b6-8b20-c9dea9d405fa |  | date | Date:
checkpoint-group |  |  | section | 3.0 - Construction
checkpoint-status |  |  | checkpoint | 3.1 - Vegetation Removal (1)
label | c4f91f9b-460b-5bf7-9724-1d68269b5fd8 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 9a06f88c-d3ba-509b-94eb-73443c6aa6a3 |  | note | ACTIVITY / DESCRIPTION: Spotter, Traffic Control
date | 24caba61-85bc-5159-b0ec-72a77a683fad |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1 - Vegetation Removal (2)
label | 2440ce69-0b95-549f-bf60-60b1909778d8 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 87e8fdf3-58d0-5c59-bdc3-c912e2382397 |  | note | ACTIVITY / DESCRIPTION: Equipment, Access
date | 9b81ac8f-b070-5323-9dca-acfbdb427325 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1 - Vegetation Removal (3)
label | ccf59e41-4ab4-5852-a208-c13193b332ce |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | d042cc4b-aab0-544a-85f7-80f1ce6852a5 |  | note | ACTIVITY / DESCRIPTION: Soil erosion / water contamination
date | c63da54d-4452-5d56-aa26-80f408262e25 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Contaminated Materials
label | f1271195-0f83-5568-b48c-aea50c41dd87 |  | note | ACTIVITY / DESCRIPTION: Contaminated Materials
date | ffafd4b5-54da-5bfe-801d-00e309038cf1 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.3 - Traffic Items (1)
label | d3430d21-a698-50e9-8359-dc7188cd9a6e |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 52a94787-19b2-56c7-bb15-816a2990cbb0 |  | note | ACTIVITY / DESCRIPTION: External review: Road Safety Audit
date | 70f42a74-ee1e-5d54-b8b0-1cde5b68b86f |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Traffic Items (2)
label | ec7ce81c-2ad7-50f3-9cbc-9f01a126af9d |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 580d0e38-7fdd-5696-a5d5-495e0cc60140 |  | note | ACTIVITY / DESCRIPTION: Internal review: adjust hold-time (traffic lights / traffic controller), flowbias, identify peak-hour period(s) / public transport / rubbish collection
date | c346f444-f86f-59e7-8e38-9f9909100dbd |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Trenching works (1)
label | 941db789-7b82-594b-bb6b-fcef0d6edb67 |  | note | ACTIVITY / DESCRIPTION: Review escape plan (routes)
date | 6d62af35-d0f5-5ef6-b239-b452fd3decb6 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.4 - Trenching works (2)
label | b4ecbe1d-c4f4-56b2-aeff-6efdc65fdd2b |  | note | ACTIVITY / DESCRIPTION: Review ground / water conditions
date | 619cc4c2-86a0-5d57-897a-31c5d6c53318 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.4 - Trenching works (3)
label | 540cea3b-7a41-5fa6-9f28-8540567fd217 |  | note | ACTIVITY / DESCRIPTION: Indentify Shoring / Benching requirements
date | 12f019cc-0473-5500-a16e-4c48b4fd9135 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.5 - Drainage Works (1)
label | 206c1000-b617-500b-9644-e5b5617da94c |  | note | ACTIVITY / DESCRIPTION: Assess surface-water impact – flow-path / catchment / outlet
date | 70024a33-18da-5be1-9e03-818c3b557391 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.5 - Drainage Works (2)
label | d8430f2c-7145-59d6-b01b-4d49402c154c |  | note | ACTIVITY / DESCRIPTION: Surface drainage (swale drain)
date | 1e06ce8b-b227-5e32-b27a-c39c24c7bb90 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.5 - Drainage Works (3)
label | 4cce8002-4d20-5487-8f39-429bf484f752 |  | note | ACTIVITY / DESCRIPTION: Sub-surface drain pipe and aggregate (agricultural drains / "agi pipe")
date | 33acb2dc-5580-585c-86fc-a0d62281f5ab |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.5 - Drainage Works (4)
label | ea0ce010-f16e-5655-b25a-79d53b30ded2 |  | note | ACTIVITY / DESCRIPTION: Review confined space entry
date | f6040a37-cd0a-5d2b-b12f-5777b19c46ac |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.5 - Drainage Works (5)
label | 055373e2-fcd2-5867-bae6-c62a3c9a7c4e |  | note | ACTIVITY / DESCRIPTION: Review lifting methods (load / equipment / plant / crane)
date | f396fea9-8948-5986-a2e1-3320dc2bbc80 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.5 - Drainage Works (6)
label | e5e82d46-11a8-5768-bb45-772759095f7e |  | note | ACTIVITY / DESCRIPTION: Levels
date | 00326889-24e1-507e-9670-084aaf6e1b9c |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.5 - Drainage Works (7)
label | 4398c1aa-7394-5b74-b0bf-a13b96671e33 |  | note | ACTIVITY / DESCRIPTION: Pit covers / Grates
date | e659082f-e4d6-5e1d-a61b-b6414277833e |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.6 - Structural Items (1)
label | 3b525321-4f28-5639-add6-31ec82bc5df6 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | be017c29-8f47-5668-bdae-a8405425460c |  | note | ACTIVITY / DESCRIPTION: Crown units / culvert
date | 395b34ca-3ed7-5d85-be46-515ca8a56d07 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Structural Items (2)
label | caeee054-0a9f-552c-80b4-84f23d4ffd26 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 43028459-d569-558f-948f-38217645075c |  | note | ACTIVITY / DESCRIPTION: Retaining structure works
date | 807220dc-dd15-50c5-a8fc-c003c6fae476 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Structural Items (3)
label | 0df10fa0-c833-55e1-9193-0d7a4569cbd7 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 303a4d60-fb15-5276-81ad-fab2e818ecb3 |  | note | ACTIVITY / DESCRIPTION: Bridge works
date | a8c8c7d3-a0f9-557d-86f0-ec9e894e650e |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Concrete kerb works: (1)
label | 85ba550e-6b28-5857-bc5e-ccbab8a99472 |  | note | ACTIVITY / DESCRIPTION: Alignment / level
date | ad6260d7-5ed9-59c9-acbc-d5ce0a530454 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.7 - Concrete kerb works: (2)
label | 196e60b1-5cf7-5548-a2a2-2f21dce71563 |  | note | ACTIVITY / DESCRIPTION: profile / finish
date | 81cc87f6-e6c0-5e62-bc6d-46af70cb2f8e |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.8 - Concrete Works (1)
label | 401cdf12-25f0-5fd8-9ee9-30975c3b2303 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 12a4338e-180e-5542-ae61-a968ebe17b5a |  | note | ACTIVITY / DESCRIPTION:
date | 30e9d4f6-b44a-5cd4-9e38-c9188dca2b01 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Concrete Works (1)
label | 50a1f3c8-852d-5f7d-a90f-bbe760fbedbf |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | b8b5e787-b8a9-522f-bc42-7971fc89dbbd |  | note | ACTIVITY / DESCRIPTION: (in-situ & pre-cast) - Bedding material / blinding material
date | c90c15f0-ebc6-556f-a851-79e244f671c9 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Concrete Works (2)
label | 3d269fdf-cde3-5045-b197-b495c7bf1264 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 1f8d3ea8-ab2f-5a5a-8252-be864ae88514 |  | note | ACTIVITY / DESCRIPTION: (in-situ) - Formwork, duct-work
date | 8f5b6cbd-ad5a-5282-b1f1-8450ee22c61c |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Concrete Works (3)
label | f8c6660a-0b26-5d62-98ea-ddc73be56ed4 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | e1f3c380-ce16-557f-9480-15d08544bce7 |  | note | ACTIVITY / DESCRIPTION: (pre-cast) Alignment/dimensions
date | f7e3ff3c-d599-5193-8553-3425282b40b2 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Concrete Works (4)
label | 538b3710-fbf1-576a-9efb-9cda272d4314 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 14e24089-3285-5a04-be40-c2f11bbf4886 |  | note | ACTIVITY / DESCRIPTION: (in-situ) - Rebar layout
date | b1c808e3-525b-5745-880b-ed644c29343e |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Concrete Works (5)
label | 4362a75c-8d17-58f2-a2b9-37e835138dc9 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 517c09cb-52a7-55c1-af1d-c19b4061c574 |  | note | ACTIVITY / DESCRIPTION: (in-situ) - Concrete mix / Compaction / Placement method(s)
date | ba98caf0-cd34-5675-a817-86ab1e308f91 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Concrete Works (6)
label | bab3caaf-3e29-5150-9f97-102d3d7e3f11 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | b0f820c0-a955-5788-bfbb-884b9b202c56 |  | note | ACTIVITY / DESCRIPTION: (pre-cast) - Lift points / placement method
date | 2088c290-f00d-5619-969f-6f3235b7382d |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Concrete Works (7)
label | dfe49555-ae54-5b30-b62e-f56301f61a2c |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | d03928cd-fe9d-5ac9-b157-dcd34632c6ea |  | note | ACTIVITY / DESCRIPTION: (in-situ & precast) - Pre-stress works (where applicable)
date | ed14191b-2a26-5984-b326-bb45015ed9c3 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Concrete Works (8)
label | 8884b095-83d5-5ce6-8d8d-80eaf4306d63 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 17cf4daa-0a6f-5fb4-9b7c-5f129acf634d |  | note | ACTIVITY / DESCRIPTION: (in-situ & precast) Finish
date | 6e271065-4fde-52f2-8ee8-97b76b48f1f6 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (1)
label | e73589a9-ec36-54cd-9029-5ee29ce1deec |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 1b3a26cc-7010-5158-ab72-bbdbee1bd096 |  | note | ACTIVITY / DESCRIPTION: Require in-situ testing / laboratory report (where required)
date | 75b4e119-6301-5b94-b8ce-839b4666ce1f |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (2)
label | 8b2306d3-92b6-5476-83a2-281a1b1190f1 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | e70bb6c6-d7ea-5908-a5dd-e5a62cd09130 |  | note | ACTIVITY / DESCRIPTION: Material dockets (ie: Lime / Cement)
date | f937da68-feb6-5804-b46e-17e5c22c049a |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (3)
label | 90496a06-77d2-58e8-a89d-fb4b7d1f7ecf |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 6bce577a-706e-5a14-aafe-da3385ac4755 |  | note | ACTIVITY / DESCRIPTION: Density results
date | c1445df0-8e52-5f7f-96e1-74811d8d9e30 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (4)
label | e51627c3-a02b-5a2c-867d-795095cde3c8 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | fd110d90-715a-5e18-9914-c7a94602cd50 |  | note | ACTIVITY / DESCRIPTION: Proof-roll
date | f3628880-a322-519a-a4fb-4d030a922d59 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.10 - Pavement Works (1)
label | b0e21f3b-781c-567f-9184-cedcd7dba172 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 5b32bd42-1cfa-5ce5-b6d4-e6b7b8432557 |  | note | ACTIVITY / DESCRIPTION: Density results
date | 981e0eb1-3b86-5839-a78d-f4ca87dddfb8 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.10 - Pavement Works (2)
label | de3488c1-cb69-51df-9b46-9083c7620eb3 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 4460a507-b9c6-5ecf-94c7-151aeee07db0 |  | note | ACTIVITY / DESCRIPTION: Proof-roll / Test Rolling
date | 13da7516-ddc1-5ea8-864c-3925ea208098 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.10 - Pavement Works (3)
label | 7f373744-f16a-59ab-8365-8d1b2626e0d1 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | ebf648f9-2a90-524a-9a17-27d3e7fcc4ed |  | note | ACTIVITY / DESCRIPTION: Dryback results (NB: required prior to sealing works)
date | 447c7ffb-ccd8-547d-8638-4bf69813c694 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.10 - Pavement Works (4)
label | 3fef4dd5-2ef3-59f8-927a-73fce94b43d5 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | cf83917c-4162-5eb0-8ed4-456ddbf42093 |  | note | ACTIVITY / DESCRIPTION: Ball Penetration Test
date | 7f10fe4e-729a-547e-a479-92f014ea1436 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.11 - Utility Services, Traffic / Public lights (1)
label | d038a06b-3e2a-5e9c-bf71-de2b832e1b7f |  | note | ACTIVITY / DESCRIPTION: Level & Location (ie: clearance requirement)
date | 43daad50-b548-5b48-a1ad-7365ecc21eef |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.11 - Utility Services, Traffic / Public lights (2)
label | 575b00ff-78d5-57f8-a161-2d17d6d112c3 |  | note | ACTIVITY / DESCRIPTION: Approved equipment for installation
date | 765441c7-7694-5c75-a283-4c365041838c |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.11 - Utility Services, Traffic / Public lights (3)
label | a46320d2-7f1e-5097-a48d-6447073a73da |  | note | ACTIVITY / DESCRIPTION: Pit and conduit (ie: clearance requirement)
date | 561ad1d9-de3b-57fe-9f7f-e9a880990643 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.11 - Utility Services, Traffic / Public lights (4)
label | 25963336-1eba-572e-b0e9-e5b299512e7c |  | note | ACTIVITY / DESCRIPTION: Audits by relevant authority / hand-over procedure
date | 3e25cae7-33e3-5629-9827-724e49802f46 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.12 - Pavement Surface Works (1)
label | b6eaf2b8-9418-57ed-b6c3-2eacb3f58fb4 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 0ab970b0-5923-5246-afca-a41d27053472 |  | note | ACTIVITY / DESCRIPTION: Seal (ie: suitable material, spray-sheet details)
date | b377244e-049f-565e-b5ab-9b6c17b108f6 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.12 - Pavement Surface Works (2)
label | b846e4a9-d9b0-5d0f-8d23-23db84ef0d0c |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 9bf5d3da-5e55-5f80-8075-102e2cd4bdbd |  | note | ACTIVITY / DESCRIPTION: Asphalt (ie: material dockets)
date | 96810742-a4c1-5113-a84e-f2d7a6584165 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.13 - Landscape (1)
label | 398e27fa-a911-566f-a856-c1ead55abbe6 |  | note | ACTIVITY / DESCRIPTION: Seed / Grass
date | 2afa04d7-980a-5c03-b9a5-80f631a38a8f |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.13 - Landscape (2)
label | 087d861a-ac33-5a99-9133-2da489077fdb |  | note | ACTIVITY / DESCRIPTION: Hydro-seed / Hydromulch
date | ced50251-08f1-5808-a1b4-ff6e82306766 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.13 - Landscape (3)
label | 851c9681-9923-5889-8551-1992519214c2 |  | note | ACTIVITY / DESCRIPTION: Street furniture
date | 52496859-46bb-5845-886a-71886ad7d6ba |  | date | Date:
checkpoint-status |  |  | checkpoint | 3.13 - Landscape (4)
label | 307cf2ee-fa00-58a1-8d27-d9f5b40676fe |  | note | ACTIVITY / DESCRIPTION: Maintenance arrangement / period: 3 / 6 / 12 / 18 / 24 months
date | 3d76ca1d-49f4-530b-ae11-4b845347c14c |  | date | Date:
checkpoint-group |  |  | section | 4.0 - Practical Completion
checkpoint-status |  |  | checkpoint | 4.1 - Road Fixtures (1)
label | a78b448f-3d6b-5115-bf91-68755dbd1d50 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 491ff107-7508-5ded-bcd7-46dc66d1889c |  | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
date | c3234fb8-5a01-54b2-8c31-df4d3772bb61 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1 - Road Fixtures (2)
label | 68e0deb5-ff03-5ad4-a55e-aa978e856497 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 4c2e81e9-4907-5868-b8d1-d123752e8ef6 |  | note | ACTIVITY / DESCRIPTION: Signs
date | 2b632d02-8e86-56ae-9497-1942b780189c |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.1 - Road Fixtures (3)
label | 8460d55e-5f83-5331-ab37-22230156ea0b |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 88345f33-bc9b-505b-98a5-80a9327974ed |  | note | ACTIVITY / DESCRIPTION: Guide posts
date | 30bfad2f-388f-5f9b-92ba-6d644b77d9e8 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Safety Barrier Works (1)
label | 45a477e3-6218-5f97-9aec-324bc41f1015 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | f7ea3589-d893-5f22-8fb1-b84637152666 |  | note | ACTIVITY / DESCRIPTION: Guardrail
date | f44c2698-72a0-5bb0-9da0-24d0e9af787d |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Safety Barrier Works (2)
label | 5816b8bc-7785-502f-93d7-b22dd3287534 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 6d99b1d0-3c0e-52c2-b183-fbdcf96608c4 |  | note | ACTIVITY / DESCRIPTION: Wire-rope
date | d834a3c0-472e-5f71-a98c-db0213e7605a |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Safety Barrier Works (3)
label | 95c4c178-aad0-5b49-958e-e6d0d0d481b1 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 2d487db0-bf78-5a7f-ad16-57cea40f5505 |  | note | ACTIVITY / DESCRIPTION: Motorcycle-safe fixtures
date | c650ada4-30b7-578a-b8e5-f31b1ba00970 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Fences and Gates
label | 8912adce-b3ab-5d7e-8c53-a6455556f9c2 |  | note | ACTIVITY / DESCRIPTION: Fences and Gates
date | da41faa5-b8d9-57fb-b5a4-91fce97a9ed7 |  | date | Date:
checkpoint-status |  |  | checkpoint | 4.4 - Quality Ride Test
label | 6930f8cd-1a69-5aeb-8223-009d731a03c5 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | b7076034-b179-54d3-a933-b8d5ceb054f0 |  | note | ACTIVITY / DESCRIPTION: Quality Ride Test
date | 1284124b-0fc7-5008-9461-e2d2bf5cf373 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5.0
checkpoint-status |  |  | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (1)
label | dff99e57-221f-5d1e-8fb6-c9aafa0555bf |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 8eedd16b-1f11-57f6-9019-0bdbc003a50b |  | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
date | 09948306-f65b-5d5a-a0b7-328132f80554 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (2)
label | 4bb23012-1b28-5815-847a-52fce7be4eac |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | de297435-d6a4-5eab-9aaa-3271b9fbf73a |  | note | ACTIVITY / DESCRIPTION: Signs, guide posts
date | 503f7189-fc53-5a4d-86b7-2acb91f9cf01 |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (3)
label | 39ec032c-277e-50b6-b1aa-1447b14abf8f |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 91679e6d-2a25-531d-9495-cb4792238201 |  | note | ACTIVITY / DESCRIPTION: Seal / Asphalt surface
date | 136e4b81-c14c-55b1-91b7-266d280b636a |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (4)
label | fbce7819-e701-5581-a44f-36c502e9a0d9 |  | note | EXTERNAL REFERENCE: Hold Point (HP)
label | 4d3ba9f5-d460-5173-b974-75d6edf1a06f |  | note | ACTIVITY / DESCRIPTION: Landscape (where applicable)
date | e560aa7e-540e-5ad9-9d8b-16f7d9db106c |  | date | Date:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Final Inspection
label | 30e35763-5253-53b3-a77e-c12431fd0cb6 |  | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
text | cb9f02e9-9908-55ca-8cd9-4341da118c0d |  | textbox | Print Name:
text | d84717bd-2a80-5c3a-b881-8158314def49 |  | textbox | Position:
date | 0f7b88f2-0a7d-540b-889a-2ecfe760bed4 |  | date | Date:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | ITP-015 - Drainage Checklist | itp |  |  |  | Yes | ITP-015 - Drainage Checklist | f6cd55d0-eaf3-43cc-a503-3c65808da246
checkpoint-status |  |  | checkpoint | Pit Details
text | afd16bda-97e3-5754-8cbb-5ee0a29304bc |  | textbox | Pit No.
text | bb7ea087-37fb-5cd4-a859-16092d3bfe5f |  | textbox | Pit Type
text | 3700b52b-7d10-594f-95f2-b8e9dab30909 |  | textbox | Dimension
text | 41e518d5-d2c6-5512-b24c-a7bc2898354f |  | textbox | Inlet Level
text | 2ab54a67-4535-5730-b9c8-a8be2f5c6bb4 |  | textbox | Outlet Level
text | c1384ddb-1ec4-550c-bd3c-4778cc89c5c9 |  | textbox | FSL
text | 290caf0d-9fba-5a85-a0dd-73e9cb030aad |  | textbox | Pit Depth
checkpoint-status |  |  | checkpoint | Checklist Items
text | ac624d40-08bc-5426-9b5b-c423dd5c0b32 |  | textbox | Drainage Line Number
text | daa29e46-8508-5a48-b08d-f361bd3ae10f |  | textbox | Pipe Size
text | e4639f21-6947-5345-a311-15e53939e1f9 |  | textbox | Trench Width (mm)
text | 499ecc76-afc3-516c-88d2-3c7a49542bfe |  | textbox | Minimum Cover (mm)
text | d2056b63-946c-5f28-b703-ec88f0006d41 |  | textbox | Beading Depth (mm)
date | ffd080c2-bbf6-53a0-9d39-930b9730536f |  | date | Start Date
date | 515a47c7-7afb-50ee-b28d-2539758af222 |  | date | Finish Date
checkpoint-status |  |  | checkpoint | Pipe/Pits/End Walls
label | 3cfaf860-9b55-5617-b805-a33a0edf6914 |  | note | Pipes/Pits/End Wall in sound condition?
date | d4d0a798-2bbd-5bd2-86b0-698bcc3f625c |  | date | Start Date
date | 829e1b3b-f075-58d3-bfe4-8c32bdbba046 |  | date | Finish Date
checkpoint-status |  |  | checkpoint | Laying Direction
label | 870fdf83-eae7-550c-8b8f-51b95043010a |  | note | The direction of Laying Satisfactory i.e Collar on Upstream?
date | ff9b4f1b-9a73-5a34-be7c-4fbdaac7d65d |  | date | Start Date
date | a56660c3-2851-551b-b087-3dbea48313df |  | date | Finish Date
checkpoint-status |  |  | checkpoint | Rubber Joint
label | f90311b1-ba4f-5fec-b632-b87d0bcff459 |  | note | Rubber Joints in Satisfactory condition?
date | c4ef5e28-032f-5e32-96aa-dea191a1df86 |  | date | Start Date
date | 3399d266-167e-5a7e-960e-a90cefa99f68 |  | date | Finish Date
checkpoint-status |  |  | checkpoint | Gap Filling
label | 97d086c1-dac2-5af5-8835-2f81a6f7f8bc |  | note | All the holes have been mortared to satisfactory condition?
date | 2d35c2c4-4f3d-540a-b840-2305de4e50f9 |  | date | Start Date
date | 9d077d7d-e1de-5a54-b9ca-c5dc9f487873 |  | date | Finish Date
checkpoint-status |  |  | checkpoint | Step Irons
label | 6448d217-65bd-5977-b378-0e887266a884 |  | note | Step Irons Installed in the Pit greater than 1000mm?
date | 1a6d2c1e-2d63-5ae4-aa0c-ccdb11fc4325 |  | date | Start Date
date | 4334c58c-5249-5bd2-82b0-431bad66f96a |  | date | Finish Date
checkpoint-status |  |  | checkpoint | Final Inspection
label | 4e42773f-3821-5e50-a586-f0f5f566380c |  | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
text | 6db91f04-ea88-5494-894e-9f5a266a884d |  | textbox | Print Name:
text | 2d884928-1d04-5d03-b9a2-196391ae2f4d |  | textbox | Position:
date | 85dc6342-20eb-5e07-af92-556a8c64f6fc |  | date | Date:
holdpoint |  |  | signoff | Sign ITP