## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Aluminium Canopies (Eyebrows) on Structural Steel Framing |  |  |  |  | Yes | Aluminium Canopies (Eyebrows) on Structural Steel Framing | 22229b61-eb15-432e-8b22-a90c2a0b3f4c
checkpoint-group |  |  | section | Sequence of Works
checkpoint-status |  |  | checkpoint | Confirm correct quantities/materials delivered to site
checkpoint-status |  |  | checkpoint | Install all materials in accordance with shop drawings and site measure as approved on Aluminium Canopy drawing and Structural Steel marking plan drawing.
checkpoint-status |  |  | checkpoint | All fixings installed as per shop drawings
checkpoint-status |  |  | checkpoint | Includes screw, nuts, bolts, rivets, washers, fixing anchors, supporting members, hangers, bracings, brackets, straps
checkpoint-status |  |  | checkpoint | All metalworks installed flush and level in accordance with specification tolerance
checkpoint-status |  |  | checkpoint | All paint or metal finishing in good condition without any damage on the surface
checkpoint-group |  |  | section | Final Inspection & Handover
checkpoint-status |  |  | checkpoint | Final site walk to confirm satisfactory installed
checkpoint-status |  |  | checkpoint | All defects closed out. Required information for warranty & certification has been submitted
checkpoint-status |  |  | checkpoint | Attach installer signature
label | 3cb031a8-0a89-5cdc-999d-e2c51462b712 |  | note | I confirm that all necessary inspections have been carried out and can verify that the work has been completed and conforms to the contract specification.
checklist-sectioned |  |  | checklist | ITP A1196-1 - Handrails |  |  |  |  | Yes | ITP A1196-1 - Handrails | 5a93e447-f79c-4617-8e93-fabd8f53478b
checkpoint-group |  |  | section | Sequence of Works
checkpoint-status |  |  | checkpoint | Confirm correct quantities/materials delivered to site
checkpoint-status |  |  | checkpoint | Handrails with stanchions/wall brackets & all materials installed as per shop drawings
checkpoint-status |  |  | checkpoint | All fixings installed as per shop drawings
label | 745acfe0-992d-557a-a919-cd1c64418a42 |  | note | Includes screw, nuts, bolts, rivets, washers, fixing anchors, supporting members, hangers, bracings, brackets, straps
checkpoint-status |  |  | checkpoint | All metalworks installed flush and level in accordance with specification tolerance
checkpoint-status |  |  | checkpoint | All paint or metal finishing in good condition without any damage on the surface
checkpoint-group |  |  | section | Final Inspection & Handover
checkpoint-status |  |  | checkpoint | Final site walk to confirm satisfactory installed
checkpoint-status |  |  | checkpoint | All defects closed out. Required information for warranty & certification has been submitted
checkpoint-status |  |  | checkpoint | Attach installer signature
label | 047d4ed5-7d0b-569d-984d-34a201c072d3 |  | note | I confirm that all necessary inspections have been carried out and can verify that the work has been completed and conforms to the contract specification.
checklist-flat |  |  | checklist | Day Site Diary |  |  |  |  | Yes | Day Site Diary | 6887ff60-0be1-4410-86a4-504420ffdeae
checkpoint-status |  |  | checkpoint | Day Diary details entered below
text | 89cfb844-9e86-5c72-8dd5-55d9c73be3fa |  | textbox | IJ Build Staff Onsite (list names)
select | ff715b02-d650-5d85-9aba-ac5745060461 |  | dropdown | Number of Staff Onsite | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10
select | 233e46b8-2e0e-57e8-92ca-072f024a3309 |  | dropdown | Hours Worked | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12
checkpoint-status |  |  | checkpoint | Works Completed (list in comments)
checkpoint-status |  |  | checkpoint | Issues faced / delays (list in comments and add photos if relevant)
checkpoint-status |  |  | checkpoint | Signed off by IJ Build (attach signature)
checklist-sectioned |  |  | checklist | Balustrade / Steel Structures Installation |  |  |  |  | Yes | H&S - Accident / Incident for Register | 6a915984-006c-4684-9c22-307f7a988524
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | Verify applicable shop drawings required for work area.
checkpoint-status |  |  | checkpoint | Check incoming materials:
boolean | 36d34710-fd11-53c5-9969-eb362fa6a7af |  | tickbox | Quantity
boolean | f3ac04f9-127e-5ce8-91d8-4e2ece0931fd |  | tickbox | Correct mark no.
boolean | a424535e-09be-5a0e-82e8-748a46d162f7 |  | tickbox | Handling damage
checkpoint-group |  |  | section | Site Assembly
checkpoint-status |  |  | checkpoint | Install the steel members as per the shop drawings.
checkpoint-status |  |  | checkpoint | Check erected steelwork:
boolean | cc878221-4e21-5b74-b333-28b89256c3d9 |  | tickbox | Orientation
boolean | cccd958d-9fe5-556d-89b1-6e802bce1919 |  | tickbox | Position
boolean | dd3d22d9-d812-54c1-9e78-7f132a4a35f7 |  | tickbox | Plumbness
boolean | 9b85c86d-f7be-5864-920d-574cb0afd842 |  | tickbox | Squareness
boolean | ec11f029-c0a5-5b09-b3c0-e88e5e1e6219 |  | tickbox | Level
checkpoint-status |  |  | checkpoint | Ensure correct bolts, nut and washers to design drawings sizes and type.
checkpoint-status |  |  | checkpoint | Check tightening of bolts as per specification.
checkpoint-status |  |  | checkpoint | Check if the threaded portion of the bolt
checkpoint-status |  |  | checkpoint | Grouting of base plates
checkpoint-status |  |  | checkpoint | Check coatings damaged during erection.
checklist-sectioned |  |  | checklist | Balustrade / Steel Structures Installation |  |  |  |  | Yes | Balustrade / Steel Structures Installation | 6f1e6a89-39ce-4d04-808a-05729f48dd68
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | Verify applicable shop drawings required for work area.
checkpoint-status |  |  | checkpoint | Check incoming materials:
boolean | 7e230518-8b10-5667-8743-8f7bf43239c0 |  | tickbox | Quantity
boolean | bb93c48b-4c61-5dca-8255-3c289f563d6d |  | tickbox | Correct mark no.
boolean | 5790ea0b-00dd-5654-bfe6-26eeac10bde3 |  | tickbox | Handling damage
checkpoint-group |  |  | section | Site Assembly
checkpoint-status |  |  | checkpoint | Install the steel members as per the shop drawings.
checkpoint-status |  |  | checkpoint | Check erected steelwork:
boolean | 10298058-5ff5-5adf-8266-c92b7e48a3d6 |  | tickbox | Orientation
boolean | 28815c57-ad3a-5bc1-8693-c89481c825a8 |  | tickbox | Position
boolean | 5f8cca78-cc22-5623-aca6-1d6d74a00216 |  | tickbox | Plumbness
boolean | 2f0144a9-6db2-54df-a152-697fa0e2bc90 |  | tickbox | Squareness
boolean | 2697217e-fb14-5c77-86ce-0f74aa88149d |  | tickbox | Level
checkpoint-status |  |  | checkpoint | Ensure correct bolts, nut and washers to design drawings sizes and type.
checkpoint-status |  |  | checkpoint | Check tightening of bolts as per specification.
checkpoint-status |  |  | checkpoint | Check if the threaded portion of the bolt
checkpoint-status |  |  | checkpoint | Grouting of base plates
checkpoint-status |  |  | checkpoint | Check coatings damaged during erection.
checklist-sectioned |  |  | checklist | ITP A1196-5 - Miscellaneous Steel Works |  |  |  |  | Yes | ITP A1196-5 - Miscellaneous Steel Works | 9c171d1f-c96d-48bc-8596-a902c46cf77c
checkpoint-group |  |  | section | Sequence of Works
checkpoint-status |  |  | checkpoint | Confirm correct quantities/materials delivered to site
checkpoint-status |  |  | checkpoint | Bollards / bike racks / metal fencing & all materials installed as per shop drawings
checkpoint-status |  |  | checkpoint | All fixings installed as per shop drawings
label | 7b468221-c5a5-57df-b420-27efee171fd9 |  | note | Includes screw, nuts, bolts, rivets, washers, fixing anchors, supporting members, hangers, bracings, brackets, straps
checkpoint-status |  |  | checkpoint | All metalworks installed flush and level in accordance with specification tolerance
checkpoint-status |  |  | checkpoint | All paint or metal finishing in good condition without any damage on the surface
checkpoint-group |  |  | section | Final Inspection & Handover
checkpoint-status |  |  | checkpoint | Final site walk to confirm satisfactory installed
checkpoint-status |  |  | checkpoint | All defects closed out. Required information for warranty & certification has been submitted
checkpoint-status |  |  | checkpoint | Attach installer signature
label | 7e1a7460-822e-5160-b9c5-40157862f8c0 |  | note | I confirm that all necessary inspections have been carried out and can verify that the work has been completed and conforms to the contract specification.
checklist-sectioned |  |  | checklist | Material Receiving and Inspection Form |  |  |  |  | Yes | Material Receiving and Inspection Form | b0ce02e4-ae00-4da2-84c7-e3c4488b0404
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Below details completed
text | 2ccc1b58-9279-57bb-a8e9-9aabf09e2fa9 |  | textbox | Project:
text | b705076a-72a5-5073-a7da-7d85a28902fe |  | textbox | Date:
text | c1dec9de-51e1-5c75-88e3-db230cf06a7b |  | textbox | Location:
text | b8f20a8f-4c55-5584-b707-da6bff8d0219 |  | textbox | Received By:
text | 800ef274-7d79-5c50-9686-34e0c1611345 |  | textbox | Arrival Time:
text | 133ea73a-d4d7-545f-ab76-aa3f6cda3e69 |  | textbox | Description of Delivery:
text | 3b9aa38b-a5dc-5825-b665-7dab818239ce |  | textbox | Cost Code/PO:
button | 78a7485e-2166-5938-aba7-b767c045e6d3 |  | button | Inspection Required? | Fabricated Balustrades, Structural Steel
checkpoint-status |  |  | checkpoint | Complete item details below
text | 8c5f101b-126c-5f42-b3f7-0887895542d2 |  | textbox | Item Detail
text | 9f9f01da-5625-53ad-8263-f10644c5fd35 |  | textbox | Quantity
text | ac1edaca-8d23-57e8-8d7a-ec6739766cbb |  | textbox | Units
text | 6123c23c-340c-5a1a-bcca-14cb349177dc |  | textbox | Discrepancy from Docket / Damage Details / Comments
checkpoint-no-status |  |  | checkpoint | Additional comments
label | 2b646e4f-febb-5423-b4cf-36fda0769c36 |  | note | Return completed forms with delivery dockets to project administration.
checklist-sectioned |  |  | checklist | Documents (Manufacturer’s Data Record) |  |  |  |  | Yes | Documents (Manufacturer’s Data Record) | cb3bce88-5e52-418c-a337-bf9fbedf591c
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Manufacturer Data report (MDR): Documentation Complied (attach)
checkpoint-status |  |  | checkpoint | As Built Marking Plans (attach)