## zres_siteapp
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP A1196-5 - Miscellaneous Steel Works |  |  |  |  | Yes | ITP A1196-5 - Miscellaneous Steel Works | 9c171d1f-c96d-48bc-8596-a902c46cf77c
checkpoint-group |  |  | section | Sequence of Works
checkpoint-status |  |  | checkpoint | Confirm correct quantities/materials delivered to site
checkpoint-status |  |  | checkpoint | Install all materials in accordance with shop drawings or approved design engineering
checkpoint-status |  |  | checkpoint | All fixings installed as per shop drawings
label | 7b468221-c5a5-57df-b420-27efee171fd9 |  | note | Includes screw, nuts, bolts, rivets, washers, fixing anchors, supporting members, hangers, bracings, brackets, straps
checkpoint-status |  |  | checkpoint | All metalworks installed flush and level in accordance with specification tolerance
checkpoint-status |  |  | checkpoint | All paint or metal finishing in good condition without any damage on the surface
checkpoint-group |  |  | section | Final Inspection & Handover
checkpoint-status |  |  | checkpoint | Final site walk to confirm satisfactory installed
checkpoint-status |  |  | checkpoint | All defects closed out. Required information for warranty & certification has been submitted
checkpoint-status |  |  | checkpoint | Attach installer signature
label | 7e1a7460-822e-5160-b9c5-40157862f8c0 |  | note | I confirm that all necessary inspections have been carried out and can verify that the work has been completed and conforms to the contract specification.
checklist-sectioned |  |  | checklist | Balustrade / Steel Structures Installation |  |  |  |  | Yes | Balustrade / Steel Structures Installation | 6f1e6a89-39ce-4d04-808a-05729f48dd68
checkpoint-group |  |  | section | Preliminaries
checkpoint-status |  |  | checkpoint | Verify applicable shop drawings required for work area.
checkpoint-status |  |  | checkpoint | Check incoming materials:
label |  |  | note | No handling damages. Complies with applicable shop drawings
boolean | 7e230518-8b10-5667-8743-8f7bf43239c0 |  | tickbox | Quantity
boolean | bb93c48b-4c61-5dca-8255-3c289f563d6d |  | tickbox | Correct mark no.
boolean | 5790ea0b-00dd-5654-bfe6-26eeac10bde3 |  | tickbox | No handling damage
checkpoint-group |  |  | section | Site Assembly
checkpoint-status |  |  | checkpoint | Install the steel members as per the shop drawings.
checkpoint-status |  |  | checkpoint | Check erected steelwork:
label |  |  | note | AS4100 - 15.3 Tolerances – Column bases alignment: Position in plan +/-6mm, level +/-10mm.
label |  |  | note | Beam is within +/-10 of its correct level at connections to other members.
boolean | 10298058-5ff5-5adf-8266-c92b7e48a3d6 |  | tickbox | Orientation
boolean | 28815c57-ad3a-5bc1-8693-c89481c825a8 |  | tickbox | Position
boolean | 5f8cca78-cc22-5623-aca6-1d6d74a00216 |  | tickbox | Plumbness
boolean | 2f0144a9-6db2-54df-a152-697fa0e2bc90 |  | tickbox | Squareness
boolean | 2697217e-fb14-5c77-86ce-0f74aa88149d |  | tickbox | Level
checkpoint-status |  |  | checkpoint | Ensure correct bolts, nut and washers to design drawings sizes and type.
checkpoint-status |  |  | checkpoint | Check tightening of bolts as per specification.
checkpoint-status |  |  | checkpoint | Check for the threaded portion of the bolt
label |  |  | note | Threaded portion of the bolt projects through the nut for a minimum of two (2) threads and a maximum of 10mm when fully tightened
checkpoint-status |  |  | checkpoint | Grouting of base plates
label |  |  | note | All grout under base plates shall be Conbextra GP free-flow non- shrink cementitious grout (U.N.O) or equivalent with Minimum compressive strength of 50MPa
label |  |  | note | Three (3) 75 mm test cubes shall be taken from the first batch of material mixed, then three (3) 75 mm cubes for every 100 kg of material used.
label |  |  | note | Test cubes shall be made in rigid steel molds
checkpoint-status |  |  | checkpoint | Check if coatings damaged during erection.