## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Panel - Level Completion |  |  |  |  | Yes | Panel - Level Completion Checklist | 08de9207-e11a-4627-968a-ec2564a3588a
checkpoint-group |  |  | section | Panel completion
checkpoint-status |  |  | checkpoint | Grids and RL's in place
checkpoint-status |  |  | checkpoint | Structural tolerance check
checkpoint-status |  |  | checkpoint | Sub Frame/Brackets installed correctly
checkpoint-status |  |  | checkpoint | Panel installed and secured with approved methods
checkpoint-status |  |  | checkpoint | Head bead/temp fixings installed
checkpoint-status |  |  | checkpoint | Smoke flashing/Area caulked
checkpoint-status |  |  | checkpoint | Panel free from damage/scratches
checkpoint-group |  |  | section | Final Sign Off
checkpoint-status |  |  | checkpoint | All panels have been inspected and installed correctly.
checkpoint-status |  |  | checkpoint | All variations/modification have been closed out
checklist-flat |  |  | checklist | Panel Completion |  |  |  |  | Yes | Panel Completion Checklist | 0eb1b3e1-3a72-41bc-867b-3cfd04506cb3
checkpoint-status |  |  | checkpoint | Panel has been installed correctly and is free from defects
boolean | e1b6352a-db83-5cd7-a19f-0bbc91e41fe3 |  | tickbox | Window Wall
boolean | 8df07143-f24f-54ce-937e-65fd75005773 |  | tickbox | Curtain Wall
boolean | 8b0dcfc2-e495-519f-8947-384cd48b90df |  | tickbox | Mullion Set Out
boolean | 34ae42ed-29a6-5a1e-a09a-f564c2e417e7 |  | tickbox | Steel
label | 432f0473-e2f0-5c87-add8-294f393696c7 |  | note | If variation/modification required, click FAIL and add Variation/Modification checklist
checklist-flat |  |  | checklist | FT01 Panel completion checklist |  |  |  |  | Yes | FT01 Panel completion checklist | 6e45f220-b6b8-44d9-b607-7a91002e8cc8
checkpoint-status |  |  | checkpoint | Panel has been installed correctly and is free from defects
boolean | 4e956b9e-7165-5cce-9473-779d78ebd1a9 |  | tickbox | Window Wall
boolean | e92ecda5-b477-56d4-84f9-e7d1273433b7 |  | tickbox | Curtain Wall
boolean | f08b491c-847a-5193-981f-314cd0edab34 |  | tickbox | Mullion Set Out
boolean | 3bba8a74-50c4-525b-b760-a76b72c34813 |  | tickbox | Steel
label | dd7123be-e22d-57fc-8b36-d2b0df19fdd9 |  | note | If variation/modification required, click FAIL and add Variation/Modification checklist
checkpoint-no-status |  |  | checkpoint | Bracket Installation
label | a65a2c3d-4a90-5036-a41e-a654a6e60d42 |  | note | Cast in Channels accepted
label | cf717ffe-0d6e-58a3-a9c4-9ff6d0932e3f |  | note | Correct BRACKET type (BRK01,02,03, etc) confirmed
label | 3761a371-18d1-5c2f-b878-63b61d1bf9ec |  | note | Bracket installed plumb and in correct location (MIN-WLC-FT01-1111-1134) Over Hang Limits ± 25mm
label | a3e6cd38-1ab0-5c66-8f77-d910f53a80ce |  | note | Bracket Edge distance from Concrete slab: 125mm (+5mm/-0mm)
label | 165b6093-97eb-5124-aa31-a032adcbb289 |  | note | Bolt type confirmed - HBC-C -60-M16 -60mm length Grade 8.8 Gal bolts
label | f9ce110b-f2e9-5ed1-a271-737c22014f25 |  | note | Bolts / Nuts All present and in Correct Location as details
label | f3a5311e-5435-5501-9ffa-ff1d6798ef48 |  | note | Bolts / Nuts tension - Torque Wrench to 60Nm
label | c867e650-2b8a-53d5-8513-1075f036a1dd |  | note | Bolts / Nuts paint - sprayed on completion
checkpoint-no-status |  |  | checkpoint | Panel
label | 7b53dd7c-3356-57f1-9df6-11b695e7239b |  | note | ID sequence number confirmed
label | 0ff4f44f-6ce9-5948-97a0-ad0cf24156c6 |  | note | Check rubbers have been installed correct way
label | b2612b92-ef21-552d-b399-d36d442ce3d8 |  | note | Repair any loose / hanging rubbers
label | 394e7927-9aff-5991-82b9-3052c33dc467 |  | note | Cut-back over-hang on rubbers
label | fce15827-5c4c-5df4-a8a2-d682c2d2ccd1 |  | note | Crimp & lubricate rubbers
label | 0ed52219-6335-5a15-99f3-0ae1fdb2fd93 |  | note | Panel glass free from damage
label | 38dda50c-40aa-5a32-a4cf-744f57dfc0d3 |  | note | Clean silicone from drain holes (side of mullion)
label | 014ea68f-9934-5914-9898-53e2c643f787 |  | note | Silicon any missed screws to prevent any future leaks
label | 99a78026-2cde-5462-8a8e-44aed48f78f0 |  | note | Clean panel from all protective tape-External
label | 02aa6201-4328-5740-8b24-8b66558d4892 |  | note | Panel colour confirmed - M.Pc2b Duratec Zeus Monument Matt
label | 89ad2eaf-9338-5f31-b282-7b838e1e1b6e |  | note | Foam Installed in area under mullion of 4-way joint
label | 47389f59-ce92-5844-9ee4-978ee60ac7f9 |  | note | Clean area be caulked thoroughly with white spirits
label | 1c357b5f-2daf-5dce-9cb7-72ddf15631ba |  | note | Ends to be completely sealed with silicone
label | 63754deb-098d-5e03-bbcd-11b504a2c3fd |  | note | Inspect for defects/correct
label | 68e857b7-9639-519c-91b4-5213f6f8c9fc |  | note | Protect panel from damage to frame when loading & erecting
label | 6d859ef0-c1ad-5992-81b0-2879262a559b |  | note | Stack head pressing and gutter sleeves installed andsealed as per shop drawings
label | 4281bac5-0cd6-5e23-9f3a-c2425b300dc8 |  | note | Ponding test for Subsill-Inspect after 24 hours
label | a5d00e54-eef7-57e1-88c8-57fd8d5fd9c4 |  | note | Panel Installation Tolerance: ±3 mm
label | 04415b4a-2542-57c5-9ece-dc7c81b6ef1e |  | note | Head to Sill Height Gap (Internal): Vertical ± 3mm
label | ac1d35c1-4e6b-546d-aa34-bda45c875d9b |  | note | Inspect panel for any damage or misalignment after erection
label | bcb15140-d1f4-521c-8aab-0711558b37d6 |  | note | Caulk all 4-way joints
label | cb004ab9-b2cb-5935-bb5d-835c0d183811 |  | note | Top & bottom of slab smoke flashing installed and caulked as per design (Fireblock XT)
label | dbb6090f-7e50-5393-b9e6-8909141f3ccb |  | note | Protection tape in place
checklist-flat |  |  | checklist | Variation/Modification |  |  |  |  | Yes | Variation/Modification Checklist | 8755db80-6c09-41a9-9636-279ec26b1596
checkpoint-status |  |  | checkpoint | Add in comments variation/modification details. Attach relevant photos