## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | SH58-M2TG | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi NZ Transport Agency | [5 empty] | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | 106877 | [5 empty] | C | Check | CM | Construction Manager | Jamie Nisbet | JN
Area/ Sub-System: | Site Wide |  |  | Lot ID Number: |  |  | D | Dimension Inspection | ER | Stantec Representative | Sam Parkinson | SP
[7 empty] | E | Examine | QE | Quality Engineer | Lyssa Gatehouse | LG
ITP Number: | SH58-ITP-C-008 Drainage Swales |  |  | Version: | 2 |  | H | Hold Point | QM | QA Manager | Diliban Sengottian | DS
ITP Description: | Swale construction | [5 empty] | I | Inspection | SV | Surveyor | Jim Robbins | JR
Discipline: | Civil | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | John Masters | JM
Specification: | MCIP SH58 East of Moonshine Road to Transmission Gully- Project Specification | [5 empty] | O | Operation | ST | Superintendent | Craig Maloney | CM
[7 empty] | R | Review | PE | Project Engineer | Dehan Erasmus | DE
Drawings: | 80510096-02B-900-C217 Rev 1 | [5 empty] | S | Subcontractor | SE | Site Engineer | Tyrese Dickson | TD
[7 empty] | V | Visual Verification | EM | Environmental Manager | Ross Glubb | RG
Prepared By: (Name) | Tyrese Dickson |  |  | Date: | 2025-08-27 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: | Jamie Nisbet |  |  | Signature: |  | #VALUE! |  |  | Date: | 2025-09-03
Downer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:

## Construction
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Specification/Drawing Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
4.1 | Topsoil stripping | Project Specification Cl15.3.4 | Prior to commencing any clearance, the Contractor shall set up a site meeting with the Engineer to agree on the depth and estimated stockpile qty following strip. The nominal depth to be stripped varies but shall be confirmed on site, depending on the actual depths available. If required, another method of measurement can be agreed with the Engineer. | CONQA Hold point approval | Prior to to topsoil stripping | Hold Point | H | ER
4.2 | Excavation | 80510096-02B-900-C217 Rev 1 | Slope batter to be 1:3 on the roadside of swale and 1:1max on opposite batter as per 80510096-02B-900-C217 Rev 1 | As-builts | during construction | Witness Point | W | SE
4.3 | Topsoil placement | Project Specification Cl 20.1.14 | The minimum topsoil depths for planting areas (as required by NZTA P39) are as follows: * In swale areas 100mm | Photos As-builts | during construction | Witness Point | W | SE
4.4 | Plant Mix | 80510096-02B-900-C217 Rev 1 | Plant mix type 7 on top of topsoil as per drawing | Photos | during construction | Witness Point | W | SE
4.5 | Tolerances | Project Specification Cl15.3.11 | Earthworks shall be constructed to the following tolerance: *Finished level ± 50 mm | As-builts | At completion | Witness Point | W | SV