## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | DS2681-SH58-ITP-C-008 Drainage Swales Rev2 | itp | DS2681-SH58-ITP-C-008 Drainage Swales
2c7cbdbe-c9f7-4797-a6e3-b3caa63de2fb | section | SECTION 4 – IN-PROCESS INSPECTIONS
5df9146d-f515-4a7e-95a2-64672e3440ae | checkpoint | 4.1 - Topsoil stripping
a8a08bf8-b5bf-5828-bef9-96fe2f6c1485 | note | Specification/Drawing Reference - Project Specification Cl15.3.4
547d3b49-84d6-55f7-bcf0-f2adf4b5ea75 | note | Acceptance Criteria - Prior to commencing any clearance, the Contractor shall set up a site meeting with the Engineer to agree on the depth and estimated stockpile qty following strip.
42ebcb72-5d88-57d1-8be4-18fbb6c2844e | note | ○ The nominal depth to be stripped varies but shall be confirmed on site, depending on the actual depths available. If required, another method of measurement can be agreed with the Engineer.
3e83e29c-e5c6-567e-b11d-0eafe177d6fa | note | Verifying Document - CONQA Hold point approval
83959c14-f680-5a19-a2df-0e6f82768cb3 | note | Frequency - Prior to to topsoil stripping
bb5a9874-43e7-51ee-ae78-bb6ff9e7c04d | note | Inspection Type (Visual, other) - Hold Point
300cad8e-e99b-5345-8441-71257192ab2a | note | Inspection: Key - H
bc11b116-94b2-5366-b1d7-54ec8988d344 | note | Inspection: By - ER
ca46e811-5a7c-4732-90c1-70fa45f01fc6 | signoff | AUTHORITY HOLDPOINT
1285a58c-bc27-4baa-b3f5-d2479bcfe8df | checkpoint | 4.2 - Excavation
bbe91289-48a8-585e-8be1-c3705e4d1f39 | note | Specification/Drawing Reference - 80510096-02B-900-C217 Rev 1
8f387c43-5a20-5104-8cf3-dcd264e6cb35 | note | Acceptance Criteria - Slope batter to be 1:3 on the roadside of swale and 1:1max on opposite batter as per 80510096-02B-900-C217 Rev 1
5a0f5234-8fc8-5c0a-a043-43e8c28646ac | note | Verifying Document - As-builts
655436bb-65f7-5d9c-a23d-7977b4329bbb | note | Frequency - during construction
c81651f3-02cb-5127-96dd-d94529a191aa | note | Inspection Type (Visual, other) - Witness Point
c2be3987-6e5d-501d-943f-ee3c81797d2d | note | Inspection: Key - W
4960c2a4-e92b-5eb9-bc92-5d2daca2ecad | note | Inspection: By - SE
d64ee5e3-5af0-44e8-a005-22dbb7eb6513 | checkpoint | 4.3 - Topsoil placement
4384baae-69d5-539b-a8e1-7884afebd7dc | note | Specification/Drawing Reference - Project Specification Cl 20.1.14
dee17f01-a66a-59ba-a056-8867c185c346 | note | Acceptance Criteria - The minimum topsoil depths for planting areas (as required by NZTA P39) are as follows:
c882bb3f-51cf-5f86-bec9-401139e216f0 | note | ○ In swale areas 100mm
ef2f33f2-0d81-5419-a169-ea5266795ea3 | note | Verifying Document - Photos, As-builts
0603d669-1eda-5150-b2c0-1bcfc65d59d3 | note | Frequency - during construction
69bd3e7e-778e-5f67-b6c2-d558158ab17f | note | Inspection Type (Visual, other) - Witness Point
8d5166d6-ceeb-5f09-be86-97874807f61f | note | Inspection: Key - W
3b9eb925-2f1c-5f9a-a2ea-67286f588a7a | note | Inspection: By - SE
50ebc9bc-2710-45c5-93d7-3ec631c714fe | checkpoint | 4.4 - Plant Mix
bc4ebb81-6e79-5a97-8f5d-63511be9fb2e | note | Specification/Drawing Reference - 80510096-02B-900-C217 Rev 1
badfe2ff-71cc-5b1c-8615-434fd05e64f3 | note | Acceptance Criteria - Plant mix type 7 on top of topsoil as per drawing
d78061c9-905e-5296-a6d6-0ed927f8b000 | note | Verifying Document - Photos
bea9b952-5740-58f8-ae98-6d701727907a | note | Frequency - during construction
e752a2ba-dfc2-556a-863d-ef44cd2c2b2b | note | Inspection Type (Visual, other) - Witness Point
71a3cee9-abe5-5a9f-9a36-2954ffd95f17 | note | Inspection: Key - W
cbf520bb-d95a-5c5d-aa52-5de198f73420 | note | Inspection: By - SE
7248eae9-f161-43d8-9b81-01d495046fb9 | checkpoint | 4.5 - Tolerances
b11800ca-40df-55a8-8e3f-5daaca9fda8b | note | Specification/Drawing Reference - Project Specification Cl15.3.11
2b1e9837-b787-59e7-8434-879d4f9196ff | note | Acceptance Criteria - Earthworks shall be constructed to the following tolerance:
281fc796-cfc4-53e6-915f-e9a4f8a516c7 | note | ○ Finished level ± 50 mm
5aaed5b5-a967-58b2-b7f8-2dd539834473 | note | Verifying Document - As-builts
dc8aeaa8-d09f-5dee-9e6a-71c85b9bae72 | note | Frequency - At completion
fba348b4-060c-5320-866f-e99166f04f44 | note | Inspection Type (Visual, other) - Witness Point
73a5215d-437f-5ed5-8cf2-db28b2f25c0d | note | Inspection: Key - W
07099577-9bb8-5ebb-bb0b-85e30436b222 | note | Inspection: By - SV