## ITP Cover Page
Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 146 - Rev C
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 146
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status: |  |  | For Approval
ITP Description: |  |  | Service Bracket Hanger Installation |  |  |  |  | Revision: | 1000 |  | C
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | Drawings DN-1205-065-DRW-01
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Approval | 2025-07-28 |  | Eva Fan |  | First Revision for Review and Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Submit for Approval | 2025-08-18 |  | Eva Fan |  | Revision for Review and Approval with Engineer's Comments |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
C | Submit for Approval | 2025-08-25 |  | Eva Fan |  | Revised 3.01.04 for reinstatement material |  |  |  | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 146- Rev C
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.01 | Site Requirements
1.01.01 | Construction Pack | Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence. | Downer | Construction Pack | Prior to Works | H | PE
1.01.02 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to activity being undertaken | H | PE
1.01.03 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
1.01.04 | Construction Methodology & ITP | The Contractor must submit their proposed construction methodology, justification and ITP to the Engineer for review at least 10 Working Days prior to commencement of the Works. The Engineer’s review will be limited to conceptual assessment of any potential impact on critical elements of the structure. ITP to be included in QA pack with confirmation of approval | PS - 11.3 SS 2146 - 3 | Methodology ITP | At least 10 Working Days prior to commencement | HP | ENG
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2.02 | Reinforcement
2.02.01 | Steel supply | Certificate of origin for all steel reinforcing supplied | NA | Certificate | Each batch of reinforcment | R | ENG
2.03 | Pre fabricated Steel Brackets
2.03.01 | SS Steel Brackets | All QA to be in separate ITP – This item to be acceptance of QA ITP | Structural steel notes on IFC DWG 4001 Construction Drawing | BBO | Before Installation | H | PE
2.03.02 | SS M16 Anchor Rod | HILTI HAS-U-A4 | Manufacturer Specification | - Material Certification - Delivery dockets or invoice | Before Installation | H | PE
2.03.03 | Epoxy | HILTI HIT-HY200 | Manufacturer Specification | - Material Certification - Delivery dockets or invoice | Before Installation | H | PE
2.03.04 | SS M16 bolts, washers and nuts | Property A4-80 | Structural steel notes on IFC DWG 4001 Construction Drawing | - Material Certification - Delivery dockets or invoice | Before Installation | H | PE
SECTION 3 – CONSTRUCTION ACTIVITY
3.01 | M16 Drill and Epoxy
3.01.01 | Hole Drilling at Existing Bridge Structure | Holes to be drilled with hammer drills. Diamond core drilling is not acceptable. Cutting of existing reinforcement is not allowed unless approved by the Engineer. | Manufacturer Specification | NA | Before Epoxy | H | PE
3.01.02 | Hole Drilling at Existing Bridge Structure | All holes shall be cleaned using a stiff bristled wire bottlebrush and an oil free compressed air source to remove all dust and debris from the side of the hole. Check to verify no reinforcements have been hit. | Manufacturer Specification | NA | Before Epoxy | H | PE
3.01.03 | Engineers Inspection | The Contractor shall advise the Engineer when he intends to commence the epoxy process. No epoxy shall be applied without Engineer's acceptance. | SS 2146 - 6 PS - 2.2.16 | Hold Point Release | Min 48h Notice | HP | ENG
3.01.04 | Reinforcement clash | If reinforcement have been hit, new spot to be scanned and marked for another potential drill hole position. New EA to be fabricated to suit the new anchor bolt position if necessary. All unused holes to be reinstated by Sika412. | Downer | Record / Photo | Before Epoxy | H | PE
3.02 | Steel Bracket (Hanger) Installation
3.02.01 | Steel bracket installation | Ensure tensioning tolerances for steelwork/bolts are checked. | Downer / AS/NZS 5131: 2016 | Hold Point Release | Before Installation | H | PE
3.02.02 | Tension bolts | Check each bolt has a washer and nut and tension all bolts | AS/NZS 5131: 2016 | Photo/Site-Approva/Checksheet | Each Baseplate | I | SE
3.02.03 | Isolation between SS & HDG Elements | Verify separation has been achieved between SS and HDG elements | Downer | Record / Photo | After Epoxy | H | PE
SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
4.01 | General
4.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE
4.01.02 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth. | Downer | Redlines | Post construction | H | PE
4.01.03 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE
REV C