## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - 146 - Service Bracket Hanger Installation | itp |  |  |  |  | ITP - 146 - Service Bracket Hanger Installation Rev C
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 1.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence.
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 1.01.02 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to activity being undertaken
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 1.01.03 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 1.01.04 - Construction Methodology & ITP
label | Acceptance / Conformance Criteria - The Contractor must submit their proposed construction methodology, justification and ITP to the Engineer for review at least 10 Working Days prior to commencement of the Works. The Engineer’s review will be limited to conceptual assessment of any potential impact on critical elements of the structure.
label | ○ ITP to be included in QA pack with confirmation of approval
label | Standard / Specification - PS - 11.3, SS 2146 - 3
label | Verifying Document - Methodology ITP
label | Frequency - At least 10 Working Days prior to commencement
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 2.02.01 - Steel supply
label | Acceptance / Conformance Criteria - Certificate of origin for all steel reinforcing supplied
label | Standard / Specification - NA
label | Verifying Document - Certificate
label | Frequency - Each batch of reinforcment
label | Verification Activity: Activity - R
label | Verification Activity: By - ENG
checkpoint | 2.03.01 - SS Steel Brackets
label | Acceptance / Conformance Criteria - All QA to be in separate ITP – This item to be acceptance of QA ITP
label | Standard / Specification - Structural steel notes on IFC DWG 4001 Construction Drawing
label | Verifying Document - BBO
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 2.03.02 - SS M16 Anchor Rod
label | Acceptance / Conformance Criteria - HILTI HAS-U-A4
label | Standard / Specification - Manufacturer Specification
label | Verifying Document - Material Certification
label | ○ Delivery dockets or invoice
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 2.03.03 - Epoxy
label | Acceptance / Conformance Criteria - HILTI HIT-HY200
label | Standard / Specification - Manufacturer Specification
label | Verifying Document - Material Certification
label | ○ Delivery dockets or invoice
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 2.03.04 - SS M16 bolts, washers and nuts
label | Acceptance / Conformance Criteria - Property A4-80
label | Standard / Specification - Structural steel notes on IFC DWG 4001 Construction Drawing
label | Verifying Document - Material Certification
label | ○ Delivery dockets or invoice
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 3 – CONSTRUCTION ACTIVITY
checkpoint | 3.01.01 - Hole Drilling at Existing Bridge Structure
label | Acceptance / Conformance Criteria - Holes to be drilled with hammer drills. Diamond core drilling is not acceptable. Cutting of existing reinforcement is not allowed unless approved by the Engineer.
label | Standard / Specification - Manufacturer Specification
label | Verifying Document - NA
label | Frequency - Before Epoxy
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.02 - Hole Drilling at Existing Bridge Structure
label | Acceptance / Conformance Criteria - All holes shall be cleaned using a stiff bristled wire bottlebrush and an oil free compressed air source to remove all dust and debris from the side of the hole.
label | ○ Check to verify no reinforcements have been hit.
label | Standard / Specification - Manufacturer Specification
label | Verifying Document - NA
label | Frequency - Before Epoxy
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.03 - Engineers Inspection
label | Acceptance / Conformance Criteria - The Contractor shall advise the Engineer when he intends to commence the epoxy process. No epoxy shall be applied without Engineer's acceptance.
label | Standard / Specification - SS 2146 - 6, PS - 2.2.16
label | Verifying Document - Hold Point Release
label | Frequency - Min 48h Notice
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.04 - Reinforcement clash
label | Acceptance / Conformance Criteria - If reinforcement have been hit, new spot to be scanned and marked for another potential drill hole position. New EA to be fabricated to suit the new anchor bolt position if necessary.
label | ○ All unused holes to be reinstated by Sika412.
label | Standard / Specification - Downer
label | Verifying Document - Record / Photo
label | Frequency - Before Epoxy
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.02.01 - Steel bracket installation
label | Acceptance / Conformance Criteria - Ensure tensioning tolerances for steelwork/bolts are checked.
label | Standard / Specification - Downer / AS/NZS 5131: 2016
label | Verifying Document - Hold Point Release
label | Frequency - Before Installation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.02.02 - Tension bolts
label | Acceptance / Conformance Criteria - Check each bolt has a washer and nut and tension all bolts
label | Standard / Specification - AS/NZS 5131: 2016
label | Verifying Document - Photo/Site-Approva/Checksheet
label | Frequency - Each Baseplate
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.02.03 - Isolation between SS & HDG Elements
label | Acceptance / Conformance Criteria - Verify separation has been achieved between SS and HDG elements
label | Standard / Specification - Downer
label | Verifying Document - Record / Photo
label | Frequency - After Epoxy
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 4.01.01 - Construction Record Compilation
label | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.02 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.01.03 - Defect, Snag and Punch List
label | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | Standard / Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature