## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
547bca51-0a20-494d-a8ac-12235855368e |  | pass | ITP - M10 Dense Graded Asphalt - Post Construction Rev 0 | checklist | FALSE | FALSE | Site QA | Zone 1 | 101 - Horahora | ACP-ITP - M10 Dense Graded Asphalt - Post Construction-LOT-001 - Site 101
1044d2cf-e0c5-4bb1-8e28-05f46a224f6c |  | pass | ITP - M10 Dense Graded Asphalt - Post Construction Rev 0 | checklist | FALSE | FALSE | Site QA | Zone 1 | 102 - Oak Tree Bends | ACP-ITP - M10 Dense Graded Asphalt - Post Construction-LOT-002 - Site 102
9145c32a-f4cd-4d05-b086-47a33be3d7dd |  | pass | ITP - M10 Dense Graded Asphalt - Post Construction Rev 0 | checklist | FALSE | FALSE | Site QA | Zone 2 | 201 - Hutton's | Asphalt | ACP-ITP - M10 Dense Graded Asphalt - Post Construction-LOT-004 - Site 201
bf7f5e10-ea98-406f-ba2f-63ce2b3d5651 |  | pass | ITP - M10 Dense Graded Asphalt - Post Construction Rev 0 | checklist | FALSE | FALSE | Site QA | Zone 2 | 202 - Putaruru | Asphalt | ACP-ITP - M10 Dense Graded Asphalt - Post Construction-LOT-005 - Site 202
b315d908-eff5-4158-92bd-ce1b3bd548d0 |  | pass | ITP - M10 Dense Graded Asphalt - Post Construction Rev 0 | checklist | FALSE | FALSE | Site QA | Zone 3 | 310 - Ngutuwera | Asphalt | ACP-ITP - M10 Dense Graded Asphalt - Post Construction-LOT-003 - 310 Ngutuwera - AC20 post completion
0cedf2f0-3ab1-421e-bf78-bf0e84415458 |  | pass | ITP - M10 Dense Graded Asphalt - Post Construction Rev 0 | checklist | FALSE | FALSE | Site QA | Zone 5 | 503 - Hill Road Passing Lane | Asphalt | ACP-ITP - M10 Dense Graded Asphalt - Post Construction-LOT-009 - Site 503
e1cbd3a2-14bd-4530-87ee-0de59cba2bf3 |  | work-in-progress | ITP - M10 Dense Graded Asphalt - Post Construction Rev 0 | checklist | FALSE | FALSE | Site QA | Zone 6 | 601 - Centennial Drive | Asphalt | ACP-ITP - M10 Dense Graded Asphalt - Post Construction-LOT-010
20430130-7f8a-407a-8bdc-8bff12971f3a |  | pass | ITP - M10 Dense Graded Asphalt - Post Construction Rev 0 | checklist | FALSE | FALSE | Site QA | Zone 8 | 803 - Mangamate | Asphalt - Section 2 (RP9822 - 10050) | ACP-ITP - M10 Dense Graded Asphalt - Post Construction-LOT-008 - Site 803
3666c7ff-40dd-4766-8c39-ad98569860b6 |  | pass | ITP - M10 Dense Graded Asphalt - Post Construction Rev 0 | checklist | FALSE | FALSE | Site QA | Zone 8 | 804 - Oturere | Asphalt | ACP-ITP - M10 Dense Graded Asphalt - Post Construction-LOT-007 - Site 804
e34c8bc6-72e3-4eee-ad14-f35ed2454389 |  | pass | ITP - M10 Dense Graded Asphalt - Post Construction Rev 0 | checklist | FALSE | FALSE | Site QA | Zone 8 | 805 - Mangatoetoe-nui | Asphalt - Section 1B | ACP-ITP - M10 Dense Graded Asphalt - Post Construction-LOT-006 - 805 - AC Post construction