## Master List Templates
Id | Type | Name | Values | Prompting Name
e706d209-a0d7-4f8a-b115-ffe897c1dbee | checklist | Add Documentation |  | Add Documentation
ff06f4ee-fc20-4592-a8a0-d50b05de58d0 | section | Details
aea326de-38aa-4580-9108-bc40108e1732 | checkpoint | Please upload all documements and press PASS.
5574dabc-93ee-4d68-ac87-18c315969b76 | checklist | Carpet Installation |  | Carpet Installation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
5e4d95a6-210a-47c4-912d-a04d36b88ead | checkpoint | Substrate clean and approved for installation?
4372bd92-3002-5861-bc4a-dfe1b132fadb | note | x 2 Picture
e3aa4c71-d2f9-45d4-939e-60a9b0e535a4 | checkpoint | Are sills, door frames & tiles flush with carpet?
f032e764-3799-5cab-a1a0-5fd51ae4b114 | note | x 2 Pictures min
7b08ddb2-070c-4af8-af6f-77c996055062 | checkpoint | Doors to be removed? Take pictures before and after (proof no damage)
d9ed088a-ab34-5791-9943-6390241d9d90 | note | x 2 Pictures min
4ee616ff-3075-43f2-bb4c-5dcef736150b | checkpoint | Confirm plan matches site and joins ok?
f01aeeff-ae27-4c66-9151-118ee4fbdea3 | checkpoint | Review job sheet confirm all detail matches e.g. colour of carpet, underlay required?
710b644e-e10a-49a6-95eb-b5fca7698ce3 | checkpoint | Take photo of carpet joins?
51a89d8f-9cb6-510d-ae6f-a5be9aa2c0fb | note | x 2 Pictures min
bed1c205-0340-47c6-ac66-810372720802 | checkpoint | No damage to skirtings or walls?
efaf9d9d-d682-5741-8f20-1087e781b682 | note | x 4 Pictures min
28092beb-2d16-4808-b805-bb7bc9b90839 | checkpoint | Doors replaced and area left clean of offcuts and rubbish? Take pictures before and after (proof no damage)
4d11ddc9-73e2-5f9d-9f99-69828acd9fc1 | note | x 2 Pictures min
33ae76fe-6753-441e-b99e-64ef5e894198 | checkpoint | Walked all areas, pins tapped down, stairs tight, no carpet lifting, all ok?
0e0473c6-0269-516a-b577-279fa2af17d3 | note | x 2 Pictures min
948b931b-65ff-41de-9dd0-31f34a59563b | signoff | Please signoff / request sign off
ddcde5d0-89cf-458c-b497-b29a46a89ca9 | checklist | Carpet Tiles Installation |  | Carpet Tile Installation
91470a5f-a51f-4b45-b91d-0c18901efd25 | section | Details
29b3160f-c0e6-46d5-b200-ee02ed2aa0b5 | checkpoint | Carpet tile range and colour check and confirmed
9aa0686c-2307-4f25-9c01-e5d1137359c2 | checkpoint | Moisture test done?
a05d860b-05ea-4ecc-86cc-f724062256dd | checkpoint | Moisture barrier required? If Yes take picture of product
b153246c-d165-57dc-a0c9-d13b59418282 | note | If required check site specification notes for product and special instructions
4a0a3676-49fd-556a-ba42-72635d45381a | note | Take picture of moisture barrier used if applicable.
c332174a-460f-48f0-9ff9-93fa384b97dc | checkpoint | Floor prep required ?
09a3d2fa-4cbd-5e68-b02e-d14fc884e830 | textbox
f9fe9dde-bf9d-4a43-bc57-6e6093d09416 | checkpoint | Installation direction confirmed ?
d1c05433-9bcb-4185-8d58-619f022cc23c | checkpoint | Setting out lines square ?
f970343b-977d-4da5-a90b-8e5fdbb0c54e | checkpoint | Are all edges free from fraying ?
ec05e9c0-f8eb-4d11-a845-ccf2c3cfcfdd | checkpoint | Are all edges cut neat and straight?
e15e8da8-586f-458f-aeb1-0bc929385dc1 | checkpoint | Carpet tile adhesive used
f359f6b9-a4a4-5c00-bc4a-1867d59ce94f | note | x1 Pictures
598ba512-42aa-4c45-88de-955654fd2d88 | checkpoint | Correct trowel or roller used?
f33b57dc-592e-5bdb-84a3-8e3d976bf0d3 | note | x1 Pictures
480431e5-24bf-43b6-bd98-dd39ba921276 | checkpoint | Check and clean any excess adhesive in joints, on wall, or skirting
03fb65a9-205f-5d00-8eb4-5abbe125c197 | note | x4 Pictures
31dd7a68-2e1c-489c-818f-bad73e0d9332 | checkpoint | Transition between other floor covering level and flush
51ee7fb7-a6cb-547d-a44f-6f22bd94e278 | note | x2 Pictures min
2d6c8e36-795f-479d-a399-d80b4ac2aab3 | checkpoint | Phase completed with no damage ?
d0e8747b-a067-580a-8da7-b0108d47e020 | note | x4 Pictures
4d16c088-5691-42f0-abfb-a04b9322b0e6 | signoff | Please signoff / request sign off
2d428dc1-8ae8-4c37-ba1c-186c9bd941e0 | checklist | CDC Floor Prep |  | CDC Floor Prep
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
aa08c00b-6eb8-45b0-ba39-794f059e7856 | checkpoint | Survey floor for flatness?
730cd1cd-7235-4fa8-bfe6-435e5ebd9a56 | checkpoint | Moisture test done prior to installation?
a89d60dc-4cb8-4d6c-803b-a8d2b9694b73 | checkpoint | At-risk surfaces protected?
18622457-a9fc-4df0-a8aa-3f38cc5bd650 | checkpoint | Apply 1st Coat - Planiseal MR Moisture barrier
eb66b571-a890-55cf-928a-ca5c0c944dad | note | x 2 Pictures min
b84f5aec-b4b4-4fe1-ada2-fbe617619a29 | checkpoint | Apply 2st Coat Planiseal MR Moisture barrier with Broadcast Sand
62b85f1e-5f45-5e8c-9fe1-2a3233dab662 | note | x 2 Pictures min
aaf8cce0-9583-41ba-b427-fbd25cc3cc18 | checkpoint | All areas dammed up to prevent leaks?
4b036c64-f778-465b-bf85-cecd2451f33d | checkpoint | Apply Mapei Ultraplan Eco Leveller
773d74f8-a18c-51f7-94ea-8747b593658c | note | x 2 Pictures min
ec7e285f-f686-4c00-bc81-b49677594f4c | checkpoint | Area clear of rubbish and debris?
233de79f-da53-4473-b1af-f12ce2fe7733 | checkpoint | No damage to other surfaces?
2e9948d0-90d2-4068-9fec-149aedb3a00a | checkpoint | Levels checked and ready for installation?
d7491de3-a314-4f2b-a55d-4da9f372dab0 | checkpoint | Preparation complete with no damage?
f69dd938-8133-5cea-9753-57664402a3ac | note | x 2 Pictures min
6902d4f5-eac1-493f-963a-876a01916260 | signoff | Please signoff / request sign off
09c21e74-d6b0-4c6b-a231-7ff297ef47bd | checklist | CDC Floor Vinyl |  | CDC Floor Vinyl
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
302a0f51-ea8d-481a-9a17-5afecfa58d41 | checkpoint | DT059 Capping strip set at 150mm
1f0fb784-8db7-43eb-af62-88fa22f6f21b | checkpoint | Plastic cove to base of skirting
78818b72-4131-4923-9807-03c1a0a6957c | checkpoint | Correct adhesive for Vinyl - Uzin KE2000S Glue
81c3983a-9e84-51b7-8789-4580df2b7311 | note | x 1 Picture
5b158be1-a6f7-493d-ae4e-f457d6420c62 | checkpoint | Correct trowel used
72d19ecf-f8a8-5a9b-9d9e-68a8f3fe286b | note | x 1 Picture roll label
5fabc77d-2d3d-4a7c-acb5-2c3acc94950b | checkpoint | Install Tarkett IQ Granit SD Sheeting to Data Halls (Pic of label + install)
f8534668-364b-5d98-90cd-b31213ff92e0 | note | x 1 Picture roll label
3eedb064-0303-44ff-8a47-a7cbe1edacad | checkpoint | Install Tarkett IQ Granit Standard to Circulation areas (Pic of label + install)
9bbdf38e-2d09-5a25-a63f-d7abeea506d7 | note | x 1 Picture roll label
3f3caf10-2e42-43e8-a3d9-666841949962 | checkpoint | All butterfly corners done with templet, images required?
d9bae323-ad3e-5212-9a24-88935de94022 | note | x 2 Pictures min
37f50a07-0b14-4324-94b4-d9c8f29bcaae | checkpoint | No excess glue on vinyl surface?
6b3b65fc-0b6d-516d-908d-ad807f677184 | note | x 2 Pictures min
32913e4c-b1a6-4ac7-9163-15d5585abc95 | checkpoint | All joints been welded?
8c25da94-6df1-56e9-8d73-6f6e208988b6 | note | x 2 Pictures min
682c999b-e246-4cc5-9dc2-f93344f184d6 | checkpoint | Has the floor been protected?
bddfe23e-2894-4711-83e9-89943869390c | checkpoint | Installation complete with no damage to joinery, skirtings or walls?
02a116ca-583c-57d2-88a3-fd0c82208aca | note | x 4 Pictures min
16f23165-9005-41e3-9bb1-9af95c071195 | signoff | Please signoff / request sign off
860fbb2f-d30a-4d24-ba56-3756b7c2ae72 | checklist | Concrete Moisture Test - On slab method |  | Concrete Moisture Test - On slab method
9003235c-6b24-46cd-b1ea-e31720473d62 | section | Details
87f35b13-da07-4738-93b4-55aae4e93253 | checkpoint-no-value | General Details
5e5c78f0-62e2-54d8-9d3d-926b79593173 | note | According to the NZS AS 1884:2013, the acceptable level of concrete moisture content is less than 4.4%
f7d17842-23c6-5b03-abf3-a2ad82d85246 | date | Date of test
a78e6d54-3ef7-53d4-9e50-7973d3405ec0 | textbox | Project name
5f8c2100-5d0f-4611-ae7f-e8f3cc780bb0 | checkpoint-no-value | Hygrometer device used for test
ad8b0a74-dc4a-5caf-8917-50f95035b558 | tickbox | Photo of Hygrometer device uploaded?
27e01714-38c1-4557-96bb-af9197d8e507 | checkpoint-no-value | Test 1
bd0ba87c-33a0-5064-86dc-dd2a4764d238 | textbox | Area/Location of test and result
f614c008-adc6-588b-962f-e22b41c6c12e | button | Result | Yes, No
2fc8ef39-c00d-4e72-98df-554b9e99077c | checkpoint-no-value | Test 2
1ff05fc3-52d1-5bc9-acee-ffbc988f1da4 | textbox | Area/Location of test and result
1766af32-fa26-5217-9b3e-028a3a8c5ce8 | button | Result | Yes, No
dd02c970-80de-4282-a6fc-50cb2f33facf | checkpoint-no-value | Test 3
3a3cc338-dc5c-5764-9033-56990c2884a1 | textbox | Area/Location of test and result
55fef819-72f9-5ae6-9c93-263c00f41027 | button | Result | Yes, No
68f3d6db-3b94-44bf-9ce3-ef8479e059a8 | checkpoint-no-value | Test 4
6814dedf-0a2a-5c62-9356-1a82dbd30c83 | textbox | Area/Location of test and result
f2157d2d-b587-5277-bd59-ce12014a904a | button | Result | Yes, No
db3cbf44-1da7-4282-9e16-f1a1e20430cb | checkpoint-no-value | Test 5
c9421414-c330-5ee7-986e-c7715481fd71 | textbox | Area/Location of test and result
959d4593-9de3-54fb-a04e-e67ab8e9f253 | button | Result | Yes, No
cee0eabd-2c44-4b10-b84a-2e206a0b9463 | checkpoint-no-value | Test 6
fe7205ca-4e01-50b5-bea7-4e7dd6338300 | textbox | Area/Location of test and result
f66c6470-26da-5f22-b49b-41f4583a7aa0 | button | Result | Yes, No
9314d1ca-cf32-48b2-9136-8a1286acec71 | checkpoint-no-value | Test 7
0585790f-0945-59f7-a896-370bfab3c14a | textbox | Area/Location of test and result
d7d39dc9-733f-5a48-8478-2ea1b1d1b89d | button | Result | Yes, No
991afabe-31b4-405d-a7c7-ae133c421d65 | checkpoint-no-value | Test 8
68e36d65-fe19-55e4-98f1-c5cd3363f27e | textbox | Area/Location of test and result
cb165c88-df2c-5ad8-944b-39c306de6f39 | button | Result | Yes, No
a9cd3a62-cbce-44b2-8212-067f369e73ed | checkpoint-no-value | Test 9
27223ecb-5c0d-5244-b18e-24ba5a979506 | textbox | Area/Location of test and result
d8e080dc-3b8b-526c-9b8c-9e7c6aa34e6e | button | Result | Yes, No
dd669385-f33d-4b96-94a3-22215410ec4f | checkpoint-no-value | Test 10
9596ef12-cfa3-5fd1-871c-263b66413364 | textbox | Area/Location of test and result
64243854-c0ac-554f-bd1c-a8bf719c87b8 | button | Result | Yes, No
7bce4e2e-e0aa-458f-a121-aed870653817 | checkpoint-no-value | Remarks from examinee
45b247fb-010b-5215-bcc2-0cc9750858d1 | textbox | Remarks/conclusion
ccb02e7e-e32e-4a46-89c3-945f91a3d9b5 | signoff | Click here to signoff
37884a91-0122-4d3a-aa98-5e00c0445138 | checklist | Dayworks Checklist |  | Dayworks Checklist
75283e1a-bc92-4034-bbed-5fd89ee2b8e0 | section | Details
07e3e74a-7530-409f-bf26-5fd4c9c84a8c | checkpoint | Job details
c4c7efbe-a617-544d-aed3-a1bfca83b280 | textbox | Job Number
f6f27b06-1459-5de1-be26-9ebbd8125645 | textbox | Client
9a82a3f5-d57d-591e-aaae-0f4e02dc9ea3 | textbox | Project
591f7fca-f8c3-5581-bd42-b784b211f774 | textbox | Area
287865e9-e1aa-4ef3-915e-d19662cc15d7 | checkpoint | Dayworks details
5ca0d170-111a-58dc-80c5-6d2b2c794d8b | date | Date
92e21ad7-ddb1-51b5-ad82-4573639bfc04 | textbox | Grinding
d1acd1f7-2794-59d2-80c9-413d5a8a48d2 | textbox | Start
219f8d61-ba95-58ed-89e2-4d035481c29b | textbox | End
57854816-19dd-57c0-9fee-2664a2d4ed04 | textbox | Hours
97bee9e7-719d-5904-a08c-d308fc88c127 | textbox | Men
ab65e62c-deb8-5797-8cb1-c07a6fc37de6 | textbox | Total hours
0275f669-a92c-5aa1-a315-1c22d8c03573 | textbox | Screed Compound
9e5e5f72-af57-501a-8c79-8fa62cb824b6 | textbox | QTY Bags
40f594a5-3ae8-5d8c-9052-c1c0c78a2e95 | textbox | Note
bfba12da-2fc4-417e-a5f3-cd23f985e6d8 | signoff | Please signoff / request sign off
c9b5f59a-6da0-4bd2-ae9e-4d35cd77e51c | checklist | Floor Prep |  | Floor Prep
7d6b4163-2e43-415c-9590-133d449689e9 | section | Details
8dd717d8-6687-468a-8d2b-d7d707edb2cd | checkpoint | Survey floor for flatness?
1da28a4f-9207-49aa-b9ac-c1975292b5bd | checkpoint | Moisture test done prior to installation?
601dbcfa-d621-4b0b-91a3-098eb4a3f35a | checkpoint | Surface grinded or scraped?
c5b0293b-86b1-5e15-ac59-77a0832012a7 | note | Comment
ade62f27-84dd-5af8-ad3e-56be246e31f9 | note | x 2 Picture of clean grinded or scraped floor
18496c26-671f-4e03-95b6-171f7c1b9f65 | checkpoint | Moisture barrier required? If yes, pictures required of product.
9c341db5-29c7-510a-9353-1218c00a1d2e | note | 1 x Picture
e898cf82-7d7c-4bd8-9fb4-63245291c18b | checkpoint | Follow special instructions regarding application.
5794a0db-da27-525c-aa96-643d3f39c853 | note | Pictures required per coat?
eec9fcb9-ce1d-4cec-8262-241ce30b688f | checkpoint | Coat of matrix required?
c43435bf-63fb-58a3-8736-4bc335d5d4fc | note | 2 x Pictures of product and matrix application
4b20c924-f8fe-4ea7-953f-643549f3e8df | checkpoint | Disk floor for vinyl - Picures if applicable
c2ce9561-4fe3-57ec-820a-d719a95a086f | note | 2 x pictures
6a63c607-4249-4d1f-85e5-0976bb6a348e | checkpoint | Preparation complete area clean with no damage?
d8f9b4b3-4002-54b8-9155-801a90131691 | note | 4 x images
fdafc374-7a26-4de9-aaae-046c26bf46bb | checkpoint | Is floor levelling required? - If Yes follow the steps below
4f9250c3-6376-4d0f-812f-09765615c777 | checkpoint | All areas dammed up to prevent leaks?
8c08af04-99d6-57db-9623-c8db00e7d528 | note | 2 x pictures
a3350a52-245d-4831-9a1a-f046d994d0e6 | checkpoint | At-risk surfaces protected?
5c2490c8-e19e-5f00-835d-7c55d2b6bee3 | note | 2 x pictures
7af6b4c3-05d4-45bb-8547-bfc71558c61f | checkpoint | Levels checked and ready for installation?
8af8f991-1ec2-5a18-b0f0-443139c63880 | note | 2 x pictures
bd2a34ff-59e2-4f0d-9ffa-ee2e008dd3d2 | checkpoint | Preparation complete with no damage?
91f6f719-cb6e-5389-9599-f917a38dda56 | note | 2 x pictures
be0ab3fb-f8dc-4bd6-a504-db5e5a2162e9 | signoff | Please signoff / request sign off
166f8698-e398-4493-8f04-6a9d3c41cc67 | checklist | Floor Prep Wet Room |  | Floor Prep Wet Room
5f954e96-e113-4134-a89e-635ceb412e39 | section | Details
eca788bb-495f-4353-b58e-ef8b9662685e | checkpoint-no-value | Details
19769dc6-3f33-541b-afbd-a193ce70b3c8 | date | Date
fd7eebce-1319-4720-943b-7a40a049342b | checkpoint | Surveyed floor for flatness?
c65f5c6d-d34d-4f1e-9828-f53a5122d5db | checkpoint | Clean Grind Subfloor
8457e3af-da65-5976-b11f-4d8329556f29 | note | 2 x pictures
749bc173-6965-4e1b-9719-1126d01e10ea | checkpoint | Apply First coat - 1 K Turbo moisture barrier North to South
de475001-a97a-568d-b4ed-ca934b3d3d1d | note | 2 x pictures
567c920f-2c42-4164-b182-5a0660b72410 | checkpoint | Apply Second coat - 1 K Turbo moisture barrier East to West
92924d9e-8b88-5e32-900c-ecd16a332c24 | note | 2 x pictures
5196b48f-4491-4ffd-b11c-6a4b289753d5 | checkpoint | Prime floor Eco Prim Grip Plus
da5a4f9c-5aca-57df-811a-9f16fcaa23d9 | note | 2 x pictures
5ca6bd24-a09c-4384-8e3a-c349fea2dc18 | checkpoint | Adjust falls with Novarapid if required and prime floor again with Eco prim Grip Plus
5cfcd4c3-c989-5fae-a5e1-bbffc3aa11ec | note | 2 x pictures
fc6ef8d0-a8d0-4a11-a60a-2d0ef5657e56 | checkpoint | Prime wall with Eco prim T Plus
24615c95-1112-5479-9f72-ede0d0bb3e7e | note | 2 x pictures
abc9c8bf-6d52-46b6-b1ba-f3ac6b5bf4c3 | checkpoint | Apply 2nd coat of Aquadefense
f14fcfad-7f30-5105-b40c-c00d7cf9f842 | note | 2 x pictures
c8c1942f-2c84-439a-b37a-b248f35f608d | checkpoint | Apply mapeband and 1st coat of Aquadefense
d76938a0-ab05-505a-97cd-bc63970785fc | note | 2 x pictures
3bd4ab39-6e55-48a5-b36a-b6452fa7bd24 | checkpoint | Skim floor with Planiprep SC
99323d74-3218-57bc-aa55-4bd028fe2a09 | note | 2 x pictures
6ef19dd8-ccb7-4a25-9c61-db954bba32ca | checkpoint | Skim Wall with Planiprep SC
a1510fde-70e6-59df-b3a2-ff65488ea1a8 | note | 2 x pictures
0fec628a-c603-4ecf-86ba-48923bb88e64 | checkpoint | Disk floor and wall ready for Vinyl
08a0b802-f196-5083-b58a-760f0b6bf735 | note | 2 x pictures
41c6b1be-7563-422b-8af9-5d6f8545994d | checklist | Floor Vinyl / LVT / Marmoleum |  | Floor Vinyl / LVT / Marmoleum
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
43d61985-a883-4b10-9de4-0ac4f559fcb6 | checkpoint | Substrate clean and approved for installation?
2bbdf7bb-17c2-479c-b65e-557af62999e3 | checkpoint | Moisture test done prior to installation?
20fbe978-9511-42a2-aaac-86a1f469c7c3 | checkpoint | Regupol required?
32636db8-08ec-434a-8e56-37fd0b0ede48 | checkpoint | Specify glue to use e.g 68T, UZ2000 or Marmoleum glue.
d712c35b-8c98-59a0-9edb-cbda7902dc76 | note | 1 x picture
128de718-0a99-4d8d-a02c-e1bb1702185f | checkpoint | Doors to be removed?
93c0a07b-5206-4867-8bb7-894a4b5e564f | checkpoint | All capping installed?
c7a8ffa8-df06-46c7-a116-fc817e263eee | checkpoint | All butterfly corners done with templet, images required?
ebb87792-62a9-523a-9bd2-65aa9f669ee1 | note | 4 x pictures
0a058ef6-6a21-454f-8a0b-51d1f24b1f41 | checkpoint | All areas welded?
1adf9530-205e-56f4-a7a0-3b59c2a081c6 | note | pictures of welds
6636affc-327f-4faf-859b-3b15dc4fd571 | checkpoint | No excess glue on vinyl surface?
9157055f-5284-5008-8443-54bec533ba8e | note | 2 x pictures
d8c3823a-bd37-481b-acb4-7a5b91bb3335 | checkpoint | All transition trims installed?
27751344-eaec-406e-99b2-5938e9daa053 | checkpoint | Area dust free and all rubbish removed?
e4ab812a-debe-47ee-9a83-0c256b20076e | checkpoint | Has the floor been protected?
b0acdf5e-c3ca-4230-9c2d-52c3f174dcb7 | checkpoint | Installation complete with no damage to joinery, skirtings or walls?
8a81cb28-17a9-5192-8ddc-c47f9dd7b40f | note | 4 x pictures
2c908600-974e-496c-8728-bd2daba48e7e | signoff | Please signoff / request sign off
ca957595-1744-44d0-89b1-d4e5a8653557 | checklist | GB Carpet Installation |  | GB Carpet Installation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
104c6c79-6ef6-4207-ad76-4921895e7537 | checkpoint | Substrate clean and approved for installation?
b7f4d298-ca22-5bed-a03c-15423c2d0b95 | note | x 2 Picture
aea26cc9-88e3-4c32-9913-68b15925364f | checkpoint | Are sills, door frames & tiles flush with carpet?
d06c5aa1-be16-5b2b-bc8c-9c366496221f | note | x 2 Pictures min
9334821a-44fe-4952-83e1-a279e2013722 | checkpoint | Doors to be removed? Take pictures before and after (proof no damage)
80feb8cf-9114-58c0-99c4-c40575638dc6 | note | x 2 Pictures min
5a823e54-ce0d-4c6b-87cf-d24d5a70f5a4 | checkpoint | Confirm plan matches site and joins ok?
0d143c03-5f01-4484-931d-1c510b5dca7b | checkpoint | Review job sheet confirm all detail matches e.g. colour of carpet, underlay required?
6fcc43b5-497f-43f4-83fc-3138a425723c | checkpoint | Take photo of carpet joins?
8756c997-6f01-528e-8068-5e7c2300d4bf | note | x 2 Pictures min
39e3369f-5a8a-4109-a202-a1d0d55bda43 | checkpoint | No damage to skirtings or walls?
bf2de8f1-a69e-53e0-a97e-2f176cf49872 | note | x 4 Pictures min
184be89b-426d-4bcc-927b-edf5e99f533d | checkpoint | Doors replaced and area left clean of offcuts and rubbish? Take pictures before and after (proof no damage)
843b9439-3162-55ea-8590-a4ee171795d0 | note | x 2 Pictures min
01fb33d0-6af0-40ff-9f50-064d737686e5 | checkpoint | Walked all areas, pins tapped down, stairs tight, no carpet lifting, all ok?
f2d6fe13-baf6-53c2-925c-e52152f23706 | note | x 2 Pictures min
af4389d3-a313-4750-b5e7-9327d17d220e | signoff | Please signoff / request sign off
9cf7f0af-2886-4fac-86ad-1e269667eca8 | checklist | GB Laminate |  | GB Laminate
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
94a87883-d0b4-416b-86d6-91ee6ff41f43 | checkpoint | Area clear of rubbish and tradespeople?
f6c766aa-e71a-57eb-a69f-325544498779 | note | x1 Picture
0e2d20f3-86e7-40f3-9681-784f9905a1b6 | checkpoint | Survey floor, More than 3 bags and 3 hours grinding? If yes, notify the office with images & scope and wait for approval.
4f4dd623-12e3-56c0-b5d2-f98e025bc435 | note | x1 Picture
942051eb-0ae5-4403-b768-9f3c3ffcf03b | checkpoint | Direction of planks shown on plan?
fddd37e0-60f0-4b70-9d9b-1d0a301b272b | checkpoint | Review job sheet confirm all detail matches e.g. colour of planks, underlay.
9cf4d2a2-ec81-4951-bd40-2b0af0fb2a70 | checkpoint | At-risk surfaces protected?
0519e2b5-a389-5479-8044-479c0b498e39 | note | x1 Picture
5a69f3f9-d386-45b4-a76d-b873af0db436 | checkpoint | Installation complete with no damage?
f0a2de87-ec08-5f3c-b0cd-0a1fe51e3553 | note | x4 Picture
b201e65d-2b76-4561-8f54-282c3dbeee53 | checkpoint | Walked area and checked for gapping, bouncing, expansion etc?
de9264ef-59e9-424b-bb38-e39c21c4dd0d | checkpoint | Opened boxes left on site and unopened returned?
c6f485d0-f9d2-4681-b1e0-ad20204ed3fd | signoff | Please signoff / request sign off
dd5dd230-8739-442e-bed2-110e773a9831 | checklist | GB Timber Installation |  | GB Timber Installation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
adaa47ab-c84f-40ed-b4aa-6a190ad276e8 | checkpoint | Moisture test done prior to installation?
e2a4a4d7-e70d-5634-adca-e653c8b5efa0 | note | x2 Picture
2ddbec60-61e1-43cf-aef5-8baf979fe34e | checkpoint | Floor prep assessed and deviation less than 3mm over 3m?
279ce6b3-30fb-4f17-8cbf-a4e4730f82c2 | checkpoint | Review job sheet confirm all detail matches e.g. colour of timber etc
d077f7a2-5d12-4915-a0d0-d1b89e592ee0 | checkpoint | Timber direction confirmed on plan?
5e56e8b3-1a3f-4697-8a75-d28434345961 | checkpoint | Bags and hours grinding signed off by FJ office before starting?
b4a49c35-557e-4e8e-b03d-fa3a5e1e1f93 | checkpoint | Timber weighted down after installation?
cbd50b8d-69b4-5740-9808-754fcfadc896 | note | x 2 Picture
031f5266-8a4d-42d7-94bd-ae093981f757 | checkpoint | All transition trims installed?
befb9013-016b-5e9c-a6e0-967c46324bed | note | x 1 Picture min
3db32861-26e2-4f41-a50a-9a1ff4b6f8e6 | checkpoint | Area dust free and all rubbish removed?
3ea2cb1c-7ccd-55fc-adc7-6a5e2ccca4c3 | note | x 2 Picture
8d0bd533-966e-40ed-b97b-7bf0c0fd3fb9 | checkpoint | Installation complete with no damage?
50d7ba69-05ea-5fe1-a5e8-d3f447c4a285 | note | x 2 Pictures min
9fc0cd20-173f-484e-8892-d6102f0c9d81 | checkpoint | Walked area, all ok no gapping or damage?
5cfe2799-7d48-5108-9008-2f7d4869ce0c | note | x 2 Pictures min
3bcd19a5-52db-4dab-8540-a1ec3a6e2824 | checkpoint | FJ Office advised of all left over materials?
5b331dc3-273e-4362-8735-9dc4d9120e6b | signoff | Please signoff / request sign off
e45071bb-c3cb-4b78-b27e-3b60297a6bcb | checklist | GB Vinyl Plank |  | GB Vinyl Plank
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f42ddf72-1e89-4872-8298-1dd3b6600a86 | checkpoint | Survey floor for flatness?
45bbfcaa-847c-4d12-9070-a7a615602f6f | checkpoint | Area clear of rubbish and debris?
0ca9ad6e-1cd7-4673-8532-648424cc4a91 | checkpoint | Planks have been on site and are acclimated?
dabae465-82b1-442c-89cf-ee0ab900c051 | checkpoint | Direction of planks shown on plan?
ecacde7f-b087-44bb-8dd2-937fcf1e507c | checkpoint | More than standard prep required? If yes, notify FJ Office with images and scope, wait for approval
6426e4d4-1354-48a4-a0f3-a5622ad3de0a | checkpoint | Moisture test done prior to installation?
ddac3fb9-9591-55e1-8272-283201905149 | note | x 2 Picture
9040d800-b465-4404-8327-c76246fc2c0c | checkpoint | Windows with direct sunlight blocked
157f24e9-dae9-5c2d-b383-54a8c61ed826 | note | x 2 Picture
c615fb47-8407-4e01-a8fc-9440d3160a96 | checkpoint | 68T used 1.5m from splashzone (sink etc)
45b9e40b-3882-4f09-a6ed-09465ba2643e | checkpoint | At-risk surfaces protected?
9fbd76fd-8e0d-5bd8-8118-746b9f7c2568 | note | x 2 Picture
7298424d-94a4-4e3c-91dd-b6645e6ceeb5 | checkpoint | Installation complete with no damage?
9c0ba7b0-f38f-591d-931f-006666bf04b3 | note | x 2 Pictures min
916e648b-735f-413c-ae0f-7516cd20599b | checkpoint | Walked all areas, checked for gapping, lifting, excess glue on boards and skirtings and all ok?
88db7a7a-4f26-4a6d-824f-a6c700473d9d | checkpoint | Opened boxes left on site and unopened returned?
d20e4780-0dd5-4350-bba9-fd5133dcd5cf | signoff | Please signoff / request sign off
4a92713b-0eaf-47df-906d-936af886f096 | checklist | Incident Report |  | Incident Report
792253bc-0164-41d0-9306-673729a34d94 | section | Details
0a75f3de-cc8c-41ce-81d5-2f62ec32417e | checkpoint-no-value | Project name or location
e7b7ae65-b8c9-5840-a4f8-72e507ce6bbc | textbox
74a29dcc-dae1-48a9-9b74-755db4f231aa | checkpoint-no-value | Date & Time of Incident
a5989674-c730-5448-9764-08a45cb19d36 | textbox | Date & Time
291a8f41-9221-421d-aebc-9ac992bf82e0 | checkpoint-no-value | Reported by
7ae33c49-e047-5ccc-a0d1-f022ad8220c2 | textbox | Name & Surname
67151643-8c1c-4a11-ace3-00c08c0e4a0f | checkpoint-no-value | Reported to
537ba48a-573b-504e-bde6-2346a1950b53 | textbox | Name & Surname
9013dd3a-ee03-49ed-b7c1-45546fda5956 | checkpoint-no-value | Incident Type
143d93d6-57a5-538d-b361-588650666f0b | textbox
26347d64-c24d-5761-8bac-1385dca84291 | note | Add Picture
815c292b-ab8c-442b-99e7-1c014d2af97c | checkpoint-no-value | Details of incident (Injuries)
ca940a3e-9ee5-4e2b-aeb4-4fc9f9f8b9b0 | checkpoint-no-value | Person involved
61e7a1ad-af1d-5139-ac6b-07294d95d4f0 | textbox | Name & Surname
c64c9e91-3c69-5ad2-a8bf-950b08a34456 | textbox | Contact details
432614fb-4c6f-435b-bc10-28afaa9513ea | checkpoint-no-value | Details of witness
de3bad08-cdc7-582c-be5e-3d2b41c88d42 | textbox | Name & Surname
ff181cb8-9a9a-58f7-9972-48b2a1092e3e | textbox | Contact details
3e753542-1c05-4815-9163-695f85deb493 | checkpoint-no-value | Manager Remarks - Actions and Follow up
12296c23-4036-555d-9e6e-9c7b954587da | textbox
5741ef4b-933e-40dd-9eed-0fe6616afdd4 | signoff | Review and signoff by Supervisor / Manager
c386ad40-607d-45f6-91d0-73a88a91b681 | checklist | Les Mills Rubber |  | Les Mills Rubber
f1a15b52-a31f-49e5-806c-e5e71479d13a | section | Details
d3f67951-6867-44a7-80b5-e7652414e26b | checkpoint | Uplift Carpet tiles
0f402091-ba34-5846-9b55-31e5a3b5a6a5 | note | x2 Picture
305aecbc-c65d-4a6e-be76-1551123cc0b9 | checkpoint | Clean grind subfloor
876f62cc-ef33-5975-a9a2-ed8bbba264ba | note | x4 Picture
1176ded2-2849-4fdb-a93c-7f8a3a86124b | checkpoint | Once installed grind Ply board edges and skim where required
35b8425b-ec56-544f-ad30-3faeb5d2b4ad | note | x4 Picture
a929f884-ebe1-4dba-98fa-d8c0f2f52436 | checkpoint | Correct Glue - Uzin 2000S
183ceba9-10dc-564a-9ad6-c3f36e57bccd | note | x4 Picture
e4c4187c-ea59-4e3d-82f0-3571ddcc97c4 | checkpoint | Install 4 mm rubber (UPSIDE DOWN)
e2a56c7d-e3e4-5ce7-b72d-935c517f6ac8 | note | x4 Picture
fa0d84b9-5dd9-41a4-83c5-db9129cd23b2 | checkpoint | Roll Rubber once installed
ca90c279-5390-5c02-b0bf-a63cf6943fc3 | note | x4 Picture
02f2fda7-aeb0-4b87-b64a-25804907da4d | checkpoint | Transition between other floor covering levels
62328630-ba19-5878-95e9-10f85ce7c541 | note | x4 Picture
d6842f6f-f35e-45a9-8ca0-a68329c6d956 | checkpoint | Phase completed with no damage ?
673528ea-a451-5e53-91b2-520fc0213879 | note | x4 Picture
b26e678e-a445-4cc8-b92f-3670ffe39841 | signoff | Please signoff / request sign off
93f8cc83-c607-4453-a987-a9ebbc151f83 | checklist | Moisture Test |  | Moisture Test
aad4edb6-183a-4782-8589-dfe682de2a04 | section | Details
e7941f5f-9f59-4174-b470-497e80eb2dd5 | checkpoint | Moisture test to be done
be723883-f742-5426-b507-f7649d941a1b | note | Comment
06d059ca-89cf-52a4-8df5-df3bf91a311e | note | Capture images of readings
6f34288e-3256-4073-9748-dcafdaf1b85c | checklist | Notes & Special Instructions |  | Notes & Special Instructions
b5a852be-25fc-46d4-9342-40f3aa7e2b92 | section | Details
8a2facd2-bcf6-4713-a14c-aca55ada8396 | checkpoint | Project specific notes & special instructions
1a0989fc-4f21-5380-860e-08f95fd104c5 | textbox | 1
c08ac1d6-9270-5333-a8d7-698556559e79 | textbox | 2
6bf9c636-4072-577e-9327-7d7a6c0c8a69 | textbox | 3
28bdb991-e89a-5352-ae98-0e110926defc | textbox | 4
58ca9aa3-1e91-548c-adbd-f93bf46d0870 | textbox | 5
057df34f-cabb-47f2-93a5-5ce4949b1a3e | checklist | Rubber |  | Rubber
2731c6b6-c8c1-4d2a-b888-147f41593775 | section | Details
cc90fa5e-3ad5-42d0-9332-6704d340bee4 | checkpoint | Dry Lay rubber to climatise.
6d35c4f8-db01-5b30-a3c6-4a83cf2e4294 | note | x4 Picture
b3f194b2-067a-485a-aefd-8cb6ac1a71cc | checkpoint | Correct Glue - Example Uzin 2000S / Regupol one Polyurethane
1661490f-beef-5542-bb42-88325f8dd407 | note | x1 Picture
d3cce33e-13c2-4477-8a8e-11cb886255d9 | checkpoint | Install 4 mm rubber
76476b38-5205-52c5-a34c-3efb6955df87 | note | x4 Picture
d3af9d1b-0049-44c9-844e-96daa49038b1 | checkpoint | Roll Rubber once installed
620c04b2-b492-5475-a203-53d355694f07 | note | x4 Picture
42acb262-db39-46c6-80fb-d1bd421bbc37 | checkpoint | Transition between other floor covering levels
aa637823-ac04-50ac-95d5-1801f440f9c5 | note | x4 Picture
d7dc2762-df7b-4c89-b9b8-7505b3ce50f9 | checkpoint | Phase completed with no damage ?
4cd0d92a-4cd9-525f-94cd-f3584d7c646e | note | x4 Picture
fe19ea64-3c6f-43e4-8fe2-bff06e31e62a | signoff | Please signoff / request sign off
0359e19d-9ebf-4beb-816e-a1d17c235ebb | checklist | Simplicity - Balcony |  | Simplicity - Balcony
1984a948-e254-4a71-9f5b-55c515a77236 | section | Details
728a1fdf-6eb8-4a2e-b53d-518c31a01ef6 | checkpoint | Details
d383befc-8b48-5d63-9402-8a00f35648bd | textbox | Block Number
2ff9d3d1-58cb-5e74-aa6f-bfe21b30f23b | textbox | Level Number
851f45da-e9fa-5042-91ad-221aeee0477f | textbox | Unit Number
6d1e0bd8-c4a1-48e3-9486-ec3ff7116865 | checkpoint | Clean Grind - 30 DISK
81b7ad5c-e643-593d-bc3e-e23d07683d16 | note | x 1 Picture
7975969c-6b06-45ea-8222-7b6b1fa366e7 | checkpoint | Dremel tool in corners and below ranch slider
1827d91a-fb21-56bb-b0cb-28cf4b18267f | note | x 1 Picture
e4a7c1a9-c6ef-441c-b564-1257e141fb42 | checkpoint | Polish Grind - 80 DISK
26407ccd-dd6d-582b-a9b0-03c08a645b51 | note | x 1 Picture
04f83a6b-c50c-42ed-895a-99df6e34085b | checklist | Simplicity - Bathroom per unit |  | Simplicity - Bathroom per unit
b4c33d22-ba6d-49a2-98bc-a47eb5b3a7fd | section | Details
bce61f49-7292-4168-b9a2-6d2e53d73f06 | checkpoint | Details
5800ac9e-32e9-598c-85c0-eab8e3c34739 | textbox | Block Number
693d1d95-fc14-5ad1-adb8-ea8e7f234ff2 | textbox | Level Number
b3261953-4109-5c8d-9640-c11c04e8c8b9 | textbox | Unit Number
cffd9c3a-38b7-4374-87f8-0e3749e5dae9 | checkpoint | Clean Grind
1a6c92ab-50c4-5ea9-8b73-155c6a9114f5 | note | x 1 Picture
1e5147dc-5f7b-4b24-8e8c-689e31d591b4 | checkpoint | MAPEI AQUA DEFENCE 1st Coat
16a41cbb-4b56-5697-9a3a-e3b9e89099ac | note | x 1 Picture
eabae515-2e78-470f-93a6-d6f3b85e74d8 | checkpoint | MAPEI AQUA DEFENCE 2nd Coat
b08c70b0-5018-5119-b18d-819508238643 | note | x 1 Picture
b49402e1-0d6e-41bd-bddf-482e498d0733 | checkpoint | Mapei band easi 400x400 waterproof membrane
f226c8dc-06cf-5b88-aa0a-ea70b4a0e65b | note | x 1 Picture
019b0409-d5cb-4cbe-a2cc-0c0167be336f | checkpoint | Apply Mapei Eco prim-T primer
92c2ce0c-4a31-5751-ab37-b072865440f5 | note | x 1 Picture
47f22508-cf97-4737-9dc0-b373b45418eb | checkpoint | Apply smoothing screed compound
4638b2c0-fe69-51e8-a03d-761c478a3e61 | note | x 1 Picture
9554c122-7f16-4112-ad01-7ab814bc9afc | checkpoint | 2mm Rubber underlay 1st floor and up only
7ab4bc02-df7b-47d1-a405-274942772f34 | checklist | Simplicity - Carpet |  | Simplicity - Carpet
9ade2120-dfa5-4a0a-8819-db4d55010b8b | section | Details
cbf1fba4-d7cb-4f79-a54f-3d6ea48f29b5 | checkpoint | Details
5e101ef3-cc14-578e-9077-6404d81d33b4 | textbox | Block Number
17bcf941-0bd4-556d-b6c5-1afdf4517aee | textbox | Level Number
b4e9eeb2-6dd0-5867-ad8f-65d1afc61028 | textbox | Unit Number
74883462-cc93-5c55-83b6-c6ddb6244fe8 | textbox | Range and colour fitted
78ff95a7-831b-5614-a27f-bb0d5194478a | note | x 1 Picture
0ce02bf3-88ce-4203-a2a8-8aebbc9a3fad | checkpoint | Underlay install
2285d62b-7162-5ed5-ad16-27a92605a2b0 | note | x 1 Picture
b6e213fa-16dd-4958-8f31-482e280d9ad6 | checkpoint | Door transition trim between vinyl and carpet
8a7f681e-5506-5b52-83c7-67f7fb4a0f51 | note | x 1 Picture
54d206a6-4275-4a3f-9a17-b08813988269 | checkpoint | Assure grippers are pushed down with bolster!
3b21f248-700f-5fb8-b5b0-84856491e171 | note | x 1 Picture
00a3a50f-203d-4e31-a072-4c6bb9832b65 | checkpoint | Completed carpet install
c5f0f425-ad11-56ea-817f-ee1b262c322b | note | x 4 Pictures
915c15a2-147d-4940-845b-caa1fbc6b504 | checklist | Simplicity - First floors and up units |  | Simplicity - First floors and up units
8b1c5340-6c5f-418f-8d9a-1987e696b496 | section | Details
b5691315-daca-4337-8369-ac7e69fc2fe3 | checkpoint | Details
f0dc14da-3c41-5ef6-823b-c861ce5ff0d6 | textbox | Block Number
97d1f63a-97df-5acd-a589-d0d2d077dca8 | textbox | Level Number
75b81db4-f384-5138-a440-c3e84b2acc36 | textbox | Unit Number
72f200fd-a1dc-4cde-bad5-d31b31437301 | checkpoint | Clean Grind subfloor
cd298a6c-6d82-5d55-9fce-95bd14a07ee4 | note | x 1 Picture
7352dcc7-ec86-4694-b968-40bd9b73aa25 | checkpoint | Fine finish screed preparation
fa98db1d-6f26-5b53-a009-d471b61dffa0 | note | x 1 Picture
19f27421-c698-47a3-8cb3-139ceffe8239 | checkpoint | Ramp at ranch sliders
6fd85957-0cc9-555a-a24f-63adff7c7d9d | note | x 1 Picture
2f5fb98e-9274-44d7-8025-5da1bb3093b8 | checkpoint | Polyvac prior vinyl
6c7376b9-089e-5e11-8ddc-d0dd6064911b | note | x 1 Picture
482a1d72-a37e-49ef-9fd1-1b193137b2f5 | checkpoint | Undercut bathroom door frame for LVT
3e957214-38f8-56ba-89d1-a7e6e5ec6772 | note | x 1 Picture
20b2ca13-5af1-428d-9876-e3860f086da2 | checkpoint | Bathroom vinyl adhesive 68T
6088a4a1-008e-5996-b140-498be09a8269 | note | x 1 Picture
a476ac76-9e4f-4133-af85-d39efe82450b | checkpoint | Completed vinyl plank install to bathroom
64c59968-84c0-520c-83fb-5b4b52017eb2 | note | x 1 Picture
9b513515-4e9a-45be-8f8b-db0825462a3f | checkpoint | Fit regupol underlay prior vinyl with KE2000 (Sub supply)
472c2da8-ecf2-5e2b-8467-d8b77c2dc416 | note | x 1 Picture
43712f73-d763-480f-9349-699afb739414 | checkpoint | LVT neatly but up against skirting
86bfab99-56ce-5226-817e-74e050201320 | note | x 1 Picture
2f8b5212-1dce-48db-a2a7-1c31921fde2a | checkpoint | Vinyl plank completed installation pictures
7c93710a-30b4-5a52-a617-7a36ddffa3a9 | note | x 2 Pictures
3c97eec6-4380-4872-ac9e-8255161c107d | checkpoint | Received and installed drain waste
d3934354-5dcc-52d0-9ae2-1575c5919269 | note | x 1 Picture
9a44e6a2-f904-4b16-b7f7-b7d169dd7ca8 | checklist | Simplicity - Ground floor units |  | Simplicity - Ground floor units
526cdd6e-5d9e-4c6a-9de5-814c695dec27 | section | Details
c12030fe-3f82-41a1-adcf-1a5f2c96c4c7 | checkpoint | Details
5a9facf2-ea51-5164-94f6-79d8c27e8a64 | textbox | Block Number
4a8ac0b6-0328-5628-93df-0901559b1257 | textbox | Level Number
61c9fca4-73ee-5471-b3e8-95bf4734ff1a | textbox | Unit Number
e6879b82-0e61-4276-9b26-e968c0511295 | checkpoint | Moisture check
0020e72c-7da7-5e4e-aead-429e03409c1e | note | x 2 Pictures
edc6ba2b-af42-41ce-9ca7-7ad34d0d00ec | checkpoint | Clean Grind subfloor
421ae55d-7ee4-5a06-ac91-63148fb13de9 | note | x 1 Picture
5e261582-f3fc-4401-9e05-db9e677556f8 | checkpoint | Fine finish screed preparation
3807ec2a-f6bb-5793-aac7-79266154982c | note | x 1 Picture
01b6388b-8ca8-49a2-8ee8-ea4084d4d355 | checkpoint | Ramp at ranch sliders
7c0d70da-a31e-55ab-84bd-7f2bd1899fb9 | note | x 1 Picture
05ab5237-f972-4b28-898a-6d23d29e0b57 | checkpoint | Polyvac prior vinyl
397bbed3-77cc-579e-9b58-672c6f6ad439 | note | x 1 Picture
5cc92f02-167e-478a-baac-2646ee9af739 | checkpoint | Undercut bathroom door frame for LVT
b4f9231a-71e8-5db1-b205-0873547e3a40 | note | x 1 Picture
81e1eac3-6b2f-4453-86b9-d799f03fbce7 | checkpoint | Bathroom vinyl adhesive 68T
ebb7845c-7590-5c78-949d-8b7fa70ecaae | note | x 1 Picture
7989f48f-75c1-4bef-aabd-47ded4e7dd1c | checkpoint | Completed vinyl plank install to bathroom
13672ebb-217c-5a44-b51f-7f2707843a65 | note | x 1 Picture
1a17e3f0-fe19-4d1e-b6b2-188374a2fa27 | checkpoint | LVT neatly but up against skirting
7bce5633-b743-5491-8d1b-2eac21ac70d8 | note | x 1 Picture
bd4fe612-982a-47fc-8c31-f2734abf9e66 | checkpoint | Vinyl plank completed installation pictures
1174e986-a7a6-58b9-983f-476fbc93bf3b | note | x 2 Pictures
b6961822-702f-4990-810f-026bb9a4d3f0 | checkpoint | Received and installed drain waste
9e1861d8-7ef7-510e-93c6-1195dce1c81d | note | x 1 Picture
4f15700f-6ff7-45b9-a7d1-3ff240d9cd89 | checklist | Simplicity - Staircase |  | Simplicity - Staircase
cb789350-cfa1-439d-a647-2db0cc0b2591 | section | Details
fde05bd9-897a-4f95-becf-13b4f119d652 | checkpoint | Details
9c2aff1a-7114-5fa2-8ce3-257ca5d2bd09 | textbox | Block Number
12167b6b-f41b-40ab-8420-1af5543497f2 | checkpoint | Staircase Number
1d21dd2b-34ae-41a0-829f-a77b3ae6a3bb | checkpoint | Sand and prep
5c5f20b8-e604-4e48-9ae4-5b3ec67b7642 | checkpoint | Prep fill next to staircase on ground slab dirt trap
16f39236-017e-59f7-a5de-80b2bf6a42ad | note | x 1 Picture
9dc6c8ee-3165-5def-8954-bcce3ad8c99c | textbox | Screed bag count
d9cd9719-5fa7-4dde-a740-b0a3dd824123 | signoff | Client Signature
192f959d-36f0-4fe9-b8da-098a54d639ca | checkpoint | Fit approved nosing and insert
a01a664a-909a-5229-be6c-b22deb01d4dd | note | x 4 Pictures
c8710bbe-aa3b-4cad-b46d-69d2ed2e7af2 | checkpoint | Fit vinyl sheeting adhesive 68T
b86662b2-c0c3-5864-b942-e585042be87d | note | x 1 Picture
9c806a1f-46cb-4d47-a148-77237752270e | checkpoint | Completed vinyl installation
d60e4ed1-5389-550e-9979-d357e3d24757 | note | x 4 Pictures
eeafb5a0-2f06-4646-b415-1a55bbeeda4c | checklist | Timber Installation |  | Timber Installation
31e640b7-9605-4f56-9492-e70e742645ba | section | Details
3cd1b770-6f30-4afb-9fa9-11d408ffc963 | checkpoint | Moisture test done prior to installation?
c640d4be-7604-4e93-b5a6-af7d53acf992 | checkpoint | Floor prep assessed and deviation less than 3mm over 3m?
8437714f-ae91-4918-b5dc-cbc23d75e912 | checkpoint | Regupol required?
9c20e43e-bcf0-4a1c-b019-8156c82f93bb | checkpoint | If applicable correct Glue and notch trowel used fo runderlay?
a6c89e07-2d01-586f-a1e2-95c5cfd38ab3 | note | 2 x picture
933628bc-50cd-49f4-b6d2-382f973c1126 | checkpoint | If applicable underlay installed and rolled?
2a27f8cb-6866-5d31-b54e-fed73e84a870 | note | 2 x picture
b86916b2-b779-4acf-ad31-3021a46df3d6 | checkpoint | Timber direction been approved?
6f39d59e-76a0-494d-8023-1443559d4a08 | checkpoint | Undercut doors and joinery?
9bb7857f-e5da-5f80-bced-c800c07a6365 | note | No damaged due to undercut?
abe4944d-6bac-5f55-9982-5f59ab95cf05 | note | 2 x picture min
57b80ff9-d4a7-4fd2-9964-a381c7f5f4bf | checkpoint | Correct Glue and notch trowel used for timber?
a62d2338-7861-5a36-a4ec-5f740d3d2353 | note | 2 x picture min
8067831e-70e6-4a17-99d5-00127b823f92 | checkpoint | Expansion gaps as per installation manual?
c2aa8397-80ea-433d-bb16-dc863423de87 | checkpoint | Timber weighted down during installation?
cbaf0c17-fc34-54d4-b354-f48f6d121434 | note | 2 x picture min
8d0947fe-03ac-41da-8e3a-2998df488f58 | checkpoint | All transition trims installed?
7b3e991a-e6df-5bc2-b597-fa674cc4eb8e | note | pictures required
087a3570-5f79-4526-b48c-ee3da0c520b0 | checkpoint | Area dust free and all rubbish removed?
570dfd05-63d5-4b20-8b3e-30300d878739 | checkpoint | No damage to joinery, skirtings or walls?
dc10ff14-d299-484b-9e7f-c4e30c7f9ee2 | checkpoint | Has the floor been protected?
b84b0af1-7201-4e7c-a5b9-836a57c5671f | checkpoint | Installation complete with no damage?
067bcf13-e829-5238-821a-fdd29fce2a00 | note | 4 x pictures min
92113c53-bb3c-4229-9f70-05ebba4dec27 | signoff | Please signoff / request sign off
ff859ab3-545e-45df-a830-0a8ce617ad42 | checklist | Toolbox Talk - Site-Specific |  | Toolbox Talk - Site-Specific
bf139301-70b2-416e-b4d9-a762278fb56d | section | Details
1723d09a-cd3b-4633-8f42-d818d1841b6a | checkpoint-no-value | General Details
be8040ee-a275-54f4-832f-11ca13906fa9 | textbox | Project name or location
a05b8ac5-747f-5e97-8425-8abd7b2daac9 | date | Conducted on Date
a65d6059-f581-5f14-92e5-06cefe9af6d9 | textbox | Who is running this meeting?
71798922-47e8-45b5-848f-a738ad066bf1 | checkpoint-no-value | Toolbox Topic
f3d71109-4c97-530f-b9c6-eb123d168631 | textbox | Description
68a76635-ee9a-5215-9fa5-62dd3e167e66 | textbox | Actions
57aeb46f-19b6-4d1c-8c39-785a19e224a8 | checkpoint-no-value | Issues raised from site?
be5a4323-b991-5bed-a004-105e8055188e | textbox | Description
b86ec3ba-c718-501e-a168-29ca34f13420 | textbox | Actions
d6bf0442-91ee-4e48-9d4c-e9ecaa27d968 | checkpoint-no-value | Employee raised issues?
86d39b9b-8016-54d0-aa25-4a45de49baa4 | textbox | Description
8a27c469-ca81-5c0f-b1ef-097f1cf82e7b | textbox | Actions
23df1e1a-5b2d-466d-a3bb-7e6f06543c14 | checkpoint-no-value | Incident or Injuries
25a52d41-d1b1-5f3e-9372-4ac7e134eb23 | button | Any Incident or Injuries to report | Yes, No
3253d100-3300-561b-a7b4-39ca6239514f | textbox | Description
8d344b37-6b67-5142-b324-86cf1b236317 | textbox | Actions
560c766c-a59a-4028-9cc0-d9f26b67334c | checkpoint-no-value | Hazards
c8f509e1-866d-532d-b1fa-27189cf13c8d | button | Any Hazards to report (Dangerous activity or condition) | Yes, No
568acc2d-fc55-5466-b9de-b27d883951ca | textbox | Description
06f671dd-67bc-5c19-bf5c-78f8fe1e4afc | textbox | Reported to
15ca8c38-6528-4e87-b5bf-5325ca4b5911 | checkpoint-no-value | Risks
8b3f082f-a0fa-5291-aa00-7d1184fe7268 | button | Any Risk to report (Possibility of something bad happening) | Yes, No
4496d1d7-6e40-553b-9e3c-e1a6fa804ea1 | textbox | Description
d252dbf8-5357-5125-8b70-694d17cad160 | textbox | Reported to
512bd35d-8f69-4a8d-b14b-7119524503ed | checkpoint | PPE - Personal Protective Equipment - Correct and in good condition ?
be5634a4-964e-5f13-a821-fc29c435db8d | tickbox | Inspected
f45fc4ca-5fc0-47eb-97cc-688614e6bd2a | checkpoint | Positive safe-action observations
1acb02a7-2989-5da3-95a2-01c265d68c98 | textbox | Observations
2625a95d-4c1f-48a9-bf34-1a1f58c800de | checkpoint | Attendance Record
324d6585-4c7e-41d7-a472-be1bb57f3d8e | signoff | Each attendee to click here to signoff
f7a98f6a-ad4f-4372-a1ec-f526ec6c8c87 | checkpoint | Supervisor / Manager remarks and signoff
4f70840d-af71-54d8-9f52-bca9ab1cf144 | textbox | Manager's remarks
2c802889-47bf-46e8-ad9d-a62c8350d0d9 | signoff | Review and signoff by Supervisor / Manager
31c2543d-a747-434e-87d5-8475abc6ec6c | checklist | Vehicle Incident Report |  | Vehicle Incident Report
c61633e3-5748-49eb-8109-e2f607f0c1b4 | section | Details
adc45638-0a11-4372-b855-c7bb1b201850 | checkpoint-no-value | Details
a08f68a3-f255-5775-897f-b9667eacceb3 | date | Date
8e315f55-5df9-53c6-8877-b4723e844c3c | textbox | Time
f2cf6de5-0d90-4428-b169-fa72c5b84fe2 | checkpoint-no-value | Reported by
00c89730-deca-518b-9060-f7a7aa04f51e | textbox | Name and Surname
fa6ea552-4050-4196-b5d0-bf7d74c33445 | checkpoint-no-value | Driver details
3edbf9f4-0569-5ece-b5f8-55e24776869e | textbox | Name & Surname
39d5c62a-2d75-4d45-a809-4f5893a0a056 | checkpoint-no-value | Vehicle Registration Number
336b2802-e837-5d14-98e4-c17772b8770f | textbox
917580f8-665a-4f4e-a603-224aae7c95a5 | checkpoint-no-value | Details of incident
19f3332c-8d12-5f14-9346-21b3aa953ad2 | textbox | (Please describe)
68576813-f526-56e8-86af-6b97de5ca537 | note | Add Pictures of vehicle and area
3ac0cc6d-e729-41ea-9d0c-1152b8689e4b | checkpoint-no-value | Was there a 3rd Party involved?
4ac0ce91-fa72-5a75-9094-02dfd37b839f | textbox
e72b51ed-793b-452d-8f57-00389efad397 | checkpoint-no-value | 3rd party or Person involved
a5145385-ee95-5fe6-8280-d07939b839bf | textbox | Name & Surname
a3bc867b-1028-4b17-8bd9-d48b56e26b38 | checkpoint-no-value | 3rd Party Contact details
b23f2c48-3215-55db-9cf2-2b1a1bf10dac | textbox
178028a4-141c-5954-b730-f156d5b5cdfd | note | Take picture 3rd Party drivers Licence
809d6f2b-5a6d-5b49-b011-8e1377694628 | note | (Front and Back)
0aeadd60-a750-530a-a4ce-6332914b6ea5 | note | Pictures of 3rd party vehicle registration plate
fc7addb9-ee12-5935-934b-6a6435dafa5b | note | Pictures of 3rd party vehicle rego details
700c154b-946b-4df9-bc3b-31c693170d54 | signoff | Review and signoff by Supervisor / Manager
23666fdb-a3a8-42fa-ac0f-a9013df2091d | checklist | Vehicle Inspection |  | Vehicle Inspection
59e2fc52-c623-4c67-bdab-8e0b0dcb1323 | section | Details
37be471d-361e-4ba6-aff4-27ea4504e5db | checkpoint | Date - Capture text
14ce378a-e188-4620-8286-60a65dcac1b7 | checkpoint | Driver - Capture text
722514ae-a1b0-49c6-aaa1-455765b2311e | checkpoint | Current Odometer reading - Capture text and photo
68954991-5dda-4444-ad0a-13c66bdee121 | checkpoint | RUC Current KM - Capture text and photo
ee135a39-3fc1-4701-8abe-14e0a3dd8585 | checkpoint | WOF Due date - Capture text and photo
9ffca5a5-b877-4707-af87-2d4794c0082b | checkpoint | Last Service date - Capture text and photo
745da648-6f94-4102-a247-8e498414951a | checkpoint | Last Service Km - Capture text and photo
a5c03856-80c2-4540-acee-3b2d1dba39d8 | checkpoint | Mirrors Clean and no visiable damages
9fa3243b-6d7c-4f82-89af-9b531effc4e4 | checkpoint | Tyres have adequate Thread - min 2mm
1395b38a-3a39-48cd-99a4-dade685625d3 | checkpoint | Check Oil and Water
7bd5d5bb-012b-4141-83e7-d5acd5f6565e | checkpoint | Headlights and Indicators working?
0123cdda-0eeb-4927-a79e-5446618ac90e | checkpoint | Break and Tail lights Working?
aabf5e07-6c1f-4e0e-a3af-84da1866912b | checkpoint | Windcsreen no cracks and chips?
797dde13-472b-4fcb-9031-560d9422a439 | checkpoint | Body of vehicle need repairs? - Take Pic all 4 sides
fc058997-d511-487b-8d23-626082ed2cc9 | checkpoint | Vechicle clean? - Take 3 Pictures of inside.
8d0af1b3-ac39-477e-ba7c-718e531b6f1c | checkpoint | Medical kit in vehicle?
2c8234ee-6c95-4207-804e-9a82612c526c | checklist | Wall Vinyl / Cove / Splashback |  | Wall Vinyl / Cove / Splashback
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0e14f3f3-5ce7-4321-aec9-0a69607ec77a | checkpoint | Substrate clean and approved for installation?
4a9454db-92c3-5e7a-b407-c40428dc4015 | note | 1 x picture
b0aecf19-107e-4833-898a-15453a436404 | checkpoint | Cove height confirmed, and capping installed?
80d42a1e-c34c-4be5-8cdf-065bdb8829b8 | checkpoint | All areas welded?
12837663-a2a6-5e6f-ae52-ce2b1c2f06e5 | note | Pictures of welds
5f95fd4d-0d2f-4690-8baf-b6381fe0214b | checkpoint | No excess glue on vinyl surface?
ec3c31a5-d0bd-4ab7-93b6-4d6f0b67086b | checkpoint | All transition trims installed?
4ca62769-4450-5c85-8086-787a74c84cc8 | note | Pictures
20886821-406e-4e38-8da1-2667f8ec6b41 | checkpoint | Area dust free and all rubbish removed?
7d981624-00cc-4287-ad47-59ba1d021383 | checkpoint | Installation complete with no damage to joinery, skirtings or walls?
84b72a1c-c984-5b9a-b434-272d8308b977 | note | 2 x pictures min
984d412d-38cb-4fad-abd8-5cf21884b64a | signoff | Please signoff / request sign off

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
dd0b8dd0-81c7-4aa0-ad1d-17e204ca5d08 | checklist | CDC Floor Prep - J1868 |  | CDC Floor Prep
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
dbb9cb9e-39fa-5f2a-bef9-73e770a37c31 | checkpoint | Survey floor for flatness?
23aef3ef-ffe6-5802-9139-121278dac909 | checkpoint | Moisture test done prior to installation?
b9ca189c-9140-5bd9-91ae-3ad7ca1ee80b | checkpoint | At-risk surfaces protected?
8626a108-b383-413f-b117-587aa88dc505 | checkpoint | Floor surface grounded
c4e5a6ce-fc37-5d27-94da-c9e7c1017149 | checkpoint | Apply 1st Coat - Planiseal MR Moisture barrier
b370c798-9a12-522d-8b91-3c104e8658f9 | checkpoint | Apply 2st Coat Planiseal MR Moisture barrier with Broadcast Sand
a0b642b9-e265-5fd9-a3bb-5675f6d6a8a2 | checkpoint | All areas dammed up to prevent leaks?
b65289cb-5ed6-571c-a749-ecfe42b3c6c5 | checkpoint | Apply Mapei Ultraplan Eco Leveller
937c9c1e-9911-5c6a-8c35-542266abc217 | checkpoint | Area clear of rubbish and debris?
e052e593-13ec-58f1-82ed-ec7959c5cb8f | checkpoint | No damage to other surfaces?
f8d3f9fc-1698-5013-8bcc-c0f7ddf14804 | checkpoint | Levels checked and ready for installation?
bb85de61-faca-5628-a714-0d6e5d468cb6 | checkpoint | Preparation complete with no damage?
aa141209-1d99-55f3-bdcc-537b31f25223 | signoff | Please signoff / request sign off