## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-157-STR-Bridge Precast T Beam Supply and Installation
ITP Description: |  | Bridge Precast T Beam Supply and Installation
Discipline (e.g. CIV/STR/RAIL: |  | 157-STR
Revision Number: |  | 0
Revision Date: |  | 2025-09-22
ITP created by: |  | Jaidyn Kempster
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Ferris Road
Inspection & Test Plan - Precast Beam Installation
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-09-22
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VR Section 613 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | VR Section 610 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | VR Section 620 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Flowable Grout | IFC Drawings | Underside of beam shall be grouted as per IFC drawings using flowable non-shrink grout with a minimum compressive strength of 50MPa. Grout shall achieve full strength and shall be completed prior to Stage 1 deck pour. Enter: Teambinder Material Approval Number [free text box] | Document Review | Each Precast Element | HP | Nominated Authority | ConQA Hold Point Release
2.2 | Beam Seating Pads (HDPE) | IFC Drawings | 2 No. 200 x 200mm high density polyethylene pads, or approved equivalent, to be designed for minimum 10MPa Stres for each end of the super-tee girder. Enter: Teambinder Material Approval Number [free text box] | Document Review | Each Precast Element | HP | Nominated Authority | ConQA Hold Point Release
2.3 | Bitumen Tape / Fibre Cement Sheet | IFC Drawings | Beam joints to be sealed at the flange as per IFC drawings using approved materials. Enter: Teambinder Material Approval Number [free text box] | Document Review | Each Precast Element | HP | Nominated Authority | ConQA Hold Point Release
3 | Preliminaries - Procedures & Documentation
3.1 | Precast Elements | IFC Drawings Section 610.47 VR Table 610.473 Section 620.03 | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Pre-stressing check sheet / ITP vi. Post-pour check sheet / ITP vii. Covermeter check record viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates Note: Different revisions of 610 have different clause numbers The identification number, date of casting, the manufacturer's name or registered mark and the maximum mass shall be marked on every precast unit. Collate: Precast Quality Assurance Documentation and upload into Teambinder Enter: Teambinder MDR Lot number [free text box] | Document Review | Each Precast Element | HP* | PE/SE/SPE | This ITP Signed Off
3.2 | Curing Methodology (for Concrete, Grout and Mortar) | 610.23 (a) | Curing methodology/procedure to be submitted for review to the Nominated Authority. Note: This may be the same document used for the concrete curing. Enter: Teambinder Correspondence Approval number [free text box] | Document Review | Once, 4 weeks prior to placement of product | HP | Nominated Authority | ConQA Hold Point Release
3.3 | Temporary Works Designs | Section 610.27 Section 613.04 Section 613.05 Section 613.16 | All temp works design shall be certified by a design engineer who is a member of Engineers Australia and with a minimum of 5 years experience in the design and construction of falsework. The temp works design shall also be proof engineered by a Proof Engineer who is independent of the design consultant’s firm and is prequalified at Level PE under the VicRoads’ prequalification scheme. Attach: Temporary Works Design | Document Review | 2 weeks prior to installation of falsework | HP | Nominated Authority | ConQA Hold Point Release
4 | Pre-construction Activities
4.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP Signed Off
4.2 | Beam Seating Pads Check | IFC Drawings | Beam seating pads shall be inspected after fixing to the abutments and prior to the landing of the precast beams. Ensure the setting and orientation of the seating pads are correct. | Visual Measure | Each Precast Element | HP* | SE/PE | This ITP Signed Off
4.3 | Crosshead Tolerances | Survey As-builts IFC Drawings | Re-check that the As-built dimensional tolerances comply with the requirements as per IFC drawings. | Document Review | Each Precast Element | IP | PE/SE/SPE | This ITP Signed Off
4.4 | Precast Beams Estimated Hog Values | IFC Drawings | Re-check hog values for each precast beams to ensure within tolerance prior to landing of beams. Estimated Hog at Transfer (S1-G1 to S1-G7) = 28mm Estimated Hog at Transfer (S2-G1 to S2-G7) = 31mm | Visual Measure | Each Precast Element | IP | SE/PE | This ITP Signed Off
5 | Construction Activities
5.1 | Seating Pad Survey Set-out | IFC Drawings | Survey activities undertaken to ensure seating pads' locations are in accordance with IFC drawings. | Measure Visual | Each Precast Element | IP | Surveyor SE/PE/SPE | This ITP Signed Off
5.2 | Install Seating Pads (HDPE) | IFC Drawings | 2No. 200x200 (plan dimensions) high density polyethylene seating pads. Pad thickness to be determined from beam soffit levels, minimum thickness = 17 | Visual | Each Precast Element | IP | SE/PE | This ITP Signed Off
5.3 | Precast Beams Handling | IFC Drawings Section 620.07 Crane Lift Study Beam Certified Lifting Design | Unless otherwise specified, precast elements shall be lifted using approved lifting points in accordance with the Crane Lift Study and Precast Beams Certified Lifting Design. During storage, transport and handling, precast beams shall be kept in an upright position and supported not more than 400mm from each end. Beams shall only be lifted by the approved lifting anchords provided. Sling Angles not to exceed 300 from the vertical | Visual Document Review | Each Precast Element | IP | SE/PE/SPE | This ITP Signed Off
5.4 | Precast Beams Placement | IFC Drawings Section 610.27 | Precast beams shall be placed onto the seating pads and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings. The nominal gap between elements is as per the IFC Drawings. Girder landing positional tolerance is ±25 mm Precast beams shall not be erected and landed until the specified 28 day concrete compressive strength for abutment/pier crossheads have been achieved, and not before 14 days after casting. Beams shall be braced in accordance with the approved Temp Works to prevent overturning at all stages of construction. | Measure Visual Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP Signed Off
5.5 | Precast Traceability | Section 620.09 | All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number. Record: The final location of each precast element, showing individual ID and date installed. Attach: Lot Maps showing beam individual IDs | Visual | Each element | IP | SE/PE/SPE | This ITP Signed Off
5.6 | Grout- Formwork Construction & Placement | IFC Drawing No | Dimensions in plan as per drawings. Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks. | Measure Visual | Each element | IP | SE/PE/SPE | This ITP
5.7 | Grout-Pre-pour Inspection | IFC Drawings 610.20 | Formwork location and dimension comply. Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product. | Measure Visual | Each element | IP | SE/PE/SPE | This ITP
5.8 | Grout-Mixing Product | Product TDS 610.28 | Size of mixer should match the application. Only whole bags to be mixed with potable water. Volume of water matches the required amount for flowable consistency and accurately measured. Product poured into the mixer slowly. Mixing time as per TDS so that a smooth, even consistency is obtained. Enter: Required information on the Grout Pour Record | Measure Visual | Each batch | IP | SE/PE/SPE | This ITP
5.9 | Grout-Product Testing - Compressive Strength Cubes | 610.28 610.33 | Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products. Testing is be in accordance with the following frequencies: First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Attach: Grout pour records | Test | Each element | IP | Tester SE/PE/SPE | This ITP
5.10 | Grout-Placement & Compaction | Product TDS | All batches are traceable. Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water. Product should flow to all areas and self consolidate. Product that stiffens or is showing signs of stiffening shall not be used. Enter: Attach Grout pour record | Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
5.11 | Grout-Curing | Curing Methodology 610.23 Table 610.231 | Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS. | Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
6 | Post-construction Activities
6.1 | Grout-Compressive Strength Test Results | IFC Drawings Product TDS | 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly. 28 day compressive strength per sample comply with the design strength. Attach: Compressive Strength Test Results | Document Review | Each cube | IP | SE/PE/SPE | This ITP
6.2 | As-built Survey | IFC Drawings Section 610.47 VR Table 610.472 | Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP Signed Off
6.3 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /