## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-315-STR-FER-Bridge Precast T Beams Supply and Installation | itp |  |  |  |  | ITP-315-STR-FER-Bridge Precast T Beams Supply and Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-157-STR-Bridge Precast T Beam Supply and Installation
label | ITP Description: Bridge Precast T Beam Supply and Installation
label | Discipline (e.g. CIV/STR/RAIL): 157-STR
label | Revision Number: 0
label | Revision Date: 22/09/2025
label | ITP created by: Jaidyn Kempster
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - IFC Drawings
label | 1.2 - Non Dependent
label | Reference - VR Section 613
label | 1.3 - Non Dependent
label | Reference - VR Section 610
label | 1.4 - Non Dependent
label | Reference - VR Section 620
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Flowable Grout
label | Reference - IFC Drawings
label | Acceptance Criteria - Underside of beam shall be grouted as per IFC drawings using flowable non-shrink grout with a minimum compressive strength of 50MPa.
textbox | ○ Grout shall achieve full strength and shall be completed prior to Stage 1 deck pour.
label | Enter: Teambinder Material Approval Number
label | Method - Document Review
label | Frequency - Each Precast Element
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Beam Seating Pads (HDPE)
label | Reference - IFC Drawings
label | Acceptance Criteria - 2 No. 200 x 200mm high density polyethylene pads, or approved equivalent, to be designed for minimum 10MPa Stres for each end of the super-tee girder.
textbox | Enter: Teambinder Material Approval Number
label | Method - Document Review
label | Frequency - Each Precast Element
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Bitumen Tape / Fibre Cement Sheet
label | Reference - IFC Drawings
label | Acceptance Criteria - Beam joints to be sealed at the flange as per IFC drawings using approved materials.
textbox | Enter: Teambinder Material Approval Number
label | Method - Document Review
label | Frequency - Each Precast Element
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Precast Elements
label | Reference - IFC Drawings Section 610.47, VR Table 610.473 Section 620.03
label | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Pre-stressing check sheet / ITP
label | vi. Post-pour check sheet / ITP
label | vii. Covermeter check record
label | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates
label | ○ Note: Different revisions of 610 have different clause numbers
label | ○ The identification number, date of casting, the manufacturer's name or registered mark and the maximum mass shall be marked on every precast unit.
label | ○ Collate: Precast Quality Assurance Documentation and upload into Teambinder
textbox | Enter: Teambinder MDR Lot number
label | Method - Document Review
label | Frequency - Each Precast Element
label | Category - HP*
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 3.2 - Curing Methodology (for Concrete, Grout and Mortar)
label | Reference - 610.23 (a)
label | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
label | ○ Note: This may be the same document used for the concrete curing.
textbox | Enter: Teambinder Correspondence Approval number
label | Method - Document Review
label | Frequency - Once, 4 weeks prior to placement of product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Temporary Works Designs
label | Reference - Section 610.27
label | ○ Section 613.04
label | ○ Section 613.05
label | ○ Section 613.16
label | Acceptance Criteria - All temp works design shall be certified by a design engineer who is a member of Engineers Australia and with a minimum of 5 years experience in the design and construction of falsework.
label | ○ The temp works design shall also be proof engineered by a Proof Engineer who is independent of the design consultant’s firm and is prequalified at Level PE under the VicRoads’ prequalification scheme.
label | ○ Attach: Temporary Works Design
label | Method - Document Review
label | Frequency - 2 weeks prior to installation of falsework
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction Activities
checkpoint | 4.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 4.2 - Beam Seating Pads Check
label | Reference - IFC Drawings
label | Acceptance Criteria - Beam seating pads shall be inspected after fixing to the abutments and prior to the landing of the precast beams. Ensure the setting and orientation of the seating pads are correct.
label | Method - Visual, Measure
label | Frequency - Each Precast Element
label | Category - HP*
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 4.3 - Crosshead Tolerances
label | Reference - Survey As-builts, IFC Drawings
label | Acceptance Criteria - Re-check that the As-built dimensional tolerances comply with the requirements as per IFC drawings.
label | Method - Document Review
label | Frequency - Each Precast Element
label | Category - IP
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 4.4 - Precast Beams Estimated Hog Values
label | Reference - IFC Drawings
label | Acceptance Criteria - Re-check hog values for each precast beams to ensure within tolerance prior to landing of beams.
label | ○ Estimated Hog at Transfer (S1-G1 to S1-G7) = 28mm
label | ○ Estimated Hog at Transfer (S2-G1 to S2-G7) = 31mm
label | Method - Visual, Measure
label | Frequency - Each Precast Element
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
section | 5. Construction Activities
checkpoint | 5.1 - Seating Pad Survey Set-out
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey activities undertaken to ensure seating pads' locations are in accordance with IFC drawings.
label | Method - Measure, Visual
label | Frequency - Each Precast Element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.2 - Install Seating Pads (HDPE)
label | Reference - IFC Drawings
label | Acceptance Criteria - 2No. 200x200 (plan dimensions) high density polyethylene seating pads. Pad thickness to be determined from beam soffit levels, minimum thickness = 17
label | Method - Visual
label | Frequency - Each Precast Element
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.3 - Precast Beams Handling
label | Reference - IFC Drawings Section 620.07
label | ○ Crane Lift Study
label | ○ Beam Certified Lifting Design
label | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using approved lifting points in accordance with the Crane Lift Study and Precast Beams Certified Lifting Design.
label | ○ During storage, transport and handling, precast beams shall be kept in an upright position and supported not more than 400mm from each end.
label | ○ Beams shall only be lifted by the approved lifting anchords provided.
label | ○ Sling Angles not to exceed 300 from the vertical
label | Method - Visual, Document Review
label | Frequency - Each Precast Element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.4 - Precast Beams Placement
label | Reference - IFC Drawings Section 610.27
label | Acceptance Criteria - Precast beams shall be placed onto the seating pads and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | ○ The nominal gap between elements is as per the IFC Drawings.
label | ○ Girder landing positional tolerance is ±25 mm
label | ○ Precast beams shall not be erected and landed until the specified 28 day concrete compressive strength for abutment/pier crossheads have been achieved, and not before 14 days after casting.
label | ○ Beams shall be braced in accordance with the approved Temp Works to prevent overturning at all stages of construction.
label | Method - Measure, Visual, Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.5 - Precast Traceability
label | Reference - Section 620.09
label | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | ○ Record: The final location of each precast element, showing individual ID and date installed.
label | ○ Attach: Lot Maps showing beam individual IDs
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.6 - Grout- Formwork Construction & Placement
label | Reference - IFC Drawing No
label | Acceptance Criteria - Dimensions in plan as per drawings.
label | ○ Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.7 - Grout-Pre-pour Inspection
label | Reference - IFC Drawings 610.20
label | Acceptance Criteria - Formwork location and dimension comply.
label | ○ Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.8 - Grout-Mixing Product
label | Reference - Product TDS 610.28
label | Acceptance Criteria - Size of mixer should match the application.
label | ○ Only whole bags to be mixed with potable water.
label | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
label | ○ Product poured into the mixer slowly.
label | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
textbox | Enter: Required information on the Grout Pour Record
label | Method - Measure, Visual
label | Frequency - Each batch
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.9 - Grout-Product Testing - Compressive Strength Cubes
label | Reference - 610.28, 610.33
label | Acceptance Criteria - Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | ○ Testing is be in accordance with the following frequencies:
label | — First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | — Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | ○ Attach: Grout pour records
label | Method - Test
label | Frequency - Each element
label | Category - IP
label | Responsibility - Tester, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.10 - Grout-Placement & Compaction
label | Reference - Product TDS
label | Acceptance Criteria - All batches are traceable.
label | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | ○ Product should flow to all areas and self consolidate.
label | ○ Product that stiffens or is showing signs of stiffening shall not be used.
textbox | Enter: Attach Grout pour record
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.11 - Grout-Curing
label | Reference - Curing Methodology 610.23 Table 610.231
label | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Foreman, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 6. Post-construction Activities
checkpoint | 6.1 - Grout-Compressive Strength Test Results
label | Reference - IFC Drawings, Product TDS
label | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength per sample comply with the design strength.
label | ○ Attach: Compressive Strength Test Results
label | Method - Document Review
label | Frequency - Each cube
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.2 - As-built Survey
label | Reference - IFC Drawings Section 610.47, VR Table 610.472
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with specified tolerances.
label | ○ Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP