## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-013 ITP Surfacing EME | itp |  |  |  |  | DN1210-013 ITP Surfacing EME Rev 0
section | 1.0. Pre-Commencement Activities
checkpoint | 1.1 - Approved JMF for EME2 Base Course
label | Detail of Activity / Test - EME2 Whitehall V1 T24/3436
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Confirm requirements are followed
label | Acceptance Criteria - JMF Validated in accordance with NZTA M/32:2021
label | Record documents (QCP - Quality Control Portal) - Mix Design Report
label | Responsibility - Paving Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Approved Quality Plan/Renewal Quality Plan
label | Detail of Activity / Test - Prepare and Submit RQP
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Review /Acceptance by Engineer
label | Record documents (QCP - Quality Control Portal) - RQP
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - TMP Approval
label | Detail of Activity / Test - Prepare and Submit TMP
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Review /Acceptance by TMC
label | Record documents (QCP - Quality Control Portal) - TMP
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Public Notification
label | Detail of Activity / Test - Communication with affected parties
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Media/Letter Drops/TREIS
label | Acceptance Criteria - Letter drop to local residents/ Greater consultation as required
label | Record documents (QCP - Quality Control Portal) - Letter
label | Responsibility - Paving Contractor
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Crew Briefing Plan
label | Detail of Activity / Test - Prepare and submit CBP and VMP
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Written Plan
label | Acceptance Criteria - Approved by Responsible Manager
label | Record documents (QCP - Quality Control Portal) - CBP
label | Responsibility - Paving Contractor
label | Eng. Rep / NZTA - I
label | Contractor - A
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Site Conditions
label | Detail of Activity / Test - Weather suitable, Site extents marked, surface suitable for paving (Depths/milling/cleanup complete etc), Environmental Controls in place
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Confirm requirements are followed
label | Acceptance Criteria - Weather conditions and Site is suitable for paving
label | Record documents (QCP - Quality Control Portal) - Site Diary/String Sheets
label | Responsibility - Paving Contractor
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Traffic Loops
label | Detail of Activity / Test - Communication with affected parties
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Minimum of 7 days Before Works commence
label | Inspection / Test method - Visual
label | Acceptance Criteria - Notify RC at least 7 days before surfacing is programmed
label | Record documents (QCP - Quality Control Portal) - Communication
label | Responsibility - Paving Contractor
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Paving Plan
label | Detail of Activity / Test - Paving Plan to be completed
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - NZTA M/32:2021 Clause 9.5.1
label | Acceptance Criteria - Paving Plan to be completed for each shift
label | Record documents (QCP - Quality Control Portal) - Paving Plan
label | Responsibility - Paving Contractor
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
section | 2.0. MANUFACTURE OF ASPHALT
checkpoint | 2.1 - Temperatures
label | Detail of Activity / Test - Mixing of aggregates and bitumen
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Constant monitoring of temperature by calibrated euipment
label | Inspection / Test method - Plant temperature probes
label | Acceptance Criteria - EME2 binder Mixing range 180 - 190°C
label | ○ NZTA M/32:2021 states max. 190 deg.C
label | Record documents (QCP - Quality Control Portal) - Plant site diary
label | Responsibility - Asphalt Manufacturer
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.2 - Production Asphalt
label | Detail of Activity / Test - Particle Size Distribution
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
label | Inspection / Test method - NZS 4407, Test 3.8.1
label | Acceptance Criteria - NZTA M/32:2021, Refer to Table 5.3
label | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
label | Responsibility - Asphalt Manufacturer
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.3 - Production Asphalt
label | Detail of Activity / Test - Binder Content
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 200t at asphalt plant
label | Acceptance Criteria - NZTA M/32:2021
label | ○ Individual Test Result: ± 0.5
label | ○ Mean of Three Test Results: ± 0.3
label | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
label | Responsibility - Asphalt Manufacturer
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.4 - Production Asphalt
label | Detail of Activity / Test - Max. Specific Gravity (MSG) of mix
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant
label | Acceptance Criteria - Report
label | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
label | Responsibility - Asphalt Manufacturer
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 2.5 - Production Asphalt
label | Detail of Activity / Test - Air Voids at lab design compaction
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - 1 per 600t at asphalt plant
label | Acceptance Criteria - NZTA M/32:2021
label | ○ Individual Test Results: +2.0, -1.0
label | ○ Mean of Three Test Results: +1.2, -0.6
label | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert
label | Responsibility - Asphalt Manufacturer
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
section | 3.0. PLACING AND FINISHING
checkpoint | 3.1 - Milling
label | Detail of Activity / Test - Surface strung to ensure milling Depth is achieved
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Before Works commence
label | Inspection / Test method - Confirm requirements are followed
label | Acceptance Criteria - Site is suitable for paving
label | Record documents (QCP - Quality Control Portal) - String Sheet
label | Responsibility - Paving Contractor
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Tack Coat, OR
label | Detail of Activity / Test - Application of Tack Coat
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
label | Inspection / Test method - Dip bitumen emulsion tank before and after
label | Acceptance Criteria - Target Between 0.2l/m2 - 0.6l/m2 +/- 0.1l/m2 From Target Application Rate
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.3 - Membrane Seal
label | Detail of Activity / Test - Application of Membrane Seal
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Per Lot
label | Inspection / Test method - Sealing Records
label | Acceptance Criteria - Application rate, chip type and binder as per membrane seal design
label | Record documents (QCP - Quality Control Portal) - Sealing Records
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.4 - Temperature
label | Detail of Activity / Test - Pavement Surface
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Start of shift and every 1 hour until temperature rising
label | Inspection / Test method - Infrared gauge
label | Acceptance Criteria - ≥ 5°C for Structural, or as otherwise agreed with NZTA
label | Record documents (QCP - Quality Control Portal) - Site diary
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.5 - Temperature
label | Detail of Activity / Test - Asphalt Delivery temperature
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Every Load on delivery to the Paver Hopper
label | Inspection / Test method - Temperature Probe/Infrared gauge
label | Acceptance Criteria - Target ≥ 150 deg.C. in the Paver
label | ○ Min. ≥ 130 deg.C in the Paver
label | ○ <130°C to be Rejected
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.6 - Temperature
label | Detail of Activity / Test - Compaction Temperature
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - During compaction
label | Inspection / Test method - Temperature Probe/Infrared gauge
label | Acceptance Criteria - 130-150°C at commencement of compaction.
label | ○ < 90°C - Stop Rolling
label | Record documents (QCP - Quality Control Portal) - Site diary
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.7 - Mat
label | Detail of Activity / Test - Load Locate
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Each load
label | Inspection / Test method - M/32
label | Acceptance Criteria - Each load can be indentified to a location using a diagram. Record includes:
label | ○ Truck ID/Rego/Driver
label | ○ Depart Plant Time
label | ○ Arrive Site Time
label | ○ AC Temp on Arrival
label | ○ Tonnage
label | ○ Run Width
label | ○ Estimated Run Length
label | ○ Calculated Area
label | ○ Calculated Average Depth
label | Record documents (QCP - Quality Control Portal) - Paving Run Sheet
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.8 - Mat
label | Detail of Activity / Test - Thickness Monitoring
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
label | Inspection / Test method - Dipping
label | Acceptance Criteria - Target Loose Thickness -0mm / +10mm
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.9 - Mat
label | Detail of Activity / Test - Compaction - NDM
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Plateau to be completed on 1st run, thereafter monitor compaction/roller passes to achieve target density.
label | Inspection / Test method - Insitu density and air voids
label | Acceptance Criteria - NZTA M/32:2021 - section 9.8
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions - Use a calibrated NDM with established core correlation. Locate and mark cores, record NDM Bulk density by core location (including any offset used).
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.10 - Mat
label | Detail of Activity / Test - Compaction
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Mat: 1 per 300m2/min. 8 per Lot Joint: 1 per 100m/min. 3 per Lot, In the event of a day's production being > 30t but < 2400m2, then it will be permissable to reduce the number of cores to; Mat: 1 per 300m2 with a minimum of 4 per Lot, and Joint: 1/100m with a minimum of 3 per Lot
label | Inspection / Test method - Insitu density and air voids
label | Acceptance Criteria - NZTA M/32:2021 - section 9.8
label | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
label | Responsibility - Paving Contractor
label | Project Specific Notes / Instructions - A pavement lot shall be an essentially homogeneous section of work completed within a shift of production.
label | ○ The lot shall be divided into an appropriate number of approximately equal sub-lots and a core shall be taken randomly within each sub-lot. The Engineer or their delegate shall use a random method for locating each core position, such as ASTM D5361 or a similar process.
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Mat
label | Detail of Activity / Test - Thickness
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - Average of 4 measurements per core
label | Inspection / Test method - Measure Cores
label | Acceptance Criteria - LCV ≥ Specified Depth (Minimum)
label | ○ NZTA M/32:2021 - section 9.7
label | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
label | Responsibility - Paving Contractor
label | Designer - A
label | Eng. Rep / NZTA - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Mat
label | Detail of Activity / Test - Shape
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Continuously
label | Inspection / Test method - 3m Straight edge
label | Acceptance Criteria - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Refer NZTA M/32:2021 - section 10.
label | ○ Not more than 5mm under a 3m Straight Edge.
label | Record documents (QCP - Quality Control Portal) - Straight Edge Record
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.13 - Paving Quality
label | Detail of Activity / Test - Texture
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
label | Inspection / Test method - Sand Circle or HSD
label | Acceptance Criteria - NZTA T/10: 2013
label | Record documents (QCP - Quality Control Portal) - IANZ accredited test cert.
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.14 - Paving Quality
label | Detail of Activity / Test - Level
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
label | Inspection / Test method - As Built Survey
label | Acceptance Criteria - -0 < +5mm from Specified Level
label | ○ Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC.
label | ○ NZTA M/32:2021 - section 10.1
label | Record documents (QCP - Quality Control Portal) - Survey As builts
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.15 - Paving Quality
label | Detail of Activity / Test - Alignment
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production) - Per Site (If Required)
label | Inspection / Test method - As Built Survey
label | Acceptance Criteria - ±50 mm from drawings
label | ○ NZTA M/32:2021 - section 10.2
label | Record documents (QCP - Quality Control Portal) - Survey As builts
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.16 - Post Paving Completion Checks
label | Detail of Activity / Test - Site clear and cleanup
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Site is cleared of plant (or parked in safe location) cleanup of all waste mix, paper and detritus is complete
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.17 - Post Paving Completion Checks
label | Detail of Activity / Test - Pavement Marking
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Roadmarking is complete
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.18 - Post Paving Completion Checks
label | Detail of Activity / Test - Cold Joint Bandaging
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Cold joint bandaging is complete
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.19 - Post Paving Completion Checks
label | Detail of Activity / Test - Service Covers Checked
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Check that service covers are cleared and level with the pavement
label | Record documents (QCP - Quality Control Portal) - Site Diary
label | Responsibility - Paving Contractor
label | Eng. Rep / NZTA - I
label | Contractor - R
checkpoint | 3.2 - Post Paving Completion Checks
label | Detail of Activity / Test - Traffic Loops Reinstated
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - Each Site/Shift
label | Inspection / Test method - Visual
label | Acceptance Criteria - Check that affected traffic loops have been reinstated
label | Record documents (QCP - Quality Control Portal) - Communication
label | Responsibility - Paving Contractor
label | Eng. Rep / NZTA - I
label | Contractor - R
section | 4.0. As Built Records
checkpoint | 4.1 - Assessment of all test results for conformity
label | Detail of Activity / Test - Review against ITP Requirements
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
label | Inspection / Test method - Review
label | Acceptance Criteria - Reporting of any non-conforming results to Engineer via NCR
label | Record documents (QCP - Quality Control Portal) - NCR
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - RAMM pavement and surface records
label | Detail of Activity / Test - RAMM surfacing pavement data spreadsheet updated
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production) - For each site on the project
label | Inspection / Test method - Prepare Data
label | Acceptance Criteria - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA
label | ○ Spray sheets for membrane area received by Contract Engineer from Sealing Team.
label | ○ Surfacing layer extents recorded and verified by Contract Engineer.
label | Record documents (QCP - Quality Control Portal) - RAMM Spreadsheet
label | Responsibility - Paving Contractor
label | Designer - I
label | Eng. Rep / NZTA - A
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature