## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
a7e827ab-b6a6-4e4e-8b23-bc6856399c92 | checklist | ITP 1 Delivery Checklist |  | Delivery Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
59bbc81c-2cb1-46ee-92f5-b277cf4a26c7 | checkpoint | Durra panel sizes to match order
3c913eb8-a67b-4c15-b352-eed4ad21bb7c | checkpoint | Durra panel quantities to match order
8bea1e70-cae7-452a-bfb5-cffb778b1b34 | checkpoint | Durra panel layers to match order
b37ea765-9690-46b8-be78-60ab18c1d7cc | checkpoint | T bars quantities to match order
5ddf2bfd-8536-407a-a4b2-bbc99d3f56dc | checkpoint | T bars have no damage
f4fc4429-1174-4070-8b92-7812046f6cfd | checkpoint | Beam size to match order
637b7c79-a04a-4158-a2a1-a96bd74f7a41 | checkpoint | Beam quantities to match order
1038e39c-4bdc-4435-ab27-74021bab934b | checkpoint | All panels have no damage
04ee72c8-1c18-45fc-9512-867471b90c34 | checkpoint | All beams have no damage
d020280e-6008-4265-99b9-154a08fd2c22 | checkpoint | Wedge quantities to match order
cbc97242-972e-4121-888e-b68a56f9df47 | checkpoint | Correct paperwork with delivery
b65210c5-50b9-4f67-829d-76c30a0266c0 | checkpoint | All works have been carried out in accordance with above ITP
51afe13e-9be1-5087-8e11-ff99ac048ba6 | note | Attach Faulkner Roofing representative signature
68fc695d-f879-4f66-b9be-5cb38debe908 | signoff | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
fd1e26f0-a2e9-4819-ad05-056b328af6a5 | checklist | ITP 2 Module Assembly |  | Module Assembly
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
99caf8d2-cbfb-450e-aca2-0d7341ec5e97 | checkpoint | All Durra layers are installed as per location mark up
cea96595-39db-4152-9c9a-4d46ecc6865f | checkpoint | All spacings are to match install area
78f379c7-d162-4e8d-be6a-c948d44861da | checkpoint | All T bars are secured
044d3c63-b09c-4e36-80b1-23d8ff27467f | checkpoint | All Durra panels are in place with correct minimum spacings
c9ec477a-e1fd-4b3d-bb01-8c8ba059d130 | checkpoint | All wedges are in place
33177343-912d-444e-9288-54d2da7de916 | checkpoint | All Durra panels are taped to all edges
67e583c4-61da-49d5-85a2-a50020805057 | checkpoint | All panels have no damage
cb0c4f65-f66b-4aa2-9010-7e30ba7a2d03 | checkpoint | Infill panels are secured ready for lift
23311b56-8780-4a1e-97c9-760e5f582674 | checkpoint | Infill T bars are secured ready for lift
b8d73299-5446-4cf4-819a-8bc3e6a49bc0 | checkpoint | All works have been carried out in accordance with above ITP
90baa2f6-55a3-5440-a030-e53596e1f87c | note | Attach Faulkner Roofing representative signature
c88fbe88-0c0a-49ea-bebe-f0b61e21e611 | signoff | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
29b86c08-3494-4309-b97c-fccd62fbf9bd | checklist | ITP 3 Module Install |  | Module Install
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1a786048-8e09-4896-afb0-74578b706be0 | checkpoint | All Durra layers are installed as per location mark up
ea214a3b-6660-4794-88ed-eccd825dde8d | checkpoint | All angles are secured correctly to pre cast
67f441d2-59ce-451a-a7e5-299df3d85c55 | checkpoint | All angles have correct amount of bolts
f917180e-982f-46b8-94b3-175420702e87 | checkpoint | All T bars are secured
6b832fb4-6784-4cd5-9223-c03d23f906b2 | checkpoint | All Durra panels are in place with correct minimum spacings
e8038303-da62-45df-8afc-b41146f2f1ed | checkpoint | All wedges are in place
261e1de9-f642-4bf7-8772-c66d50b8e80c | checkpoint | All Durra panels are taped to all edges
b8de12bd-b418-4889-99cb-c159fc1009ab | checkpoint | All infill panels are in place and wedged
bfcc8ba2-6436-4d81-aef2-ff54fbab24e0 | checkpoint | All beams are bolted
8db725ca-5a6c-4d25-9237-eb6f1c2c839d | checkpoint | All bolts are correct length and size
e390a8ee-4c6a-46b9-a8ce-aa64c74b996a | checkpoint | All bolts have been tensioned
1aa7b76d-3598-4727-9a7b-787fbf15be27 | checkpoint | All panels have no damage
82266669-8731-497a-b736-565ce8f0a293 | checkpoint | All works have been carried out in accordance with above ITP
76dc3716-16b1-53eb-a57d-76428ab7989a | note | Attach Faulkner Roofing representative signature
58c9f76d-1b5c-46a0-bb4f-eb9aaf1efae1 | signoff | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
26316569-46d0-44c1-b054-35b730f3ff49 | checklist | ITP 4 Fire Draft Walls |  | Fire Draft Walls
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9b325852-5c12-49c2-bd87-9e64a60f33ae | checkpoint | All Durra layers are installed as per location mark up
601b1a70-413d-4267-bcf1-ce68517e1e3f | checkpoint | All T bars are secured
f804324b-42c4-4049-b1fd-8fc640107c9a | checkpoint | All Durra panels are in place with correct minimum spacings
f414a97c-0e20-4649-b091-f0b6fe0f2aa7 | checkpoint | All Durra panels are taped to all edges
7775aaec-3225-4b9f-a0ae-a34244d9f4c6 | checkpoint | Any gaps bigger than 3mm have been caulked
1d16188a-3a14-493e-a491-bddcba35ce02 | checkpoint | All frames are securely fastened
6116293a-7207-4baf-8686-f9d419cbf3a5 | checkpoint | All works have been carried out in accordance with above ITP
4e8bd5d4-3647-5112-b75b-70d0dfa1d8c4 | note | Attach Faulkner Roofing representative signature
f4c5c514-acc0-44ef-9cd8-3f0760f9fa56 | signoff | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
02a14def-e7ad-424c-ac12-d7449dc73754 | checklist | ITP 5 Durra Panels Top Layer |  | Durra Panels Top Layer
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
836d0465-30ac-4720-b4d0-f23385ce4d80 | checkpoint | All Durra layers are installed as per location mark up
48921587-c734-4209-a4e3-921527d2838b | checkpoint | All T bars are secured
75ec098c-85a7-40fd-8c92-343a73f07678 | checkpoint | All bolts are in place and tensioned
f11f791d-ac98-421a-86ad-f1cb9515ab8e | checkpoint | All bolts used are correct length and size
d601840e-f74e-454f-be72-dd47001fb3a3 | checkpoint | All Durra panels are in place with correct minimum spacings
5f0e53c3-a237-4bd2-8d1b-122e8ac5ca6e | checkpoint | All wedges are installed
edab53a9-222a-40dd-808c-b34c31713c51 | checkpoint | All Durra panels are taped to all edges
2cd27bcd-fb04-49f2-933e-d9f6545ea0db | checkpoint | All infill pieces are in place and wedged completely
4cd194d6-fc61-4492-a589-3c303da51195 | checkpoint | All works have been carried out in accordance with above ITP
ec98733d-cda8-532a-ab6f-61fcd709c23f | note | Attach Faulkner Roofing representative signature
83b94ef5-01e4-4cf4-9f0a-466dde001a44 | signoff | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
a67fcc2e-eb74-4617-bfcb-c890d0d2701d | checklist | ITP 6 Roof Layers |  | Roof Layers
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7c6236b6-0f28-4121-96f3-9f3f75169c7e | checkpoint | All roof layers are installed as per location mark up
5c1ec810-4688-45f6-8974-706c0a37804b | checkpoint | Safety mesh installed as per manufactures tech data
2c546780-83db-4ad2-9afd-215991eafa92 | checkpoint | Layer of sarking with tape to joins no gaps in tape
90f0d0fd-c077-4ae1-b112-79bb67814922 | checkpoint | Sarking taped with correct sarking tape
f0bd5b52-ebe0-4b65-9d4f-f0d9639e8fa1 | checkpoint | 2 layers of cement sheeting with no gaps
057e71c8-a8ff-4c29-ad7f-b2f6444a9361 | checkpoint | Correct thickness cement sheeting to suit area as per mark up attached
5fa5a81a-1dc5-4218-b7b6-6097242ec4d1 | checkpoint | Correct size insulation blanket to suit area as per mark up attached
b9898a79-8058-4846-863e-868c863c480d | checkpoint | Correct size roof spacers to suit insulation as per mark up attached
543f26be-cb6c-4f32-86ef-0a034a17e92a | checkpoint | Vapour barrier installed with minimum 150mm lap
2b8fec47-e83a-4f92-aa9c-60aaa27514ae | checkpoint | Vapour barrier taped with correct tape
a2c57df8-2465-4e57-aa74-063ba7792e13 | checkpoint | Vapour barrier taped with no gaps or breaks in taping
44c5a6d5-8a20-4d1a-b67e-f6194078a0a6 | checkpoint | Any holes have been taped over
1751cc80-cec0-4632-a01d-e528789fd681 | checkpoint | All works have been carried out in accordance with above ITP
b9713956-6ded-599a-be92-1d6b986820b6 | note | Attach Faulkner Roofing representative signature
f476ac41-606c-4116-9059-174edc6870cf | signoff | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
80ff9957-b433-4ce1-ae0f-f7036b010ab1 | checklist | ITP 7 Gutters |  | Gutters
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8662a189-fd44-46a6-8f29-d46bcc47aba8 | checkpoint | Gutters have correct fall
3af1a96b-a0ee-4537-b64b-48bdf6a21cf8 | checkpoint | Gutters have expansions joins(where necessary)
56b42474-a6f1-4500-8f4d-1648e8459cd2 | checkpoint | Gutters have compliant overflow precautions
1e190eb9-ae19-4d1a-9aa0-e6f8d5f78259 | checkpoint | Gutters/sumps clean of swarf
a83c0475-840d-42c0-bb9e-ecc742ee886d | checkpoint | Eaves gutters have correct bracket spacings to suit manufacturers tech data
5b5e1aaf-c637-4c02-bfb2-abb119d3f7ad | checkpoint | Downpipe clip spacings as per regulations
d7534b8a-1d34-435f-8292-70ff4997860c | checkpoint | Spreaders include ½ stop ends where needed
9335e93e-fcfb-4774-ba23-43d073efcacb | checkpoint | Downpipes are located as per Hydraulic plans
d971d81c-8141-44b9-90d1-b0bf2288b802 | checkpoint | Overflows are located as per Hydraulic plans
989788ec-9b0a-4c3c-98c2-b6ac076e4859 | checkpoint | Sumps installed where located on Hydraulic plans
7b58b678-a8fa-465c-ae1c-155b1beed87f | checkpoint | Correct size outlets to match Hydraulic plans
7b45d986-2572-4c29-923c-25c794fdb50a | checkpoint | Correct size overflows to match Hydraulic plans
8c46f751-04f1-4d5d-8dd5-7f37f27041f9 | checkpoint | Box gutter Corrosion break strip installed between bird flashing and boxy
63b58260-35af-4bcf-851c-c734c07f766b | checkpoint | Box gutters use 4mm stainless rivets
6a1188fb-7822-4507-852c-ee3275e19f6d | checkpoint | Box gutters use activator cleaner and sikaseal for joint sealants
f9d34bc7-d148-4e4e-b735-4bc22983c70f | checkpoint | All works have been carried out in accordance with above ITP
f154ae13-2891-5d05-be55-a7a52c1241cb | note | Attach Faulkner Roofing representative signature
95780f49-a562-41c8-8bce-abd1f489baad | signoff | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
84781648-4913-4781-861f-6d7a53b6e79a | checklist | ITP 8 Roof |  | Roof
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1f7fc870-9878-4be5-98c7-2d3d9cb6762f | checkpoint | Roof profile is compliant with roof pitch
607d5177-3960-42c3-92c2-559dbbb75d79 | checkpoint | Roof sheets minimum 50mm into gutter
3aa58c19-28f1-4182-910e-25f91a04abf8 | checkpoint | Roof sheets turned up (and down if required)
d35c078f-98c4-41af-8b49-cf3640f3e9d4 | checkpoint | Roof screwed off correctly
6b99fd5e-7b3f-439b-9504-a1f0e2315196 | checkpoint | Flashings correctly screwed off/riveted
aa3ed895-52d1-4b12-97ac-0ffb1ba21a7b | checkpoint | Flashings cover 150mm or 2 ribs
dc458b2a-2f59-4f7b-9f11-58269361b9f1 | checkpoint | Penetrations backtrays correctly screwed/riveted/oversealed
54a14cff-30a7-4b6c-a481-9b4ad2c67a83 | checkpoint | Dektites screwed/oversealed
0cb1bdc7-2050-4b6e-af71-5addb8ca5b58 | checkpoint | Ensure ponding is not present in or around dektite
13b2d9e9-b658-4d8d-b6d1-1b2c727ce6e0 | checkpoint | Cappings screwed off every 500mm
3b66e203-9213-40f4-b8ad-267482ae428d | checkpoint | Roof clean of swarf
19ecd715-c06a-4a8f-9d96-df95494810d0 | checkpoint | Gutters have correct fall
eba888da-94ed-4a08-b90d-f02dfed54323 | checkpoint | Gutters have expansions joins
9559f6cc-2fa2-4ee1-892d-19a8e6894e03 | checkpoint | Gutters have compliant overflow precautions
9ea61f05-9c71-4861-b74a-961d142f2bce | checkpoint | Gutters/sumps clean of swarf
88f2afcd-a8fc-46ef-a4c9-6f70f63c2718 | checkpoint | Downpipe clip spacings as per regulations
ada48b3e-24b6-47ef-9a7e-faf283b5df9a | checkpoint | Spreaders include ½ stop ends where needed
4851556c-a0d6-44be-b9d8-180d6d116006 | checkpoint | All works have been carried out in accordance with above ITP
4ba9c094-f6f8-53e5-94a5-8cba4defe029 | note | Attach Faulkner Roofing representative signature
ef1a4867-95c1-4f3e-b19e-930438656074 | signoff | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing
8b1741a2-ed36-4c6d-b469-ec9df4ed6a5d | checklist | Roofing Inspection Checklist |  | Roofing Inspection Checklist
c490e7fe-1ee6-40ea-a2ee-c04337536b0f | section | Structure
bd283528-e018-46c5-a16e-0a02f190b2c1 | checkpoint | Structure has been completed and inspected by the Permanent Works Engineer.
34da21cf-8838-4b42-b9c6-1476d4bfd109 | checkpoint | Purlins are in alignment and within tolerance - +/-10mm vertically and horizontally
a552f86c-7ee4-5cc2-8c30-cd7efdd27b3f | note | Class 1 tolerance as outlined in AS/NZS 5131 and the structural specifications.
d3d30d0c-d0c5-45f3-92fc-6d7bc2cba2df | checkpoint | Pitch is suitable for proposed product.
4cd24e93-ec3b-53fb-8669-1be04f56d783 | note | Reference - NCC 3.5.11
4ed78810-ea3e-50bf-9af8-2abf5023cc64 | note | · Corrugated – Min 5o
c5bf0c4b-096e-5dc5-b1ac-815b009bd222 | note | · Trapezoidal – Min 2o
3c00bcf9-8d9f-5f49-9023-6ce2f83db051 | note | · Concealed Fastened – Min 1o
c4c46a7a-a487-52aa-9ddb-07dafce09f44 | note | · Close Pitched Trapezoidal – Min 2o
efaa7eac-9ba9-45f8-b769-cad44625c579 | section | Safety Mesh
1f81f758-a788-46d2-88ce-224685e6d856 | checkpoint | Safety Mesh installed and twitched to specification
de407f47-0936-5001-90bd-85ab616dbac3 | note | When working over a roof frame, as a minimum, approved safety mesh, meeting Australian Standards, must be installed over the roof purlins including with double side laps (min. 300 mm) and 2mm staples every 2nd square on alternate sides. This minimum protection system must be used regardless of purlin spacing.
77b5e3db-729e-5c5e-9d5d-d8768f7ae642 | note | All longitudinal wires need to be wrapped around or through drilled holes in the purlins and tied off with a minimum of four full turns.
daeeaf83-5754-4710-8b06-20c839b35320 | section | Gutters
8bea6085-b3c1-4f73-9ce6-9538ca2a662b | checkpoint | Gutter types and size have been nominated. Each downpipe must not serve more than 12 m of gutter length. Reference - NCC 3.5.3.5
63d438fb-fbfd-490f-9090-a30d89bed45c | checkpoint | Fall has been achieved
a355f1ff-3b85-4054-8ed0-d0f271311745 | checkpoint | Water tested
8b2c2be9-df2f-4e97-909b-211a69ce3403 | checkpoint | Gutter board and brackets installed at the correct centres. Supported by brackets securely fixed at stop ends and at not more than 1.2 m centres. Reference - NCC 3.5.3.4
16172216-c9e8-4232-8890-1cb684179e43 | checkpoint | Outlets fitted & sealed
4202a66b-1ee1-4fde-85b9-71180545e356 | checkpoint | Overflows fitted and welded and installed at correct height
4d95af32-5bc9-4d33-a8a4-0d684a44709e | checkpoint | Hydrostatic testing of gutters
f13a912a-e827-4a55-8911-f7ad0457cc1d | section | Acoustic Layer
b1a2d55a-9ff5-4917-b802-3ae2c3409676 | checkpoint | Confirm cement sheet is installed as per the acoustic report and nominated details. Joints lapped 9mm thick FC sheet/layer
846885d4-0911-4e57-9684-e90b045b2554 | section | Insulation
224b889f-33dd-4a7a-87c4-831cae891270 | checkpoint | Insulation and sarking are on-site as specified (i.e. brand, thickness, R-value)
74afb595-87f2-4650-8725-522ad171ebe4 | checkpoint | Thermal spacers installed as per specification
8d6ba953-4917-429f-b0a2-bef9f7fcb5d0 | checkpoint | Thermal break strips installed as per specification
da1091bf-8429-4ee5-a5fc-dae783540448 | checkpoint | Insulation / sarking is free of holes and tears
7b83be28-4294-41a5-b392-f4c80f4e98e9 | section | Roof Sheeting
d29bc4b8-1555-405f-bfc7-cc8f6940e953 | checkpoint | Sheet is as per specification (i.e. type, profile, colour and BMT)
979a1dd9-acb7-4cf7-9371-3174d842900a | checkpoint | All fixings present and within crest of roof sheet profile.
fdcf416e-4e47-5ba7-a677-c04f22cf0772 | note | Reference NCC 3.5.1.4 - Trapezoidal – Side lap Every rib
debf315d-4ba9-4884-b132-9b9318985373 | checkpoint | Maximum spans between roof supports complied with.
b6795a38-ef75-559c-a86e-16afff3c80bd | note | Reference NCC 3.5.1.3 (0.48 BMT)
a9b6974b-1f2e-4b70-b18e-8d41ec72465f | checkpoint | Lapped as per specification and in line with manufacture specifications for proprietary lap joints
6b893eec-9203-5fc2-a225-4f3cc6b8e78e | note | Reference NCC 3.5.1.6 - Wherever possible, use complete lengths from fascia to ridge.
3d70aea4-5b73-4395-a113-03f2ebcbbe50 | checkpoint | Clean and free of all rubbish, swarf
7efc5fc5-45d3-467a-85e7-fa845367c512 | section | Penetrations
1460943c-625a-4012-a6cb-28e188363f86 | checkpoint | All service penetrations marked on roof by respective trades
46351ee7-2e8e-4841-8b8e-6df7cdc36341 | checkpoint | All penetrations <50mm sealed with Dektite or similar
7179240f-ab4d-4719-9b58-2ab50b863f5d | checkpoint | All penetrations >50mm sealed with flashing
ca3b2164-9997-4de5-bae7-5545d1356572 | section | Flashings
b20ca3f1-5db1-4b0f-a91d-793d708b0b4c | checkpoint | Straight and lapped to direction of flow
5d598eb9-ea88-58c0-86aa-fa70f3bb8899 | note | Reference NCC 3.5.1.7 - Joints must be no less than 75mm and lapped in direction of roof fall
ffc8c500-11e8-4935-a752-89ae44d00da7 | checkpoint | Scribing neat and close
0b0d5628-8ce1-43f0-aa36-d8fc7731736f | checkpoint | All joints sealed and clear of excess silicone
60f556e9-1f52-41ff-aefb-2987ada6b557 | checkpoint | Metal materials are compatible with each other as described
c37517f4-02f2-485a-8070-32844160b1ed | checkpoint | Backfall on flashing in direction of gutter
d680fc8d-de99-4393-8de0-e01093e62d1c | section | Final Inspection
9a29f1a2-1887-4f4e-be59-46de5cf021e9 | checkpoint | Clean and free of all rubbish, swarf
0b5aa1bc-685c-47a4-abdd-b111b98975bf | checkpoint | All fixings present
5a122321-11e0-453e-80b3-be117b12f6ab | checkpoint | Free of dents, damage and major scratches