## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
a67fcc2e-eb74-4617-bfcb-c890d0d2701d | checklist | ITP 6 Roof Layers |  | Roof Layers
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7c6236b6-0f28-4121-96f3-9f3f75169c7e | checkpoint | All roof layers are installed as per location mark up
5c1ec810-4688-45f6-8974-706c0a37804b | checkpoint | Safety mesh installed as per manufactures tech data
2c546780-83db-4ad2-9afd-215991eafa92 | checkpoint | Layer of sarking with tape to joins no gaps in tape
90f0d0fd-c077-4ae1-b112-79bb67814922 | checkpoint | Sarking taped with correct sarking tape
f0bd5b52-ebe0-4b65-9d4f-f0d9639e8fa1 | checkpoint | 2 layers of cement sheeting with no gaps
057e71c8-a8ff-4c29-ad7f-b2f6444a9361 | checkpoint | Correct thickness cement sheeting to suit area as per mark up attached
5fa5a81a-1dc5-4218-b7b6-6097242ec4d1 | checkpoint | Correct size insulation blanket to suit area as per mark up attached
b9898a79-8058-4846-863e-868c863c480d | checkpoint | Correct size roof spacers to suit insulation as per mark up attached
543f26be-cb6c-4f32-86ef-0a034a17e92a | checkpoint | Vapour barrier installed with minimum 150mm lap
2b8fec47-e83a-4f92-aa9c-60aaa27514ae | checkpoint | Vapour barrier taped with correct tape
a2c57df8-2465-4e57-aa74-063ba7792e13 | checkpoint | Vapour barrier taped with no gaps or breaks in taping
44c5a6d5-8a20-4d1a-b67e-f6194078a0a6 | checkpoint | Any holes have been taped over
1751cc80-cec0-4632-a01d-e528789fd681 | checkpoint | All works have been carried out in accordance with above ITP
b9713956-6ded-599a-be92-1d6b986820b6 | note | Attach Faulkner Roofing representative signature
f476ac41-606c-4116-9059-174edc6870cf | signoff | Builder representative sign off: ITP has been conducted and signed by Faulkner Roofing