## Master List Templates
Id | Type | Name | Values | Prompting Name
c755ba6d-cc14-48b7-b857-ac5c6c2947c9 | checklist | Carpet Tiles Installation |  | QA Carpet Tile Installation :
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3e5897ea-15f3-46bf-b8f4-09ec59218523 | checkpoint | Carpet tile range and colour check and confirmed
ca7af71d-548d-4271-82d5-f91e1eb21437 | checkpoint | Area / Location to receive carpet tiles
0b919c41-9165-5e29-816f-07ff4a87f876 | textbox
3532ecac-75ae-4ea3-854d-dc05161964e5 | checkpoint | Floor prep required ?
91ba2909-8cb2-5a4b-aedb-b40d54d1bd25 | textbox
169e1a52-41ac-4c26-9a53-294cfc40585c | checkpoint | Installation direction confirmed ?
1d613fa5-4aa9-4b5d-92b7-441fd2b3f438 | checkpoint | Setting out lines square ?
02ce727b-a5dd-4c24-8eda-32c3a18156aa | checkpoint | Are all edges free from fraying ?
6192cd56-5fa2-495f-919d-a7d392832aa1 | checkpoint | Are all edges cut neat and straight?
7ae6fe07-6a0a-41ca-bec2-53b8e2010ba7 | checkpoint | Carpet tile adhesive used
7af8d0dc-ff0e-56dd-ba5a-1931b6cc8f31 | note | x1 Pictures
d2dae3fd-f1bc-4394-85d7-b6acded2717d | checkpoint | Completed Carpet Tile installation
9a74155b-f21a-5bf5-8025-8359e41031ef | note | x4 Pictures
c062a656-2501-4b33-9ade-fb586f853bfd | checkpoint | Check and clean any excess adhesive in joints, on wall, or skirting
139fcae5-bae5-43c3-bfca-24d9c03d6d2e | checkpoint | Transition between other floor covering level and flush
1606949e-9f0a-4713-83ac-d9e56454bdf1 | checkpoint | Phase completed with no damage ?
5608e008-a164-4b9c-acc1-422397f875d0 | signoff | Please signoff / request sign off
40c41e6e-0df1-460b-bb00-d4f5b255d1e1 | checklist | NZ Living - Balcony |  | NZ Living - Balcony
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7ce3de8b-ebfb-49c8-abbf-cbf5607eec15 | checkpoint | Details
3b66c41c-5832-58af-b30d-aab645656b94 | textbox | Block Number
2a2c7c17-e211-5282-a8a1-1ddd9c192777 | textbox | Level Number
bb56e98e-7d19-5fa2-b1d5-e93cebdb9d01 | textbox | Unit Number
f097b912-f1dc-4300-b21b-1fef39f3ab3d | checkpoint | Clean Grind - 30 DISK
259c8eb9-6c3b-59c3-95e2-5979aaf689e5 | note | x 1 Picture
f90a54ae-fe66-44fe-ae1e-96c13ea700cc | checkpoint | Dremel tool in corners and below ranch slider
a81d49a5-c168-5aac-97be-6447ced9f159 | note | x 1 Picture
1fc5ca35-8d7c-4e24-8f0f-e82ebbb2e561 | checkpoint | Polish Grind - 80 DISK
28c00610-8bc0-580e-b15e-e12e33a12bbb | note | x 1 Picture
c213c337-a37e-4162-ac3f-a82e7c29b575 | checklist | NZ Living - Bathroom per unit |  | NZ Living - Bathroom per unit
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
ab05fcbb-1748-47e3-90b8-663aced12aa0 | checkpoint | Details
62c4610d-546b-585f-8d64-9c81583e0754 | textbox | Block Number
17fe428e-02a3-53eb-847a-5cea3f9a665e | textbox | Level Number
67503979-e505-5611-b446-1f2a9fed8b97 | textbox | Unit Number
34f359bc-c678-4db5-a02b-7b820bb78df7 | checkpoint | Clean Grind
b71261fa-66d5-54cf-9442-b44abfbd6d43 | note | x 1 Picture
51f08809-5d6b-49bf-9e21-ac16205653f5 | checkpoint | MAPEI AQUA DEFENCE 1st Coat
17b9648e-ff44-547d-9549-0865cd103a94 | note | x 1 Picture
305989d0-a2d5-4cd6-af4c-c69fda218039 | checkpoint | MAPEI AQUA DEFENCE 2nd Coat
69dc96c5-49fe-5c3b-a659-db695343b86b | note | x 1 Picture
cc28aa46-f819-4e47-bc81-269b791d0d43 | checkpoint | Mapei band easi 400x400 waterproof membrane
68a86f11-03af-5084-b331-bd4339feeb46 | note | x 1 Picture
b82ed121-16e5-4a53-b617-45c5e238a3d2 | checkpoint | Apply Mapei Eco prim-T primer
17d3bc52-d6c4-5fd7-ba07-532d4eb532a4 | note | x 1 Picture
445969d4-6478-43e6-aac0-0856032789b0 | checkpoint | Apply smoothing screed compound
cfd1b85b-aacc-5b1e-8831-74929dc9ee9a | note | x 1 Picture
6465b791-ab83-42d4-9acf-0a8fcc011dc1 | checkpoint | 2mm Rubber underlay 1st floor and up only
ec704735-8bbf-4949-a04f-0e30f374a9b5 | checklist | NZ Living - Carpet |  | NZ Living - Carpet
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
22b8558b-d24b-4f87-96c0-1425124b0867 | checkpoint | Details
110fb50b-77c3-55a7-9a1b-a18168dbae8d | textbox | Block Number
713dd5e4-7298-511d-92d2-1821d2a70a59 | textbox | Level Number
1c9aa9ea-2105-5e9c-9d08-20139ba03453 | textbox | Unit Number
4303f131-278b-5ef8-89ee-87c46b2d719b | textbox | Range and colour fitted
57123ab1-6a6c-5633-bf40-30a3191ae492 | note | x 1 Picture
4e386b45-18dd-4fd3-bf69-e88705b7a254 | checkpoint | Underlay install
20fdefdb-12f3-599a-98aa-35acc713423c | note | x 1 Picture
964db42b-e47b-4f06-8a8a-e99a2391bb0e | checkpoint | Door transition trim between vinyl and carpet
80230ffc-8bb3-5fcf-b4a2-c764f8583e27 | note | x 1 Picture
9895d920-20e4-49fb-be08-3e384e5ff0b4 | checkpoint | Assure grippers are pushed down with bolster!
c39b79f5-3f49-5326-8e57-a27f3bf57b62 | note | x 1 Picture
07fa7299-d18b-49ec-8cb9-63da78649569 | checkpoint | Completed carpet install
e7c72250-d848-5b13-8fb4-2983b7e62fd3 | note | x 4 Pictures
a60ce3bb-924d-4201-a939-9ebc9fa553c8 | checklist | NZ Living - First floors and up units |  | NZ Living - First floors and up units
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3e7892ab-e67b-4652-811e-da7440c22f55 | checkpoint | Details
6fb61526-62f6-569c-af18-8ecc704d6c13 | textbox | Block Number
85365474-8916-57d4-bbad-b14755783f16 | textbox | Level Number
89bce13e-fbe1-51b6-a817-014fa2ba1ba2 | textbox | Unit Number
dac7de8b-001f-4b89-8983-12cc3e350f67 | checkpoint | Clean Grind subfloor
375b1547-2f5c-5cee-b550-9d3a96dd475c | note | x 1 Picture
004b2fbd-6ca3-4b5e-bc5d-5c8ebf28c3fe | checkpoint | Fine finish screed preparation
a3680f3e-520f-5687-9112-f8dcec0d5476 | note | x 1 Picture
a904a498-7457-405b-a9d7-de24b186d978 | checkpoint | Ramp at ranch sliders
d91a104c-d4dd-59e1-aca3-6c1273c90170 | note | x 1 Picture
ce60c6ac-c924-4c97-8bdd-8aa5b23844d2 | checkpoint | Polyvac prior vinyl
57421dfe-1a8b-53e7-a6d7-70e2eff4ba1c | note | x 1 Picture
b8b13317-cb27-48d7-a1fd-96dca8c94efb | checkpoint | Undercut bathroom door frame for LVT
1ede50d0-025b-5cf4-b87c-1021a017acb2 | note | x 1 Picture
9dd4dc33-0e44-4003-bd4e-704e8e1bbef9 | checkpoint | Bathroom vinyl adhesive 68T
355b04bd-89b2-5f1a-bb58-9d142e8abf03 | note | x 1 Picture
b7b93896-11c1-4462-9fac-5145f3977edd | checkpoint | Completed vinyl plank install to bathroom
9a8106ef-e130-5b7a-8088-dffb3bfab866 | note | x 1 Picture
981badb4-3c25-419b-9a4a-ea91179f88f4 | checkpoint | Fit regupol underlay prior vinyl with KE2000 (Sub supply)
bcefa41d-f009-5450-a543-98d530e380bf | note | x 1 Picture
03c528e1-5765-4972-9f42-31fcfa2a2c8d | checkpoint | LVT neatly but up against skirting
81f4f70f-0765-5fbf-8d99-824ae2cb5dec | note | x 1 Picture
5f6eec5c-80ea-4047-86b8-f693b2d79a65 | checkpoint | Vinyl plank completed installation pictures
029549b8-b3b0-51fd-ab16-831277f65782 | note | x 2 Pictures
5ae53c51-f74c-4b0b-bc92-1bce42b0640d | checklist | NZ Living - Ground floor units |  | NZ Living - Ground floor units
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
48f8aec8-fc05-49c1-aba5-8187ebcb93da | checkpoint | Details
89f450d3-8cfd-58f5-ae7c-a7bf59fc51de | textbox | Block Number
4ef5ae9a-53db-529f-a5ed-d84b9f970025 | textbox | Level Number
7d60b79e-0042-5143-ac99-efacd5711d90 | textbox | Unit Number
2d1c327b-7d1d-4fc6-84bc-961cb24b96c5 | checkpoint | Moisture check
4f4621d1-d2b0-5a3b-a91f-daf29e0d07f1 | note | x 2 Pictures
42c0fdfd-d555-4289-8c32-697a29674910 | checkpoint | Clean Grind subfloor
4644957c-12a8-5d9f-9f08-ec6d2260e839 | note | x 1 Picture
237594b2-ede1-4b8d-b254-19bcc55fd3bb | checkpoint | Fine finish screed preparation
fa63d555-f08a-535e-b9c2-51bc42e8c212 | note | x 1 Picture
bb8e3122-a053-4485-bada-41fd0ab508a1 | checkpoint | Ramp at ranch sliders
b718fbd0-5099-5ff2-b478-6456e0a6b11b | note | x 1 Picture
be244f02-fe81-4634-8ffc-26e33c9db0b1 | checkpoint | Polyvac prior vinyl
857fa70e-f7b8-5818-b66f-f2d28cca5080 | note | x 1 Picture
3ad04569-0997-4a2c-971f-08e10230d495 | checkpoint | Undercut bathroom door frame for LVT
d4d94bd7-bc00-583a-8c69-65d68b7f0226 | note | x 1 Picture
2ff1608a-74f3-41d2-aeee-f08ba27b8596 | checkpoint | Bathroom vinyl adhesive 68T
f7915530-9b84-537f-a5a8-b087ac2c9f05 | note | x 1 Picture
c42dfadf-3415-4f3c-9fd5-e743552cd225 | checkpoint | Completed vinyl plank install to bathroom
c2852327-6e67-50c9-86ec-8f620e652d92 | note | x 1 Picture
d6936fa0-a258-48fd-95a4-e14dd1111984 | checkpoint | LVT neatly but up against skirting
19d42c2c-eed3-5879-bf12-3078158318bf | note | x 1 Picture
96b02104-2423-47d7-a1f4-59be0702e326 | checkpoint | Vinyl plank completed installation pictures
e9b94e1c-8b5e-5658-8d61-c0559aec995e | note | x 2 Pictures
86edd4f1-e8e6-4701-a026-2d827693e3f8 | checklist | NZ Living - Staircase |  | NZ Living - Staircase
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
12c171aa-a421-471f-aac9-6577a71a53d8 | checkpoint | Details
b8834cfd-0d0a-5c6f-9556-2009c224453b | textbox | Block Number
0555051f-e1e4-4ff2-bbda-2338d6ab98b6 | checkpoint | Staircase Number
151e9679-931b-4f70-9348-b67fa475bae4 | checkpoint | Sand and prep
c2fe2d1e-093a-4f7d-a5db-a1e37218f6de | checkpoint | Prep fill next to staircase on ground slab dirt trap
574a19d3-f5ef-546d-9f96-6f435f4dc65a | note | x 1 Picture
5a96285a-9d35-52f5-b411-eef97aeb6244 | textbox | Screed bag count
f5045963-8405-4eb2-ab45-31864c710a2f | signoff | Client Signature
49a990d7-e417-4f89-800e-dedef0796771 | checkpoint | Fit approved nosing and insert
ddbb2961-fa47-52d1-93d6-5349acec9a63 | note | x 4 Pictures
8ed85664-7dde-41c3-bb81-0d3669ef41ad | checkpoint | Fit vinyl sheeting adhesive 68T
d190fb1b-aa51-5a7f-af7a-987e9aa4619d | note | x 1 Picture
4fd48300-befa-4689-b672-46e3166722e4 | checkpoint | Completed vinyl installation
4c749be7-18f6-527e-9081-e8cfb65315aa | note | x 4 Pictures

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
d2a640f8-8f4b-54e0-9180-4a9346dec021 | checklist | Carpet Tile Installation |  | Carpet Tile Installation
ee9dc83b-144a-596a-9418-efc47324c835 | section | Preparation
959e20a0-9f45-5585-8e13-1ef31708fc23 | checkpoint | Check area clear of all other trades and their materials
a3b20bbe-e9c5-5809-aabd-f9196cba9334 | checkpoint | Check floor if prep is required
c9c13bc2-ce99-5801-8076-00023c18b9c6 | checkpoint | Measure area
e8adbc84-b448-5119-bc35-7edd8200d05f | section | Installation
d15c700f-a2fc-5176-a03f-3e8bce645787 | checkpoint | Confirm carpet tile pattern direction/layout
909bc00d-59d9-585d-8eff-582007e6a2f2 | checkpoint | Glue out floors
7bb4effb-5cde-5732-b7a3-55f85951dbf0 | checkpoint | Install carpet tiles
c2b5659a-2e70-53d1-afa3-f6167f1d83c6 | checkpoint | Install trims as applicable
b0eb8b69-a23a-5590-bfd3-a62c0ad370d9 | section | Handover & Signoff
2c7eac63-3869-58de-a69c-6727bb4858a2 | checkpoint | Remove all excess material
2bbb5ed5-5710-5cf9-ae7c-03dde387e395 | checkpoint | Clean any excess glue
900859d4-e0a1-521e-93f0-51c078b31eaa | checkpoint | Report for inspection
6b2db137-7712-53f1-84bd-0dcc1b1a4c3d | checkpoint | Quality Approval
4c6593a6-445d-5d5c-856e-23bb735827fb | signoff | Click to request signoff
4371c25c-66cb-4b30-bb3e-5ee5890d2722 | checklist | Concrete Moisture Test - On slab method |  | Concrete Moisture Test - On slab method
6e10d568-5c73-42ae-b276-6ae78e72ed17 | section | Details
7b0d1a65-0e48-4c8e-93b2-0949aabd384f | checkpoint-no-value | General Details
7a1702d1-32a7-53d6-a4f1-0da2d15fede5 | note | According to the NZS AS 1884:2013, the acceptable level of concrete moisture content is less than 4.4%
0d0b47a2-ac8b-5271-9708-23f04e181cd0 | date | Date of test
0cdd0e06-58bf-561c-b9dd-19059b1bc03c | textbox | Project name
e5039212-06c5-4799-a0da-4cd06f62a473 | checkpoint-no-value | Hygrometer device used for test
cb7b23c8-e6a7-51f8-89a1-654d0157fb41 | tickbox | Photo of Hygrometer device uploaded?
d55b850b-d8f0-4a87-ba38-4d058fb9304b | checkpoint-no-value | Test 1
f1707158-aafd-55d5-bb76-6f081db8b61b | textbox | Area/Location of test and result
8261673c-50bb-521b-ad9d-139fdaba478c | button | Result | PASS, FAIL
162c85d1-9995-4780-b2a4-1ebc99e6c687 | checkpoint-no-value | Test 2
27565ae3-c10b-5b12-8e05-a3eda3bf8fc4 | textbox | Area/Location of test and result
c09b8c32-2f7f-59f9-9d14-075808f9fb02 | button | Result | PASS, FAIL
0c7fca74-c4ca-4f53-bcd9-77e593aef8c7 | checkpoint-no-value | Test 3
0ca36135-ebac-5f8a-a06e-55e943fc365e | textbox | Area/Location of test and result
a123bf99-a549-5999-aa10-e799fa758d16 | button | Result | PASS, FAIL
b2bc5867-c8ec-4dac-a345-7eb308eb613d | checkpoint-no-value | Test 4
255e3037-7f7d-5339-8cde-d357b3da26b7 | textbox | Area/Location of test and result
caf3c05c-a2d0-51fc-b668-15efc8df1d61 | button | Result | PASS, FAIL
7e5a9764-0c46-4362-95a2-987bb52f947d | checkpoint-no-value | Test 5
e56da83b-2645-55f2-b3d6-0faeb2e15433 | textbox | Area/Location of test and result
1517dd51-ed92-5f2f-bccd-c89b524f01da | button | Result | PASS, FAIL
d748bbaf-c89a-4635-b564-f60bdb5934b6 | checkpoint-no-value | Test 6
d3f43faa-4e9e-5c66-b720-b4d6a1d18210 | textbox | Area/Location of test and result
598a0e64-0a66-5c50-be66-0d8865f78573 | button | Result | PASS, FAIL
6fda11d1-65b4-4705-9043-57441a4e4b34 | checkpoint-no-value | Test 7
dbf60223-b2fc-5ed4-9e21-f4672b5501b1 | textbox | Area/Location of test and result
7e3ff7e6-4ac1-59e6-8e25-e592a21ccad3 | button | Result | PASS, FAIL
ac48e067-d33c-473f-a027-05c121be1d7e | checkpoint-no-value | Test 8
b16ebf9f-451f-5179-922a-ac0c41ec83d6 | textbox | Area/Location of test and result
01a62c36-6e82-5c30-817c-3c784556c441 | button | Result | PASS, FAIL
8a35916e-723a-4e0d-86b7-211f9dda6d6e | checkpoint-no-value | Test 9
c27fce32-5bd2-5b75-9bf2-2939fa901e16 | textbox | Area/Location of test and result
abb12b55-d300-5869-8ba6-bd6ea610c485 | button | Result | PASS, FAIL
7dd58da1-6309-476c-b22d-76cca011de04 | checkpoint-no-value | Test 10
361080d3-ad18-5ab8-9e15-80ec806dd963 | textbox | Area/Location of test and result
0e26fedd-b712-5c47-9d24-70972f43ebfb | button | Result | PASS, FAIL
73a8e47b-d0a5-4e8f-8906-2f941d931e5f | checkpoint-no-value | Remarks from examinee
eea45184-cb17-5d74-af04-7771bdbc73c1 | textbox | Remarks/conclusion
163229cf-a242-4b7d-8d79-7e381cbf7fdc | signoff | Click here to signoff
b739ebf3-2a0a-487f-96bf-0df2eea25748 | checklist | Dayworks Checklist |  | Dayworks Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c9874600-3f1e-4789-90fd-b3c92474a351 | checkpoint | Job details
b24c4113-9610-57c4-b5bd-f220e5b8c81d | textbox | Job Sheet
1e64838d-de49-57cd-a1de-bc9bc49a560f | textbox | Client
8698df71-9832-503b-8f1c-2e0292a77a6d | textbox | Project
0d7a347a-64e5-5dc2-8d9c-bb14cdb91fa7 | textbox | Project Number
cc484d20-d5da-413a-9542-dc4d4f26fce5 | checkpoint | Dayworks details
6c573f64-14d2-5b1e-ac7f-0c6e1fb4d540 | date | Date
98ddf7c2-20a8-57de-88c4-c3cf0d4ed952 | textbox | Grinding
f071ca1e-dc6d-54d1-9dd0-7285072ef36f | textbox | Start
892cdc61-c268-5b97-8247-c15d98f1a475 | textbox | End
87b62626-8515-535a-bcfd-f3143f6896ce | textbox | Hours
db84204b-0755-5853-9b95-c769e0b6673b | textbox | Men
e561682f-2acd-5b62-aa2f-c9365db0c53d | textbox | Total hours
3987d398-e27e-5fb4-a06a-069f23de2ded | textbox | Compound / Area
b672c2b9-e6dc-5daf-85da-959bccb10fe8 | textbox | QTY Bags
c20b95f3-665c-5014-a70e-31947436a1fb | textbox | Note
a4724775-20d9-443b-a41d-416116fb410f | signoff | SIGNATURE
100df97b-edec-5625-a6a3-7651f1ad93a9 | checklist | Delivery |  | Delivery
44e8ca0e-2774-5cc2-b7b5-2609b718e641 | checkpoint | Check material supplied matches what was ordered
cc94f6c5-07e5-5946-86d7-fda388522b03 | checkpoint | Check batch numbers
8bef7fc8-1be0-5f63-8393-c2c8cfc35c11 | checkpoint | Confirm material matches what is specified
6de594af-a932-4788-bd12-0a093cea1d84 | checklist | Incident Report |  | Incident Report
4fdeb5b7-1f33-4e6a-8fb0-af8be58dc091 | section | Details
c524be0e-a73c-440e-beac-857d00a264d1 | checkpoint-no-value | Project name or location
f237baa0-8176-5839-b1a0-f317fec2d5b6 | textbox
3e4eb054-e419-40ea-b319-da1f25df21a7 | checkpoint-no-value | Date & Time of Incident
b5cc9a96-9bed-51f8-89da-656ae82cf881 | textbox | Date & Time
93efd180-23f0-4538-8b74-5bcc23986a17 | checkpoint-no-value | Reported by
d79e2da1-5bc0-50a9-aabc-95ee1d36aeb8 | textbox | Name & Surname
57657323-d987-4c94-ba88-6f1f9d2dc8aa | checkpoint-no-value | Reported to
a62c4072-ae3d-5887-b29d-eabae428e145 | textbox | Name & Surname
0f524741-a896-466c-adf3-7f2101200f58 | checkpoint-no-value | Incident Type
12b77f08-8723-5c56-8ada-4c62e131cdae | textbox
d4139d55-6b01-5351-a8a3-178e8ae3d926 | note | Add Picture
085e930d-4433-47df-a23b-6f94aed8075b | checkpoint-no-value | Details of incident (Injuries)
0a5f58d3-85b6-445e-ae53-d588c5aa009d | checkpoint-no-value | Person involved
21ece807-6371-5b65-9b9c-27c203254384 | textbox | Name & Surname
1793e77d-b728-5da2-b617-05ec3bfcec73 | textbox | Contact details
4c17915f-65fc-403b-912c-7caf66e218e1 | checkpoint-no-value | Details of witness
bd6d8b5e-215f-523d-b8a8-a96255bf9738 | textbox | Name & Surname
38992af8-30b8-5e95-a4af-f7304541c87a | textbox | Contact details
3197afad-345f-4917-869b-dbc69052d514 | checkpoint-no-value | Manager Remarks - Actions and Follow up
0f7dc310-246b-5942-847a-62fa0e928b73 | textbox
a4b8b6d2-36f2-41d8-b093-f17f42c81ec2 | signoff | Review and signoff by Supervisor / Manager
ca35ef1a-8951-451a-9cd2-8cc15d8d70ce | checklist | Project Stock Control |  | Project Stock Control
e5e0dde8-355f-4ca2-8508-509345a2b796 | section | Details
fbc084d7-642e-4bc3-9571-bd610bf59c57 | checkpoint-no-value | General Details
0585ee62-1ed6-593c-adbf-1009a23fdd6d | textbox | Project name
ac637098-0371-5e3e-8ec8-a4b0f92bc8ba | textbox | Job number
80f9913c-8df5-50f8-94a4-ab752b281abe | textbox | Product Manufacturer
4a72a1a2-28f9-5e85-832f-a900801cccb9 | textbox | Product Range
a4fa1bcf-dbe6-5b0b-91ac-b531431a810f | textbox | Product colour(s)
ac99e370-14c5-4300-b99a-6d6e0cd3dae7 | checkpoint | Quantity Received from suppliers
6bf095ca-19d0-5551-8aa0-12ba48bc649c | textbox | Boxes
37c26cf0-b9d0-5d17-a5c3-bd9910c37ab3 | textbox | Square Metre Per/Box
e97ba47d-6ff0-5f75-9103-ee8b38925865 | textbox | Square Metre Per/Roll
e027e308-b3f4-4a43-80a4-5d2c95f40db2 | checkpoint-no-value | Stock issued out to installer - 1
811ef4a8-2521-541e-a78a-12bb6ec183cc | textbox | Colour/Range
c087e8c4-2af0-5c80-baf6-c24143c2cab2 | date | Date
d3a814e4-f445-5324-95e9-52ad7a665939 | textbox | Quantity
fe70c49c-7667-5d24-af95-db2a49efb4d1 | textbox | Balance left
afdb825b-dd73-4452-b742-8177d456e331 | signoff | SIGN HERE
07852df2-45cd-4c2b-8f31-09f23263395b | checkpoint-no-value | Stock issued out to installer - 2
64028a43-4e03-5082-be82-7101744b8bc8 | textbox | Colour/Range
5bf3402f-964d-5dba-94db-9a1574d72d7c | date | Date
ee6ef0f6-11b9-5a47-981d-227ac8042ba1 | textbox | Quantity
779ec205-2ab5-524c-96ac-8da6cf0733ea | textbox | Balance left
5cff91d9-d0f8-4753-84b3-d3fd5b6483d0 | signoff | SIGN HERE
39f16962-4ae2-4795-841a-cdb23ae291dc | checkpoint-no-value | Stock issued out to installer - 3
5fa7cca7-c24f-53a4-972b-3a68d010a2c3 | textbox | Colour/Range
f2043300-71d6-5414-a6e9-0f5c9b1bde58 | date | Date
ae8d587d-6cee-52a5-9779-bc9edde8554d | textbox | Quantity
a4539763-cfbb-5ed9-8a60-e703f1f98a69 | textbox | Balance left
5ddee04d-8e5d-47d1-8674-08bfb09c676f | signoff | SIGN HERE
a34aaa04-c61b-44c8-b006-8a2444773051 | checkpoint-no-value | Stock issued out to installer - 4
78e34b71-4613-5813-89dc-073682e77349 | textbox | Colour/Range
9f925955-9ddc-5b40-a33e-c8b874de0db7 | date | Date
a0681fc4-c283-5e6b-8291-bd218a52e66b | textbox | Quantity
2a361e5c-6339-57b7-aa9b-1692daed6dd6 | textbox | Balance left
c281dfd0-a612-4725-a8bb-6705c334678c | signoff | SIGN HERE
51867098-aed1-46b1-84f7-67a6c5971a5a | checkpoint-no-value | Stock issued out to installer - 5
3a57c803-6f46-5cf3-ac0f-db57fd1a825d | textbox | Colour/Range
54447f60-898f-5bd0-b278-f1b83611d6f6 | date | Date
a0f517c2-7906-5728-9a8b-ca3965312068 | textbox | Quantity
69532a86-ae04-5479-9e6b-77e7f0a96bcc | textbox | Balance left
708b71a9-dba1-4207-8ab7-afca6ab1d355 | signoff | SIGN HERE
4be97d49-6c97-42c4-91ed-cdf4feddd8a4 | checkpoint-no-value | Julius Remarks
915ffdd8-21f4-5b9a-8924-1f1bc9ab5be5 | textbox | Remarks
c9127451-22b9-4d5b-8cd3-bbdd3b3996cc | checkpoint | Any material returned upon completion?
f895ec0b-34e5-5a82-811c-6aa5a847248b | textbox
5df3ac60-e506-4070-9359-db4da92a9221 | checkpoint | Signoff
803e088c-bdc6-4a38-8d18-f85a674c9c28 | signoff | Review and signoff by Manager upon completion of project
b5f84763-9516-5fcf-b799-f5bdc80906b7 | checklist | SYS - Timber Installation |  | Timber Installation
23aef3ef-ffe6-5802-9139-121278dac909 | checkpoint | Moisture test done prior to installation?
43ca088a-92b6-5a45-b362-a1fe7169eb42 | checkpoint | Underlay installed and rolled with roller?
9f6c8dda-641b-5b59-9e92-ea734c0160a5 | checkpoint | Timber direction been approved?
17fe55bd-d3bb-5cea-9c0d-6b2e09ff33d5 | checkpoint | Undercut doors and joinery?
20fa1cfc-5121-5275-bde4-a513799d8b57 | checkpoint | Correct notch trowel used as per specifications?
050b7ca3-62c2-5d6f-ba2e-e9545466f5df | checkpoint | Expansion gaps as per installation manual?
f344c09d-df6b-5dcd-865a-e15b67f4138e | checkpoint | Timber weighted down during installation?
52b5a535-3c44-54bb-a29b-1532a9c7a937 | checkpoint | All transition trims installed?
d0d6cd78-bc19-5bc5-af09-c892b6a6d12e | checkpoint | Area dust free and all rubbish removed?
cf15ad2f-0517-55f7-9cf8-6fd9bc004a58 | checkpoint | No damage to joinery, skirtings or walls?
ddfc8926-e396-574a-811d-857efbe76348 | checkpoint | Has the floor been protected?
43594070-4ef1-580d-abd9-d55822997b5f | checkpoint | Installation complete with no damage
3d376b14-0def-57cf-bcce-7504a9a67475 | signoff | Please signoff / request sign off
c2cf25dd-8aaf-4420-a4e6-fca2564495a2 | checklist | Toolbox Talk - Site-Specific |  | Toolbox Talk - Site-Specific
06236ce0-0f58-4112-9207-6e0e2c10ebfe | section | Details
d6a1c9e9-2ab7-48d4-a696-ff98a34766b7 | checkpoint-no-value | General Details
1ffa78a8-b877-57f3-ba3d-1f39be72f467 | textbox | Project name or location
6d433079-dc84-52a4-897a-ef14da774936 | date | Conducted on Date
693641de-22ee-55cd-bf80-50784b8510fd | textbox | Who is running this meeting?
d447e8a9-6ff4-466a-ab29-064597c5ae70 | checkpoint-no-value | Toolbox Topic
6280a338-4234-5088-b8e6-9abeac69e084 | textbox | Description
6befc31e-77f8-5230-b1a2-3b0fba69607f | textbox | Actions
a788f56e-ec74-4101-8450-6d0d3d43ac4a | checkpoint-no-value | Issues raised from site?
47a30aa7-60d0-5419-a241-d1d1f619d021 | textbox | Description
cb5cc7f3-73ad-5fd8-bc8a-4c1c0ba41d71 | textbox | Actions
39a60cf3-2c47-4315-8d3c-c9f76fc4bd3a | checkpoint-no-value | Employee raised issues?
aa0e8102-0a28-5f9a-bd7f-64392252e9c8 | textbox | Description
d3d032cb-a514-51d7-b604-6aa8f6101c61 | textbox | Actions
e70b5c5b-0c8a-4edf-9d3b-d5082dc30fca | checkpoint-no-value | Incident or Injuries
39c4916f-80a0-557d-b994-21de24c2b39c | button | Any Incident or Injuries to report | Yes, No
df5dca4d-42c2-5203-bfa7-d595062ef018 | textbox | Description
33c4c1aa-d31e-581c-8f11-32eb673d5beb | textbox | Actions
ec84c563-af2b-4eb9-a64a-887c67bc181f | checkpoint-no-value | Hazards
04ba420f-f658-5bc2-b00d-e0f827886f39 | button | Any Hazards to report (Dangerous activity or condition) | Yes, No
5eae470a-999b-513c-86bb-e878ed603ab6 | textbox | Description
078f7180-f761-5030-a0a8-a2a6c2c0d2c4 | textbox | Reported to
186155a8-1356-4a51-af7e-18f2258f4f0d | checkpoint-no-value | Risks
10d4ce44-2e03-5625-8b07-953b2dbbed59 | button | Any Risk to report (Possibility of something bad happening) | Yes, No
eca849cc-4b6d-5b7b-b261-f6668ad267a6 | textbox | Description
0b6131f0-c5da-5428-8acb-00e87c230fb0 | textbox | Reported to
a4a1ac77-abd5-4659-b12b-a74a2f40844e | checkpoint | PPE - Personal Protective Equipment - Correct and in good condition ?
51747051-77f3-5330-acb2-7e771e9ff5a3 | tickbox | Inspected
c3a0d9d4-ff93-4401-a280-2f00089a4bea | checkpoint | Positive safe-action observations
20bda59e-c9e0-51ca-9c75-92e4a58759c9 | textbox | Observations
afdef0b8-425e-44ed-9bab-47aae5f01dd9 | checkpoint | Attendance Record
c0e83bcb-d1ad-4ecf-82f5-ac0644d8999c | signoff | Each attendee to click here to signoff
99b39a30-7324-48c4-a9cf-38978fcf0d1f | checkpoint | Supervisor / Manager remarks and signoff
616d0632-5ecc-509e-ba0e-197151c3a6c3 | textbox | Manager's remarks
de162328-ab6d-4159-afdf-6aa5a51622c3 | signoff | Review and signoff by Supervisor / Manager
c4789074-e436-5cfa-9130-86e226037029 | checklist | Vinyl Installation |  | Vinyl Installation
ee9dc83b-144a-596a-9418-efc47324c835 | section | Preparation
959e20a0-9f45-5585-8e13-1ef31708fc23 | checkpoint | Check area clear of all other trades and their materials
73ce6ea3-eb38-5630-9adf-a8b1d12be5ef | checkpoint | Check floor for U3 (3mm variance over 3m)
d89e06d4-7705-5b5f-8274-56653b1aa62a | checkpoint | Check wall for smoothness where coving
c9c13bc2-ce99-5801-8076-00023c18b9c6 | checkpoint | Measure area
99557dbf-2e65-5e11-9b3a-9bf5986adaf1 | checkpoint | Acclimatise vinyl
e8adbc84-b448-5119-bc35-7edd8200d05f | section | Installation
1e6aaaed-6f83-5f08-990f-dbc309fc9094 | checkpoint | Confirm vinyl layout direction
ba73561c-0fb1-596c-8cfa-a4dd7592d395 | checkpoint | Confirm coving location/type
909bc00d-59d9-585d-8eff-582007e6a2f2 | checkpoint | Glue out floors
5620aa21-b3c8-55ac-95eb-51fd2fd63461 | checkpoint | Install vinyl
d46b8eeb-f583-58ee-a5f0-3875971b2d2e | checkpoint | Install coving & capping/sealant as applicable
b0eb8b69-a23a-5590-bfd3-a62c0ad370d9 | section | Handover & Signoff
2c7eac63-3869-58de-a69c-6727bb4858a2 | checkpoint | Remove all excess material
2bbb5ed5-5710-5cf9-ae7c-03dde387e395 | checkpoint | Clean any excess glue
900859d4-e0a1-521e-93f0-51c078b31eaa | checkpoint | Report for inspection
6b2db137-7712-53f1-84bd-0dcc1b1a4c3d | checkpoint | Quality Approval
4c6593a6-445d-5d5c-856e-23bb735827fb | signoff | Click to request signoff