## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-01 - Rocker-roller Bearing Replacement | itp |  |  |  |  | ITP-01 - Rocker-roller Bearing Replacement Rev 0
section | Preliminaries
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to starting Works and at regular intervals
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | i. using the correct and complete set of drawings
label | ii. all drawings are the latest revision
label | REFERENCE DOCUMENTS: IFC Drawings Drawing Register
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Structural Steel Components
label | FREQUENCY: Where applicable, once, for each component
label | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component. This consists of, but is not limited to:
label | i. Certificate of Compliance
label | ii. Material Certificates and traceability
label | iii. Quality Assurance check sheets
label | iv. Coating certificate(s)
label | v. As-built Drawings to demonstrate compliance with dimensional tolerances of AS5131, Appendix F2
label | Collate: Structural Steel Quality Assurance Documentation so it can be uploaded as a separate attachment (do not attach it here)
label | REFERENCE DOCUMENTS: IFC Drawings Shop Drawings
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Bearing Plate Structural Epoxy Grout, Mortar or Adhesive Product Selection
label | FREQUENCY: Where applicable, once, for each product, prior to use
label | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | i. Have a minimum compressive strength equal to or greater than substrate (if unknown use 40MPa)
label | ii. Thickness constraints suitable to the end use
label | iii. Compressive strength gain suitable to the end use
textbox | Either, Attach: TDS & Approval, or Enter: RFI No.
label | REFERENCE DOCUMENTS: IFC Drawings RFIs, Product TDS
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Bearing Plate Pin Epoxy Resin Product Selection
label | FREQUENCY: Where applicable, once, for each product, prior to use
label | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | i. Have a minimum bond strength equal to or greater than substrate's (if unknown use 1.5MPa)
label | ii. Compressive strength gain suitable to the end use
textbox | Either, Attach: TDS & Approval, or Enter: RFI No.
label | REFERENCE DOCUMENTS: IFC Drawings RFIs, Product TDS
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Pre-replacement
checkpoint | 2.1 Indentification of Defective Bearings
label | FREQUENCY: Each replacement bearing location, when accessible
label | ACCEPTANCE CRITERIA: Ensure that the correct bearings are clearly identified and named using the Temporary Works Design Drawings.
label | REFERENCE DOCUMENTS: Temporary Works Design
label | INSPECTION/TEST METHOD: Document Review, Visual
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Survey of Existing Bearing Plate Heights
label | FREQUENCY: Each replacement bearing location, when accessible
label | ACCEPTANCE CRITERIA: Survey the existing bearings in reference to each other using an arbitrary datum on each pier.
label | ○ Note: a minumum of 2 points to determine RLs.
label | REFERENCE DOCUMENTS: Detailed Works Methodology
label | INSPECTION/TEST METHOD: Measure
label | RECORD OF CONFORMITY: This ITP
label | SCP, HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Existing Conditions for Temporary Works
label | FREQUENCY: Each replacement bearing location, when accessible
label | ACCEPTANCE CRITERIA: Supervisor to inspect of the area where the Temporary Works will be located to ensure that it meets or exceeds the conditions defined in the Temporary Works Design.
label | ○ Photograph/Record: The existing conditions, noting any damage to the piers, including coatings Complete: Temporary Works Permit to Construct
label | REFERENCE DOCUMENTS: Temporary Works Design, Permit to Construct, Apply Load & Remove
label | INSPECTION/TEST METHOD: Visual Measure
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Establishment of Temporary Works
label | FREQUENCY: Each pair of steel girders at each replacement bearing location
label | ACCEPTANCE CRITERIA: All structural steel packers, shims, supports and hydraulic cylinders / jacks are the correct size, grade and locational tolerance nominated on the Temporary Works Design and fixed accordingly.
label | ○ Complete: Temporary Works Permit to Apply Load
label | REFERENCE DOCUMENTS: Temporary, Works Design, Permit to Construct, Apply Load & Remove
label | INSPECTION/TEST METHOD: Visual Measure
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Survey of Existing Track Heights
label | FREQUENCY: Prior to Jacking Operations
label | ACCEPTANCE CRITERIA: Measure both track heights at 5m intervals, staggered 2.5m above all planned the bearing replacement locations.
label | ○ Record: Pre-lift Track Heights
label | REFERENCE DOCUMENTS: Detailed Work Methodology
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP
label | SCP, HP*
label | RESPONSIBILITY: Surveyor, Fulton Hogan Engineer
textbox | Date Completed:
section | Replacement
checkpoint | 3.1 Jacking Operations - Raising
label | FREQUENCY: Each pair of jacking points
label | ACCEPTANCE CRITERIA: Hydraulic jacks to be raised simultaneously in a steady, controlled manner until the maximum height of 25mm is reached.
label | ○ Locking collars to be engaged and hydraulic lines to be disconnected and capped with dust caps.
label | ○ Record: Maximum height and pressure gauge readings for information
label | ○ Record: Any movement or damage to the crossheads Attach: Shore HIre's Jacking Operations ITP
label | REFERENCE DOCUMENTS: Shorehire ITP, Detailed Work Methodology
label | INSPECTION/TEST METHOD: Visual Measure
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Shore Hire, Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.2 Survey of Existing Track Heights
label | FREQUENCY: Post-jacking Operations, Occupation #1 Only
label | ACCEPTANCE CRITERIA: Measure both track heights at 5m intervals, staggered 2.5m above all planned the bearing replacement locations.
label | ○ Record: Post-lift Track Heights
label | ○ Check: The readings are within 25mm from initial survey
label | REFERENCE DOCUMENTS: Detailed Work Methodology
label | INSPECTION/TEST METHOD: Measure
label | RECORD OF CONFORMITY: This ITP
label | SCP, HP*
label | RESPONSIBILITY: Surveyor, Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.3 Removal of Existing Bearing Componentry
label | FREQUENCY: Each defective bearing
label | ACCEPTANCE CRITERIA: Disassemble bearing componetry and safely relocate outside of the Work area.
label | ○ Bearing plate pins to be removed by prizing, levering or other suitable means to minimise damage to the crosshead.
label | ○ Clean the area to remove any loose particles, dust and contaminants.
label | ○ Note: Bearing plates may need to be flame-cut to reduce size and weight.
label | REFERENCE DOCUMENTS: Detailed Work Methodology
label | INSPECTION/TEST METHOD: Visual
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.4 Existing Bearing Plate Pin Holes
label | FREQUENCY: Each bearing plate pin location
label | ACCEPTANCE CRITERIA: Inspect the existing hole depth and locations to ensure compliance with the IFC Drawings - dry-fitting the replacement pin (M30 threaded rod) is recommended.
label | ○ Where necessary, drill or core holes to achieve the required depth. Flush the hole and surrounding area to remove newly created contaminants.
label | REFERENCE DOCUMENTS: Detailed Work Methodology
label | INSPECTION/TEST METHOD: Visual Measure
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.5 Placement of New Bearing Componentry
label | FREQUENCY: Each bearing
label | ACCEPTANCE CRITERIA: Manoeuvre new bearings into position, measuring height and level against pre-determined survey marks using shims where necessary.
label | ○ Raise the bearing, mix and place epoxy bedding mortar onto the concrete surface of the crosshead and lower the bearing into the bedding epoxy mortar.
label | ○ Where bearing components require assembly, place and tighten bolts to snug tight conditions.
label | REFERENCE DOCUMENTS: Detailed Work Methodology, Product TDS
label | INSPECTION/TEST METHOD: Visual Measure
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 3.6 Placement of Bearing Plate Pins
label | FREQUENCY: Each pin
label | ACCEPTANCE CRITERIA: While the bearing epoxy bedding mortar is wet, mix and inject epoxy bonding resin into each holes.
label | ○ Insert the replacement bearing plate pins into the awaiting holes until the washer seats onto the top surface of the bearing plate.
label | ○ Clean any residue from the plate before it sets.
label | REFERENCE DOCUMENTS: Detailed Work Methodology, Product TDS
label | INSPECTION/TEST METHOD: Visual
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Post-replacement
checkpoint | 4.1 Removal of Temporary Works
label | FREQUENCY: Each pair of steel girders at each replacement bearing location
label | ACCEPTANCE CRITERIA: Inspect any epoxy bedding mortar to determine if sufficient time has elapsed for it to have achieve the same strength of the crosshead (if unknown, use 40MPa).
label | ○ Where a skim coat for levelling purposes has been applied, check that it has hardened.
label | ○ Complete: Temporary Works Permit to Remove
label | REFERENCE DOCUMENTS: Temporary Works Design, Permit to Construct, Apply Load & Remove
label | INSPECTION/TEST METHOD: Visual
label | RECORD OF CONFORMITY: This ITP
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 4.2 Jacking Operations - Releasing
label | FREQUENCY: Each pair of jacking points
label | ACCEPTANCE CRITERIA: Hydraulic jacks to be lowered simultaneoulsy in a steady, controlled manner until the new bearings are supporting the super-structure and the pressure gauges read 0MPa.
label | ○ Complete: Shore Hire's Jacking Operations ITP Photograph/Record: The new conditions, noting any damage to the piers, including coatings
label | REFERENCE DOCUMENTS: Shorehire ITP, Detailed Work Methodology
label | INSPECTION/TEST METHOD: Visual Measure
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Shore Hire, Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 4.3 Survey of Existing Track Heights
label | FREQUENCY: Post-bearing replacement
label | ACCEPTANCE CRITERIA: Measure both track heights at 5m intervals, staggered 2.5m above all planned the bearing replacement locations.
label | ○ Record: Post-bearing Replacement Track Heights Check: The readings are within 25mm from initial survey.
label | REFERENCE DOCUMENTS: Detailed Work Methodology
label | INSPECTION/TEST METHOD: Measure
label | RECORD OF CONFORMITY: This ITP
label | SCP, HP*
label | RESPONSIBILITY: Surveyor, Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 4.4 Protective Coating Touch-up
label | FREQUENCY: Where required
label | ACCEPTANCE CRITERIA: Where required, apply a tocuh-up to the bearing's protective coating following the coating specification.
label | REFERENCE DOCUMENTS: Coating Specification
label | INSPECTION/TEST METHOD: Visual
label | RECORD OF CONFORMITY: This ITP
label | IP
label | RESPONSIBILITY: Fulton Hogan
textbox | Date Completed:
checkpoint | 4.5 Client Inspection
label | FREQUENCY: Before the end of the occupation
label | ACCEPTANCE CRITERIA: Prior to the occupation being closed, a joint inspection is to occur with the Client to ensure that the replacement bearings are fit for purpose and any damage to the crossheads of coatings is complete.
label | REFERENCE DOCUMENTS: Detailed Work Methodology
label | INSPECTION/TEST METHOD: Visual
label | RECORD OF CONFORMITY: ConQA Hold Point Release
label | HP
label | RESPONSIBILITY: Client
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with Fulton Hogan’s Quality Management Plan and verifies lot compliance with the IFC Drawings, nominated specifications & standards.
textbox | Print Name:
textbox | Position:
textbox | Date: