## Checklists ITPs
type | name | values | prefix | "Add+" Template Name | Q's for CONQA
checklist | QA4 - Installation Test Sheet (Waste, Vent, Downpipes etc) |  |  | QA 4 - Installation Test Sheet (Waste, Vent, Downpipes etc.)
checkpoint | Installation Test Sheet:
text | Drawing No.:
text | Rev.:
checkpoint | PIPE CLIP HANGERS
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | MATERIAL AND SIZE
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | ALIGNMENT
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | LABELLING AND IDENTIFICATION
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | JOINTING
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | PENETRATION SEALING
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | FIRE STOP COLLARS
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | TESTING
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | AUTHORITY INSPECTION (if applicable)
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | AS BUILT INFORMATION UPDATED ONTO DRAWINGS
text | Details:
text | Tester:
text | Date:
text | Notes:
checklist | checklist |  |  | Project Photos
checkpoint | Upload Photos and Comments below
checklist | QA5 - Installation Test Sheet (Cold Water, Hot Water & Flusher Line) |  |  | QA 5 - Installation Test Sheet (Cold Water, Hot Water & Flusher Line)
checkpoint | Installation Test Sheet:
text | Drawing No.:
text | Rev.:
checkpoint | PIPE CLIP HANGERS
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | MATERIAL AND SIZE
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | ALIGNMENT
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | LABELLING AND IDENTIFICATION
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | JOINTING
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | PENETRATION SEALING
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | FIRE STOP COLLARS
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | PRESSURE TESTING COMPLTED (QA6)
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | AUTHORITY INSPECTION (if applicable)
text | Details:
text | Tester:
text | Date:
text | Notes:
checkpoint | AS BUILT INFORMATION UPDATED ONTO DRAWINGS
text | Details:
text | Tester:
text | Date:
text | Notes:
checklist | QA11 - Equipment Calibration Register |  |  | QA 11 - Equipment Calibration Register
checkpoint | 1
text | Equipment Type:
text | Manufacturer:
text | Model and Type:
text | Serial No.:
text | Next Service Due:
checkpoint | 2
text | Equipment Type:
text | Manufacturer:
text | Model and Type:
text | Serial No.:
text | Next Service Due:
checkpoint | 3
text | Equipment Type:
text | Manufacturer:
text | Model and Type:
text | Serial No.:
text | Next Service Due:
checkpoint | 4
text | Equipment Type:
text | Manufacturer:
text | Model and Type:
text | Serial No.:
text | Next Service Due:
checkpoint | 5
text | Equipment Type:
text | Manufacturer:
text | Model and Type:
text | Serial No.:
text | Next Service Due:
checkpoint | 6
text | Equipment Type:
text | Manufacturer:
text | Model and Type:
text | Serial No.:
text | Next Service Due:
checkpoint | 7
text | Equipment Type:
text | Manufacturer:
text | Model and Type:
text | Serial No.:
text | Next Service Due:
checkpoint | 8
text | Equipment Type:
text | Manufacturer:
text | Model and Type:
text | Serial No.:
text | Next Service Due:
checkpoint | 9
text | Equipment Type:
text | Manufacturer:
text | Model and Type:
text | Serial No.:
text | Next Service Due:
checkpoint | 10
text | Equipment Type:
text | Manufacturer:
text | Model and Type:
text | Serial No.:
text | Next Service Due:
checklist | QA 18 - Gasket Installation |  |  | QA 18 - Gasket Installation
checkpoint | Gasket Installtion:
text | Location/Identification:
text | Nominal Bolt Size:
text | Gasket Contact Surface Finish on Flange:
text | Lubricant used:
label | 1. Galvanised nuts and bolts  must use good quality lubricating oil on threads
label | 2. Below Ground Galvanised nuts and bolts must denzo and plastic wrap full flange and cover bolts
label | 3. Stainless steel nuts and bolts  must use anti seize / molybond on threads  must return 24 hrs later to tighten in sequence and required torque
label | 4. Galvanised nuts and bolts on stainless steel flanges / backing rings - Thinsulators (insulating top hats) or insulating washer with thin PE sleeve must be used, and complete flange must be denzo wrapped with plastic protection
label | 5. Stainless Steel nuts and bolts on galvanised steel flanges / backing rings - Thinsulators (insulating top hats) or insulating washer with thin PE sleeve must be used, and complete flange must be denzo wrapped with plastic protection
label | 6. Zinc bolts, nuts and washers rust when used externally  use galvanised
checkpoint | Visually examine and clean flanges, bolts, nuts and washers. Replace components if necessary. Alignment of flange faces is very important and maintain support of the flange, pipework and valve at all times
checkpoint | Lubricate bolts, nuts AND flange surface AROUND BOLT HOLES, not on flange/gasket surface, or use hardened steel washers. Use anti-seize on stainless steel threads and nuts or on galvanised bolts and nuts lightly oil with good quality lubricating oil. Insert bolts in locations 1 to 4 as indicated in the below diagrams.
checkpoint | Install new gasket. DO NOT REUSE OLD GASKET, OR USE MULTIPLE GASKETS. Gaskets for water applications must be EPDM potable water gasket PN16 type. Gaskets for gas need to be AGA and GPL approved
checkpoint | Number bolts in cross-pattern sequence according to the appropriate sketch below with a marker pen, black or white
checkpoint | IMPORTANT! HAND TIGHTEN; then PRE-TIGHTEN BOLTS to 7Nm torque, but DO NOT EXCEED 20% of Target Torque. Target torque is required to be supplied by Gasket manufacturer / supplier  seek from GPL foreman
checkpoint | Check gap for uniformity.
checkpoint | Use the appropriate cross-pattern tightening sequence in the sketch below for Rounds 1,2 and 3 and/or Round 4 (each sequence constitutes a Round )
checkpoint | Final Torque
text | Final torque*: |  | (Nm)
label | * Refer to gasket manufacturer spec with torque chart on next page and GPL advice
label | Lubricate, Hand Tighten, Pre-Tighten bolts (5% of final torque) (as mentioned in item 5 above)
text | Round 1  Tighten to: |  | (Nm)
text | Round 2  Tighten to: |  | (Nm)
text | Round 3  Tighten to: |  | (Nm)
label | Check gap around the circumference between each of these rounds, measured at every other bolt. If the gap is not reasonably uniform around the circumference, make the appropriate adjustments be selective bolt tightening before proceeding.
label | Final Rotational Round  100% of Final Torque (same as Round 3 or 4 above). Use ROTATIONAL, clockwise tightening sequence starting with Bolt No.1, for one complete round and continue by selective bolt tightening before proceeding.
label | Short-term bolt preload loss can occur between four to twenty-four hours after initial tightening due to bolt relaxation. Consider retightening to help recover this loss.
select | Tightening Method Used: | Hydraulic Torque Wrench, Impact Wrench, Manual Torque Wrench, Other,Hand Wrench
text | Other:
text | Where was torque information provided from:
text | Joint Assembler Name:
holdpoint | Joint Assembler Signature
checklist | QA 8.1F - Installation of Stormwater Pit Checklist |  |  | QA 8.1F - Installation of Stormwater Pit Checklist
checkpoint | Stormwater Pit Installation Report Details:
text | Pit Number:
text: | Pit Type:
text | Project Specification:
text | Drawing & Revision no.:
text: | Shop Drawings no:
text: | RL of the bottom of the pit
checkpoint | Bedding material, placement and compaction meets specification.
text: | Spec#:
text: | Material used:
checkpoint | Pit installation
text | Date Installed:
text: | Pit Base:
text: | Step Irons - GPL Initial/Date:
text: | Outlet IL
button | Placement of cover | Yes, No
button | Concreting of cover | Yes,No
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Builder Representative Sign-Off added below | Yes,No
checkpoint | Backfill
Text: | Spec#: Project Specification
Text: | Material used:
checkpoint | Hand-over Photos
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Builder Group Signature Sign-Off added below | Yes,No
checklist | QA 8.1C - Below Ground Pipework Checklist - Fire |  |  | QA 8.1C - Below Ground Pipework Checklist - Fire
checkpoint | Principal Contractor Permits Issued
checkpoint | Set out trench depths and runs.
label | Project drawing #
label | Shop drawing #
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
label | Spec#: AS3500
text | Material used
button | Approved by Principal | Yes,No
checkpoint | Bedding placement and compaction and material meets specification.
label | Spec#: AS3500 and Hydraulic Specification
text | Geschke - Initial/Date
text | Comments
checkpoint | Jointing of pipes
Text | Jointing type
Text | Attach welding checklist if applicable
text | Geschke - Initial/Date
text | Comments
checkpoint | Hydrostatic tests are carried out as required.
button | GPL QA6 form completed | Yes,No
label | Fire system tested to 1700 kpa regularly prior to finished surfaces installed. Independent fire test at completion.
checkpoint | Placement and compaction of backfill and material meets spec.
button | Compacted backfill as per the Specification | Yes, no
label | Detectable marker tape
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings
label | To be provided
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Builder Representative Sign-Off added below | Yes,No
checklist | QA 8.1D - Below Ground Pipework Checklist - Water |  |  | QA 8.1D - Below Ground Pipework Checklist - Water
checkpoint | Principal Contractor Permits Issued
checkpoint | Set out trench depths and runs.
text | Project drawing #
text | Shop drawing #
text | Depth of the installed run
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
label | Spec#: AS3500
text | Material used
button | Approved by Principal | Yes,No
checkpoint | Bedding placement and compaction and material meets specification.
label | Spec#: AS3500 and Hydraulic Specification
text | Geschke - Initial/Date
text | Comments
checkpoint | Jointing of pipes
Text | Jointing type
Text | Attach welding checklist if applicable
text | Geschke - Initial/Date
text | Comments
checkpoint | Hydrostatic tests are carried out as required.
button | GPL QA6 form completed | Yes,No
text | Water system tested to (kPa)
checkpoint | Placement and compaction of backfill and material meets spec.
button | Compacted backfill as per the Specification | Yes, no
label | Detectable marker tape
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings
label | To be provided
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Builder Representative Sign-Off added below | Yes,No
checklist | QA 8.1E - Below Ground Pipework Checklist - Gas |  |  | QA 8.1E - Below Ground Pipework Checklist - Gas
checkpoint | Principal Contractor Permits Issued
checkpoint | Set out trench depths and runs.
text | Project drawing #
text | Shop drawing #
text | Depth of the installed run
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
label | Spec#:
text | Material used
button | Approved by Principal | Yes,No
checkpoint | Bedding placement and compaction and material meets specification.
label | Spec#: AS3500 and Hydraulic Specification
text | Geschke - Initial/Date
text | Comments
checkpoint | Jointing of pipes
Text | Jointing type
Text | Attach welding checklist if applicable
text | Geschke - Initial/Date
text | Comments
checkpoint | Hydrostatic tests are carried out as required.
button | GPL QA6 form completed | Yes,No
text | System tested to (kPa)
checkpoint | Placement and compaction of backfill and material meets spec.
button | Compacted backfill as per the Specification | Yes, no
label | Detectable marker tape
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings
label | To be provided
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Builder Representative Sign-Off added below | Yes,No
checklist | QA 6 - Quality Control Pressure Test Report |  |  | QA 6 - Quality Control Pressure Test Report
checkpoint | Quality Control Pressure Test Report:
text | Drawing No.:
text | Rev.:
button | Test: | Air,Water
text | Section
text | From
text | To
text | Applicable Standard No.
label | Specified System Working
text | Pressure (KPA)
text | Duration (HRS)
label | Specified System Test
text | Pressure (KPA)
text | Duration (HRS)
checkpoint | 1st Reading
text | Time
text | KPA
text | Ambient Temp
checkpoint | 2nd Reading
text | Time
text | KPA
text | Ambient Temp
checkpoint | Test Result - Passed?
text | Repeat
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Builder Representative Sign-Off added below | Yes,No
checklist | QA 32 - Water Services Flushing |  |  | QA 32 - Water Main Flushing
checkpoint | Water Services Flushing Details:
text | Zone/Pod No's:
Bool | Mains
Bool | Cold Water
Bool | Fire Hydrant
Bool | RW
checkpoint | As built information updated onto drawings
label | Ongoing
label | To be provided
checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | FINAL SIGN OFF - Pass when work completed and signed off by Geschke Supervisor
label | Company: Geschke Group
label | Phone: 03 9798 1619
label | Address: 45 Pacific Drive, Keysborough
checkpoint | Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Supervisor Sign-Off added below | Yes, No
button | Principal Contractor Representative Sign-Off added below | Yes, No
checklist | QA 30 Fixture / Hydraulic Installation |  |  | QA 30 - Fixture / Hydraulic Installation
checkpoint | What is being installed?
Bool | WC
Bool | Shower
Bool | Basin
Bool | Sink
Bool | Tapware
Bool | Boiling Water Unit
Bool | TMV Cover
Bool | RPZD Cover
Bool | Other (Specify Below)
text | Other (Specify Below)
checkpoint | Where is this fixture being installed?
text | Location
checkpoint | Have all parts been connected/completed and tested? - Pass = Yes / Fail = No (Detail why below)
checkpoint | Photos of installation been taken and uploaded below
checklist | QA 7 - Commissioning Test Report |  |  | QA 7 - Commissioning Test Report
checkpoint | Commissioning Test Report:
textbox | Zone/Grid:
textbox | Drawing No.:
textbox | Rev.:
checkpoint | Item: FIXTURE OPERATION - Pans, Basins, Sinks, Other
note | Test:
note | Performance Test CL 2.20
note | Fill fixture with water remove plug
note | Test for:
note | Leaks
note | Loss of water
note | Seal in Trap
note | Induce siphonage in trap of adjacent fixture
note | Complete draining of fixture
textbox | OK:
textbox | Not OK:
checkpoint | Item: Water Supply
note | Test:
note | Performance Test CL 2.20
note | Check for adequate water volume.
note | Flush out pipework
note | Clean aerator
note | Water hammer
textbox | OK:
textbox | Not OK:
checkpoint | Item: Flush Performance
note | Test:
note | Performance Test
note | Check for:
note | Water Volume
note | Duration of flush
note | Flush out pipework
note | Water hammer
textbox | OK:
textbox | Not OK:
checkpoint | Other
checklist | QA 13 - Backflow Prevention Device Test Report |  |  | QA 13 - Backflow Prevention Device Test Report
checkpoint | Backflow Prevention Device Test Report Details:
textbox | Owner/Occupier:
textbox | Address:
note | Licence: 50043
button | Type of Test: | Annual Test, Installation Test
textbox | Location of Device:
textbox | Authorized Tester Name:
textbox | Test Kit Serial No.
textbox | Tester Licence No.:
textbox | Test Kit Calibration Date:
textbox | Date of Test:
checkpoint | Device Details and Test Results
button | Permission to Isolate Water Supply | No,Yes
note | Device:
textbox | Make:
textbox | Size:
textbox | Model No.:
textbox | Serial No.:
button | Is the device installed high enough to prevent ingress of any possible contaminated water? | No,Yes
tickbox | Containment Protection
tickbox | Individual Protection
tickbox | Zone Protection
button | Strainer Installed | No,Yes
button | Strainer Cleaned | No,Yes
button | Device Type | Double Check Valve, RPZD (Reduced Pressure Zone Device)
note | Valve
textbox | Check Valve 1
textbox | Check Valve 2
textbox | Relief Valve
note | Testing Results
textbox | Close tight at:
tickbox | Leaked
textbox | Close tight at:
tickbox | Leaked
textbox | Opened at:
tickbox | Leaked
note | Reason for the device failure
tickbox | Incorrect position
tickbox | Incorrect installation
tickbox | Foreign material in the device
tickbox | Spring wear damage
tickbox | Seal or Rubber Damage
tickbox | Other
textbox | Other:
note | Test after maintenance
textbox | Close tight at:
tickbox | Leaked
textbox | Close tight at:
tickbox | Leaked
textbox | Opened at:
tickbox | Leaked
button | Water turned back on | Yes, No
textbox | Describe the maintenance:
textbox | Parts used in repair:
button | Is the device installed correctly | Yes, No
checkpoint | Test Result
textbox | Tester Name:
textbox | Date:
signoff | Add Signature
checklist | QA 19 - Service Cross Connection Check List Report |  |  | QA 19 - Service Cross Connection Check List Report
checkpoint | Service Cross Connection Check List Report Details:
textbox | Zone/Grid:
textbox | Drawing No.:
textbox | Rev:
checkpoint | Service to be tested
note | Isolation of potable supply in general.
checkpoint | Potable Water Supply
note | Confirmation of service isolation at all fixtures.
note | Keep potable water turned off.
checkpoint | Non Potable Supply
note | Confirmation of water flow for non potable water supply at each non potable fixture while potable is still isolated.
checkpoint | Turn potable back on
note | Potable back on
checkpoint | Non potable supply
note | Isolate non potable water flow and prove that each non potable fixture has no water flow.
checkpoint | Potable Supply
note | Check all fixtures that receive potable water are still getting potable water.
checkpoint | Pipe Identification
note | Confirm recycled water piping is identified by colour and noteling.
checkpoint | Other
checkpoint | Conducted by
text | Conducted by:
checklist | QA 33- Installation of in-ground tank |  |  | QA 33 - Installation of in-ground tank
checkpoint | Tank Installation Report Details:
text | Number / Name:
text: | Tank Type:
text | Drawing & Revision no.:
text: | Shop Drawings no:
checkpoint | Bedding material, placement and compaction meets specification.
text: | Material used:
checkpoint | Tank installation
text | Date Installed:
text: | Pit Base:
text: | Inlet IL
text: | Outlet IL
checkpoint | Backfill
Text: | Material used:
checkpoint | Hand-over Photos
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Builder Group Signature Sign-Off added below | Yes,No
checklist | 8.1B Stormwater Drainage Checklist |  |  | 8.1B - Stormwater Drainage Checklist
checkpoint | Stormwater Drainage Inspection Report Details:
text | Spec No.:
text | Drawing & Revision no.:
text: | Shop Drawings no:
text: | Starting IL established:
checkpoint | Pipes and fittings comply with relevant Authority and Specification
label | Spec#: AS3500 and Project Specification
text | Materials used, Size and Class:
button | Approved by Principal | Yes,No
checkpoint | Pipe Lines
text | Date started:
text | Drainage Line Number:
button | Pipe Damaged? | Yes,No
text | Jointing Required
button | Bedding and Haunching | Yes,No
checkpoint | Bedding material, placement and compaction meets specification.
label | Spec#: AS3500 and Project Specification
Text: | Material used:
Text: | Docket #:
text | GPL - Initial/Date
text | Builder - Initial/Date
checkpoint | Laying and jointing of pipes - RL and fall
Text: | Jointing Type:
Text: | Fall:
Text" | AS3500
Text: | RL's as installed
text | GPL - Initial/Date
text | Builder - Initial/Date
checkpoint | Backfill
label | Spec#: AS3500 and Project Specification
Text: | Material used:
Text: | Docket #:
checkpoint | Pit Sign off: Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Builder Representative Sign-Off added below | Yes,No
checklist | QA 8.1G - Sewer Rising Main (Poly) |  |  | QA 8.1G - Sewer Rising Main (Poly)
checkpoint | Principal Contractor Permits Issued
checkpoint | Set out trench depths and runs.
text | Project drawing #
text | Shop drawing #
text | Depth of the installed run
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
label | Spec#: AS3500
text | Material used
button | Approved by Principal | Yes,No
checkpoint | Bedding placement and compaction and material meets specification.
label | Spec#: AS3500 and Hydraulic Specification
text | Geschke - Initial/Date
text | Comments
checkpoint | Jointing of pipes
Text | Jointing type
Text | Attach welding checklist if applicable
text | Geschke - Initial/Date
text | Comments
checkpoint | Hydrostatic tests are carried out as required.
button | GPL QA6 form completed | Yes,No
text | Pipeline tested to (kPa)
checkpoint | Placement and compaction of backfill and material meets spec.
button | Compacted backfill as per the Specification | Yes, no
label | Detectable marker tape
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings
label | To be provided
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Builder Representative Sign-Off added below | Yes,No