## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | QA 8.1G - Sewer Rising Main (Poly) | [5 empty] | QA 8.1G - Sewer Rising Main (Poly)
section | Details
checkpoint | Principal Contractor Permits Issued
checkpoint | Set out trench depths and runs.
textbox | Project drawing #
textbox | Shop drawing #
textbox | Depth of the installed run
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
label | Spec#: AS3500
textbox | Material used
button | Approved by Principal | Yes,No
checkpoint | Bedding placement and compaction and material meets specification.
label | Spec#: AS3500 and Hydraulic Specification
textbox | Geschke - Initial/Date
textbox | Comments
checkpoint | Jointing of pipes
textbox | Jointing type
textbox | Attach welding checklist if applicable
textbox | Geschke - Initial/Date
textbox | Comments
checkpoint | Hydrostatic tests are carried out as required.
button | GPL QA6 form completed | Yes,No
textbox | Pipeline tested to (kPa)
checkpoint | Placement and compaction of backfill and material meets spec.
button | Compacted backfill as per the Specification | Yes, no
label | Detectable marker tape
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings
label | To be provided
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Builder Representative Sign-Off added below | Yes,No
checklist | QA 8.1A - Below Ground Sewer Checklist | [5 empty] | QA 8.1A - Below Ground Sewer Checklist
section | Details
checkpoint | Principal Contractor Permits Issued
checkpoint | Set out pits, trench depths and runs.
textbox | Drawing & Revision #
textbox | Survey setout completed by:
textbox | Starting IL established - enter IL
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
label | Spec#: AS3500 and Hydraulic Specification
textbox | Materials used:
button | Approved by Principal | Yes,No
checkpoint | Bedding material, placement and compaction meets specification.
label | Spec#: AS3500 and Hydraulic Specification
textbox | Material used:
checkpoint | Laying and jointing of pipes - RL and fall
textbox | Jointing Type:
textbox | Fall:
textbox | AS3500
textbox | RL's as installed
checkpoint | Connections to pits and existing services as per Hydraulic Specification and Australian Standards
checkpoint | Check of each inlet
textbox | Comments
checkpoint | Service run was inspected prior being covered
button | Geschke Group Signature Sign-Off added below | Yes,No
checkpoint | Hydrostatic tests are carried out as required.
button | Air or Water? | Water,Air
button | Inspected and recorded by Independent Certifier or PIC | Yes,N/A, No
textbox | Geschke - Initial/Date
textbox | Principal- Initial/Date
checkpoint | Placement and compaction of backfill and material meets spec
textbox | Material used:
checkpoint | Temporary cover provided to open drain.
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings
button | Drain installed as per nominated drawing | Yes,No
textbox | Comments
checkpoint | Invert levels checked by a surveyor
label | As Built drawings to be updated as required
checkpoint | Work(s) completed to specification/drawings & Area left clean/tidy
label | FINAL SIGN OFF - Pass when work completed and signed off by Geschke Supervisor
label | Company: Geschke Group
label | Phone: 03 9798 1619
label | Address: 45 Pacific Drive, Keysborough
checkpoint | Foreman/QA Officer Sign-Offs completed - Click to Attach Signature(s) below
button | Geschke Group Signature Sign-Off added below | Yes,No
button | Principal Sign-Off added below | Yes,No