## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | CHK-007-STR-Material Inspection-Precast Barrier Kerb Rev 0 | itp | CHK-007-STR-Material Inspection-Precast Barrier Kerb |  | dcd269e2-52fc-4e4e-9293-64d08944e7a2
| section | Details
| checkpoint-no-value | CHK-007-STR-Material Inspection-Precast Barrier Kerb
e469640e-3c01-5ed7-9fc3-eeb71270911e | note | Document Title: CHK-001-STR-CPD-Material Inspection-Precat Barriers & Kerbs
fae92e32-3bb4-57dd-ad1d-ade7635cf64b | note | ITP Description: CPD-Material Inspection-Precat Barriers & Kerbs
1f5c1b7f-6b2b-5ce5-bb1a-9539e5e93e99 | note | Discipline (e.g. CIV/STR/RAIL): STR
11a794b9-a787-5911-aa0e-95fd5afd65c8 | note | Revision Number: 0
216bca35-8d09-5ad8-a1f1-65aa8b9cbbaa | note | Revision Date: 14/11/2024
8d87d9a0-7d15-598b-affe-675e7189c4ae | note | ITP created by: Ahmed Abdelsalam
90e2e9a0-a505-5c44-b985-768dad6329d7 | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1 - Delivery Details
5afe63df-1959-55e0-9c02-18348a624c95 | note | Acceptance Criteria -
432a6b00-8939-57b9-aee2-bd11fcce45e1 | textbox | Enter: Delivery Docket Number:
3b3e115e-eac9-507e-a24c-0b54eda8740e | textbox | Enter: Delivery Date:
ba2f1975-2484-5138-9e07-7afb8bbb0ac4 | textbox | Enter: Element ID (s):
616c1f8a-7c02-5b8f-bacb-8f0e20e24619 | note | ○ Attach: Delivery Docket and packaging Slip
e7d5fb1a-8168-57c9-ac75-2956bd9d979e | note | Method - Document Review, Visual
59550ca9-5b3c-5389-8acc-49fa34123e95 | note | Frequency - Each Delivery
75288f34-99b3-5803-a85a-808373fdbc56 | note | Category - IP
efe2a752-9e61-5094-9c8e-0814ebc5913f | note | Responsibility - PE/SE
35240e98-fa09-5c91-b10a-8247c3a181bb | note | Verifying Documents - This Checklist
65a9f303-805f-5d09-abb3-838c10299453 | date | Date Completed:
| checkpoint | 2 - Packaging Inspection-Quantity
2d781e84-61db-5aaa-a7d1-16818c6f8ba1 | note | Acceptance Criteria - Does the number of packages in the delivery match that listed on the freight list/packaging slip?
369b570a-818d-5bfd-8630-c5b01930b41e | note | Method - Visual
30b9c5db-acb4-544a-8f24-e39fcd53f468 | note | Frequency - Each Delivery
568bb209-33ef-5188-b43f-4066f060cf3d | note | Category - IP
a30982b9-800c-5fdd-bbb2-a6d19b3e2022 | note | Responsibility - PE/SE
2963adf6-24e8-594e-b680-5d6cd6ff019d | note | Verifying Documents - This Checklist
086531de-f20c-5de3-b99d-e810583198b6 | date | Date Completed:
| checkpoint | 3 - Packaging Inspection-Delivery Contents
6194e9a0-c606-58f2-be84-f2f05fd21d88 | note | Acceptance Criteria - Do the contents of the delivery match the freight list/packaging slip?
ff183877-0a32-52f1-a5fa-2f3c4413d460 | note | Method - Document Review, Visual
264c4f04-99b2-52af-a49f-537fd015bbf6 | note | Frequency - Each Delivery
fe7de8c6-a226-59c7-8a84-d14687db7342 | note | Category - IP
49852d9d-7902-5b9f-9ef0-3ca9a0061d07 | note | Responsibility - PE/SE
5e8c51d1-9ba1-5e11-a234-25b94a9df41d | note | Verifying Documents - This Checklist
b72702ed-eebe-5772-a770-64cb7fe96432 | date | Date Completed:
| checkpoint | 4 - Packaging Inspection-Birth Certificate
eefdac6e-56af-5b6d-8518-155569e47ddd | note | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
f679be31-e1e6-5213-aab5-4c10aca50cd0 | note | ○ Precast components are to be marked on the birth certificate.
887e9375-055a-5521-9c53-591430cd8bfd | note | ○ Cast date and lot are to be marked on the birth certificate.
72253f60-4e80-5651-a4bb-407b96b1cf8b | note | Method - Document Review
6bb19e26-7c40-52bc-bd22-63101d22f498 | note | Frequency - Each Precast item
a5e942ea-5e38-5c53-8804-ba2de20f3e59 | note | Category - IP
1e05cbb6-f07a-5a4f-9a8e-2f64ac8ac87b | note | Responsibility - PE/SE
aa91501e-3bba-5c14-b675-d0f6ebf71c3e | note | Verifying Documents - This Checklist
1a060393-24ac-5d0d-8c5d-64bcd3b338bb | date | Date Completed:
| checkpoint | 5 - Packaging Inspection-Transport
56fbdfb3-c2c0-59a1-929c-a06192a8a98d | note | Acceptance Criteria - Is the condition of packaging acceptable.
4482d5e9-7cca-5c08-a4af-f7e911839251 | note | ○ Precast items are protected from damage during the transport
04e39873-534f-544e-8017-8ebea06586a3 | note | Method - Visual
b2523e62-c3fc-516c-a88e-493ad0db5231 | note | Frequency - Each Precast item
68a94509-5f89-5eea-a49e-93e60c29f075 | note | Category - IP
0d5550ce-b517-54e8-8c25-18d07b339c9c | note | Responsibility - PE/SE
a4cbe996-6671-5f52-b005-3b51f285cc80 | note | Verifying Documents - This Checklist
bf411180-4897-5cfd-abb6-d269644dc22a | date | Date Completed:
| checkpoint | 6 - Fault IDs:
939f8944-e534-5133-a686-e578a873fed7 | note | Acceptance Criteria - For each precast type delivered, check for the following:
7982b518-a35f-5873-8dcf-15d84ca6690b | note | 1 - Identification markings match the panel type
c89d62dd-3ffe-547a-8f51-c25286374195 | note | 2 - Panels fabricated as per drawings
f43542f0-0730-5204-8573-176803e51c7f | note | 3 - Cracks
78763097-2d5f-525e-a919-597ea0212bc5 | note | 4 - Spalling/Damage to concrete surface
8a72dff5-ac8b-5add-93c3-7986094a1ae3 | note | 5 - Exposed Reinforcement
6b512374-128d-5df2-943b-ea6972d0a48c | note | 6 - Damage to Anti-Graffiti coating
39bc54ef-643f-55ea-8542-f39da5f27522 | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
ce71e41b-61f1-5a42-a771-362da0a42150 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 1
cb2e5740-f2ae-5e2f-9756-a57f1e167821 | note | Reference - Item 6 on this Checklist
74081c42-f939-5bec-8fe7-5416275335f8 | note | Acceptance Criteria - For Each Precast type delivered:
eebfd5e7-7812-5bbd-9f40-2fed1c7f6d71 | textbox | Enter: Panel Identification:
6f76945f-6d8c-585f-8edc-73f03c9c36ef | textbox | Enter: Quantity:
ce5aec17-5de1-53ab-82e1-b04b13163cbb | textbox | Enter: Fault ID if any:
9ef251d7-aa28-5077-9268-9e0f6428ef4d | note | Method - Visual, Measure
0234c31e-d84a-59a5-8f78-ab6e615c1b8c | note | Frequency - Each precast type delivered
84199d18-ef68-5be8-84fc-46a3a0230183 | note | Category - IP
78d17ee3-e0ac-5644-9dc0-3aa7791ff0dd | note | Responsibility - PE/SE
822695b1-2c68-531f-aaef-0aa8a90a996a | note | Verifying Documents - This Checklist
8e19a4aa-cc5b-5826-827d-815e31121474 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 2
6d9eddd5-4fb9-5ffe-a990-60c80c6863bd | note | Reference - Item 6 on this Checklist
bdfce283-101b-5d96-89a0-43d1fba73ab5 | note | Acceptance Criteria - For Each Precast type delivered:
f2ae48df-969e-5709-97de-a72050ba9242 | textbox | Enter: Panel Identification:
504eb1dc-ea42-55b1-bfba-7a6340da04a9 | textbox | Enter: Quantity:
8846ec9f-06fb-514f-b6c2-895021b4492b | textbox | Enter: Fault ID if any:
0d75ca2b-fda8-5d0b-9af1-0ad28286631e | note | Method - Visual, Measure
09672778-da8b-502f-ae0b-7ede357a9202 | note | Frequency - Each precast type delivered
611e8a2f-3aab-5022-a490-b954cc42db68 | note | Category - IP
80793d0c-b70e-554e-a524-566722badd54 | note | Responsibility - PE/SE
2b47d4e7-2caa-59c3-80b3-2203262b9641 | note | Verifying Documents - This Checklist
47dc582f-0786-52dc-b73f-125095fb2126 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 3
22256d15-28c1-54dd-b072-1a85566dc108 | note | Reference - Item 6 on this Checklist
e7402e77-bcd3-57c9-bd8f-baa8feff9c22 | note | Acceptance Criteria - For Each Precast type delivered:
5af4e06d-6e9a-5518-bec4-79daf72dd593 | textbox | Enter: Panel Identification:
eeab3a8e-6c67-59a8-9f65-2e9cd5f1d123 | textbox | Enter: Quantity:
612008cb-80ec-5674-b931-160fc982215f | textbox | Enter: Fault ID if any:
0cbdc9ea-2789-560f-a379-ffd3ae25d6cc | note | Method - Visual, Measure
bfebb9c9-2184-5db9-9e6b-cac1df1760f0 | note | Frequency - Each precast type delivered
f209954c-c4ab-5237-ab6d-f0f8b007246f | note | Category - IP
e1c4a3fd-2135-5c6a-a20b-40a3c0234781 | note | Responsibility - PE/SE
8c7a252c-72df-5081-bd4e-67c93ec3acc7 | note | Verifying Documents - This Checklist
a5e50592-ab52-5f03-8734-4a75ebdd5520 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 4
69db7343-da9e-5b21-84cf-2634ec2922ef | note | Reference - Item 6 on this Checklist
b6ad2bc8-42a2-51d6-8e65-6b542773f42f | note | Acceptance Criteria - For Each Precast type delivered:
15a23a9d-a71a-5af1-9b6e-ee964692dae8 | textbox | Enter: Panel Identification:
b2a08a7f-fc40-5ff1-b021-1f745974eba4 | textbox | Enter: Quantity:
f4bf8ca7-769a-50fd-84d3-d640442f2eb8 | textbox | Enter: Fault ID if any:
c70502d9-c3e0-5886-be51-bc22912ba809 | note | Method - Visual, Measure
7017341d-2cd7-5208-93a2-b6932ddeefb4 | note | Frequency - Each precast type delivered
134184ca-2190-5905-80a1-07804d33541e | note | Category - IP
3b9e7bf8-eac0-5c9a-8570-d28e8f57ad33 | note | Responsibility - PE/SE
93600b47-ed92-52ea-95a6-92acaa92da77 | note | Verifying Documents - This Checklist
fdccf58d-ae7f-5ea0-89fa-d7fe3415ad07 | date | Date Completed:
| checkpoint | 7 - Check for Faults - 5
a29e2cb8-72b8-5950-9e2c-8b26f121ff14 | note | Reference - Item 6 on this Checklist
a0343fad-141a-554e-9149-e73c399b672c | note | Acceptance Criteria - For Each Precast type delivered:
48158eae-2f23-5c6b-8e43-90089bb22cc9 | textbox | Enter: Panel Identification:
cb04520a-e075-5ac2-8d83-c884ace45ee8 | textbox | Enter: Quantity:
53e1ab9f-9013-58d5-b33e-7b1e56a7391c | textbox | Enter: Fault ID if any:
78443e11-aeed-5707-8a19-f44d0c905a48 | note | Method - Visual, Measure
d994f362-05e5-5c8c-b2c7-a1cca7c54169 | note | Frequency - Each precast type delivered
90d05006-4584-518b-ab08-a61dd0f01b60 | note | Category - IP
0724f2b5-b4ce-561e-af92-c50f29ec82a7 | note | Responsibility - PE/SE
fcab2355-995c-5b47-94fd-7c412942559b | note | Verifying Documents - This Checklist
6f8a9585-328e-53ce-9522-ed57a42565ec | date | Date Completed:
| checkpoint | Final Inspection
8722ffbc-3472-504b-b794-4062e309ec0d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
97ace8a3-8753-5403-b01c-278f4bce7ce9 | textbox | Name:
8b205473-e432-5081-8751-e9d03fda011c | textbox | Position:
b866d173-fbc3-56f2-be80-889991cffb9c | textbox | Date Completed:
| signoff | Sign ITP