## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
c3acc1b5-2186-40a2-a292-9799a5dac62a | checklist | Post Pour Checklist (Pre-Stressing) |  | Post Pour Checklist (Pre-Stressing)
e0192c22-f455-487e-ad1a-80a168bf94e9 | section | Post Pour Checklist
28732844-e953-42f2-8fef-782f75f559c1 | checkpoint | Check the dimensions are correct after pour
5196469d-a94b-4744-9031-e984bb4286d1 | checkpoint | No change in the penetration size and location
e79c4e17-2ad8-46c0-8e64-cfdfb87eb298 | checkpoint | Ferrules, lifter points, penetrations/blockouts are cleaned out
| checkpoint | Tendons release pattern according to the structural drawings
| checkpoint | Is Hog measurement is according to the structural drawing
| textbox | The Recorded Hog measurement
| textbox | Hog measurement time after the strand release
| checkpoint | RUGSOL sides are washed out (If Required)
| checkpoint | Tendons cut to required length as per structural drawings
| checkpoint | Tendons protruding correct length (onion ends/Megapoxy ends)
dfeb2a7c-75af-42c1-8b06-5853f875be66 | checkpoint | Any defects identified (Bugholes, Honeycombing, etc.,)
dfa54cc4-5f46-4e0d-bb86-eb19171cc3e4 | checkpoint | Propsed repair methodology
1ec0b789-fae7-59f0-863a-61757296eeca | textbox | Methodology:
| checkpoint | Planks are stored properly on dunnage
5560e403-8717-47f6-b5ee-45ea9e377022 | checkpoint | Product Cleared For Delivery
acf85eb4-745b-433d-92a2-5531d18cfa0c | checkpoint | Inspector sign off attached below