## Master List Templates
Id | Type | Name | Values | Prompting Name
e90f1869-561d-401c-b451-543bfb3da2be | checklist | Pre-Pour Checklist |  | Pre-Pour Checklist
1f5ad4e3-2440-49d1-8cc6-8da58cf41420 | section | Product Detail
d90bfa34-8b4c-4a15-bb28-723c46deeef4 | checkpoint | Details
ce8b5be3-ea75-58b1-a3e7-2967a0383f77 | textbox | Product ID
57ba2d73-fb61-53ed-8da5-4f1f3c774daa | textbox | Weight
b5306076-958a-5cc4-8f8e-67426ad1dc5f | textbox | Manufacture Date
| checkpoint | Is the manufacturing shop drawings issued for construction
| checkpoint | Is the manufacturing shop drawings current revision
42c9fa11-750c-4886-a6b6-88596bff77de | section | Formwork
3f0cdcab-4b3f-476d-b56b-b16ee107e388 | checkpoint | Check Length
aa821181-55ff-5434-9c60-590f582ffa1a | textbox | length
52ec7df5-ba4b-4cfb-a76e-660dcfff8f63 | checkpoint | Check Width
24e33343-a8e9-549c-b3fa-c26f874bb8c4 | textbox | width
478266b9-d083-4b39-8262-306e351e2909 | checkpoint | Check Thickness
0570df06-5d73-5fa2-a207-7cd5401af655 | textbox | thickness
dcc56b68-3340-44ea-92f1-17fa5704ae43 | checkpoint | Check Diagnonal
5320e261-0158-45f1-80f6-3ac8bfd372dd | checkpoint | Sideform Trueness
826c421c-3819-4e01-a290-04d4799f9553 | checkpoint | Magnets / Forms Secure
fbfd6b1e-be95-4fed-ace9-bd78d0e8e3f9 | checkpoint | Splayed forms checked
809900d9-8079-4836-8656-f6783a846e5c | checkpoint | Penotration dimensions checked
344dceb0-c2d3-4e2c-afd4-2f75ec739272 | checkpoint | Curves / Radius Checked
26a843b1-0618-4e73-9fb7-82c2d06c617c | checkpoint | Rebates size and location checked
f2115ccc-c889-4060-9566-a6369573178a | checkpoint | Weather steps dimensions checked
b8c4f4f1-454e-4936-a39c-ed94b5d75f1e | checkpoint | Weather steps orientation checked
26681f59-631d-4176-aa8e-8dcb2fcc9401 | checkpoint | Form release applied correctly
67e25267-f2b1-4a07-855d-ecbd0989ca8f | section | Reinforcement
2f21ec73-92fc-4e82-836f-b3989297918d | checkpoint | Reinforcement mat as per shop drawings
1e0aeba2-4fe3-4650-8304-d891167a56a9 | checkpoint | Reo Mat Orientation
0c210185-a25b-4466-84b2-1a5e37dcaa5d | checkpoint | Perimeter Bars Size Correct
9a489e36-4f9d-4f76-b76d-f289d5e9e5b8 | checkpoint | Perimeter Bars No. Off Correct
947f18c1-05a0-4f0e-9d2e-8b6895718245 | checkpoint | Additional Bars Correct
0921695a-8f0a-471f-b834-4beb5804a7a0 | checkpoint | Reo Changes Noted
1adcf415-b514-4ed5-ab0b-4a5706df10d7 | checkpoint | Reo Changes Passed By PM
2b194a7c-1046-4ad3-af5a-5e70144d6d87 | checkpoint | COGS / Laps As Per SD
5dcaf330-b436-4a1a-a794-710950fb0b0a | checkpoint | Any Splice 40 x Dia Min
78b57408-913e-4838-8887-f9f714bfe8d9 | checkpoint | Rebar Photos
6abd83fe-cb5a-4016-b8af-151bbb00796c | section | Fixings / Cast Ins
2a353ad3-4ca2-4a79-a2ff-22f917e27dc8 | checkpoint | Ferrule Location Checked
976aa919-133c-4371-af4a-65684fe4851d | checkpoint | Ferrule Cross Bars Inserted
014bcf87-a1fd-4abd-ab69-4cf240288554 | checkpoint | Lifting Inserts as Per Lift Design
04949cef-6019-4944-9abf-bc21c636b45d | checkpoint | Lifter Type correct
98ba53ce-8947-5e57-b8b0-b08b91d643fc | dropdown | Lifter Type | Leviat Edj Pro Mini 8.5T, Leviat Edj Pro Max 15T, Foot Anchor 1.3T, Foot Anchor 2.5T, Foot Anchor 5T, Foot Anchor 10T, Foot Anchor 20T
0e605e4f-634a-42b2-97b8-af21d479bcf2 | checkpoint | Lifting V Bars Inserted
c4ec3f31-2fc9-42de-882d-31d8f5f7c1a6 | checkpoint | Cast Plates Per Design
140de006-93d1-4cc6-8d8a-175509f130b2 | checkpoint | Cast Plate Location Checked
e4b203fb-fcb1-4e06-93dc-1fbccdd4ec34 | checkpoint | Additional Cast Plate Bars Inserted
1ef55d89-2b7e-4009-81c3-5e8f3153538a | checkpoint | Starter Bars Correct Per SD
e446f9b8-7a10-4207-93df-b1e230f0ec45 | checkpoint | Pertruding Bars Orientation
a417c0c9-137f-42cb-a33e-36be0df4875b | checkpoint | Grout Tube Size Checked
77f6b57d-9e42-4987-acff-cc1cfadef084 | checkpoint | Grout Tube Exit Orientation Checked
84a235aa-1b45-4714-9676-71e05dbd6e80 | checkpoint | Grout Tube Photo
3814317c-2f36-41f8-90ff-3e82d38d9f19 | checkpoint | Lifting Insert Photo
c1b2e65e-761e-4cbd-8e49-2327b604394e | checkpoint | Cast In Plate Photo
7f6e72fd-61e0-4019-aef5-f1811355e1b7 | checkpoint | Penetration Photo
21422afa-f6af-4343-83e4-64da9761b74d | section | Final Checks
6c8bbf16-a6ff-4bd9-8ed4-933a91d76417 | checkpoint | All SD Dimensions Shown
9bfb6b82-4553-425d-8c5d-f7b11ccef887 | checkpoint | Photo of For "Construction" Shop Drawing
f6a6f3c3-e8de-4f22-bb4b-82a888ed9b8d | checkpoint | Panel ID Tag Placed
788889ae-a4ca-46d9-a1b6-b83c0a5d78c8 | checkpoint | Product Cleared For Pouring
c23f8dac-cfd1-4d5b-b829-38f3c8573c22 | checkpoint | Inspector sign off attached below