## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
c3acc1b5-2186-40a2-a292-9799a5dac62a | checklist | Post Pour Checklist (Pre-Stressing) |  | Post Pour Checklist (Pre-Stressing)
e0192c22-f455-487e-ad1a-80a168bf94e9 | section | Post Pour Checklist
28732844-e953-42f2-8fef-782f75f559c1 | checkpoint | Check the dimensions are correct after pour
5196469d-a94b-4744-9031-e984bb4286d1 | checkpoint | No change in the penetration size and location
e79c4e17-2ad8-46c0-8e64-cfdfb87eb298 | checkpoint | Ferrules, lifter points, penetrations/blockouts are cleaned out
4596d663-4f23-4464-8d68-b845f167fa83 | checkpoint | Tendons release pattern according to the structural drawings
9cc2f59e-99bb-403e-a125-0cacd027de96 | checkpoint | Is Hog measurement is according to the structural drawing
3070ba4c-eaa1-56d5-bffe-b1d9956b39b2 | textbox | The Recorded Hog measurement
3eb7fe49-230f-500e-9ec4-f8e493addea2 | textbox | Elapsed time after the strand release for Hog Measurement
eacc52ed-6eb2-433e-9ac3-4c27b6e6a04c | checkpoint | RUGSOL sides are washed out (If Required)
302947d7-46ad-44aa-bb60-a445d51863a0 | checkpoint | Tendons cut to required length as per structural drawings
| checkpoint | Has Protruding tendons been Onioned as per structural drawings (if applicable)
| checkpoint | Has flush cut tendons been Megapoxed as per structural drawings (if applicable)
| checkpoint | Has the temperature been recorded from the loggers
dfeb2a7c-75af-42c1-8b06-5853f875be66 | checkpoint | Any defects identified (Bugholes, Honeycombing, etc.,)
dfa54cc4-5f46-4e0d-bb86-eb19171cc3e4 | checkpoint | Propsed repair methodology
1ec0b789-fae7-59f0-863a-61757296eeca | textbox | Methodology:
4716153b-1f47-4bfc-b25a-a5c21508860e | checkpoint | Planks are stored properly on dunnage in accordance with Engineer's Design
| checkpoint | Has Planks been lifted properly
5560e403-8717-47f6-b5ee-45ea9e377022 | checkpoint | Product Cleared For Delivery
acf85eb4-745b-433d-92a2-5531d18cfa0c | checkpoint | Inspector sign off attached below
58c2ce69-af17-4e53-9970-f56a76668c9c | checklist | Pre-Pour Checklist (Pre-Stressing) |  | Pre-Pour Checklist (Pre-Stressing)
3b4c79d6-a607-4331-b4be-fd7bc444b2e7 | section | Product Detail
57c29981-cbcc-473a-8dfa-f73880f835a1 | checkpoint | Details
7233ee70-ab58-5cbb-b2c6-c0fbe21720d5 | textbox | Product ID
00431790-c665-59a3-8cb9-315b438d38bf | textbox | Weight
1b04ade1-e485-551e-8f0f-da7cb090dcdc | textbox | Manufacture Date
7d94ac61-1322-4c9d-a0e3-4dfb77d895bf | checkpoint | Is the manufacturing shop drawings issued for construction
ed115715-4452-490f-aca9-042a350ac7e1 | checkpoint | Is the manufacturing shop drawings current revision
d864ac16-f363-4f78-98aa-9acdd772aef8 | section | Formwork
6da9b84d-61dc-4b4b-92c1-d3734743f0ee | checkpoint | Check Length
dd84890b-3959-51ee-ae5d-dc0a1b676a39 | textbox | length
9abc2ea3-b8cd-4533-b99e-d4640b033bfd | checkpoint | Check Width
50e0b2c0-6701-53ba-9122-7bda59d59e52 | textbox | width
786405f2-55d4-47e3-ac70-1350f0ab87c6 | checkpoint | Check Thickness
97ece5af-4211-505f-8bb8-e3a010263e54 | textbox | thickness
c091e3b8-c064-4db3-a4d2-e2c81f5e4f07 | checkpoint | Check Diagnonal
d8886378-6d11-49cb-91af-64e46f085a76 | checkpoint | Sideform Trueness
317d18ab-9c2f-4673-ad89-bc3445efa5be | checkpoint | String-line the forms on the top edge
c44f174c-9b6e-44b0-ab0f-029ea79d901d | checkpoint | Place Sideform braces (Cradles & Stays)
318d5abc-de63-4b7c-b4fe-ead93bf48667 | checkpoint | Have all the foam retainers been installed
55f91b35-757a-4a2f-b9c1-17005a27daee | checkpoint | Magnets / Forms Secure
6470a893-ee96-4ddc-8787-b79162978e75 | checkpoint | Splayed forms checked
b195679c-a956-4b7f-ba2d-68b5d8d41040 | checkpoint | Penotration dimensions checked
f435282e-8a0b-4fd4-8713-f63ff861ffa9 | checkpoint | Rebates size and location checked
2215c343-4161-488a-b478-8c58c78634db | checkpoint | Form release applied correctly
a8792618-9e4f-44c8-9024-9fa196e66ff7 | checkpoint | Excessive form release has been cleaned out
0fad1d38-b744-4b4e-b072-da2574f70a4c | section | Reinforcement
e73ec773-a5ac-4e13-848c-192be0f61d5e | checkpoint | Reinforcement cage as per shop drawings
15a7465f-c522-49d1-90d5-71ae3751fb34 | checkpoint | Is the reinforcement clear of dirt and debris
4950d77a-3537-41b1-888b-98f6dfd3a179 | checkpoint | Reniforcement cover is per Shop drawings
5673881c-138d-431f-888f-5e4f062a1689 | checkpoint | Additional Bars Correct
4fc04166-f8d5-4f2a-bb47-045cbf113947 | checkpoint | COGS / Laps As Per SD
c0667ad6-3e05-42a8-9374-281afc317d6f | checkpoint | Any Splice 40 x Dia Min
74202838-93cd-414c-890c-85c220e409b5 | checkpoint | Rebar Photos
5f54e234-6665-4602-bb93-151a81d6281e | section | Fixings / Cast Ins
b0ab1932-b633-4810-88e3-dff9fbd19940 | checkpoint | Details
ce8a454b-0af1-5572-89cd-fed6424b70b4 | textbox | Strand Size
cb5d9547-9b44-4582-af0f-bcbe99c5c59c | checkpoint | Is the strand size correct as per Structural drawings
83c74cdb-7d87-599b-935c-8240f788f3e9 | textbox | Coil Id
99487dd4-5f97-5570-b057-c611c7f24d10 | textbox | Strand Photo
dc81997e-277a-5e7f-8702-e1ccd574f83b | textbox | Stressing Guage Photo (Mpa)
b2dda9e2-80bc-421e-807e-efb41e0c5683 | checkpoint | Read Dimension as per extension Calculations
ccc32d53-e255-4d04-a098-0027f94405c7 | checkpoint | Is the Correct extension Calculations been used
48bdde35-b35e-4d57-b155-a35178b94446 | checkpoint | Is the Correct extension Calculation KN as per structural drawings
6988efb1-4bc3-4ecc-8b89-8461b8c502ab | checkpoint | Has the temperature loggers tied in?
adf465d7-29a8-4292-9279-ab32b5461589 | checkpoint | Ferrule/Bolts Location Checked
| checkpoint | Ferrule Cross Bars Inserted
f7f1eada-a7ed-4e5f-afbb-fa6b6e72ff4c | checkpoint | Lifting Inserts as Per Lift Design
0d5c03ed-5b69-48cd-b258-514523e59679 | checkpoint | Lifter Type correct
aad0581e-3cbd-54d2-871f-24f963ceac49 | dropdown | Lifter Type | Leviat Edj Pro Mini 8.5T, Leviat Edj Pro Max 15T, Foot Anchor 1.3T, Foot Anchor 2.5T, Foot Anchor 5T, Foot Anchor 10T, Foot Anchor 20T
6fcd6a4a-3ec1-4347-a039-517db51a5f70 | checkpoint | Starter Bars Correct Per SD
17f0f6c1-c3c3-4772-bae3-bffa348cf5c2 | checkpoint | Pertruding Bars Orientation
f9ac8fc8-698c-455c-8053-679835c62e1b | checkpoint | Grout Tube Size Checked
3f0a76b2-c13c-4f7c-aaf4-174d1d09b759 | checkpoint | Grout Tube Photo
3a2d9fe1-1e9f-4802-91ad-72b00054d3e8 | checkpoint | Lifting Insert Photo
f15e079d-23cf-42f4-b657-29257ecdee38 | checkpoint | Penetration Photo
49682576-074a-4bff-acdd-774fec400acc | section | Final Checks
430639d0-17cb-4254-a56a-53752225f1d1 | checkpoint | All SD Dimensions Shown
3ad6f01c-832d-4060-b1f3-7c13e1cee1c2 | checkpoint | Photo of For "Construction" Shop Drawing
feeb23db-3e1a-4c67-9a3a-03e7d5b7e0c6 | checkpoint | Panel ID Tag Placed
7e09dfc1-e350-4b96-beaa-ae5a40fcac08 | checkpoint | Product Cleared For Pouring
ebdcbe3b-aaab-4f0e-8d91-e7e46868c5dc | checkpoint | Inspector sign off attached below