## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Lot | itp |  |  |  |  | Lot Checks (Concrete Slabs)
section | Section 1: Preliminaries
checkpoint | 1.1 - Review of approved construction drawings and specifications
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Approved IFC drawings and project specifications available on-site
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings
checkpoint | 1.2 - Site condition check and access preparation
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Site cleared, accessible, and suitable for concrete slab works
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
checkpoint | 1.3 - Site safety induction and toolbox talks
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - All personnel inducted and briefed on safety, site-specific risks
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Site inductions records
checkpoint | 1.4 - Inspection of plant and equipment (e.g., concrete pump, vibrators)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - All equipment calibrated and operational
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Calibration/Pre-start
checkpoint | 1.5 - Foundation preparation
label | Responsibility - SE/PE
label | Specification Reference - Geotechnical report/memo/ geotechnical engineer’s specifications
label | Conformance Criteria Summary - Compaction test reports/geotechnical engineer’s specifications
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Calibration/Pre-start
section | Section 2: Pre-pour preparations
checkpoint | 2.1 - Verification of work permits
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - All necessary permits for concrete works in place (GDA/GDP)
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - GDA/GDP
checkpoint | 2.2 - Blinding concrete installation
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007 Design drawings
label | Conformance Criteria Summary - Approved mix design
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 2.3 - Review of concrete mix design and material certificates
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Approved mix design, material certificates compliant with AS 1379
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Product certificate of compliance
holdpoint | HOLD POINT
checkpoint | 2.4 - Formwork inspection – alignment, cleanliness, and dimensions
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Formwork in line with drawings, clean, and dimensionally correct
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - TWD FIC
holdpoint | HOLD POINT
checkpoint | 2.5 - Reinforcement inspection (size, spacing, placement, cover)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007 AS 4671
label | Conformance Criteria Summary - Correct bar size, spacing, reinforcement securely tied, adequate cover
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings FIC
holdpoint | HOLD POINT
checkpoint | 2.6 - Verify waterproofing membrane
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Membrane installed as per drawings/specs
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - WP
label | Hold/Witness Point Requirements: SEPD - WP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings FIC
checkpoint | 2.7 - Re-entrant bars (starter bars) and corner reinforcement
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Correct positioning of all embedded items per drawings
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - WP
label | Hold/Witness Point Requirements: SEPD - WP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings FIC
checkpoint | 2.8 - Concrete batch plant inspection
label | Responsibility - SE/PE
label | Specification Reference - AS 1379
label | Conformance Criteria Summary - Batch plant adheres to mix design, and delivery meets timing requirements
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checklist | RR-SEPD-BESS-ITP-002-02 - Concrete slabs - Layer | itp |  |  |  |  | RR-SEPD-BESS-ITP-002-02 - Concrete slabs
section | Section 1: Concrete placement
checkpoint | 3.1 - Pre-pour concrete delivery inspection
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007 AS 1379
label | Conformance Criteria Summary - Batch delivery dockets match approved mix
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - WP
label | Hold/Witness Point Requirements: SEPD - WP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Delivery dockets
checkpoint | 3.2 - Slump test at site (conformance to mix design)
label | Responsibility - SE/PE
label | Specification Reference - AS 1012
label | Conformance Criteria Summary - Slump within specified range (e.g., 100mm +/- 20mm)
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Lab test report
holdpoint | HOLD POINT
checkpoint | 3.3 - Concrete placement and compaction
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Concrete placed within formwork, no segregation, fully compacted
label | Method - T
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Pour record
checkpoint | 3.4 - Cylinder samples for compressive strength testing
label | Responsibility - SE/PE
label | Specification Reference - AS 1012
label | Conformance Criteria Summary - Minimum of 12 cylinders in total for 7, 14, 28-day tests
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Lab test report
holdpoint | HOLD POINT
checkpoint | 3.5 - Concrete temperature monitoring
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Temperature within acceptable range
label | Method - T
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Pour record
holdpoint | HOLD POINT
checkpoint | 3.6 - Placement monitoring – free- fall limit
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007 AS 3600
label | Conformance Criteria Summary - Concrete poured with a maximum free-fall height of 1.8m to avoid segregation
label | Method - T
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 3.7 - Vibration and compaction monitoring
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007 AS 3600
label | Conformance Criteria Summary - Concrete properly compacted with vibrators, no voids or segregation
label | Method - T
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 3.8 - Concrete curing
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007 FRP section 4.25.11 AS 3600
label | Conformance Criteria Summary - Concrete curing per approved concrete curing method statement
label | Method - T
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
section | Section 2: Final Inspection
checkpoint | 4.1 - Surface finishing (Class of finish per AS 3610)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007 AS 3610
label | Conformance Criteria Summary - Class 5 finish for surfaces that are not visible after construction
label | Method - S
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 4.2 - Curing procedure inspection
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007 AS 3799
label | Conformance Criteria Summary - Curing compound applied or wet curing in place
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 4.3 - Formwork stripping and post-pour inspection
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007 AS 3610
label | Conformance Criteria Summary - Formwork removed at required strength, surface defects repaired
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - WP
label | Hold/Witness Point Requirements: SEPD - WP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 4.4 - Compressive strength test results
label | Responsibility - SE/PE
label | Specification Reference - AS 1012
label | Conformance Criteria Summary - Compressive strength >32 MPa at 28 days
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Lab test report
holdpoint | HOLD POINT
checkpoint | 4.5 - Final inspection and acceptance of slab
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Surface levels, dimensions, and finish within tolerances
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 4.6 - Joint Inspections
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Expansion and contraction joints installed per design drawings
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 4.7 - Post-cure inspections for shrinkage and cracking
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0007
label | Conformance Criteria Summary - Inspection for early shrinkage cracks and proper curing continuation
label | Method - R
label | Frequency - R
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
section | Document Sign-off
checkpoint | Close-out
textbox | SEPD - Name:
textbox | SEPD - Position:
date | SEPD - Date:
signoff | Add Signature