## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Concrete Works - Owhata Retaining Wall | itp |  |  |  |  | ITP - Concrete Works - Owhata Retaining Wall
section | Setout, Materials and Preparation
checkpoint | 1.1 - Survey Set Out
label | Detail of Activity - GPS Setout of the Retaining wall as per the construction drawings.
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of the retaining wall
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Survey Report
label | Record documents - Contractor's site diary and/or photos
label | Responsibility - Contractor
label | Comments - Setout location prior to commencing works.
checkpoint | 1.2 - Materials Approvals
label | Detail of Activity - Submit testing data fir the following materials:
label | – AP65
label | – GAP 40
label | – GAP 20
label | – Hardfill
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Once for each material
label | Inspection / Test method - Quarry Testing Data
label | Acceptance Criteria - Engineer's Acceptance
label | Record documents - InEight Records
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
section | Construction and Finshing
checkpoint | 2.1 - Bases, Footings and/or Toes
label | Detail of Activity - Subgrade Cut / Base Thickness
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 5m section
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - THE SAFETY OF ALL TEMPORARY OPEN CUTS SHALL BE THE RESPONSIBILITY OF THE CONTRACTOR. THE CONTRACTOR SHALL PROVIDE ANY AND ALL SLOPE PROTECTION NECESSARY TO PREVENT ANY GROUND MOVEMENT.
checkpoint | 2.2 - Bases, Footings and/or Toes
label | Detail of Activity - Subgrade Testing
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 20m
label | Inspection / Test method - Scalar Penetrometer
label | Acceptance Criteria - ≥ 3 blows per 100mm to 1.5m depth.
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Bases, Footings and/or Toes
label | Detail of Activity - Reinforcing WSP INSPECTION
label | Action (Hold, Monitor, Witness) - M, H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 6m panels
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL.
label | ○ MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | Record documents - QC Sheets
label | Responsibility - Contractor/Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Bases, Footings and/or Toes
label | Detail of Activity - Formwork
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 6m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - FORMWORK SUPPLIED BY DOKA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Bases, Footings and/or Toes
label | Detail of Activity - Concrete
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All concrete orders
label | Inspection / Test method - Concrete Dockets
label | Acceptance Criteria - Concrete strength 25MPa at 28 days
label | ○ Mix design to be apporved by the Engineer
label | ○ Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise
label | Record documents - Concrete Dockets
label | Responsibility - Contractor
label | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE.
label | ○ ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
label | ○ THE CONTRACTOR SHALL PROVIDE THE CONCRETE MIX DESIGN FOR THE APPROVAL OF THE ENGINEER PRIOR TO THE COMMENCEMENT OF ANY CONCRETE WORKS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Bases, Footings and/or Toes
label | Detail of Activity - Dowels (greased and plain ended)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 300mm centers
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES
label | ○ CONTROL JOINTS SHALL BE KEY JOINTS
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Walls
label | Detail of Activity - Reinforcing WSP INSPECTION
label | Action (Hold, Monitor, Witness) - M, H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 6m panels
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL.
label | ○ MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
label | Record documents - QC Sheets
label | Responsibility - Contractor/Engineer
label | Comments - Scabble or green cut interface in accordance with Type B construction joint to NZS 3109
label | ○ For joints, the surface of the concrete may be prepared by green cutting (using high velocityair/water jets or vigirous wire brush) to remove all laitanceand inferior surface concrete after the concrete has hardened suffieciently to prevent loosening of any aggregate which is not removed.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Walls
label | Detail of Activity - Formwork
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 5m
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - FORMWORK SUPPLIED BY DOKA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Walls
label | Detail of Activity - Dowels (greased & plain ended)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 300mm centers
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES
label | ○ CONTROL JOINTS SHALL BE KEY JOINTS SPACED AT MAXIMUM 6.1m INTERVALS OR A SUITABLE LESSER LENGTH IF REQUIRED
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments -
checkpoint | 2.10 - Walls
label | Detail of Activity - Finish / Joints
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All areas
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Smooth, off shutter finish. Cut joints as appropriate.
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments -
checkpoint | 2.11 - Walls
label | Detail of Activity - Concrete
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All concrete orders
label | Inspection / Test method - Concrete Dockets
label | Acceptance Criteria - Concrete strength 25MPa at 28 days
label | ○ Mix design to be apporved by the Engineer
label | ○ Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise
label | Record documents - Concrete Dockets
label | Responsibility - Contractor
label | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE.
label | ○ ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.12 - Walls
label | Detail of Activity - Weep Holes
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 2,000mm
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - 50mm Ø WEEPHOLES THROUGH WALL STEM AT MAXIMUM 3.0m SPACING
checkpoint | 2.13 - Backfill
label | Detail of Activity - Backfill behind wall (Shared service trench)
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Refer to Shared Service Trench ITP
label | Inspection / Test method - Refer to Shared Service Trench ITP
label | Acceptance Criteria - Refer to Shared Service Trench ITP
label | Record documents - Refer to Shared Service Trench ITP
label | Responsibility - Refer to Shared Service Trench ITP
label | Comments - Refer to Shared Service Trench ITP
checkpoint | 2.14 - Joints
label | Detail of Activity - Completed Joints
label | Action (Hold, Monitor, Witness) - W
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All concrete orders
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Concrete strength 25MPa, at 28 days
label | Record documents - Concrete Dockets
label | Responsibility - Contractor
label | Comments - SIKAFLEX SEALANT OR APPROVED EQUIVALENT
checkpoint | 2.15 - Joints
label | Detail of Activity - Joint formwork
label | Action (Hold, Monitor, Witness) - w
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - At joints between sections
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - Smooth, off shutter finish. Construction joints as per drawing.
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - COMPRESSIBLE BOARD BETWEEN WALL SECTIONS
checkpoint | 2.16 - Subsoil drainage - front of wall
label | Detail of Activity - Subsoil drain - back of wall
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of wall
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.16 - Subsoil drainage - back of wall
label | Detail of Activity - Installation of subsoil drain
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Lentgh of wall
label | Inspection / Test method - Visual Inspection
label | Acceptance Criteria - As per drawing
label | Record documents - QC Sheets
label | Responsibility - Contractor
label | Comments - 100Ø PERFORATED SUBSOIL DRAIN WITH 40/20 DRAINAGE AGGREGATE WRAPPED IN GEOTEXTILE OF STRENGTH CLASS B AND FILTRATION CLASS 2 TO TNZ F/7
label | ○ SUBSOIL DRAIN TO BE LAID WITH 1% FALL AND DISCHARGE TO THE NEAREST STORMWATER SUMP
holdpoint | AUTHORITY HOLDPOINT
section | Close Out
checkpoint | 3.1 - Collate above documentation
label | Detail of Activity - Document review
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Each ITP
label | Inspection / Test method - Review
label | Acceptance Criteria - All above documentation is shown as attached to this work pack.
label | Record documents - Review
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - As-built drawings
label | Detail of Activity - Survey
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - At completion of construction
label | Inspection / Test method - Asbuilts to besubmitted at the completion of construction, information to be captured
label | Acceptance Criteria - Asbuilts reviewed and submitted
label | Record documents - In Eight record
label | Responsibility - Contractor
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - Contractor
note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
signoff | Add Signature
checkpoint | Client Final Inspection - BBO Engineer
note | The signature below verifies that this ITP has been completed in accordance with NZTA Specifications and verifies lot compliance.
textbox | BBO Engineers Rep Name:
signoff | Add Signature