## ITP-010
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # DTM-ITP-010
[11 empty] | Revision : 0 | Date : 16/10/24
Client: |  | Department of State Growth |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Davey to Macquarie Street |  | Subsurface Drainage |  | Name: | Mileva Savic | Name: | Patrick Schurink-Moeller |  | Name: | Sam Arnold
Contract No: |  | C3741 |  | Specifications: Specification Section 702
|  |  |  | Structure / Component: Subsoil Drainage |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Davey to Macquarie Street |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | QAV | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP/WP | Site Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TGS, SWMS, WP | Visual Inspection | This ITP signed off | HP/WP | Site Engineer | N/A |  | N/A
1.3 | Material Classification |  | Each Lot | Subsurface drainage pipes: 100mm DIA Class 1000 and 400 corrugated perforated plastic pipe Granular filter material for bedding and backfill: Trench backfilled with B3 granular filter material complying with Cl 702.05 No Fines Concrete: Shall consist of 4.0% Type GP cement Geotextiles: Robust geotextiles shall comply with Cl 702.12 and Table 702.061 and have a minimum robustness of 600-900. Subsurface drain pits: Stormwater drainage pits are to be used as access points. Invert levels in pits to comply with Cl 702.10 Flushout risers: Shall have surface fittings as shown on the drawing | 702.04 702.05 702.06 702.10 702.12 702.061 | Verify | This ITP signed off | IP | Site Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | This ITP Signed Off | HP* | Site Engineer | N/A |  | N/A
2.2 | Excavation of Trench |  | Each Lot | Hold Point Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by QAV with at least 24 hours notice prior to placement of bedding. | 702.08 | Visual Inspection | This ITP signed off | HP | Site Engineer/ QAV | N/A
2.3 | Placement of bedding |  | Each Lot | Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level | 702.09 (c) | Visual Inspection | This ITP signed off | IP | Site Engineer | N/A |  | N/A
2.4 | Placing pipes and geofabric (if required) |  | Each Lot | Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe. If geofabric required (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm | 702.09(d) | Visual Inspection | This ITP signed off | IP | Site Engineer | N/A |  | N/A
2.5 | Placement of granular backfill methodology |  | Prior to backfilling | Hold Point Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent. Where no fines concrete is used, the contractor shall submit quality procedures for review by the QAV which detail the method of placing. No fines concrete shall be placed and compacted within 1 hour of mixing. | 702.09(g) | Visual Inspection | This ITP signed off | HP | Site Engineer/ QAV | N/A
2.6 | Placement of backfill |  | Each Lot | Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing | 702.09 (g) | Visual inspection | This ITP signed off | IP | Site Engineer | N/A |  | N/A
2.7 | Install Pits and Flushouts |  | Each Lot | Installed in accordance with drawings and Cl 702.10 | 702.10 | Verify | This ITP signed off | IP | Site Engineer | N/A |  | N/A
2.8 | Flushing Test |  | At completion of stage | Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture. | 702.09(h) | Site inspection | Signed ITP/ Record of flushing tests | WP | Site Engineer | N/A |  | N/A
2.9 | CCTV |  | At completion of stage | Hold Point All subsurface drainage lines constructed shall be inspection, after completion of the flushing test and prior to the placement of asphalt, by an independent testing organisation using CCTV, in accordance with WSA 05-2013. | 702.09(i) WSA 05-2013 | Site inspection | Signed ITP/ CCTV Reports | HP | Site Engineer / QAV | N/A
2.10 | Marker Posts |  | Each Lot | At all fill batter and drain outlets, supply and erect marker posts as shown on the drawings. | 702.11 DSG 3401-3/P17-4 | Site inspection | Signed ITP/ As-Built records | IP | Site Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.