## ITP-02-06
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # DTM-ITP-012
[11 empty] | Revision : 0 | Date: 18/10/2024
Client: |  | Department of State Growth |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Macquarie to Davie St Transit Connection |  | Installation of masonry block retaining (noise attenuation) wall |  | Name: | Patrick Schurink-Moeller | Name: James Clark |  |  | Name: Sam Arnold
Contract No: |  | 3741 |  | Specifications: DSG Standard Specification – Section 160, Appendix M, A0171.005 Sheets: 0310 Rev 1, 0300, 0301, 0320, 0321 Rev 0
|  |  |  | Structure / Component: Masonry block retaining wall |  | Signed : P.S.Moeller |  | Signed : |  |  | Signed :
|  |  |  | Location: 326 Macquarie St / 241 Davie St |  | Date : 18/10/2024 |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | QAV | Fulton Hogan | Client | Date
1 | Pre-Construction
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, OHSMP, SWMS, WP | Visual Inspection | This ITP signed | WP | FH Engineer / Site Foreman | N/A |  | N/A
2 | Prequalification
2.1 | Reinforcement |  | Prior to commencing | Steel reeinforcement complies with the requirements of Section 611 and the design drawings | Specification Section 611 | Visual Inspection | This ITP signed, Pre-pour (core-fill) inspection checklist | IP | FH Engineer / QAV | N/A |  | N/A
2.2 | Reinforcement supply and certification |  | Prior to commencing | Supplier must hold Australian Certification Authority for Reinforcing Steel (ACRS) certificate. Hold Point No Third Party Certification. Approval shall be obtained in writing from the Superintendent for the use of steel reinforcing materials that are not covered by the long-term quality level of AS/NZS 4671 at least 14 days prior to the intended first date of use of such steel. | Specification Section 611.05 | Verify | HPR release in Procore if required | HP | FH Engineer / QAV |  |  | N/A
2.3 | Supply of masonry blocks |  | Prior to commencing | Ensure blocks comply with sections 713 and 765 of the AS/NZS 4455.1:2008 and section 765 of AS3700:2018 standards and are of the same type/description as set out in IFC drawings: Adrbri Masonry Versawall (oatmeal) blocks. | IFC drawings | Verify | This ITP signed off | IP | FH Engineer / QAV | N/A |  | N/A
3 | Testing and Acceptance
3.1 | Pre-mixed concrete |  | As per M14 of A0171.005 sheet 0301 Rev 0 | Ensure concrete strength is of the minimum specified f'c strength rating of 20MPa to AS3600. Ensure minimum cement content, max aggregate size and slump are as designated in note M14 are adhered to. | As per M14 of A0171.005 sheet 0301 Rev 0 | Test Point | Mix design, concrete docket, this ITP signed off | TP | FH Engineer | N/A |  | N/A
3.2 | Concrete Testing - Sampling Frequency |  | Each Lot | Concrete cast in one continuous operation to be tested at a frequency as shown below: 0m³ to 10m³ = 1 sample 10m³ to 25m³ = 2 samples 25m³ to 50m³ = 3 samples 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders. For each additional 50m³ and additional sample shall be taken. Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum. Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength. Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads. Record: Required information on the Concrete Pour Record. | 610.16 (b) 610.16 (g) 610.16 (j) | Test Point | Test Report, Pre-pour inspections checklist | TP | FH Engineer | N/A |  | N/A
3.3 | Concrete Testing - Core Sample Frequency (Post construction) |  | Each Lot | If required by the Superintendent: Hold Point: The coring procedure and core locations shall be submitted for approval by the Superintendent. 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below: 0m³ to 25m³ = 1 sample 25m³ to 50m³ = 2 samples For each additional 50m³ an additional sample shall be taken. Each sample shall consist of 6 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum. Core samples shall be tested for: 1 no. 3 day compressive strength 1 no. 7 day compressive strength 2 no. 28 day compressive strength 2 no. VPV tests | 610.16 (b) | Test Point | Test Report, Pre-pour inspections checklist | HP | FH Engineer | N/A |  | N/A
3.4 | Concrete Testing - Slump |  | Each Lot | Slump testing tolerances = >80mm to ≤110mm = ±20mm Record: Required information on the Concrete Pour Record. | 610.16 (c) | Test Point | This ITP signed | TP | FH Engineer | N/A
3.5 | Reinforcement |  | Prior to commencing | Steel reinforcement placement, fixing and lapping complies with requirements of Drawings | Structural Drawing Set | Visual Inspection | Pre-pour inspection checklist Subcontractor ITP | IP | FH Engineer | N/A |  | N/A
3.6 | Mortar |  | Prior to placement | Use class M3 Mortar: 1 part cement:5 parts sand and a methyl cellulose water thickener to AS3700. Use white cement to AS3972 type GP or GB. | Structural Drawing Set | Visual Inspection | This ITP signed | IP | FH Engineer | N/A |  | N/A
3.7 | Building Permit |  | Prior to commencing | Building Surveyor has provided Start Work Notification (Form 39) and inspected element prior to concrete pour | 160.08 | Verify | Start Work Notification (Form 39) Pre-pour inspection checklist | IP | FH Engineer | N/A |  | N/A
4 | Application
4.1 | Pre-pour |  | Each Lot | Pre-pour inspection checklist completed and details recorded (Temperature, Evaporation limits and concreting operations). | As per M20 of A0171.005 sheet 0301 Rev 0 | Verify | this ITP signed | IP | FH Engineer | N/A |  | N/A
4.2 | Concrete Pumping |  | Each Lot | Initial discharge of concrete pumped to waste until a consistent workable mix observed. | Specification Section 610.18 | Visual Inspection | Pre-pour inspection checklist | IP | FH Engineer | N/A |  | N/A
4.3 | construction of blockwork |  | 6 courses / 1500mm | Do not proceed with blockwork construction more than 6 courses or 1500mm ahead of concrete placement. Wet masonry blocks before placing concrete. | As per M20 of A0171.005 sheet 0301 Rev 0 | Visual Inspection | this ITP signed | IP | FH Engineer | N/A |  | N/A
4.3 | Core-filling |  | 6 courses / 1500mm | Wet masonry blocks before placing concrete. Stop concrete 50 mm below top of blocks to provide key for following concrete. Ensure proper compaction of concrete by 'rodding' or other approved means | As per M21 of A0171.005 sheet 0301 Rev 0 | Visual Inspection | this ITP signed | IP | FH Engineer | N/A |  | N/A
4.4 | Traceability |  | Each Lot | All concrete deliveries traceable from the batch plant to location in the structure including time from batching to spraying. Continuous concrete pours max lag between trucks = 25 minutes | Specification Section 610.15 | Verify | Concrete traceability checklist, Pour Record | IP | FH Engineer | N/A |  | N/A
4.5 | Curing |  | Each Lot | Curing in accordance with Specification Section 610. Freshly finished concrete protected where erequired from sun, wind or rain until curing implemented | Specification Sections 610 | Visual Inspection | This ITP signed / Post pour inspection checklist | IP | FH Engineer/JSCB | N/A |  | N/A
4.6 | Joints |  | Each Lot | All control joints as per control joint detail on A0171.005 sheet 0321 using R12-400 Galv. Dowels 450 long (greased and wrapped one end) and flexible joint filler and 10x10 approved joint sealant each face. | structural drawing set | Visual inspection | This ITP signed | IP | FH Engineer | N/A |  | N/A
4.7 | Cleaning |  | Each Lot | clean masonry progressively. Clean face work to remove mortar smears, stains, discolouration etc. Use cavity batten (lift progressively) to keep cavities clear of mortar fins, droppings etc.) remove mortar droppings from bottom of cores by use of cleanout blocks before placing concrete and at horizontal breaks in construction. Remove mortar fins protruding from joints before placing concrete. | As per M12 and M19 of A0171.005 sheet 0301 Rev 0 | Visual inspection | This ITP signed | IP | FH Engineer | N/A |  | N/A
5 | Finishing Activities
5.1 | Repair of defective areas |  | Each occurrence | Areas of finished work that have been deemed non-conforming alerted to the QAV and rectification method approved |  | Verify | This ITP signed, NCR report | HP* | FH Engineer | N/A |  | N/A
5.2 | As Built Documentation |  | Each Lot | Survey pick-up to be progressively completed. As built drawings to be be progressively completed. Test data, ITPs, Concrete Dockets, Checklists to be compiled and lot to be closed out. | FH Detailed Construction Methodology - Shotcrete Works | Verify | This ITP signed | IP | FH Engineer | N/A |  | N/A
6 | Post Construction
6.1 | Final inspection |  | After construction complete | Visual inspetion conducted by Lee Tyers Building surveyors following the completion of construction |  | Visual Inspection | Form 39 signed | HP | FH Engineer | N/A |  | N/A
6.2 | Compressive Strength (& VPV Test Results if requested by Superintendent) |  | Each Lot | 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength comply with table 610.061. Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength. Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%. Attach: Compressive Strength Test Results Attach: Core Sample Compressive Strength Test Results | Table 610.051 Table 610.061 610.16 (g) | Document Review, Each cylinder and core sample | This ITP signed | IP | FH Engineer | N/A |  | N/A
6.3 | As-built Survey |  | Each Lot | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the Table 610.472 as applicable to the element. Where a shape is required, ±25mm with no depressions greater than 15mm. Attach: Survey As-builts / Survey Report |  | As built | This ITP signed, HPR release in Procore | IP | FH Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which may be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent