## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
cd4160fa-ca9b-40c6-a0ef-aca8b3a37421 | checklist | DTM-ITP-001- Clearing and Grubbing Rev0 | itp | DTM-ITP-001- Clearing and Grubbing
978d3c0a-7747-4b99-83ca-ecbaeb8ba080 | section | 1 - Preliminary Works
f221dbc5-e143-4614-a874-4554378c07a3 | checkpoint | 1.1 - Check for correct documentation
b95c5f0c-11bb-52b8-8212-813958013045 | note | FREQUENCY: Prior to commencing any activity
7d5ddbac-fbf8-5407-951e-596fa573a7c8 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
65bbcb94-b151-5b75-9c6c-e5f13f1a1dc6 | note | – using the correct and complete set of drawings & all drawings are the latest revision
e74b2e37-1e25-51eb-8460-50e28e63059f | note | – Signed onto work pack
8de91b5a-0d0d-52cf-b60c-59e914fd3a39 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
ec18207d-e8a8-5b7a-b8dd-503cf9ebe8a8 | note | INSPECTION/TEST METHOD: Visual inspection
e839934b-0753-597a-8036-ef1e53ee90de | note | RECORD OF CONFORMITY: This ITP signed
4e5ae235-e8fa-513d-ac2f-3a67d50835e2 | note | HP*
3708c0ab-c870-5cf3-ba43-31c81b715047 | note | RESPONSIBILITY: Site Engineer
56cdb1c4-b025-5088-bab0-3fde9c3bfe5c | date | Date Completed:
485cf77c-9a7f-498b-a96c-1f88289e621c | checkpoint | 1.2 - Limits of work
6986b71f-10f9-54f4-ba48-75833b69e278 | note | FREQUENCY: Prior to pre commencment inspections
b0a446b7-0218-53a5-9ecd-0fe2241b93d0 | note | ACCEPTANCE CRITERIA: Clearing extents to be marked out as per drawings and ATC's/ RFI's.
741cd4f1-9d14-5a87-b4ae-440e65898768 | note | ○ Southern Outlet Highway is Road A0171, Link 5, CH 0.33 to CH 0.00.
8d59367b-1b74-58f9-aa79-4a6d517a38dd | note | ○ Davey Macquarie Couplet Main Road A1010, Link 5, CH 0.00 to CH 0.09.
dafe03b4-ea83-5376-bf7f-af0407061411 | note | ○ Davey Macquarie Couplet Main Road A1010, Link 10, CH 0.00 to CH 0.1 (approx.)
0e3b2984-c822-5138-991f-d734420bfdcb | note | REFERENCE DOCUMENTS: Cl 201.03
fd521529-655f-5dfa-9bb9-a25048f004a0 | note | INSPECTION/TEST METHOD: Visual inspection
8819e083-54f0-5acf-a92f-0622bf7eebbb | note | RECORD OF CONFORMITY: This ITP signed
9aace2a4-9a2e-5a85-a0ec-9b99f2c7034a | note | HP*
74b43e52-8f8d-5b71-a688-bd3a280e6fed | note | RESPONSIBILITY: Surveyor / Site Engineer / Foreman / Clearing Contractor
db282bd0-48fb-5114-bbd9-ef6fa91da74c | date | Date Completed:
2961961f-5fef-4f51-8943-fcb98c4d8a99 | checkpoint | 1.2 - Implementation of all measures and controls
d1b594a0-25e2-5e19-ba71-c53e42dc6be2 | note | FREQUENCY: Prior to commencing any activity
622630fc-0fa2-5d8a-ba35-eca41bf2df2a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: PSP, EMP, TMP, SWMS & WP
483316a1-2d33-5271-9e9f-601953098e53 | note | REFERENCE DOCUMENTS: PMP, EMP, TMP, SWMS, Work Pack
ce3d923e-2652-59b7-83e0-cc1eec4f4dc0 | note | INSPECTION/TEST METHOD: Visual Inspection
b657f43c-adc2-5903-a1a4-d1832bdc43f7 | note | RECORD OF CONFORMITY: This ITP signed
a55ecc6e-2c88-5290-8f39-cc98916bc127 | note | HP*
ac66bc81-0d6e-5fa2-8a64-271cec937abf | note | RESPONSIBILITY: Site Engineer
9d26fd4d-7426-50f3-ab1f-dce4021aa70e | date | Date Completed:
4c336d60-d2ac-46e9-b845-a15843fc929f | checkpoint | 1.3 - Implementation of environmental measures and controls
87dda4f8-f8d5-57a6-bff3-eca8184cc618 | note | FREQUENCY: Prior to commencing any activity
c380380e-9686-5547-bb60-51ec3bfdf8a4 | note | ACCEPTANCE CRITERIA: Hold Point
68d7c897-9ed6-5daf-ad2d-32d51ba29215 | note | ○ EMP meets the requirements of the specification and all controls have been implemented as per approved EMP
72481796-685e-507a-99c7-533a9209f0e7 | note | REFERENCE DOCUMENTS: Project Spec Cl160.24 EMP
f4cd4980-7ba3-5189-abba-8166853b77da | note | INSPECTION/TEST METHOD: Verify
09fdd594-e413-57a8-90df-9f6a7e57c6f1 | note | RECORD OF CONFORMITY: This ITP signed
69a8138c-3d07-5fbe-9a62-5414570075c0 | note | HP*
2e582631-845e-5355-8dd6-237fdb21550a | note | RESPONSIBILITY: Site Engineer
01112224-bd0d-5660-b162-13ddebad2ccd | date | Date Completed:
29876525-1f8e-4b96-ba43-fa34e1528849 | checkpoint | 1.4 - Flora and Fauna
6d201ff0-31ce-5bba-82b0-ac109cacfbb8 | note | FREQUENCY: Prior
768182a0-d263-515e-87a6-004ac0d8c2eb | note | ACCEPTANCE CRITERIA: Hold Point
b6baab11-a1f3-52d9-871a-64dd8471c6cf | note | ○ Vegetation to be removed clearly marked and agreed. All removal consistent with contract drawings and permits.
d56bdb8d-be0f-5e29-864f-6109f6309b50 | note | REFERENCE DOCUMENTS: EMP Cl176.I1(c)
80961749-d9ae-5a3e-904f-bb21e2424a68 | note | INSPECTION/TEST METHOD: Verify
c254e81d-846c-52f9-a90a-865e56fb2bc5 | note | RECORD OF CONFORMITY: This ITP signed, Vegetation Removal and Clearing Permit
6666e963-96af-55dc-967e-33581ec66f46 | note | HP
0c8aa277-1f1d-54cc-a94c-c144b44412d4 | note | RESPONSIBILITY: Site Engineer / QAV
6688cf9c-28c0-52ca-b77c-b311608985bb | date | Date Completed:
cc49166c-f91d-4348-b875-c39c1adb8494 | signoff | AUTHORITY HOLDPOINT
7d3152d4-3bea-43c4-933d-9bbf5896589d | checkpoint | 1.5 - Protection of Existing Vegetation
2d264ab3-fd01-5487-b6a4-7ab60d913fc0 | note | FREQUENCY: Prior to comencement of any work
4eb5b136-d200-52c3-9f6c-82b0718ba33a | note | ACCEPTANCE CRITERIA: Prior to the commencement of any work, the Contractor and the QAV shall conduct a joint inspection of the site to identify vegetation to be retained and protected.
e46c452f-1e38-53fa-ba91-121421d7dda7 | note | ○ If directed by the QAV, existing trees, shrubs, native grasses and groundcovers and other areas of existing vegetation shall be protected by temporary fencing and incorporated into the works by the Contractor.
a4680e63-bed2-551b-ac47-b56eeb481e31 | note | REFERENCE DOCUMENTS: EMP Cl201.10,Cl160.24, 176.I1
886d51df-c7dd-5730-90eb-0aa0d1df30ef | note | INSPECTION/TEST METHOD: Visual inspection
4ac6c785-e3b2-5ec1-b07e-a5a5e1c9d48e | note | RECORD OF CONFORMITY: Vegetation Removal and Clearing Permit, Tree Protection Plan
f8e94bad-5992-5597-ba14-961f028d1835 | note | IP
29bd3e7a-66e8-5acf-a88c-56283241438d | note | RESPONSIBILITY: Site Engineer / QAV
6e0f9275-cbf8-5c84-b3d9-0f35c8cc2c37 | date | Date Completed:
632d5c5d-6ee8-424f-a136-35784a7aff7e | checkpoint | 1.6 - Cultrual Heritage
6e651572-afdc-5e9c-8573-43e023289f16 | note | FREQUENCY: Prior to removal of vegetation
4c30c36c-95fd-5c4c-b790-8e4d14cea67f | note | ACCEPTANCE CRITERIA: Hold Point
7568c301-9bc8-57e1-8548-c5e2ff08c7ef | note | ○ Nominated sites of archaelogical and / or heritage significance inspected on-site and clearly identified and protected as No-Go zones
8f5da0ed-aea7-5d96-ba36-444ed2354b54 | note | REFERENCE DOCUMENTS: EMP Cl176.J1(e)
3cfd59fa-295f-58f7-824d-4588055cbb06 | note | INSPECTION/TEST METHOD: Verify
22ad1479-77ac-5bbf-9337-bec46374c948 | note | RECORD OF CONFORMITY: Vegetation Removal and Clearing Permit, Tree Protection Plan
35b0fe92-ed26-5caa-95bb-c05ed4f9dd59 | note | HP
f5d0a6a8-87d1-5fcd-b233-1a85e8022573 | note | RESPONSIBILITY: Site Engineer / QAV
3a91009f-fcdf-5b63-b0b9-a92effc19bfa | date | Date Completed:
084ca863-f8ae-4ed2-984e-149419237db6 | signoff | AUTHORITY HOLDPOINT
cd370f2f-489b-453b-b982-deb672d58016 | checkpoint | 1.7 - Authorisation for works
36a3075a-7ad4-51ef-af56-03609344b910 | note | FREQUENCY: Prior to commencing works
fb3b54b8-71e3-59b4-b5d8-3679e0c7828d | note | ACCEPTANCE CRITERIA: Check that all relevant approvals (Access to 241 Davey, 326 Macquarie) have been granted including verification of the works area.
8e29ec26-dc8c-59d0-95c9-84118d80b584 | note | ○ Ensure work pack is reviewed & signed
68988739-b1ff-5959-b3b2-9dfdd09b1baa | note | REFERENCE DOCUMENTS: Work Pack 160.08
e2f3e977-804f-5f01-bc43-fc17b7586dfb | note | INSPECTION/TEST METHOD: Verify
14c63dc5-315f-5208-a91d-17b01abeaa6e | note | RECORD OF CONFORMITY: This ITP signed, Property Access Approval
78e054fc-418b-5d40-b724-3972ee32e47d | note | HP*
5611b064-7a63-5466-9202-4c5bd47f3072 | note | RESPONSIBILITY: Site Engineer
11105919-1f33-541c-8ac9-bbaeb6797e7d | date | Date Completed:
b263f5cf-4f17-494e-b51e-6ce510fa3e8b | checkpoint | 1.8 - Utilities
db61a8cf-77a4-544f-ab50-2b7d82468a15 | note | FREQUENCY: Prior to commencing works
b3bb7563-761e-5939-9af0-c4720ace3635 | note | ACCEPTANCE CRITERIA: DBYD - locate and mark all existing services and confirm clearance from proposed work
1d8c708a-7a7f-553c-aa4c-d630e5890074 | note | REFERENCE DOCUMENTS: DBYD Records, Plan Mark-Ups, Excavation Permit
9742321b-ec0a-5d37-8374-db933beb50f6 | note | INSPECTION/TEST METHOD: Verify
f1000026-16aa-5393-8910-95be20fa72a0 | note | RECORD OF CONFORMITY: This ITP signed
a385f50f-ae0c-5b03-ac1c-1235b819d039 | note | IP
caf65a5d-d16e-593e-b1ab-5354174010bb | note | RESPONSIBILITY: Site Engineer
a53d7a95-6a9c-5403-9202-880c83cbaa06 | date | Date Completed:
35d9a4b5-99b5-427b-b648-00ba29e210b0 | checkpoint | 1.9 - Traffic Management
4f8f2031-f747-5de6-a207-0b98f72fa2b5 | note | FREQUENCY: Prior to commencing works
6e92de9e-223d-5029-adee-78d80c4a1f20 | note | ACCEPTANCE CRITERIA: Consider the requirements for traffic management, ensuring all works comply with required TMS, TMP and TGS. Where localised speed reductions are required they shall be at the discretion of the QAV. TGS shall be submitted and approved by the Superintendent.
5f036104-e406-5f90-a630-7f70a5c18b8c | note | REFERENCE DOCUMENTS: TMS, TGS, TMP, 160.07
f6d0534b-ef37-5413-91a6-cc1a59a91203 | note | INSPECTION/TEST METHOD: Verify
4c1ccd6b-22e2-54c0-988e-b0845e902e23 | note | RECORD OF CONFORMITY: This ITP signed
5521c832-8b66-54b9-aa1e-28a75edd2097 | note | IP
e1a95a07-9a49-53de-a511-71512b6549fc | note | RESPONSIBILITY: Site Engineer
145d7c15-0390-5793-ad0b-874974fe4ca4 | date | Date Completed:
e75dcb2a-eff8-4502-9bd9-1c4c9c48064b | section | 2 - Clear & Grub
7b3e8eaa-2984-4daf-9625-fcb2227531df | checkpoint | 2.1 - Clear and grub trees and vegetation
50186ea9-b68d-5954-8064-716aa7df6b73 | note | FREQUENCY: Each Lot
fdd95a45-b152-5755-8866-d27b4c95f642 | note | ACCEPTANCE CRITERIA: Area within specified limits cleared of all vegetation, refuse and obstructions down to natural surface. Trees brought down in a manner so as to avoid danger to personnel and traffic as well as damage to other trees, structures and property.
4b0a80d2-f9e7-551f-a25d-4ab78b92af91 | note | REFERENCE DOCUMENTS: Cl201.04
0e71f4f6-4d4b-5d47-a6b5-2968ac2e7554 | note | INSPECTION/TEST METHOD: Visual Inspection
a07841ef-527b-566e-ad41-314a557d1877 | note | RECORD OF CONFORMITY: This ITP signed
e04997f7-5156-5e72-9217-75db12823421 | note | IP
1fb784be-af17-5b63-950d-f406fbf0df85 | note | RESPONSIBILITY: Site Engineer
8de3606e-462f-54c1-892e-a6baa3b38c59 | date | Date Completed:
0c70dc08-416c-402e-9b0d-6390a2b081be | checkpoint | 2.2 - Clear and grub trees and vegetation
9f1575bf-8394-5bc9-b565-f7413de4d6b6 | note | FREQUENCY: Each Lot
429f80ac-4467-5202-a587-ea86216e2e62 | note | ACCEPTANCE CRITERIA: In areas where excavation is to occur: all vegetation, refuse and obstructions totally grubbed or grubbed > 0.3m below subgrade and batters (whichever is the lesser treatment)
c4b0f60c-ef0f-580a-a35f-478cef69d5c4 | note | REFERENCE DOCUMENTS: Cl201.05
51a4a279-8076-5c7b-888a-6eb82301c676 | note | INSPECTION/TEST METHOD: Visual inspection
72d28079-259c-5101-924d-a4a6fafd39a7 | note | RECORD OF CONFORMITY: This ITP signed
d5d4d87e-deec-5595-ae64-8aabbd47354a | note | IP
0363a4b8-9e4c-5b08-8b9a-c22c546ed2a0 | note | RESPONSIBILITY: Site Engineer
6f2c79ce-9b79-5b84-aef1-09b9e2e5387c | date | Date Completed:
3fea4e0e-64e0-4dd8-8ebd-3243cf88c6c3 | checkpoint | 2.3 - Clear and grub trees and vegetation (embankment areas)
871b09e6-b563-5344-9466-86e9049f3f9d | note | FREQUENCY: Each Lot
4abdea04-bafc-5aeb-9d07-2d58eb933b02 | note | ACCEPTANCE CRITERIA: In areas to be covered by embankments < 1.0m in height: all vegetation, refuse and obstructions grubbed > 0.3m below stripped surface OR > 0.6m below subgrade level (whichever is the lesser treatment)
1fb1d363-cd1a-5d44-a20d-410e29e6551b | note | ○ In areas to be covered by embankments > 1.0m in height: foundations may remian if located or cut off not more than 0.4m above natural surface but not less than 1.0m below subgrade
36fe859e-d562-5171-8842-c3ef83cffda9 | note | REFERENCE DOCUMENTS: Cl201.05
347372dd-857a-5305-a489-a82cc7a3ccf5 | note | INSPECTION/TEST METHOD: Visual inspection
36349761-d9bc-5976-9713-2f5a00dddaee | note | RECORD OF CONFORMITY: This ITP signed
d12603bf-3aef-5728-abb9-04ae5f94b3bb | note | IP
826bcc99-4c54-5121-abbb-cf208e26d95e | note | RESPONSIBILITY: Site Engineer
70aa8aa3-27d0-569d-a98f-9dd9e2f8c819 | date | Date Completed:
e4492093-5490-4bf5-859d-5865dae265ab | checkpoint | 2.4 - Clear and grub trees and vegetation at culvert sites
86a86409-02e9-5239-9587-0ef9571bdc39 | note | FREQUENCY: Each Lot
fc162fa0-733c-5544-ba01-4f443cd00570 | note | ACCEPTANCE CRITERIA: Clear and grub trees and stumps within 10m of any proposed bridge or culvert having a waterway area > 6m2 (unless otherwise shown on drawings)
5402f6e0-43c7-5089-9b94-8a0617a183d2 | note | REFERENCE DOCUMENTS: Cl201.06
c51e21a3-43a7-5bbc-a485-49d8103291f2 | note | INSPECTION/TEST METHOD: Verify
c7783ec9-28ad-56e6-bbb5-1ea14270ca92 | note | RECORD OF CONFORMITY: This ITP signed
bfff7fde-82d1-5ac1-b1c3-7979ac7f4ef2 | note | IP
fe634f17-c416-5434-8144-52aa5fe04379 | note | RESPONSIBILITY: Site Engineer
6ff5f44b-db46-5961-adc0-b0326d95bcba | date | Date Completed:
7238c519-32d0-44cb-b878-03d93b64ae75 | checkpoint | 2.5 - Backfill holes
9d70a48c-e269-59dd-8e76-c7ca935e7fb2 | note | FREQUENCY: After clearing
6c7b5e58-0a6b-5502-8c20-3d8a8eb66bca | note | ACCEPTANCE CRITERIA: Any remnants of pits shall be backfilled with similar material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
2405bb84-105d-562a-b305-3d027d77b53b | note | REFERENCE DOCUMENTS: Work Pack Cl201.05
375985ca-7351-5e79-8975-4a65964c7456 | note | INSPECTION/TEST METHOD: Verify
a11d151d-fcb2-56d0-84cc-0e56a6b81321 | note | RECORD OF CONFORMITY: This ITP signed
6113525d-a67d-52d4-904e-72e6de7205b5 | note | TP
96d532c1-fb1d-5475-b2cd-4bdde76b94ae | note | RESPONSIBILITY: Site Engineer
3f3d4923-203c-5928-b904-059d3c47df76 | date | Date Completed:
2fb30172-3a6a-4bde-8553-4ce009c86671 | checkpoint | 2.6 - Dispose of Trees and vegetation
eed877d1-f64c-56fc-b17b-f799ab710708 | note | FREQUENCY: After clearing
a410877f-4afc-51ba-89a3-bb96c4f9ab2e | note | ACCEPTANCE CRITERIA: All vegetation within clearing limits shall be removed from site. Weeds not to be mulched and disposed of appropriately.
945b3756-20bc-5603-959c-de2aac83f47d | note | REFERENCE DOCUMENTS: Cl201.07
fe801138-cd85-503c-9c4a-7aeffc4d6f88 | note | INSPECTION/TEST METHOD: Verify
9b4cc6ec-a2b4-502f-b75b-3502b6b6f8c7 | note | RECORD OF CONFORMITY: This ITP signed
bee1236d-395f-5e33-b326-5abecacc03a3 | note | IP
7af4b583-d0e0-53bf-9b39-ba7ea70fc531 | note | RESPONSIBILITY: Site Engineer
7d2501bf-115b-543e-87c7-53cd986e7e86 | date | Date Completed:
1dac20ce-7d06-40b7-81e7-998ca642f827 | checkpoint | 2.7 - Damage to Fencing
98b70d25-b997-56df-ad11-b88d2f4f0d05 | note | FREQUENCY: During Clearing
c4093e29-5214-5216-ae3f-9f4e9d14718f | note | ACCEPTANCE CRITERIA: Immediately repair any damage to fences to a condition at least equal to that before damage
c93ee17f-8c34-512e-b4e9-a2bce4dc8e4a | note | REFERENCE DOCUMENTS:
7f21f095-b9f6-5dc3-8d5c-019cc5aa86b2 | note | INSPECTION/TEST METHOD: Verify
f93c19e4-0427-5a3b-ba41-38c0c42c578f | note | RECORD OF CONFORMITY: This ITP signed
92c25d65-4cf3-574b-b562-ed02251f1281 | note | IP
757cadaa-1d83-52f2-a79d-de725a5da008 | note | RESPONSIBILITY: Site Engineer
0a1320b5-a237-523f-987d-41c97d79a9d3 | date | Date Completed:
0cc48126-9a7f-44f7-8948-9daf8e9d31f4 | checkpoint | 2.8 - Salvage of Vegetation
c4e5ae7b-9cd0-5526-b180-181c64792695 | note | FREQUENCY: During Clearing
33337043-e448-519a-a7b5-09e81fe84368 | note | ACCEPTANCE CRITERIA: Co-ordinating works with activities involving the salvage of plants and the collection of cuttings and available seed from areas of native vegetation on the site.
ea752a98-2893-54cc-ae5f-c5c1710326a2 | note | REFERENCE DOCUMENTS:
4235e68d-d813-5542-8848-aaad66ac5a34 | note | INSPECTION/TEST METHOD: Verify
96b6ca11-d379-5431-92df-fda6caca8d26 | note | RECORD OF CONFORMITY: This ITP signed
78c9f3d2-f55a-577c-a408-3e757735b698 | note | IP
d9414b16-d038-55f8-bb95-8fc25afc98b6 | note | RESPONSIBILITY: Site Engineer
7b68940d-888f-5cec-bd79-628f7fce2b6a | date | Date Completed:
4b3ff4e1-ec59-44ea-990c-1779139eb4bf | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c95c5dad-a2d5-5357-822d-56696a2a3fa9 | textbox | QAV - Print Name:
43162616-6a77-5bb5-9387-59e4242d2329 | textbox | QAV - Position:
ed646561-6cc6-52f1-86c3-8f5f8defd656 | textbox | Fulton Hogan - Print Name:
1564af1a-5ea5-5f2a-a445-60f29007d5d1 | textbox | Fulton Hogan - Position:
6b45587f-aa7b-5edf-baac-d8b136e3fbe1 | date | Work Completed On:
aa8f376b-2657-4dee-aa1b-40042ea2a8ed | signoff | Add Signature
21401525-0012-46e5-a968-0d0b2a27afd9 | checklist | DTM-ITP-003- Earthworks Demolition Rev0 | itp | DTM-ITP-003- Earthworks Demolition
35832db6-d0bb-4f06-9f0e-b770577bfb82 | section | 1 - Preliminary Works
87a550e6-0823-455c-89c2-8025f6dfee9e | checkpoint | 1.1 Check for correct documentation
f0eb97b3-8884-596f-abaa-8e5b31c89424 | note | FREQUENCY: Prior to commencing any activity
7bde79dc-68f9-553f-9cdf-02f244d9539d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
b267049b-4f74-5b2a-9c89-b8d00a2189c0 | note | – using the correct and complete set of drawings
d522b19d-258e-5e07-899f-329031c6f2bd | note | – all drawings are the latest revision
94ce975c-6385-5712-a5d2-1fb6cc36f580 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
1ecbc5e7-8191-5398-a2b1-3b7962442904 | note | INSPECTION/TEST METHOD: Visual inspection
a5e9656f-e3a3-5a44-9234-49e0d75b552f | note | RECORD OF CONFORMITY: This ITP signed off
3ba874b5-de5d-5e5a-98e1-9504da249f5f | note | HP*
3491bcb4-f82a-5df7-b394-f04cb5b819b3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0a4be045-86ab-500f-90a7-fcec3db23047 | date | Date Completed:
032acfb9-6dda-4e9c-ad6f-f84cc679b8f9 | checkpoint | 1.2 Implementation of all measures and controls
d9b7d730-67a0-52d9-8ba8-8cefb94abd0c | note | FREQUENCY: Prior to commencing any activity
a82ea240-8562-5539-b354-6bb766749e3e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, JSEA, SWMS & Work Pack
d918cc24-2253-517a-99eb-8fa99dc63b2f | note | REFERENCE DOCUMENTS: PMP, EMP, TMP, JSEA, SWMS, Work Pack
75ff653f-05fa-55e3-848d-e1aedd909702 | note | INSPECTION/TEST METHOD: Visual Inspection
b6df93bb-63bb-5dc2-af80-bd1716fa4026 | note | RECORD OF CONFORMITY: This ITP signed off
408bb220-1a1a-5a27-89cb-7b70c47334de | note | HP*
e499f18c-a063-5160-a3a4-d1cc0bcb364d | note | RESPONSIBILITY: Site Engineer / Site Foreman
25863c8f-39b9-556c-9050-76f58ae23774 | date | Date Completed:
3f1f832a-0615-469e-99ef-e735ff17c243 | section | 2 - Construction Works
ecf8d1d9-4189-4cc7-a17e-d01a5f229498 | checkpoint | 2.1 Survey Set-Out
fc9dffbd-3174-552c-b711-d84a9ae21816 | note | FREQUENCY: Prior to commencement of excavation
77546868-73df-59de-971c-813bc2f7776a | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
4e97442e-f261-5375-83a3-de1af1ce7fbd | note | REFERENCE DOCUMENTS: Work Procedure
f3102c44-38f5-51f2-9cce-bb8a5cd55897 | note | INSPECTION/TEST METHOD: Verify
8d576cb8-adff-5460-819a-65845488b1c0 | note | RECORD OF CONFORMITY: This ITP signed off
c3360caa-8efc-52ec-8d40-01de15685fd8 | note | IP
393a68e8-dae2-5138-8f38-30f1e9499771 | note | RESPONSIBILITY: Site Engineer/ Surveyor
c64eeaa5-60f0-5ef3-a37f-4f6340830527 | date | Date Completed:
799d83a3-4f60-4da3-a129-c9650fedeb28 | checkpoint | 2.2 Excavation Permit
03eb3bad-7ee9-50b3-b054-d02a81a33a55 | note | FREQUENCY: Each lot
05b20a37-81a5-5cf8-9b91-985e561ce0e5 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
3aeecd28-b75a-5483-84db-bd898de9d456 | note | ○ Plant and equipment shall be appropriate for the task.
d88258eb-17bc-57de-a38a-45b790172f74 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
33018481-990d-53f4-bc09-839027b492cd | note | REFERENCE DOCUMENTS: Excavation permit
c0f8ad95-80c9-56c5-a750-a969cc6f066e | note | INSPECTION/TEST METHOD: Verify
5dafb385-edab-5d89-9c4a-14050ad9a859 | note | RECORD OF CONFORMITY: This ITP Signed Off
17f183a9-6bb2-5fc6-9d4d-898311581265 | note | HP*
caa09739-1063-5027-8877-e1fd60810f81 | note | RESPONSIBILITY: Site Engineer
cd9def00-e488-5dce-b086-8294d98cbf22 | date | Date Completed:
01e0efe8-6555-4cfa-92fc-46f32da51b2f | checkpoint | 2.3 Material Categorisation
2e2a43ac-dda0-5624-9ebd-6848c33f50b0 | note | FREQUENCY: Each lot
f66df72f-eaa7-55c3-a4f8-c1d1bcaa2692 | note | ACCEPTANCE CRITERIA: HOLD POINT
8e9c4190-083b-5d8c-b240-29abbc4a92a5 | note | ○ Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
102ad923-cc7b-5f18-b693-32a5841f0d23 | note | REFERENCE DOCUMENTS: 204.06(c)
bf2fe195-4921-572f-8140-c77901b61772 | note | INSPECTION/TEST METHOD: Verify
2a43679b-e731-5176-93b3-5dd905e9305f | note | RECORD OF CONFORMITY: This ITP Signed Off
e77b0694-6eb8-55dd-8508-c6848e4971ec | note | HP
719594ee-7180-545b-aaac-1febda669b93 | note | RESPONSIBILITY: Site Engineer/ Superintendent
3003c5aa-8f02-5f51-a752-630c9cf8f867 | date | Date Completed:
112364dd-e9fd-4bcb-8993-955052ee4a4e | signoff | AUTHORITY HOLDPOINT
96b08bd4-bdac-408a-a1f7-45c225d32790 | checkpoint | 2.4 Stripping of Topsoil
3f4ef5b5-67e5-5e33-8d7b-586726814c51 | note | FREQUENCY: Each lot
08a89dc1-0e50-5da8-95de-ef0c137739bd | note | ACCEPTANCE CRITERIA: Topsoil stripped to full width of the formation and placed in approved stockpile location. Stockpile shaped to shed water and stripped surfaces graded to be self draining. Topsoil shall not be removed from site unless approved by the superintendent.
6d71dd34-8267-5d72-9939-ef4c0eddd28e | note | REFERENCE DOCUMENTS: 204.05
7e7f9716-06e9-5751-836e-9100dc68ee5f | note | INSPECTION/TEST METHOD: Visual inspection
45faca66-4638-5ed4-ac6d-a7bf4b16fa80 | note | RECORD OF CONFORMITY: This ITP Signed Off
39a5732f-1070-5922-9a22-59783bafaa49 | note | IP
fa042f8e-bf1c-5596-ad26-9e30cb195214 | note | RESPONSIBILITY: Site Engineer
40d0c638-78f3-5b9a-951e-2930651098e6 | date | Date Completed:
e85876a2-2a79-4e3f-a47f-468eb41f12d0 | checkpoint | 2.5 Type A Material
c6385ed8-e19a-5063-bde7-dc62970bf13a | note | FREQUENCY: Prior to Commencing
486f9b1a-7cbe-5f77-843f-cf17f3891565 | note | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
14364c38-6933-5ce8-bf19-0a09eec74b08 | note | ○ HOLD POINT
0adca298-cf97-5c83-a2fa-d17a3c4ed838 | note | ○ Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent.
414e8c1b-e78d-5a9d-b224-880ac1b5d245 | note | REFERENCE DOCUMENTS: 204.04(b)
3bec5ae9-ecd0-550c-b528-3412cf682347 | note | INSPECTION/TEST METHOD: Document Review
18f95cb7-f662-5205-b412-59f76a60b16c | note | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation, Signed ITP/ records
0dbe48c2-e32a-5dd9-8498-807147e38d1b | note | HP
9556e1d4-47c2-581a-be78-7a4fb7053085 | note | RESPONSIBILITY: Site Engineer/ Superintendent
fa5b24e3-f84d-5e85-b64f-266c2f54be93 | date | Date Completed:
8d12b47e-76a7-40f8-883d-5e8cfddb8078 | signoff | AUTHORITY HOLDPOINT
3a3b3349-32b3-4155-a2d3-57ec1a873ac3 | checkpoint | 2.5 Type B Material
b6de7786-2ebb-59e3-bdd2-88b08901c7fc | note | FREQUENCY: Each Lot
2d7717db-2730-56f6-9f51-e768f533654a | note | ACCEPTANCE CRITERIA: Type B material shall be free of topsoil, deleterious and/or perishable matter. Type B shall have a minimum assigned CBR >5% and Assigned Percent Swell < 2.5%. Materials with swell greater than 2.5% can only be used as Type B material if approved by the superintendent.
de4c311e-4fad-5813-b20a-d43eaeac8a99 | note | REFERENCE DOCUMENTS: 204.04(c)
ebb5d02e-b628-5f42-930e-7d8d35bf6e99 | note | INSPECTION/TEST METHOD: Test Point
4f70ade5-0698-530e-8b70-ad08da4fab16 | note | RECORD OF CONFORMITY: Test Reports
c71bb65d-9aac-50fd-a36b-01f64f4c6ee5 | note | IP
1458fd14-f723-5c3b-b46f-e4c74f217a23 | note | RESPONSIBILITY: Site Engineer / Superintendent
18cbd72d-7a3b-5440-af0b-695ce57f08e2 | date | Date Completed:
81ed21a7-f55a-4363-b766-4a08a7efa18e | checkpoint | 2.6 Acceptance of Rock Subgrade (when applicable)
db11a445-a0be-5af9-b5b4-8184e3dc76b9 | note | FREQUENCY: Prior construction of the regulating layer
e22ce874-a3d7-5210-8e47-53405c59624a | note | ACCEPTANCE CRITERIA: HOLD POINT
1f4d7da2-f230-55e4-8338-461948c4454e | note | ○ Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
f2d75627-e524-5667-bac6-e243cf368281 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
72e91fa5-48d8-598d-b469-ac303dae96b8 | note | REFERENCE DOCUMENTS: 204.06(f)
fac5d2db-1cae-527c-83a4-a47c62b36c21 | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
2d667551-9b67-5e52-939a-910a4f732a0b | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
61d3dceb-6934-51a1-ac6c-c4b515315204 | note | HP
09119aea-7373-5cbe-a486-b184ba43328b | note | RESPONSIBILITY: Site Engineer/ Superintendent
4a91920e-4536-5ac2-8f0b-650fcbc5892e | date | Date Completed:
68e5c353-724f-405c-9f5a-adaabdfa86e8 | signoff | AUTHORITY HOLDPOINT
520847a1-7c23-490b-97a4-6df72926d306 | checkpoint | 2.7 Unsuitable Material
323daa7c-a5ac-5900-8e6f-e6ec0fb7c1a7 | note | FREQUENCY: Each Lot
a2ecb495-4483-5a2e-957f-71db8672a6f1 | note | ACCEPTANCE CRITERIA: HOLD POINT
c09e2b2d-1596-57d1-b740-1d9cbd7c05dd | note | ○ Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
548698ef-8757-54ef-87b5-421884ef1556 | note | REFERENCE DOCUMENTS: 204.07(d)
20aaa280-b18c-515b-bb26-e69b506acbbc | note | INSPECTION/TEST METHOD: Visual Inspection
81791d72-cb0d-54c9-b5a3-6a287116a44a | note | RECORD OF CONFORMITY: This ITP Signed Off, Work Procedure
99f652d2-38cf-5453-9531-48fcd6fe6491 | note | HP
9b104fb8-17ab-5f65-ad13-24b3a76b19f3 | note | RESPONSIBILITY: Site Engineer/ Superintendent
f6ccb8a5-6d8c-5dda-bfc7-ab1af2764bbc | date | Date Completed:
348cbeab-bae8-463b-8676-8d6a00709b19 | signoff | AUTHORITY HOLDPOINT
c63d6ada-d230-4e34-a13e-bd4a2d0278c4 | checkpoint | 2.8 Groundwater
48d3b861-9fbc-5f42-aedd-2530ff07913b | note | FREQUENCY: Each Lot
ba66d295-176e-5106-8aff-817ba6356966 | note | ACCEPTANCE CRITERIA: HOLD POINT
6d6ee4d2-1332-53db-a2dc-4632119ffceb | note | ○ Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
d831d6a0-810a-5c2c-a519-2823043c86c7 | note | REFERENCE DOCUMENTS: 204.06 (h)
0d25939a-de83-58f8-b59b-63fa53ad254f | note | INSPECTION/TEST METHOD: Visual inspection
69a2eb79-73f9-5cbb-87c1-21251d6b783d | note | RECORD OF CONFORMITY: This ITP signed off, Work Procedure
84bea4da-5652-58b3-b50d-b8377048b3ab | note | HP
cdff3982-fd09-56b1-960a-68de902c5242 | note | RESPONSIBILITY: Site Engineer/ Superintendent
8540a718-eca2-59bf-a535-996c9d0e0bb7 | date | Date Completed:
f2843205-91b0-41e8-b4f7-44d4aef2e735 | signoff | AUTHORITY HOLDPOINT
529633bb-7275-4f85-b94f-4a96b82225bd | checkpoint | 2.9 Trimming and Level conformity
4ee68268-b510-5d45-b984-811e1bdcda75 | note | FREQUENCY: Each Lot
5cd83eca-144c-5154-8c2d-78fdeb22fc05 | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
95f78799-1a3f-57da-9a65-5f3696188661 | note | ○ Level tolerances:
b917797b-c3fc-51d5-a5e2-02cc75a9a8e9 | note | – Range x = +5, -15mm
5d207bd9-0148-5446-bed9-621d68e0d702 | note | – Max S = 12 mm
59ef12d0-833d-5c68-a6d0-a0947c31495c | note | ○ 80 measurements per lot (Scale A)
b63ccf20-6014-5a75-9884-9892740cb4f3 | note | – Range x = +5, -25mm
8d4298a9-283e-5262-8f7d-1565cf406271 | note | – Max S = 15 mm
5ef8f02e-ff2f-523b-a2e1-877dfa697eac | note | ○ 40 measurements per lot (Scale B)
b2f023de-ee30-5292-9c70-4e4fe4d97d67 | note | REFERENCE DOCUMENTS: 204.03(f)(g)(h)
bdd35211-3e11-550d-87d9-b60ad9f78bd4 | note | INSPECTION/TEST METHOD: Survey Report
f03d3755-7c5d-586a-ab69-a45bad93d1ca | note | RECORD OF CONFORMITY: Survey Record
c0fe898f-30c1-51cd-bc79-18943c7c4031 | note | SCP
11106bc9-a8bd-55c0-afea-fcf70dc7671c | note | RESPONSIBILITY: Site Engineer/ Surveyor
af574adb-b15b-5696-a94d-72f8e9cd9e70 | date | Date Completed:
0f86b799-5844-47a6-8f4e-b1070736e7dd | section | 3 - Testing
bc9cc799-b643-41c8-9c20-975c243250ec | checkpoint | 3.1 Proof Rolling
ddaba18d-d39f-5410-a4f6-aee6a6cefeeb | note | FREQUENCY: Each Lot
57b502ae-556d-5308-98b9-2222bcb83eaf | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173, before proceeding to subbase construction.
68753619-4725-59cf-a1dd-c590823aa400 | note | ○ The Contractor shall submit a test rolling procedure to the Superintendent including the method of preparing an area for test rolling, the extent of test rolling and a requirement to provide not less than 24 hours notice of the location and commencement time for the test rolling to the Superintendent.
cd64ca2b-49d5-50c3-adab-81adf5d36d66 | note | REFERENCE DOCUMENTS: 173.03, 204.12
db4fc166-42d7-5d70-9306-f02162f10c46 | note | INSPECTION/TEST METHOD: Visual Inspection
bfe32bb9-084e-5c7d-880f-9046f3cf4fa0 | note | RECORD OF CONFORMITY: This ITP signed off
f17fc5ac-e72a-5422-807e-18c8dfaf44bf | note | HP* WP
a79c5175-5624-58b8-9fff-134715fa6aae | note | RESPONSIBILITY: Site Engineer/ QAV
dcb079dd-777b-59e0-b082-2d8debdba3d6 | date | Date Completed:
3198912b-0f7b-4825-b939-c3982114c903 | signoff | AUTHORITY HOLDPOINT
13e1b6d0-9e53-48e9-8e9b-1f6f5005eddd | checkpoint | 3.2 Compaction Testing
abc22811-c840-5992-b948-9ae3df6fe68e | note | FREQUENCY: Each Lot
3bc05732-42e1-533e-b5b7-8542046feb10 | note | ACCEPTANCE CRITERIA: Ripped and re-compacted material below Cut Floor Level = minimum compaction 99% MDD.
9ec8cb80-5601-5d82-b310-d3ed9e798577 | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 99% MDD.
10b66637-9338-5571-a90b-b907fb6cbc95 | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 97% MDD.
17c76ed2-2355-58be-b819-26960a36b8b8 | note | REFERENCE DOCUMENTS: Table 204.131
d1c596e3-d5f1-5be9-bb49-7103663b4fad | note | INSPECTION/TEST METHOD: Test Point
2fe9e162-11c2-515e-a885-0237346cf665 | note | RECORD OF CONFORMITY: Test Records, Lot Register
0d401493-e3dc-5d24-8e3e-db5a45584a08 | note | TP
d12ba0f2-dc20-5804-9b58-0cf190840ab8 | note | RESPONSIBILITY: Site Engineer
5307e531-53aa-582c-acb4-cf9e33d6ada1 | date | Date Completed:
322d4055-e4d5-4161-8f24-fea433470604 | checkpoint | 3.3 Materials Property Testing
654718eb-72fb-5ba3-bf09-696db7c57dcc | note | FREQUENCY: Each Lot
ff0045d9-c52e-5807-9d19-e190ce2d27e0 | note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Frequency of Testing and Material Properties Testing Requirements.
52aca5c9-3c21-5ef4-9e14-f7d43aa52643 | note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
fa1b8d13-3232-5b31-8058-1edda881493f | note | REFERENCE DOCUMENTS: Tables 204.141, 204.142, 204.161
84f993c5-4f09-51f8-bf92-7d863e18d7aa | note | INSPECTION/TEST METHOD: Verify
25e52858-1eae-51e1-80c6-0bbbb4d9fa0e | note | RECORD OF CONFORMITY: This ITP Signed, Test Records
b8cd9b0e-4a01-5a84-835f-5dd297ad718c | note | TP
2730d33c-f14b-50c2-9af1-fd92b2659ce9 | note | RESPONSIBILITY: Site Engineer
bc563173-1b81-5226-a628-d8f4db97854f | date | Date Completed:
39ac548f-3700-4231-beba-9becf60e8c94 | checkpoint | Final Inspection
1824ad7b-2037-5e72-923e-c95f1c4c7009 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
98480b67-069c-5523-b958-20807d491c24 | textbox | Print Name:
c6dac621-e790-528a-a936-7af5f6ae13a3 | textbox | Position:
71550dec-7b12-55ef-a6cb-542898c0718f | date | Work Completed On:
fce7aed6-771a-47b2-bdb4-e0a52c44e5aa | signoff | Add Signature
a0d1a2b7-9d17-43a3-b4e5-4a179b167459 | checklist | DTM-ITP-004- Service Relocations - Telstra and NBN Rev1 | itp | DTM-ITP-004- Service Relocations - Telstra and NBN
e2929edf-a48c-4495-a490-5e51752822b5 | section | 1 - Preliminary Works
a8e3ef38-a922-4d7e-b6b9-305edcd9ef5c | checkpoint | 1.1 - Check for correct documentation
8739de85-a719-53ad-ae88-fe3abe7991fb | note | FREQUENCY: Prior to commencing any activity
7b2706f3-eed3-520b-bf03-cd4bcddbeb26 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
cfab979a-0043-59b1-8013-01d8750c4906 | note | – using the correct and complete set of drawings
aef4afea-cc0f-5722-868c-25b67e3e11a3 | note | – all drawings are the latest revision
4f64324d-dc54-512a-9c12-b2a1f19a461e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
8e074d9b-b15d-534a-affd-2f213516bb5b | note | INSPECTION/TEST METHOD: Visual inspection
903a8c05-cf0c-54e9-9ef9-1e4eb546e1c9 | note | RECORD OF CONFORMITY: This ITP signed off
a4b19705-7fcc-56c5-93c9-a26eee34c696 | note | HP*
f21b82c4-3551-5cc8-8aec-238ddd4fddb2 | note | RESPONSIBILITY: Fulton Hogan Engineer
7774f7ef-2a25-59e0-aebb-4bd0eb2530f0 | date | Date Completed:
fba94add-43b2-43ab-8477-fc2ad1a7d90c | checkpoint | 1.2 - Implementation of all measures and controls
c6f7b3fa-bed3-5e87-befb-03efdbff5439 | note | FREQUENCY: Prior to commencing any activity
4b5a6131-2fba-5860-99a6-a8086f6e3f61 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP/TGS, JSEA, SWMS & WP
e346acfd-a32d-5896-bdb9-06ff31850176 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
1e33b699-e9d5-5ce8-b362-df46f8693411 | note | INSPECTION/TEST METHOD: Visual Inspection
050c4651-7f1a-5c03-99e1-0a305c093b86 | note | RECORD OF CONFORMITY: This ITP signed off
b22980e5-5ae6-5a5d-9538-6ec97c21a301 | note | HP*
92b5eed7-be37-5d22-9127-44154718d429 | note | RESPONSIBILITY: Fulton Hogan Engineer
b9df3831-dd87-579d-8fad-74898d49a90c | date | Date Completed:
bc5fb38a-c27f-4962-bf53-fc06c9f6dd4d | checkpoint | 1.3 - Scheduling trenching works with Telstra/NBN contractor
3a44dbe7-c764-5a16-8b53-b241a6ca4771 | note | FREQUENCY: Prior to commencing works
218e374c-b8e8-508d-8b2b-30af758b3bc1 | note | ACCEPTANCE CRITERIA: Provide Telstra with an accurate date for when the trenches will be available for cable installation and when final ground levels will be established
d289c897-3936-5562-bc2d-734dc675e5e3 | note | REFERENCE DOCUMENTS: APPENDIX L
aa568454-9bdf-5272-b238-99073affd167 | note | INSPECTION/TEST METHOD: Verify
21bc649c-6936-5274-8d7e-c4ce392d8a75 | note | RECORD OF CONFORMITY: Service Installation Programme
d74c72e0-c2c0-59a2-a525-6f0d0ad216f9 | note | HP*
93e4c8e4-fd5e-51bc-913c-b665f24098e9 | note | RESPONSIBILITY: Fulton Hogan Engineer
f80677c2-85c8-5cd6-aac2-4e2456cc6def | date | Date Completed:
9b0faa9a-a6f8-4fce-879f-26db6d90bc2b | checkpoint | 1.4 - Proving Services
8900a367-4b6e-51e6-93bb-eb76bc8301bf | note | FREQUENCY: Prior to commencing works
a1e2adf4-52ec-5302-97da-60f3127af6aa | note | ACCEPTANCE CRITERIA: Underground services shall be proved by clearly marking the location of the service on the ground and physical exposure of relevant services at appropriate locations, in accordance with service authority requirements.
230c2d71-7f9b-58ed-a702-b3e4d972b94c | note | REFERENCE DOCUMENTS: 160.12B
aad6f317-3890-58ea-9cf4-9e65c38d3d6e | note | INSPECTION/TEST METHOD: Verify
f92132f4-7ceb-513c-813e-ce23c5eb0750 | note | RECORD OF CONFORMITY: This ITP signed off
5165d4e0-06b8-5cbc-a2bc-20c8f8dc30d3 | note | HP
79285147-1b84-5fcd-bf7c-6a5031d440ea | note | RESPONSIBILITY: Fulton Hogan Engineer/QAV
7adc9435-dda9-5df2-b9a2-26edc31eaa73 | date | Date Completed:
439c7f63-f6ba-4f9f-abcb-8b3c3e4e8906 | signoff | AUTHORITY HOLDPOINT
6b22b14f-cab4-4e5a-9dca-9d48e426a202 | section | 2 - Construction Works
8b0645aa-f560-4853-a4c9-cfc489917a9c | checkpoint | 2.1 - Survey set-out
f39d6dbc-fe7d-58e4-9f58-7dae6c1caef6 | note | FREQUENCY: As required
cbad503e-5e24-5951-89fa-5f7dce3854ed | note | ACCEPTANCE CRITERIA: Prior to setting out trench, advice should be sought from Telstra/NBN for accuracy of cable routes. Cable routes shown on drawing are only approximate.
8375a272-ab55-5dba-be7f-79f303725ff2 | note | REFERENCE DOCUMENTS: APPENDIX L
c0944b17-126c-573b-88b2-13195a724a92 | note | INSPECTION/TEST METHOD: Verify
591366a0-c10d-561e-91ca-e45b6c7d2591 | note | RECORD OF CONFORMITY: This ITP signed
c525372b-78a7-51a0-a531-21bb8e12cb46 | note | IP
209f92bf-bb19-5024-94d1-e2b95696fe2b | note | RESPONSIBILITY: Fulton Hogan Engineer
b1c8588f-dedd-5531-9394-d62be1cfd845 | date | Date Completed:
a899e2f5-928a-42fb-9050-581c4aec190e | checkpoint | 2.2 - Excavation
2329d397-a2cd-5cd6-bf60-93cd38e3e8ec | note | FREQUENCY: Each Lot
d1a765c2-5197-56da-9313-b8f0485cabab | note | ACCEPTANCE CRITERIA: The edges of all trenches located within a road pavement shall be sawcut
29e786bd-b579-5808-a897-23ea0ca016b3 | note | ○ Trench to be excavated to the nominal trench depth of 1.8m with a minimum width of 1.0m.
5e9ed78b-c45d-5713-9575-fae9de8e4d6c | note | ○ If trench depth is greater than 1.5m; bench, batter or shore
e2fc3c4d-6f20-58ad-a877-a31323ff7e8e | note | ○ 5m EW shall be provided for all conduit bends
ecf27a6a-7b28-5d04-ba3b-c2313c50e4a2 | note | REFERENCE DOCUMENTS: APPENDIX L
0ce2f4b1-15d2-55df-84f5-402ad6f9fccd | note | INSPECTION/TEST METHOD: Verify
994dd539-4a78-5c04-9074-00e914a49447 | note | RECORD OF CONFORMITY: This ITP signed
1a26cd82-a07f-5df6-8aeb-aa3dff83cd99 | note | IP
36df679e-4a7a-5549-8cef-afa8f472f77e | note | RESPONSIBILITY: Fulton Hogan Engineer
ac042d2c-b7ac-5403-9471-b1e1f2642523 | date | Date Completed:
f0893a60-b6ca-4372-b1c3-001d559c370f | checkpoint | 2.3 - Material Assessment
41c04de9-a0a2-53f9-8b5f-efa760a18c41 | note | FREQUENCY: Each Lot
5a6a02fc-7da0-5e9f-ab6f-85bc2df38e88 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
0e6bc110-e6bf-5f63-b781-4ef550460c96 | note | REFERENCE DOCUMENTS: 204.06
548bd80e-05c6-5ca5-a5eb-ac79aaacca9b | note | INSPECTION/TEST METHOD: Verify
c7a55852-4f0b-5397-8f53-b924936328bd | note | RECORD OF CONFORMITY: This ITP signed
abf8d17e-de0d-5d82-97b1-473d48fe1570 | note | HP
ced14e5c-5abf-5a81-a081-17584b689f38 | note | RESPONSIBILITY: Fulton Hogan Engineer/Superindentant
04119fb9-fe4e-5a49-a021-24e35f62fddb | date | Date Completed:
d59f233d-7e4f-48e5-a73f-f4df27c19519 | signoff | AUTHORITY HOLDPOINT
abd4f865-02e6-496d-80d8-578e82104a09 | checkpoint | 2.4 - Bedding
8fa01f5a-eabd-5aaf-8ecf-93561fd67dee | note | FREQUENCY: Each Lot
37ce90cd-8eeb-562f-b08d-c8e6402bf804 | note | ACCEPTANCE CRITERIA: Bedding material shall be placed and compacted for the full width of the trench to a depth of not less than 80 mm on an earth foundation or 200 mm on a rock foundation.
18c7439b-0b46-5d11-b893-518efa45c0ee | note | REFERENCE DOCUMENTS: 733.06(B)
85db5793-11c0-5263-b888-3fec1ce16b65 | note | INSPECTION/TEST METHOD: Verify
3b839f2c-4bb1-586e-a6d5-3fd5aa3de385 | note | RECORD OF CONFORMITY: This ITP signed
d45b9d85-56c7-5b84-bca2-8d57d2e36bf4 | note | IP
03c93edb-3821-5a76-a641-ef9f33a164cb | note | RESPONSIBILITY: Fulton Hogan Engineer
79822215-beb5-5866-ac66-a86d41f9ec8d | date | Date Completed:
c1263f74-23ae-433e-a389-cf028fa587e4 | checkpoint | 2.5 - Installation of Conduits and Cables
dae95c93-ac43-53ac-b2c5-e16a2e71ff09 | note | FREQUENCY: Each Lot
a51ec234-9580-58f1-bec0-a0737532b8c1 | note | ACCEPTANCE CRITERIA: Conduits and cables to be installed by Telstra/NBN contractor.
7c47345d-0c2e-5642-9cfc-175d31340329 | note | ○ Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by superintendent or representative.
03ec30e0-1c3a-559a-84df-2df1b00267d9 | note | ○ Conduit bends to be concrete encased as per Telstra Specifications
9aaa7c45-f32a-5975-b476-bce61227b5f7 | note | REFERENCE DOCUMENTS: 160.12A, 733.06(B)
7602de14-0da9-5872-bf5a-210defceed44 | note | INSPECTION/TEST METHOD: Verify
045df1ce-6467-5cd1-92d4-4320b9e3cfe3 | note | RECORD OF CONFORMITY: This ITP signed WP
2b618832-5c6a-5486-aa0d-06e1c0ff24b3 | note | HP
93805304-677f-5da0-9d62-2faa1e01aafe | note | RESPONSIBILITY: Fulton Hogan Engineer
ac6daedc-ee23-5629-9b71-237310b7feb9 | date | Date Completed:
ffff246c-8ed5-4565-a527-016f019cd24e | signoff | AUTHORITY HOLDPOINT
63e18159-0385-4e6a-9bb3-99daa7522f13 | checkpoint | 2.6 - Back Fill of Trenches
b9398c22-8c94-5525-a70a-2eb32045ae4b | note | FREQUENCY: Each Lot
6bc3edfb-70f2-524d-ba14-64c0169033b2 | note | ACCEPTANCE CRITERIA: Conduits to be backfilled as per Table 733.061
9d089547-29de-5dfd-94d8-d4689d1ebc05 | note | ○ Conduits shall be backfilled with stablised sand to 100mm above top of conduits as per AS3000.
f9e8f717-ecd0-5dad-9627-2e4cbb19fd2f | note | REFERENCE DOCUMENTS: 733.06, APPENDIX L
72521bd2-d281-5db5-9920-580702f40cbf | note | INSPECTION/TEST METHOD: Verify
e86a5be9-15c2-55c6-97be-526d736cca0a | note | RECORD OF CONFORMITY: This ITP signed
6b403bef-6cbe-569b-8b8a-bf51ad2d3db9 | note | IP
9f7b1a2e-cfda-5ada-8168-2acbca98235b | note | RESPONSIBILITY: Fulton Hogan Engineer
f9ba14c7-f502-535c-8a91-c5f784aa2868 | date | Date Completed:
1e6771ae-ed86-40be-b1f7-bc8c006b6165 | checkpoint | 2.7 - Compaction
0dc75fd3-d078-5ffa-b9c3-c0cccfa5c0c4 | note | FREQUENCY: Each Lot
be7bdaa5-c6d3-5f35-95d5-601f293adfbf | note | ACCEPTANCE CRITERIA: Bedding, and backfill shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Standard compaction test.
e1e1f1f0-5347-5bfe-91b2-ca3e2d8f8b88 | note | ○ All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
34c85aa6-e08f-5a0d-805e-6a5dce4eabb6 | note | ○ Backfilling beneath areas to be paved shall be assessed for compaction:
14c9f831-dc47-550e-a696-d939418b7818 | note | – The number of tests per lot shall be three
d05336f0-c0ae-5b9e-9abf-a8af5f7c7dc1 | note | – Compacted to a mean value of density ratio of not less than 95% (passing 37.5mm AS sieve)
aadb7a7f-d0ae-582a-a36e-155a0f1d31b4 | note | ○ Backfilling of pavement materials shall be assessed for compaction:
f189c219-817e-5869-879c-6b889c2d57f5 | note | – Compacted to a mean value of density ratio of not less than 98%
afed51f1-1a3a-5c65-9063-9364e8a36451 | note | REFERENCE DOCUMENTS: 733.06 (D)
95d7aec6-d931-5978-aafc-2c0896ad2cc4 | note | INSPECTION/TEST METHOD: Verify
23650fc9-48e5-585e-a275-5d8a9f4285f4 | note | RECORD OF CONFORMITY: Test Reports
a1cac03f-9765-5c8f-a67c-2334db86aee9 | note | TP
38b1660b-6800-53a5-90f8-469811a003b5 | note | RESPONSIBILITY: Fulton Hogan Engineer
167d8989-0121-54eb-90d8-3381108e8a3a | date | Date Completed:
87f17174-82ee-49f4-b325-4263f28be014 | checkpoint | 2.8 - Installation of marker tape
7cfa4074-6d05-5626-8aff-0018805c8876 | note | FREQUENCY: Each Lot
bef6c66a-664f-5358-9ade-613c6c7d346b | note | ACCEPTANCE CRITERIA: Marker tape to be installed by Telstra/NBN contractor
dd9d543e-0052-5c43-af6a-8731b02b46e1 | note | REFERENCE DOCUMENTS: 160.12A
d7be2bfb-5e6c-5c40-bde2-9162eef172a9 | note | INSPECTION/TEST METHOD: Verify
b1d55b4e-dfb9-55fa-9810-55440c7112e6 | note | RECORD OF CONFORMITY: This ITP signed
b79201e5-e59b-5ad1-8de4-795d119d48ba | note | IP
a99550db-9f12-5491-8a77-36555000cb59 | note | RESPONSIBILITY: Fulton Hogan Engineer
df26bd6a-f6fb-54a6-84b4-56e41d19f121 | date | Date Completed:
6d5e003d-1c86-4739-8632-87f8108dfebf | checkpoint | 2.9 - Cable Pits & Pit Lids
7a94789e-f7d2-52bb-aca4-47ea49f74860 | note | FREQUENCY: Each Lot
02a82bc7-f5ab-5f12-aac3-a4f4cbb0b63d | note | ACCEPTANCE CRITERIA: Cable pit excavation to be provided by Fulton Hogan
8d227917-8a3b-5165-b67d-00ad7766f8e2 | note | ○ Cable pit bedding to be installed and approved by Telstra/NBN contractor
6eb8c85d-9c01-5f77-b7d1-4db4c3aec3f9 | note | ○ Cable pits and lids to be installed by Telstra/NBN contractor
c5d824b2-05c5-55e0-bf26-c791ad1fdd07 | note | ○ Lift Analysis to be provided to Fulton Hogan by Telstra/NBN contractor 24-48hrs prior to lift.
3d255024-cef9-526a-adcd-c43125eb1947 | note | REFERENCE DOCUMENTS: 160.12A
3585c0de-ef2e-579c-aa91-d9cc3ff2cde7 | note | INSPECTION/TEST METHOD: Verify
e69a4ee5-d914-5b4f-ab07-b7070610675a | note | RECORD OF CONFORMITY: This ITP signed
755da37d-cc88-5a71-bfa9-67f617123994 | note | IP
4a925ebd-4e95-50cb-b620-e798184246aa | note | RESPONSIBILITY: Fulton Hogan Engineer
04da2545-fcf2-5df3-b0e5-8a0b1cc0860d | date | Date Completed:
f49b3102-d5a7-49d0-a850-9b00287921d6 | section | 3 - Completion
d41ed426-2765-4984-a7d3-e8c244b6a200 | checkpoint | 3.1 - Cleaning of Site
061ac621-351b-518d-92e8-9c8cbe4ec562 | note | FREQUENCY: Each Lot
f4fc0d99-b8a7-5aff-be6d-c7836b5aed53 | note | ACCEPTANCE CRITERIA: Surplus excavated material shall be removed from road reserve. All affected areas shall be restored to similar conditions that existed prior to work.
f253f432-33f6-58a0-884d-b230566e4b68 | note | REFERENCE DOCUMENTS: 733.09
8ff1cbf2-d64a-502d-aac8-67a370b1f9d0 | note | INSPECTION/TEST METHOD: Visual inspection
83d9fddc-e932-5070-bc3a-31f055738996 | note | RECORD OF CONFORMITY: This ITP signed
96865f95-a9e7-579f-bd6e-bb8594cdf6d6 | note | IP
741e4ad7-c220-53f5-96b7-7f52697ae402 | note | RESPONSIBILITY: Fulton Hogan Engineer
d0f6ba4f-90d2-5b2a-bda8-ab9003a1224c | date | Date Completed:
7a358ba3-9e3f-401f-8e20-fc0822f47132 | checkpoint | 3.2 - Recording/As Built
65693317-e1d0-5661-bf7f-27e37788ae19 | note | FREQUENCY: Each Lot
537eecac-24d8-5173-93d4-abadee2cc90a | note | ACCEPTANCE CRITERIA: Record any changes to cable routes on red line mark-ups. The final alignment of installed Telstra and NBN conduits shall be updated on the service plan
3ef40f8e-3b33-5f2c-8298-0d63d82b65e7 | note | REFERENCE DOCUMENTS: 160.12A
e0f4c80d-93e8-5f05-b60a-38454952486d | note | INSPECTION/TEST METHOD: Verify
4d99107e-d698-5a77-8dbb-ab82c1d4865b | note | RECORD OF CONFORMITY: This ITP signed, As Built Drawing
fb55a1bd-2000-5321-bc67-13fb97569314 | note | *HP
56f8010a-4a0a-5f3e-b395-ad2f89c31d83 | note | RESPONSIBILITY: Fulton Hogan Engineer
28de0ab5-3e73-5425-9bf3-a52f0c279f50 | date | Date Completed:
e446cb49-2ade-4ccb-a53e-416b54ea4173 | checkpoint | Final Inspection
39810d0f-f90b-5f68-835f-223c9f2c0c51 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9e6f536b-4fad-5044-a6be-16dedc437053 | textbox | Print Name:
4192c946-79ef-5d3a-be50-506a02b2c6d7 | textbox | Position:
18b70c10-43d6-5236-be4c-ad767e9dc8af | date | Work Completed On:
ff5276c4-a850-477d-a08a-7321eb093909 | signoff | Add Signature
8380e5f3-85ef-4d86-acf4-d566cff7fbcd | checklist | DTM-ITP-005- Service Relocations - Power (TasNetworks) Rev1 | itp | DTM-ITP-005- Service Relocations - Power (TasNetworks)
d939b3fc-278e-4d62-868c-df54f125cbcf | section | 1 - Preliminary Works
2ea71fd8-e69a-42c1-b39a-ec0d4e4e8acd | checkpoint | 1.1 - Check for correct documentation
4233d5bf-120e-53f1-8e7d-5d65a0981ea0 | note | FREQUENCY: Prior to commencing any activity
8f5c8733-cd0d-59c8-acaf-958478f3b05b | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
541acc5e-45ad-5502-b70b-b70d3bff793c | note | – using the correct and complete set of drawings
41b77edc-7783-5239-8431-ada38a7ce11d | note | – all drawings are the latest revision
da8eb80c-8856-5d7d-b794-d5694d0fdf9f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
194f0b86-01ea-5efd-9652-d0f99dcfa4b5 | note | INSPECTION/TEST METHOD: Visual inspection
7ba87a31-400d-5251-b1b4-2cb96010129e | note | RECORD OF CONFORMITY: This ITP signed off
eb116be9-5088-510b-bf8c-ffb608201949 | note | HP*
a0f34ef4-a9b8-5c5b-a522-19cdb3006ba5 | note | RESPONSIBILITY: Fulton Hogan Engineer
d27a18ce-27c3-5018-b3a9-81ee58e7158c | date | Date Completed:
317d7c09-9b94-46b5-8a7d-c880c8291dd8 | checkpoint | 1.2 - Implementation of all measures and controls
1759240f-3f10-593f-bdf7-c5c859a9f693 | note | FREQUENCY: Prior to commencing any activity
d7312306-1ec0-5c7c-a8b2-a3c4f453747c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP/TGS, JSEA, SWMS & WP
d148d02d-edcd-517e-98c0-0bbf8a77a811 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
3b83f8d1-1e03-542b-8ab7-05fc0e46e674 | note | INSPECTION/TEST METHOD: Visual Inspection
9d9019c4-2bc4-5a7d-862b-0efc6e2679c2 | note | RECORD OF CONFORMITY: This ITP signed off
c20b328a-d7d1-512e-9273-9cd8c3032bf5 | note | HP*
bd4f9120-640d-5ec3-9768-968a674efffd | note | RESPONSIBILITY: Fulton Hogan Engineer
05bcead0-affe-5137-a9d8-9f577785fcbb | date | Date Completed:
72c0e01b-1725-47be-acb6-b02577f6ef1b | checkpoint | 1.3 - Scheduling trenching works with TasNetworks
8c2e19b5-125f-59b3-9a64-de7d3b2647bc | note | FREQUENCY: Prior to commencing works
92cbbaa1-77a7-52b4-aa27-a91b60c1d4bd | note | ACCEPTANCE CRITERIA: Provide TasNetworks with an accurate date for when the trenches will be available for cable installation and when final ground levels will be established
31324708-486d-52d9-8935-3f1c5b86389e | note | REFERENCE DOCUMENTS: AS-32433
b5f80a46-9784-5f0d-b1b3-cc2225abc234 | note | INSPECTION/TEST METHOD: Verify
bcb3fe6f-733a-5cee-b001-840a0c2a5157 | note | RECORD OF CONFORMITY: Service Installation Programme
2bf0c941-13b2-59b1-9713-b66c47c83624 | note | HP*
34a3fb09-f2aa-57e8-9f4f-5357b104e75e | note | RESPONSIBILITY: Fulton Hogan Engineer
41baa004-54ca-5fc7-91e7-6389d7bf27d2 | date | Date Completed:
255c5a3f-9d48-45ef-b6ce-695a28da53c8 | checkpoint | 1.4 - Proving Services
1396a90b-2490-563c-9093-827ad4fe9636 | note | FREQUENCY: Prior to commencing works
98d90d5b-31d0-5ca7-97df-9503c264ea33 | note | ACCEPTANCE CRITERIA: Underground services shall be proved by clearly marking the location of the service on the ground and physical exposure of relevant services at appropriate locations, in accordance with service authority requirements.
2e70bd91-9a2e-5c0e-ab81-58448eead14a | note | REFERENCE DOCUMENTS: 160.12B
b736b6d2-f18f-5729-8197-574f622f8a98 | note | INSPECTION/TEST METHOD: Verify
980fa25b-edaf-5c3e-8be8-28051693b809 | note | RECORD OF CONFORMITY: This ITP signed off
ec39c5ff-3a20-5f5d-9626-14771c428e7d | note | HP
8ae9bec3-3725-5fbc-a13c-3533dd39026b | note | RESPONSIBILITY: Fulton Hogan Engineer/QAV
98f804af-9068-5aed-bb08-7de89ef83f6b | date | Date Completed:
368b19a6-c847-4fed-aaf5-5c683d124078 | signoff | AUTHORITY HOLDPOINT
98364c4f-845e-4c6e-88ab-5de31cb3f3ce | checkpoint | 1.5 - Excavations within 3m of poles or stays, Exacavtions within 1m of Underground Assets
f2c1a4cc-888b-58a8-ac82-d44526c9d10c | note | FREQUENCY: Prior to commencing works
97cdd966-bd88-559a-a414-412e93e3d8b0 | note | ACCEPTANCE CRITERIA: Advice must be sought for any excavations within 3m of poles or stays, or 1m of Underground assets
109fb950-4338-52c8-949c-94647d36284d | note | REFERENCE DOCUMENTS: 160.12A
1edf7c48-1c8c-56ca-9909-d23760273f73 | note | INSPECTION/TEST METHOD: Verify
7daf5271-e4aa-5067-b66f-23613dba0412 | note | RECORD OF CONFORMITY: This ITP signed
c20ad7a0-708b-51af-8302-b2c9cc5f095d | note | WP
c7a3366c-e2df-55d6-854a-0afc0ef03a70 | note | RESPONSIBILITY: Fulton Hogan Engineer/ TasNetworks
65c17231-a658-5515-9d24-5275ad60c2f6 | date | Date Completed:
3bee79c7-32ea-427e-b0b8-970c33db4411 | section | 2 - Construction Works
33e8a60c-420a-4465-b7b8-d02dd7bf7507 | checkpoint | 2.1 - Survey set-out
56a267a6-83f5-5bad-9db3-7e32686fd6cf | note | FREQUENCY: As required
8b900195-1112-58ff-8839-c3f1dd7dff7d | note | ACCEPTANCE CRITERIA: Prior to setting out trench, advice should be sought from TasNetworks for accuracy of cable routes. Cable routes shown on drawing are only approximate.
3810cb95-de5e-50d9-a745-24a9be68b0c2 | note | REFERENCE DOCUMENTS: AS-32433
261064b6-74ba-5c31-8a0b-95f08075c186 | note | INSPECTION/TEST METHOD: Verify
d644a3e4-36d6-563e-9b60-2fd9cfd860e0 | note | RECORD OF CONFORMITY: This ITP signed
db98ed0d-5714-5127-a686-0dcd702034b4 | note | IP
b4bd8982-7f25-573c-ae9a-88168a9086a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
bd7a19ed-1b83-5944-98de-1f708704e8cb | date | Date Completed:
a4dc456e-3c6f-4b8c-893f-c8f6eca26baa | checkpoint | 2.2 - Excavation
d3e5fbfc-266a-5d92-89f8-2649c7e4927e | note | FREQUENCY: Each Lot
cdfa50dc-67d3-521b-bd85-82d32d19533a | note | ACCEPTANCE CRITERIA: Check drg AS-32433 to confirm trench detail
fd516152-2ee8-5b3a-88b9-06afe1f92a1c | note | ○ The edges of all trenches located within a road pavement shall be sawcut
2bd45980-f634-51a3-a4e9-80d9660741ad | note | ○ Trench to be excavated to the nominal trench depth shown on drg AS-32433
65b43533-9ea4-5b5e-a6ce-fa055d408d18 | note | ○ If trench depth is greater than 1.5m; bench, batter or shore
1a3a9728-32a0-524e-b631-727a9009872e | note | REFERENCE DOCUMENTS: AS-32433
1a8f2bd6-f159-5294-9a81-a4163b0371bf | note | INSPECTION/TEST METHOD: Verify
3a7b1ad6-b43a-5a3e-8d6a-09242098ffcb | note | RECORD OF CONFORMITY: This ITP signed
473b576a-107f-5248-9177-9431e3d0fd85 | note | IP
ea2921e4-6f3c-5b21-be8a-59a82d901ba2 | note | RESPONSIBILITY: Fulton Hogan Engineer
8fbdb4a7-b7c1-5af4-87eb-2cafe8c2205d | date | Date Completed:
caa4fd3d-449c-4888-a301-cbdacdd98381 | checkpoint | 2.3 - Material Assessment
6ac9d39a-2be4-5a9c-9f5d-7ed0e95e0ecc | note | FREQUENCY: Each Lot
db62f081-a394-5732-b01e-f4701e709721 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
63a264bc-1642-52cc-bef4-5b5ec37616fa | note | REFERENCE DOCUMENTS: 204.06
20e6c71b-6b2d-5334-9ed5-e0ae0177e59b | note | INSPECTION/TEST METHOD: Verify
aafef60e-d3f7-5453-865a-feaafdd6ba1d | note | RECORD OF CONFORMITY: This ITP signed
a8d727c1-cd23-5b31-97e7-8137d4de0cbf | note | HP
472fe792-0dac-5cda-bd00-46be07045025 | note | RESPONSIBILITY: Fulton Hogan Engineer/Superindentant
a45758cc-342e-5762-bb8c-8474388646c2 | date | Date Completed:
a1117ce2-70f4-42c3-910b-fb486ee46144 | signoff | AUTHORITY HOLDPOINT
82a33b10-d3c9-4af5-b2c8-ea01862c9564 | checkpoint | 2.4 - Bedding
236844bb-4b7e-5f5d-a9ca-708b57e907f3 | note | FREQUENCY: Each Lot
1b670bc5-1c1a-5d2c-b3dc-5a591730b864 | note | ACCEPTANCE CRITERIA: TasNetworks to place sand bedding
d707f8c3-ebd2-5aaa-b883-deef10be29ad | note | REFERENCE DOCUMENTS: 160.12A
90ed6bc7-995f-5541-b5c1-d0cf8f9d9e09 | note | INSPECTION/TEST METHOD: Verify
be997fb6-152a-52c9-a8de-afcf03f08e2c | note | RECORD OF CONFORMITY: This ITP signed
8e1979ea-1c6d-556e-b1ed-12859198b5dc | note | IP
e509421f-ea61-5e83-8d33-c8968b1815ed | note | RESPONSIBILITY: Fulton Hogan Engineer
021fd59a-8917-5dda-b014-357d26d6499c | date | Date Completed:
671918a0-6483-41b6-9d49-eea9d1a8883e | checkpoint | 2.5 - Installation of Conduits and Cables
26d489af-66af-5947-915b-8a2c7382864f | note | FREQUENCY: Each Lot
fec3b8bc-acdd-5cff-94f6-16efc078ad22 | note | ACCEPTANCE CRITERIA: Conduits and cables to be installed by TasNetworks.
f5dd55ac-45f3-58b6-a91c-fc7765131d33 | note | ○ Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by superintendent or representative.
57e648f4-247b-579d-b7e4-cd1cebf06bbe | note | REFERENCE DOCUMENTS: 160.12A, 733.06
dce75d9f-3b55-52a1-a517-52a7162261c1 | note | INSPECTION/TEST METHOD: Verify
d40dab27-dbef-5405-b9e2-f0547e9bc728 | note | RECORD OF CONFORMITY: This ITP signed WP
61e10f7d-7a1b-582e-b4c2-66e0cc0423c9 | note | HP
5b431d3d-7c77-548b-b029-9c9879c537d8 | note | RESPONSIBILITY: Fulton Hogan Engineer
ce7e57bd-c1d8-56cf-9881-2fd5072e87c4 | date | Date Completed:
9baf5c5b-4bb5-4a66-a719-8650db4cb44a | signoff | AUTHORITY HOLDPOINT
171c3922-604a-4511-b9ec-abca4e6bdb79 | checkpoint | 2.6 - Back Fill of Trenches
3d628aff-d635-5cc6-b66a-32ad554fcd6a | note | FREQUENCY: Each Lot
5a94b26d-4b80-54bb-94b9-73d33e30d1d2 | note | ACCEPTANCE CRITERIA: Conduits to be backfilled with approved FCR or site won backfill material under the approval of TasNetworks
6f8c3d2d-2caa-5126-bad9-b9cb12d54741 | note | ○ Conduits may be backfilled with stab sand under the approval of TasNetworks
989494cb-8c23-5f50-bbd5-4e4c92e31e9d | note | REFERENCE DOCUMENTS: 733.06, AS-32433
9d79c7a6-b01d-5685-8a02-cbb2c2fb073f | note | INSPECTION/TEST METHOD: Verify
f552f145-e6dd-5018-8594-470aa916defe | note | RECORD OF CONFORMITY: This ITP signed
f52cefd0-8260-563f-8855-2cfca0c58a3c | note | IP
9a0a453c-3a37-5acf-9d09-213b819e9e4f | note | RESPONSIBILITY: Fulton Hogan Engineer
cf27b670-0bf1-5add-9d01-cbec39f360f1 | date | Date Completed:
b0ad1601-b4c2-47fa-b3b9-07de07483016 | checkpoint | 2.7 - Compaction
fa7ac0cb-9a90-5233-b51c-efa578411b8d | note | FREQUENCY: Each Lot
5e8768bc-b7fc-51ce-a642-9e8e20da1557 | note | ACCEPTANCE CRITERIA: Bedding, and backfill shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Standard compaction test.
5ad669e4-3ef4-58a2-881c-92c21e1a15b7 | note | ○ All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
1cb0bbaf-9e51-5c57-b034-161980161d6b | note | ○ Backfilling beneath areas to be paved shall be assessed for compaction:
50f91a05-943c-533d-9146-bc4895658dcb | note | – The number of tests per lot shall be three
61bee9e7-50e8-5ed2-9aac-7b2f8b1261cd | note | – Compacted to a mean value of density ratio of not less than 95% (passing 37.5mm AS sieve)
abf08659-068e-56ab-9208-6b592e84f245 | note | ○ Backfilling of pavement materials shall be assessed for compaction:
3600eaa0-cecd-553c-a2a8-02946b7b1950 | note | – Compacted to a mean value of density ratio of not less than 98%
9d3ee4a7-83c5-544e-99ed-eb833cdc51b0 | note | REFERENCE DOCUMENTS: 733.06 (D)
5cdab68f-cd28-506d-a896-faeadd4a2c15 | note | INSPECTION/TEST METHOD: Verify
2f62bc96-a90f-5952-8ad6-9ece8175a8a5 | note | RECORD OF CONFORMITY: Test Reports
90f3d0ba-1658-52c7-b590-b22f6639605d | note | TP
e34e080a-0744-5721-9927-488a0266d0ca | note | RESPONSIBILITY: Fulton Hogan Engineer
7aa64389-7af8-50e9-958e-3069682e8a9e | date | Date Completed:
a605a1f4-0cb3-435b-8348-1dfe8cf8f215 | checkpoint | 2.8 - Installation of marker tape
ef455e35-ac7b-536e-bb3b-fe6d4591fc85 | note | FREQUENCY: Each Lot
3332028d-dd69-5f41-95cf-5ae467426449 | note | ACCEPTANCE CRITERIA: Marker tape to be installed by TasNetworks
399e8d32-7791-5a24-b8af-796f5ab86bad | note | REFERENCE DOCUMENTS: 160.12A
a9d13828-7e44-5322-ac8c-e17000921279 | note | INSPECTION/TEST METHOD: Verify
4ae89711-3816-5ed6-bce9-ef8ff6dd1890 | note | RECORD OF CONFORMITY: This ITP signed
5875a302-3bf1-5f72-97d0-37845f1135ed | note | IP
8b1bce2d-bdc5-507d-9bb0-24ec2df5a85a | note | RESPONSIBILITY: Fulton Hogan Engineer
8a1f8861-4255-5ae7-b08f-35f163dcfa20 | date | Date Completed:
bf395b5d-3961-4cf0-94f2-244e18aa0632 | checkpoint | 2.9 - Cable Pits & Pit Lids
fa8d89b4-7e89-5075-8fea-0cfae1fc0a78 | note | FREQUENCY: Each Lot
c87361e6-e170-5fab-aa38-cb26f2864f58 | note | ACCEPTANCE CRITERIA: Cable pits and lids to be installed by TasNetworks
d4d3a8d4-2ad8-5a51-8e11-f6cd5428b8ff | note | REFERENCE DOCUMENTS: 160.12A
8649850f-7e06-5581-8372-78e75c34f9cc | note | INSPECTION/TEST METHOD: Verify
2734d5cf-0230-5e62-8a69-10dda69602c6 | note | RECORD OF CONFORMITY: This ITP signed
99e1fb6c-df4d-54ad-937b-7222a9b697a7 | note | IP
0df0a70e-c223-533a-9727-ec60a9dac1db | note | RESPONSIBILITY: Fulton Hogan Engineer
9a6da8ca-983b-5f33-9f20-f9ba754e5973 | date | Date Completed:
47bf6d72-5df1-40bd-bbe3-819c549ffccd | section | 3 - Completion
28e46eb7-d3b7-41c4-ad8d-35de5463f74b | checkpoint | 3.1 - Cleaning of Site
7a9dec18-113a-5d76-903f-65ecf31534cc | note | FREQUENCY: Each Lot
98dce7e7-c10a-58c0-8bb5-a8ce4c440b03 | note | ACCEPTANCE CRITERIA: Surplus excavated material shall be removed from road reserve. All affected areas shall be restored to similar conditions that existed prior to work.
264e7725-f6a4-5bc6-9413-154e74c53b56 | note | REFERENCE DOCUMENTS: 733.09
3c0093a9-d20c-5f38-9b8e-84bedd4b5a98 | note | INSPECTION/TEST METHOD: Visual inspection
5c945f7b-be30-5d99-9a02-246ad7674c70 | note | RECORD OF CONFORMITY: This ITP signed
ed5ac589-b828-5d4f-8256-2d8357c12624 | note | IP
dc6041bf-23ed-562c-be64-8baf0aab6e0e | note | RESPONSIBILITY: Fulton Hogan Engineer
d7d4cec8-65e9-5bb7-aab1-60f1c943dde6 | date | Date Completed:
2136825f-22c8-43e4-af91-381847c6a986 | checkpoint | 3.2 - Recording/As Built
ab719fe3-bf72-5312-8285-2762ec4d5083 | note | FREQUENCY: Each Lot
77c8246a-881e-57ab-b65c-e4bf1530de4b | note | ACCEPTANCE CRITERIA: Record any changes to cable routes on red line mark-ups
4a9b190f-2db0-5be6-b327-8b675d1d7c55 | note | REFERENCE DOCUMENTS: 160.12A
c53db618-0320-5a4a-af8c-f00dfdec5e95 | note | INSPECTION/TEST METHOD: Verify
50227621-c6c8-5c3a-ae45-061d51a6790c | note | RECORD OF CONFORMITY: This ITP signed, As Built Drawing
8a7772b0-df17-54c5-9793-b2305bdf5fe4 | note | *HP
e1276f20-b32c-5afc-8626-8603512ec923 | note | RESPONSIBILITY: Fulton Hogan Engineer
e3635b30-053a-514e-a0be-03081782dadc | date | Date Completed:
405c33de-087e-4ad3-bdf8-9c0f8b3b4512 | checkpoint | Final Inspection
765caa9d-6107-5579-b9fb-9bd546c78009 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fe9a5ce3-65d0-5351-9d3e-339534a622c4 | textbox | Print Name:
9887c2af-41e9-5c86-a47c-80c57fffe257 | textbox | Position:
0378c736-65c6-58b4-bd2b-12221383be64 | date | Work Completed On:
d94314d0-43a4-4c64-b6e6-6b92b66bd72c | signoff | Add Signature
86c7edee-b38e-4391-b135-bbba6c1d17e9 | checklist | DTM-ITP-006- Unbound Flexible Pavement Construction Rev0 | itp | DTM-ITP-006- Unbound Flexible Pavement Construction
1a8775ca-8808-4828-be75-2ee2b40877ad | section | 1 - Preliminary Works
5eddf287-a6f1-4e48-abac-dad025f95fbd | checkpoint | 1.1 - Check for correct documentation
e05b1258-b4c6-54ec-a92f-959fc204c337 | note | Frequency - Prior to commencing any activity
a0756a10-4aa1-5475-a467-03928b5cef17 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
2ac1746c-a1ab-5955-a62d-9e69207e7b0a | note | – using the correct and complete set of drawings
73568102-2ed7-5fb3-b92c-f5964bed16af | note | – all drawings are the latest revision
34696bd9-bf22-5ef8-885b-1e66054b2e9a | note | Reference Documents - IFC Drawings
b9ea98d3-758f-56c4-aed2-4cb2c33082de | note | Inspection/Test Method - Visual inspection
fa53e52c-57b5-51df-9e5e-4fe215d03c18 | note | Record of conformity - This ITP signed
5a5efa5c-a2dc-56ae-a7d6-b9c607924274 | note | HP*
0ad274df-2c8b-5d9a-84ee-c8403439b2a1 | note | Responsibility - Site Engineer
9145bf74-02d9-54d4-8292-89ab14a5dc9f | date | Date Completed:
e3d763b4-d05b-4437-b648-a8952cd9ec03 | checkpoint | 1.2 - Material Mix Design
efce4ed2-f7d0-52db-95de-4fe0e0fa5487 | note | Frequency - Prior to commencing works
66205b41-111a-5751-b121-5500c25fe130 | note | Acceptance Criteria - Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175.
3f325e40-6cce-5bfd-9729-cdb6fe74cbde | note | Reference Documents - 812.04, VicRoads RC500.02
87fdf747-4978-5281-b676-f39ad1b198f2 | note | Inspection/Test Method - Document Review
db1b15b3-cdd3-56df-981a-890f8c7eb3ef | note | Record of conformity - Crushed Rock Registration, This ITP signed
2367df4c-24b9-5f02-a72a-28c7aef4852a | note | HP
cc66152d-9eb9-50e1-a3ed-5f1f02f4290d | note | Responsibility - Site Engineer / QAV
3510e962-d684-530b-8eae-d48d1936fb71 | date | Date Completed:
f54053d9-69ff-4bdb-be08-e864b9434296 | signoff | AUTHORITY HOLDPOINT
7bb1899d-ef75-43c6-a077-08316a5628bc | checkpoint | 1.3 - Material Quality
3dedca60-ea26-5995-8b06-f7eaa549da80 | note | Frequency - Prior to commencing works
445e555d-e4d0-5439-a734-4e3803f790bd | note | Acceptance Criteria - Material complies with the Class 4 specification for crushed rock
e1effdb3-545c-5927-93fc-b7a2fbe7cc09 | note | Reference Documents - 812, Table 812.121
1060e3f6-cc1d-5052-8114-88cef4ef8e05 | note | Inspection/Test Method - Measure
10395d39-0e6d-5f2f-96ae-ab051e277063 | note | Record of conformity - Test Results
08ebec4d-3c23-595e-a057-f1fea8f07a09 | note | IP
7c7857cd-aa37-58bc-9aae-105293ce53b3 | note | Responsibility - Site Engineer
7bf14732-7239-593d-8158-cfbd8f78b720 | date | Date Completed:
71ca29a6-b1d3-4b76-96fa-2b069695d14a | section | 2 - Placement
a8574eba-4b79-408f-80ec-d218634417a8 | checkpoint | 2.1 - Layer Thickness
01aa338c-6f4c-5883-bf53-60c31453ce81 | note | Frequency - Each layer
b9be0ccc-cd61-5695-b974-9b052f97db5c | note | Acceptance Criteria - In addition to complying with pavement layer surface tolerances specified in Clause 304.06(b), the following tolerances shall apply to the thickness of any pavement layer:
96f633b2-02d4-5565-8694-df1c2076620c | note | (i) the subbase course shall be not less than the specified thickness by more than 15 mm;
4afb7f21-810c-5c38-b010-c01a1717e69a | note | (ii) the base course shall be not less than the specified thickness by more than 10 mm and the average thickness of base over every 100 m section, over the full carriageway width, shall be not less than the specified thickness;
3731f1e3-52ad-5b9d-81c9-35477fbfb62a | note | (iii) the combined thickness of subbase and base courses shall be not less than the specified thickness by more than 15 mm.
718ea684-c783-593c-9bdc-55edf1e0705a | note | Reference Documents - Drawings and 304.06(c)
3d28ebb9-d6a4-567c-8c40-353b74407110 | note | Inspection/Test Method - Visual and Measure
af432db7-84ad-5584-afda-fe469c64dbd8 | note | Record of conformity - This ITP signed
2d737984-8822-5e49-bceb-4a921cedb5fa | note | IP
8efe5d45-7fce-55d3-8379-fd1ced244ba9 | note | Responsibility - Site Engineer
443f77d9-f154-5c6e-aa50-42f7e14f0d85 | date | Date Completed:
62cf241d-6e12-464f-b479-2e259baba906 | checkpoint | 2.2 - Jointing
1febb21e-ab73-5d4b-99de-4e5e947ed256 | note | Frequency - Each lot
80d1b681-0354-507b-934a-f00d2ea84d37 | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
c512cd25-58da-5d43-962a-2d1c865e9c55 | note | (a) material shall be spread in such a manner as to minimize the number of joints;
9a94eac2-c6ad-5759-ae24-4069fe963a81 | note | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
63921b0e-d161-50be-8422-f3118dff2a40 | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
81a1dbbc-58d6-57cf-ae19-557e05516638 | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
77a0305c-a928-5ffe-817d-56611733b9a5 | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
2968fb0f-887c-57f4-8c7a-6282657de1fa | note | Reference Documents - 304.07
ccd9c6a2-3c9e-553f-94bb-a863e3099ec3 | note | Inspection/Test Method - Visual Inspection
6fc41273-9e14-51ad-97af-4e60cbbcb55c | note | Record of conformity - This ITP signed
2ef0ba38-335f-57ee-b854-6298b3141c87 | note | IP
7dc5dec1-74f3-5df8-9dbc-adaadb6aa6e8 | note | Responsibility - Site Engineer
9eeefbfb-3ee5-5f12-b4d4-448167661dfb | date | Date Completed:
0df55d27-e8a1-4c0a-a3bc-6a8969eedcc9 | checkpoint | 2.3 - Test Rolling
2f71ffd5-7bf9-51e2-8afc-14b7f476ea22 | note | Frequency - Each lot
18ca211a-b7e4-5ae8-8c79-840b0b5db85d | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173, prior to acceptance of the layer.The Contractor shall provide for the Superintendent to be present during all test rolling.
09ea5a48-5a25-5199-a05a-985fb2944899 | note | Reference Documents - 304.08
8cabdd34-716b-5371-835d-06fd43f6f254 | note | Inspection/Test Method - Test Roll
fe1290bd-5dbd-5bc9-af6d-3c519a8bc20a | note | Record of conformity - Witness Point
fb993113-0f33-51c5-9691-31242a05f680 | note | HP
84a099d2-9477-5585-9778-37cf4f6dfd40 | note | Responsibility - Site Engineer / QAV
4ae2c90c-f022-56b2-9344-ad6d64fcc93a | date | Date Completed:
049e51fd-ce8d-41f9-b9b2-7b6750f138bd | signoff | AUTHORITY HOLDPOINT
1efc5127-2654-4b11-bc08-9f7da2354171 | section | 3 - Testing and Conformance
98dde69d-9e6a-4a4c-a0c0-d9b6155ded2d | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
351f6066-fce6-5750-b37c-dd65d1cb8993 | note | Frequency - Prior to Testing
90f8f1a0-4bac-58df-86cc-ebd5f1c74394 | note | Acceptance Criteria - Scale B - The first lot of each material type shall be tested to demonstrate compliance with the material property requirements specified in Clause 204.04. Where the first lot of each material type satisfies the material property requirements in, no further testing will be required unless changes are observed or where directed by the Superintendent.
a9c48088-e400-5a16-bf5d-8f248fe6a238 | note | Reference Documents - 204.161
056c3e23-ec99-5b12-a2d5-8dacc1833f35 | note | ○ 304.08 (a)
f4870894-c595-5676-89c1-3655dcb6d411 | note | ○ 304.11 (b)
1499bbc4-97d8-5445-b40f-dc63e62c8c3c | note | ○ 304.11 (c)(iii)
6bea931e-dc01-5ca3-ada1-c4bb28aa466e | note | ○ Table 304.111
1a4801c9-34db-5be8-9348-8fea4a05c46e | note | ○ Table 304.121
5e276bec-eb13-548c-8c42-393c0d553f7e | note | Inspection/Test Method - Document Review/ Site Inspection
73c78cc6-768c-545a-9ada-7898de088814 | note | Record of conformity - Signed ITP
dd044276-bd46-5e64-962e-b0711eb1955a | note | AP
414f04fb-dca9-5aff-9256-00bbdc1abaea | note | Responsibility - Site Engineer
197ba428-6e86-5104-8ea1-ffe601920e8d | date | Date Completed:
d41c5992-c0db-4ecb-8171-975cab200ba7 | checkpoint | 3.2 - Compaction Testing
a472dce2-9ff2-5994-932e-362682476d9a | note | Frequency - Every Lot, Every second lot (reduced frequency)
bb0d979a-b833-5736-9686-a1e6fa708150 | note | Acceptance Criteria - Minimum Characteristic Density Ratio (CDR) of not less than 97% (subbase) for Scale B, using Modified compaction effort. Material during compaction shall have a moisture content of not less than 85% of optimum.
e0505b7c-c60f-54a8-960b-01b8591bc482 | note | Reference Documents - 304.081, 304.11 (b), Table 304.111
d26f15f8-7c89-59b5-98c3-8bab5b325761 | note | Inspection/Test Method - Test point
3e45ed57-aae7-567c-b1b6-fec8751a6f2d | note | Record of conformity - This ITP signed off; Test reports
c008aed0-3675-51ef-ae40-e0afede0af49 | note | TP
b50aa93d-9ce8-529d-b693-bdd2285e2fe6 | note | Responsibility - Site Engineer
4501c3ee-d325-5362-ba4c-4b16adbc3d75 | date | Date Completed:
706b13e7-d288-40bf-b151-8a4655b98238 | checkpoint | 3.5 - Completed Surface Level Compliance
ff2c3ae3-d37a-5419-bbbf-b7d9e2e63b1a | note | Frequency - Each lot
e75f8fd1-102a-5a01-be58-1ef58ec3d89e | note | Acceptance Criteria - Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
fbe73e80-9490-5885-87a9-ed82737f6d98 | note | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
ba3534f3-4f9f-559e-9177-c43499e4bc11 | note | ○ Surface level tolerances: As per table 304.062 below
8bfe2e7d-29cb-53e9-af9c-7daea85c14ae | note | – 40 measurements per lot (Scale B - Davey Street, Macquarie Street, Southern Outlet)
0e1f2ab3-3508-5de6-ae4e-3db3213e78ce | note | Reference Documents - 304.06, IFC Drawings Table 304.062
c12859b6-4009-5df4-a6ea-511f6a6d619f | note | Inspection/Test Method - Survey
a42b464b-e520-596e-b5ac-b88f63744b8c | note | Record of conformity - This ITP signed off; Survey Report
e447ac31-dce0-593e-8013-e7971a73ddb2 | note | TP
b798766c-d316-5000-92ab-3e699d2496e9 | note | Responsibility - Site Engineer
4c6ab624-8013-5ec4-9fd1-8db368c92a2e | date | Date Completed:
075f394c-80ce-4057-a11e-ef7e5dc8cf54 | checkpoint | 3.6 - Pavement Dryback and Embedment
d1c0858a-1de0-5165-9097-50d7128ee45f | note | Frequency - Prior to sealing works (only for uppermost layer below asphalt)
ce41f9eb-42b7-5f2a-ad75-d6c0ae059d08 | note | Acceptance Criteria - Scale A - The uppermost pavement layer after preparation of the surface and prior to sealing shall be allowed to dry back so the moisture content of the layer meets the requirements of Table 310.031 for each test lot. Also, pavement embedment shall be assessed by Ball Penetration testing when required as detailed in Table 310.031
9a02ee6a-2e52-590e-9887-d6a1df98ff69 | note | Reference Documents - 310.03, Table 310.031
507695b9-a376-56a0-bdc2-769c1fdac2ce | note | Inspection/Test Method - Review
280075d4-4c40-558c-9e3d-558fbb8ff1df | note | Record of conformity - Test Results
f870b41d-28c1-588a-9508-ffae6031b3b0 | note | TP
5b9531e0-7048-50dd-9331-94940801f093 | note | Responsibility - Site Engineer
d667f806-b586-545b-83e1-9ef7b9efce8d | date | Date Completed:
e82ffce7-6014-48f3-a443-0291bd6dd3c5 | checkpoint | Final Inspection
c0d66bd6-2c7f-5526-bc16-161f4f316dba | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4b4094f9-cca4-5ada-812b-56aaf4886a19 | textbox | Print Name:
3ce844e7-d77d-5973-86a8-df16e2cf17d6 | textbox | Position:
a2539846-c8ab-5499-b45b-9ecd077a6fdc | date | Work Completed On:
85fd8af8-39c4-474d-ae23-c75ec95c4642 | signoff | Add Signature
f803f3f1-a911-43a5-89c9-bbefbebc5f9b | checklist | DTM-ITP-008- Stormwater Drainage Rev0 | itp | DTM-ITP-008- Stormwater Drainage
47c5b580-7a4e-48d9-b3ef-4d10619b258c | section | 1 - Preliminary Works
69221198-7e3f-46f9-a9be-9188de2c9ed5 | checkpoint | 1.1 - Check for correct documentation
7f8c5b73-4308-5cd8-bc5b-73b4588f9f7c | note | FREQUENCY: Prior to commencing any activity
90bb94c7-bf6b-5639-b321-9f1088b365a6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
970ad1dd-b639-597f-bbb3-c745ca0e298b | note | – using the correct and complete set of drawings
3eddf108-b22d-5f89-9c5b-bea713c048de | note | – all drawings are the latest revision
b7485cf0-e6a8-555c-a583-57e284eb1632 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
7703a567-7dcb-57fc-bfeb-dc728f869312 | note | INSPECTION/TEST METHOD: Visual inspection
52f2d40f-a8fe-5d15-b93a-b216e99483ed | note | RECORD OF CONFORMITY: This ITP Signed
8a7b6241-935d-5d0c-8c9e-d345048df46c | note | HP*
bcaca3ca-39ce-5680-bffd-c0dffdda4474 | note | RESPONSIBILITY: Site Engineer
ffde6022-84c0-52f6-b81c-4edc7b5249c9 | date | Date Completed:
9adb4ca9-bbc6-430c-91f5-2427cb39ac9c | checkpoint | 1.2 - Implementation of all measures and controls
fd8428b9-955c-5e81-9020-689a9c056852 | note | FREQUENCY: Prior to commencing any activity
03eaf50e-b06c-5fa0-a6b9-a3dc541c085d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
83871e18-ce89-5518-931e-986e6bda8f5d | note | REFERENCE DOCUMENTS: OHSMP, EMP, TMS, SWMS, WP
a31955e5-6901-5849-8614-d403999882ec | note | INSPECTION/TEST METHOD: Visual Inspection
fb185b71-0c65-56ce-b781-7eac638f98ca | note | RECORD OF CONFORMITY: This ITP Signed
5f7e9290-3382-56e9-bd49-0c5adbe9d959 | note | HP*
24cd3256-330e-556d-80e3-c556ab569313 | note | RESPONSIBILITY: Site Engineer
26682638-8b5d-52a8-bda5-9294f7798d47 | date | Date Completed:
0f03afd7-cc9c-4e40-8eca-1fbb821b0968 | section | 2 - Procurement of Materials
c775c4f7-7724-4b6b-8b23-f17f1f3f7e8a | checkpoint | 2.1 - Precast Reinforced Concrete Pipe Supply
af0ff8aa-e416-5b94-bf99-e3126c79b8d6 | note | FREQUENCY: Prior to works commencing
9e7a95f8-b2b5-5310-82a1-c91d9b515551 | note | ACCEPTANCE CRITERIA: All portland cement-based precast reinforced concrete pipes shall be produced in accordance with AS4058. Rubber ring joints shall comply with the requirements of AS 1646.
8fa34ae5-880a-5929-8f5b-5022bed5db80 | note | ○ Pipes shall arrive onsite free from defect or deformity.
43ec0713-4283-5451-9dc2-b63df1f940c6 | note | REFERENCE DOCUMENTS: 701.05, AS4058, AS1646
a673eaa6-5179-5e69-943a-efc1e20ff3f2 | note | INSPECTION/TEST METHOD: Verify
8511953f-0394-5cec-94f2-141a4c9e6051 | note | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
2038ec1c-d0ae-5758-ac49-7f1b234c740a | note | HP*
49d93e04-e3a3-5f8c-b68d-ffd6ea8021b6 | note | RESPONSIBILITY: Site Engineer
074fcbfc-e5ad-59ce-b6d6-c5b5941766f2 | date | Date Completed:
c9738c4a-00d7-4aeb-99fc-735a61f66149 | checkpoint | 2.2 - Precast Reinforced Concrete Pit Supply and Inlet and Outlet Structure
14b81a5d-c36b-5801-8757-8c0e76365588 | note | FREQUENCY: Prior to works commencing
fdecb4a7-8fdf-56af-86af-a0dbc34206bb | note | ACCEPTANCE CRITERIA: The supply of precast pits and inlet and outlet structures shall conform with the requirements of the specification section 705.
86be4f79-79a8-51a9-aa6d-b6268bb7d6ad | note | ○ Concrete supply shall conform with Section 610 and reinforcement supply shall comply with Section 611.
0a9f5c02-5def-554a-a173-65c5e2ec2978 | note | REFERENCE DOCUMENTS: 610.474, 611, 705.07
06f53f6f-0f3a-52c8-af3c-050bd85c63d8 | note | INSPECTION/TEST METHOD: Verify
aa31c7b8-fe9c-5857-b528-0ef1ab032093 | note | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
a643ed25-40a9-5ec0-b570-aac10a2ed3c1 | note | HP*
a324bed4-ff90-5e96-a638-57869d77353c | note | RESPONSIBILITY: Site Engineer
fb7dc051-42af-5f01-8b3c-e9c88cd6537e | date | Date Completed:
d6e5b176-6853-41c1-a755-b2d8a8d99690 | checkpoint | 2.3 - Covers, Lintels and Grates
4a954307-51d5-5d5c-8553-34a8d5863694 | note | FREQUENCY: Prior to works commencing
c4a8bb64-fabe-5da5-b9d2-d7a5d7776644 | note | ACCEPTANCE CRITERIA: Covers, Lintels and Grates shall be as shown on DSG standard drawings
9a41e196-2e38-5b5b-aa20-63ac0b7a4088 | note | REFERENCE DOCUMENTS: DSG Standard Drawings 3402-9 P20 to P30
0ede429b-3a4a-5d5a-83b0-3f4307561f7a | note | INSPECTION/TEST METHOD: Verify
e552c5bb-cd29-585c-b1a6-e993a35dac0d | note | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
50421523-bdc4-5502-921a-9d0c94d64b6d | note | IP
22374310-e525-5bbd-9866-bdb5b06810c0 | note | RESPONSIBILITY: Site Engineer
2d89ae8d-319a-57ba-b444-9b8fab7f32c1 | date | Date Completed:
6184cbf2-9833-4353-bab0-dd995bbf2a4b | checkpoint | 2.4 - Provision for Stormwater Connections in Pits
ada54654-73cd-5c64-a047-7ac1cad3b71d | note | FREQUENCY: Prior to works commencing
091af229-5bcc-5399-ad39-66f34b3903c9 | note | ACCEPTANCE CRITERIA: Precast pits must allow 150mm diameter holes for subsurface drains and holes of sufficient diameter to allow for connections of stormwater culverts as shown on the drawings with the holes not greater than 50mm larger than required.
ef893a98-c6bb-50f9-9855-24ae92721801 | note | REFERENCE DOCUMENTS: 705.09, 705.11
fb43eae2-bc96-5ccf-8bf9-28a268d0d899 | note | INSPECTION/TEST METHOD: Verify
eebdead7-5540-5390-95c6-66585c0545ac | note | RECORD OF CONFORMITY: This ITP Signed
256d4ffa-aa52-5ef7-952b-34b170afc834 | note | IP
26355c8d-4aa9-5056-8dae-46bd2c463618 | note | RESPONSIBILITY: Site Engineer
e82ce2f4-4a8b-53d5-8ba2-e8d34cc46c76 | date | Date Completed:
8a73ae90-ef99-4de3-beb2-33865ffc05f3 | checkpoint | 2.5 - Bedding and Backfill Material Specification
0a799cb3-1c61-5c89-a8f4-714e66090b2d | note | FREQUENCY: Grading 1 test per 1,000t
106dd1dd-89fb-5224-b847-e174ce2e5d0a | note | ACCEPTANCE CRITERIA: Bedding and Backfill materials to conform to sieve requirements of Table 701.091 in the specification. Select Backfill shall also conform to the plasticity requirements of table 701.092
50bfc650-1e82-5cd7-ad59-8e4398f7f94d | note | REFERENCE DOCUMENTS: Table 701.091, Table 701.092
2db91944-f232-583a-86f8-890d1cc8a2f8 | note | INSPECTION/TEST METHOD: Verify
54de130b-109b-50b1-a7f6-bbf6fdbc004d | note | RECORD OF CONFORMITY: This ITP Signed, Quarry test report
02b655b4-1f27-5834-a335-697179b7c77f | note | HP*
3a53a52d-def8-51a8-9fad-117c5f89c9b3 | note | RESPONSIBILITY: Site Engineer
4a9ac342-d0eb-518d-9c08-c7005ceb5a26 | date | Date Completed:
1a3cf757-b83b-411a-877c-b2f19da8501f | checkpoint | 2.6 - Setout of Works
a44fb256-a0b3-59d4-855b-f3e08a9380f6 | note | FREQUENCY: Prior to works commencing
eaddbb64-ee0d-571c-9f37-92144cb04d7b | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
1e11bbff-1a0d-5794-b08a-b5a6ab55ca6c | note | ○ Works to be setout to true line and level by a surveyor.
cf2aafde-ecd9-5e69-849e-b6b0fa6eb766 | note | REFERENCE DOCUMENTS: 701.1
bb72067c-ae0a-5a98-aa30-d075602a0bb3 | note | INSPECTION/TEST METHOD: Verify
ff7a6d60-d0cd-5f11-b8b1-eecc8fc204e4 | note | RECORD OF CONFORMITY: Survey records, pegs on ground & this ITP Signed
6148a768-4c6c-5490-9b87-ea51f3281d8b | note | HP
b7f5d205-349d-5b8d-a213-766ac9f0cd2e | note | RESPONSIBILITY: Site Engineer / QAV
c201bbfd-58e2-50ab-a396-a83c24525ec7 | date | Date Completed:
21ecb27b-d76c-44bb-8019-06ed60d416e2 | signoff | AUTHORITY HOLDPOINT
b9810ba5-ebec-40eb-a6e2-9c975f987256 | section | 3 - Installation of Underground Stormwater Drainage
a2865515-d33c-4396-af23-f8de62bea131 | checkpoint | 3.1 - Excavation for pipe
8be10e95-2d62-5286-92f9-a7ebfe4000b3 | note | FREQUENCY: Each Lot
6474cacb-c3df-5d31-93b9-64f0752e09ea | note | ACCEPTANCE CRITERIA: Excavation for the installation of pipes shall allow for the clearance from the outside of the pipe to the wall of the trench between 300mm and 600mm
15a31952-c20b-5e98-8f1e-5d03fbcce713 | note | REFERENCE DOCUMENTS: 701.15, Table 701.151
33564a92-33b8-56a5-88be-a69465b7ebf9 | note | INSPECTION/TEST METHOD: Visual Inspection
4b3a83bb-b6a0-554f-8fd2-a915a87c03bc | note | RECORD OF CONFORMITY: This ITP Signed
0a0ef7db-d3e4-5e31-8db0-5476ef4cd994 | note | IP
908c10ac-03cf-5e06-a8b9-fd28234b7219 | note | RESPONSIBILITY: Site Engineer
b3c70046-71ea-52c2-b7fa-0173abec431d | date | Date Completed:
da0f5240-e8a9-4494-81bb-5bcd6f698d6c | checkpoint | 3.2 - Trench Base Preparation / Bedding
b2fbe3f6-ef19-51cd-a3d1-e8d88d51596d | note | FREQUENCY: Each Lot
435b4b49-f638-58b4-9773-18a0bc37ddc3 | note | ACCEPTANCE CRITERIA: Treat or replace all soft, wet or unstable material below the level required.The compacted thickness of bedding material following any shaping necessary shall be not less than 100mm where D < 1500 mm.
751c23fa-c7a0-5871-bc5b-b21a25a468f7 | note | REFERENCE DOCUMENTS: 701.16
420c61e6-6cd3-53b3-94b1-1ab94aa22b08 | note | INSPECTION/TEST METHOD: Verify
d8c2a80f-9cd6-5e70-a563-5b2cd2e686c5 | note | RECORD OF CONFORMITY: This ITP Signed
1e772ea2-b9e7-5b7f-a08b-0b507e346201 | note | IP
0a9c542f-e023-508d-b283-fa16dcf85b7c | note | RESPONSIBILITY: Site Engineer
6cf374ec-68cf-5992-aca5-9bba8a4b77a8 | date | Date Completed:
72673e06-f986-4cb1-ae36-cb213173d162 | checkpoint | 3.3 - Laying of pipes
ba37b5fb-34cf-5caf-8777-665069af8199 | note | FREQUENCY: Each Lot
56f67604-6d40-581e-b76e-294649af3a5f | note | ACCEPTANCE CRITERIA: Pipes to be laid with rebate or socket end facing upstream, design grade tolerance of +- 10mm in 10m and +-50mm invert level of pipes at pits.
de3d2366-4666-5adb-b0de-41b4d6a67f1b | note | ○ Multiple pipes to be laid with a horizontal spacing of 0.3m for pipes under 600mm diameter and D/2 for pipes with a diameter of 600mm or greater.
4619d772-a4f2-5a52-b811-291b321c84c5 | note | REFERENCE DOCUMENTS: 701.17, Table 701.171
8852aab1-777d-5077-b718-7f1e9b6468e5 | note | INSPECTION/TEST METHOD: Verify
cf545d41-85f0-5c08-81e1-58055438231b | note | RECORD OF CONFORMITY: This ITP Signed
df9da1e8-ed0c-5b00-bb7d-797acce57557 | note | IP
f4c8db40-ff95-522c-ba84-3abd0eb50fc4 | note | RESPONSIBILITY: Site Engineer
f1e3eb1e-6a75-56cb-9ce3-7f97980d173e | date | Date Completed:
eb647d35-6445-4fe9-83bb-c19f37ceced7 | checkpoint | 3.4 - Jointing
a19a1d11-0708-5594-9573-133d8832f861 | note | FREQUENCY: Each Lot
3935ee83-04bd-5a80-8602-b2b59a9c45d7 | note | ACCEPTANCE CRITERIA: Reinforced concrete pipes shall be wrapped with a 200mm wide external joint rubber band. Rubber rings shall be kept undisturbed, clean and free from dirt and other foreign materials.
c9bdd8b8-8807-5fce-9af9-5335a0c13d1e | note | ○ Rubbers are to be inspected afer each connection and in place before proceeding to next section.
45eaa7f3-0174-5cb6-b02c-4b2fa44df84e | note | REFERENCE DOCUMENTS: 701.18
482c517f-cb64-5f2b-b924-ed0eb9ab2279 | note | INSPECTION/TEST METHOD: Verify
274638cb-2a85-5789-aa14-c08de012f64b | note | RECORD OF CONFORMITY: This ITP Signed
f2c62e56-4e53-526f-a018-455f581cf478 | note | IP
d671ff03-b674-5991-8d99-40ac585ceffa | note | RESPONSIBILITY: Site Engineer / Foreman
5d0ccc66-059d-5e73-be89-23cc43f25f2b | date | Date Completed:
29754aa9-6958-43c6-94f4-715042f707df | checkpoint | 3.5 - Haunching
d113e8fe-36f8-574f-91dc-1b7f9cc78d89 | note | FREQUENCY: Each Lot
7be6323f-7880-5f08-beb4-e257f358d5e7 | note | ACCEPTANCE CRITERIA: Haunching layer to be reaching a height equal to 30% of nominal diameter. Layer thickness shown below:
a7b8949f-9863-5e4d-91af-20e0bf59feae | note | ○ DN600 Pipe Bedding above = 200MM
ba1bd5d6-bee1-5348-ae73-9f605bb66b02 | note | ○ DN525 Pipe Bedding above = 175MM
9fb40173-01cd-56af-9e04-a3319f33d7a9 | note | ○ DN450 Pipe Bedding above = 150MM
bbe6eff8-7841-5ab5-8426-6781096574c4 | note | ○ DN300 Pipe Bedding above = 100MM
81ae7421-b928-52ee-a635-5723a46a5675 | note | ○ DN225 Pipe Bedding above = 100MM
0b2fefb0-36aa-504e-9df3-dc67849e10ed | note | REFERENCE DOCUMENTS: 701.2
42abd899-b540-58bf-a6fb-b96e4c2be879 | note | INSPECTION/TEST METHOD: Verify
cef0c1cc-0472-5650-8d7d-20d286d1156a | note | RECORD OF CONFORMITY: This ITP Signed
5d5be12f-edcd-53db-acd2-406a5993d608 | note | IP
fc607c31-3a9b-5bc9-b7a6-c7a3e2102bd1 | note | RESPONSIBILITY: Site Engineer
d11846ce-a371-5e51-8348-4d1475c5eee5 | date | Date Completed:
2d1cb00a-21d8-4d1b-ab95-f68ba096969f | checkpoint | 3.6 - Pit Connections
b59814cf-8ea8-5f55-861e-f3deec66f92a | note | FREQUENCY: Each Lot
5bdfc2c0-3730-564e-8522-8cf983609ab3 | note | ACCEPTANCE CRITERIA: Weepholes or holes installed on site shall be cut and not broken out. Pits shall be replaced if cracking occurs as a result of installing holes or if the hole exceeds the pipe dia by more than 50mm.
c6a10f03-1cc1-5538-b620-f150bc2c8551 | note | REFERENCE DOCUMENTS: 705.11
ca63ba19-a8d5-553f-8a9c-f94d03db29f2 | note | INSPECTION/TEST METHOD: Verify
68f70bb2-22e1-59b5-9d17-8cc4d66c4f56 | note | RECORD OF CONFORMITY: This ITP Signed
03271ec8-812d-508b-93ab-0d33f4485e48 | note | IP
0879c71e-ad61-59aa-8b3e-656c6b000b7b | note | RESPONSIBILITY: Site Engineer
dd4fb099-6f6d-58e9-a62a-f9c2b0b44926 | date | Date Completed:
3749c2df-23ca-46c1-aced-1f047343536f | checkpoint | 3.7 - Culverts
7f2bd848-e881-5e9e-9d2b-4b775c10496d | note | FREQUENCY: Each Lot
9abdf869-6915-5e87-8f59-ea59c160c63a | note | ACCEPTANCE CRITERIA: Prior to commencement of any excavation for culverts the position shall be confirmed with the superintendant
c2ef615e-b172-5972-b0e0-d59e4ee06bf6 | note | REFERENCE DOCUMENTS: 701.1
b5a13ba0-8195-5331-a785-2f7ba1c2d20d | note | INSPECTION/TEST METHOD: Verify
644492a3-67b0-55e0-9dba-d2d5bb728155 | note | RECORD OF CONFORMITY: Hold point release
b1848968-0dd4-5dc3-8847-e800dcdb1377 | note | HP
5202f5cc-795d-5551-b074-7fc7d5619d0e | note | RESPONSIBILITY: QAV
fc5257b2-3549-5f53-bb77-72487221cde9 | date | Date Completed:
d66ead1d-85f8-4602-9470-6ab6ebfd0082 | signoff | AUTHORITY HOLDPOINT
0a177f69-5ec7-49c2-b321-863876633591 | checkpoint | 3.8 - Tolerance
6d0134d4-751b-5aaa-9423-28e0490862c5 | note | FREQUENCY: Each Lot
3e6386c2-3b12-5c38-9951-03b78d1fb694 | note | ACCEPTANCE CRITERIA: Location of each culvert run verified by survey prior to backfilling and recorded in as-constructed drawings.
90e6c306-5c72-5a23-9a94-0c0ca46436d6 | note | ○ Tolerance:
759a04cc-728b-5bd2-9fbd-83f895e88129 | note | – Offset of entry pits required to match lines of kerbs or barriers ± 20mm
cfe6b4c7-da2f-57f5-b952-2a0937daf5fb | note | – Plan location of pits other than offsets to kerb lines or barriers ± 100mm
2c4a40aa-91a5-53b7-bdb2-e1fb44f05242 | note | – Invert level of pipes at pits ± 50mm
d046ee14-1f73-5bf2-8caa-3e9b3ffd6bce | note | – Departure from design grade of pipe runs ± 10mm in 10m provided min grade > 1:250
c52ab5d0-f8b2-5c6e-a65c-809e7c913c93 | note | REFERENCE DOCUMENTS: 701.1
eff1b7ab-5f95-59c4-afb9-bf70d839e42f | note | INSPECTION/TEST METHOD: Verify
cdd5a0fd-1ec7-517d-84d7-3c2595881638 | note | RECORD OF CONFORMITY: This ITP Signed
1abd2408-a66c-585c-a748-b9acd278f78a | note | SCP
90ece154-79fa-5c2b-aac4-6f9cfbfc1e16 | note | RESPONSIBILITY: Surveyor, Site Engineer
6953a4a8-8e22-57bb-9942-e089e3f45f78 | date | Date Completed:
cef7209a-6873-42e7-9512-565120aa78a3 | section | 4 - Backfilling of Stormwater
7c4e3467-0cb8-48a4-bc43-f55fc7dad5c9 | checkpoint | 4.1 - Filling
8f14dab1-c501-518e-a4c4-61935f06ca84 | note | FREQUENCY: Each Lot
c8544a1f-9db7-51d5-ab39-6b160702f072 | note | ACCEPTANCE CRITERIA: (i) Culvert Under Area to be Paved
4e2e658b-e602-5847-ad7b-c8f18a184fb9 | note | – The trench shall be backfilled as per requirements from Table 701.091 and 701.092. Above subgrade level, materials as per pavement design.
b7004f59-6ed2-5f4b-91e3-3ec7b97b7884 | note | (ii) Culvert Under Area not to be Paved
56dbe809-4056-5152-be08-47687179343a | note | – The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
72662cbb-9c7c-5efb-9b64-00ae4cd0f45b | note | – Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
68f28d4c-bbe1-57a0-8e2d-023b963d3dfc | note | REFERENCE DOCUMENTS: 701.19, 705.18
d075f1fc-f8fc-5942-a63f-533f4417672e | note | INSPECTION/TEST METHOD: Verify
d16af8a0-4e3a-5b09-b21d-e88bc52e6c52 | note | RECORD OF CONFORMITY: This ITP Signed, Particle size distribution certificate of selected backfill material
efef20b9-795d-59ec-b833-aaf388619d10 | note | IP
0725f950-6c69-552c-a0d3-0157439862d2 | note | RESPONSIBILITY: Site Engineer
5e49515c-25a7-58c4-bce3-5c85baee7d66 | date | Date Completed:
bf7ee17b-70a1-4741-8809-9e3437b96227 | checkpoint | 4.2 - Testing and Acceptance of Fill Materials
b381542e-64de-59f6-a3b6-340e473159d4 | note | FREQUENCY: 3 Tests per Lot tested with 20% of all Lots for each culvert tested
9a669bf1-d9c9-5e43-a58f-328eab7f20cd | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150mm loose thickness and shall be assessed for compaction and moisture content.
cbeabd06-cf36-572c-919f-dfe71d2e49ec | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment.
ba9d91e2-0e9e-5828-9b4e-146011260805 | note | ○ Backfill material (nominal size < 40mm after compaction) shall be compacted to a mean density ratio of not less than 97% SDR.
c06c9f1b-6f86-5c6f-b526-c3bd3d7a6131 | note | ○ Backfill (nominal size > 40mm after compaction) material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
945ec37a-0f98-54a3-86a8-1ce5607b50ae | note | REFERENCE DOCUMENTS: 701.2
26269cd3-220e-5a8b-a9bd-054883be4565 | note | INSPECTION/TEST METHOD: Verify
7273558c-01cf-54ef-915c-5636e893d575 | note | RECORD OF CONFORMITY: Compaction Test Result
842c3bbe-6603-5c2d-bcd6-94b799449448 | note | TP
8dd6ff99-f357-5fbd-a4d8-8780cdca3442 | note | RESPONSIBILITY: Site Engineer
7c08ab6c-42a3-5286-8393-b1734d28ac78 | date | Date Completed:
7c02ade6-36d0-4085-8d76-c873935a2d83 | checkpoint | 4.3 - Installation of Inlet or Outlet Structure
db7e36ee-925f-5e50-8c53-56e2e1869f5c | note | FREQUENCY: Each Lot
20055737-212f-5232-8812-1febff77ee47 | note | ACCEPTANCE CRITERIA: Inlet and outlet structures shall be installed to a tolerance of +-20mm where matching kerbs or barriers or +-100mm in all other areas.
a6e9351b-58fb-5bf1-ad96-824ed1e493cb | note | REFERENCE DOCUMENTS: 701.10, 701.25
99a04fa7-0cb6-536f-b841-6e511fda03ac | note | INSPECTION/TEST METHOD: Verify
cdf3a147-6409-5648-8ced-1e42251c63e4 | note | RECORD OF CONFORMITY: This ITP Signed
48eff23c-45ee-5fe0-8320-e73eb292ecdb | note | IP
4667def4-a32d-5c7d-902f-6b1900c761fd | note | RESPONSIBILITY: Site Engineer
b0eb9528-2cbf-5f2c-ac53-b16799d62c3e | date | Date Completed:
05aee72a-a821-44bf-abba-17bfdbfeb2be | checkpoint | 4.4 - Culvert Coverage
098284d9-1a0d-537f-ae56-c012d389237f | note | FREQUENCY: Each Lot
40ad8794-e7f5-54b1-a3a6-0e40e5a1825e | note | ACCEPTANCE CRITERIA: Until the minimum compacted thickness of cover in Table 701.141 for each type of vehicle are met, construction shall not be allow to travel over the culvert
abc78094-292e-509f-b82e-43217ba78040 | note | REFERENCE DOCUMENTS: 701.14, Table 701.141
18151f62-e6e1-54e2-8b98-544507a8a5ec | note | INSPECTION/TEST METHOD: Visual inspection
0cd4dadd-c1f4-5422-9c00-51b2cfd898f7 | note | RECORD OF CONFORMITY: This ITP Signed
90fed762-3536-50d0-b620-2cccf468bdda | note | IP
f1a2fc7e-4adf-50a7-a1f0-7cdc3c97ec79 | note | RESPONSIBILITY: Site Engineer
4f98b1ce-9c11-532c-9110-d3889abf45dc | date | Date Completed:
7e33f3cb-2243-4733-a716-03f5f4fb6328 | section | 5 - Finishing and Commissioning
9b491a65-1e2f-436e-8b70-0cbb879331e1 | checkpoint | 5.1 - Finishing and Rendering Pipes
1315350b-d965-50af-a4ce-7f68882bdebf | note | FREQUENCY: Each Lot
666ae082-5f9e-57be-b4b2-d09838777781 | note | ACCEPTANCE CRITERIA: All stormwater connections and subsurface drain connections shall be cut trimmed neat and finished with cementitious mortar.
1f64556c-a8eb-5808-81d9-98224891e688 | note | REFERENCE DOCUMENTS: 705.11, 705.15
bb5ef8bf-c5b8-5610-a023-8fbbd1351801 | note | INSPECTION/TEST METHOD: Verify
72e43d61-aecc-5441-a868-88fcc87204f6 | note | RECORD OF CONFORMITY: This ITP Signed
f673d52e-efde-5125-b6f5-48b165563b06 | note | IP
1833ecbd-4f7d-51ab-aa80-297f2b84c11e | note | RESPONSIBILITY: Site Engineer
799b0844-9971-5f74-9c91-df210e46c9db | date | Date Completed:
294b43fd-2148-470c-b1d0-012c421dbde2 | checkpoint | 5.2 - Repair of Damaged Pipes
96d39035-a472-554f-bf53-145a73d3f5f2 | note | FREQUENCY: Each Lot
bda9de78-0bc6-5ed5-b7ce-93e234ba0af7 | note | ACCEPTANCE CRITERIA: Damaged pipes shall be repaired in accordance with 701.31 of the Specification, no repairs shall be undertaken without the Superintendent's approval. Repairs to be in accordance with relevant ITP.
55e75df9-c1ea-5457-bba2-18a31be59dac | note | REFERENCE DOCUMENTS: 701.31
69635456-3399-54f9-a68c-6cedc336aae0 | note | INSPECTION/TEST METHOD: Verify
fd0b6525-17f8-5237-8ffe-2090f59711aa | note | RECORD OF CONFORMITY: This ITP Signed
f52c5ba8-fa4e-5fc0-8947-da02acc54978 | note | HP
7b46850a-c9df-52ac-8732-88b15b2c4a49 | note | RESPONSIBILITY: Superintendent / Site Engineer/ QAV
e16ef4c5-7b4e-5bc9-ac6c-4ea661d4a5a0 | date | Date Completed:
2b4d847a-8c27-426e-8bb6-39eeb29226db | signoff | AUTHORITY HOLDPOINT
4aac5730-98b9-4edc-ae16-46ff82d97da9 | checkpoint | 5.3 - CCTV
cb15d638-611b-597a-8cbf-b2ecda7f4060 | note | FREQUENCY: Each Lot
6efabaf3-a43b-5164-946b-19249c624993 | note | ACCEPTANCE CRITERIA: All drainage lines constructed beneath pavements shall be inspected after earthworks to subgrade level are complete and prior to the construction of pavement layers by an indpendent organisation using CCTV in accordance with WSA 05-2013 - Conduit Inspection Reporting Code of Australia. Verify that the flow of water is not obstructed by waste construction material and check for visible signs of defects
0718b63e-c88a-57f9-8689-03a859401816 | note | REFERENCE DOCUMENTS: 701.30, WSA 05-2013
e7ae3593-0f25-53e4-8273-6d8fdb0ffbeb | note | INSPECTION/TEST METHOD: Verify
04160332-f3e8-5d6e-8fce-e6882bab7d6f | note | RECORD OF CONFORMITY: This ITP Signed
9a82d08c-d41d-5227-ab04-26bee047218a | note | HP
b726e68c-5341-5821-ad9e-1d224e44be98 | note | RESPONSIBILITY: Site Engineer / QAV
b0f5412c-6067-5747-b8d5-69f0e960d9ea | date | Date Completed:
a742b8fd-79c7-47f3-8531-705b4adc3df5 | signoff | AUTHORITY HOLDPOINT
49ab4c00-ccc9-4f41-bb81-6d2a92d8235b | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9237ffb6-5ac8-569f-93c4-5b4825262369 | textbox | QAV - Print Name:
77ae5fb2-be77-5372-8fb6-e3eb4aa7bd23 | textbox | QAV - Position:
afb867ec-45c1-59ce-a91e-598016d45f50 | textbox | Fulton Hogan - Print Name:
9bbe1327-5e26-547d-8b0a-6782bdbb6636 | textbox | Fulton Hogan - Position:
5237d247-5cc9-508e-a3dd-85ed9d8f4b58 | date | Work Completed On:
c101f08c-9db2-47ab-8923-83252faaee39 | signoff | Add Signature