## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DTM-ITP-010- Subsurface Drainage | itp |  |  |  |  | DTM-ITP-010- Subsurface Drainage Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP/WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TGS, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP/WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Material Classification
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000 and 400 corrugated perforated plastic pipe
label | ○ Granular filter material for bedding and backfill: Trench backfilled with B3 granular filter material complying with Cl 702.05
label | ○ No Fines Concrete: Shall consist of 4.0% Type GP cement
label | ○ Geotextiles: Robust geotextiles shall comply with Cl 702.12 and Table 702.061 and have a minimum robustness of 600-900.
label | ○ Subsurface drain pits: Stormwater drainage pits are to be used as access points. Invert levels in pits to comply with Cl 702.10
label | ○ Flushout risers: Shall have surface fittings as shown on the drawing
label | REFERENCE DOCUMENTS: 702.04
label | ○ 702.05
label | ○ 702.06
label | ○ 702.1
label | ○ 702.12
label | ○ 702.061
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Excavation of Trench
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Hold Point
label | ○ Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by QAV with at least 24 hours notice prior to placement of bedding.
label | REFERENCE DOCUMENTS: 702.08
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Placement of bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | REFERENCE DOCUMENTS: 702.09 (c)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Placing pipes and geofabric (if required)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
label | ○ If geofabric required (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
label | REFERENCE DOCUMENTS: 702.09(d)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.5 - Placement of granular backfill methodology
label | FREQUENCY: Prior to backfilling
label | ACCEPTANCE CRITERIA: Hold Point
label | ○ Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
label | ○ Where no fines concrete is used, the contractor shall submit quality procedures for review by the QAV which detail the method of placing. No fines concrete shall be placed and compacted within 1 hour of mixing.
label | REFERENCE DOCUMENTS: 702.09(g)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Placement of backfill
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
label | REFERENCE DOCUMENTS: 702.09 (g)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.7 - Install Pits and Flushouts
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
label | REFERENCE DOCUMENTS: 702.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.8 - Flushing Test
label | FREQUENCY: At completion of stage
label | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
label | REFERENCE DOCUMENTS: 702.09(h)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.9 - CCTV
label | FREQUENCY: At completion of stage
label | ACCEPTANCE CRITERIA: Hold Point
label | ○ All subsurface drainage lines constructed shall be inspection, after completion of the flushing test and prior to the placement of asphalt, by an independent testing organisation using CCTV, in accordance with WSA 05-2013.
label | REFERENCE DOCUMENTS: 702.09(i), WSA 05-2013
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ CCTV Reports
label | HP
label | RESPONSIBILITY: Site Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Marker Posts
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on the drawings.
label | REFERENCE DOCUMENTS: 702.11, DSG 3401-3/P17-4
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ As-Built records
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | QAV - Print Name:
textbox | QAV - Position:
textbox | Fulton Hogan - Print Name:
textbox | Fulton Hogan - Position:
date | Work Completed On:
signoff | Add Signature
checklist | DTM-ITP-011- Structural Concrete | itp |  |  |  |  | DTM-ITP-011- Structural Concrete Rev0
section | 1 - Pre-Construction
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, OHSMP, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | WP
label | RESPONSIBILITY: FH Engineer / Site Foreman
date | Date Completed:
section | 2 - Prequalification
checkpoint | 2.1 - Submission of Mix Design
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Hold Point
label | ○ Concrete mix design complies with requirements of Section 610 and appears on the Register of State Growth approved concrete mixes.
label | ○ Submit for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
label | REFERENCE DOCUMENTS: Specification Section 610.07
label | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | RECORD OF CONFORMITY: Superintendent HP Release on Procore
label | HP
label | RESPONSIBILITY: FH Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Reinforcement
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Steel reeinforcement complies with the requirements of Section 611.
label | REFERENCE DOCUMENTS: Specification Section 611
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed, Pre-pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer / QAV
date | Date Completed:
checkpoint | 2.3 - Reinforcement supply and certification
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Supplier must hold Australian Certification Authority for Reinforcing Steel (ACRS) certificate.
label | ○ Hold Point
label | ○ No Third Party Certification. Approval shall be obtained in writing from the Superintendent for the use of steel reinforcing materials that are not covered by the long-term quality level of AS/NZS 4671 at least 14 days prior to the intended first date of use of such steel.
label | REFERENCE DOCUMENTS: Specification Section 611.05
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: HPR release in Procore if required
label | HP
label | RESPONSIBILITY: FH Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing and Acceptance
checkpoint | 3.1 - Pre-mixed concrete
label | FREQUENCY: as per table 610.161
label | ACCEPTANCE CRITERIA: Concrete sampled at the worksite and complies to requirements of Section 610 including slump and temperature
label | REFERENCE DOCUMENTS: Specification Section 610
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
label | TP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.2 - Concrete Testing - Sampling Frequency
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | ○ 0m³ to 10m³ = 1 sample
label | ○ 10m³ to 25m³ = 2 samples
label | ○ 25m³ to 50m³ = 3 samples
label | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | For each additional 50m³ and additional sample shall be taken.
label | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | – Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads.
label | Record: Required information on the Concrete Pour Record.
label | REFERENCE DOCUMENTS: 610.16 (b), 610.16 (g), 610.16 (j)
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
label | TP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.3 - Concrete Testing - Core Sample Frequency (Post construction)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: If required by the Superintendent:
label | Hold Point: The coring procedure and core locations shall be submitted for approval by the Superintendent.
label | 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below:
label | ○ 0m³ to 25m³ = 1 sample
label | ○ 25m³ to 50m³ = 2 samples
label | – For each additional 50m³ an additional sample shall be taken.
label | – Each sample shall consist of 6 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum.
label | Core samples shall be tested for:
label | ○ 1 no. 3 day compressive strength
label | ○ 1 no. 7 day compressive strength
label | ○ 2 no. 28 day compressive strength
label | ○ 2 no. VPV tests
label | REFERENCE DOCUMENTS: 610.16 (b)
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
label | HP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Concrete Testing - Slump
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | ○ <60mm = ±10mm
label | ○ ≥60mm to ≤80mm = ±15mm
label | ○ >80mm to ≤110mm = ±20mm
label | ○ >110mm to ≤150mm = ±30mm
label | ○ >150mm = ±40mm
label | Record: Required information on the Concrete Pour Record.
label | REFERENCE DOCUMENTS: 610.16 (c)
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: This ITP signed
label | TP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.5 - Reinforcement
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Steel reinforcement placement, fixing and lapping complies with requirements of Drawings
label | REFERENCE DOCUMENTS: Structural Drawing Set
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Pre-pour inspection checklist, Subcontractor ITP
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.6 - Building Permit
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Building Surveyor has provided Start Work Notification (Form 39) and inspected element prior to concrete pour
label | REFERENCE DOCUMENTS: 160.08
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Start Work Notification (Form 39), Pre-pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 4 - Application
checkpoint | 4.1 - Pre-pour
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pre-pour inspection checklist completed and details recorded (Temperature, Evaporation limits and concreting operations).
label | REFERENCE DOCUMENTS: Specification Section 610, Figure 610.171
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Pre-pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.2 - Concrete Pumping
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Initial discharge of concrete pumped to waste until a consistent workable mix observed
label | REFERENCE DOCUMENTS: Specification Section 610.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Pre-pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.3 - Traceability
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete deliveries traceable from the batch plant to location in the structure including time from batching to spraying. Continuous concrete pours max lag between trucks = 25 minutes
label | REFERENCE DOCUMENTS: Specification Section 610.15
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Concrete traceability checklist, Pour Record
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.4 - Finishing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Not specified in project specification. A trowel finish will be applied. No decorative/anti-carbonation coating required as footing will not be exposed in anyway following construction
label | REFERENCE DOCUMENTS: Specification Section 610.31
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.5 - Curing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Curing in accordance with Specification Section 610. Freshly finished concrete protected where erequired from sun, wind or rain until curing implemented
label | REFERENCE DOCUMENTS: Specification Sections 610
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed / Post pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer/JSCB
date | Date Completed:
checkpoint | 4.6 - Joints
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All joints formed in accordance with Specification Section 610, Drawing requirements
label | REFERENCE DOCUMENTS: 610.20, Structural Drawing Set
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.7 - Dimensional Tolerances
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Maintain records of dimensional measurements to demonstrate that all completed concrete members comply with Spection Section 610.
label | ○ Ensure that the records are available for review by the Superintendent.
label | REFERENCE DOCUMENTS: 610.47
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, AS BUILT
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 5 - Finishing Activities
checkpoint | 5.1 - Final inspection
label | FREQUENCY: Each Lot after 28 days
label | ACCEPTANCE CRITERIA: Visual and soundness inspection conducted for analysis of compaction, dry patches, voids or sand pockets. Soundness inspection for drummy or hollow response.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed, post pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 5.2 - Repair of defective areas
label | FREQUENCY: Each occurrence
label | ACCEPTANCE CRITERIA: Areas of finished work that have been deemed non-conforming alerted to the QAV and rectification method approved
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, NCR report
label | HP*
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 5.3 - As Built Documentation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Survey pick-up to be progressively completed. As built drawings to be be progressively completed. Test data, ITPs, Concrete Dockets, Checklists to be compiled and lot to be closed out.
label | REFERENCE DOCUMENTS: FH Detailed Construction Methodology - Shotcrete Works
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 6 - Post Construction
checkpoint | 6.1 - Compressive Strength (& VPV Test Results if requested by Superintendent)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength comply with table 610.061.
label | ○ Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects.
label | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%.
label | Attach: Compressive Strength Test Results
label | Attach: Core Sample Compressive Strength Test Results
label | REFERENCE DOCUMENTS: Table 610.051, Table 610.061, 610.16 (g)
label | INSPECTION/TEST METHOD: Document Review, Each cylinder and core sample
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 6.2 - Surface Inspection
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Surface to be as per the required class of finish with no visible lack of compaction, dry patches, voids or sand pockets.
label | ○ Soundness inspection shall be conducted with a small hammer to locate ‘drummy’ or ‘hollow’ response areas which indicate a possible lack of bond, delamination or other defect.
label | ○ For core sample penetrations and if any visual defects are observed, follow Structural Concrete Cementitious Patch Repair ITP for investigation and repair.
label | ○ No cracks greater than 0.2mm (exposure classification B1)
label | ○ If cracking is observed, follow Structural Concrete Crack Repair ITP for investigation and repair.
label | REFERENCE DOCUMENTS: 610.31 (a) - (n), 610.32, 610.24
label | INSPECTION/TEST METHOD: Visual, Measure
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 6.3 - As-built Survey
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the Table 610.472 as applicable to the element.
label | ○ Where a shape is required, ±25mm with no depressions greater than 15mm.
label | Attach: Survey As-builts / Survey Report
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: As built
label | RECORD OF CONFORMITY: This ITP signed, HPR release in Procore
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | QAV - Print Name:
textbox | QAV - Position:
textbox | Fulton Hogan - Print Name:
textbox | Fulton Hogan - Position:
date | Work Completed On:
signoff | Add Signature
checklist | DTM-ITP-012- Masonry Block Wall | itp |  |  |  |  | DTM-ITP-012- Masonry Block Wall Rev0
section | 1 - Pre-Construction
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, OHSMP, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | WP
label | RESPONSIBILITY: FH Engineer / Site Foreman
date | Date Completed:
section | 2 - Prequalification
checkpoint | 2.1 - Reinforcement
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Steel reeinforcement complies with the requirements of Section 611 and the design drawings
label | REFERENCE DOCUMENTS: Specification Section 611
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed, Pre-pour (core-fill) inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer / QAV
date | Date Completed:
checkpoint | 2.2 - Reinforcement supply and certification
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Supplier must hold Australian Certification Authority for Reinforcing Steel (ACRS) certificate.
label | ○ Hold Point
label | ○ No Third Party Certification. Approval shall be obtained in writing from the Superintendent for the use of steel reinforcing materials that are not covered by the long-term quality level of AS/NZS 4671 at least 14 days prior to the intended first date of use of such steel.
label | REFERENCE DOCUMENTS: Specification Section 611.05
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: HPR release in Procore if required
label | HP
label | RESPONSIBILITY: FH Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Supply of masonry blocks
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Ensure blocks comply with sections 713 and 765 of the AS/NZS 4455.1:2008 and section 765 of AS3700:2018 standards and are of the same type/description as set out in IFC drawings: Adrbri Masonry Versawall (oatmeal) blocks.
label | REFERENCE DOCUMENTS: IFC drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: FH Engineer / QAV
date | Date Completed:
section | 3 - Testing and Acceptance
checkpoint | 3.1 - Pre-mixed concrete
label | FREQUENCY: As per M14 of A0171.005 sheet 0301 Rev 0
label | ACCEPTANCE CRITERIA: Ensure concrete strength is of the minimum specified f'c strength rating of 20MPa to AS3600. Ensure minimum cement content, max aggregate size and slump are as designated in note M14 are adhered to.
label | REFERENCE DOCUMENTS: As per M14 of A0171.005 sheet 0301 Rev 0
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Mix design, concrete docket, this ITP signed off
label | TP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.2 - Concrete Testing - Sampling Frequency
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | ○ 0m³ to 10m³ = 1 sample
label | ○ 10m³ to 25m³ = 2 samples
label | ○ 25m³ to 50m³ = 3 samples
label | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | For each additional 50m³ and additional sample shall be taken.
label | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | – Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads.
label | Record: Required information on the Concrete Pour Record.
label | REFERENCE DOCUMENTS: 610.16 (b), 610.16 (g), 610.16 (j)
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
label | TP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.3 - Concrete Testing - Core Sample Frequency (Post construction)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: If required by the Superintendent:
label | Hold Point: The coring procedure and core locations shall be submitted for approval by the Superintendent.
label | 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below:
label | ○ 0m³ to 25m³ = 1 sample
label | ○ 25m³ to 50m³ = 2 samples
label | – For each additional 50m³ an additional sample shall be taken.
label | – Each sample shall consist of 6 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum.
label | Core samples shall be tested for:
label | ○ 1 no. 3 day compressive strength
label | ○ 1 no. 7 day compressive strength
label | ○ 2 no. 28 day compressive strength
label | ○ 2 no. VPV tests
label | REFERENCE DOCUMENTS: 610.16 (b)
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
label | HP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Concrete Testing - Slump
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Slump testing tolerances = >80mm to ≤110mm = ±20mm
label | Record: Required information on the Concrete Pour Record.
label | REFERENCE DOCUMENTS: 610.16 (c)
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: This ITP signed
label | TP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.5 - Reinforcement
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Steel reinforcement placement, fixing and lapping complies with requirements of Drawings
label | REFERENCE DOCUMENTS: Structural Drawing Set
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Pre-pour inspection checklist, Subcontractor ITP
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.6 - Mortar
label | FREQUENCY: Prior to placement
label | ACCEPTANCE CRITERIA: Use class M3 Mortar: 1 part cement:5 parts sand and a methyl cellulose water thickener to AS3700. Use white cement to AS3972 type GP or GB.
label | REFERENCE DOCUMENTS: Structural Drawing Set
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.7 - Building Permit
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Building Surveyor has provided Start Work Notification (Form 39) and inspected element prior to concrete pour
label | REFERENCE DOCUMENTS: 160.08
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Start Work Notification (Form 39), Pre-pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 4 - Application
checkpoint | 4.1 - Pre-pour
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pre-pour inspection checklist completed and details recorded (Temperature, Evaporation limits and concreting operations).
label | REFERENCE DOCUMENTS: As per M20 of A0171.005 sheet 0301 Rev 0
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: this ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.2 - Concrete Pumping
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Initial discharge of concrete pumped to waste until a consistent workable mix observed.
label | REFERENCE DOCUMENTS: Specification Section 610.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Pre-pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.3 - construction of blockwork
label | FREQUENCY: 6 courses / 1500mm
label | ACCEPTANCE CRITERIA: Do not proceed with blockwork construction more than 6 courses or 1500mm ahead of concrete placement. Wet masonry blocks before placing concrete.
label | REFERENCE DOCUMENTS: As per M20 of A0171.005 sheet 0301 Rev 0
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: this ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.3 - Core-filling
label | FREQUENCY: 6 courses / 1500mm
label | ACCEPTANCE CRITERIA: Wet masonry blocks before placing concrete. Stop concrete 50 mm below top of blocks to provide key for following concrete. Ensure proper compaction of concrete by 'rodding' or other approved means
label | REFERENCE DOCUMENTS: As per M21 of A0171.005 sheet 0301 Rev 0
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: this ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.4 - Traceability
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete deliveries traceable from the batch plant to location in the structure including time from batching to spraying. Continuous concrete pours max lag between trucks = 25 minutes
label | REFERENCE DOCUMENTS: Specification Section 610.15
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Concrete traceability checklist, Pour Record
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.5 - Curing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Curing in accordance with Specification Section 610. Freshly finished concrete protected where erequired from sun, wind or rain until curing implemented
label | REFERENCE DOCUMENTS: Specification Sections 610
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed / Post pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer/JSCB
date | Date Completed:
checkpoint | 4.6 - Joints
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All control joints as per control joint detail on A0171.005 sheet 0321 using R12-400 Galv. Dowels 450 long (greased and wrapped one end) and flexible joint filler and 10x10 approved joint sealant each face.
label | REFERENCE DOCUMENTS: structural drawing set
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.7 - Cleaning
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: clean masonry progressively. Clean face work to remove mortar smears, stains, discolouration etc. Use cavity batten (lift progressively) to keep cavities clear of mortar fins, droppings etc.)
label | ○ Remove mortar droppings from bottom of cores by use of cleanout blocks before placing concrete and at horizontal breaks in construction. Remove mortar fins protruding from joints before placing concrete.
label | REFERENCE DOCUMENTS: As per M12 and M19 of A0171.005 sheet 0301 Rev 0
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 5 - Finishing Activities
checkpoint | 5.1 - Repair of defective areas
label | FREQUENCY: Each occurrence
label | ACCEPTANCE CRITERIA: Areas of finished work that have been deemed non-conforming alerted to the QAV and rectification method approved
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, NCR report
label | HP*
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 5.2 - As Built Documentation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Survey pick-up to be progressively completed. As built drawings to be be progressively completed. Test data, ITPs, Concrete Dockets, Checklists to be compiled and lot to be closed out.
label | REFERENCE DOCUMENTS: FH Detailed Construction Methodology - Shotcrete Works
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 6 - Post Construction
checkpoint | 6.1 - Final inspection
label | FREQUENCY: After construction complete
label | ACCEPTANCE CRITERIA: Visual inspetion conducted by Lee Tyers Building surveyors following the completion of construction
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Form 39 signed
label | HP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Compressive Strength (& VPV Test Results if requested by Superintendent)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength comply with table 610.061.
label | ○ Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects.
label | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%.
label | Attach: Compressive Strength Test Results
label | Attach: Core Sample Compressive Strength Test Results
label | REFERENCE DOCUMENTS: Table 610.051, Table 610.061, 610.16 (g)
label | INSPECTION/TEST METHOD: Document Review, Each cylinder and core sample
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 6.3 - As-built Survey
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the Table 610.472 as applicable to the element.
label | ○ Where a shape is required, ±25mm with no depressions greater than 15mm.
label | Attach: Survey As-builts / Survey Report
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: As built
label | RECORD OF CONFORMITY: This ITP signed, HPR release in Procore
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | QAV - Print Name:
textbox | QAV - Position:
textbox | Fulton Hogan - Print Name:
textbox | Fulton Hogan - Position:
date | Work Completed On:
signoff | Add Signature