## Master List Templates
Id | Type | Name | Values | Prompting Name
a8311761-dbf9-5c8f-b57f-ab1545c765d9 | checklist | 2 Sided Onsite Structural |  | 2 Sided Onsite Structural
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
5880b06a-cafe-52e7-aa3c-bd3f5de38bdf | checkpoint | Frame cleaned and prepped
258c6ee5-7bc2-5ac3-8513-f263979af662 | checkpoint | Correct structural tape applied
77d9e818-f2be-5100-966c-e6f1eb2602e0 | checkpoint | Glass installed per structural submission
5f4cf3c4-f912-504b-8043-f7943f2c47df | note | Pre-check edgework & any markings on glass
633cea8d-8f19-5bec-b368-176283a147e9 | checkpoint | Beads installed
1a44c9c3-e51f-5545-a25a-215e099a7ef9 | checkpoint | Ties installed
45b99fc3-f3a5-56b7-8373-8d67c3a899c1 | checkpoint | Structural silicone completed
a9cd0d6f-3c98-5dae-b6f9-295ad6ff06fb | note | Correct silicone bite per submission
73cd9f06-f83f-5792-b62d-87dafde7ebaf | checkpoint | Ties removed
1a5daf92-7a23-596b-9c95-d7d89a6c5308 | checkpoint | Weather seal completed
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
3377e97d-54f6-58a2-a941-4643a89b024d | checklist | 4 Sided Factory Structural |  | 4 Sided Factory Structural
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
af47faff-516d-5127-bb20-80aff458ebc0 | checkpoint | Frame free from damage
5880b06a-cafe-52e7-aa3c-bd3f5de38bdf | checkpoint | Frame cleaned and prepped
258c6ee5-7bc2-5ac3-8513-f263979af662 | checkpoint | Correct structural tape applied
77d9e818-f2be-5100-966c-e6f1eb2602e0 | checkpoint | Glass installed per structural submission
099a11f6-35ae-5916-834d-9a7192027ff5 | note | Pre-check edgework & any markings on glass
45b99fc3-f3a5-56b7-8373-8d67c3a899c1 | checkpoint | Structural silicone completed
4cebb073-a4b5-53dc-8257-0bf9fd7b0e4c | note | Correct silicone bite per submission
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
24df3756-0e81-5c9a-98af-9b7f0aff4c63 | checkpoint | Deglaze tests completed at correct intervals
593e8a3a-0a42-53ce-b800-d042edc95628 | note | Refer to test reports
b96078db-f05d-5dc0-80a6-5763df85f03a | checklist | Balustrades (Channel & Point Fix) |  | Balustrades (Channel & Point Fix)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
7c2efd40-8e20-5408-a815-543d5e6f9eba | checkpoint | Fixings drilled & chem-set
f7e49d6d-bcb7-507b-a9cc-32d199043809 | note | timber: coach screwed with sika-fix
45b8f605-9770-5937-b027-171018c25966 | checkpoint | Hardware installed per PS1
f6bb5ca3-2f2a-5e2b-8d49-3a51df0699ea | note | Re-tension fixings & check hardware for damage
b5861ccb-c203-5228-bf9b-d41c197163e9 | checkpoint | Glass installed & plumbed per PS1
c89600bd-2781-50b8-958b-a51b5d2b0842 | note | Pre-check edgework & ensure gaps are even
15b4fdd3-f5bc-4e51-9e35-d7500d595f18 | checkpoint | Gate Installed
b06bd6ac-163a-5288-bbeb-eccd84c03c5f | note | Set closing speed
6bed3c41-2fef-5534-9a39-5c75a6ffa023 | note | Check hinges and latch are tightened
28c3a267-79bf-5a35-aaaa-746d877861f2 | checkpoint | Hand-rail / link-rail installed
23111fcf-1600-549d-8fbb-ce6e0b22aadd | checkpoint | Cover Caps and end caps Installed
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
5940ac21-b373-5ea0-934a-dc627f85ac8f | checklist | Dry Glazed Rooflight/Skylight |  | Dry Glazed Rooflight/Skylight
d161f0e3-d5f6-59d0-be00-dc9bc4bdb353 | checkpoint | Frame installed securely
e9941a3f-2a34-5650-90f0-967a41c8ae61 | checkpoint | Correct glass installed
4dcea734-e85f-50d2-be4b-afc394ec957c | checkpoint | Glass centralised in frame
e382f693-6b2e-5c13-960c-2ae7cadb1460 | checkpoint | Location blocks installed
a32dd21b-97da-5233-9185-bdc3e7c1744f | note | Check feet are installed by others
633cea8d-8f19-5bec-b368-176283a147e9 | checkpoint | Beads installed
1ff5b66f-76c1-5f83-8e5a-20a1cc4381d2 | note | No damage
8d248bee-9285-590e-a320-6c749e5202db | checkpoint | Wedge rubber complete
e79b8e7a-300c-518f-87b4-bca675419375 | note | No lumps
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
0c7e62b4-809b-5107-8053-4dc82ad20957 | checklist | Dry Glazed W&Ds |  | Dry Glazed W&Ds
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
d161f0e3-d5f6-59d0-be00-dc9bc4bdb353 | checkpoint | Frame installed securely
e9941a3f-2a34-5650-90f0-967a41c8ae61 | checkpoint | Correct glass installed
6d9b0c70-096a-59e1-b742-dc435864d477 | note | Make note of glass type from sticker
bebb0f37-6190-5799-9848-12615c808ad2 | checkpoint | Glass installed with correct face to the outside
a2d68127-0b07-5475-b025-c1c91500df94 | checkpoint | Setting/location blocks correctly installed
6ed94e23-91db-591a-ad9a-9692bd1d6314 | note | 1/4 points
633cea8d-8f19-5bec-b368-176283a147e9 | checkpoint | Beads installed
9c9c8b1e-638b-59c1-8138-1838b8fcde11 | note | No damage
8d248bee-9285-590e-a320-6c749e5202db | checkpoint | Wedge rubber complete
81880b62-8816-5f01-8e65-3de83fd62ab8 | note | No lumps
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
73fe6a97-ca93-5d65-8508-f1d5163025b6 | checklist | Frameless Auto Doors |  | Frameless Auto Doors
e9941a3f-2a34-5650-90f0-967a41c8ae61 | checkpoint | Correct glass installed
28c698cc-e905-53c0-988d-c3280d866ab7 | checkpoint | All fixings tightened correctly
0073c13d-a1c9-56ec-a5d3-4424f46ea501 | checkpoint | Glass installed plumb
8ba9a343-5478-56d1-b997-fb6ad7c312d9 | checkpoint | Correct gap to allow guide install
e0e0819c-0c9e-57c8-93e0-654b55e2cdd2 | note | Guides by others
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
a6c744fc-947b-5f22-9003-548e18b36b7a | checklist | Frameless Canopy |  | Frameless Canopy
ee3f6171-419f-5cb6-9554-7907cefd2235 | checkpoint | Steel is secure and acceptable
dd9a9c45-a6bf-5f38-80bd-2a6c6d240796 | checkpoint | Install hardware per PS1 or shop drawings
6221fe98-60ca-5b09-b8e0-44f0e5d6705e | note | Ensure fittings & swivel heads bolted tight
551d3547-9d41-5625-b318-7e43fc3e3542 | checkpoint | Glass installed & aligned
ce23c91e-3a82-54ae-bede-269373f35cf2 | note | Check edge-work & unit marking
921f2cf2-54a5-507f-8bda-8548ea70fce4 | checkpoint | Silicone joints
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
93812233-ad4d-5cd0-a5a9-fd34e63b349d | checklist | Frameless Facade |  | Frameless Facade
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
8034f7a7-a457-5f25-b2b6-bd931902ab81 | checkpoint | Sill tray packers installed
c3f26abe-b5dd-5acb-a6b4-ac9a2d70a8e4 | note | Refer design
92831874-6d3e-5a4b-92dd-c3dbee069f8d | checkpoint | Sill tray & channel installed and sealed
d7e62154-e5b6-5d99-ab01-023979ebd1ba | note | Fixings at specified centres & sealed. Refer design
1f08d26b-8427-5f4d-9e61-a6cf46c2f41d | checkpoint | Head & side channels installed
a7c04a75-1ba8-564a-b5eb-742c7319ddfe | note | Fixings at specified centres & sealed. Refer design
1878f365-9763-5f2e-a7de-978f2762d0d5 | checkpoint | Fin brackets installed
dc273a4c-18b8-52fd-b20e-adf7f9324137 | note | Refer design
4060dd95-cafd-5107-93ff-26a5a762a288 | checkpoint | Fin glass installed
1f230976-57a2-54d5-afa5-10fef01c615c | note | Fixings tightened to correct torque setting. Refer design
f28a5ebb-a331-5a9e-9bf8-ad41ca36c615 | note | Make note of torque setting.
99794865-178c-53e0-bb7b-80f75e44c282 | checkpoint | Façade spiders installed
98bbb526-cf84-58a6-b69c-5364e129b32b | note | Fixings tightened to correct torque setting. Refer design
51e14df7-c3ee-5e6a-9c55-900d93d66292 | note | Make note of torque setting.
e9941a3f-2a34-5650-90f0-967a41c8ae61 | checkpoint | Correct glass installed
d63c561b-f5fd-5f79-8286-70e212c8aec8 | note | As per quote. Quarterly blocking
8d248bee-9285-590e-a320-6c749e5202db | checkpoint | Wedge rubber complete
9130ce20-18c0-5453-bd11-3eaf33800db3 | note | No lumps
814b6469-63ef-5ec5-b952-bf02c2be1490 | checkpoint | Silicone joins complete
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
bdbe3a81-aaea-5b12-8ae8-27b768721947 | checklist | Frameless Pivot Doors |  | Frameless Pivot Doors
6ecfadb7-25ba-5f06-85f0-7dc1ab89b45d | checkpoint | Opening plumb and level
f09c735f-3a97-5353-9a5e-72cc107580a1 | note | Check for fixing in the ceiling
b8493b4b-787f-51db-989b-5610d1aecd06 | checkpoint | Floor spring installed correctly
b47f269b-be1d-5737-8478-2e1ab423b166 | note | Position/height
487b8fdf-5bb6-5a9c-9d92-081925214e93 | checkpoint | Top pivot installed to solid fixing
108c1be4-d989-5ec9-9e3f-5d695bb0c61d | note | Solid fixing
5ea1036d-b007-59c6-aca1-8fa57de2c6f2 | checkpoint | Patch fittings/rails aligned with door edges
07826a54-f2a9-54b8-9deb-a6caf64ca57e | checkpoint | Correct glass installed evenly to opening
dc6b1b2c-efce-51fd-8f57-8aaae39e782f | note | Check gaps and alignment
e7a63149-ac9d-5b98-8d23-44320d2227c1 | checkpoint | Correct handle installed and tightened
5cbadc20-d41d-5a39-babc-03e41b3b2c47 | checkpoint | Lock and keeper installed and working correctly
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
9a3adc6a-e1a2-5224-911f-626d360b9360 | checklist | Frameless Shopfront |  | Frameless Shopfront
7ebf3446-7d4c-542e-b6e3-d260b59f5278 | checkpoint | Substrate acceptable
92831874-6d3e-5a4b-92dd-c3dbee069f8d | checkpoint | Sill tray & channel installed and sealed
a5f4d56f-17b6-5230-870c-ce055b571be3 | note | Fixings at specified centres & sealed. Refer design/PS1
c7d2e127-3c1e-514c-b847-aa111701d353 | checkpoint | Head and side channels installed
226f85c5-604b-5724-8883-7b144dc1d54f | note | Fixings at specified centres & sealed. Refer design/PS1
1878f365-9763-5f2e-a7de-978f2762d0d5 | checkpoint | Fin brackets installed
a4406580-fa66-5931-89f3-d6dd21dec374 | note | Refer design/PS1
4060dd95-cafd-5107-93ff-26a5a762a288 | checkpoint | Fin glass installed
23c41a4e-d796-573a-a8b5-613f2226ba5a | note | Fixings tightened to correct torque setting. Refer design/PS1
e9941a3f-2a34-5650-90f0-967a41c8ae61 | checkpoint | Correct glass installed
d1c05a66-dfec-56e4-a739-7ffef6a19f2f | note | As per quote
8d248bee-9285-590e-a320-6c749e5202db | checkpoint | Wedge rubber complete
82a226f1-72e5-540c-b23f-baf782479908 | note | No lumps
814b6469-63ef-5ec5-b952-bf02c2be1490 | checkpoint | Silicone joins complete
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
c89de34f-602f-526f-9a9b-3e56e13299a4 | checklist | Internal aluminium doors |  | Internal aluminium doors
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8ef59978-71d4-5f59-b8a0-fb2b4e5210f8 | checkpoint | Frame hung securely
f61ffab3-ccfd-525c-8526-1ea77ca7d414 | note | Check for screws
e9941a3f-2a34-5650-90f0-967a41c8ae61 | checkpoint | Correct glass installed
e8bdd0f2-eb25-51a4-9d46-bd7244dcfceb | note | As per quote
3aa045ee-bd02-5c02-9492-f7966bc21ba5 | checkpoint | Toe and heel blocking complete
aa32c343-6f9b-57d5-bfa0-1a402877acc5 | note | Gaps even
8d248bee-9285-590e-a320-6c749e5202db | checkpoint | Wedge rubber complete
201a5769-9e67-5372-a99d-6192ca0ca7e3 | note | No lumps
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
e2b87123-ba64-5bda-9c0c-dee7adf3b79b | checklist | Internal Partitions |  | Internal Partitions
3a4433c4-3fcf-5bfe-9857-769f5c02d1a8 | checkpoint | Frame fixed off
7eac8ede-f453-5b4f-986a-17f4878d9aec | note | Check for corner brackets
e9941a3f-2a34-5650-90f0-967a41c8ae61 | checkpoint | Correct glass installed
1a48be0d-9591-5883-b47f-fb919c1f5555 | checkpoint | As per quote
8d248bee-9285-590e-a320-6c749e5202db | checkpoint | Wedge rubber complete
f1b94071-1bfd-5cfa-a19c-c2709246be9e | note | No lumps
814b6469-63ef-5ec5-b952-bf02c2be1490 | checkpoint | Silicone joins complete
1a5abdb7-e41c-5c9c-aead-8fe98f3ae713 | checkpoint | Door jambs glued
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
ef20b8d3-8555-5318-b4d1-f26691b7d982 | checklist | Mirrors |  | Mirrors
31e551d6-a41e-536f-9b33-754667ae6749 | checkpoint | Vanity installed
8585617a-3a17-5991-a5d8-139081c5b2da | checkpoint | Wall prepped correctly
a6c656af-fd9b-5929-bad7-41c5b4261aa0 | checkpoint | Install mirror
c2e60cd2-d35d-5068-a9fc-914fd6606c71 | note | Check level/plumb
dad310fb-664b-56d3-ba1e-edc604b83e56 | checkpoint | Remove props
d0525c99-4e6d-5311-8388-4564bbafadb1 | checkpoint | Seal around mirror
8a3026d8-c3ca-5832-96c7-1b4784be753e | note | Check if needed
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
c06bad27-6e01-5adc-9d30-f01120ccf87f | checklist | Showers |  | Showers
ede24bfc-d509-5c4e-ac2e-1abf28ba66d7 | checkpoint | Substrate 100% complete
779a0999-6b97-578a-8a03-b2152ae24213 | checkpoint | Channel installed
c4fb2548-05d7-5507-9834-468360482626 | note | Check heel seal is complete
e51ed0cb-a5c8-5524-96b7-9c54f94c139c | checkpoint | Fixed glass installed
12b7497f-9ede-5fec-8b22-784edea4892a | note | Check level/plumb
d41aacde-c6df-59fa-8b10-87768894cfc6 | checkpoint | Head brace installed
b0562e0f-ec27-5074-aa3a-56b9873854b3 | checkpoint | Check glued into brackets
f1c74b9a-f545-5048-999c-cc5b53ac79eb | checkpoint | Shower door installed
4e3e7681-fb1f-5657-a87a-44322e6a0224 | checkpoint | Check hinges are the required finish and screws are tightened
cd4c0499-8923-5b2d-92e4-5e125b64e69f | checkpoint | Check door swings freely
7e7b4369-5f77-57c0-8aa1-e78aaab10432 | checkpoint | Correct handle installed
d2331f2a-0884-584b-8c12-9a3007b3bb86 | checkpoint | Check required finish and screws are tightened
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
22b3b10f-6355-494c-8b5e-c6fe08434065 | checklist | Smoke Baffle |  | Smoke Baffle
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
fa3fe5da-1059-4690-b74e-c35a13bcc92c | checkpoint | Frame installed securely
0ff01e42-b718-4eeb-a59b-5f09a9f6fc47 | checkpoint | Hole setout correct
55dc988b-e3e6-41ff-aa62-e82f3026efdd | checkpoint | Gaskets fitted front and back
dd3ffe9d-9bf5-4aa2-98f7-5b66670769a9 | checkpoint | Nylon bush fitted to inside glass hole
12c56b7f-d44f-45a7-825c-c00100b7485a | checkpoint | M16 316 bolts, washers & nuts used as per drawing - D1
33dcdfc3-faa3-4882-908d-718d6c10668d | checkpoint | SS washer sealed with 795 as per D4
dd8684eb-1446-471c-b15b-7666c4f5b18f | checkpoint | Correct glass installed
ddf7745a-4a9f-5420-8723-03bb5ea7b556 | textbox | Make note of glass type from sticker
628c8847-b588-4902-9c0e-1b19d68a9628 | checkpoint | Glass join sealed with 795
8ce4a07d-7a71-4b0b-8781-1e64db71deb0 | checkpoint | SS trim fitted as per drawings with 795
7703d292-4268-4f34-9e32-bb45a5147950 | checkpoint | End SS panel installed as per drawing D3
f7480071-5ea3-447d-a65b-cc3412e3eadb | checkpoint | Seal to end panel & wall completed as per DRW D3
32b4bae0-55a7-4d14-9963-c7fd555e3076 | checkpoint | Seal to end panel & glass completed as per DRW D2
8fee4eee-e8e5-4881-a1a2-a53bd894675b | checkpoint | Trade clean
1d64428e-f067-50aa-975e-4e38f0ffbccf | checklist | Splashback |  | Splashback
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8585617a-3a17-5991-a5d8-139081c5b2da | checkpoint | Wall prepped correctly
d0804066-c184-50d0-a218-ae63ec94e093 | checkpoint | Glass free of defects
ea19798c-b913-5ed3-9605-a98273b86816 | checkpoint | Install splashback
d6038006-a7ff-5018-aceb-992c7601f0fb | note | Check level/plumb
dad310fb-664b-56d3-ba1e-edc604b83e56 | checkpoint | Remove props
2d9f48ee-fbf5-5d80-9fe3-9f7a016175a4 | checkpoint | Seal around splashback
ccf115d0-67e3-5420-8894-7005117802a7 | note | Check if needed
cde13f59-28ef-5322-ab6f-6ff315c2f034 | checkpoint | Trade clean
99306196-ae1b-50fc-b612-973a0365626f | checklist | Twin Skin Partitions |  | Twin Skin Partitions
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
3a4433c4-3fcf-5bfe-9857-769f5c02d1a8 | checkpoint | Frame fixed off
4afa6813-16a8-52d1-b99d-fadbc26497f9 | note | Check for corner brackets
6810c0dd-a8dc-5200-8dc5-2ba2f60a55c0 | checkpoint | Correct glass installed to first skin
89b40b99-1642-5f52-ba33-6ebbb93f2c5d | note | As per quote
8d248bee-9285-590e-a320-6c749e5202db | checkpoint | Wedge rubber complete
59096b67-ebdb-5435-906c-f7b8bf46f587 | note | No lumps
814b6469-63ef-5ec5-b952-bf02c2be1490 | checkpoint | Silicone joins complete
1a5abdb7-e41c-5c9c-aead-8fe98f3ae713 | checkpoint | Door jambs glued
bfb4699a-9dee-5c56-b45e-c964986eb0da | checkpoint | Internal side of first skin cleaned
6e8070b5-5ccb-5d42-a5aa-61c882facb2e | checkpoint | Internal side of second skin cleaned
96cfdbd7-0e49-57e4-b9a0-ec689aff9d66 | checkpoint | Correct glass installed to second skin
c957ac61-0e75-5dd0-97b9-f0dd67d1d14c | note | As per quote
f589bf5e-be5c-4dbc-a85b-5fcebcc2eda7 | checkpoint | Wedge rubber complete
81dc0c9d-1765-5416-b2c4-ed1d34847113 | note | As per quote
8ddc280f-a734-4ea5-9557-d8b86529b948 | checkpoint | Silicone joins complete
1e803ff6-c6dc-576b-8866-9f3c345c5e8b | note | No ties
9a5e8ad1-5d0c-4322-9522-bc83bc9cd75b | checkpoint | Door jambs glued
44e13536-d4fe-52ad-a4c9-c65fea19ef2a | checkpoint | Trade clean outside of the partition

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
7ab96b84-a705-4083-9aa9-cbacdfc06ebc | checklist | Site Specific re-wedging (118 Broadway) |  | Site Specific re-wedging (118 Broadway)
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0d45aad7-27d6-4771-918d-3044ae7fac01 | checkpoint | Aluminium joints acceptable
ad34674e-8109-5611-a82d-56be57d63598 | note | Rectify with small joint sealer if not ok.
b8d83479-2d2a-44ff-a099-7fa7ff02724e | checkpoint | Drainage holes clear of debris
18157539-113b-4a2d-bef6-c1196173bcfd | checkpoint | Setting blocks in correct position
fc09edfd-ea11-5cb2-917a-40ad26395f27 | note | Not covering drainage holes
3fb90be2-7df2-45ac-bd74-10224e465d5b | checkpoint | New wedge rubber installed