## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0069 Tactile Ground Surface Indicator (TGSI) Installation | itp |  |  |  |  | 1630-P200-SYM-QAC-ITP-0069 Tactile Ground Surface Indicator (TGSI) Installation
section | ITP Details
checkpoint | ITP Details
label | ITP No. - 0069
label | Rev No. - 00
label | Date of Issue - 18/10/2024
label | ITP Type - New
section | 1.0 Pre-start activities
checkpoint | 1.1 - Material Conformance
label | Ref docs - AS1428.4.1 Fig 2.1, Fig 3.1 RDN 06-05
label | Acceptance criteria - Tactile indicators shall conform to the requirements of AS1428.4.1.
label | ○ Tactiles shall be chosen from the DTP approved list per RDN 06-05
label | ○ Tactiles shall be approved by council representative where (if applicable).
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Luminance-contrast testing
label | Ref docs - AS 1428.4.1 Cl 2.2
label | Acceptance criteria - Luminance-contrast testing shall be completed as per AS 1428.4.1 to confirm the selected TGSIs have a luminance-contrast to the base surface of not less than 30%
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
bool | Test Report
section | 2.0 Installation
checkpoint | 2.1 - Set out
label | Ref docs - AS 1428.4.1 Cl 2.2, Cl 3.2
label | Acceptance criteria - TGSI’s shall be inspected prior to fixing to confirm the below tolerances are met:
label | – TGSI’s shall be inspected prior to fixing to confirm the below tolerances are met:
label | – 300mm from face of kerb ± 10mm
label | – TGSI base is a maximum 3mm above the ground surface.
label | – Within 300mm of traffic signal push-buttons (where applicable).
label | Freq - Each Lot
label | Key - H
label | Resp - SE
checkpoint | 2.2 - Tactile Install - Warning
label | Ref docs - AS1428.4.1 Cl 2.2
label | Acceptance criteria - Tactiles shall be installed:
label | – Perpendicular to the carriageway
label | – To the full width of the path of travel
label | – So that there is no likelihood of the edges lifting
label | – In accordance with AS1428.4.1 and the IFC drawings
label | Freq - Each Lot
label | Key - H
label | Resp - SE
checkpoint | 2.3 - Tactile Install - Directional
label | Ref docs - AS1428.4.1 Cl 3.2
label | Acceptance criteria - Tactiles shall be installed:
label | – Parallel to the required direction of travel
label | – Along the centreline of the required direction of travel
label | – So that there is no likelihood of the edges lifting
label | – In accordance with AS1428.4.1 and the IFC drawings
label | Freq - Each Lot
label | Key - H
label | Resp - SE
section | 3.0 Work Lot Close Out
checkpoint | 3.1 - Product Non-Conformance
label | Ref docs - CQMP
label | Acceptance criteria - All Product Non-Conformance(s) recorded and closed (if applicable)
label | Freq - Each lot
label | Key - R
label | Resp - SE
checkpoint | 3.2 - Quality Representative to check the above criteria and records to confirm
label | Ref docs - CQMP, Lot Records
label | Acceptance criteria - All above criteria met, and records identified attached.
label | Freq - Each lot
label | Key - R
label | Resp - SE