## Sheet1
1.1 | Survey Set Out | GPS Setout of the Retaining wall as per the construction drawings. | W | Length of the retaining wall | Visual Inspection | Survey Report | Contractor's site diary and/or photos | Contractor | Setout location prior to commencing works. | 1.1 - Survey Set Out | Detail of Activity - GPS Setout of the Retaining wall as per the construction drawings. | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of the retaining wall | Inspection / Test method - Visual Inspection | Acceptance Criteria - Survey Report | Record documents - Contractor's site diary and/or photos | Responsibility - Contractor | Comments - Setout location prior to commencing works. | 1.1 - Survey Set Out
1.2 | Materials Approvals | Submit testing data fir the following materials: - AP65 - GAP 40 - GAP 20 - Hardfill | H | Once for each material | Quarry Testing Data | Engineer's Acceptance | InEight Records | Contractor |  | 1.2 - Materials Approvals | Detail of Activity - Submit testing data fir the following materials: - AP65 - GAP 40 - GAP 20 - Hardfill | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Once for each material | Inspection / Test method - Quarry Testing Data | Acceptance Criteria - Engineer's Acceptance | Record documents - InEight Records | Responsibility - Contractor | Comments - | Detail of Activity - GPS Setout of the Retaining wall as per the construction drawings.
2.1 | Bases, Footings and/or Toes | Subgrade Cut / Base Thickness | M | Every 5m section | Visual Inspection | As per drawing | QC Sheets | Contractor | THE SAFETY OF ALL TEMPORARY OPEN CUTS SHALL BE THE RESPONSIBILITY OF THE CONTRACTOR. THE CONTRACTOR SHALL PROVIDE ANY AND ALL SLOPE PROTECTION NECESSARY TO PREVENT ANY GROUND MOVEMENT. | 2.1 - Bases, Footings and/or Toes | Detail of Activity - Subgrade Cut / Base Thickness | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 5m section | Inspection / Test method - Visual Inspection | Acceptance Criteria - As per drawing | Record documents - QC Sheets | Responsibility - Contractor | Comments - THE SAFETY OF ALL TEMPORARY OPEN CUTS SHALL BE THE RESPONSIBILITY OF THE CONTRACTOR. THE CONTRACTOR SHALL PROVIDE ANY AND ALL SLOPE PROTECTION NECESSARY TO PREVENT ANY GROUND MOVEMENT. | Action (Hold, Monitor, Witness) - W
2.2 | Bases, Footings and/or Toes | Subgrade Testing | H | Every 20m | Scalar Penetrometer | ≥ 3 blows per 100mm to 1.5m depth. | QC Sheets | Contractor |  | 2.2 - Bases, Footings and/or Toes | Detail of Activity - Subgrade Testing | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 20m | Inspection / Test method - Scalar Penetrometer | Acceptance Criteria - ≥ 3 blows per 100mm to 1.5m depth. | Record documents - QC Sheets | Responsibility - Contractor | Comments - | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of the retaining wall
2.3 | Bases, Footings and/or Toes | Reinforcing WSP INSPECTION | M H | Every 6m panels | Visual Inspection | ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. | QC Sheets | Contractor/ Engineer |  | 2.3 - Bases, Footings and/or Toes | Detail of Activity - Reinforcing WSP INSPECTION | Action (Hold, Monitor, Witness) - M H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 6m panels | Inspection / Test method - Visual Inspection | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. | Record documents - QC Sheets | Responsibility - Contractor/ Engineer | Comments - | Inspection / Test method - Visual Inspection
2.4 | Bases, Footings and/or Toes | Formwork | H | Every 6m | Visual Inspection | As per drawing | QC Sheets | Contractor | FORMWORK SUPPLIED BY DOKA | 2.4 - Bases, Footings and/or Toes | Detail of Activity - Formwork | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 6m | Inspection / Test method - Visual Inspection | Acceptance Criteria - As per drawing | Record documents - QC Sheets | Responsibility - Contractor | Comments - FORMWORK SUPPLIED BY DOKA | Acceptance Criteria - Survey Report
2.5 | Bases, Footings and/or Toes | Concrete | H | All concrete orders | Concrete Dockets | Concrete strength 25MPa at 28 days Mix design to be apporved by the Engineer Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise | Concrete Dockets | Contractor | ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE. ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2. THE CONTRACTOR SHALL PROVIDE THE CONCRETE MIX DESIGN FOR THE APPROVAL OF THE ENGINEER PRIOR TO THE COMMENCEMENT OF ANY CONCRETE WORKS | 2.5 - Bases, Footings and/or Toes | Detail of Activity - Concrete | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All concrete orders | Inspection / Test method - Concrete Dockets | Acceptance Criteria - Concrete strength 25MPa at 28 days Mix design to be apporved by the Engineer Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise | Record documents - Concrete Dockets | Responsibility - Contractor | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE. ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2. THE CONTRACTOR SHALL PROVIDE THE CONCRETE MIX DESIGN FOR THE APPROVAL OF THE ENGINEER PRIOR TO THE COMMENCEMENT OF ANY CONCRETE WORKS | Record documents - Contractor's site diary and/or photos
2.6 | Bases, Footings and/or Toes | Dowels (greased and plain ended) | H | Every 300mm centers | Visual Inspection | R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS | QC Sheets | Contractor |  | 2.6 - Bases, Footings and/or Toes | Detail of Activity - Dowels (greased and plain ended) | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 300mm centers | Inspection / Test method - Visual Inspection | Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS | Record documents - QC Sheets | Responsibility - Contractor | Comments - | Responsibility - Contractor
2.7 | Walls | Reinforcing WSP INSPECTION | M H | Every 6m panels | Visual Inspection | ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. | QC Sheets | Contractor/ Engineer | Scabble or green cut interface in accordance with Type B construction joint to NZS 3109 For joints, the surface of the concrete may be prepared by green cutting (using high velocityair/water jets or vigirous wire brush) to remove all laitanceand inferior surface concrete after the concrete has hardened suffieciently to prevent loosening of any aggregate which is not removed. | 2.7 - Walls | Detail of Activity - Reinforcing WSP INSPECTION | Action (Hold, Monitor, Witness) - M H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 6m panels | Inspection / Test method - Visual Inspection | Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. | Record documents - QC Sheets | Responsibility - Contractor/ Engineer | Comments - Scabble or green cut interface in accordance with Type B construction joint to NZS 3109 For joints, the surface of the concrete may be prepared by green cutting (using high velocityair/water jets or vigirous wire brush) to remove all laitanceand inferior surface concrete after the concrete has hardened suffieciently to prevent loosening of any aggregate which is not removed. | Comments - Setout location prior to commencing works.
2.8 | Walls | Formwork | H | Every 5m | Visual Inspection | As per drawing | QC Sheets | Contractor | FORMWORK SUPPLIED BY DOKA | 2.8 - Walls | Detail of Activity - Formwork | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 5m | Inspection / Test method - Visual Inspection | Acceptance Criteria - As per drawing | Record documents - QC Sheets | Responsibility - Contractor | Comments - FORMWORK SUPPLIED BY DOKA | 1.2 - Materials Approvals
2.9 | Walls | Dowels (greased CHAR(AMP) plain ended) | M | Every 300mm centers | Visual Inspection | R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS SPACED AT MAXIMUM 6.1m INTERVALS OR A SUITABLE LESSER LENGTH IF REQUIRED | QC Sheets | Contractor |  | 2.9 - Walls | Detail of Activity - Dowels (greased CHAR(AMP) plain ended) | Action (Hold, Monitor, Witness) - M | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 300mm centers | Inspection / Test method - Visual Inspection | Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS SPACED AT MAXIMUM 6.1m INTERVALS OR A SUITABLE LESSER LENGTH IF REQUIRED | Record documents - QC Sheets | Responsibility - Contractor | Comments - | Detail of Activity - Submit testing data fir the following materials: - AP65 - GAP 40 - GAP 20 - Hardfill
2.1 | Walls | Finish / Joints | W | All areas | Visual Inspection | Smooth, off shutter finish. Cut joints as appropriate. | QC Sheets | Contractor |  | 2.1 - Walls | Detail of Activity - Finish / Joints | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All areas | Inspection / Test method - Visual Inspection | Acceptance Criteria - Smooth, off shutter finish. Cut joints as appropriate. | Record documents - QC Sheets | Responsibility - Contractor | Comments - | Action (Hold, Monitor, Witness) - H
2.11 | Walls | Concrete | H | All concrete orders | Concrete Dockets | Concrete strength 25MPa at 28 days Mix design to be apporved by the Engineer Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise | Concrete Dockets | Contractor | ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE. ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2. | 2.11 - Walls | Detail of Activity - Concrete | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All concrete orders | Inspection / Test method - Concrete Dockets | Acceptance Criteria - Concrete strength 25MPa at 28 days Mix design to be apporved by the Engineer Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise | Record documents - Concrete Dockets | Responsibility - Contractor | Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE. ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2. | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Once for each material
2.12 | Walls | Weep Holes | W | Every 2,000mm | Visual Inspection | As per drawing | QC Sheets | Contractor | 50mm Ø WEEPHOLES THROUGH WALL STEM AT MAXIMUM 3.0m SPACING | 2.12 - Walls | Detail of Activity - Weep Holes | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 2,000mm | Inspection / Test method - Visual Inspection | Acceptance Criteria - As per drawing | Record documents - QC Sheets | Responsibility - Contractor | Comments - 50mm Ø WEEPHOLES THROUGH WALL STEM AT MAXIMUM 3.0m SPACING | Inspection / Test method - Quarry Testing Data
2.13 | Backfill | Backfill behind wall (Shared service trench) | W | Refer to Shared Service Trench ITP | Refer to Shared Service Trench ITP | Refer to Shared Service Trench ITP | Refer to Shared Service Trench ITP | Refer to Shared Service Trench ITP | Refer to Shared Service Trench ITP | 2.13 - Backfill | Detail of Activity - Backfill behind wall (Shared service trench) | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Refer to Shared Service Trench ITP | Inspection / Test method - Refer to Shared Service Trench ITP | Acceptance Criteria - Refer to Shared Service Trench ITP | Record documents - Refer to Shared Service Trench ITP | Responsibility - Refer to Shared Service Trench ITP | Comments - Refer to Shared Service Trench ITP | Acceptance Criteria - Engineer's Acceptance
2.14 | Joints | Completed Joints | W | All concrete orders | Visual Inspection | Concrete strength 25MPa, at 28 days | Concrete Dockets | Contractor | SIKAFLEX SEALANT OR APPROVED EQUIVALENT | 2.14 - Joints | Detail of Activity - Completed Joints | Action (Hold, Monitor, Witness) - W | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All concrete orders | Inspection / Test method - Visual Inspection | Acceptance Criteria - Concrete strength 25MPa, at 28 days | Record documents - Concrete Dockets | Responsibility - Contractor | Comments - SIKAFLEX SEALANT OR APPROVED EQUIVALENT | Record documents - InEight Records
2.15 | Joints | Joint formwork | w | At joints between sections | Visual Inspection | Smooth, off shutter finish. Construction joints as per drawing | QC Sheets | Contractor | COMPRESSIBLE BOARD BETWEEN WALL SECTIONS | 2.15 - Joints | Detail of Activity - Joint formwork | Action (Hold, Monitor, Witness) - w | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - At joints between sections | Inspection / Test method - Visual Inspection | Acceptance Criteria - Smooth, off shutter finish. Construction joints as per drawing | Record documents - QC Sheets | Responsibility - Contractor | Comments - COMPRESSIBLE BOARD BETWEEN WALL SECTIONS | Responsibility - Contractor
2.16 | Subsoil drainage - front of wall Subsoil drainage - back of wall | Subsoil drain - back of wall | H | Length of wall | Visual Inspection | As per drawing | QC Sheets | Contractor |  | 2.16 - Subsoil drainage - front of wall Subsoil drainage - back of wall | Detail of Activity - Subsoil drain - back of wall | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of wall | Inspection / Test method - Visual Inspection | Acceptance Criteria - As per drawing | Record documents - QC Sheets | Responsibility - Contractor | Comments - | Comments -
|  | Installation of subsoil drain | H | Lentgh of wall | Visual Inspection | As per drawing | QC Sheets | Contractor | 100Ø PERFORATED SUBSOIL DRAIN WITH 40/20 DRAINAGE AGGREGATE WRAPPED IN GEOTEXTILE OF STRENGTH CLASS B AND FILTRATION CLASS 2 TO TNZ F/7 SUBSOIL DRAIN TO BE LAID WITH 1% FALL AND DISCHARGE TO THE NEAREST STORMWATER SUMP | - | Detail of Activity - Installation of subsoil drain | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Lentgh of wall | Inspection / Test method - Visual Inspection | Acceptance Criteria - As per drawing | Record documents - QC Sheets | Responsibility - Contractor | Comments - 100Ø PERFORATED SUBSOIL DRAIN WITH 40/20 DRAINAGE AGGREGATE WRAPPED IN GEOTEXTILE OF STRENGTH CLASS B AND FILTRATION CLASS 2 TO TNZ F/7 SUBSOIL DRAIN TO BE LAID WITH 1% FALL AND DISCHARGE TO THE NEAREST STORMWATER SUMP | 2.1 - Bases, Footings and/or Toes
3.1 | Collate above documentation | Document review | H | Each ITP | Review | All above documentation is shown as attached to this work pack. | Review | Contractor |  | 3.1 - Collate above documentation | Detail of Activity - Document review | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Each ITP | Inspection / Test method - Review | Acceptance Criteria - All above documentation is shown as attached to this work pack. | Record documents - Review | Responsibility - Contractor | Comments - | Detail of Activity - Subgrade Cut / Base Thickness
3.2 | As-built drawings | Survey | H | At completion of construction | Asbuilts to besubmitted at the completion of construction, information to be captured | Asbuilts reviewed and submitted | In Eight record | Contractor |  | 3.2 - As-built drawings | Detail of Activity - Survey | Action (Hold, Monitor, Witness) - H | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - At completion of construction | Inspection / Test method - Asbuilts to besubmitted at the completion of construction, information to be captured | Acceptance Criteria - Asbuilts reviewed and submitted | Record documents - In Eight record | Responsibility - Contractor | Comments - | Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 5m section
Inspection / Test method - Visual Inspection
Acceptance Criteria - As per drawing
Record documents - QC Sheets
Responsibility - Contractor
Comments - THE SAFETY OF ALL TEMPORARY OPEN CUTS SHALL BE THE RESPONSIBILITY OF THE CONTRACTOR. THE CONTRACTOR SHALL PROVIDE ANY AND ALL SLOPE PROTECTION NECESSARY TO PREVENT ANY GROUND MOVEMENT.
2.2 - Bases, Footings and/or Toes
Detail of Activity - Subgrade Testing
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 20m
Inspection / Test method - Scalar Penetrometer
Acceptance Criteria - ≥ 3 blows per 100mm to 1.5m depth.
Record documents - QC Sheets
Responsibility - Contractor
Comments -
2.3 - Bases, Footings and/or Toes
Detail of Activity - Reinforcing WSP INSPECTION
Action (Hold, Monitor, Witness) - M H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 6m panels
Inspection / Test method - Visual Inspection
Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
Record documents - QC Sheets
Responsibility - Contractor/ Engineer
Comments -
2.4 - Bases, Footings and/or Toes
Detail of Activity - Formwork
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 6m
Inspection / Test method - Visual Inspection
Acceptance Criteria - As per drawing
Record documents - QC Sheets
Responsibility - Contractor
Comments - FORMWORK SUPPLIED BY DOKA
2.5 - Bases, Footings and/or Toes
Detail of Activity - Concrete
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All concrete orders
Inspection / Test method - Concrete Dockets
Acceptance Criteria - Concrete strength 25MPa at 28 days Mix design to be apporved by the Engineer Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise
Record documents - Concrete Dockets
Responsibility - Contractor
Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE. ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2. THE CONTRACTOR SHALL PROVIDE THE CONCRETE MIX DESIGN FOR THE APPROVAL OF THE ENGINEER PRIOR TO THE COMMENCEMENT OF ANY CONCRETE WORKS
2.6 - Bases, Footings and/or Toes
Detail of Activity - Dowels (greased and plain ended)
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 300mm centers
Inspection / Test method - Visual Inspection
Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS
Record documents - QC Sheets
Responsibility - Contractor
Comments -
2.7 - Walls
Detail of Activity - Reinforcing WSP INSPECTION
Action (Hold, Monitor, Witness) - M H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 6m panels
Inspection / Test method - Visual Inspection
Acceptance Criteria - ALL REINFORCING BARS SHALL BE OF GRADE 500E MILD STEEL. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS. MINIMUM REINFORCING LAP LENGTHS SHALL BE 550mm FOR HD12 BARS AND 800mm FOR HD16 BARS UNLESS NOTED OTHERWISE ON THE DRAWINGS.
Record documents - QC Sheets
Responsibility - Contractor/ Engineer
Comments - Scabble or green cut interface in accordance with Type B construction joint to NZS 3109 For joints, the surface of the concrete may be prepared by green cutting (using high velocityair/water jets or vigirous wire brush) to remove all laitanceand inferior surface concrete after the concrete has hardened suffieciently to prevent loosening of any aggregate which is not removed.
2.8 - Walls
Detail of Activity - Formwork
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 5m
Inspection / Test method - Visual Inspection
Acceptance Criteria - As per drawing
Record documents - QC Sheets
Responsibility - Contractor
Comments - FORMWORK SUPPLIED BY DOKA
2.9 - Walls
Detail of Activity - Dowels (greased CHAR(AMP) plain ended)
Action (Hold, Monitor, Witness) - M
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 300mm centers
Inspection / Test method - Visual Inspection
Acceptance Criteria - R20 DOWEL 450 LONG AT 300 CENTRES CONTROL JOINTS SHALL BE KEY JOINTS SPACED AT MAXIMUM 6.1m INTERVALS OR A SUITABLE LESSER LENGTH IF REQUIRED
Record documents - QC Sheets
Responsibility - Contractor
Comments -
2.1 - Walls
Detail of Activity - Finish / Joints
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All areas
Inspection / Test method - Visual Inspection
Acceptance Criteria - Smooth, off shutter finish. Cut joints as appropriate.
Record documents - QC Sheets
Responsibility - Contractor
Comments -
2.11 - Walls
Detail of Activity - Concrete
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All concrete orders
Inspection / Test method - Concrete Dockets
Acceptance Criteria - Concrete strength 25MPa at 28 days Mix design to be apporved by the Engineer Minimum cover to reinforcing for walls and footings 75mm unless noted otherwise
Record documents - Concrete Dockets
Responsibility - Contractor
Comments - ALL CONCRETE USED SHALL ATTAIN 25MPa COMPRESSIVE STRENGTH AT 28 DAYS CURE. ALL CONCRETE USED SHALL COMPLY WITH THE REQUIREMENTS FOR EXPOSURE CLASS XA2.
2.12 - Walls
Detail of Activity - Weep Holes
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Every 2,000mm
Inspection / Test method - Visual Inspection
Acceptance Criteria - As per drawing
Record documents - QC Sheets
Responsibility - Contractor
Comments - 50mm Ø WEEPHOLES THROUGH WALL STEM AT MAXIMUM 3.0m SPACING
2.13 - Backfill
Detail of Activity - Backfill behind wall (Shared service trench)
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Refer to Shared Service Trench ITP
Inspection / Test method - Refer to Shared Service Trench ITP
Acceptance Criteria - Refer to Shared Service Trench ITP
Record documents - Refer to Shared Service Trench ITP
Responsibility - Refer to Shared Service Trench ITP
Comments - Refer to Shared Service Trench ITP
2.14 - Joints
Detail of Activity - Completed Joints
Action (Hold, Monitor, Witness) - W
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - All concrete orders
Inspection / Test method - Visual Inspection
Acceptance Criteria - Concrete strength 25MPa, at 28 days
Record documents - Concrete Dockets
Responsibility - Contractor
Comments - SIKAFLEX SEALANT OR APPROVED EQUIVALENT
2.15 - Joints
Detail of Activity - Joint formwork
Action (Hold, Monitor, Witness) - w
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - At joints between sections
Inspection / Test method - Visual Inspection
Acceptance Criteria - Smooth, off shutter finish. Construction joints as per drawing
Record documents - QC Sheets
Responsibility - Contractor
Comments - COMPRESSIBLE BOARD BETWEEN WALL SECTIONS
2.16 - Subsoil drainage - front of wall Subsoil drainage - back of wall
Detail of Activity - Subsoil drain - back of wall
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Length of wall
Inspection / Test method - Visual Inspection
Acceptance Criteria - As per drawing
Record documents - QC Sheets
Responsibility - Contractor
Comments -
-
Detail of Activity - Installation of subsoil drain
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Lentgh of wall
Inspection / Test method - Visual Inspection
Acceptance Criteria - As per drawing
Record documents - QC Sheets
Responsibility - Contractor
Comments - 100Ø PERFORATED SUBSOIL DRAIN WITH 40/20 DRAINAGE AGGREGATE WRAPPED IN GEOTEXTILE OF STRENGTH CLASS B AND FILTRATION CLASS 2 TO TNZ F/7 SUBSOIL DRAIN TO BE LAID WITH 1% FALL AND DISCHARGE TO THE NEAREST STORMWATER SUMP
3.1 - Collate above documentation
Detail of Activity - Document review
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - Each ITP
Inspection / Test method - Review
Acceptance Criteria - All above documentation is shown as attached to this work pack.
Record documents - Review
Responsibility - Contractor
Comments -
3.2 - As-built drawings
Detail of Activity - Survey
Action (Hold, Monitor, Witness) - H
Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) - At completion of construction
Inspection / Test method - Asbuilts to besubmitted at the completion of construction, information to be captured
Acceptance Criteria - Asbuilts reviewed and submitted
Record documents - In Eight record
Responsibility - Contractor
Comments -