## QA Folder Structure
QA Folder Structure
Melbourne Quarter Tower
Wet Areas
WPM01
|  |  | B1 - Zone 1 | Enviro HP1200+800TC
|  |  | Level 00 Cleaner Room (L00.16) | Enviro HP1200+800TC
|  |  | Level 01 Zone 1 | Enviro HP1200+800TC
|  |  | Level 02 Zone 1 | Enviro HP1200+800TC
|  |  | Level 04 Zone 1 | Enviro HP1200+800TC
|  |  | Level 06-17 Typical low rise Zone 1 （L06.17, L06.19) | Enviro HP1200+800TC
|  |  | Level 06-08 Typical low rise Zone 1 to Winter Garden (L06.14) | Enviro HP1200
|  |  | Level 09 Zone 1 (L09.14) | Enviro HP1200
|  |  | Level 10 Zone 1 (L10.14) | Enviro HP1200+800TC
|  |  | Level 19 LMR Zone 1 (L19.13, L19.18) | Enviro HP1200+800TC
|  |  | Level 20 Typical high rise | Enviro HP1200+800TC
|  |  | Level 22-31 Typical high rise | Enviro HP1200+800TC
|  |  | Level 28 Zone 1 | Enviro HP1200+800TC
|  |  | Level 29 Zone 1 | Enviro HP1200+800TC
|  |  | Level 30 Zone 1 | Enviro HP1200+800TC
|  |  | Level 32 Zone 1 | Enviro HP1200+800TC
|  |  | Level 33 Zone 1 | Enviro HP1200+800TC
Exposed Sealed Concrete
WPM03
|  |  | B3 - Zone 1 | Enviro CSH
|  |  | B1 - Zone 1 | Enviro CSH
|  |  | B1 - Zone 2 | Enviro CSH
|  |  | Level 00 Zone 1 | Enviro CSH
|  |  | Level 00 Zone 2 | Enviro CSH
|  |  | Level 01 Zone 1 | Enviro CSH
|  |  | Level 01 Zone 2 | Enviro CSH
|  |  | Level 02 Zone 1 | Enviro CSH
|  |  | Level 02 Zone 2 | Enviro CSH
|  |  | Level 03 Zone 1 | Enviro CSH
|  |  | Level 04 Zone 1 | Enviro CSH
|  |  | Level 05 Lower Plant Zone 1 | Enviro CSH
|  |  | Level 06-16 Typical low rise Zone 1 | Enviro CSH
|  |  | Level 17 Transfer Zone 1 | Enviro CSH
|  |  | Level 18 Mid Plant Zone 1 | Enviro CSH
|  |  | Level 19 LMR Zone 1 | Enviro CSH
|  |  | Level 20 Typical high rise | Enviro CSH
|  |  | Level 20 Typical high rise | Enviro CSH
|  |  | Level 21 Zone 1 | Enviro CSH
|  |  | Level 22-30 Typical high rise (Stair 01&02) | Enviro CSH
|  |  | Level 31 Zone 1 | Enviro CSH
|  |  | Level 32 Zone 1 | Enviro CSH
|  |  | Level 33 Zone 1 | Enviro CSH
|  |  | Level 34 Zone 1 | Enviro CSH
|  |  | Level 35 Upper Plant Zone 1 | Enviro CSH
Dry Plantroom
WPM04
|  |  | B3 - Zone 1 | Enviro Epoxy RC / Ultra Tuff
|  |  | B1 - Zone 1 (LB1.55-59, LB1.47, LB1.76, LB1.78, LB1.85, Under bike backs) | Enviro Epoxy RC / Ultra Tuff
|  |  | B1 - Zone 2 | Enviro Epoxy RC / Ultra Tuff
|  |  | B1 - Zone 3 | Enviro Epoxy RC / Ultra Tuff
|  |  | Level 00 Zone 1 | Enviro Epoxy RC / Ultra Tuff
|  |  | Level 01 Zone 2 | Enviro Epoxy RC / Ultra Tuff
|  |  | Level 02 Zone 2 | Enviro Epoxy RC / Ultra Tuff
|  |  | Level 05 Lower Plant Zone 1 | Enviro Epoxy RC / Ultra Tuff
|  |  | Level 18 Mid Plant Zone 1 | Enviro Epoxy RC / Ultra Tuff
|  |  | Level 19 LMR Zone 1 | Enviro Epoxy RC / Ultra Tuff
|  |  | Level 21 Elec/Comms | Enviro Epoxy RC / Ultra Tuff
|  |  | Level 31 Zone 1 | Enviro Epoxy RC / Ultra Tuff
|  |  | Level 35 Upper Plant Zone 1 | Enviro Epoxy RC / Ultra Tuff
Wet Plantroom
WPM05
|  |  | B3 - Zone 1 | Enviro HP1200+800TC
|  |  | Bin wash room Upturns 2400mm | Enviro HP1200+800TC
|  |  | B1 - Zone 1 | Enviro HP1200+800TC
|  |  | B1 - Zone 2 | Enviro HP1200+800TC
|  |  | Level 00 Zone 1 | Enviro HP1200+800TC
|  |  | Level 00 Zone 2 | Enviro HP1200+800TC
|  |  | Level 02 Zone 2 | Enviro HP1200+800TC
|  |  | Level 05 Lower Plant Zone 1 | Enviro HP1200+800TC
|  |  | Level 18 Mid Plant Zone 1 | Enviro HP1200+800TC
|  |  | Level 18 Membrane under tanks in the Mid plant area | Enviro HP1200+800TC
|  |  | SPR Tank 1&2 (L18.16, L18.17) (Confined space work) | Enviro HP1200
|  |  | Soffit | Enviro HP1200+800TC
|  |  | Level 33 Zone 1 | Enviro HP1200+800TC
|  |  | Level 35 Zone 1 (L35.08) | Enviro HP1200+800TC
|  |  | Level 35 Lift lids | Enviro HP1200+800TC
Roof Membrane
WPM06
|  |  | Level 04 Zone 1 | Enviro HP1200+800TC
External Areas
WPM07
|  |  | Level 00 Zone 1 | Enviro HP1200+800TC
|  |  | Level 01 Zone 1 Balcony | Enviro HP1200+800TC
|  |  | Level 01 Zone 2 | Enviro HP1200+800TC
Carpark
WPM08
|  |  | B1 - Zone 1 | Enviro CSH
|  |  | B1 - Zone 2 | Enviro CSH
|  |  | B1 - Zone 3 | Enviro CSH
Landscape Paved Areas
Ground Level
|  |  | Ground Level Sheet 01 Paved areas | Enviro HP1200
|  |  | Ground Level Sheet 02 Paved areas | Enviro HP1200
|  |  | Ground Level Sheet 03 Paved areas | Enviro HP1200
|  |  | Ground Level Sheet 03 Ballast Roof | Enviro HP1200 + Geotextile Fabric
Sky Park
|  |  | Sky Park Sheet 01 Paved areas | Enviro HP1200
|  |  | Sky Park Sheet 02 Paved areas | Enviro HP1200
|  |  | Sky Park Sheet 02 Ballast Roof | Enviro HP1200 + Geotextile Fabric
MQT Planters
Ground Level
|  |  | Ground Level Sheet 01 Planter base | Enviro HP1200
|  |  | Ground Level Sheet 02 Planter base | Enviro HP1200
|  |  | Ground Level Sheet 03 Planter base | Enviro HP1200
Sky Park
|  |  | Sky Park Sheet 01 Planter base | Enviro HP1200
|  |  | Sky Park Sheet 02 Planter base | Enviro HP1200
OSD Tank
Stage 1
|  |  | Tank Waterproofing | Enviro HP1200
Stage 2
|  |  | Tank Waterproofing | Enviro HP1200
East Precast Panel
Elevation Waterproofing
|  |  | Elevation PE01, PE02, PE03, PE04 Precast panel joints (Horizontal) | Enviro HP1200
|  |  | Elevation PE01, PE02, PE03, PE04 Precast panel joints (Vertical) | Enviro HP1200
|  |  | Elevation CE03 Precast panel joints (Horizontal) | Enviro HP1200
|  |  | Elevation CE03 Precast panel joints (Vertical) | Enviro HP1200
|  |  | Elevation CE07, CE08 Precast panel joints (Horizontal) | Enviro HP1200
|  |  | Elevation CE07, CE08 Precast panel joints (Vertical) | Enviro HP1200
Sandwich Panelling
Bandage Waterproofing
|  |  | Bandage to Sandwich panelling W: 300mm | Enviro HP1200
Lift Pit
Lift Pit Base and Walls
|  |  | Negative Tanking | Enviro Hydrostatic 1
Basement
Additional Bandage to CJ
|  |  | L28 | Enviro HP1200
|  |  | L29 | Enviro HP1200
|  |  | L30 | Enviro HP1200
|  |  | L31 | Enviro HP1200
|  |  | L32 | Enviro HP1200
Temporary Waterproofing
|  | Temporary Waterproofing | Bandage to Tower Crane #1#2#3, Alimak Single 650 W: 300mm | Enviro HP1200
|  |  | Bandage to Construction joints W: 300mm | Enviro HP1200
|  |  | Temporary membrane to MQT lift core lid on Roof Level | Enviro HP1200+800TC
|  |  | Temporary waterproofing to MQT Stair cores, Lift protection desk, service risers (every 4 levels) (take L6 as typical measurement) | Enviro HP1200+800TC
|  |  | Temporary waterproofing to L29 Slab under roof on south side to extent as per addendum 5 mark-up | Enviro HP1200+800TC
M1 Building
MX-01 (Ground Floor)
Ground Floor
|  |  | GF Zone 1 External area | Enviro HP1200+800TC
MX-02 (External - Non Trafficable)
External - Non Trafficable
|  |  | Level 01 Zone 1 North Terrace (UV) | Enviro HP1200+800TC
|  |  | Level 01 Zone 2 North and South Terrace (UV) | Enviro HP1200+800TC
MX-03 (Concrete Sealer)
Concrete Sealer
|  |  | GF Zone 2 | Enviroseal WB + Aggregates
|  |  | Level 01 Zone 1 | Enviroseal WB + Aggregates
|  |  | Level 01 Zone 2 | Enviroseal WB + Aggregates
|  |  | Level 02 Zone 2 | Enviroseal WB + Aggregates
|  |  | Level 03 | Enviroseal WB + Aggregates
|  |  | Level 04 | Enviroseal WB + Aggregates
|  |  | Level 05 | Enviroseal WB + Aggregates
|  |  | Roof Level | Enviroseal WB + Aggregates
MX-04 (Wet Areas)
Wet Areas
|  |  | GF Airlock | Enviro HP1200+800TC
MX-05 (Dry Plant Room)
Dry Plant Room
|  |  | GF Zone 2 Comms & Elec | Enviro Epoxy RC / Ultra Tuff
|  |  | Roof Level Plant & Store | Enviro Epoxy RC / Ultra Tuff
MX-06 (Roof Trafficable)
Roof Trafficable
|  |  | GF Zone 2 | Enviro HP1200+800TC
|  |  | Level 02 Zone 2 | Enviro 700X + 800TC
|  |  | Upper Roof | Enviro HP1200+800TC
M1 (Landscape Paved Areas)
Landscape Paved Areas
|  |  | Ground Level Paved areas | Enviro HP1200
|  |  | Level 02 Maintenance access | Enviro HP1200
|  |  | Level 06 Paved areas | Enviro HP1200
|  |  | Level 06 Maintenance Zone | Enviro HP1200+800TC
M1 (Planters)
Planters
|  |  | Level 02 | Enviro 700X
|  |  | Level 06 | Enviro HP1200
M1 (Temporary Waterproofing)
Temporary Waterproofing
|  |  | Temporary membrane to M1 lift core lid on Roof Level | Enviro HP1200+800TC
|  |  | Temporary waterproofing to M1 Stair cores, Lift protection desk, service risers | Enviro HP1200+800TC
2MQ (Landscape Paved Area)
External
|  |  | Paved Area | Enviro HP1200
Planters
|  |  | Base and Walls | Enviro HP1200

## ITPs Checklists
type | name | values
checkpoint | Check correct materials are received at least 24 hours prior to commencing work on site
text | Batch No.
label | Specification / Standard: AS4654.1-2012; Manufacturer’s Technical Data Sheet
label | Attach Delivery Docket
checklist-flat | Enviro HP1200
checkpoint | Relevant Australian Standards Checked
label | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | Attach Photo
checkpoint | Moisture Content Test
label | Attach Photo
checkpoint | Apply primer using a brush or roller
label | Attach Photo
checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | Attach Photo
checkpoint | Mixing
checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint | Curing
checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | Attach Photo
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat | Enviro HP1200+800TC
checkpoint | Relevant Australian Standards Checked
label | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | Attach Photo
checkpoint | Moisture Content Test
label | Attach Photo
checkpoint | Apply primer using a brush or roller
label | Attach Photo
checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | Attach Photo
checkpoint | Mixing
checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint | Curing
checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | Attach Photo
checkpoint | Top Coat - Mix and Apply Enviro 800TC with brush or new roller Re-apply as required or determined by the Specification or broadcast sand (sand seeded) as required to Performance Requirements
label | Attach Photo
checkpoint | Dry Film Thickness Test
label | Attach Photo
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat | Enviro HP1200 + Geotextile Fabric
checkpoint | Relevant Australian Standards Checked
label | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | Attach Photo
checkpoint | Moisture Content Test
label | Attach Photo
checkpoint | Apply primer using a brush or roller
label | Attach Photo
checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | Attach Photo
checkpoint | Mixing
checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint | Curing
checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | Attach Photo
checkpoint | Secure Geotextile Fabric to the Waterproof Membrane. Ensure no debris is remaining or left in between the two materials.
label | Attach Photo
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat | Enviro 700X
checkpoint | Relevant Australian Standards Checked
text | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
label | Attach Photo
checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | Attach Photo
checkpoint | Moisture Content Test
label | Attach Photo
checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | Attach Photo
checkpoint | Apply primer using a brush or roller
label | Attach Photo
checkpoint | Membrane Application (1st coat) - Apply Enviro 700X using a brush or roller
checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint | Membrane Application (2nd coat) - Apply Enviro 700X using a brush or roller
checkpoint | Flood Testing (if required)
label | Attach Photo
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checkpoint | Relevant Australian Standards Checked
label | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | Attach Photo
checkpoint | Moisture Content Test
label | Attach Photo
checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | Attach Photo
checkpoint | Apply primer using a brush or roller
label | Attach Photo
checkpoint | Membrane Application (1st coat) - Apply Enviro Flex 2 Part using a brush or roller
checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint | Membrane Application (2nd coat) - Apply Enviro Flex 2 Part using a brush or roller
checkpoint | Flood Testing (if required)
label | Attach Photo
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat | Enviro Epoxy RC / Ultra Tuff
checkpoint | Relevant Australian Standards Checked
label | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | Attach Photo
checkpoint | Moisture Content Test
label | Attach Photo
checkpoint | Cutting - Make sure that adjoining ends of intersecting waterstop segments are cut extremely straight
label | Attach Photo
checkpoint | Apply primer using a brush or roller
label | Attach Photo
checkpoint | Epoxy Application (1st coat) - Apply Enviro Epoxy RC / Enviro Ultra Tuff with a brush, roller or spray
label | (If no aggregate is required, 1st coat of epoxy can be dilluted with 10% xylene
label | If aggregate is required, broadcast at correct coverage while 1st coat has been applied and is in it's wet state prior to curing
checkpoint | Epoxy Application (2nd Coat) - Apply Enviro Epoxy RC / Enviro Ultra Tuff with a brush, roller or spray
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured.
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat | Enviro Hydrostatic 1
checkpoint | Relevant Australian Standards Checked
label | Specification / Standard: AS4654.2-2012, Manufacturer’s Technical Data Sheet
checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | Attach Photo
checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | Attach Photo
checkpoint | Primer application - Lightly Spray areas to receive Hydrostatic 1
label | Attach Photo
checkpoint | Membrane Application (1st coat) - Mix Enviro Hydrostatic 1 thoroughly using a mechanical mixer. Apply first coat of Enviro Hydrostatic 1 by brush or roller Use Enviro Joint Band in floor-wall junctions and general movement joints
checkpoint | Membrane Application (2nd coat) - Mix Enviro Hydrostatic 1 thoroughly using a mechanical mixer. Apply second coat of Enviro Hydrostatic 1 by brush or roller
checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checkpoint | Relevant Australian Standards Checked
text | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | Attach Photo
checkpoint | Prepare Substrate. (moisture test if required) prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | Attach Photo
checkpoint | Apply primer (Enviro Shield/Enviro prime P2 or Enviro Epoxy B-LV) by brush/roller
label | Attach Photo
checkpoint | Caulking. Apply Enviro Flex FC junction fillets (where applicable)
label | Attach Photo
checkpoint | Mixing and Application. Mix Enviro 700X thoroughtly using mechanical mixer. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT.
label | Attach Photo
checkpoint | Testing. Flood test when applicable.
label | Attach Photo
checkpoint | First signoff. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder.
checkpoint | Check Screed (moisture test if required).
checkpoint | Apply primer (Enviro Shield/Enviro Shield or Prime WB by brush/roller
label | Attach Photo
checkpoint | Apply first coat of Enviro 200P Ultra with a brush or roller.
label | Attach Photo
checkpoint | Apply second coat of Enviro 200P Ultra with a brush or roller. Achieve 0.8mm WFT and 1.0mm DFT.
label | Attach Photo
checkpoint | Final signoff. Visually inspect and ensure adequately cured. Sign-off from builder and hand-over
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat | Enviro CSH
checkpoint | Relevant Australian Standards Checked
label | Specification / Standard: Manufacturer’s Technical Data Sheet
checkpoint | Check Substrate. (moisture test if oncrete not fully cured) and prepare surface using a scraper or grinder and vacuum or sweep residual debris.
checkpoint | Check for cracks/defect in concrete.
label | Attach Photo
checkpoint | Perform mechanical profiling / shot blasting to concrete
label | Visual
checkpoint | Spray Enviro CSH concrete surface hardener and moisture barrier, first application
label | Visual
checkpoint | Spray Enviro CSH concrete surface hardener and moisture barrier, second application
label | Visual
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
label | Attach Photo.
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat | Enviro 700X + 800TC
checkpoint | Relevant Australian Standards Checked
text | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | Attach Photo
checkpoint | Priming. Apply primer (Enviro Epoxy B-LV / Enviro Prime P2 / Enviro Shield) using a brush or roller. Allow primer to fully cure before proceeding with the application of Enviro 700X.
label | Attach Photo
checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X.
label | Attach Photo
checkpoint | Mixing and Application. Enviro 700X should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT. (2 coats).
label | Attach Photo
checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed Enviro 700X to ensure the membrane is not damaged.
checkpoint | Top Coat. Enviro 800 TC should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat.
label | Attach Photo
checkpoint | Testing. Carry Out DFT as required by the Supplier's Technical Advice
label | Attach Photo
checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat | Enviroseal WB + Aggregates
checkpoint | Relevant Australian Standards Checked
text | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint | Check Substrate/Work Area, Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | Attach Photo
checkpoint | Prepare Substrate. (moisture test if required) Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | Attach Photo
checkpoint | Apply primer by brush/roller
label | Attach Photo
checkpoint | Broadcast Aggregates (as required by the Performance Standards to be achieved) evenly across the applied membrane to ensure proper adhesion.
label | Attach Photo
checkpoint | Carry out Dry Film Thickness test Repair any defects found using patch and repair method specified in procedures.
label | Attach Photo
checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF