## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | S - S - Electrical - Cable Trays |  |  |  |  | Yes | S - S - Electrical - Cable Trays | 1cb6b401-13ab-41df-871f-82c6f93b3bfb
checkpoint-status |  |  | checkpoint | Tray ready to start
checkpoint-status |  |  | checkpoint | Building to correct Drawings (BIM model)
checkpoint-status |  |  | checkpoint | Correct Tray / Basket size used
checkpoint-status |  |  | checkpoint | Tray height correct of RL
checkpoint-status |  |  | checkpoint | Tray position as per BIM model measurements
checkpoint-status |  |  | checkpoint | Tray level
checkpoint-status |  |  | checkpoint | Tray locked down
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | First Fix |  |  |  |  | Yes | PRE - S - First Fix - Electrical | 32c93962-9caa-45bd-b041-04a07c91d8a8
checkpoint-status |  |  | checkpoint | Flushboxes at correct orientation and heights
checkpoint-status |  |  | checkpoint | Flushbox positioned correctly to suit kitchen and bathroom layouts
checkpoint-status |  |  | checkpoint | Metal flushboxes installed at Fire walls
checkpoint-status |  |  | checkpoint | Cables protected thru metal studs
checkpoint-status |  |  | checkpoint | Cables penetrating firewalls are supported 200mm from the wall
checkpoint-status |  |  | checkpoint | Kitchen island conduit installed.C/D/E 69,70,78,79,84,85,86,87.F75,F76,F77 & F78
checkpoint-status |  |  | checkpoint | Bathroom Reo earth bond installed and extended to DB
checkpoint-status |  |  | checkpoint | Check lighting installation against drawing
checkpoint-status |  |  | checkpoint | cables at correct locations (including kitchen island) , cables labelled, 2- way lighting correctly wired,
checkpoint-status |  |  | checkpoint | Check no downlight clashes with rondo or strong backs
checkpoint-status |  |  | checkpoint | Check ceiling fans prewired in bedrooms and lounge 2 x 1.5mm 2c+e at each location
checkpoint-status |  |  | checkpoint | Check power installation against drawing
checkpoint-status |  |  | checkpoint | cables at correct locations (including kitchen island) , cables labelled, Comms panel, HWC and Heat pump wired wired
checkpoint-status |  |  | checkpoint | Check laundry power has separately labelled cable for dryer
checkpoint-status |  |  | checkpoint | Check laundry extract fan supply in place
checkpoint-status |  |  | checkpoint | Check bathroom/WC extract fan supply (inc surface socket) in position with switch loops
checkpoint-status |  |  | checkpoint | Confirm E4M contractor has installed controller before gib ceiling installed
checkpoint-status |  |  | checkpoint | Check UFH prewired inc draw wire
checkpoint-status |  |  | checkpoint | Check towel rail nogs inc draw wire
checkpoint-status |  |  | checkpoint | Check switchboard back box install in correct location and all cables are labelled
checkpoint-status |  |  | checkpoint | Check circuits against DB schedule
checkpoint-status |  |  | checkpoint | Check submain and hot water supply are installed to DB
checkpoint-status |  |  | checkpoint | Check any client extras are prewired
checklist-flat |  |  | checklist | POST - S - Second Fix - Electrical |  |  |  |  | Yes | POST - S - Second Fix - Electrical | 682a3041-61c0-4e85-9705-2d379a00cd2c
checkpoint-status |  |  | checkpoint | All cover plates in place & fitted correctly and straight
checkpoint-status |  |  | checkpoint | All light fittings tight & secure and acceptable
checkpoint-status |  |  | checkpoint | All cables are tied up
checkpoint-status |  |  | checkpoint | Switch board fit off is completed and acceptable
checkpoint-status |  |  | checkpoint | Test sheet for insulation Resistance are completed and acceptable
checkpoint-status |  |  | checkpoint | Fixtures level & in place and acceptable
checklist-flat |  |  | checklist | S - S - Electrical - Distribution Boards |  |  |  |  | Yes | S - S - Electrical - Distribution Boards | 6b3d23d0-b9eb-4e2e-ad30-e956e9a31d99
checkpoint-status |  |  | checkpoint | DB details
text | 6dbfc516-a35d-5f9a-83f7-3eb07d0cc42b |  | textbox | Engineer
text | 86feec8a-3bd5-5b56-b411-de96fb2d4533 |  | textbox | Test Instrument
text | 6733d95a-a9b1-50b2-b3f0-9eabc2b311b6 |  | textbox | Cable Size/Type
text | 59018a64-e83b-5262-8399-7dce019f64ae |  | textbox | Main SW Size (A)
text | 9d9ec29e-d1af-5691-9e06-0412c962b8c0 |  | textbox | Submain Insulation Resistance
text | ea0e43b5-0305-5bf7-88f3-dd6a1dddb966 |  | textbox | Polarity
text | 052a38dc-732e-5d9f-85f6-8fee33d7d4bb |  | textbox | Main SW Voltage E-N (V)
text | 5c099c94-2e76-5d85-95fa-8fd7e0797a00 |  | textbox | Main SW Voltage R-E/N (V)
text | 9eab5ce2-259c-5da6-b305-73ac53a7623b |  | textbox | Main Sw Fault Loop Impedance (Z)
checkpoint-status |  |  | checkpoint | DB completed as per spec 100%
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | S - S - Electrical |  |  |  |  | Yes | S - S - Electrical | f1c4e1c3-78cb-49b2-bc67-852d877fc12c
checkpoint-group |  |  | section | First Fix
checkpoint-status |  |  | checkpoint | Handover Accepted/Nogs Installed and area clean and tidy before starting
checkpoint-status |  |  | checkpoint | Check all drawings, plan symbols are identified and wired for, raise any anomalies
checkpoint-status |  |  | checkpoint | Check wall and ceiling outlets and fitting positions against Architectural/ Electrical drawings and acceptable
checkpoint-status |  |  | checkpoint | Check for any purchaser variations/ client extras
checkpoint-status |  |  | checkpoint | Check all power & light feeds present and acceptable
checkpoint-status |  |  | checkpoint | Check loop wires installed and acceptable
checkpoint-status |  |  | checkpoint | All joinery plans are followed and correct position of outlets installed and acceptable
checkpoint-status |  |  | checkpoint | Flush boxes straight and level and acceptable
checkpoint-status |  |  | checkpoint | Fire rated flush boxes where required + fire pads installed and acceptable
checkpoint-status |  |  | checkpoint | Lights are marked out on plans or floor ready for cut out
checkpoint-status |  |  | checkpoint | Electrical First Fix completed and acceptable and area clean and tidy for next trade
checkpoint-group |  |  | section | Second Fix
checkpoint-status |  |  | checkpoint | All cover plates in place & fitted correctly and straight
checkpoint-status |  |  | checkpoint | All light fittings tight & secure and acceptable
checkpoint-status |  |  | checkpoint | All cables are tied up
checkpoint-status |  |  | checkpoint | Switch board fit off is completed and acceptable
checkpoint-status |  |  | checkpoint | Test sheet for insulation Resistance are completed and acceptable
checkpoint-status |  |  | checkpoint | Fixtures level & in place and acceptable
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | f6b470b5-b1b1-4a96-9d12-a717a3aeceed
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | 08feab34-3705-53e1-9d23-c7bd2d6fe5eb |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 5c978754-0794-529a-9348-da833b68ddad |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS