## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
12a9aa79-83c0-43ef-88ef-799d8b616a5e | checklist | TuSRAP Runway Pre-works ITP - Construction - 04 - REV C | itp | TuSRAP Runway Pre-works ITP - Construction - 04 - REV C
ad4fe333-e544-457e-97d1-fe4444fa80a6 | section | SECTION 5 – CONSTRUCTION ACTIVITY – TNZ F/01:1997 SPECIFICATION FOR EARTHWORKS CONSTRUCTION
0433a418-43b3-4a8c-84cb-e2bece382fac | checkpoint | 5.01.01 - Subgrade CBR Testing
864587fa-7aa5-5d55-be3e-8ad087955bc4 | note | Acceptance / Conformance Criteria - DCP-Scala tesing of subgrade to not less 1.0m below design subgrade level. The average inferred CBR shall not be less than 5% or any single value less than 3% at any depth within 500mm of final subgrade level.
cbdc5b64-3cff-5491-ba42-faadbf8fbc13 | note | Standard / Specification - NZS 4402:1986 - 6.5.2
e0bf9e76-df4e-57ca-bf83-9d35f79a8b1e | note | Verifying Document - DCP Report
251a7daa-f207-5fc4-91b7-cac857920b58 | note | Frequency - min 2 tests per lot
9767fe72-791e-59ba-9798-1e8181a11e80 | note | Verification Activity: Activity - R
4918dc09-be3d-5a0e-b881-0231cb14b549 | note | Verification Activity: By - PE
907a6f84-4f4b-58f0-b470-bd36d442cae1 | note | Comments / Closeout Details - CBR=5 OK
5453a2a4-ae45-5007-83af-193b64bd0a68 | note | ○ CBR>3 excavate 200mm and place geogrid
738813f3-62e9-5bb9-be5c-2d7945a846e8 | note | ○ CBR<3 notify Eng or as directed by Eng
53ecede2-6023-4cd7-8afa-31dd641c673a | checkpoint | 5.01.02 - Subgrade Compaction & Trimming
1de67f95-6ed6-5062-bdc4-6fd019b8ac81 | note | Acceptance / Conformance Criteria - Neatly trim and compact subgrade with appropriate equipment
58fee362-3ec7-515c-8792-0bb4969c49f5 | note | Standard / Specification - TNZ F/01: 1997 11.0
8e4c4995-b278-5abd-8d5e-f5286dac74bb | note | Verifying Document - DCP Report
d3025e05-873c-5380-b9e5-85673c5c3f7e | note | Frequency - min 2 tests per lot
0693e15c-8764-5c91-8ad8-98694b924d01 | note | Verification Activity: Activity - HP
a6f1c36f-9b16-5162-8fbc-345ad9c57b0e | note | Verification Activity: By - ENG
958a3047-48d6-5f1a-8f60-7de82e13127c | note | Comments / Closeout Details - Or as directed by Eng
311f3a99-4be7-417b-8e64-46d08906b28a | signoff | AUTHORITY HOLDPOINT
013e0ef1-ba30-45ab-a271-08e70cc478a0 | section | SECTION 6 – CONSTRUCTION ACTIVITY – TNZ B/02:2005 SPECIFICATION FOR CONSTRUCTION OF UNBOUND GRANULAR PAVEMENT LAYERS
aa46dbf9-5c74-4b54-af3c-19c4230ad281 | checkpoint | 6.01.01 - Material Placement
0b01ab0d-57c9-55be-9af6-7eff5cc439a9 | note | Acceptance / Conformance Criteria - The dimensional tolerances, uniformity, contamination and segregation shall be continuously monitored thoughout
fc9d4914-9bde-5b36-8299-c32ba856f4e3 | note | Standard / Specification - TNZ B/02: 2005 - 5.1
37f61782-543b-56d2-8f82-e6d4796081be | note | Verifying Document - Survey / Level Checks
f9bea438-84f8-5aec-a805-a886c6a0bb1a | note | Frequency - Continuous monitoring.
36071fd9-a359-51e8-b68a-4c57b1e5ca11 | note | Verification Activity: Activity - I
8919882a-4949-57ec-9240-b363fccd8394 | note | Verification Activity: By - SV / PE
610604f5-2bf8-46a3-bb2e-e37d48a16af3 | checkpoint | 6.01.02 - Sub-basecourse Pavement Layer Compaction
56c29852-9602-5e3c-848e-9bfbe1c8e39b | note | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
099ec4bf-1508-5695-9de4-b09a4b75ac4b | note | Standard / Specification - TNZ B/02: 2005 - 7.6
b5061f05-b0f0-5cd4-ad11-9e409d571ddc | note | Verifying Document - NDM Report
643038c8-aa1d-506d-b5c1-af81cec3bd40 | note | Frequency - Min 2 Tests per lot
96f4d0df-0f90-5179-8495-3ac86e329188 | note | Verification Activity: Activity - HP
c7e29e17-280b-520a-885f-f744445607a7 | note | Verification Activity: By - ENG
3df6e2cf-5c42-5cd0-9986-d0130cf68558 | note | Comments / Closeout Details - Or as directed by Eng
359861f9-dbc0-4312-a3b7-6d86a1fd9a63 | signoff | AUTHORITY HOLDPOINT
e7b5873d-913c-48cd-9a27-788853784f37 | checkpoint | 6.01.03 - Sub-basecourse Layer thickness.
ab7900af-88fa-568d-9b3f-b9ba332faac9 | note | Acceptance / Conformance Criteria - The Sub-basecourse shall be monitured for Layer thickness.
8edfebb5-703f-520f-9471-8ba5af4aab5c | note | Standard / Specification - TNZ B/02: 2005 - 7.5
dcc95455-107b-55c0-906b-73b470560a8f | note | Verifying Document - Survey / Level Checks
4c6395fc-9331-5330-b4db-4c6e8ec72974 | note | Frequency - Continuous monitoring.
0b31a53f-4bc4-59e9-af72-2f8818ddbedf | note | Verification Activity: Activity - W
0dad02c0-5fee-5a28-8d58-01c2c2bbeb42 | note | Verification Activity: By - SV / PE
5b17bb76-8f4b-4cb1-afb8-a12e51651d63 | checkpoint | 6.01.04 - Basecourse Pavement Layer Compaction
3c2b2d1c-2a82-56c8-b718-4d805d6f956a | note | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95
0c596d4e-c224-5ba3-b4b4-cac19fa3d21b | note | Standard / Specification - TNZ B/02: 2005 - 7.6
17de9f08-b7a3-5727-8747-6198068a737c | note | Verifying Document - NDM Report
37b533b5-ae84-593c-bcb2-9555336fdc22 | note | Frequency - Min 2 Tests per lot
4e4f40ce-b251-51bf-9d66-88ba28c8dcd3 | note | Verification Activity: Activity - HP
e683e7eb-dedc-55af-b5a8-4b9fe9c16bfc | note | Verification Activity: By - ENG
143e7331-1362-5b4f-b23e-624a72cda210 | note | Comments / Closeout Details - Or as directed by Eng
54c36219-6476-4bd8-8d16-40053b87abd5 | signoff | AUTHORITY HOLDPOINT
7bd9f691-02d3-4c3c-a132-1c988a00bba8 | checkpoint | 6.01.05 - Basecourse Layer thickness.
be6a84ac-9356-5fda-8f96-69d8498befbd | note | Acceptance / Conformance Criteria - The Basecourse shall be monitured for Layer thickness.
59818846-e355-5552-b41c-320bf5487321 | note | Standard / Specification - TNZ B/02: 2005 - 7.5
f36c2b98-26a8-5a2e-9968-81b7c04c199c | note | Verifying Document - Survey / Level Checks
d9fe6af2-8050-5436-bb44-05ff7bbc6d61 | note | Frequency - Continuous monitoring.
94ed5a82-f0df-5e3f-a736-aa37c5acc207 | note | Verification Activity: Activity - W
0ba63824-40f9-53d0-92dc-72c973046ec7 | note | Verification Activity: By - SV / PE
5340f595-ddd3-4d57-a01f-568a4de08c72 | checkpoint | 6.01.06 - Surface Shape
daec8a74-53d1-53e6-a2d1-3e50cf248463 | note | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
70f1ce0b-3069-5f0a-9fba-f84856991644 | note | Standard / Specification - TNZ B/02: 2005 - 7.7
e32745c6-6945-5d88-a077-a164c17723ea | note | Verifying Document - Survey / Straight edge Report
dc8afe70-4324-5afb-93f1-9566b02cf893 | note | Frequency - Prior to sealing
6bb118bd-0ae8-59ab-ae19-babae4d1b336 | note | Verification Activity: Activity - I
3644e366-aeda-5ffa-b7ff-456817cd1d65 | note | Verification Activity: By - SV / PE
d64b815e-9d26-445f-b914-21dcf78e38bf | checkpoint | 6.01.07 - Holding Water
84dbef0d-5cda-5843-94b4-baff19e9e2a3 | note | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
83fb723e-be50-5d4b-bb94-f1f63b5988bd | note | Standard / Specification - TNZ B/02: 2005 - 7.7
6196c767-2cf8-5346-87a1-62a5a439dde5 | note | Verifying Document - Survey
f22cfeb7-42cb-5ddc-949c-2b0ea448d511 | note | Frequency - Prior to sealing
9a1accf3-8991-5dad-98fd-25e51429de31 | note | Verification Activity: Activity - I
e3cfff18-bfbc-544a-b84a-6f3ee4a1e77c | note | Verification Activity: By - SV / PE
796b1379-539e-407e-80a7-ea9d6bed5744 | checkpoint | 6.01.08 - Surface Finish post sweeping
339db2ef-1f8b-53bd-b21d-b1b34aa3737a | note | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
7e870358-4622-5a18-b5dd-6b24bd18e4e0 | note | Standard / Specification - TNZ B/02: 2005 - 7.8
fc48552e-b400-5652-aee3-0ab6832ef085 | note | Verifying Document - Photos
d25c871b-b57e-5dee-b4df-c78762145c55 | note | Frequency - Prior to sealing
d1742464-0b5e-54cf-b68f-6ca396adfc0c | note | Verification Activity: Activity - R
e9e71a42-63bc-54e5-a3ec-29ab66ad5156 | note | Verification Activity: By - PE
6686bb87-4e88-4276-8764-458594c4e960 | checkpoint | 6.01.09 - Pre-surfacing Requirements
acfebde1-fa64-5593-b0a5-690b0d015163 | note | Acceptance / Conformance Criteria - Surface to be dry and clean
43debf96-d372-5d8b-ae28-7af1e64916a6 | note | Standard / Specification - QPR2000 Manufacturer's Requirements
d4ff0bb9-953a-57a2-b16f-0d476d7a366d | note | Verifying Document - Photos
3f43b6af-ec4a-5924-8a8b-9af6b078fb15 | note | Frequency - Prior to sealing
9a646daa-349a-5d79-899f-8c7eb94b62d0 | note | Verification Activity: Activity - R
a8e680b5-08f7-5aca-afdd-ffc867511b28 | note | Verification Activity: By - PE
0e03b584-8f71-40dc-ae73-723696f0fa81 | checkpoint | 6.01.10 - Surfacing
fdcad890-ea94-5790-aaa8-3bdc83719708 | note | Acceptance / Conformance Criteria - Place QPR2000 in layers not exceeding 50mm thickness to 10-15mm above existing asphalt pavement top surface and compact with appropriate comapction equipment
58875e94-f2b8-5ad3-b022-a004b8cc670a | note | Standard / Specification - QPR2000 Manufacturer's Requirements
0b4e1792-3106-5495-ae03-4e4f787aa652 | note | Verifying Document - Photos
4612cf83-633b-59e6-b280-bcda43aab4eb | note | Frequency - Post Sealing
68f1f8c1-ff65-5279-bd9d-96d2b5be76f7 | note | Verification Activity: Activity - R
d1770bc8-7aa2-53d1-b870-4039bd04f46a | note | Verification Activity: By - PE
91d5f2d2-0dde-4479-8c0a-51f29d561337 | checklist | TuSRAP Runway Pre-works ITP - Material Tests - 04 - REV C | itp | TuSRAP Runway Pre-works ITP - Material Tests - 04 - REV C
15ebe88d-7892-4ffd-b539-ee9f051554c7 | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
69427b01-7a67-462d-8c87-bd058ea0f7ce | checkpoint | 4.01.01 - Source Property Tests and Sampling
c92b3b48-5812-55fb-a088-872ad5c2772d | note | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
b19ab540-ad10-5621-8eab-0bd7097b2c47 | note | Standard / Specification - TNZ M/4: 2024 - 4, NZS 4407 : 1991, NZS 4402 : 1986
cddcb988-8f9b-5b46-813e-45b65335148e | note | Verifying Document - IANZ Lab Reports
07288829-5b58-5db3-9bbb-414b76f93065 | note | Frequency - 10,000m3
7f7be884-9d46-51ca-aa82-01523529be1c | note | Verification Activity: Activity - HP
28a0abc9-7686-5642-8062-00529bb8cbb6 | note | Verification Activity: By - ENG
69d2e17d-5019-422f-939d-167144316561 | signoff | AUTHORITY HOLDPOINT
ced94e3e-7c5d-4f3e-ac7e-ac1bed8636fd | checkpoint | 4.1.02 - Production Property Test Sampling
0dfe6569-14ac-5f8e-9cd9-6fe6cce6e3b6 | note | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine as per M/4 Figure 1, Broken Face Content, and WET Particle Size Distribution Limits and Shape Control.
9c7fc5b5-c1b5-5d22-847a-28e0ac348562 | note | Standard / Specification - TNZ M/4: 2024 - 5, NZS 4407 : 1991
93da7a28-e958-5bad-acd6-abecfecde7df | note | Verifying Document - IANZ Lab Reports
0947792d-4ec4-5b61-80b7-6f1d05dc36e9 | note | Verification Activity: Activity - HP
1eff4b62-eb3a-573b-bd9e-2c0ff2a846b5 | note | Verification Activity: By - ENG
292f52ee-3b93-4da4-8936-ee4213947ba3 | signoff | AUTHORITY HOLDPOINT
7b360e5f-4dfa-45c0-bad0-f0b52602d807 | checkpoint | 4.01 - Testing for Layer Compaction - MDD
403f6371-d2fa-528b-b4a0-b7c5bfb7fad9 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
38061b35-4ca4-57d9-a6cb-8e468c1a9a6f | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
a11b1f62-875c-5522-9c8b-89814428ef70 | note | Verifying Document - IANZ Lab Reports
cff61491-3235-5f5f-b470-8dfde49c959d | note | Frequency - 5,000m2
598c2d29-91c4-5639-aa83-3afbc2c1c10f | note | Verification Activity: Activity - R
bb8f14fb-524a-5834-9cde-7075ed0503bd | note | Verification Activity: By - PE
8a84f793-dfdf-59da-ba11-4ae96e8290ec | note | Comments / Closeout Details - 5000m3 is typically used where source is consistent
3a3d24cc-d054-4dbc-bb36-636ddabd9953 | checkpoint | 4.02.01 - Source Property Tests and Sampling
a94017dd-a069-524b-bf9b-0d64b15016fc | note | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, and California Bearing Ratio.
c0488604-00a9-5913-9496-3466ba415b59 | note | Standard / Specification - TNZ M/3 Notes : 1986, TNZ M/4: 2024, NZS 4407 : 1991, NZS 4402 : 1986
704ee7d8-2aa5-58e2-a38e-0720a69a1e7c | note | Verifying Document - IANZ Lab Reports
40ec720d-d951-5fd9-97f0-5e6169bcfeb7 | note | Frequency - 10,000m3
bb83112f-ba90-5a9f-a9f3-7bc97d6f1d68 | note | Verification Activity: Activity - HP
94b804d3-9eff-5cf5-b4c1-d46f8a32c7fc | note | Verification Activity: By - ENG
0fcaee61-5662-51d1-88d5-0808af87dd2b | note | Comments / Closeout Details - M/3 is a guide not a specification. Refer to Contract Specification
1815e1dc-3349-4746-be80-0bcd4d7e72cc | signoff | AUTHORITY HOLDPOINT
44a49ff4-23c4-4ffe-af7b-864bdce35062 | checkpoint | 4.02.02 - Production Property Test Sampling
deb0d003-5e92-5393-8573-20735db5e50f | note | Acceptance / Conformance Criteria - The basecourse aggregate shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Permeability, and Particle Size Distribution.
ea4d24be-0c89-573d-b0a1-d38fa7d010d5 | note | Standard / Specification - TNZ M/3 Notes : 1986, TNZ M/4: 2024, NZS 4407 : 1991
7645c07a-d3db-586f-859b-6a9fd055d0c4 | note | Verifying Document - IANZ Lab Reports
8528a830-bb25-5dd5-8286-da204013f7ea | note | Verification Activity: Activity - HP
f9819894-554b-5931-a8e7-77b46e026295 | note | Verification Activity: By - ENG
4452e3d0-9ae4-59af-99f7-1bc55075b35c | note | Comments / Closeout Details - M/3 is a guide not a specification. Refer to Contract Specification. Refer to M/4 Figure 1 for Fines testing hierarchy
e9983680-2349-4ff5-8205-a163910abc9f | signoff | AUTHORITY HOLDPOINT
0556c749-608e-4480-92bb-d0e51b4cdbb0 | checkpoint | 4.02.03 - Testing for Layer Compaction - MDD
08968754-ae9c-5177-868a-0749527f4045 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
d25aaf43-38da-5ef0-97e2-8b4bdabafef6 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
f2477bc0-06a9-5874-bdb7-2c4e50622258 | note | Verifying Document - IANZ Lab Reports
a0a1999d-4119-5405-850a-5682e12f98e0 | note | Frequency - 5,000m2
5be98e23-3713-52dc-a112-e1f2deff767f | note | Verification Activity: Activity - R
152c4717-b148-523e-82b1-8f98839d13a7 | note | Verification Activity: By - PE
589b2d57-a4fc-5496-905f-4edb8095b59d | note | Comments / Closeout Details - 5000m3 is typically used where source is consistent
76699059-5240-4015-b7d5-dee25c271e4f | checklist | TuSRAP Runway Pre-works ITP - Post Construction - 04 - REV C | itp | TuSRAP Runway Pre-works ITP - Post Construction - 04 - REV C
56199ba2-18e2-4c0d-9c1c-16f3bc657c03 | section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
39174e2b-9464-4e94-b424-d9bc82f93228 | checkpoint | 7.01.01 - Construction Record Compilation
105a7cda-42b0-5dcb-9ffe-b58c14271317 | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
5056e4a3-4450-51e9-a0db-2d5bda37dea8 | note | Standard / Specification - Downer
ea133edb-af22-5b8b-a0ba-9c892c46d1d3 | note | Verifying Document - Records
360dee64-55a6-59d8-9c7c-076bef296ee9 | note | Frequency - Post construction
d561fc80-33d5-5a5f-839d-4c8aa6a643f0 | note | Verification Activity: Activity - R
c138dce7-f5b3-577c-a674-6123985eb536 | note | Verification Activity: By - SE
ea60b3f5-a43d-4e1d-bd4e-a147081a435e | checkpoint | 7.01.02 - Survey Records
8b5ec411-e492-5cae-a765-63f968042edd | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
8734b9b6-8ecc-530d-ad2c-0704b29c2ae4 | note | Standard / Specification - Downer
16fad128-92cf-5baf-8f89-cec0ecb7df06 | note | Verifying Document - Records
11ee2d76-d61b-53af-a391-2f4d0928fb04 | note | Frequency - Post construction
28a05d40-1ce5-5201-a6f0-336b9a668f3f | note | Verification Activity: Activity - R
4fce123b-b5e7-5666-81d8-9355ba3c3941 | note | Verification Activity: By - SV
6471eb62-b80a-41e5-9c58-8bb6462deb74 | checkpoint | 7.01.03 - Redline Drawings
2d157d38-f0a8-56aa-aee0-dc138b2cf689 | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
ba8d5eb3-30c6-527f-946d-cb21e6f2a516 | note | Standard / Specification - Downer
5e1608d5-b3fa-5d42-b390-b71fccc85868 | note | Verifying Document - Redlines
e6fc62b5-0ef1-566c-b124-82fdf598e490 | note | Frequency - Post construction
62d7c100-591e-59a9-af5e-762e7dbe4de7 | note | Verification Activity: Activity - R
00e2cba2-3c8d-5fe4-b524-a6a7734cf9ea | note | Verification Activity: By - PE
a22773f4-aa2c-473b-a0a0-a7f58a0a5c1c | checkpoint | 7.01.04 - Defect, Snag and Punch List
ed419730-aca8-56e7-97d9-34f1187a18a4 | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
bcda02da-fc88-51ec-87ca-3637d1888d09 | note | Standard / Specification - Downer
74b73af5-85f6-5953-bb20-23db074c28e0 | note | Verifying Document - Register
6e05af19-9659-539b-bd00-cfe8531a09d2 | note | Frequency - Post construction
45e9a188-4d78-5edf-a73b-ceabbad317cd | note | Verification Activity: Activity - R
bd7a04c2-d5f5-56ed-979f-e17e1d11b4e2 | note | Verification Activity: By - PE