## MFU-FH-ITP-0010
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-009
2024-10-23
Client: | DTP |  | Construction Process: | Subsoil Drainage |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Howitt Avenue Traffic Signals |  |  |  |  | Name: | Justin Barnes | Name: | Brett Walker |  | Name: | Brett Walker
Contract No: | DOT34605 |  | Specifications: | VicRoads Specifications Section 702
|  |  | Structure / Component: | Subsoil Drainage
|  |  | Location: Wy Yung |  |  | Date : | 2024-10-23 | Date : | 2024-10-23 |  | Date : | 2024-10-23
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Induction |  | Prior to Commencing | All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site | Inductions Register | Document review | Site induction signed. | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken |  | Prior to commencing | All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS | Health and Safety Co-Ordination Plan | Document Review | SWMS(s) signed | HP | Site Engineer, Site Foreman & Superintendent
1.3 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.4 | Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | IFC Drawings CEMP CHMP | Document review & Site inspection | Signed ITP | IP | Site Engineer | N/A
1.5 | Excavation Permit issued |  | Prior to Commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review | Excavation Permit # | IP | Site Engineer | N/A |  | N/A
1.6 | Materials |  | Prior to Commencing | All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2 | Project Spec. Cl.3030.05(a) | Document review | Signed ITP | IP | Site Engineer | N/A |  | N/A
2 | Drainage Works
2.1 | Excavation of Trench |  | When placing drainage | The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed. Perforated Pipe Crown level to be minimum 200mm below subgrade level. Grade of trench to be not flatter than 1 in 250. | VicRoads Spec. Cl.702.08 VicRoads Spec. Cl.702.09(a)(b) | Site inspection | Signed ITP | HP | Superintendent / Site Engineer |  |  | N/A
2.2 | Use of Geotextile |  | When placing drainage | Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile. | VicRoads Spec. Cl.702.08 | Site inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.3 | Installation of Subsoil Drainage |  | When placing drainage | Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level. Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe | VicRoads Spec. Cl.702.09(d) | Site inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.4 | Placing of Granular Filter Material |  | When placing drainage | Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent. | VicRoads Spec. Cl.702.09(g) | Document Review | Signed ITP | HP | Superintendent / Site Engineer |  |  | N/A
2.5 | Flushing Test |  | After drainage is placed | Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction | VicRoads Spec. Cl.702.09(h) | Site inspection | Signed ITP/ Record of flushing tests | WP | Superintendent / Site Engineer |  |  | N/A
2.6 | CCTV |  | After drainage is placed | All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects. | VicRoads Spec. Cl.702.09(i) | Site inspection | Signed ITP/ Record of flushing tests | HP | Superintendent / Site Engineer |  |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent