## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-001 - Clearing & Grubbing | itp |  |  |  |  | ITP-001 - Clearing & Grubbing
section | 1 - Preliminary Works
checkpoint | 1.1 - Check current drawings are used on site for works
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Flora & Fauna
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: A qualified Ecologist is or trained wildlife handler to be present during removal of native vegetation; has provided advice on alternative fauna habitat sites if applicable and be present on the site during any relocation works if required.
label | REFERENCE DOCUMENTS: Construction Environmental Management Plan Appendix 2
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.5 - Permit to distrurb flora & fauna
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: VicRoads has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
label | REFERENCE DOCUMENTS: Condition Plans endorsement
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Clear & Grub
checkpoint | 2.1 - Define work area
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
label | REFERENCE DOCUMENTS: 201.1
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Cultural Heritage and Areas of Significance
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | ○ Works are to be suspended immediately and Cultural Heritage representatives (BLCAC) are to be notified, if any items of significance are discovered or identified during construction.
label | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | REFERENCE DOCUMENTS: CHMP
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Joint Inspection to Mark vegetation or habitat to be removed
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the project Arborist and project Ecologist
label | REFERENCE DOCUMENTS: Drawings, CEMP Tree Management Plan 176.I1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Felling of Trees
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared
label | REFERENCE DOCUMENTS: 201.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.5 - Backfill holes
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted
label | REFERENCE DOCUMENTS: 201.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.6 - Dispose of Trees and vegetation
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
label | ○ Noxious weeds shall not be mulched.
label | REFERENCE DOCUMENTS: 201.07
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Dispose of concrete, bituminous and other recyclable materials.
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
label | REFERENCE DOCUMENTS: 201.07
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Stripping of topsoil
label | FREQUENCY: Prior and after commencement of any ground disturbing activities
label | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation.
label | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil, and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
label | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.9 - Removal of abandoned services
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Pits which are no longer required shall be removed or broken back to a depth not less than 0.3 m below the finished surface of the subgrade. Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.10 - Clearing of Trees and Vegetation
label | FREQUENCY: During clearin works
label | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified limits of work.
label | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.11 - Grubbing of vegetation
label | FREQUENCY: Prior and after commencement of any ground disturbing activities
label | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment.
label | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
label | REFERENCE DOCUMENTS: CEMP VicRoads Spec. Cl.201.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-002 - Construction of Underground Stormwater Drainage | itp |  |  |  |  | ITP-002 - Construction of Underground Stormwater Drainage
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Precast Materials Inspection
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
label | REFERENCE DOCUMENTS: 701.04b
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.4 - Precast Pipe Compliance
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
label | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
label | REFERENCE DOCUMENTS: VicRoads Spec.
label | ○ Cl.619
label | ○ Cl. 701.04(a)
label | ○ Cl. 701.04(b)(i)
label | ○ Cl. 705.04(d)
label | ○ Cl. 705.11
label | ○ AS4058
label | ○ AS4680
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.5 - Bedding material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | ○ 100% passing 19mm sieve.
label | ○ 5%-40% passing 0.075mm.
label | ○ PI = 20 max.
label | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.6 - Backfill material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | ○ 100% passing 37.5mm sieve.
label | ○ 5%-40% passing 0.075mm sieve.
label | ○ PI = 20 max.
label | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.7 - Mortar material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
label | REFERENCE DOCUMENTS: 610.33
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Set out drainage
label | FREQUENCY: Prior to excavation
label | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | REFERENCE DOCUMENTS: Drawings 701.10
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Excavation (pipes)
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical.
label | Depth of trench:
label | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
label | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
label | REFERENCE DOCUMENTS: 701.15 Table 701.151
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
checkpoint | 2.4 - Compact base of trench
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.5 - Place bedding material & compact
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
label | ○ 100mm under pipes.
label | ○ 80mm (earth foundation)
label | ○ 150mm (rock foundation)
label | REFERENCE DOCUMENTS: 701.19
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Place pipes
label | FREQUENCY: Each Line/Pit
label | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
label | REFERENCE DOCUMENTS: Drawings 701.17
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Jointing pipe sections
label | FREQUENCY: Each Line
label | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
label | REFERENCE DOCUMENTS: 701.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Place & compact backfill material over pipes
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
label | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
label | ○ Loose layer thickness <= 150mm.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.14, 701.15
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.9 - Repairs to damaged pipes
label | FREQUENCY: Each damaged pipe
label | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
label | ○ All repair procedures undertaken in accordance with Cl 701.25
label | REFERENCE DOCUMENTS: 701.31
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing & Completion
checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
label | FREQUENCY: as required/requested
label | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort.
label | ○ Bedding material shall be compacted using a compaction plated to refusal.
label | REFERENCE DOCUMENTS: 701.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP
checklist | ITP-009 - Subsoil Drainage | itp |  |  |  |  | ITP-009 - Subsoil Drainage
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP
label | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Materials
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2
label | REFERENCE DOCUMENTS: Project Spec. Cl.3030.05(a)
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Drainage Works
checkpoint | 2.1 - Excavation of Trench
label | FREQUENCY: When placing drainage
label | ACCEPTANCE CRITERIA: The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed.
label | ○ Perforated Pipe Crown level to be minimum 200mm below subgrade level.
label | ○ Grade of trench to be not flatter than 1 in 250.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08, VicRoads Spec. Cl.702.09(a)(b)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Use of Geotextile
label | FREQUENCY: When placing drainage
label | ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Installation of Subsoil Drainage
label | FREQUENCY: When placing drainage
label | ACCEPTANCE CRITERIA: Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level.
label | ○ Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(d)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Placing of Granular Filter Material
label | FREQUENCY: When placing drainage
label | ACCEPTANCE CRITERIA: Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(g)
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Flushing Test
label | FREQUENCY: After drainage is placed
label | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(h)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | WP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | 2.6 - CCTV
label | FREQUENCY: After drainage is placed
label | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(i)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP