## Lot Register
NAL Airport Apron Upgrade
Lot No | Activity | Actual Location | Inspection and Test Plan Number | LOT DATE OPENED | LOT DATE CLOSED | Submission Status | Comments
Work Area
1.X.X | Erosion & Sediment Control
1.1.X | Stage 1-6
1.1.1 | Erosion & Sediment Control
2.X.X | Pavement Construction
2.1.X | Stage 1
2.1.1 | Subgrade
2.1.2 | Subbase
2.1.3 | Basecourse
2.1.4 | Surfacing
2.2.X | Stage 2
2.2.1 | Subgrade
2.2.2 | Subbase
2.2.3 | Basecourse
2.2.4 | Surfacing
2.3.X | Stage 3
2.3.1 | Subgrade
2.3.2 | Subbase
2.3.3 | Basecourse
2.3.4 | Surfacing
2.4.X | Stage 4
2.4.1 | Subgrade
2.4.2 | Subbase
2.4.3 | Basecourse
2.4.4 | Surfacing
2.5.X | Stage 5
2.5.1 | Subgrade
2.5.2 | Subbase
2.5.3 | Basecourse
2.5.4 | Surfacing
2.6.X | Stage 6
2.6.1 | Subgrade
2.6.2 | Subbase
2.6.3 | Basecourse
2.6.4 | Surfacing
3.X.X | Drainage
3.1.X | Stage 1
3.1.1 | Drainage
3.1.2 | Utilities
3.2.X | Stage 2
3.2.1 | Stage 2 Drainage
3.3.X | Stage 3
3.3.1 | Stage 3 Drainage
3.4.X | Stage 4
3.4.1 | Stage 4 Drainage
3.5.X | Stage 5
3.5.1 | Stage 5 Drainage
3.6.X | Stage 6
3.6.1 | Stage 6 Drainage
3.6.2 | Stage 6 Utilities
4.X.X | MISC
4.1.X | Stage 1-6
4.1.1 | Road Marking
4.1.2 | Crack Sealing
4.1.3 | Ground Lighting
4.1.4 | Landscaping

## ITP Register
ITP | Status | Date | Comment
Subgrade | Draft | 2024-10-22
Subbase | Draft | 2024-10-22
Basecourse | Draft | 2024-10-22
Surfacing | Draft | 2024-10-22
Drainage | Draft | 2024-10-22
Utilities | Draft | 2024-10-22
Erosion & Sediment Control | Draft | 2024-10-22
Compliance Record | Draft | 2024-10-22

## Checksheets
Checksheet | Status | Date | Comment
Drainage Line record | Draft | 2024-10-22
Scala/clegg Test sheet | Draft | 2024-10-22