## Footpath & KC
ITP - Aviemore
Enabling Works - Footpath, Kerb and Channel, Pram Crossing
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Every site | Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
Kerb and Channel
2A | Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Every 10m for Scalar | Subgrade CBR > 5 | In process Inspection | Scalar Sheet | Site Engineer
2B | Kerb & Channel | QA FORM | TDM Technical Standards - KC0001 | Every 10m for Clegg | Kerb & Channel to be laid using precast hand-laid on compacted GAP40. Thickness - 100mm on Footpath / 300mm on roads CIV > 25 | In process Inspection | Clegg Sheet Photos | Site Engineer
2C | Kerb Setout | QA FORM | TDM Technical Standards - KC0001 | Every site | Site Setout as per construction drawings and heights and falls verified | Mandatory HOLD POINT - | K&C Pre-pour Checklist | Site Engineer / MSQA
2D | Channel Material | QA FORM | TDM Technical Standards - KC0001 | Every site | Concrete Strength 20MPa @28 Days Trowel Finish | In process Inspection | Concrete Docket | Site Engineer
2E | Channel Level | QA FORM | TDM Technical Standards - KC0001 | Every site | Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level | In process Inspection | Photos | Site Engineer
Footpath
3A | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m intervals | Subgrade CBR > 3 | In process Inspection | Scalar Sheet | Site Engineer
3B | Concrete Footpaths | QA FORM | TDM Technical Standards - FP0001 | 10m intervals | Basecourse - 100mm min. thickness Clegg CIV > 12 | In process Inspection | Clegg Sheet Photos | Site Engineer
3C | Footpath Setout | QA FORM | TDM Technical Standards - FP0001 | 10m intervals | Site set out as per construction drawings and heights and falls verified | Mandatory HOLD POINT - | Pre-pour Concrete Sheet Photos | Site Engineer / MSQA
3D | Footpath finishing | QA FORM | TDM Technical Standards - FP0001 | Every site | Concrete Strength 20 MPa @ 28 days. FP = 4kg/m3 black oxide with broom finish Cycle Lane = 8kg/m3 black oxide with broom finish Standard Footpath - 100mm thick Heavy Duty - 150mm thick | In process Inspection | Concrete Docket Photos | Site Engineer
4 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | 10m Intervals | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones. | In process Inspection | Photos | Site Engineer
5 | Service Covers and Street Furniture | Visual | AT Contract Specification 14000 | Every site | Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works. | In process Inspection | Nil | Site Engineer
6A | Tactiles /Pram crossing | Visual | TDM Technical Standards - FP006 TDM Technical Standards - FP0010 | Every site | Tactiles set out must be agreed with MSQA Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing. Warning TGSI tiles should have 100mm concrete slab underneath | Mandatory HOLD POINT - | Photos | Site Engineer / MSQA
6B | Tactile Material | Visual | NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every site | Tactile to be yellow concrete paver slab type - 300x300mmx60mm | In process Inspection | Photos | Site Engineer
6C | Tactile | Visual | AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY | Every site | Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep. | In process Inspection | Photos | Site Engineer
As-builts
7 | As built information | Drawings | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | As-Built drawings | In Process Inspection | As-built records | Supervisor and Engineer
8 | RAMM DATA | RAMM DATA SHEET | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | RAMM SHEET | In Process Inspection | As-built records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Daniel Tat | Initial |  |  | Date:
Approving Delegate |  | Daeyoung Jeong | Initial |  |  | Date:

## Traffic Islands
ITP - Aviemore
Traffic Island
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Materials
1 | Kerb | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Every site | Kerb to be laid using precast hand-laid | In process Inspection | FH Concrete QA sheet Photos | Site Engineer
Construction
2 | Survey Setout | Survey | Setout Kerb Alignment required to construct to design | Prior to commencement. | Survey | In process Inspection | Survey Receipt. | Site Engineer
3A | In-Situ Concrete Island | QA FORM | TDM Technical Standards - IS0001 | Each Site | Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm CIV > 25 | In process Inspection | Photos | Site Engineer
3B | Stick On Concrete Island | QA FORM | TDM Technical Standards - IS0002 | Each Site | Bonding Agent to be applied on existing surface Mountable Kerbs laid flat to be sticked on to the existing road using Epoxy Mortar Mix. Gaps between kerbs shall be no larger that 10mm | In process Inspection | Photos | Site Engineer
4 | Concrete Infill | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | 150/180mm depth of 20MPa Concrete Surface finish to confirm with Engineer's Rep | In process Inspection | FH Concrete QA sheet. Concrete Delivery Dockets | Site Engineer
As-builts
5 | As built information | Drawings | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | As built drawings | In Process Inspection | As-built records | Supervisor and Engineer
6 | RAMM DATA | RAMM DATA SHEET | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | RAMM SHEET | In Process Inspection | As-built records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  |  | Initial |  |  | Date:
Approving Delegate |  |  | Initial |  |  | Date:

## Roundabout
ITP - Aviemore
Traffic Island
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Materials
1 | Kerb | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Every site | Kerb to be laid using precast hand-laid | In process Inspection | FH Concrete QA sheet Photos | Site Engineer
Construction
1 | Survey Setout | Survey | Roundabout shape and heights to be set-out by the surveyor | Prior to commencement. | Survey | In process Inspection | Survey Receipt. | Site Engineer
2 | Roundabout Apron | QA FORM | Construction Drawings | Every site | Chamfer shape to be handformed in-situ concrete pour with with two layers of 65 mesh with minimum 50mm cover. 200mm thickness with broom finish NO OXIDE CIV > 25 | In process Inspection | FH Concrete QA sheet Photos | Site Engineer
3A | Precast Kerb & Nib | QA FORM | TDM Technical Standards - IS0001 | Each Site | Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm CIV > 25 | In process Inspection | Photos | Site Engineer
4 | Concrete Infill | QA FORM | TDM Technical Standards - IS0001 & IS0002 | Each Site | 180mm depth of 20MPa Concrete 6kg/m3 red oxide broom finish On minimum 150mm of GAP65 CIV >25 | In process Inspection | FH Concrete QA sheet. Concrete Delivery Dockets | Site Engineer
As-builts
5 | As built information | Drawings | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | As built drawings | In Process Inspection | As-built records | Supervisor and Engineer
6 | RAMM DATA | RAMM DATA SHEET | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP. | Every Site | RAMM SHEET | In Process Inspection | As-built records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  |  | Initial |  |  | Date:
Approving Delegate |  |  | Initial |  |  | Date:

## Commerical VX
ITP - Aviemore
Enabling Works - Commercial Vehicle Crossing
Number | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | Hold Point | Records | Onsite Responsibility
Site Set Out
1 | Site Set out | Surveyor | Surveyor | Every site | Site set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable. | Mandatory HOLD POINT - | Onsite records/photos | Site Engineer
Commercial VX
2A | Commerical VX | QA FORM | TDM Technical Standards - VX0203 | Each VX | Subgrade CBR > 3 | In process Inspection | Scalar Sheet | Site Engineer
2B | Commerical VX | QA FORM | TDM Technical Standards - VX0203 VX Consents as provided by Pak 'N' Save | 4 Cleggs per VX | VX to be laid using on compacted 100mm min GAP40. CIV > 12 | In process Inspection | Clegg Sheet Photos | Site Engineer
2C | Commerical VX | QA FORM | TDM Technical Standards - VX0203 VX Consents as provided by Pak 'N' Save | Every VX | Site set out as per construction drawings and heights and falls verified | Mandatory HOLD POINT - | Concrete Pre-pour Checklist | Site Engineer / MSQA + AT Compliance Team
| VX Material | QA FORM | TDM Technical Standards - VX0203 VX Consents as provided by Pak 'N' Save | Every VX | 661 Mesh Required and R6 Stirups and 4 D-12 bars | In process Inspection | Photos | Site Engineer
2D | VX Material | QA FORM | TDM Technical Standards - VX0203 VX Consents as provided by Pak 'N' Save | Every VX | Concrete Strength 20MPa @28 Days Thickness - 200mm No black oxide with broom finish as per VX consents | In process Inspection | Concrete Docket | Site Engineer
2E | Commerical VX | QA FORM | TDM Technical Standards - VX0203 VX Consents as provided by Pak 'N' Save | Every VX | Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg | In process Inspection | Photos | Site Engineer
2D | Commerical VX | QA FORM | TDM Technical Standards - VX0203 VX Consents as provided by Pak 'N' Save | Every VX | Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg 1m reinstatement on carriageway | In process Inspection | Photos | Site Engineer
3 | Grass Berms | Visual | ATCOP Section 12 Footpaths and Pedestrian Facilities | 10m Intervals | 100mm thick layer of compacted approved quality topsoil, free of weeds and stones. | In process Inspection | Photos | Site Engineer
4 | Final Inspection | Visual | VX Consent | Each VX | Final Inspection | NA | Photos | AT Complaince Team
As-builts
5 | As built information | Drawings | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP | Every Site | As-Built drawings | In Process Inspection | As-built records | Supervisor and Engineer
6 | RAMM DATA | RAMM DATA SHEET | As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP | Every Site | RAMM SHEET | In Process Inspection | As-built records | Supervisor and Engineer
ITP APPROVAL
Prepared By |  | Daniel Tat | Initial |  |  | Date:
Approving Delegate |  | Daeyoung Jeong | Initial |  |  | Date:

## Stormwater Drainage
|  |  |  | ITP - Aviemore |  |  | Approved |  | Signature
|  |  |  | Contract Name: | Aviemore Roundabout |  | FH Engineer |  | Divnish Chand
|  |  |  | Procedure: | Stormwater Drainage |  | FH Quality Manager |  | Daeyoung Jeong
Inspection & Test Plan / Checklist
Job No: 2095332
Detailed Location: Aviemore and Highland Park Drive Intersection
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method (Submission, Visual Inspection, Testing, Measurement, Review) | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits & Services (1) | H | Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space) | Prior to any construction commencing | Document Review | Relevant Fulton Hogan Permits to Work. AT Access Authority approved and signed by RCA Authority | Permit attached or permit number noted. | Site Engineer
1 | Permits & Services (2) | H | Locate and mark out all existing services | Prior to any construction commencing |  | B4u dig procedure - follow utility protocols and GPR Report | B4u dig plans & GPR report attached | Site Engineer
2 | Pre-Construction Sign Offs | H | Sub-Contract and Supplier Agreements | Prior to commencement. | Document Review | Sub-Contract and Supplier Agreements to be agreed and signed | Subcontract and Supplier Agreements | Site Engineer
3 | Design | H | Design is approved and Drawings are of the latest revision. | Prior to commencement. | Document Review | Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC. | Drawing Register. | Site Engineer | Engineers Rep.
4 | Survey Setout | H | Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design | Prior to commencement. | Survey | As per IFC Drawings and design AutoCAD file. | Survey Receipt. | Site Engineer
5 | Pipe and Manhole Material Compliance | H | Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards | Prior to commencement. | Document Review, Visual Inspection | Pipe shall be Check for freshly formed pipes and return if required 1).Class 4 RCRRJ pipes AS/NZS 4058 2). All Concrete RCRRJ pipes to be fitted with Rubber rings 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058 Prefabricated concrete Manhole shall be in accordance with TDM Standards | Manufacturers Data Sheets, Delivery Dockets | Site Engineer
6 | Locate Existing Services by Hand Digging / Hydro Vac | H | Ensure all services conflicting with the line of trench have been exposed by hand digging. | Prior to commencement. | Potholing / Survey | All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services. | As-built Drawings. Doc. Review | Site Engineer
7 | Trenching & Excavation (1) | H | Excavation methodology | Daily | Prestart review | The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016) | Prestart RCP
7 | Trenching & Excavation (2) | M | Trench Profile - Width | Daily / as trenching takes place. Different depth methodology | Visual Inspection, Excavation methodology | Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing | Construction Photos | Site Engineer
7 | Trenching & Excavation (3) | W | Trench Profile - Depth | Daily / as trenching takes place. | Visual Inspection, Measurement | Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings | FH Drainage Line Record / Construction Photos | Site Engineer
7 | Trenching & Excavation (4) | M | Trench Base | Every 10m | Scalar testing | Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2. | Test reports / Construction Photos | Site Engineer
8 | Bedding for Concrete Pipe Laying & Manhole & Cesspit | W | Placing and compaction of Bedding Material. | Inspected continuously during placing and compaction of Bedding Material. | Visual Inspection | Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725 | FH Drainage Line Record / Construction Photos | Site Engineer
9 | Pipe Position Tolerance | M |  | At any point of pipe |  | Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design. | FH Drainage Line Record, Survey Data. | Site Engineer
10 | Trench Backfill - Placing & Compacting | M | Placing and compacting of Trench Backfill Material | Throughout Trench Backfilling operation. | Visual Inspection | Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm ATAP40 for subbase/basecourse. | Construction Photos | Site Engineer
Subsoil Construction
13 | Subsoil Material Compliance (1) | H | Ensure Subsoil Drainage pipe complies with TDM RD010 | Upon delivery to site | Ensure delivery docket matches materials delivered | 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock | Delivery docket | Site Engineer
13 | Subsoil Material Compliance (2) | H | Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate |  | Visual inspection | Ensure clean drainage aggregate - F2 Sand | Delivery docket | Site Engineer
14 | Trenching (1) | H | Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade | 10m intervals | Visual inspection and measurement | Record levels of base of trench on dip sheet. | Photo / subsoil log | Site Engineer
14 | Trenching (2) | H | Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings. | 10m intervals | Visual inspection and measurement | Ensure trench line and levels match the design drawings | Photo / subsoil log | Site Engineer
15 | Bedding, pipe installation and Backfill (1) | W | Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench. | 10m intervals | Visual inspection | Record levels of top of bedding on dip sheet | Photo / subsoil log | Site Engineer
15 | Bedding, pipe installation and Backfill (2) | W | Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | 10m intervals | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer
15 | Bedding, pipe installation and Backfill (3) | W | Backfill by tipping AP20 as bedding & ATAP40 as pavement structure into the trench | - | Visual inspection | Ensure good coverage | Photos | Site Engineer
16 | Catchpit Connection (1) | W | Ensure minimum entry point 150mm above soffit of outlet stormwater pipe | As required | Visual inspection | Consistency with Subsoil Details | Photo | Site Engineer
16 | Catchpit Connection (2) | W | Perforate Catchpit and epoxy grout pipe from inside to completely seal connection. | As required | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer
17 | As-Built Drawings | W | Red pen marked-up As-Builts of every 'Issued for Construction' | Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure. | Drawings / Visual Inspection | As Built and GIS Data | Redline As-Built Drawings, scanned as .pdf files. | Site Engineer | Engineers Rep.
Comments:
[5 empty] | Signature: |  |  | Date:
QA checked By Quality Manager:
[5 empty] | Signature: |  |  | Date:
Accepted By Engineers Rep:

## Pavements
Pavement - Structural Asphalt on Concrete
Project Name: |  | Triangle Road Pavement Rehabilitation | [10 empty] | Design Report . | Triangle Road Pavement Rehabilitation
ITP Prepared By: |  | Bartley Consultants Amended by FH | [5 empty] | Date: | Revision 0 – Bartley – May 2024 Revision 1 – FH – 05/09/2024 |  |  |  | Peer Review By: | Andrew Deakin (Bartley) – initial version only |  | Date: 06/12/2023
No. | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE |  |  |  |  | FREQUENCY | ACCEPTANCE CRITERIA |  |  |  | TYPE | RECORDS (Responsibility) | ONSITE RESPONSIBILITY | CONTRACT MANAGER SIGNOFF
Excavation
1 | Identification and location of shallow services | Measure depth of cover to utility services | Trained contractor staff |  |  |  |  | Two measures per service (each side of the road) | Services sufficently deep to avoid damage. |  |  |  | Mandatory HOLD POINT Designer Signoff Required | Marked up sheet | Project Engineer | Designer Signoff
2 | Milling / Cut to Waste (325mm) | Stringline | Dip from stringline or survey as-built |  |  |  |  | 10m each lane | +0 / -20mm to design level |  |  |  | Mandatory HOLD POINT Designer Signoff Required | Stringline Sheet | Project Engineer | Designer Signoff
3 | Subgrade | No unacceptable subgrade materials after excavation | Visual Inspection |  |  |  |  | NA | Free of detritius and loose material |  |  |  | Inprocess Inspection | Site diary | Project Engineer
AP40 Layer (Widenings and where subgrade is encountered)
4 | 150mm Excavation | Stringline | Dip from string line |  |  |  |  | 10m each lane | +0 / -20mm No trafficking of the excavated subgrade |  |  |  | Mandatory HOLD POINT Designer Signoff Required | Marked up drawing | Project Engineer | Designer Signoff
5 | Class C Geotextile | N/A | NZTA F/7 |  |  |  |  | NA | Geotextile material and construction in accordance with NZTA F/7 |  |  |  | Inprocess Inspection and Contractor Records | Testing Results | Project Engineer
Only required under the concrete subbase if clay
subgrade or highly
contaminated granular material
exposed post milling
6 | ATAP40 (material) | No non-compliant results | Material test results |  |  |  |  | Once | Compliance with AT Series 800 Specification for the Supply of Aggregates |  |  |  | Contractor Records | Testing Results | Project Engineer
7 | ATAP40 (Compaction) | Density Testing | NDMs |  |  |  |  | Every 10m in each lane | N95% MDD mean compaction with no results less than 92% |  |  |  | Contractor Records | Testing Results | Project Engineer
8 | ATAP40 (Level Tolerance) | Stringline | Dip from string line |  |  |  |  | 10m each lane | +5 / -25mm No trafficking of the excavated subgrade |  |  |  | Contractor Records | Testing Results | Project Engineer
9 | ATAP40 (Surface finish) | N/A | Visual Inspection |  |  |  |  | NA | Free of detritius and loose material |  |  |  | Inprocess Inspection | Site diary | Project Engineer
Undercutting Contingency
10 | Contingency Weak / Soft Spot | Scala Pentrometer tests/proof roll | Design Report |  |  |  |  | At 10m intervals in each lane | Subgrade CBR ≥ 2 or no visible deflection greater than 3.0mm |  |  |  | Mandatory HOLD POINT Designer Signoff Required | Marked up drawing | Project Engineer | Designer Signoff
11 | 50mm Excavation | Stringline | Dip from string line |  |  |  |  | 10m each lane | +0 / -20mm No trafficking of the excavated subgrade |  |  |  | Inprocess Testing | Stringline Sheet | Project Engineer | Designer Signoff
12 | Subgrade | No unacceptable subgrade materials after excavation | Visual Inspection |  |  |  |  | NA | Free of detritius and loose material |  |  |  | Inprocess Inspection | Site diary | Project Engineer
Concrete Subbase (150mm, additional 50mm over soft spots with visible movement)
13 | Concrete Subbase | Strength and slump | Concrete dockets |  |  |  |  | each pour | Strength = 20MPa |  |  |  | Inprocess Testing | Docket | Project Engineer
Slump = 130mm pump mix
|  |  |  | 1 x Slump Test at Plant every 75m3 of | [5 empty] | Pump mix being used hence cannot specify particular
[6 empty] | production |  |  |  | lump. Shape of the concrete to be closely monitored
due to fluidity nature of pump mix on graded surface
75m3 of production
14 | Concrete Subbase | Levels / thickness | Dip from stringline or survey as-built to top of subbase (Surveyor to provide set-out information prior to concrete pour) |  |  |  |  | 10m each lane | Target Depth = 175mm below design surface -0 / +10mm |  |  |  | Mandatory HOLD POINT Designer Signoff Required | Stringline Sheet | Project Engineer | Designer Signoff
15 | Concrete Subbase | Rough trowel surface finish | Visual Inspection |  |  |  |  | NA | Rough surface verified over 100% of surface area |  |  |  | Inprocess Inspection | Production Recurs | Project Engineer
16 | Concrete Joint | Roughened / Keyed Joint | Visual Inspection |  |  |  |  | Each Subsection | Roughened or keyed joint confirmed over full depth of concrete |  |  |  | Mandatory HOLD POINT Designer Signoff Required | NTC | Project Engineer | Designer Signoff
1 x 28-day cylinder Test at Plant every s
Emulsion (Concrete and AC layer)
17 | Emulsion tack coat | CAT60 cationic emulsion or approved alternative | Visual Inspection |  |  |  |  | each lot | Hand spray tack coat emulsion |  |  |  | Inprocess Testing | Photos | Project Engineer
Structural Asphalt (AC14 in two lifts)
18 | AC14 | Check weather reports | Forecast and thermometer |  |  |  |  | Daily | No fog, rain or wet surface. Base temp ≥ 7o C |  |  |  | Inprocess Testing | AC check sheet | Project Engineer
19 | AC14 | Ensure previous layer is broomed clean | Visual |  |  |  |  | Prior to starting | Free of detritius and loose material |  |  |  | Inprocess Testing | AC check sheet | Project Engineer
20 | AC14 | Production tests | Grading, binder content, max density, temp |  |  |  |  | As per M/10 | NZTA M/10 |  |  |  | Inprocess Testing | Lab test | Project Engineer
21 | AC14 | Surface finish inspection | Visual inspection by the Engineer |  |  |  |  | Each lot | Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. |  |  |  | Inprocess Testing | Inspection sheet | Project Engineer
22 | AC14 | Density testing | NDM |  |  |  |  | Every 30m2 | Air voids (4% - 6%) |  |  |  | Inprocess Testing | Inspection sheet | Project Engineer | Auckland Transport Signoff
23 | AC14 | As-built layer | Stringline |  |  |  |  | Each lot | First layer = 60mm +/- 10mm |  |  |  | Inprocess Testing | As-build drawings & stringline measures | Project Engineer
24 | AC14 | As-built layer | Stringline |  |  |  |  | Each lot | Second layer = 60mm +/- 10mm |  |  |  | Inprocess Testing | As-build drawings & stringline measures | Project Engineer
25 | Joint Inspection | Visual | Design Report |  |  |  |  | Each Subsection |  |  |  |  | Mandatory HOLD POINT Auckland Transport Signoff Required | NTC | Project Engineer | Auckland Transport Signoff
Cores on AC14
26 | AC14 | Density testing | Cores (Random testing plan to be agreed with client) |  |  |  |  | 1/300m2 or min 4 no. | Air voids to meet NZTA M/10:2020 |  |  |  | Mandatory HOLD POINT Auckland Transport Signoff Required | RFI response | Project Engineer | Auckland Transport Signoff
27 | AC14 | Thickness | Cores depth (Random testing standard) |  |  |  |  | 1/300m2 or min 4 no. | - Target depth 120mm (no less than 120mm thickness) |  |  |  | Mandatory HOLD POINT Auckland Transport Signoff Required | Core test report | Project Engineer | Auckland Transport Signoff
Hatelit grid to be laid on concrete not in between asphalt layers
28 | Hatelit XP50 | Length direction grid overlap | Visual inspection |  |  |  |  | Ongoing during install | Min. 250mm |  |  |  | Inprocess Testing | Photo / diary note / check sheet | Project Engineer
29 | Hatelit XP50 | Cross direction grid overlap | Visual inspection |  |  |  |  | Ongoing during install | Min. 150mm |  |  |  | Inprocess Testing | Photo / diary note / check sheet | Project Engineer
30 | Hatelit XP50 | Tack coat | Visual inspection |  |  |  |  | Ongoing during install | 0.4 lt / m2 - 0.8 lt/m2, residual bitumen emulsion (depending on surface condition) |  |  |  | Inprocess Testing | Photo / diary note / check sheet | Project Engineer
31 | Hatelit XP50 | Emulsion on overlaps | Visual inspection |  |  |  |  | Ongoing during install | 0.3 lt / m2 if required |  |  |  | Inprocess Testing | Photo / diary note / check sheet | Project Engineer
32 | Hatelit XP50 | Evenly laid grid | Visual inspection |  |  |  |  | Ongoing during install | Minimal air voids in grid, grid pulled tight |  |  |  | Inprocess Testing | Photo / diary note / check sheet | Project Engineer
Asphalt Surfacing
33 | Rougness of Road | Insitu | Contract Spec 4415 |  |  |  |  | Every 100m | The new pavement shall have an average dynamic roughness, when measured over a length of 100m, of less than 60 NAASRA counts/km for any three consecutive results and no individual value greater than 70 |  |  |  | Inprocess Inspection | NAASRA count | Project Engineer
34 | Shape of road | 3m straight edge | NZTA M/10 spec |  |  |  |  | At joints and any other areas of concern | Irregularities < 5mm under straight edge |  |  |  | Inprocess Inspection | Check sheet | Project Engineer
35 | Temperature Limitations | Temperature | Contract Spec / M10 Spec |  |  |  |  | Every Site | Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 120 Degree |  |  |  | Inprocess Inspection | Asphalt QA | Project Engineer
36 | Surface Preparation | Visual | NZTA M/10 spec |  |  |  |  | Every Site | Swept clean; all necessary measures to prevent ponding prior to any surfacing |  |  |  | Inprocess Inspection | Visual | Project Engineer
37 | Asphalt Production Tests for AC14 | Production Tests | [5 empty] | As per M/10 | NZTA M/10 |  |  |  | Laboratory Testing | IANZ Lab | Project Engineer
Grading, binder content, max density,
temp
38 | Joint Placement | Paving Plan | [5 empty] | Every Site | Paving Plan to be completed for every site with dimensions. Joint sealing shall be applied between new and existing surfacing. Joints off-set 150mm |  |  |  | Inprocess Inspection | Nil | Project Engineer
39 | AC14 - Layer thickness - 55mm/60mm compacted depth | Insitu | Contract Spec / NZTA M10 Spec |  |  |  |  | Continuous | 55 mm minimum and 60 mm maximum compacted depth |  |  |  | Mandatory HOLD POINT Auckland Transport Signoff Required | Asphalt QA | Project Engineer | Auckland Transport Signoff
40 | AC14 | Density testing | NDM |  |  |  |  | Every 30m2 | NZTA M/10 |  |  |  | Mandatory HOLD POINT Auckland Transport Signoff Required | RFI response | Project Engineer | Auckland Transport Signoff
41 | Reinstatement of Linemarking and RRPM's | Visual | NZTA M7 approved (Class B or C as required for anticipated traffic level) |  |  |  |  | Every site | *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated |  |  |  | Inprocess Inspection | Linemarking Records | Project Engineer
APPROVALS
Approved by Project Engineer : |  | TBC | [5 empty] | Signature: |  |  |  |  | Date:
Approved by Contract Manager : |  | TBC | [5 empty] | Signature: |  |  |  |  | Date:
Approved by Client Rep : |  | TBC | [5 empty] | Signature: |  |  |  |  | Date: