## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Aviemore - Enabling Works - Footpath, Kerb and Channel, Pram Crossing | itp |  |  |  |  | ITP - Aviemore - Enabling Works - Footpath, Kerb and Channel, Pram Crossing
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Kerb and Channel
checkpoint | 2A - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every 10m for Scalar
label | ACCEPTANCE CRITERIA: Subgrade CBR > 5
label | HOLD POINT: In process Inspection
label | RECORDS: Scalar Sheet
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2B - Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every 10m for Clegg
label | ACCEPTANCE CRITERIA: Kerb & Channel to be laid using precast hand-laid on compacted GAP40.
label | ○ Thickness - 100mm on Footpath / 300mm on roads
label | ○ CIV > 25
label | HOLD POINT: In process Inspection
label | RECORDS: Clegg Sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2C - Kerb Setout
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Site Setout as per construction drawings and heights and falls verified
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: K&C Pre-pour Checklist
label | ONSITE RESPONSIBILITY: Site Engineer / MSQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2D - Channel Material
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days
label | ○ Trowel Finish
label | HOLD POINT: In process Inspection
label | RECORDS: Concrete Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2E - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Footpath
checkpoint | 3A - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m intervals
label | ACCEPTANCE CRITERIA: Subgrade CBR > 3
label | HOLD POINT: In process Inspection
label | RECORDS: Scalar Sheet
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3B - Concrete Footpaths
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m intervals
label | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness
label | ○ Clegg CIV > 12
label | HOLD POINT: In process Inspection
label | RECORDS: Clegg Sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3C - Footpath Setout
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m intervals
label | ACCEPTANCE CRITERIA: Site set out as per construction drawings and heights and falls verified
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Pre-pour Concrete Sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer / MSQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3D - Footpath finishing
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Concrete Strength 20 MPa @ 28 days.
label | ○ FP = 4kg/m3 black oxide with broom finish
label | ○ Cycle Lane = 8kg/m3 black oxide with broom finish
label | ○ Standard Footpath - 100mm thick
label | ○ Heavy Duty - 150mm thick
label | HOLD POINT: In process Inspection
label | RECORDS: Concrete Docket, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Service Covers and Street Furniture
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AT Contract Specification 14000
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Service covers to be adjusted to new surface levels. Ensure no damage is done to street furniture in the vicinity while carrying out works.
label | HOLD POINT: In process Inspection
label | RECORDS: Nil
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6A - Tactiles /Pram crossing
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FP006
label | ○ TDM Technical Standards - FP0010
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Tactiles set out must be agreed with MSQA
label | ○ Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | ○ Warning TGSI tiles should have 100mm concrete slab underneath
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer / MSQA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6B - Tactile Material
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impaired pedestrians
label | ○ AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type - 300x300mmx60mm
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6C - Tactile
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Edge of warning indicators to set back 300mm from the face of the kerb or lane, extend the full width of ramp and be 600mm deep.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | As-builts
checkpoint | 7 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As-Built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 8 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
note | Prepared by: Daniel Tat
note | Approving Delegate: Daeyoung Jeong
checklist | ITP - Aviemore - Traffic Island | itp |  |  |  |  | ITP - Aviemore - Traffic Island
section | Materials
checkpoint | 1 - Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 2 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: In process Inspection
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3A - In-Situ Concrete Island
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm
label | ○ CIV > 25
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3B - Stick On Concrete Island
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Bonding Agent to be applied on existing surface
label | ○ Mountable Kerbs laid flat to be sticked on to the existing road using Epoxy Mortar Mix.
label | ○ Gaps between kerbs shall be no larger that 10mm
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Infill
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 150/180mm depth of 20MPa Concrete
label | ○ Surface finish to confirm with Engineer's Rep
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet. Concrete Delivery Dockets.
label | ONSITE RESPONSIBILITY: Site Engineer
section | As-builts
checkpoint | 5 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 6 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | Prepared by:
textbox | Approving Delegate:
checklist | ITP - Aviemore - Roundabout | itp |  |  |  |  | ITP - Aviemore - Roundabout
section | Materials
checkpoint | 1 - Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 1 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Roundabout shape and heights to be set-out by the surveyor
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: In process Inspection
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2 - Roundabout Apron
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: Construction Drawings
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Chamfer shape to be handformed in-situ concrete pour with with two layers of 65 mesh with minimum 50mm cover.
label | ○ 200mm thickness with broom finish NO OXIDE
label | ○ CIV > 25
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3A - Precast Kerb & Nib
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm
label | ○ CIV > 25
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Infill
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa Concrete
label | ○ 6kg/m3 red oxide broom finish
label | ○ On minimum 150mm of GAP65
label | ○ CIV >25
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet. Concrete Delivery Dockets.
label | ONSITE RESPONSIBILITY: Site Engineer
section | As-builts
checkpoint | 5 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 6 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | Prepared by:
textbox | Approving Delegate:
checklist | ITP - Aviemore - Enabling Works - Commercial Vehicle Crossing | itp |  |  |  |  | ITP - Aviemore - Enabling Works - Commercial Vehicle Crossing
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Site set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Commercial VX
checkpoint | 2A - Commerical VX
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX0203
label | FREQUENCY: Each VX
label | ACCEPTANCE CRITERIA: Subgrade CBR > 3
label | HOLD POINT: In process Inspection
label | RECORDS: Scalar Sheet
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2B - Commerical VX
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX0203
label | ○ VX Consents as provided by Pak 'N' Save
label | FREQUENCY: 4 Cleggs per VX
label | ACCEPTANCE CRITERIA: VX to be laid using on compacted 100mm min GAP40.
label | ○ CIV > 12
label | HOLD POINT: In process Inspection
label | RECORDS: Clegg Sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2C - Commerical VX
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX0203
label | ○ VX Consents as provided by Pak 'N' Save
label | FREQUENCY: Every VX
label | ACCEPTANCE CRITERIA: Site set out as per construction drawings and heights and falls verified
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Concrete Pre-pour Checklist
label | ONSITE RESPONSIBILITY: Site Engineer / MSQA + AT Compliance Team
holdpoint | AUTHORITY HOLDPOINT
checkpoint | VX Material
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX0203
label | ○ VX Consents as provided by Pak 'N' Save
label | FREQUENCY: Every VX
label | ACCEPTANCE CRITERIA: 661 Mesh Required and R6 Stirups and 4 D-12 bars
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2D - VX Material
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX0203
label | ○ VX Consents as provided by Pak 'N' Save
label | FREQUENCY: Every VX
label | ACCEPTANCE CRITERIA: Concrete Strength 20MPa @28 Days
label | ○ Thickness - 200mm
label | ○ No black oxide with broom finish as per VX consents
label | HOLD POINT: In process Inspection
label | RECORDS: Concrete Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2E - Commerical VX
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX0203
label | ○ VX Consents as provided by Pak 'N' Save
label | FREQUENCY: Every VX
label | ACCEPTANCE CRITERIA: Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2D - Commerical VX
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - VX0203
label | ○ VX Consents as provided by Pak 'N' Save
label | FREQUENCY: Every VX
label | ACCEPTANCE CRITERIA: Saw cut expansion joints at 4m centres maximum each way in addition to saw cuts shown on dwg
label | ○ 1m reinstatement on carriageway
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Final Inspection
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: VX Consent
label | FREQUENCY: Each VX
label | ACCEPTANCE CRITERIA: Final Inspection
label | HOLD POINT: NA
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: AT Complaince Team
section | As-builts
checkpoint | 5 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As-Built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 6 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | Prepared by:
textbox | Approving Delegate:
checklist | ITP - Aviemore - Stormwater Drainage | itp |  |  |  |  | ITP - Aviemore - Stormwater Drainage
section | Stormwater Drainage
checkpoint | 1 - Permits & Services (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all permits are obtained (Deep excavation, beforeUdig, Digging permit, Confined Space)
label | FREQUENCY: Prior to any construction commencing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Relevant Fulton Hogan Permits to Work.
label | ○ AT Access Authority approved and signed by RCA Authority.
label | RECORDS: Permit attached or permit number noted.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1 - Permits & Services (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Locate and mark out all existing services
label | FREQUENCY: Prior to any construction commencing
label | CONFORMANCE CRITERIA: B4u dig procedure - follow utility protocols and GPR Report
label | RECORDS: B4u dig plans & GPR report attached
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-Construction Sign Offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Sub-Contract and Supplier Agreements
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Sub-Contract and Supplier Agreements to be agreed and signed
label | RECORDS: Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Design is approved and Drawings are of the latest revision.
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Ensure that Design is approved and Drawings are of the latest revision.
label | ○ Drawings to be 'ISSUED FOR CONSTRUCTION' status.
label | ○ HOLD POINT of not issued to IFC.
label | RECORDS: Drawing Register.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Survey Setout
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Setout Pipe Alignment and Service Locations with inlet & outlet points and inverts as required to construct to design
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey
label | CONFORMANCE CRITERIA: As per IFC Drawings and design AutoCAD file.
label | RECORDS: Survey Receipt.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Pipe and Manhole Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Cesspit, Manhole and Pipe shall comply with relevant AT/TDM/AC Standards
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review, Visual Inspection
label | CONFORMANCE CRITERIA: Pipe shall be
label | ○ Check for freshly formed pipes and return if required
label | 1).Class 4 RCRRJ pipes AS/NZS 4058
label | 2). All Concrete RCRRJ pipes to be fitted with Rubber rings
label | 3). Pipes shall have product certification (ISO Type 5) to AS/NZS 4058
label | ○ Prefabricated concrete Manhole shall be in accordance with TDM Standards
label | RECORDS: Manufacturers Data Sheets, Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging / Hydro Vac
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all services conflicting with the line of trench have been exposed by hand digging.
label | FREQUENCY: Prior to commencement.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing / Survey
label | CONFORMANCE CRITERIA: All conflicts have been located. New services and / or conflicts to be advised to Project Manager. As-built all services.
label | RECORDS: As-built Drawings. Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Excavation methodology
label | FREQUENCY: Daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Prestart review
label | CONFORMANCE CRITERIA: The excavation, benching and shoring requirements shall be in accordance with WorkSafe Excavation safety guidelines (2016)
label | RECORDS: Prestart RCP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Trenching & Excavation (2)
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Trench Profile - Width
label | FREQUENCY: Daily / as trenching takes place. Different depth methodology
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Excavation methodology
label | CONFORMANCE CRITERIA: Ensure the trench is cut in such a manner that the SW pipe will be laid true to the depths, grades and lines shown on the drawing
label | RECORDS: Construction Photos
checkpoint | 7 - Trenching & Excavation (3)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Trench Profile - Depth
label | FREQUENCY: Daily / as trenching takes place.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Measurement
label | CONFORMANCE CRITERIA: Trench depth varies according to long section and sufficient to provide a minimum of 100mm bedding below each pipe, and to the depths, grades and lines as shown on the drawings
label | RECORDS: FH Drainage Line Record / Construction Photos
checkpoint | 7 - Trenching & Excavation (4)
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Trench Base
label | FREQUENCY: Every 10m
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Scalar testing
label | CONFORMANCE CRITERIA: Trench base capacity to be tested using scala testing. Not less than 3 blows per 150mm for CBR 3.5 and 200mm for CBR 2.
label | RECORDS: Test reports / Construction Photos
checkpoint | 8 - Bedding for Concrete Pipe Laying & Manhole & Cesspit
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Placing and compaction of Bedding Material.
label | FREQUENCY: Inspected continuously during placing and compaction of Bedding Material.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Bedding & Pipe surround material to be GAP7 or GAP 20 or alternate material that complies with AS/NZS 3725
label | RECORDS: FH Drainage Line Record / Construction Photos
checkpoint | 9 - Pipe Position Tolerance
label | ACTION (Hold, Monitor, Witness): M
label | FREQUENCY: At any point of pipe
label | CONFORMANCE CRITERIA: Position tolerance for pipe laying at any point along the length of the installation shall be within ±10 mm from the specified design.
label | RECORDS: FH Drainage Line Record, Survey Data.
checkpoint | 10 - Trench Backfill - Placing & Compacting
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Placing and compacting of Trench Backfill Material
label | FREQUENCY: Throughout Trench Backfilling operation.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Backfill shall be placed in layers less than 200 mm thick. Compacted backfill material to be free of Lumps > 150mm
label | ○ ATAP40 for subbase/basecourse.
label | RECORDS: Construction Photos
section | Subsoil Construction
checkpoint | 13 - Subsoil Material Compliance (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Subsoil Drainage pipe complies with TDM RD010
label | FREQUENCY: Upon delivery to site
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Ensure delivery docket matches materials delivered
label | CONFORMANCE CRITERIA: 110mm diameter Drain flow TNZ F/2 Grade pipe - filter sock
label | RECORDS: Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Subsoil Material Compliance (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure Material for Bedding, Side support and backfill F2 filter sand drainage aggregate
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Ensure clean drainage aggregate - F2 Sand
label | RECORDS: Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Trenching (1)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Inspect trench profile and ensure it is 0.300m wide and 375mm below subgrade
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
label | CONFORMANCE CRITERIA: Record levels of base of trench on dip sheet.
label | RECORDS: Photo / subsoil log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Trenching (2)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection and measurement
label | CONFORMANCE CRITERIA: Ensure trench line and levels match the design drawings
label | RECORDS: Photo / subsoil log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Bedding, pipe installation and Backfill (1)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure 50/100mm (KC or Road) thick F2 Drainage aggregate bedding is placed in base of trench.
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Record levels of top of bedding on dip sheet
label | RECORDS: Photo / subsoil log
checkpoint | 15 - Bedding, pipe installation and Backfill (2)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | FREQUENCY: 10m intervals
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photos
checkpoint | 15 - Bedding, pipe installation and Backfill (3)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Backfill by tipping AP20 as bedding & ATAP40 as pavement structure into the trench
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Ensure good coverage
label | RECORDS: Photos
checkpoint | 16 - Catchpit Connection (1)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure minimum entry point 150mm above soffit of outlet stormwater pipe
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photo
checkpoint | 16 - Catchpit Connection (2)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Perforate Catchpit and epoxy grout pipe from inside to completely seal connection.
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Consistency with Subsoil Details
label | RECORDS: Photos
checkpoint | 17 - As-Built Drawings
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Red pen marked-up As-Builts of every 'Issued for Construction'
label | FREQUENCY: Final As-Built Drawings to be completed within three months of the construction completion of the asset or infrastructure.
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings / Visual Inspection
label | CONFORMANCE CRITERIA: As Built and GIS Data
label | RECORDS: Redline As-Built Drawings, scanned as .pdf files.
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | QA checked By Quality Manager:
textbox | Accepted By Engineers Rep:
checklist | ITP - Aviemore - Pavement - Structural Asphalt on Concrete | itp |  |  |  |  | ITP - Aviemore - Pavement - Structural Asphalt on Concrete
section | Excavation
checkpoint | 1 - Identification and location of shallow services
label | VERIFICATION ACTIVITY: Measure depth of cover to utility services
label | METHODS OR REFERENCE: Trained contractor staff
label | FREQUENCY: Two measures per service (each side of the road)
label | ACCEPTANCE CRITERIA: Services sufficently deep to avoid damage.
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Marked up sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Milling / Cut to Waste (325mm)
label | VERIFICATION ACTIVITY: Stringline
label | METHODS OR REFERENCE: Dip from stringline or survey as-built
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm to design level
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Stringline Sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Subgrade
label | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Site diary
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 4 - 150mm Excavation
label | VERIFICATION ACTIVITY: Stringline
label | METHODS OR REFERENCE: Dip from string line
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm
label | ○ No trafficking of the excavated subgrade
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Marked up drawing
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Class C Geotextile
label | VERIFICATION ACTIVITY: N/A
label | METHODS OR REFERENCE: NZTA F/7
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Geotextile material and construction in accordance with NZTA F/7
label | ○ Only required under the concrete subbase if clay subgrade or highly contaminated granular material exposed post milling
label | TYPE: Inprocess Inspection and Contractor Records
label | RECORDS (Responsibility): Testing Results
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 6 - ATAP40 (material)
label | VERIFICATION ACTIVITY: No non-compliant results
label | METHODS OR REFERENCE: Material test results
label | FREQUENCY: Once
label | ACCEPTANCE CRITERIA: Compliance with AT Series 800 Specification for the Supply of Aggregates
label | TYPE: Contractor Records
label | RECORDS (Responsibility): Testing Results
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 7 - ATAP40 (Compaction)
label | VERIFICATION ACTIVITY: Density Testing
label | METHODS OR REFERENCE: NDMs
label | FREQUENCY: Every 10m in each lane
label | ACCEPTANCE CRITERIA: N95% MDD mean compaction with no results less than 92%
label | TYPE: Contractor Records
label | RECORDS (Responsibility): Testing Results
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 8 - ATAP40 (Level Tolerance)
label | VERIFICATION ACTIVITY: Stringline
label | METHODS OR REFERENCE: Dip from string line
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +5 / -25mm
label | ○ No trafficking of the excavated subgrade
label | TYPE: Contractor Records
label | RECORDS (Responsibility): Testing Results
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 9 - ATAP40 (Surface finish)
label | VERIFICATION ACTIVITY: N/A
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Site diary
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 10 - Contingency Weak / Soft Spot
label | VERIFICATION ACTIVITY: Scala Pentrometer tests/proof roll
label | METHODS OR REFERENCE: Design Report
label | FREQUENCY: At 10m intervals in each lane
label | ACCEPTANCE CRITERIA: Subgrade CBR ≥ 2 or no visible deflection greater than 3.0mm
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Marked up drawing
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - 50mm Excavation
label | VERIFICATION ACTIVITY: Stringline
label | METHODS OR REFERENCE: Dip from string line
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm
label | ○ No trafficking of the excavated subgrade
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Stringline Sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
checkpoint | 12 - Subgrade
label | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Site diary
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 13 - Concrete Subbase
label | VERIFICATION ACTIVITY: Strength and slump
label | METHODS OR REFERENCE: Concrete dockets
label | ○ 1 x Slump Test at Plant every 75m3 of production
label | ○ 75m3 of production
label | FREQUENCY: each pour
label | ACCEPTANCE CRITERIA: Strength = 20MPa
label | ○ Slump = 130mm pump mix
label | ○ Pump mix being used hence cannot specify particular lump. Shape of the concrete to be closely monitored due to fluidity nature of pump mix on graded surface
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Docket
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 14 - Concrete Subbase
label | VERIFICATION ACTIVITY: Levels / thickness
label | METHODS OR REFERENCE: Dip from stringline or survey as-built to top of subbase (Surveyor to provide set-out information prior to concrete pour)
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: Target Depth = 175mm below design surface
label | ○ -0 / +10mm
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): Stringline Sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 - Concrete Subbase
label | VERIFICATION ACTIVITY: Rough trowel surface finish
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Rough surface verified over 100% of surface area
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Production Recurs
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 16 - Concrete Joint
label | VERIFICATION ACTIVITY: Roughened / Keyed Joint
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: Each Subsection
label | ACCEPTANCE CRITERIA: Roughened or keyed joint confirmed over full depth of concrete
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS (Responsibility): NTC
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Designer Signoff
holdpoint | AUTHORITY HOLDPOINT
section | Emulsion (Concrete and AC layer)
checkpoint | 17 - Emulsion tack coat
label | VERIFICATION ACTIVITY: CAT60 cationic emulsion or approved alternative
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: Hand spray tack coat emulsion
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Photos
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
section | Structural Asphalt (AC14 in two lifts)
checkpoint | 18 - AC14
label | VERIFICATION ACTIVITY: Check weather reports
label | METHODS OR REFERENCE: Forecast and thermometer
label | FREQUENCY: Daily
label | ACCEPTANCE CRITERIA: No fog, rain or wet surface. Base temp ≥ 7o C
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): AC check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 19 - AC14
label | VERIFICATION ACTIVITY: Ensure previous layer is broomed clean
label | METHODS OR REFERENCE: Visual
label | FREQUENCY: Prior to starting
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): AC check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 20 - AC14
label | VERIFICATION ACTIVITY: Production tests
label | METHODS OR REFERENCE: Grading, binder content, max density, temp
label | FREQUENCY: As per M/10
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Lab test
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 21 - AC14
label | VERIFICATION ACTIVITY: Surface finish inspection
label | METHODS OR REFERENCE: Visual inspection by the Engineer
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Inspection sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 22 - AC14
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: NDM
label | FREQUENCY: Every 30m2
label | ACCEPTANCE CRITERIA: Air voids (4% - 6%)
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Inspection sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
checkpoint | 23 - AC14
label | VERIFICATION ACTIVITY: As-built layer
label | METHODS OR REFERENCE: Stringline
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: First layer = 60mm +/- 10mm
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): As-build drawings & stringline measures
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 24 - AC14
label | VERIFICATION ACTIVITY: As-built layer
label | METHODS OR REFERENCE: Stringline
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Second layer = 60mm +/- 10mm
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): As-build drawings & stringline measures
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 25 - Joint Inspection
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: Design Report
label | FREQUENCY: Each Subsection
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): NTC
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
section | Cores on AC14
checkpoint | 26 - AC14
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: Cores (Random testing plan to be agreed with client)
label | FREQUENCY: 1/300m2 or min 4 no.
label | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): RFI response
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 27 - AC14
label | VERIFICATION ACTIVITY: Thickness
label | METHODS OR REFERENCE: Cores depth (Random testing standard)
label | FREQUENCY: 1/300m2 or min 4 no.
label | ACCEPTANCE CRITERIA: - Target depth 120mm (no less than 120mm thickness)
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): Core test report
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
section | Hatelit grid to be laid on concrete not in between asphalt layers
checkpoint | 28 - Hatelit XP50
label | VERIFICATION ACTIVITY: Length direction grid overlap
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Ongoing during install
label | ACCEPTANCE CRITERIA: Min. 250mm
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Photo / diary note / check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 29 - Hatelit XP50
label | VERIFICATION ACTIVITY: Cross direction grid overlap
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Ongoing during install
label | ACCEPTANCE CRITERIA: Min. 150mm
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Photo / diary note / check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 30 - Hatelit XP50
label | VERIFICATION ACTIVITY: Tack coat
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Ongoing during install
label | ACCEPTANCE CRITERIA: 0.4 lt / m2 - 0.8 lt/m2, residual bitumen emulsion (depending on surface condition)
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Photo / diary note / check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 31 - Hatelit XP50
label | VERIFICATION ACTIVITY: Emulsion on overlaps
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Ongoing during install
label | ACCEPTANCE CRITERIA: 0.3 lt / m2 if required
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Photo / diary note / check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 32 - Hatelit XP50
label | VERIFICATION ACTIVITY: Evenly laid grid
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Ongoing during install
label | ACCEPTANCE CRITERIA: Minimal air voids in grid, grid pulled tight
label | TYPE: Inprocess Testing
label | RECORDS (Responsibility): Photo / diary note / check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
section | Asphalt Surfacing
checkpoint | 33 - Rougness of Road
label | VERIFICATION ACTIVITY: Insitu
label | METHODS OR REFERENCE: Contract Spec 4415
label | FREQUENCY: Every 100m
label | ACCEPTANCE CRITERIA: The new pavement shall have an average dynamic roughness, when measured over a length of 100m, of less than 60 NAASRA counts/km for any three consecutive results and no individual value greater than 70
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): NAASRA count
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 34 - Shape of road
label | VERIFICATION ACTIVITY: 3m straight edge
label | METHODS OR REFERENCE: NZTA M/10 spec
label | FREQUENCY: At joints and any other areas of concern
label | ACCEPTANCE CRITERIA: Irregularities < 5mm under straight edge
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 35 - Temperature Limitations
label | VERIFICATION ACTIVITY: Temperature
label | METHODS OR REFERENCE: Contract Spec / M10 Spec
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 120 Degree
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Asphalt QA
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 36 - Surface Preparation
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA M/10 spec
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Swept clean; all necessary measures to prevent ponding prior to any surfacing
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Visual
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 37 - Asphalt Production Tests for AC14
label | VERIFICATION ACTIVITY: Production Tests
label | METHODS OR REFERENCE: Grading, binder content, max density, temp
label | FREQUENCY: As per M/10
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Laboratory Testing
label | RECORDS (Responsibility): IANZ Lab
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 38 - Joint Placement
label | VERIFICATION ACTIVITY: Paving Plan
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Paving Plan to be completed for every site with dimensions. Joint sealing shall be applied between new and existing surfacing. Joints off-set 150mm
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Nil
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
checkpoint | 39 - AC14 - Layer thickness - 55mm/60mm compacted depth
label | VERIFICATION ACTIVITY: Insitu
label | METHODS OR REFERENCE: Contract Spec / NZTA M10 Spec
label | FREQUENCY: Continuous
label | ACCEPTANCE CRITERIA: 55 mm minimum and 60 mm maximum compacted depth
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): Asphalt QA
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 40 - AC14
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: NDM
label | FREQUENCY: Every 30m2
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS (Responsibility): RFI response
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF: Auckland Transport Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 41 - Reinstatement of Linemarking and RRPM's
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA M7 approved (Class B or C as required for anticipated traffic level)
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Carried out within 12 hours of each shift completed and as per the existing markings
label | ○ Suitable Traffic Control to remain in place until pavement markings have been reinstated
label | TYPE: Inprocess Inspection
label | RECORDS (Responsibility): Linemarking Records
label | ONSITE RESPONSIBILITY: Project Engineer
label | CONTRACT MANAGER SIGNOFF:
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | Approved by Project Engineer:
textbox | Approved by Contract Manager:
textbox | Approved by Client Rep: